## ELEC 2017-2024
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2
ELECTRIFICATION 2017 | CAR | Abra | 135027 | Benben PS | LA PAZ | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 456305.94 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135076 | Pacoc ES | LACUB | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 892219 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135214 | Lukgay PS | LAGAYAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 198244.95 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135117 | Tukipa PS | LUBA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 405290.61 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 134996 | Liagan PS | MANABO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219559.98 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 218519 | Tattawa PS | PEÑARRUBIA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 254540.88 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135186 | Lam-aoan PS | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1028689.05 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135191 | Nangas-Asan PS | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 465967.53 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135195 | Ud-udiao ES | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 599527.41 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 329073.96 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135196 | Alawa ES | TINEG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 364334.71 |  | COMPLETED | 100% | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Benguet | 219529 | Cadsi-Amoy ES - Poway Annex | BAKUN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174192.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135750 | Haitan PS | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286085.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135759 | Nepojnoc PS | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 234895.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135761 | Talite Primary School | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 434246.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135766 | Busilac ES | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 802683.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135773 | Laya ES | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835389.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 220011 | Maligaya PS | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 401332.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 319006 | Banaue NHS Extension | BANAUE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 537965.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135838 | Kayang PS | HINGYON | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 311555.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 925056.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 940908.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135937 | Nattum PS (Proper) | MAYOYAO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245847.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135965 | Bassao PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231941.93 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135966 | Bayowong PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 680800.49 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135968 | Bonong Community School | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 351309.51 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135969 | Buaya ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 483534.77 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135970 | Bullalayao PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92771.34 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135975 | Kabugao ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 480823.46 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135977 | Mabaca ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 445017.81 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135985 | Tawang ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 600152.85 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135986 | Ubual PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477185.26 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135988 | Colong PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92038.13 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135990 | Dugnac PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 145589.59 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135991 | Latawan PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 60030.07 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136020 | Cagaluan ES Annex (Da-o PS) | PASIL | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 90008.33 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136021 | Cagaluan ES Annex (Putao PS) | PASIL | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 75019.41 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220527 | Aguimitan PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 112190.04 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220511 | Baclas PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 145546.34 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136036 | Ballayangon ES | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 115317.67 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136037 | Bonnong PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 680998.83 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220516 | Coddog PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110076.5 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136051 | Liplipoken PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 140168.49 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136060 | Sagsag PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 393590.64 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136116 | Baclayam ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 165143.57 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136121 | Darulog ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 146393.25 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136125 | Liyang ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 90084.87 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220509 | Magtoma PS | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110504.51 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136128 | Pangol ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 144802.45 |  | COMPLETED | 100% | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136272 | Nabhar PS | NATONIN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 518252.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136274 | Pangtor PS | NATONIN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 420817.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136281 | Addang ES | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 431600.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 319226 | Bacarri National Trade Agricultural High School-Bunot Extension | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 403508.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136286 | Bagabag Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 389551.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136291 | Camparadi Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 471192.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136294 | Catao Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 320237.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 221002 | Catubangan PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 267892.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 221009 | Damsite PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 153581.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136299 | Gassilang PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1574032.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136301 | Kalao PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 572634.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136305 | Makilo Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 494337.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136306 | Marallag Primary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 267148.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136308 | Natta'Longan PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 409013.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 409013.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 319223 | Lubon NHS - Mabalite Extension | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 280934 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136378 | Vicente Pe ES | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 260832.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Norte | 211503 | Cabayugan ES | BUENAVISTA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Norte | 131415 | A.P. Quiamjot ES | CARMEN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220633.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131710 | Makalindang PS | ESPERANZA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 264557.49 | 168059.72 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131897 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131777 | La Fortuna Eementary School | PROSPERIDAD (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 400034.38 | 263642.28 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131710 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212051 | Jose T. Cuyos, Sr. I PS | ROSARIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 163465.08 | 162809.72 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 212051 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131943 | Datu Bandahan ES | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 211004.38 | 236243.74 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131854 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212074 | DOP BINATUNAN IP SCHOOL (IPA) | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 332058.21 | 457504.63 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 212032 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131954 | Mahagsay ES | SAN LUIS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 366700.99 | 652599.78 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131864 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212026 | Balonbon Elementary School | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 395070.28 | 365367.45 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131954 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131864 | Banag-banag ES | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 653936.23 | 223062.4 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131758 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131874 | Magkalape ES | SIBAGAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 354088.04 | 353050.87 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131874 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131988 | New Davao ES | TALACOGON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 209911.75 | 250997.12 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131901 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212060 | San Roque PS | TALACOGON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 200138.25 | 487312.68 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 212029 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131662 | Sta. Monica ES | BUNAWAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 522735.74 | 353050.87 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131874 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131748 | Angeles PS | LA PAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 210638.25 | 162809.72 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 212051 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131758 | Log Pond 3 PS | LA PAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 223243.06 | 521986.02 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131662 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131854 | Manangahon ES | SAN FRANCISCO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 236554.34 | 210405.87 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131748 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212032 | Dao Elementary School | SANTA JOSEFA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 459079.18 | 456711.45 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 132014 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212057 | DATU MADAGNAS PS | SANTA JOSEFA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 263830.99 | 393689.97 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 212026 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 132014 | San Marcos ES | TRENTO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 458082.2 | 209813.14 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131943 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 212029 | Singapore Elementary School | TRENTO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 488330.22 | 208220.63 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131988 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131897 | Basilica PS | VERUELA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168715.08 | 168059.72 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131897 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | MRS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Agusan del Sur | 131901 | Candiis ES | VERUELA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 251685.26 | 398862.85 | COMPLETED | 100% | 2018-03-09 |  | BEFF 2017 | 131777 | 2017-12-11 | 2017-12-11 | 12/27/2017 | 12/29/2017 | 2018-02-02 | DATREBIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Bayugan City | 212012 | Datu Hugmakan ES | CITY OF BAYUGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 406181.81 | 404000 | COMPLETED | 100% | April 23, 2018 |  |  | 2018-002 | November 24, 2017 |  | December 1, 2017 | December 18, 2017 | January 15, 2018 | Vinnex Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Bayugan City | 131642 | Sto Nino ES | CITY OF BAYUGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373719.04 | 370000 | COMPLETED | 100% | April 23, 2018 |  |  | 2018-001 | November 24, 2017 |  | December 1, 2017 | December 18, 2017 | January 15, 2018 | Vinnex Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Bislig City | 322507 | Danipas NHS Labisma Annex | CITY OF BISLIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 100690.38 | 100368.97 | COMPLETED | 100% | 2018-04-10 | 2018-04-10 | 2017BEFF-Electrification | 2017BEFF-Electrification | 2017-11-17 | 2017-11-29 | 2017-12-11 | 2017-12-18 | 2018-01-03 | RMF Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Bislig City | 235003 | New Bongga PS | CITY OF BISLIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170998.68 | 170467.83 | COMPLETED | 100% | 2018-04-10 | 2018-04-10 | 2017BEFF-Electrification | 2017BEFF-Electrification | 2017-11-17 | 2017-11-29 | 2017-12-11 | 2017-12-18 | 2018-01-03 | RMF Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Butuan City | 132095 | Mabuhay ES | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 | 287803.06 | COMPLETED | 100% | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Butuan City | 132078 | Masago PS | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294804.52 | 287803.06 | COMPLETED | 100% | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Butuan City | 212504 | Tud-ol ES | BUTUAN CITY (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220633.82 | 215393.88 | COMPLETED | 100% | April 16, 2018 | April 5, 2018 | 015 S’2017 | 015 S’2017 | Oct. 20, 2017 | Nov. 24, 2017 | Dec.08, 2017 | 2017-12-18 | 2018-01-17 | ADSE ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Cabadbaran City | 281003 | Dagnasay ES | CABADBARAN CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 177560.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Cabadbaran City | 131523 | Lusong ES | CITY OF CABADBARAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 177560.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132273 | Alang-alang ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220203.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132274 | Alegria ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 405084.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477182.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132277 | Bay-bay ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 180524.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132278 | Bilabid PS | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92522.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132279 | Buenavista ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 406380.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132280 | Catadman ES | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 108642.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao City | 132285 | Tomas Florya Eder Memorial Elementary School | SURIGAO CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 270646.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CARAGA | Surigao del Norte | 132438 | Meliton Morales PS | MAINIT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 222400 | 221000 | COMPLETED | 100% | 2018-02-19 | 2018-02-19 |  | 010-2018 | 2017-12-10 | N/A | N/A | 2017-12-13 | 2018-01-05 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102132 | Bila ES | SISON | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 201940.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102024 | Calunetan ES | SISON | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 287690.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | NOT.IN.BEIS | Bangar ES | San Nicolas | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190649.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101971 | Cristobal Rodrigo ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 125121.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101992 | Pastoran ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169595.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 101993 | Puyao ES | SAN NICOLAS | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174550.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region I | Pangasinan II, Binalonan | 102099 | Casilan ES | UMINGAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 113224.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Cagayan | 102460 | Bulala Sur ES | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 551885.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Cagayan | 102472 | Plaza PS | APARRI | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 474509.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Cagayan | 102565 | Mala Este PS | BUGUEY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 360773.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Isabela | 103759 | Malaya ES (Maldam ES) | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219362.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Isabela | 103763 | Panninan ES | SAN MARIANO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 129288.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1076701.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156020 | Pelaway ES Annex | ALFONSO CASTAÑEDA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 412734.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1154735.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156019 | Pogonsino Annex Primary School | BAGABAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 660613.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 103990 | Kakilingan ES | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1201001.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104000 | Villa Adriano PS | BAYOMBONG (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 785827.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104102 | Pudi PS | KASIBU | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 784569.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104122 | Dayap PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 975474 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104131 | Macdu ES | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1527697.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104137 | Oliweg E/S | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1419459.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 156001 | Tidang Village PS | KAYAPA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 473808.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Nueva Vizcaya | 104197 | Cauco ES | SANTA FE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1260159.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Quirino | 156513 | Diodol PS Annex | AGLIPAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 199320.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Quirino | 104311 | Pamungyen PS | DIFFUN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 181750.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region II | Quirino | 104359 | Macabo ES | NAGTIPUNAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286571.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region III | Mabalacat City | 159536 | Mamatitang PS | MABALACAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 204313.15 | 201719.65 | COMPLETED | 100% |  | january 10, 2018 | [6 empty] | 2017-12-27 | ANGEL GABRIEL BUILDERS AND REALTY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Laguna | 164505 | Tubog ES | PAETE | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 80008.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108549 | San Isidro Ilaya ES | BUENAVISTA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 139411.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109092 | Inanuran ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 515315.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109097 | Tala ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 834971.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109099 | Tamnao ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 556061.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109120 | Cawayan II ES | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228870.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109121 | Cumbahan ES | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294194.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 308044 | Huyon-Uyon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195687.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109138 | Bangkuro ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 241645.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109146 | Nangka ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 152536.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109147 | Pinagsama ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243594.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108580 | Mambaling ES | CALAUAG | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 331718.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108802 | Cawayanin ES | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213636.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 308042 | Cogorin Ibaba NHS - Jongo Ext. | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160892.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231264.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 301387 | Ilayang Ilog-A NHS (Formerly San Francisco B NHS Ilayang Ilog A Ext.) | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213066.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108819 | Sta. Catalina ES | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 187812.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108830 | VIllaminda Elementary School | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 143866.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109218 | Sabang ES | TAGKAWAYAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 252026.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109226 | Sto. Niño ES | TAGKAWAYAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 155957.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High school | CITY OF CALAPAN (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 402289.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Marinduque | 169005 | Sinambahan PS | TORRIJOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 205929.74 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110086 | Layaban Min. Sch. | CALINTAAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 292608.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110166 | Karyandangan Min. School | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 264530.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110175 | Pola Min. Sch. | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 259843.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110191 | Tuguilan Min. Sch. | MAMBURAO (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373145.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Occidental Mindoro | 110316 | Yawi-Yawi II PS | SAN JOSE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 361588.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110544 | MALINAO ELEMENTARY SCHOOL | NAUJAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 222965.53 | 222644.72 | COMPLETED | 100% | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301627 | DOMINGO YU CHU NATIONAL HIGH SCHOOL | POLA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1259439.16 | 1249794.2 | COMPLETED | 100% | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301634 | LEUTEBORO NATIONAL HIGH SCHOOL | SOCORRO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 645323.62 | 641648.42 | COMPLETED | 100% | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110370 | BAGONG BAYAN CENTRAL SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 546247.31 | 545009.9 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110392 | CAMANTIGUE ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 444682.51 | 444418.36 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110391 | CASTOR F. SOLABO ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 507738.64 | 507738.64 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110382 | MORENTE ELEMENTARY SCHOOL | BONGABONG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 460639.07 | 460639.07 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110435 | BANUS ELEMENTARY SCHOOL | GLORIA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 480732.42 | 480183.75 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 309002 | PRESIDENT DIOSDADO MACAPAGAL MNHS | GLORIA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 723876.34 | 720010.25 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110478 | STA. MARIA ELEMENTARY SCHOOL | MANSALAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 331845.6616 | 331845.66 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110573 | INCLANAY ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 401469.4 | 400885.55 | COMPLETED | 100% | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110559 | LUMAMBAYAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 410423.58 | 410229.59 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301646 | PAMBISAN NATIONAL HIGH SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 874426.51 | 868065.61 | COMPLETED | 100% | May 31, 2018 | May 28, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 062-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110562 | PAPANDAYAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 699122.06 | 696696.05 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110564 | QUINABIGAN ELEMENTARY SCHOOL | PINAMALAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 498665.2 | 497890.51 | COMPLETED | 100% | May 31, 2018 | May 30, 2018 | CY2017BEFF-Electrification Project Batch2-001 | 063-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | February 1, 2018 | ETVR TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110631 | HAPPY VALLEY ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 387643.91 | 387643.91 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110633 | LIBTONG ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 372026.15 | 372026.15 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 301639 | MARCELO I. CABRERA VOCATIONAL HIGH SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 866786.68 | 866786.68 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110645 | SAN RAFAEL ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 456224.49 | 456224.49 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Oriental Mindoro | 110649 | UYAO ELEMENTARY SCHOOL | ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 391381.72 | 391381.72 | COMPLETED | 100% | May 28, 2018 | June 10, 2018 | CY2017BEFF-Electrification Project Batch2-002 | 064-2018 | 2017-12-01 | 2017-12-01 | December 21, 2017 | December 27, 2017 | January 29, 2018 | 811 TRADING & CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170533 | Calawit PS | BUSUANGA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 744618.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110965 | Calusa ES | CAGAYANCILLO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 348234.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 342234.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110920 | Abud-Abod ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 415435.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110930 | Cabulihan ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 363584.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110933 | Canimango ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 395639.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110942 | Halsey ES | CULION | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 476354.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301667 | Barotuan NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1680000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301693 | El Nido NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1780000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111025 | Lamoro ES | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 279614.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301713 | New Ibajay NHS | EL NIDO (BACUIT) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1420000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility, No utility can provide in this area only Solar Power is the source of Energy in this Area. | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111136 | Andres Soriano MES | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 910000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301705 | Magara School for Philippine Crafstmen | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1750000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231510.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170512 | Ramon Gacayan Elementary School | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 230019.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301731 | ROXAS NATIONAL COMPREHENSIVE HIGH SCHOOL | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1800000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301732 | San Jose (Roxas) NHS | ROXAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1640000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Coop suggest Platform for 100 kVA | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1520000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301723 | Port Barton NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1430000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1760000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301658 | Abongan NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1490000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301669 | Bato NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1520000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 309103 | Central Taytay NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1500000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan |  | Central Taytay Senior HS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1490000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, X'former Not Installed | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301703 | Liminangcong NHS | TAYTAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1500000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301659 | Aborlan NHS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301701 | Isaub National High school | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1674473.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Not finished rewiring of Classroom | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170556 | Tina PS | ABORLAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 502744.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301668 | Bataraza NHS | BATARAZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2628689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301730 | Rio Tuba NHS | BATARAZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Not yet finished installed of distribution line | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301671 | Brooke's Point NHS - Pangobilian NHS | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301699 | GOV. ALFREDO ABUEG SR. NATIONAL TECHNOLOGY & VOCATIONAL MEMORIAL HIGH SCHOOL | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Adjustment of Pole due to New Construction | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301704 | Maasin NHS (Bernas NHS) | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110884 | Mate ES | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168715.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 110892 | Saraza ES | BROOKE'S POINT | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 196968.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301663 | Aramaywan NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1418751.1081 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Relocation of Pole due to Road Widening | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301690 | Dumaguena NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2000000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301710 | NARRA NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Relocation of Steel Pole due to New Construction | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301718 | Panacan NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1666214.844 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301724 | Princess Urduja NHS | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301739 | Sandoval National High School | NARRA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2828689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111107 | Magara ES | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 194424.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 111118 | Pinaglabanan ES | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 427669.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301726 | Quezon NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 3000000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301728 | Quezon-Panitian NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1418750.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301743 | Tagusao NHS | QUEZON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 438813.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301702 | J. P. Rizal NHS | RIZAL (MARCOS) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2628689.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, Rewiring of some Classroom | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 170567 | Rancho II PS | RIZAL (MARCOS) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 595235.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301657 | Abo-Abo NHS | SOFRONIO ESPAÑOLA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1821855.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2722839.896 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Tapping Connection from Utility (Paleco - Coop), Application Process, | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1560756.5353 | 1554389.1 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301779 | Bacungan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1373645.9305 | 1366136.85 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111474 | Bagong Bayan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 377032.32 | 369942.77 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301780 | Bahile NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1224743.0953 | 1219441.76 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111475 | Bualbualan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 386899.49 | 379825.91 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1084304.2345 | 1075130.11 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301784 | Langogan National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1284745.8793 | 1276994.46 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301788 | Luzviminda NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 488070.24 | 487128.72 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 171505 | Mabuhay PS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 295333.32 | 291228.44 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301785 | Macarascas NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1345563.3193 | 1339176.5 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301789 | Mangingisda NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1193587.5625 | 1186017.07 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301792 | Marcelino Abadiano Javarez National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1526126.741 | 1518143.21 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111490 | Napsan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 457672.08 | 445810.72 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301786 | Napsan National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1036069.4938 | 1028557.39 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. HS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1344217.7065 | 1337629.01 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301793 | San Jose NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1402395.6173 | 1395073.25 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301794 | San Miguel National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1194273.3466 | 1400532.14 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301795 | San Rafael National High School | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1545008.2744 | 1193294.52 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301796 | Sicsican NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1291533.4441 | 1515931.36 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111493 | Simpokan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 458845.5 | 446705.74 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 301790 | Sta. Lourdes NHS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1272309.3197 | 1264470.49 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City |  | Sta. Monica HS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1287640.1449 | 1284918.68 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 111496 | Sto. Niño ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 577862.51 | 563544.73 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City | 171503 | Tagbarungis ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 779958.37 | 761800.67 | COMPLETED | 100% | Jun. 25, 2018 |  | 2017 - E01 | 001-2017 | Nov. 2, 2017 | Nov. 6, 2017 | Nov. 20, 2017 | Dec. 8, 2017 | Dec. 19, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-B | Puerto Princesa City |  | Tagburos Annex | PUERTO PRINCESA CITY (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 1425145.3202 | 1280095.95 | COMPLETED | 100% | Jul. 4, 2018 |  | 2017 - E02 | 002-2017 | Nov. 7, 2017 | Nov. 13, 2017 | Nov. 27, 2017 | Dec. 28, 2017 | Dec. 29, 2017 | CARINA ELECTRICAL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga City | 199005 | Latap ES-Lacumba Annex | ZAMBOANGA CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 740248.18 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga City | 126144 | Mt. View ES | ZAMBOANGA CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 515884.75 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124549 | Bagong Silang PS | PIÑAN (NEW PIÑAN) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303720 | Rizal NHS | RIZAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124643 | Don Eleno Razo ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124661 | Macalibre ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124663 | Nazareth ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124652 | Situbo ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303737 | Sibutad NHS | SIBUTAD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124323 | Bitoon ES | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124331 | Lumaping ES | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220880.44 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 315641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124365 | Danao PS | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303727 | Seres NHS | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 315641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124517 | Serongan ES | MANUKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124481 | Mateo Denoyo ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124489 | Sibatog ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124490 | Sibod ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124674 | Balok ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124681 | Dumuyog ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124684 | Guibo ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124686 | Gunyan ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 321141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303730 | Siayan NHS | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 321141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124703 | Suminogod ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124769 | Dagum ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124793 | Datagan ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOO | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303739 | Sindangan NHS | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320141.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124807 | Tinaplan ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303675 | Bacungan NHS Annex - Tinuyop | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 322641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124430 | Cilago ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263892.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195525 | San Isidro ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 328641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195510 | Malinao PS | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124270 | Nonoyan ES | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303684 | Godod NHS | GODOD | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 325641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 328641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195501 | Matunoy ES | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124320 | Tipan ES | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 261310.12 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 327641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124354 | Palalihan ES | KALAWIT | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314120 | Balas NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 325641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303707 | COMPRA NHS | LILOY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303706 | Liloy NHS | LILOY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 324641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 324641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303721 | Salug National High School | SALUG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 322641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124714 | Dumintag ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124715 | Guimba Parang ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195532 | Litawan ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303708 | Malayal NHS | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 340641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124732 | Puliran ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303734 | Sibuco NHS | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 340641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303735 | Sibuco NHS Annex - Lunday | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124735 | Sto. Niño ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124816 | Cuyan ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195533 | Jolito Camatura ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124826 | Matiag ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195517 | Paduan ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124834 | Bitugan ES | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303743 | Dacon NHS (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 335641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 333641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124845 | Tapanayan ES | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 100% |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 124942 | Grap ES | DIMATALING | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 226606.17 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 124982 | Songayan ES | DINAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 200398.72 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 125359 | Mabang Intermediate School | SAN PABLO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160500.21 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125536 | Tantawan PS | ALICIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 385756.45 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125552 | Ligaya PS | BUUG | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 239668.95 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125597 | Israel PS | IMELDA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160729.35 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125604 | Mali Little Baguio PS | IMELDA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336448.94 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125682 | Tandu-Comot ES | MABUHAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 239258.89 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125699 | Malongon ES | MALANGAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 249361.67 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125708 | Tigabon PS | MALANGAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 445775.63 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125770 | Mayabo PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160075.71 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125771 | Minundas PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 455738.57 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125780 | Talaptap PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 272143.76 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125620 | Labe Primary School | IPIL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 313968.32 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125643 | Goodyear PS | KABASALAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 272383.69 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125653 | Salupan PS | KABASALAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 162327.35 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 196526 | Gutayan PS | ROSELLER LIM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160290.83 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125799 | San Ernesto ES | ROSELLER LIM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160531.61 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125811 | Bagong Silang ES | SIAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 314449.84 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 196517 | Teras Elementary School | TUNGAWAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 486239.05 |  | COMPLETED | 100% | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Albay | 112031 | Hamorawon ES | RAPU-RAPU | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1232937.25 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region V | Albay | 112042 | Nstr. Sra De Guadalupe ES | RAPU-RAPU | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336798.67 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112576 | Cabasag Comm. Sch | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 519535.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173504 | Salvacion ES | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 580689.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112585 | San Pablo Comm Sch | DEL GALLEGO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 528799.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173514 | Agawan (Sitio of Tabog) | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 159624.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112532 | Canatuan PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 440198.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112543 | Hanoy PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 446985.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112573 | Terogo PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 697001.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112574 | Toboan PS | CARAMOAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 583800.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 112643 | Mangogon ES | LAGONOY | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 801783.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Camarines Sur | 173555 | San Andres ES | SIRUMA | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 586539.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113588 | Pasig ES | CLAVERIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 879014.24 | 871113.92 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-015 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113593 | San Ramon ES | CLAVERIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 842231.87 | 834308.05 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-016 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113864 | Cabug ES | SAN FERNANDO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 507440.05 | 497291.25 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113908 | Boca Chica ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 693094.89 | 669727.65 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174522 | Gregorio T. Vilar Elementary School | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 436891.64 | 436011.01 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113917 | Halabangbaybay ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 625621.18 | 617321.82 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113920 | Laurente ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 716445.44 | 709572.52 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-014 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113921 | Lukban ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 384943.122 | 377244.26 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113923 | Mabuhay ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 732908.54 | 724986.88 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-016 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113931 | Ramona ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220922.35 | 213563.9 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113906 | San Rafael ES (Alimango ES) | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 744754.94 | 736798.25 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-015 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174523 | Segundina L. Rivera Primary School | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 422920.72 | 410233.1 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-006 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113937 | Sulficio Elliot ES | SAN PASCUAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110554.08 | 107428.81 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-005 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 562749.64 | 496360.28 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174517 | Isidoro F. Calimotan, Sr. ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 571423.4 | 569904.26 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113387 | Manamoc ES | AROROY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 515477.22 | 507164.93 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113436 | Madancalan PS | BALENO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 298127.43 | 258590.57 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113451 | Danao ES | BALUD | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 716664.73 | 644272.05 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113452 | Guinbanuahan ES | BALUD | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 986746.48 | 875664.78 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113644 | Centro E/S | MANDAON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 285395.97 | 273044.21 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 201-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113648 | Guincaiptan ES | MANDAON | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 373294.56 | 330363.49 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 201-02-011 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113720 | Bonbon ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469697.85 | 405805.55 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-010 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Ascentia Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113726 | Matanglad ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 284297.83 | 282591.43 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113731 | Pamangpangon ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 304461.49 | 301413.06 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 727933.44 | 720055.57 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-012 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Aaron Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113746 | Mabuhay ES | MOBO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 489767.12 | 482908.48 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Red Diamond Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 174506 | Agoho Elementary School | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 679668.44 | 677729.17 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113555 | Pin-as ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 436779.92 | 436756.66 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113563 | Talisay ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 929820.19 | 921218.74 | COMPLETED | 100% |  |  | INFRA 2017-12-017 | 2018-02-013 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113566 | Vienteriales ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 361926.77 | 361894.39 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113567 | Villaganas Village ES | CAWAYAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 483029.3 | 481716.24 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113607 | Divisoria ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 534411.47 | 532831.07 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113614 | Rizal ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 545468.67 | 541541.5 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323164.42 | 323084.91 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113625 | Libertad PS | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 227024.48 | 226010.32 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-008 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113630 | Rizal PS | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195333.11 | 195130.72 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-007 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Zarepath Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113632 | Santiago ES | ESPERANZA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 439980.67 | 437340.4 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-04-10 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region V | Masbate | 113837 | Tubod ES | PLACER | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469965.55 | 467113.81 | COMPLETED | 100% |  |  | INFRA 2017-10-014 | 2018-02-009 | 2017-10-31 | 2017-11-08 | 2017-11-20 | 2018-02-15 | 2018-02-26 | Sansa Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114728 | Yawan PS | IBAJAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 218247.73 | 217775.5 | COMPLETED | 100% |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114799 | Sibalew PS | LIBACAO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 217807.91 | 217497.55 | COMPLETED | 100% |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114808 | Catabana PS | MADALAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 139502.69 | 138000 | COMPLETED | 100% |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114824 | Panipiason PS | MADALAG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 155252.69 | 155000 | COMPLETED | 100% |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Aklan | 114931 | Lanipga-Napatag PS | TANGALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220151.62 | 219144 | COMPLETED | 100% |  |  |  |  | 2017-11-06 | 2017-11-13 | 2017-11-27 | 2017-12-01 | 2017-12-18 | Solid Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115029 | Batbatan ES | CULASI | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 100% | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115067 | Cantulan ES | HAMTIC | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 100% | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 178503 | Cacao PS | SAN REMIGIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232720.9 | 231627.1 | COMPLETED | 100% | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115241 | Carmelo I PS | SAN REMIGIO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174755.62 | 174652.76 | COMPLETED | 100% | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | for termination (far flung/contractor issue) | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178560.06 | 177709.16 | COMPLETED | 100% | 2018-04-15 |  | R6-D2-2017BEFF-01A-E | R6-D2-ELECTRIFICATION OF SCHOOLS ON-GRID-2017BEFF-112 |  |  | December 14, 2017 | December 15, 2017 | January 3, 2018 | Hadden Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Cadiz City | 117569 | Aluyan ES | CADIZ CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1101216.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Capiz | 115626 | Eugenio Regalado PS | PANAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 185817.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123326.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116731 | IGDAGMAY ELEMENTARY SCHOOL | SAN JOAQUIN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 278988.16 | 360162.5 | COMPLETED | 100% | #REF! | [5 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 180044 | Jawod ES | SAN JOAQUIN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 208479 | 196344.52 | COMPLETED | 100% | #REF! | [5 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116408 | Cunsad PS | JANIUAY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 366003.6 | 302542.73 | COMPLETED | 100% | #REF! | [5 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 180017 | Bayuco PS | LAMBUNAO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 161809.47 | 156251.44 | COMPLETED | 100% | #REF! | [5 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Iloilo | 116675 | Amayong PS | SAN DIONISIO | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 108102.06 | 103081.11 | COMPLETED | 100% | #REF! | [5 empty] | December 1, 2017 | December 13, 2017 | January 12, 2018 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117831 | Ballo ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 327426.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117878 | Camandaan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 103109.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 185501 | Cara-an ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 575339.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117883 | Ilan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 375014.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 185502 | Mambaog PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 258222.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117888 | Mamig Elementary School | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233902.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117866 | Piliopiliohan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 377135.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117891 | Sagumayon PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 77360.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Kabankalan City | 117868 | Sampac PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 201772.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180505 | Tugas ES | CITY OF HIMAMAYLAN | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1116889.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117202 | Canlupa PS | ISABELA | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263400 | 265174.3 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117258 | Binata-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 536631.35 | 698921.58 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117262 | E. Basa PS | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 699806.92 | 535718.22 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116971 | Macapula ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 629037.28 | 628377.12 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 669838 | 667903.43 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116977 | Payong PS | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 758672.56 | 757285.55 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116979 | Sibucao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 896856.69 | 896003.99 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 116983 | Talimagao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349163.74 | 348928.02 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117014 | Taya-o ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 549601.5 | 548807.25 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180518 | Aguinaldo Primary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 723035.78 | 922663.56 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 923210.17 | 722527.62 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117145 | Cabanbanan PS | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835486.41 | 834624.64 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117146 | Cemeco ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 970538.94 | 969541.76 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 180508 | MAATOP ELEMENTARY SCHOOL | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 958158.87 | 956847.73 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Negros Occidental | 117155 | Manlawa-an Elementary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 786342.28 | 784935.17 | COMPLETED | 100% |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117731 | Hamticon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 572834.21 |  | COMPLETED | 100% | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117732 | Laon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 504099.64 |  | COMPLETED | 100% | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117701 | Onofre Dela Paz ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 841603.67 |  | COMPLETED | 100% | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 117702 | Pedro R.Katalbas, Sr. II ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 433936.72 |  | COMPLETED | 100% | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VI | Sagay City | 184001 | Uychiat ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 570050.58 |  | COMPLETED | 100% | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bais City | 120084 | Biso PS | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 248776.32 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | FAILED BIDDING NO TAKER | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Bais City | 237501 | Cambayungon ES | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 505185.69 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | FAILED BIDDING NO TAKER | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 487551.32 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | FAILED BIDDING NO TAKER | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Bohol | 118491 | Badbad ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 347696.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 186504 | Cabacungan ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 291626.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118474 | Cabilao ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1082997.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118476 | Cambaquiz ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392980.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118542 | Lagtangon ES | MARIBOJOC | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 154103.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118059 | Anonang PS | BUENAVISTA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 122092.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118330 | Corte-Baud ES | JETAFE | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 281657 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Bohol | 118814 | Cuya Elem School | UBAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 83692.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Guihulngan City | 120266 | Dadiangao PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 831989.92 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1340772.59 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Guihulngan City | 120255 | Panagtugas PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1355741.1 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Guihulngan City | 120286 | Tominhao PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1360645.41 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Negros Oriental | 189530 | Alagasihan PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 39782.2 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Negros Oriental | 120342 | Barang-barang PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 41069.35 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Negros Oriental | 120350 | Campo-aling ES | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 184157.53 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Negros Oriental | 120523 | Sto. Tomas ES | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 71674.73 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Negros Oriental | 189521 | Tubod PS | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 52592.75 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Siquijor | 190008 | Cantugbas PS | MARIA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 75845.97 | 75742.97 | COMPLETED | 100% | Dec. 30, 2017 |  |  |  | Oct. 31, 2017 |  | Nov. 6, 2017 | Nov. 9, 2017 | Dec. 15, 2017 | Vanzdarryl Construction Design & Consultancy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VII | Tanjay City | 234005 | Bulo Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 532231.32 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | contract terminated | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Tanjay City | 120545 | Camuyogan ES | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 481609.38 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | contract terminated | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Tanjay City | 120546 | Canghatap Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349670.02 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | contract terminated | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Tanjay City | 120558 | Mato-Bato Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 447814.41 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | contract terminated | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VII | Tanjay City | 322306 | Namonbon HS | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 597036.67 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | contract terminated | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region VIII | Borongan City | 122400 | Canyupay ES | CITY OF BORONGAN (Capital) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245013.26 | 216888.33 | COMPLETED | 100% | February 19, 2018 | February 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID BORONGAN-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | Ootober 10, 2018 | October 20, 2018 | November 3, 2018 | November 6, 2018 | November 13, 2018 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122324 | Aguinaldo ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190242.77 | 190117.84 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122330 | Cagsalay ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228038.08 | 227972.11 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122331 | Campacion ES | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 171252.93 | 171187.07 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122333 | Casidman Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 189411.34 | 189359.73 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192501 | Inayawan Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168654.72 | 168550.02 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122336 | Macarthur Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245013.26 | 245004.03 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122339 | Tibalawon Elementary School | ARTECHE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 186392.77 | 186272.45 | COMPLETED | 100% | February 23, 2018 | March 7, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122409 | Baruk ES | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 544518.25 | 541551.01 | COMPLETED | 100% | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122411 | Caghalong PS | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 232283.83 | 231539.61 | COMPLETED | 100% | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122422 | Obong PS | CAN-AVID | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 190108.9 | 189894.16 | COMPLETED | 100% | February 23, 2018 | February 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122447 | Cabago-an ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 470006.38 | 468983.99 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192511 | Cagdanao ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 324124.37 | 322963.97 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122448 | Cagtabon ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168114.82 | 167079.73 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122431 | Del Pilar ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220455.4 | 219357.17 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122452 | Gap-ang ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 451823.73 | 450882.22 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122464 | Osmena ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 380236.45 | 379219.99 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122465 | Pasak ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 303437.3 | 302457.68 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192505 | Quiatan ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 312518.47 | 311425.1 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 3 | CY 2017 BEFF ELECTRIFICATION-03 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122437 | San Isidro ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392961.69 | 392337.8 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122440 | San Vicente ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 306873.58 | 305536.52 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122468 | Sta. Catalina PS | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 195417.5 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122443 | Tamsion PS | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170447.81 | 169561.23 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122469 | Tan-awan ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 401627.55 | 401330.72 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122472 | Villahermosa ES | DOLORES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477742.36 | 463065.91 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122474 | Alang-alang PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178353.68 | 175579.75 | COMPLETED | 100% | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122478 | Calutan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 187667.44 | 185690.89 | COMPLETED | 100% | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192502 | Inu-olanguhan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168161.09 | 166401.15 | COMPLETED | 100% | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122487 | Limbujan PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 180596.25 | 177094.53 | COMPLETED | 100% | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122495 | Quirino PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 189824.69 | 187618.8 | COMPLETED | 100% | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122496 | Roxas PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 178540.55 | 174356.4 | COMPLETED | 100% | February 23, 2018 |  | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122500 | San Roque PS | GENERAL MACARTHUR | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 193314.86 | COMPLETED | 100% | February 23, 2018 | May 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122515 | Pres. Roxas ES | GIPORLOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323898.08 | 321889.96 | COMPLETED | 100% | February 23, 2018 | January 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122517 | San Miguel ES | GIPORLOS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224354.54 | 222851.21 | COMPLETED | 100% | February 23, 2018 | January 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122534 | Banahao ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 502965.21 | 487057.72 | COMPLETED | 100% | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122547 | San Antonio PS | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169079.12 | 167041.65 | COMPLETED | 100% | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192519 | San Juan ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224354.54 | 220289.21 | COMPLETED | 100% | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192518 | Tagporo ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 176549.25 | 173008.14 | COMPLETED | 100% | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122553 | Trinidad ES | GUIUAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 558391.64 | 542422.31 | COMPLETED | 100% | February 23, 2018 | March 12. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122477 | Cacatmonan PS | HERNANI | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169583.63 | 169573.57 | COMPLETED | 100% | February 23, 2018 | January 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122573 | Casapa PS | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224661.33 | 222563.84 | COMPLETED | 100% | February 23, 2018 | March 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122576 | Jiwaran PS | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 224988.77 | 218797.18 | COMPLETED | 100% | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122577 | Mabuhay ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 312132.55 | 307690.63 | COMPLETED | 100% | February 23, 2018 | January 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122580 | Recare ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233222.41 | 230211.41 | COMPLETED | 100% | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122581 | Roxas ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 329283.85 | 325845.74 | COMPLETED | 100% | February 23, 2018 | January 5, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122582 | San Roque ES | JIPAPAD | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 459544.25 | 456790.07 | COMPLETED | 100% | February 23, 2018 | January 5, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 2 | CY 2017-BEFF ELECTRIFICATION-02 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122352 | San Isidro PS | LAWAAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195849.99 | 184256.29 | COMPLETED | 100% | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 408495.62 | 218703.93 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192515 | Taytay PS | MASLOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 222349.09 | 407901.96 | COMPLETED | 100% | February 23, 2018 | April 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 4 | CY 2017-BEFF ELECTRIFICATION-04 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | LOBRINOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122615 | Del Pilar ES | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223783.25 | 220221.96 | COMPLETED | 100% | February 23, 2018 | January 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122629 | San Gabriel ES | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 303314.44 | 303180.18 | COMPLETED | 100% | February 23, 2018 | February 15, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122630 | Tagasli-an Elementary School | MAYDOLONG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 298329.53 | 297876.2 | COMPLETED | 100% | February 23, 2018 | March 10, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 6 | CY 2017 BEFF ELECTRIFICATION-06 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122535 | Banuyo ES | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 372480.66 | 368930.21 | COMPLETED | 100% | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122539 | Cabunga-an PS | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170555.27 | 166401.15 | COMPLETED | 100% | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122550 | San Roque PS | MERCEDES | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 299085.39 | 295990.11 | COMPLETED | 100% | February 23, 2018 | March 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 5 | CY 2017-BEFF ELECTRIFICATION-05 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122652 | Agsam ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 553874.61 | 551425.2 | COMPLETED | 100% | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122653 | Alang-alang PS | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 234478.86 | 233406.1 | COMPLETED | 100% | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122655 | Balingasag ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392928.66 | 391826.62 | COMPLETED | 100% | February 23, 2018 | February. 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122664 | Gamot PS | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219556.54 | 219231.1 | COMPLETED | 100% | February 23, 2018 | January 28, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122667 | Naga ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 323913.65 | 323005.83 | COMPLETED | 100% | February 23, 2018 | March 3, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122669 | Rizal ES | ORAS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 469541.73 | 468171.17 | COMPLETED | 100% | February 23, 2018 | March 3, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 9 | CY 2017 BEFF ELECTRIFICATION-09 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122677 | Cambilla ES | QUINAPONDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 230252.7 | 227259.16 | COMPLETED | 100% | February 23, 2018 | April 2. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122678 | Cantinio PS | QUINAPONDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 168901.65 | 165760.65 | COMPLETED | 100% | February 23, 2018 | April 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122717 | Maliwaliw ES | SALCEDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336540.42 | 334891.69 | COMPLETED | 100% | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 10 | CY 2017 BEFF ELECTRIFICATION-10 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | DAYBREAK ENTERPRISES AND ENGINEERING CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122735 | Bangon PS | SAN POLICARPO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 170555.27 | 170545.05 | COMPLETED | 100% | February 23, 2018 | March 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122743 | Sta. Cruz ES | SAN POLICARPO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 218776.35 | 218760.39 | COMPLETED | 100% | February 23, 2018 | March 12, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 1 | CY 2017 BEFF ELECTRIFICATION-01 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122748 | Kandalakit ES | SULAT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 186023.48 | 185937.19 | COMPLETED | 100% | February 23, 2018 | March 18, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122749 | Mabini ES | SULAT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 387754.43 | 386510.7 | COMPLETED | 100% | February 23, 2018 | March 18, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122760 | Beto PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213897.81 | 213573.35 | COMPLETED | 100% | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122762 | Bongdo PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 241138.48 | 240935.86 | COMPLETED | 100% | February 23, 2018 | April 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122764 | Danao ES | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 225506.12 | 225292.14 | COMPLETED | 100% | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122765 | Del Remedios ES | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 308879.48 | 308702.32 | COMPLETED | 100% | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122766 | Gayam PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 169344.07 | 169217.01 | COMPLETED | 100% | February 23, 2018 | April 2, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 7 | CY 2017 BEFF ELECTRIFICATION-07 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | E.M PAULE CONSTRUCTION AND TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 192509 | Pangabutan PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 227008.72 | 226483.9 | COMPLETED | 100% | February 23, 2018 | February 20, 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region VIII | Eastern Samar | 122774 | San Rafael PS | TAFT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243122.67 | 242352.21 | COMPLETED | 100% | February 23, 2018 | march 17. 2018 | CY2017BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS ON-GRID ESAMAR-LOT 8 | CY 2017 BEFF ELECTRIFICATION-08 | October 13, 2017 | October 23, 2017 | November 6, 2017 | November 13,2017 | November 17,2017 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region X | Bukidnon | 199541 | Don Antonio O. Floirendo Sr. Primary School | QUEZON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 299968.2 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | NO TAKER | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 276066 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region X | Camiguin | 315004 | Bugang Integrated School | SAGAY | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286844.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1189918.94 | 1183082.61 | COMPLETED | 100% | 2018-03-08 | April 18.2018 | [7 empty] | GREEN BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region X | Lanao del Norte | 127215 | Lininding ES | TAGOLOAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 2479096.78 | 2473089.45 | COMPLETED | 100% | 2018-03-08 | April 24.2018 | [7 empty] | GREEN BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2017 | Region X | Malaybalay City |  | Senior High within Casisang CES | Malaybalay City | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 692717.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128423 | Anagase Elementary School | MONKAYO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 818399.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 204019 | Cabanggatan PS | MONTEVISTA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 575410.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128467 | Mabanda PS | MONTEVISTA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 420762.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128510 | Andap ES | NEW BATAAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 668672.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 204022 | Limot ES | LAAK (SAN VICENTE) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 632284.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128351 | Kinuban ES | MACO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 934118.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Compostela Valley | 128356 | New Barili PS | MACO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 463178.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128580 | Mahayahay PS | ASUNCION (SAUG) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 2067596.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128707 | Kauswagan PS | NEW CORELLA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 3128902.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Davao del Norte | 128805 | Paiton ES | TALAINGOD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 2573784.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129083 | Langan ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 737544.94 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129096 | Patulangon ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 842005.11 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 129087 | Tubison ES | SANTA CRUZ | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1713885.41 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 128885 | Mangili ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1692446.88 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 128890 | San Felipe ES | JOSE ABAD SANTOS (TRINIDAD) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 404576.81 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao del Sur | 205056 | Malandog PS | MALITA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 821644.79 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | road right of way, redflag area | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Davao Oriental | 129201 | Cauwayanan PS | BOSTON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 745934.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Davao Oriental | 129230 | Balete PS | CARAGA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 437974.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XI | Island Garden City of Samal | 128741 | Tagluno ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 849741.28 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XI | Island Garden City of Samal | 128742 | Tayapoc ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 461553.36 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317201 | Bacongco NHS (Koronadal NCHS - Annex, Bacongco Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 220860.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 156384.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304670 | Esperanza NHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 222512.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 494116.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 131381 | Marbel 7 Elementary School | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 217391.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317203 | Rotonda National High School | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 178926.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317202 | Saravia NHS (Koronadal NCHS - Annex, Saravia Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 217649.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129829 | Maracabac ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207548 | Pidatan ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207527 | Tabunan ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207549 | Talha ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129860 | Dungguan ES | ALEOSAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129931 | Balindong PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207516 | Buay-Buay PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207540 | Kalalagan PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129939 | Kudon Elementary School | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207501 | Kulawan ES | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129950 | Sabang PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129976 | Bai Matabay Piang MPS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129957 | BAROYON ELEMENTARY SCHOOL | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129983 | Kibenes ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207535 | Kilabao PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129985 | Langogan Elementary School | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129964 | Macabenban ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207521 | Malugasa PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129969 | Mesopa PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129970 | New Bentangan PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129971 | Old Bentangan ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129988 | Palanggalan ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129990 | Sambag PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129974 | Tawagon PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207569 | Tulunan ES | KABACAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207525 | Dabpil Sampulna ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130223 | Datu Guilem Piang ES (Upper Olandang ES) | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130221 | Kadingilan ES (Pagao Memorial) | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130213 | Kudarangan ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130216 | Macasendeg ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130218 | Mudseng ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 200221.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316532 | Salunayan NHS-Dabpil Sampulna Olandang HS Annex | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130283 | Balacayon Primary School | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130285 | Buricain Elementary School | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207542 | Datu Mantil PS | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130289 | KADINGILAN ELEMENTARY SCHOOL | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130294 | Matilac ES | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 304479 | Matilac HS | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130305 | Balongis ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130335 | Binandal PS | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130319 | Bulod ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130343 | Dulangan M. Abid ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130341 | Langayen ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207563 | Malik Mem. ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207543 | Senior Malao ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 200221.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129882 | Datu Embangan PS | ANTIPAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129894 | Anuling PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316553 | Datu Ladayon HS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129907 | Kapayahan PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129908 | Katindu ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129910 | Kiatao PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129913 | Kulaman ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129916 | Lumbo PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207502 | Paco-Paco ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207544 | Sinayawan ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316538 | Bagumbayan HS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207555 | Cebomailo Primary School Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130075 | Datu Celo ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130053 | Don Panaca ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130059 | Lubas PS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207537 | Mahongkog PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207518 | Noa PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130063 | Owas ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207541 | Temporan PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130067 | Timodos PS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207558 | Agustin Doneza PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130084 | Balawan ES | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207566 | Lower Saguing PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130105 | San Isidro PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207560 | Sitio Mainit PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130144 | Arakan PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207572 | Diosdado Almarines ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207552 | Eden Elementary School-Maligaya Primary School Annex | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130149 | Ilian ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207529 | Kulog ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207573 | Langka ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130132 | Layangan ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207562 | Migcuan ElementarySchool | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130138 | New Xavier ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207561 | Rajah Sumonsang Dilangalen PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207505 | West Patadon PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207567 | Banawa ES | M'LANG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130350 | Calixta Daguman ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130353 | Guinto ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130354 | Hope PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130359 | Kabinuangan PS (Lawitan) | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 207272.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130356 | Kimahuring PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130358 | Lamalama ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130386 | Sumakwelan PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130364 | Tahongtong PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130365 | Tarinan PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130401 | Batang ES | TULUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130012 | Buluan ES | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207551 | Dangleg Primary School | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207545 | Dilanggalen PS | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130016 | Malabuaya ES | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207547 | Simbuhay ES - Mulita PS Annex | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207546 | Tamped ES - Dilutan PS Annex | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130648 | Ebenezer ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130629 | Kataan ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 159283.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130650 | Lam-asam ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 201220.9 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130651 | Lamkot Elementary School | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 270638.88 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130634 | Lamtabong ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 255453.43 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130652 | Little Baguio ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 228620.67 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 208522 | Gumama PS | NORALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 171895.18 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 208514 | Lambusong ES | NORALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 201220.9 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130768 | Defensor ES | SURALLAH | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130777 | Upper Talahik ES | SURALLAH | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 298038.66 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130956 | Balisan PS | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 369182.57 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130971 | Lasak ES | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 188877.94 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130973 | Limonzo PS | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130961 | New Ilocos ES | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123724.46 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 316801 | Laguilayan NHS - Sultan Ali Akbar Sinenggayan HS Annex | ISULAN (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 209029 | Baumol ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130947 | San Vicente ES | BAGUMBAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 149388.48 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 209036 | Tiger ES | ESPERANZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131035 | Minorok ES | KALAMANSIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123724.46 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131125 | Kimakang ES | LEBAK | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 421377.59 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131170 | Dumolol E/S | PALIMBANG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 240299.44 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131049 | Balite ES | SEN. NINOY AQUINO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131057 | Malegdeg Primary School | SEN. NINOY AQUINO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2018 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | UPGRADING | 1 | 825727.12 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | 0 | 1 | UPGRADING | 1 | 807054.31 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305105 | Western Abra NHS | DANGLAS | 0 | 1 | UPGRADING | 1 | 1001258.48 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 | 1 | UPGRADING | 1 | 1221450.81 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | UPGRADING | 1 | 1177438.05 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305102 | Tagodtod NHS | LAGANGILANG | 0 | 1 | UPGRADING | 1 | 1168924.11 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305094 | Pulot NHS | LAGAYAN | 0 | 1 | UPGRADING | 1 | 1162253.81 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | UPGRADING | 1 | 1794998.25 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 | 1 | UPGRADING | 1 | 1072964.35 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 | 1 | UPGRADING | 1 | 729023.16 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | UPGRADING | 1 | 713435.55 |  | COMPLETED | 100% | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318811 | PIO DALIM Memorial SAT-Sta.Filomena | CALANASAN (BAYAG) | 0 | 1 | UPGRADING | 1 | 886166.84 | 908090.3 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318803 | Conner Central NHS Cupis Annex | CONNER | 0 | 1 | UPGRADING | 1 | 826570.72 | 796851.23 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318812 | Conner Central NHS Ili Annex | CONNER | 0 | 1 | UPGRADING | 3 | 1253305.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318802 | Conner Central NHS Talifugo Annex | CONNER | 0 | 1 | UPGRADING | 3 | 1282984.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135259 | Conner Central School | CONNER | 0 | 1 | UPGRADING | 3 | 976624.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305112 | Conner Natl. HS | CONNER | 0 | 1 | UPGRADING | 3 | 1317860.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 | 1 | UPGRADING | 3 | 1162205.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 219020 | Mabiga Elementary School | CONNER | 0 | 1 | UPGRADING | 3 | 398700.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | UPGRADING | 1 | 823927.98 | 895499.5 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135287 | Balasi Elementary School | FLORA | 0 | 1 | UPGRADING | 3 | 739360.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135289 | Flora CS | FLORA | 0 | 1 | UPGRADING | 3 | 1214859.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 | 1 | UPGRADING | 1 | 1199958.86 | 1156657.37 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135294 | Mallig ES | FLORA | 0 | 1 | UPGRADING | 3 | 723531.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 | 1 | UPGRADING | 1 | 767937.37 | 988685.78 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS Main | KABUGAO (Capital) | 0 | 1 | UPGRADING | 1 | 1026403.1 | 1074016.92 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305107 | Apayao Science HS | LUNA | 0 | 1 | UPGRADING | 1 | 929638.03 | 1239931.36 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 | 1 | UPGRADING | 2 | 952154.67 | 922980.49 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135336 | Luna CS | LUNA | 0 | 1 | UPGRADING | 3 | 1314374.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305116 | Luna National High School Main | LUNA | 0 | 1 | UPGRADING | 1 | 933340.55 | 725415.93 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | UPGRADING | 2 | 998955.38 | 961612.22 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | UPGRADING | 2 | 879844.34 | 851601.82 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135356 | Mataguisi ES | PUDTOL | 0 | 1 | UPGRADING | 3 | 513708.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135357 | Pudtol CS | PUDTOL | 0 | 1 | UPGRADING | 3 | 1415078.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | UPGRADING | 1 | 1284282.48 | 849654 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318810 | Swan National Agricultural and Trade High School | PUDTOL | 0 | 1 | UPGRADING | 3 | 1224974.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | 0 | 1 | UPGRADING | 3 | 1280614.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305120 | Mayor Guillermo Barsalan SAT | SANTA MARCELA | 0 | 1 | UPGRADING | 1 | 1119970.26 | 799643.44 | COMPLETED | 100% | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | 0 | 1 | UPGRADING | 3 | 1368646.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 5037080.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305269 | Baguio City National High School - Main | BAGUIO CITY | 0 | 1 | UPGRADING | 1 | 5343246.78 | 5314182.16 | COMPLETED | 100% | Sept. 8, 2018 |  |  |  | 2018-04-26 | 2018-05-04 | 2018-05-18 | 2018-05-22 | 2018-06-08 | www.construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136388 | Elpidio R. Quirino Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4795287.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4182575.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4892682 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3894208.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136417 | SPED Center (FL) | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3136655.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3283387.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305129 | Atok NHS | ATOK | 0 | 1 | UPGRADING | 1 | 1128082.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318913 | Ampusongan NHS - Kayapa Ext. | BAKUN | 0 | 1 | UPGRADING | 1 | 1036761.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318901 | Bokod NHS - Daclan Extension | BOKOD | 0 | 1 | UPGRADING | 1 | 1123051.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305134 | Binga NHS | ITOGON | 0 | 1 | UPGRADING | 1 | 1120443.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305159 | Fianza Mem'l NHS - Tinongdan | ITOGON | 0 | 1 | UPGRADING | 1 | 1163516.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305142 | Laurencio Fianza National High School | ITOGON | 0 | 1 | UPGRADING | 1 | 1184835.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 | 1 | UPGRADING | 1 | 1183986.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318908 | Gov. Bado Dangwa Agro-Industrial School Extension - Taba-ao Annex | KAPANGAN | 0 | 1 | UPGRADING | 1 | 1139374.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305147 | Kapangan Central NHS (RA8841) | KAPANGAN | 0 | 1 | UPGRADING | 1 | 1022559.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305154 | MADAYMEN NATIONAL HIGH SCHOOL | KIBUNGAN | 0 | 1 | UPGRADING | 1 | 1147876.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305140 | Cordillera Regional Science HS | LA TRINIDAD (Capital) | 0 | 1 | UPGRADING | 1 | 1004906.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305156 | Bulalacao NHS | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1134226.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1130157.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305144 | Guinaoang NHS | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1147228.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305155 | Mankayan National High School | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1167917.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 | 1 | UPGRADING | 1 | 1162986.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305160 | Tuba NHS (Nangalisan) | TUBA | 0 | 1 | UPGRADING | 1 | 1147313.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305171 | Eastern Potia National High School | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 1679924.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305187 | Namillangan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 2203262.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 1552581.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305190 | Sta. Maria NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 2725220.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305173 | Haliap NHS | ASIPULO | 0 | 1 | UPGRADING | 2 | 2115765.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 319001 | Bangbang National High School | HUNGDUAN | 0 | 1 | UPGRADING | 2 | 1968987.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 | 1 | UPGRADING | 2 | 1619239.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 | 1 | UPGRADING | 2 | 1450065.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | UPGRADING | 1 | 1410957.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | UPGRADING | 2 | 1676892.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305183 | Lawig NHS | LAMUT | 0 | 1 | UPGRADING | 1 | 1692354.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305192 | Tinoc NHS | TINOC | 0 | 1 | UPGRADING | 2 | 1443313.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | UPGRADING | 1 | 2442507.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305223 | Lubuagan National High School | LUBUAGAN | 0 | 1 | UPGRADING | 1 | 784163.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 340131 | SHS - Lubuagan | LUBUAGAN | 0 | 1 | UPGRADING | 1 | 979846.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 | 1 | UPGRADING | 1 | 1792826.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305201 | Cal-owan Agricultural Vocational National High School | PINUKPUK | 0 | 1 | UPGRADING | 1 | 1088979.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | PINUKPUK | 0 | 1 | UPGRADING | 1 | 1895776.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305218 | Macutay-Palao National High School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | 1 | 1090872.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305217 | Rizal National School of Arts & Trades | RIZAL (LIWAN) | 0 | 1 | UPGRADING | 1 | 2016943.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305211 | Magtoma Pangol NHS-Main | TANUDAN | 0 | 1 | UPGRADING | 1 | 967916.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305220 | Bangad National High School | TINGLAYAN | 0 | 1 | UPGRADING | 1 | 1506409.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 | 1 | UPGRADING | 1 | 984873.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 | 1 | UPGRADING | 1 | 1559940.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305244 | Guinzadan National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1722122.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305252 | Mt. Data National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1255178.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305259 | Otucan-Bila National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1195926.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305237 | Besao National High School | BESAO | 0 | 1 | UPGRADING | 1 | 703212.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305260 | Panabungen School of Arts, trades, and Home Industries | BESAO | 0 | 1 | UPGRADING | 1 | 1490662.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 | 1 | UPGRADING | 1 | 1648360.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 340155 | Natonin SHS_Stand Alone | NATONIN | 0 | 1 | UPGRADING | 1 | 943990.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1351919.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305230 | Bacarri National Trade & Agricultural School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1297230.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305239 | Butigue National High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1396732.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1637975.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1913096.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | 0 | 1 | UPGRADING | 1 | 1121246.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305263 | Sabangan National High School | SABANGAN | 0 | 1 | UPGRADING | 1 | 1691013.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305264 | Sadanga National High School | SADANGA | 0 | 1 | UPGRADING | 1 | 1041709.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305266 | Ankileng NHS (Suyo NHS) | SAGADA | 0 | 1 | UPGRADING | 1 | 1041024.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | 0 | 1 | UPGRADING | 1 | 923929.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305240 | Cagubatan National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1035377.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305247 | Lubon National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1055606.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305251 | Masla National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1022374.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305267 | Tadian School of Arts & Trades | TADIAN | 0 | 1 | UPGRADING | 1 | 2542733.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 1437535.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1737997.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1566626.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 2823729.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 1471209.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1321850.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 3248280.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304680 | Casiklan NHS- Durian NHS Annex | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 908776.8783 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304679 | Durian NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1001800.817 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1995482.4464 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304694 | Marcos Calo NHS | LAS NIEVES | 1 | 1 | UPGRADING | 2 | 1000395.19 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 1375813.6202 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304682 | Guinabsan NHS | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 890124.6 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 500049 | Manapa II Integrated School | BUENAVISTA | 2 | 1 | UPGRADING | 2 | 1485353.95 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317304 | Cahayagan NHS (Carmen NHS Annex) | CARMEN | 2 | 1 | UPGRADING | 2 | 722664.43 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 | 1 | UPGRADING | 2 | 1264534.97 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304688 | Kitcharao NHS | KITCHARAO | 2 | 1 | UPGRADING | 2 | 1511842.0007 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304691 | Magallanes National High School | MAGALLANES | 2 | 1 | UPGRADING | 2 | 1352554.6445 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 | 1 | UPGRADING | 2 | 1598975.7697 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317302 | Nasipit NHS | NASIPIT | 2 | 1 | UPGRADING | 2 | 781156.32 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304673 | Agay National High School | REMEDIOS T. ROMUALDEZ | 2 | 1 | UPGRADING | 2 | 1461966.2225 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 | 1 | UPGRADING | 2 | 1422466.5055 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304698 | Santiago NHS | SANTIAGO | 2 | 1 | UPGRADING | 2 | 1381089.87 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 | 1 | UPGRADING | 2 | 1058491.7855 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | UPGRADING | 2 | 1063694.0519 |  | COMPLETED | 100% |  |  |  |  | 2018-05-02 | 2018-05-10 | 2018-05-18 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304730 | Patin-ay National High School | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 3637477.62 |  | COMPLETED | 100% |  |  |  | 2018-09-012 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | RJB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304731 | Prosperidad NHS | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 4255007.78 |  | COMPLETED | 100% |  |  |  | 2018-09-015 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304749 | Sta. Irene National High School | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 5421042.52 |  | COMPLETED | 100% |  |  |  | 2018-09-014 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 317428 | West Prosperidad Nhs | PROSPERIDAD (Capital) | 1 | 1 | UPGRADING | 2 | 2904296.75 |  | COMPLETED | 100% |  |  |  | 2018-09-013 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | A-MARTINA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304709 | Bunawan National High School | BUNAWAN | 2 | 1 | UPGRADING | 2 | 4335897.39 |  | COMPLETED | 100% |  |  |  | 2018-09-016 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 | 1 | UPGRADING | 2 | 3924975.51 |  | COMPLETED | 100% |  |  |  | 2018-09-018 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | UPGRADING | 2 | 3571779.59 |  | COMPLETED | 100% |  |  |  | 2018-09-017 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2 | 1 | UPGRADING | 2 | 2315300.82 |  | COMPLETED | 100% |  |  |  | 2018-09-019 | AUGUST 8, 2018 | AUGUST 16, 2018 | SEPTEMBER 04, 2018 |  |  | ARCLER BUILDERS & CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 1247694.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 304728 | Noli National High School | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 1313237.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bayugan City | 340297 | STAND ALONE SHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING | 2 | 2716825.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 2627484.1 | 2596626.53 | COMPLETED | 100% | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304919 | Mangagoy NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1519924.76 | 1502002.64 | COMPLETED | 100% | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bislig City | 304869 | Sikahoy NHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1144311.01 | 1130069.36 | COMPLETED | 100% | Aug. 27, 2018 |  | 2018BEFF-Electrification-C2 | 2018BEFF-Electrification-C2 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 2 | 1438901.82 | 1422202.03 | COMPLETED | 100% | Sept. 26, 2018 |  | 2018BEFF-Electrification-C1 | 2018BEFF-Electrification-C1 | 2018-03-23 | 2018-04-05 | 2018-04-17 | 2018-04-25 | May 23, 2018 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2221583.24 | 1949719.39 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2205770.32 | 1877249.5724 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 340337 | Butuan City Senior High School Stand Alone | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2762431.87 | 1818553.25 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1414442.2064 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-007 | RRC-2018-007 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | July 6, 2018 | Two J.E. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1663800.35 | 1652389.55 | COMPLETED | 100% | December 15, 2018 |  | RRC-2018-006 | RRC-2018-006 | 2018-03-24 | 2018-05-02 | 2018-05-16 | 2018-06-11 | july, 23, 2018 | ETP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2 | 1 | UPGRADING | 2 | 1117389.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 | 1 | UPGRADING | 2 | 1006220.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304815 | Cagdianao NHS | CAGDIANAO | 0 | 1 | UPGRADING | 1 | 2138817.1 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-02 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | UPGRADING | 1 | 2371554.25 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-04 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 | 1 | UPGRADING | 1 | 2001578.36 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-05 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304808 | Albor NHS | LIBJO (ALBOR) | 0 | 1 | UPGRADING | 1 | 2335700.05 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-01 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | 1 | 2337098.19 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-03 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 | 1 | UPGRADING | 1 | 2390442.95 |  | COMPLETED | 100% | NOV. 17, 2018 |  |  | INFRA18-002-06 |  |  |  |  | JULY 11, 2018 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304774 | Dapa NHS | DAPA | 1 | 1 | UPGRADING | 1 | 2929746.09 | 2905000 | COMPLETED | 100% |  |  |  | BEFF-INFRA2018-008 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304783 | Del Carmen NHS | DEL CARMEN | 1 | 1 | UPGRADING | 1 | 2271995.06 | 2250000 | COMPLETED | 100% |  |  |  | BEFF-INFRA2018-009 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304777 | Gen Luna NHS | GENERAL LUNA | 1 | 1 | UPGRADING | 1 | 2775183.35 | 2750000 | COMPLETED | 100% |  |  |  | BEFF-INFRA2018-010 | February 8 ,2018 | February 19, 2018 | March 5, 2018 | May 3, 2018 | May 16, 2018 | Vic B. Borja Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304784 | Roxas National High School | SAN ISIDRO | 1 | 1 | UPGRADING | 2 | 2109106.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304790 | Pamosaingan National High School | SOCORRO | 1 | 1 | UPGRADING | 3 | 3050000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 | 1 | UPGRADING | 3 | 3000000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1 | 1 | UPGRADING | 3 | 3700000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304800 | Anomar NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 568659.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 340383 | Cabrera-Altres National High School | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 565967.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304794 | Caraga Regional Science HS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 567310.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 1348769.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 317704 | Lipata National High School | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 953359.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304799 | mat-i national high school | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1356411.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2488304.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao City | 317701 | Taft NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 3 | 987826.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 | 1 | UPGRADING | 3 | 1657085.43 |  | COMPLETED | 100% | 2019-02-20 |  |  | 025-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 | 1 | UPGRADING | 1 | 1168482.85 | 1162181.16 | COMPLETED | 100% | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 | 1 | UPGRADING | 1 | 1178282.61 | 1171932.16 | COMPLETED | 100% | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317806 | Payapag NHS | BACUAG | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1123572.18 | COMPLETED | 100% | 2018-08-05 |  |  | 017-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 | 1 | UPGRADING | 1 | 1915898.59 | 1901116.76 | COMPLETED | 100% | 2018-07-11 |  |  | 018-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-04 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304835 | Hacienda NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1271122.29 | 1263572.957 | COMPLETED | 100% | 2018-08-29 |  |  | 023-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1121180.273 | COMPLETED | 100% | 2018-07-19 |  |  | 020-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 | 1 | UPGRADING | 1 | 1336228.12 | 1326699.973 | COMPLETED | 100% | 2018-07-19 |  |  | 020-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 | 1 | UPGRADING | 1 | 1284562.4 | 1276946.207 | COMPLETED | 100% | 2018-08-29 |  |  | 023-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2 | 1 | UPGRADING | 3 | 1593266.33 |  | COMPLETED | 100% | 2019-02-20 |  |  | 026-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304833 | Malimono NHS | MALIMONO | 2 | 1 | UPGRADING | 3 | 1943819.1 |  | COMPLETED | 100% | 2019-02-20 |  |  | 027-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | UPGRADING | 1 | 1178282.61 | 1171195.167 | COMPLETED | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 | 1 | UPGRADING | 3 | 1493969.85 |  | COMPLETED | 100% | 2019-02-20 |  |  | 028-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | UPGRADING | 1 | 1284443.5 | 1276827.897 | COMPLETED | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 | 1 | UPGRADING | 3 | 1405226.13 |  | COMPLETED | 100% | 2019-03-29 |  |  | 031-2018 | 2018-11-30 | 2018-12-07 | 2018-12-21 | 2018-12-27 | 2018-12-29 | RCDG Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132482 | Sta Cruz ES | PLACER | 2 | 1 | UPGRADING | 3 | 1627085.43 |  | COMPLETED | 100% | 2019-02-20 |  |  | 029-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 3 | 1582814.07 |  | COMPLETED | 100% | 2019-02-20 |  |  | 030-2018 | 2018-10-19 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2018-11-21 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 1 | 1163382.98 | 1150077.79 | COMPLETED | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1116543.31 | COMPLETED | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS - Annex (TS PSMHS) | SISON | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1120606.347 | COMPLETED | 100% | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304850 | Mayag National High School | SISON | 2 | 1 | UPGRADING | 3 | 1858090.45 |  | COMPLETED | 100% | 2019-03-29 |  |  | 032-2018 | 2018-11-30 | 2018-12-07 | 2018-11-07 | 2018-12-27 | 2018-12-29 | RJB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304849 | T.S Pantilo, Sr. MNHS | SISON | 2 | 1 | UPGRADING | 1 | 1141983.51 | 1132847.827 | COMPLETED | 100% | 2018-07-19 |  |  | 021-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1900350.59 | 1883378.9 | COMPLETED | 100% | 2018-08-03 |  |  | 016-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | UPGRADING | 1 | 1280970.03 | 1273371.717 | COMPLETED | 100% | 2018-08-05 |  |  | 019-2018 | 2018-04-04 | 2018-04-11 | 2018-04-23 | 2018-05-30 | 2018-05-05 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1118994.447 | COMPLETED | 100% | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 | 1 | UPGRADING | 1 | 1129680.82 | 1118994.447 | COMPLETED | 100% | 2018-08-29 |  |  | 024-2018 | 2018-04-04 | 2018-05-04 | 2018-05-22 | 2018-05-24 | 2018-06-15 | Maxter Resources, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304861 | Barobo National High School | BAROBO | 1 | 1 | UPGRADING | 2 | 1215833.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304888 | Gamut National School (Barobo) | BAROBO | 1 | 1 | UPGRADING | 2 | 1132934.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304895 | Lingig National High School | LINGIG | 1 | 1 | UPGRADING | 2 | 2040849.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304862 | Cabacungan National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 826611.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317941 | Rizal National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 989901.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 | 1 | UPGRADING | 2 | 1165346.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500577 | Baculin Integrated School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1230229.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1285902.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1958192.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317940 | Hinatuan NCHS - Cambatong NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 2157380.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317939 | Hinatuan NCHS - Roxas NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 1076759.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304920 | Tagasaka National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1018059.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304921 | Tagasaka NHS - Bigaan NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 699350.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 317910 | Tagasaka NHS - Loyola NHS Annex | HINATUAN | 2 | 1 | UPGRADING | 2 | 1686150.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500579 | Tarusan Integrated School | HINATUAN | 2 | 1 | UPGRADING | 2 | 980049.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304923 | Tidman National High School | HINATUAN | 2 | 1 | UPGRADING | 2 | 1039113.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500581 | Anibongan Integrated School | LINGIG | 2 | 1 | UPGRADING | 2 | 634932.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304860 | BARCELONA NATIONAL HIGH SCHOOL | LINGIG | 2 | 1 | UPGRADING | 2 | 1692675.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304896 | M.K.Yusingco National High School | LINGIG | 2 | 1 | UPGRADING | 2 | 1370222.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated School | LINGIG | 2 | 1 | UPGRADING | 2 | 886819.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1162180.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1426254.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500586 | Jobar Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1034475.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1167541.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500324 | Maglambing Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1136011.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1117283.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500582 | Malixi Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1210039.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500585 | Manambia Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1130028.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500580 | Osmeña Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1356777.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500325 | Quary I Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 829362.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500583 | Quezon Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1275561.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1162498.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CARAGA | Surigao del Sur | 500584 | Sta. Maria Integrated School | TAGBINA | 2 | 1 | UPGRADING | 2 | 1295078.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 | UPGRADING | 1 | 1957934.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 672163.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Samaria Tala Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 754858.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Sampaguita Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 743289.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING | 2 | 1947303.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | UPGRADING | 2 | 4724091.14 | 3665127.39 | COMPLETED | 100% | 2019-06-20 |  |  |  |  | 2018-11-07 | 2018-11-19 | 2018-12-03 | 2018-12-26 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School (Isaac Lopez ES) | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | 2 | 3345858.02 | 2496908.97 | COMPLETED | 100% |  |  | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | 2 | 4891117.15 | 3650087.43 | COMPLETED | 100% | 2019-01-31 | 2019-01-31 | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | SAMPALOC | 4 | 1 | UPGRADING | 2 | 3105124.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Marikina City | 500052 | Concepcion Integrated School | CITY OF MARIKINA | 2 | 1 | UPGRADING | 2 | 784512.82 |  | COMPLETED | 100% | June 16, 2019 | May 22, 2019 |  |  | March 22, 2019 |  | March 27, 2019 | March 27, 2019 | April 12, 2019 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 | 1 | UPGRADING | 2 | 591084.11 |  | COMPLETED | 100% | June 16, 2018 | May 22, 2018 |  |  | March 22, 2018 |  | March 27, 2018 | March 27, 2018 | April 12, 2018 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | 2 | 679397.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | 2 | 1192859.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | UPGRADING | 2 | 2194937.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | UPGRADING | 3 | 6470050.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 | 1 | UPGRADING | 2 | 4774665.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305320 | Balingasa HS | Quezon City | 1 | 1 | UPGRADING | 1 | 3168383.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 | 1 | UPGRADING | 1 | 3248178.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | Quezon City | 1 | 1 | UPGRADING | 1 | 1105837.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 | 1 | UPGRADING | 1 | 5943563.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 136540 | Pres. Corazon C. Aquino E/S | QUEZON CITY | 2 | 1 | UPGRADING | 4 | 1744063.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 | 1 | UPGRADING | 1 | 4917426.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305361 | Manuel A. Roxas HS | Quezon City | 4 | 1 | UPGRADING | 1 | 3106367.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 | 1 | UPGRADING | 1 | 3401452.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Taguig | 305466 | Pateros National High School | PATEROS | 1 | 1 | UPGRADING | 2 | 2165075.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | UPGRADING | 3 | 2626512.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Valenzuela City | 320404 | Bignay National High School | CITY OF VALENZUELA | 1 | 1 | UPGRADING | 2 | 2484345.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING | 2 | 2376416.44 | 2364155.76 | COMPLETED | 100% | 2018-07-19 | 2018-07-19 |  |  | 2018-04-13 | 2018-04-19 | 2018-05-03 | 2018-05-10 | 2018-05-21 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Batac City | 300005 | Batac National High School | Batac City | 2 | 1 | UPGRADING | 2 | 1305111.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Batac City | 300012 | CRISPINA MARCOS VALDEZ NHS | Batac City | 2 | 1 | UPGRADING | 2 | 1305111.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 711644.09 | 705.320.36 | COMPLETED | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 958451.44 | 950712.2 | COMPLETED | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 880009.36 | 873967.44 | COMPLETED | 100% | 2018-11-26 | 2019-02-13 | PB-INFRA-02-2018 |  | 2018-07-07 | 2018-07-17 | 2018-07-17 | 2018-08-20 | 2018-08-28 | MRK SQUARE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 102157 | East Central IS | DAGUPAN CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1567287.75 | 1554489.25 | COMPLETED | 100% | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 | 1 | UPGRADING | 2 | 1136698.75 | 1127180.5 | COMPLETED | 100% | 2018-09-25 | 2018-09-25 | [5 empty] | 2018-06-28 | 2018-07-06 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Dagupan City | 102178 | Pugaro IS | DAGUPAN CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1069836.08 | 1059523.39 | COMPLETED | 100% | July 4, 2018 | July 4, 2018 | [6 empty] | April 6, 2018 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300001 | Adams NHS | ADAMS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 825617.42 | 803491.0678 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787840.2812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1143193.66 | 1119174.8024 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1131237.69 | 1107922.4984 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300019 | Luzong NHS | PAGUDPUD | 1 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 | 1 | UPGRADING | 2 | 712493.4423 | 695928.5312 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787840.2812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500592 | Pandan IS | SARRAT | 1 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | UPGRADING | 2 | 804898.5191 | 787039.6562 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 | 1 | UPGRADING | 2 | 681691.7501 | 665344.6562 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1 | 1 | UPGRADING | 2 | 589286.6733 | 573753.1562 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1 | 1 | UPGRADING | 2 | 620088.3656 | 603536.4062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 2 | 1 | UPGRADING | 2 | 881902.7497 | 864700.2812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500000 | Caraitan Integrated School | BADOC | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665024.4062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300021 | Nagrebcan NHS | BADOC | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665344.6562 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 2 | 1 | UPGRADING | 2 | 681691.7501 | 665504.7812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300008 | Caestebanan NHS | BANNA (ESPIRITU) | 2 | 1 | UPGRADING | 2 | 620088.3656 | 604337.0312 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300013 | Currimao NHS | CURRIMAO | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634120.2812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320806 | Dingras NHS/Lt. Edgar Foz Mem. NHS (Barong Campus) | DINGRAS | 2 | 1 | UPGRADING | 2 | 589286.6733 | 573593.0312 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320809 | Dingras NHS/Lt. Edgar Foz Mem. NHS- (Sulquiano Campus) | DINGRAS | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320807 | San Marcelino National High School | DINGRAS | 2 | 1 | UPGRADING | 2 | 620088.3656 | 604240.9563 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300022 | NUEVA ERA NATIONAL HIGH SCHOOL | NUEVA ERA | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2 | 1 | UPGRADING | 2 | 804898.5191 | 787039.6562 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 500593 | Sacritan IS | PINILI | 2 | 1 | UPGRADING | 2 | 650890.0578 | 634920.9062 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300028 | San Nicolas NHS | SAN NICOLAS | 2 | 1 | UPGRADING | 2 | 727894.2885 | 710980.2812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2 | 1 | UPGRADING | 2 | 774096.8268 | 711620.7812 | COMPLETED | 100% | [6 empty] | 2018-07-08 | 8/22/2018 | 09/20/2018 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100370 | Bantay East CS | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 593540.61 | 588675.89 | COMPLETED | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300038 | Bantay NHS | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 686696.24 | 648431.79 | COMPLETED | 100% | 2018-11-26 | 2018-12-03 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100371 | Bantay West Central School | BANTAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 618227.78 | 589207.33 | COMPLETED | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100372 | Bulag ES | BANTAY | 1 | 1 | UPGRADING | 1 | 379200.22 | 375489.93 | COMPLETED | 100% | 2018-11-09 | 2018-12-03 |  |  | 2018-08-30 |  | 2018-09-06 | 2018-09-07 | 2018-09-10 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300045 | Caoayan NHS | CAOAYAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 986746.23 | 979288.47 | COMPLETED | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300035 | SAN JUAN NHS | SAN JUAN (LAPOG) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1092784.66 | 1085483.84 | COMPLETED | 100% | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 100617 | San Vicente IS | SAN VICENTE | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 808567.21 | 803172.25 | COMPLETED | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300080 | Sinait NHS | SINAIT | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 557523.26 | 534791.41 | COMPLETED | 100% | 2018-11-26 | 2019-03-29 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300063 | Narvacan Nat'l. Central HS | NARVACAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 629893.44 | 624266.05 | COMPLETED | 100% | 2018-11-26 | 2019-03-21 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 320901 | Mabilbila IS | SANTA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 947353.53 | 940831.52 | COMPLETED | 100% | 2018-11-26 | 2018-11-23 |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Ilocos Sur | 300077 | Santa Maria NHS | SANTA MARIA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 887388.59 | 882020.33 | COMPLETED | 100% | 2018-11-26 |  |  |  | 2018-03-15 | 2018-03-21 | 2018-04-04 | 2018-04-16 | 2018-04-30 | RAMSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300106 | Balaoan NHS-Castor Concepcion MNHS | BALAOAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1536816.3 | 1362570.53 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 321018 | LUNA NATIONAL VOCATIONAL HIGH SCHOOL | LUNA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1006982.57 | 891632.77 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300124 | Oanari NHS | LUNA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 969820.67 | 860218.38 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300097 | Balbalayang NHS | SAN GABRIEL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1092741.59 | 968373.08 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union |  | SAN JUAN SENIOR HIGH SCHOOL | SAN JUAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1011563.33 | 894104.76 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1789981.7 | 1780026.31 | COMPLETED | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300090 | Eulogio Clarence De Guzman Junior Memorial National Vocational High School | BAUANG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 956985.36 | 904095.35 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300128 | Paringao NHS | BAUANG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 970724.94 | 917914.02 | COMPLETED | 100% | [9 empty] | JANPAC ENGINEERING & CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300136 | San Gregorio National High School | CABA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1025780.07 | 1019626.69 | COMPLETED | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300091 | Amlang-Nagtagaan NHS | ROSARIO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1163070.09 | 1156233.67 | COMPLETED | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | La Union | 300152 | Tubao National High School | TUBAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1949479.54 | 1938730.64 | COMPLETED | 100% | [9 empty] | NMDC CONSTRUCTION CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Laoag City | 300374 | ILOCOS NORTE NATIONAL HIGH SCHOOL | LAOAG CITY | 1 | 1 | UPGRADING | 2 | 2213609.278 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300158 | Anda National High School | ANDA | 1 | 1 | UPGRADING | 2 | 940466.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 500608 | BANI EAST INTEGRATED SCHOOL | BANI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1238583.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 459052.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1709137.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 500441 | Dasol IS | DASOL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1008247.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | SUAL | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1188525.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300173 | Bocboc East NHS | AGUILAR | 2 | 1 | UPGRADING | 2 | 1180826.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 459052.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan NHS | LINGAYEN (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1301990.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan SAT | LINGAYEN (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1200219.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 923773.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300168 | Bayambang NHS (Bayambang) | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1086061.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan NHS | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 577242.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | BAYAMBANG | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 654297.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1622181.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 954894.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan I, Lingayen | 300237 | Payas NHS | SANTA BARBARA | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 641892.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 815407.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500383 | Mangaldan IS | MANGALDAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1560913.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300326 | Mangaldan National High School | MANGALDAN | 4 | 1 | UPGRADING | 2 | 2534915.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 693500.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300274 | Anonang NHS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 876203.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500006 | San Fabian IS | SAN FABIAN | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 897261.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300321 | Lobong NHS | SAN JACINTO | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 824735.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300348 | San Jacinto National High School | SAN JACINTO | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 808925.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300355 | San Pedro Apartado NHS | ALCALA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 701069.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 820000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300290 | Bobonan National High School | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 827525 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500380 | Dilan Integrated School | POZORRUBIO | 5 | 1 | UPGRADING | 2 | 814693.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300329 | San Pedro Apartado NHS | POZZORUBIO | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 904428.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300279 | Alejandro F. Oligan HS (Asan Sur NHS) | SISON | 5 | 1 | UPGRADING | 2 | 853000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 | 1 | UPGRADING | 2 | 881072.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300284 | Barangobong NHS | VILLASIS | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 682758.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 500385 | DUNGON IS | VILLASIS | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 581796.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | ASINGAN | 6 | 1 | UPGRADING | 2 | 653572.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300281 | Balungao NHS | BALUNGAO | 6 | 1 | UPGRADING | 2 | 874817.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | UPGRADING | 2 | 759129.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300311 | Eugenio P. Perez NHS | POZORRUBIO | 6 | 1 | UPGRADING | 2 | 886391.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300340 | Robert B. Estrella Memorial NHS | ROSALES | 6 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 655749.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | SAN MANUEL | 6 | 1 | UPGRADING | 2 | 921000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | UPGRADING | 2 | 1598495.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1427586.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300379 | Cobol NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 954866.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300380 | COLILING NATIONAL HIGH SCHOOL | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1004365.1075 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300382 | Libas NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1009366.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1187919.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300385 | Malacanang NHS | SAN CARLOS CITY | 3 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1016668.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300389 | Tamayo National High School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1252621.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300390 | Tandoc NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1361537.6706 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 500057 | Tarece Integrated School | SAN CARLOS CITY | 3 | 1 | UPGRADING | 3 | 1996698.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 | 1 | UPGRADING | 2 | 1464095.4917 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 300099 | Bangbangolan NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1328769.3294 | 1189731.25 | COMPLETED | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 500983 | San Fernando City SPED Integrated School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1097980.9423 | 917243.5 | COMPLETED | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 1051360.8415 | 925785.69 | COMPLETED | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING | 2 | 620849.2327 | 541254.44 | COMPLETED | 100% |  |  |  |  | 2018-04-27 | 2018-05-08 | 2018-05-18 | 2018-05-30 | 2018-06-01 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5 | 1 | UPGRADING | 2 | 1068477.85 | 957618.51 | COMPLETED | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300397 | Camabu NHS | CITY OF URDANETA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 847104.78 | 783323.06 | COMPLETED | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 500007 | Catablan IS | CITY OF URDANETA | 5 | 1 | UPGRADING | 2 | 913475.77 | 843045.43 | COMPLETED | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Urdaneta City | 300406 | Nancalobasaan NHS | CITY OF URDANETA | 5 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1006805.78 | 930663.77 | COMPLETED | 100% | 8-16-2018 | 10-15-2018 |  |  | 2018-02-04 | 2018-10-04 | 4-23-2018 | 2018-07-05 | 2018-11-05 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100786 | Burgos Memorial School West | CITY OF VIGAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1258735.11 | 1218637.93 | COMPLETED | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100798 | San Julian ES | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | 1 | 220225.14 | 219081.49 | COMPLETED | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region I | Vigan City | 100800 | Vigan CS | CITY OF VIGAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1032751.73 | 1024505.51 | COMPLETED | 100% |  |  |  |  | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-04-17 | 2018-04-23 | ELKAN Engineering Services and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region II | Batanes | 300415 | Ivana NHS | IVANA | 0 | 1 | UPGRADING | 1 | 1126860.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | 0 | 1 | UPGRADING | 1 | 1095087.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1 | 1 | UPGRADING | 1 | 495971.47 |  | terminated | 29.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 29.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300421 | Alcala Rural School | ALCALA | 1 | 1 | UPGRADING | 1 | 518889.44 |  | terminated | 95% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 95% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1 | 1 | UPGRADING | 1 | 699410.46 |  | terminated | 95% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 95% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300470 | Aparri West National High School | APARRI | 1 | 1 | UPGRADING | 1 | 567838.55 |  | terminated | 95% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 95% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300437 | Bukig National Agr'l. and Tech. School | APARRI | 1 | 1 | UPGRADING | 1 | 730017.81 |  | terminated | 48% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 48% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1 | 1 | UPGRADING | 1 | 634259.39 |  | terminated | 67% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 67% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300429 | Baggao NAS | BAGGAO | 1 | 1 | UPGRADING | 1 | 643414.67 |  | terminated | 10.97% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 10.97% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1 | 1 | UPGRADING | 1 | 589120.28 |  | terminated | 10.97% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 10.97% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 155053 | Cagurungan Primary School | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300432 | Hacienda Intal NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 571264.33 |  | terminated | 10.97% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 10.97% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300433 | Imurung NHS | BAGGAO | 1 | 1 | UPGRADING | 1 | 2011343.55 |  | terminated | 67% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 67% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 102498 | San Antonio ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 1753452.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 102503 | Tabugan ES | BAGGAO | 1 | 1 | SOLAR PANEL | 1 | 559889.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1 | 1 | UPGRADING | 1 | 588020.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300440 | Calaoagan Dackel NHS | GATTARAN | 1 | 1 | UPGRADING | 1 | 637964.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 617102.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1 | 1 | UPGRADING | 1 | 2263197.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 155051 | Laoc Primary School | GONZAGA | 1 | 1 | SOLAR PANEL | 1 | 1846756.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1 | 1 | UPGRADING | 1 | 628809.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | UPGRADING | 1 | 709465.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 306004 | Magapit NHS | LAL-LO | 1 | 1 | UPGRADING | 1 | 515742.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1 | 1 | UPGRADING | 1 | 841324.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300490 | Sta. Teresita NHS | SANTA TERESITA | 1 | 1 | UPGRADING | 1 | 602505.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300473 | Libertad NHS | ABULUG | 2 | 1 | UPGRADING | 1 | 1233921.78 |  | terminated | 60.85% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 60.85% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300424 | Allacapan VHS | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 500065 | Mapurao Integ. Learning School | ALLACAPAN | 2 | 1 | UPGRADING | 1 | 671431.74 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300434 | Ballesteros NHS | BALLESTEROS | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 60.85% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 60.85% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 155040 | Bibigsan PS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 663729.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300441 | Calayan HS | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1478886.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 102586 | Caniwalan ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 1586151.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 | 1 | UPGRADING | 1 | 1688631.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 102593 | Morol ES | CALAYAN | 2 | 1 | SOLAR PANEL | 1 | 930135.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2 | 1 | UPGRADING | 1 | 501909.48 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 2131509.18 |  | terminated | 90% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2 | 1 | UPGRADING | 1 | 1915584.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300497 | Western Cagayan SAT | LASAM | 2 | 1 | UPGRADING | 1 | 1118621.25 |  | terminated | 50.13% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 50.13% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300481 | Piat National HS | PIAT | 2 | 1 | UPGRADING | 1 | 964556.11 |  | terminated | 14.52% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 14.52% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 102854 | Kittag ES | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 527749.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 506644.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING | 1 | 740050.2 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 102862 | Santiago Elementary School | SANCHEZ-MIRA | 2 | 1 | SOLAR PANEL | 1 | 734565.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300489 | Sta. Praxedes HS | SANTA PRAXEDES | 2 | 1 | UPGRADING | 1 | 570762.04 |  | terminated | 69.94% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 69.94% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 306017 | Amulung NHS - Dadda Ext. | AMULUNG | 3 | 1 | UPGRADING | 1 | 1146918.75 |  | terminated | 34.08% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 34.08% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 668475.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3 | 1 | UPGRADING | 1 | 579730.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300459 | Western Enrile Vocational High School | ENRILE | 3 | 1 | UPGRADING | 1 | 824448.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 306421 | CARIDAD B. TRINIDAD NHS | IGUIG | 3 | 1 | UPGRADING | 1 | 612469.14 |  | terminated | 34.08% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 34.08% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300446 | Cabbo NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 599373.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 730602.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | UPGRADING | 1 | 620842.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 300467 | Itawes National High School | TUAO | 3 | 1 | UPGRADING | 1 | 730602.29 |  | terminated | 14.52% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 14.52% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3 | 1 | UPGRADING | 1 | 538676.19 |  | terminated | 14.52% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 14.52% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300492 | Tuao Voc'l. and Tech'l. School | TUAO | 3 | 1 | UPGRADING | 1 | 750245.64 |  | terminated | 5.91% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 5.91% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cagayan | 300493 | Tuao Voc'l. and Tech'l. School - Culung Annex | TUAO | 3 | 1 | UPGRADING | 1 | 532184.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cagayan | 306019 | Tuao Voc'l. and Tech'l. School - Malummin Annex | TUAO | 3 | 1 | UPGRADING | 1 | 505444.28 |  | terminated | 5.91% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 5.91% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 569092.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cauayan City | 103215 | Faustino ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 1416994.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cauayan City | 103241 | Sillawit ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2061137.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cauayan City | 323903 | Villa Concepcion HS - Rogus Ext. | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 348325.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 618992.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Cauayan City | 306107 | WEST TABACAL REGION NATIONAL HIGH SCHOOL | CITY OF CAUAYAN | 3 | 1 | UPGRADING | 1 | 2160530.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | City of Ilagan | 300542 | Isabela NHS - Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 1452300.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | City of Ilagan | 306105 | ISAT-Main | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 3689427.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN (Capital) | 1 | 1 | UPGRADING | 1 | 679654.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300521 | Alfreda Albano NHS - Magassi, Cabagan | CABAGAN | 1 | 1 | UPGRADING | 1 | 1800665.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300522 | Delfin Albano HS - San Juan Annex | CABAGAN | 1 | 1 | UPGRADING | 1 | 1406343.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300520 | Delfin Albano HS-Main | CABAGAN | 1 | 1 | UPGRADING | 1 | 1897430.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103145 | Cabagan Science Elementary School | CABANGAN | 1 | 1 | UPGRADING | 3 | 868239.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306133 | Aneg National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 995822.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306162 | Bayabo Integrated School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 1046855.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103269 | Delfin Albano Central School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 3325977.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 3 | 2637011.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300585 | San Antonio NHS | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | UPGRADING | 1 | 2827752.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 | 1 | UPGRADING | 3 | 2574707.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300554 | Isabela SF | PALANAN | 1 | 1 | SOLAR PANEL | 1 | 2206445.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300601 | St. Paul Voc'l. & Ind'l. HS-Main | SAN PABLO | 1 | 1 | UPGRADING | 1 | 1323322.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300605 | Buenaventura G. Masigan National High School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1382139.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1 | 1 | UPGRADING | 1 | 1646981.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1 | 1 | UPGRADING | 3 | 1992023.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300606 | Sto Tomas NHS | SANTO TOMAS | 1 | 1 | UPGRADING | 1 | 1649011.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103871 | Sto. Tomas Central School | SANTO TOMAS | 1 | 1 | UPGRADING | 3 | 1190764.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300547 | Antagan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2155606.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306153 | Cumabao IS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1451220.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306109 | Fermeldy National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2709258.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300556 | Lalauanan National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2201117.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2321207.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300609 | Tumauini NHS | TUMAUINI | 1 | 1 | UPGRADING | 1 | 1628465.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103884 | Tumauini North Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1896448.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103903 | Tumauini South Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 2222813.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 | 1 | UPGRADING | 3 | 1898495.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103072 | Aurora Central School | AURORA | 2 | 1 | UPGRADING | 3 | 1176056.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103102 | Benito Soliven Central School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1012396.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300503 | Benito Soliven NHS | BENITO SOLIVEN | 2 | 1 | UPGRADING | 1 | 1176226.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500079 | Maluno Integrated School - Main | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1468714.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 896259.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | 3 | 1414672.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103128 | Burgos Central School | BURGOS | 2 | 1 | UPGRADING | 3 | 1153599.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300509 | BURGOS NHS (formerly Caliguian NHS-Main) | BURGOS | 2 | 1 | UPGRADING | 1 | 1414778.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300511 | San Antonino NHS | BURGOS | 2 | 1 | UPGRADING | 1 | 1273274.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103343 | Gamu Central School | GAMU | 2 | 1 | UPGRADING | 3 | 1113294.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300559 | Mabini National High School | GAMU | 2 | 1 | UPGRADING | 3 | 1639894.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 2 | 1 | UPGRADING | 2 | 1218106.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103496 | Mallig Central School - Main | MALLIG | 2 | 1 | UPGRADING | 3 | 1628332.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300561 | Mallig NHS (formerly Mallig NHS - Main) | MALLIG | 2 | 1 | UPGRADING | 1 | 1148985.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306110 | San Jose NHS (formerly Mallig HS -San Jose Norte Annex) | MALLIG | 2 | 1 | UPGRADING | 1 | 1190682.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103520 | Naguilian Central School | NAGUILIAN | 2 | 1 | UPGRADING | 3 | 2080920.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306112 | Barucboc National High School | QUEZON | 2 | 1 | UPGRADING | 3 | 1222637.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103571 | Quezon CS | QUEZON | 2 | 1 | UPGRADING | 3 | 2092542.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300568 | Quezon HS - Main | QUEZON | 2 | 1 | UPGRADING | 1 | 1181729.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500071 | San Juan Integrated School | QUEZON | 2 | 1 | UPGRADING | 3 | 872096.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103580 | Quirino Central School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1860295.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500068 | Villa Cacho Integrated School | QUIRINO | 2 | 1 | UPGRADING | 3 | 1736088.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306111 | Monico Rarama NHS (Munoz HS -San Pedro Extension) | ROXAS | 2 | 1 | UPGRADING | 1 | 1252371.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300562 | Munoz HS | ROXAS | 2 | 1 | UPGRADING | 1 | 1173740.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300579 | Roxas NHS-Main | ROXAS | 2 | 1 | UPGRADING | 1 | 1999770.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 2 | 1 | UPGRADING | 1 | 1218106.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300512 | Callang NHS - Main | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1744759.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300514 | Sandiat NHS | SAN MANUEL | 2 | 1 | UPGRADING | 1 | 1547898.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300593 | Alibadabad National High School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 430415.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500086 | Dicamay Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | 3 | 964475.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | UPGRADING | 2 | 1648463.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300565 | Palayan Region HS | ALICIA | 3 | 1 | UPGRADING | 1 | 1186861.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300576 | Rizal Region NHS , Alicia, Isabela | ALICIA | 3 | 1 | UPGRADING | 1 | 1075486.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300506 | Cadaloria HS | ANGADANAN | 3 | 1 | UPGRADING | 1 | 1049158.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3 | 1 | UPGRADING | 3 | 876175.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300504 | Cabatuan National High School | CABATUAN | 3 | 1 | UPGRADING | 1 | 1929966.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300558 | Luna NHS | LUNA | 3 | 1 | UPGRADING | 1 | 1195227.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103624 | Reina Mercedes Central School | REINA MERCEDES | 3 | 1 | UPGRADING | 3 | 974739.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1432514.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306116 | Reina Mercedes Vocational High School | REINA MERCEDES | 3 | 1 | UPGRADING | 1 | 1116614.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300590 | San Guillermo Voc'l & Ind'l High Sch. | SAN GUILLERMO | 3 | 1 | UPGRADING | 1 | 1074656.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300581 | Salinungan NHS | SAN MATEO | 3 | 1 | UPGRADING | 1 | 1245397.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306143 | Cagasat HS-Magsasay Annex | CORDON | 4 | 1 | UPGRADING | 1 | 813316.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300508 | CAGASAT NHS | CORDON | 4 | 1 | UPGRADING | 1 | 790744.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300523 | Diadi Region HS | CORDON | 4 | 1 | UPGRADING | 1 | 885270.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300532 | Dona Josefa E. Marcos HS | CORDON | 4 | 1 | UPGRADING | 1 | 834063 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300526 | Dinapigue NHS | DINAPIGUE | 4 | 1 | UPGRADING | 1 | 889647.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300529 | Don Mariano Marcos NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 784636.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 | 1 | UPGRADING | 2 | 825152.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300539 | Highway Region NHS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 820545.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300566 | Pangal Sur HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 831472.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300611 | Ugad HS | ECHAGUE | 4 | 1 | UPGRADING | 1 | 1062208.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | UPGRADING | 1 | 1480331.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 103600 | Gen. Aguinaldo ES - Villa Verde PS Annex | RAMON | 4 | 1 | UPGRADING | 3 | 939585.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300572 | Gen. Emilio Aguinaldo NHS | RAMON | 4 | 1 | UPGRADING | 1 | 817580.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300571 | Ramon National High School | RAMON | 4 | 1 | UPGRADING | 2 | 967178.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300574 | Raniag HS | RAMON | 4 | 1 | UPGRADING | 1 | 1184147.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 500092 | San Miguel Integrated School-Main | RAMON | 4 | 1 | UPGRADING | 2 | 1127436.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 306142 | San Sebastian Integrated School | RAMON | 4 | 1 | UPGRADING | 1 | 1149327.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300518 | Dabubu High School Main & Annex | SAN AGUSTIN | 4 | 1 | UPGRADING | 1 | 1145258.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Isabela | 300591 | San Isidro NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 1 | 903294.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | UPGRADING | 1 | 2380840.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | 0 | 1 | UPGRADING | 1 | 4643660.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300635 | Dupax del Norte NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | 1 | 5168669.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | UPGRADING | 1 | 1453392.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104098 | Papalungan ES | KASIBU | 0 | 1 | SOLAR PANEL | 1 | 3440083.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 104114 | Ban-et PS | KAYAPA | 0 | 1 | SOLAR PANEL | 1 | 1377860.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan NHS | KAYAPA | 0 | 1 | UPGRADING | 1 | 2511723.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Nueva Vizcaya | 306204 | Runruno National High School | QUEZON | 0 | 1 | UPGRADING | 1 | 2299961.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 470878.68 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300663 | Pinaripad NHS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 722573.4 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300653 | Victoria HS | AGLIPAY | 0 | 1 | UPGRADING | 1 | 605581.61 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 938805.89 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300664 | Quirino General HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 995383.23 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300666 | Tucod HS | CABARROGUIS (Capital) | 0 | 1 | UPGRADING | 1 | 618440.27 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | UPGRADING | 1 | 865201.89 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | UPGRADING | 1 | 561006.88 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300654 | Balligui HS | MADDELA | 0 | 1 | UPGRADING | 1 | 506369.85 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 306317 | Dumabato Integrated School | MADDELA | 0 | 1 | UPGRADING | 1 | 742761.6 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300660 | Maddela CHS | MADDELA | 0 | 1 | UPGRADING | 1 | 1181950.74 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 306309 | San Martin IS | MADDELA | 0 | 1 | UPGRADING | 1 | 222063.52 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 306310 | GIAYAN INTEGRATED SCHOOL | NAGTIPUNAN | 0 | 1 | SOLAR PANEL | 1 | 2653311.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300662 | Nagtipunan NHS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 687122.84 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 306303 | Sangbay IS | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 350034.81 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 306316 | Scala Integrated School | NAGTIPUNAN | 0 | 1 | UPGRADING | 1 | 759093.07 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | UPGRADING | 1 | 716743.19 |  | COMPLETED | 100% |  |  |  |  | 2018-04-03 | 2018-04-06 | 2018-04-23 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 1974024.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | UPGRADING | 1 | 372407.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300668 | CAGAYAN NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 762912.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300669 | CATAGGAMAN NHS-SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 447205.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 300670 | LINAO NHS - SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 369305.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Tuguegarao City | 306401 | TUGUEGARAO CITY SENIOR HIGH SCHOOL | Tuguegarao City | 0 | 1 | UPGRADING | 1 | 751115.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region II | Tuguegarao City |  | GOSI NHS - SENIOR HIGH SCHOOL | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | 2 | 440825.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | UPGRADING | 1 | 173058.28 | 170000 | COMPLETED | 100% | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 | 1 | UPGRADING | 1 | 173058.28 | 170000 | COMPLETED | 100% | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora |  | Baler Stand Alone | BALER | 0 | 1 | UPGRADING | 1 | 1894542.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) | 0 | 1 | UPGRADING | 1 | 1697974.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300673 | Aurora NHS | BALER (Capital) | 0 | 1 | UPGRADING | 1 | 930975.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306504 | Diagyan NHS | DILASAG | 0 | 1 | UPGRADING | 1 | 1902320 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 | 1 | UPGRADING | 2 | 2077387.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 | 1 | UPGRADING | 1 | 1180594.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 | 1 | UPGRADING | 1 | 1955011.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | 0 | 1 | UPGRADING | 2 | 2064302.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 | 1 | UPGRADING | 1 | 2318025.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300686 | Ditumabo NHS | SAN LUIS | 0 | 1 | UPGRADING | 1 | 1000358.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 | 1 | UPGRADING | 1 | 2758246.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300708 | Luakan National High School | DINALUPIHAN | 1 | 1 | UPGRADING | 1 | 1895363.51 | 1878142.77 | COMPLETED | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | UPGRADING | 2 | 3272047.49 | 3247080.92 | COMPLETED | 100% | 2018-09-07 |  |  |  | April 24, 2018- May 7, 2018 | 2018-05-03 | 2018-05-21 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300719 | Samal NHS | SAMAL | 1 | 1 | UPGRADING | 1 | 1809224.16 | 1791256.13 | COMPLETED | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 | 1 | UPGRADING | 1 | 3559235.68 | 3529388.39 | COMPLETED | 100% | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 306711 | San Francisco Xavier High School | BULACAN | 1 | 1 | UPGRADING | 2 | 5985580.68 | 5060899.37 | COMPLETED | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300755 | San Pedro National High School | HAGONOY | 1 | 1 | UPGRADING | 2 | 3732220.36 | 3342196.08 | COMPLETED | 100% | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300756 | Sta. Monica National High School | HAGONOY | 1 | 1 | UPGRADING | 2 | 3027526.83 | 2768984.18 | COMPLETED | 100% | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 2 | 1 | UPGRADING | 2 | 4117936.44 | 3482904.82 | COMPLETED | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300742 | Guiguinto Nat'l Voc'l. High School | GUIGUINTO | 2 | 1 | UPGRADING | 3 | 6709671.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 | 1 | UPGRADING | 2 | 3003849.46 | 2543748.22 | COMPLETED | 100% | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Cabanatuan City | 301045 | Camp Tinio National High School | CABANATUAN CITY | 3 | 1 | UPGRADING | 2 | 2498371.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT | 1 | 1 | UPGRADING | 1 | 341218.2 |  | COMPLETED | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 306909 | Mabalacat TVS | MABALACAT | 1 | 1 | UPGRADING | 1 | 762937.98 |  | COMPLETED | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 306942 | Santos Ventura NHS | MABALACAT | 1 | 1 | UPGRADING | 1 | 350614.35 |  | COMPLETED | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 345342 | SHS w/in Sapang Biabas ES | MABALACAT | 1 | 1 | UPGRADING | 1 | 745566.71 |  | COMPLETED | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | UPGRADING | 1 | 865728.1 |  | COMPLETED | 100% | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | 1 | 2604906.2 | 2573336.85 | COMPLETED | 100% |  |  | MLL2018-06 | MLL2018-06 |  | 2018-05-31 | 2018-06-22 | 2018-07-10 | 2018-07-18 | LOURBEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 | 1 | UPGRADING | 2 | 686281.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Munoz Science City | 500630 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 | 1 | UPGRADING | 2 | 752305.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 | 1 | UPGRADING | 2 | 378620.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300801 | Cuyapo National High School | CUYAPO | 1 | 1 | UPGRADING | 2 | 346345.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Cuyapo National High School (SHS) | CUYAPO | 1 | 1 | UPGRADING | 2 | 508561.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 | 1 | UPGRADING | 2 | 268199.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | UPGRADING | 2 | 415294.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 | 1 | UPGRADING | 2 | 257461.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300869 | Triala NHS | GUIMBA | 1 | 1 | UPGRADING | 2 | 305424.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1 | 1 | UPGRADING | 2 | 334163.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Eduardo L. Joson Mem. HS (SHS) | QUEZON | 1 | 1 | UPGRADING | 2 | 380604.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 | 1 | UPGRADING | 2 | 463571.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 | 1 | UPGRADING | 2 | 541860.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300865 | Tabacao National High School | TALAVERA | 1 | 1 | UPGRADING | 2 | 648501.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Carmen NHS (SHS) | ZARAGOZA | 1 | 1 | UPGRADING | 2 | 276511.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 | 1 | UPGRADING | 2 | 402027.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Carranglan NHS (SHS) | CARRANGLAN | 2 | 1 | UPGRADING | 2 | 352136.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300870 | Llanera National HIgh School | LLANERA | 2 | 1 | UPGRADING | 2 | 245855.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300866 | Talugtug NHS | TALUGTUG | 2 | 1 | UPGRADING | 2 | 323471.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300816 | Macabaclay National High School | BONGABON | 3 | 1 | UPGRADING | 2 | 197600.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3 | 1 | UPGRADING | 2 | 267018.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300858 | Sto. Rosario NHS , Sta. Rosa | SANTA ROSA | 3 | 1 | UPGRADING | 2 | 299957.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) | 4 | 1 | UPGRADING | 2 | 374333.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300836 | Lambakin National High School | JAEN | 4 | 1 | UPGRADING | 2 | 538124.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300835 | Putlod-San Jose NHS | JAEN | 4 | 1 | UPGRADING | 2 | 532712.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4 | 1 | UPGRADING | 2 | 312976.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | STA. BARBARA NATIONAL HS (SHS) | SAN ANTONIO | 4 | 1 | UPGRADING | 2 | 450566.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300794 | Calaba National High School | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 325560.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300834 | Pulo NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 452449.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 384194.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300817 | Magpapalayok NHS | SAN LEONARDO | 4 | 1 | UPGRADING | 2 | 195151.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4 | 1 | UPGRADING | 2 | 347681.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Olongapo City | 162003 | Iram II ES | OLONGAPO CITY | 1 | 1 | SOLAR PANEL | 1 | 2077391.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA | 1 | 1 | UPGRADING | 1 | 2770962.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 | 1 | UPGRADING | 1 | 529630.83 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307106 | JESUS F. MAGSAYSAY TECHNICAL-VOCATIONAL HIGH SCHOOL | CASTILLEJOS | 1 | 1 | UPGRADING | 1 | 359481.51 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160503 | Chiang Chio Te Mem. Aeta School (Ibad PS) | SAN MARCELINO | 1 | 1 | SOLAR PANEL | 1 | 578540.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301029 | San Guillermo NHS | SAN MARCELINO | 1 | 1 | UPGRADING | 1 | 555871.38 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307112 | Nagyantok HS | SUBIC | 1 | 1 | UPGRADING | 1 | 238791.09 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 | 1 | UPGRADING | 1 | 433078.49 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307124 | Subic NHS Annex IV - San Isidro HS | SUBIC | 1 | 1 | UPGRADING | 1 | 238791.09 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301008 | Baquilan Resettlement High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 289720.92 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 2901396.11 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160523 | Burgos ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 787612.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160504 | Cabatuan ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 813993.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307131 | Lakas High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 229562.69 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | MAGUISGUIS IS | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 940096.27 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 281505 | Moraza Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1979019.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301026 | New Taugtog National High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 302634.44 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 101788 | Owaog-Nebloc Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1963474.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 281503 | Palis Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1790672.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160526 | Poon Bato Elementary School | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 782336.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160515 | Villar ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 782336.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301010 | Cabangan National High School | CABANGAN | 2 | 1 | UPGRADING | 1 | 2678122.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307120 | Pamibian IS | CANDELARIA | 2 | 1 | UPGRADING | 1 | 378399.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301004 | Amungan NHS | IBA (Capital) | 2 | 1 | UPGRADING | 1 | 402537.56 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301037 | Zambales NHS | IBA (Capital) | 2 | 1 | UPGRADING | 1 | 2934885.85 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301005 | Bani NHS | MASINLOC | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301007 | Coto High School | MASINLOC | 2 | 1 | UPGRADING | 3 | 524075.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106884 | Felipe E. Estella Elementary School | MASINLOC | 2 | 1 | UPGRADING | 3 | 502782.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106891 | Inhobol Elementary School | MASINLOC | 2 | 1 | UPGRADING | 3 | 432186.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307103 | San Salvador HS | MASINLOC | 2 | 1 | UPGRADING | 1 | 320002.7 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | TALTAL NHS | MASINLOC | 2 | 1 | UPGRADING | 1 | 439552.69 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 | 1 | UPGRADING | 1 | 391157.45 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301032 | San Miguel NHS | SAN ANTONIO | 2 | 1 | UPGRADING | 1 | 438055.75 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160520 | Banawen PS | SAN FELIPE | 2 | 1 | SOLAR PANEL | 1 | 771783.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | SAN FELIPE | 2 | 1 | UPGRADING | 3 | 562157.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307104 | San Rafael Technical Vocational High School | SAN FELIPE | 2 | 1 | UPGRADING | 3 | 551263.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106975 | Babuyan ES | SANTA CRUZ | 2 | 1 | SOLAR PANEL | 1 | 976746.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | BOLITOC NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 443158.94 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301014 | Guisguis NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 455413.83 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | LIPAY NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 373296.29 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301033 | Sta. Cruz NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 294724.19 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307102 | Sta. Cruz NHS - Jesus F. Magsaysay HS Annex | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 323846.39 |  | COMPLETED | 100% |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 500391 | APIA IS | Antipolo City | 2 | 1 | UPGRADING | 2 | 513838.5906 |  | COMPLETED | 100% |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 109349 | CANUMAY ES | Antipolo City | 2 | 1 | UPGRADING | 2 | 783383.1514 |  | COMPLETED | 100% |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 321502 | Canumay NHS | Antipolo City | 2 | 1 | UPGRADING | 2 | 751744.6159 |  | COMPLETED | 100% |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 109322 | LIBIS ES | Antipolo City | 2 | 1 | UPGRADING | 2 | 778402.4915 |  | COMPLETED | 100% |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Bacoor City | 107867 | Proposed Stand-Alone SHS 5- Bacoor ES | Bacoor City | 2 | 1 | UPGRADING | 1 | 1146067.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301470 | Balete NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 695612.46 | COMPLETED | 100% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301473 | Conde Labac NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855711.74 | 850003.71 | COMPLETED | 100% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855977.1 | 851559.48 | COMPLETED | 100% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 695939.47 | COMPLETED | 100% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 697193.22 | ONGOING | 90% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | DONE Erection of Post for Transformer waiting for the schedule of meralco | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301481 | Tabangao NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855711.74 | 849691.66 | COMPLETED | 100% | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Calamba City | 301515 | Calamba Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | 2 | 2227134.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Calamba City | 301514 | Calamba Bayside Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | 2 | 1863464.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 301166 | Amadeo National High School | AMADEO | 6 | 1 | UPGRADING | 2 | 1591456.9177 | 1554123.06 | COMPLETED | 100% |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 307817 | Tanza Trade NHS | TANZA | 6 | 1 | UPGRADING | 2 | 2324139.6983 | 2259976.58 | COMPLETED | 100% |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 301165 | ALFONSO NATIONAL HIGH SCHOOL | ALFONSO | 7 | 1 | UPGRADING | 2 | 2307918.5169 | 2245684.72 | COMPLETED | 100% |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 301230 | Biñan National High School | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 1581624.3 | 1560549.3 | COMPLETED | 100% | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 307931 | Saint Francis NHS | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 569350.89 | 543300.29 | COMPLETED | 100% | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 607488.83 | 586424.13 | COMPLETED | 100% | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Quezon | 301307 | Camohaguin National High School | GUMACA | 4 | 1 | UPGRADING | 2 | 2607323.41 |  | COMPLETED | 100% | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Quezon | 301386 | San Francisco B NHS | LOPEZ | 4 | 1 | UPGRADING | 2 | 2832509.36 |  | COMPLETED | 100% | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301428 | Bagumbong NHS | JALA-JALA | 2 | 1 | UPGRADING | 2 | 1630063.4 | 1618689.15 | COMPLETED | 100% |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301430 | Bayugo NHS | JALA-JALA | 2 | 1 | UPGRADING | 1 | 1995063.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 308121 | Hulo National High School | PILILLA | 2 | 1 | UPGRADING | 2 | 1136666.03 | 1128753.89 | COMPLETED | 100% |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 308133 | Laiban NHS | TANAY | 2 | 1 | SOLAR PANEL | 1 | 1001553.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301461 | Sto. Niño NHS | TANAY | 2 | 1 | SOLAR PANEL | 1 | 1646492.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301467 | Teresa National High School | TERESA | 2 | 1 | UPGRADING | 2 | 905229.96 | 899714.96 | COMPLETED | 100% |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 301504 | San Pablo City National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | SAN PABLO CITY | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 100% | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TANAUAN CITY | 301133 | Pantay NHS | CITY OF TANAUAN | 3 | 1 | UPGRADING | 1 | 490560.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TANAUAN CITY | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 | 1 | UPGRADING | 1 | 1383834.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TAYABAS CITY | 342576 | STAND ALONE SHS (POTOL) | TAYABAS | 1 | 1 | UPGRADING | 1 | 1306742.55 |  | COMPLETED | 100% | 2018-10-01 |  |  |  | 2018-06-07 | 2018-06-13 | 2018-06-25 | 2018-07-01 | 2018-07-04 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING | 1 | 415231.83 | 392996.4016 | COMPLETED | 100% | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 446113.47 | 423592.7535 | COMPLETED | 100% | 10/25/2018 |  |  | 2018-18 | 07/17/2018 | 07/23/2018 | 08/06/2018 | 08/13/2018 | 08/22/2018 | ETVR TRADING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 109930 | Gaspar ES | GASAN | 0 | 1 | SOLAR PANEL | 1 | 897069.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301557 | Mogpog NCHS | MOGPOG | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 437061.38 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301558 | Mongpong NHS | SANTA CRUZ | 0 | 1 | SOLAR PANEL | 1 | 897069.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301553 | Maranlig National High School | TORRIJOS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 437061.38 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Marinduque | 301556 | Matuyatuya NHS | TORRIJOS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 626955.35 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301583 | Looc National School Of Fisheries | LOOC | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 876671.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301605 | Sta Teresa NHS | MAGSAYSAY | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 562469.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301594 | Paluan NHS | PALUAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 866324.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 817030.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301582 | Paulino Legaspi, Sr. Memorial. NHS | SABLAYAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 852498.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301600 | Central NHS | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 881194.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 301589 | Magsaysay NHS - Mapaya Annex | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 849048.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 308908 | San Jose NAIHS - Mangarin Annex | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 562469.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 869277.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Occidental Mindoro |  | Pinagturilan NHS | SANTA CRUZ | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 824424.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro |  | Anastacio Dela Chica High School | BACO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1517078.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309004 | Puerto Galera NHS | PUERTO GALERA | 1 | 1 | UPGRADING | 1 | 631356.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309035 | Puerto Galera NHS - San Isidro Ext. | PUERTO GALERA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 583660.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1 | 1 | UPGRADING | 1 | 1324535.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2 | 1 | UPGRADING | 2 | 747780.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1384901.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301624 | Cawayan National High School | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 938249.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301625 | Dayhagan NHS | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1343352.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 309005 | Labasan National High School | BONGABONG | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1075277.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301621 | Maujao National High School | BULALACAO (SAN PEDRO) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1494745.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301622 | San Roque NHS | BULALACAO (SAN PEDRO) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1325200.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 908171.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 944527.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110742 | Concepcion ES | AGUTAYA | 1 | 1 | SOLAR PANEL | 1 | 2124271.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1 | 1 | SOLAR PANEL | 1 | 2509183.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. NHS | AGUTAYA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1244774.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301662 | Araceli NHS | ARACELI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1348153.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301678 | Calandagan NHS | ARACELI | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1856418.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309134 | Cheey NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1436313.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309167 | Concepcion NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1415684.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301711 | New Busuanga NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1629060.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301734 | Salvacion NHS | BUSUANGA | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1764088.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 1443595.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110965 | Calusa ES | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 2429697.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | SOLAR PANEL | 1 | 2080947.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110973 | Banuang Daan ES | CORON | 1 | 1 | SOLAR PANEL | 1 | 859977.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1426067.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 110979 | Cabugao ES | CORON | 1 | 1 | SOLAR PANEL | 1 | 966266.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301684 | Coron SOF | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1653895.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309168 | Decalachao NHS | CORON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1246826.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301687 | Culion Sanitarium Special NHS | CULION | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1374419.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301688 | Cuyo NHS | CUYO | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1278597.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301691 | Dumaran NHS | DUMARAN | 1 | 1 | SOLAR PANEL | 1 | 1319944.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301740 | Santa Teresita NHS | DUMARAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1419892.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301737 | San Miguel NHS (Gaudencio Abordo NHS) | LINAPACAN | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1411416.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301689 | Danawan NHS | MAGSAYSAY | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1246964.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111155 | Maragoc ES | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 1942556.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 170512 | Ramon Gacayan Elementary School | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 1970006.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111166 | Salvador ES | ROXAS | 1 | 1 | SOLAR PANEL | 1 | 2576686.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 111223 | Casian ES | TAYTAY | 1 | 1 | SOLAR PANEL | 1 | 2928722.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301682 | Casian NHS | TAYTAY | 1 | 1 | SOLAR PANEL | 1 | 4966964.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301666 | Balabac NHS | BALABAC | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1502475 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309113 | Bancalaan National High School | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 3065598.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309127 | Sibaring NHS | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 730635 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309149 | Taburi NHS | BALABAC | 2 | 1 | SOLAR PANEL | 1 | 1202985 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309129 | Southern Bataraza NHS | BATARAZA | 2 | 1 | SOLAR PANEL | 1 | 2374815 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309126 | Tarusan NHS | BATARAZA | 2 | 1 | SOLAR PANEL | 1 | 3048165 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301727 | Quezon-Aramaywan NHS | QUEZON | 2 | 1 | SOLAR PANEL | 1 | 2594910 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301729 | Quinlogan NHS | QUEZON | 2 | 1 | SOLAR PANEL | 1 | 2221050 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309160 | Canipaan NHS | RIZAL | 2 | 1 | SOLAR PANEL | 1 | 2070300 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 309146 | Panalingaan NHS | RIZAL | 2 | 1 | SOLAR PANEL | 1 | 2107485 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301680 | Candawaga NHS | RIZAL (MARCOS) | 2 | 1 | SOLAR PANEL | 1 | 1402980 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Palawan | 301719 | Panitian National High School | SOFRONIO ESPAÑOLA | 2 | 1 | UPGRADING | 1 | 1430115 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301785 | Buenavista Annex | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 462343.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111510 | Buenavista ES | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 472895.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 770482.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301781 | Cabayugan NHS | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 1506969.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111467 | East Central School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 2493419.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301782 | Inagawan NHS | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1125863.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS - Matahimik - Bucana Annex | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 919823.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 301785 | Macarascas NHS - Buenavista Annex | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 826086.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111520 | Makirawa Elementary School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 462343.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City |  | Mandaragat - San Miguel Senior HS | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1472587.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 2779446.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309301 | PALAWAN NATIONAL SCHOOL | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 6802283.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 111470 | Puerto Princesa Pilot ES | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 3735812.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 770482.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309302 | Simpucan NHS (Napsan NHS - Simpucan Annex) | Puerto Princesa City | 3 |  | UPGRADING | 2 | 1509331.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 | 1 | SOLAR PANEL | 2 | 590961.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 309303 | Tagabinet High School | Puerto Princesa City | 3 |  | SOLAR PANEL | 2 | 946895.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Puerto Princesa City | 300400 | Ubaldo L. Conde High School | Puerto Princesa City | 3 | 1 | UPGRADING | 2 | 1070770.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1836679.92 | 1811342.4 | Terminated | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 80% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301755 | Cambalo NHS | CAJIDIOCAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1461469.76 | 1409881.03 | Terminated | 90% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301753 | Lumbang East National High School | CAJIDIOCAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1231361.43 | 1204491.32 | Terminated | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 80% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 309201 | Calatrava NHS | CALATRAVA | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1323540.82 | 1269933.37 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301757 | Corcuera NHS | CORCUERA | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1282934.39 | 1261369.12 | Terminated | 80% | 2019-01-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 80% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301761 | Ferrol National High School | FERROL | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1565256.73 | 1479621.63 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301769 | Odiongan, National High School | ODIONGAN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 2144933.9 | 1997168.88 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 309205 | Carmen NHS (Cabolutan NHS Ext.) | SAN AGUSTIN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1374449.99 | 1324624.29 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1515602.48 | 1488591.8 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1416442.65 | 1340420.86 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301763 | Sta. Fe NHS | SANTA FE | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1464802.14 | 1405144.61 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1707966.77 | 1647944.34 | Terminated | 90% | 2019-05-10 |  |  |  | 2018-05-14 | 2018-05-21 | 2018-06-11 | 2018-07-16 | 2018-08-06 | 6 Jewels Construction |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | ENERGIZATION |  | ongrid | Terminated
ELECTRIFICATION 2018 | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 871922.87 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2011470.98 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City |  | Zamboanga Norte NHS - Miputak Campus | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 443826.29 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City |  | Zamboanga Norte NHS - Turno Campus | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 875609.79 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 4706721.6 |  | COMPLETED | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 2098158.43 |  | COMPLETED | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 314601 | Isabela City NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 939814.63 |  | COMPLETED | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303895 | Malamawi National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 1155357.27 |  | COMPLETED | 100% | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126086 | Banale ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 637234.95 | 633785.58 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126037 | Bogo ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 616609.25 | 611977.36 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126060 | Bulatok ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 709967.65 | 702771.47 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 314705 | Co Tek Chun National Trade School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1470348.25 | 1462436.82 | COMPLETED | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126039 | Danlugan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 690065.67 | 683848.14 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 964515.41 | 956340.56 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303901 | Lala National High School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1297232.37 | 1290162.54 | COMPLETED | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303904 | Manga NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1284604.6 | 1277620.44 | COMPLETED | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 724441.83 | 719003.36 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 314702 | Norberta Guillar NHS (Napolan NHS - Norberta Guillar Mem. School Ext.) | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1483030.63 | 1475015.43 | COMPLETED | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303908 | Pagadian City NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 1614991.95 | 1595444.32 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 683190.44 | 675872.5 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126052 | San Pedro Central Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 802766.55 | 798127.74 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126079 | Sta. Lucia Central Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 847998.33 | 840631.43 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City |  | Stand Alone - Zamboanga del Sur NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2660165.92 | 2645388.69 | COMPLETED | 100% | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1542244.33 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 762798.38 | 754866.03 | COMPLETED | 100% |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303915 | Ayala NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 2010000 | 1788937.91 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 345869 | Baliwasan Senior High School | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 904500 | 738378.12 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 314805 | Recodo NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 838517.37 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303933 | Southcom NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 847456.17 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303935 | Talisayan NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 814771.02 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303918 | Bunguiao NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 629391.63 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303928 | Manicahan NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 628909.03 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303929 | Mercedes NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 1005000 | 919671.2 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303936 | Tictapul NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 627582.12 | COMPLETED | 100% | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1 | 1 | UPGRADING | 1 | 636254.46 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 | 1 | UPGRADING | 1 | 640017.36 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124561 | Piñan CS | PIÑAN (NEW PIÑAN) | 1 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124579 | Polanco CS | POLANCO | 1 | 1 | UPGRADING | 1 | 637379.23 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124597 | Silawe CS | POLANCO | 1 | 1 | UPGRADING | 1 | 637379.23 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124610 | Rizal CS | RIZAL | 1 | 1 | UPGRADING | 1 | 640017.36 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124671 | San Isidro CS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING | 1 | 643710.73 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124651 | Sergio Osmeña CS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING | 1 | 641600.23 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | UPGRADING | 1 | 641072.61 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124335 | Ponot CS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124369 | Katipunan CS | KATIPUNAN | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124396 | Taga CS | KATIPUNAN | 2 | 1 | UPGRADING | 1 | 634829.87 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124524 | Gupot ES | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124510 | Manukan East CS | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124511 | Manukan West CS | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124495 | Dohinob CS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124488 | Roxas CS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124701 | Siayan CS | SIAYAN | 2 | 1 | UPGRADING | 1 | 637930.59 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124778 | Juan Bugarin CS | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124802 | Mandih CS | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124278 | Godod CS | GODOD | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124417 | Labason CS | LABASON | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124463 | Baybay CS | LILOY | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124454 | Liloy CS | LILOY | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124625 | Bacong CS | SALUG | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124623 | Salug CS | SALUG | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124830 | Siocon CS | SIOCON | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 100% | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1 | 1 | UPGRADING | 1 | 1060275 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1 | 1 | UPGRADING | 1 | 974850 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 | 1 | UPGRADING | 1 | 1015050 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125030 | Mate ES | DUMINGAG | 1 | 1 | UPGRADING | 1 | 547725 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 | 1 | UPGRADING | 1 | 547725 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 | 1 | UPGRADING | 1 | 1206000 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 345844 | LABANGAN SENIOR HIGH SCHOOL | LABANGAN | 1 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125183 | Lactayan ES | MAHAYAG | 1 | 1 | UPGRADING | 1 | 874350 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125190 | Pilas ES | MAHAYAG | 1 | 1 | UPGRADING | 1 | 407025 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | UPGRADING | 1 | 1125600 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303817 | Sominot NHS | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | UPGRADING | 1 | 849225 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1 | 1 | UPGRADING | 1 | 1100475 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303757 | Bayog NHS | BAYOG | 2 | 1 | UPGRADING | 1 | 1075350 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 124920 | Deporehan IES | BAYOG | 2 | 1 | UPGRADING | 1 | 532650 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 196004 | Lower Conacon ES | BAYOG | 2 | 1 | UPGRADING | 1 | 351750 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303770 | Dimataling NHS | DIMATALING | 2 | 1 | UPGRADING | 1 | 994950 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303771 | Dinas NHS | DINAS | 2 | 1 | UPGRADING | 1 | 1097460 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 124983 | Sumilom PS | DINAS | 2 | 1 | UPGRADING | 1 | 593250 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303778 | Guipos NHS | GUIPOS | 2 | 1 | UPGRADING | 1 | 1085400 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125104 | Mapao CPS | KUMALARANG | 2 | 1 | UPGRADING | 1 | 331650 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314249 | Poblacion Comprehensive NHS | LAKEWOOD | 2 | 1 | UPGRADING | 1 | 1100475 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303823 | Tubod NHS | LAKEWOOD | 2 | 1 | UPGRADING | 1 | 974850 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125152 | Cubo ES | LAPUYAN | 2 | 1 | UPGRADING | 1 | 407025 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314261 | Lapuyan National High School - Maralag Extension | LAPUYAN | 2 | 1 | UPGRADING | 1 | 530250 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125161 | Mahalingeb PS | LAPUYAN | 2 | 1 | UPGRADING | 1 | 362250 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303783 | Kalian NHS | MARGOSATUBIG | 2 | 1 | UPGRADING | 1 | 859275 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303804 | Paulino Dari NHS | PITOGO | 2 | 1 | UPGRADING | 1 | 829125 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 | 1 | UPGRADING | 1 | 854250 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303813 | San Pablo NHS | SAN PABLO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Ext. | SAN PABLO | 2 | 1 | UPGRADING | 1 | 672000 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303768 | Tabina NHS | TABINA | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303800 | Nilo NHS | TIGBAO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303782 | Kabatan NHS | VINCENZO A. SAGUN | 2 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 100% | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309515 | Malilipot NHS | MALILIPOT | 1 | 1 | UPGRADING | 1 | 2106133.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301871 | San Antonio NHS, Malilipot | MALILIPOT | 1 | 1 | UPGRADING | 1 | 1155364.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309505 | San Francisco NHS | MALILIPOT | 1 | 1 | UPGRADING | 1 | 1005974.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 111639 | Baligang ES | CAMALIG | 2 | 1 | UPGRADING | 1 | 6161438.9 |  | REVERTED | 0% | [10 empty] | no sub-aro downloaded | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region V | Albay | 301813 | Batan National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1868547.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309509 | Bilbao National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1482133.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301884 | Mancao National High School | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1595786.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 309519 | Tinopan HS | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1570749.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301882 | Villahermosa NHS | RAPU-RAPU | 2 | 1 | UPGRADING | 1 | 1709022.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 111965 | Alabangpuro ES | PIO DURAN | 3 | 1 | UPGRADING | 1 | 1374646.64 |  | REVERTED | 0% | [10 empty] | no downloaded fund | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region V | Albay | 309503 | Alabangpuro High School | PIO DURAN | 3 | 1 | UPGRADING | 2 | 1374646.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3 | 1 | UPGRADING | 1 | 1496125.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1 | 1 | UPGRADING | 1 | 3939736.92 | 3913595.4 | COMPLETED | 100% | 2018-07-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | UPGRADING | 1 | 2492745.53 | 2468080.15 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | UPGRADING | 1 | 1656810.17 | 3631385.71 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301922 | Tulay Na Lupa NHS | LABO | 1 | 1 | UPGRADING | 1 | 3649542.64 | 1642239.75 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1 | 1 | UPGRADING | 1 | 2626785.92 | 2596870.62 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301910 | Paracale NHS | PARACALE | 1 | 1 | UPGRADING | 1 | 2634173.86 | 2608327.86 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301889 | Basud NHS | BASUD | 2 | 1 | UPGRADING | 1 | 7013018.85 | 6963077.23 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301906 | Moreno Integrated School | DAET (Capital) | 2 | 1 | UPGRADING | 1 | 3642946.55 | 3606232.35 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | UPGRADING | 1 | 2523429.7 | 2495864 | COMPLETED | 100% | 2018-07-01 |  |  |  | 2018-02-28 |  | 2018-03-21 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301988 | Lupi-Iligan HS | LUPI | 1 | 1 | UPGRADING | 1 | 2261423.66 | 1969455.26 | COMPLETED | 100% | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301929 | Simeon Tycangco MHS | RAGAY | 1 | 1 | UPGRADING | 1 | 2549977.63 | 2251366.66 | COMPLETED | 100% | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301930 | Sisa Feliciano MHS | RAGAY | 1 | 1 | UPGRADING | 1 | 2083426.75 | 1717914.86 | COMPLETED | 100% | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309743 | Bolo Norte HS | SIPOCOT | 1 | 1 | UPGRADING | 1 | 2657221.68 | 2323637.87 | COMPLETED | 100% | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309767 | Manangle High School | SIPOCOT | 1 | 1 | UPGRADING | 1 | 1015428.28 | 961058.46 | COMPLETED | 100% | 1/17/2019 | 2019-10-01 |  | 2018-10-036 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301935 | Bahao HS | LIBMANAN | 2 | 1 | UPGRADING | 1 | 2174993.93 | 1894351.47 | COMPLETED | 100% | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | UPGRADING | 1 | 2474177.75 | 2296519.86 | COMPLETED | 100% | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309745 | Northern Plain HS | LIBMANAN | 2 | 1 | UPGRADING | 1 | 1247131.89 | 1147671.47 | COMPLETED | 100% | 1/19/2019 | 1/14/2019 |  | 2018-10-038 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | UPGRADING | 1 | 1947146.05 | 1936318.45 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302025 | Sagrada Familia High School | MINALABAC | 2 | 1 | UPGRADING | 1 | 2033467.72 | 2020150.3 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1852571.57 | 1839633.71 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302032 | Maura N. Sibulo National HS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1852571.57 | 1840158.72 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309732 | Dr. Lorenzo P. Ziga MHS | PASACAO | 2 | 1 | UPGRADING | 1 | 1886881.46 | 1870097.06 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301965 | Rolando R. Andaya, Sr. MHS | PASACAO | 2 | 1 | UPGRADING | 1 | 1293794.83 | 1284175.86 | COMPLETED | 100% | 1/19/2019 | on-going |  | 2018-10-037 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309707 | Siembre HS | BOMBON | 3 | 1 | UPGRADING | 1 | 1096756.47 | 1089277.69 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302053 | Sulpicio A. Roco MHS | BOMBON | 3 | 1 | UPGRADING | 1 | 1585526.55 | 1577100.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309735 | Northern Canaman HS | CANAMAN | 3 | 1 | UPGRADING | 1 | 1622289.56 | 1610170.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301957 | Doroteo Federis, Sr. NHS (frmerly: Carangcang HS) | MAGARAO | 3 | 1 | UPGRADING | 1 | 1351201.39 | 1340545.39 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302034 | Magarao NHS (formerly: San Isidro NHS) | MAGARAO | 3 | 1 | UPGRADING | 1 | 2031906.68 | 2020570.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301946 | Binanuaanan NHS | PILI (Capital) | 3 | 1 | UPGRADING | 1 | 2223308.53 | 2200190.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302017 | Gov.Mariano E. Villafuerte HS | PILI (Capital) | 3 | 1 | UPGRADING | 1 | 1913337.83 | 1901222.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302054 | Tabgon HS, Goa | GOA | 4 | 1 | UPGRADING | 1 | 1372217.91 | 1363063.5 | COMPLETED | 100% | 1/25/2019 | on-going |  | 2018-10-039 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309768 | Cabotonan High School | LAGONOY | 4 | 1 | UPGRADING | 1 | 688543.69 | 657566.44 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301963 | Dahat National Vocational HS | LAGONOY | 4 | 1 | UPGRADING | 1 | 1291895.7 | 1141972.43 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302039 | San Ramon Pilot NHS, Lagonoy (frmerly:Sn.Ramon Pilot HS) | LAGONOY | 4 | 1 | UPGRADING | 1 | 1914501.56 | 1531284.58 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309708 | Catalotoan HS | SAGÑAY | 4 | 1 | UPGRADING | 1 | 876848.61 | 871188.51 | COMPLETED | 100% | 1/19/2019 |  |  | 2018-10-040 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309714 | Dr. Rodolfo V. Pamor MHS - Sagñay Southeastern Annex HS | SAGÑAY | 4 | 1 | UPGRADING | 1 | 1968881.53 | 1951156.85 | COMPLETED | 100% | 1/19/2019 |  |  | 2018-10-040 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309753 | Salogon HS | SAN JOSE | 4 | 1 | UPGRADING | 1 | 1614124.45 | 1298414.41 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309771 | Villafuerte-Peña High School | SAN JOSE | 4 | 1 | UPGRADING | 1 | 1176699.96 | 1042098.45 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301984 | Vivencio Obias - Kinalansan NHS (formerly: Kinalansan NHS) | SAN JOSE | 4 | 1 | UPGRADING | 1 | 3138071.77 | 2994583.84 | COMPLETED | 100% | 1/19/2019 | 2019-09-01 |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301986 | La Salvacion NHS | TIGAON | 4 | 1 | UPGRADING | 1 | 2413979.33 | 2393533.47 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309766 | San Rafael National High School - Cabalinadan Annex HS | TIGAON | 4 | 1 | UPGRADING | 1 | 1459235.29 | 1448397.7 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302029 | Tinawagan NHS | TIGAON | 4 | 1 | UPGRADING | 1 | 2198602.27 | 2183966.34 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-041 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | UPGRADING | 1 | 1335674.46 | 1326372.24 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5 | 1 | UPGRADING | 1 | 881608.32 | 875269.53 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302014 | Pararao HS | BALATAN | 5 | 1 | UPGRADING | 1 | 1558409.79 | 1546681.07 | COMPLETED | 100% | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5 | 1 | UPGRADING | 1 | 1826170.87 | 1810585 | COMPLETED | 100% | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302059 | Tapayas HS | BALATAN | 5 | 1 | UPGRADING | 1 | 1339454.4 | 1331418.75 | COMPLETED | 100% | 1/25/2019 | 8/31/2019 |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 309746 | Payak HS | BATO | 5 | 1 | UPGRADING | 1 | 1375160.28 | 1366978.29 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5 | 1 | UPGRADING | 1 | 1791228.85 | 1778610.22 | COMPLETED | 100% | 1/25/2019 |  |  | 2018-10-042 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/25/2018 | CARINA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5 | 1 | UPGRADING | 1 | 1395935.08 | 1301496.18 | COMPLETED | 100% | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301982 | Inoyonan HS | BULA | 5 | 1 | UPGRADING | 1 | 1527923.25 | 1312067.77 | COMPLETED | 100% | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5 | 1 | UPGRADING | 1 | 945965.75 | 858981.7 | COMPLETED | 100% | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Camarines Sur | 301992 | Tandaay Provincial HS | NABUA | 5 | 1 | UPGRADING | 1 | 1219125.3 | 1140672.11 | COMPLETED | 100% | 1/19/2019 | 1/17/2018 |  | 2018-10-043 | 2018-07-08 |  | 2018-10-09 | 2018-01-10 | 10/19/2018 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302101 | Sicmil IS | GIGMOTO | 0 | 1 | UPGRADING | 1 | 1251978.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 309802 | Cobo IS | PANDAN | 0 | 1 | UPGRADING | 1 | 1496144.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES (CALOLBON) | 0 | 1 | UPGRADING | 1 | 2069243.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES (CALOLBON) | 0 | 1 | UPGRADING | 1 | 1955914.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | UPGRADING | 1 | 2230044.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Iriga City | 343238 | San Agustin Senior High School | IRIGA CITY | 5 | 1 | UPGRADING | 1 | 1224536.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Legaspi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2771096.04 | 2716466.89 | COMPLETED | 100% | 2018-09-15 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Legaspi City | 302261 | Pag-asa NHS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | 1 | 3313445.5 | 3106673.93 | COMPLETED | 100% | 2018-09-10 |  |  |  | 2018-04-12 | 2018-04-20 | 2018-05-02 | 2018-05-18 | 2018-05-21 | ZAREPATH Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | UPGRADING | 2 | 2588654.65 | 2250000 | COMPLETED | 100% | 9/24/2018 |  |  | DO LIGAO 04-05-2018 | 2018-04-23 | 2018-05-02 | 2018-05-17 | 2018-06-29 | 2018-07-04 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3 | 1 | UPGRADING | 2 | 3548375.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302121 | Buenavista National High School | USON | 3 | 1 | UPGRADING | 2 | 2529306.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3 | 1 | UPGRADING | 2 | 3394197.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3 | 1 | UPGRADING | 2 | 1346259.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 302133 | Capitolina O. Legaspi Memorial High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 1228060.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 113695 | Jose Zurbito Sr. Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 3 | 1472274.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 3621816.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Masbate City |  | Masbate National Comprehensive High School Annex-Senior High School | CITY OF MASBATE (Capital) | 2 | 1 | UPGRADING | 2 | 1220272.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302197 | Casiguran Technical Vocational School | CASIGURAN | 1 | 1 | UPGRADING | 2 | 2652600.35 | 2112236.92 | COMPLETED | 100% | 2018-10-16 | [7 empty] | 2018-06-26 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | UPGRADING | 2 | 1681856.55 | 1340119.31 | COMPLETED | 100% | 2018-10-16 | [7 empty] | 2018-06-26 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES | 1 | 1 | UPGRADING | 2 | 1534901.95 | 1340000 | COMPLETED | 100% | 2018-11-19 | [7 empty] | 2018-08-01 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302220 | Magallanes National Vocational HS | MAGALLANES | 1 | 1 | UPGRADING | 2 | 1546296.31 | 1400426.11 | COMPLETED | 100% | 2018-11-19 | [7 empty] | 2018-07-27 | JERA Gen. Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302184 | Barcelona National Comprehensive HS | BARCELONA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1501127.63 | 1418661.93 | COMPLETED | 100% | Sept. 22, 2018 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302190 | Bulan NHS | BULAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1980291.25 | 1650000 | COMPLETED | 100% | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302214 | Gubat NHS | GUBAT | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1447611.59 | 1152240.71 | COMPLETED | 100% | Sept. 22, 2018 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302212 | Gallanosa National High School | IROSIN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1766634.29 | 1410046.01 | COMPLETED | 100% | 2018-10-03 | [7 empty] | 2018-07-17 | Riderscorner Construction & General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302186 | Biriran NHS | JUBAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1317882.11 | 1120000 | COMPLETED | 100% | Sept. 22, 2018 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302187 | Juban National High School | JUBAN | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 881760.7 | 750000 | COMPLETED | 100% | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 967339.2 | 825000 | COMPLETED | 100% | 2018-10-03 | [7 empty] | 2018-07-17 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 988154.78 | 934630.94 | COMPLETED | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 656937.92 | 650397.97 | COMPLETED | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302272 | MERCEDES B. PERALTA SENIOR HIGH SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 1351069.37 | 1337619.24 | terminated | 40% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Zarepath | Terminated due to lapse of fund | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 40% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 1 | 1153525.17 | 1097641.39 | COMPLETED | 100% | October 31, 2018 |  |  |  |  | April 25, 2018 | May 7, 2018 |  |  | Riders Corner |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1 | 1 | UPGRADING | 2 | 1818648.95 | 1799599.67 | terminated | 40% | [9 empty] | Zarepath | Terminated due to lapse of fund | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 40% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | UPGRADING | 2 | 6729139.42 | 6007162.8 | COMPLETED | 100% | 2018-12-17 | 2018-12-17 |  |  | 2018-05-18 |  | 2018-07-12 |  | Sept. 9, 2018 | Zarepath Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 0 | 1 | UPGRADING | 2 | 1493310.87 | 1479478.88 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302286 | ALTAVAS NATIONAL SCHOOL | ALTAVAS | 0 | 1 | UPGRADING | 1 | 1828613.6343 | 1817691.55 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302288 | LINAYASAN NHS | ALTAVAS | 0 | 1 | UPGRADING | 1 | 1054537.9176 | 1048040.97 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500170 | AGUINALDO T. REPIEDAD, Sr. INTEGRATED SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1334452.73 | 1325969.03 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302289 | BACAN NATIONAL HIGH SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1252893.42 | 1244975.31 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302338 | TORRALBA NATIONAL HIGH SCHOOL | BANGA | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080649.5 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302291 | BATAN ACADEMY (A NAT'L SCH.) | BATAN | 0 | 1 | UPGRADING | 1 | 1081899 | 1080649.5 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302294 | BAY-ANG MAGPAG-ONG NHS | BATAN | 0 | 1 | UPGRADING | 1 | 1170314.3204 | 1163311.24 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302301 | CAMANCI NATIONAL HIGH SCHOOL | BATAN | 0 | 1 | UPGRADING | 1 | 1054537.9176 | 1048224.4 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302333 | RIZAL J. RODRIGUEZ Sr. NATIONAL HIGH SCHOOL | BATAN | 0 | 1 | UPGRADING | 1 | 1071776.59 | 1065266.16 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302297 | BURUANGA VOCATIONAL SCHOOL | BURUANGA | 0 | 1 | UPGRADING | 1 | 1433471.0093 | 1424067.78 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302330 | IBAJAY NATIONAL HIGH SCHOOL | IBAJAY | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080649.5 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302321 | NAILE NHS | IBAJAY | 0 | 1 | UPGRADING | 1 | 1170314.3204 | 1163244.61 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302322 | NAISUD NATIONAL HIGH SCHOOL | IBAJAY | 0 | 1 | UPGRADING | 1 | 1087308.49 | 1080648.45 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | 2 | 1559325.69 | 1549237.27 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-20 | HOVERT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302332 | REGIONAL SCIENCE HIGH SCHOOL FOR REGION VI | KALIBO (Capital) | 0 | 1 | UPGRADING | 1 | 1076755.992 | 1070325.88 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500171 | LEZO INTEGRATED SCHOOL | LEZO | 0 | 1 | UPGRADING | 1 | 1334452.7327 | 1326561.92 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500181 | DALAGSAAN INTRGRATED SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 689097.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302311 | GUADALUPE NHS | LIBACAO | 0 | 1 | UPGRADING | 1 | 1180866.8204 | 1173499.96 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302310 | LIBACAO NFVHS | LIBACAO | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245178.92 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114791 | MAYTARAW PRIMARY SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 558245.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114800 | TAROYTOY PRIMARY SCHOOL | LIBACAO | 0 | 1 | SOLAR PANEL | 1 | 778090.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302315 | MADALAG NHS | MADALAG | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080811.72 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302305 | ANSELMO B. LEGASPI NHS | MAKATO | 0 | 1 | UPGRADING | 1 | 1054537.92 | 1047441.42 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500172 | MAKATO IS | MAKATO | 0 | 1 | UPGRADING | 1 | 1499637.911 | 1490537.95 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 0 | 1 | UPGRADING | 2 | 1424551.34 | 1416036.31 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 0 | 1 | UPGRADING | 2 | 1340741.03 | 1332392.44 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114850 | Malay Elementary School | MALAY | 0 | 1 | UPGRADING | 2 | 1375101.76 | 1366795.3 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 310611 | Manocmanoc National High School | MALAY | 0 | 1 | UPGRADING | 2 | 1424551.34 | 1416037.9 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302317 | MALAY NHS | MALAY | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245413.07 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302319 | MALINAO SFPC | MALINAO | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245399.42 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114887 | Nabas ES | NABAS | 0 | 1 | UPGRADING | 2 | 1359273.01 | 1346335.63 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302302 | CANDELARIA NHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1245100.04 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-05-29 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 0 | 1 | UPGRADING | 2 | 1359273.01 | 1346585.61 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302303 | NEW WASHINGTON NCHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1252893.4202 | 1244985.81 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302328 | OCHANDO NHS | NEW WASHINGTON | 0 | 1 | UPGRADING | 1 | 1087308.492 | 1080248.4 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500035 | NUMANCIA IS | NUMANCIA | 0 | 1 | UPGRADING | 1 | 1433471.0093 | 1424990.47 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 302327 | NUMANCIA NSOF | NUMANCIA | 0 | 1 | UPGRADING | 1 | 1334452.7327 | 1326239.93 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500183 | JAWILI INTEGRATED SCHOOL | TANGALAN | 0 | 1 | UPGRADING | 1 | 988371.02 | 982463.37 | COMPLETED | 100% |  |  |  |  | 2018-06-07 | 2018-06-14 | 2018-06-26 | 2018-07-09 | 2018-08-28 | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Aklan | 500173 | TAMALAGON INTEGRATED SCHOOL | TANGALAN | 0 | 1 | UPGRADING | 1 | 1071776.59 | 1065192.94 | COMPLETED | 100% |  |  |  |  | 2018-02-21 | 2018-02-28 | 2018-03-10 | 2018-04-11 | 2018-06-19 | Micro-asia builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302361 | Igpalge NHS | ANINI-Y | 0 | 1 | UPGRADING | 1 | 1473366.6544 | 1098409.6 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302376 | San Roque-Ezpeleta NHS | ANINI-Y | 0 | 1 | UPGRADING | 1 | 763541.358 | 737317.19 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302346 | Barbaza NHS | BARBAZA | 0 | 1 | UPGRADING | 1 | 1574739.8 | 1142078.54 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302347 | Belison NS | BELISON | 0 | 1 | UPGRADING | 1 | 1893925.7549 | 1511206.51 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302368 | Northern Bugasong NHS | BUGASONG | 0 | 1 | UPGRADING | 1 | 1167437.5 | 872394.36 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310709 | Northern Bugasong NHS Annex - Pangalcagan Campus | BUGASONG | 0 | 1 | UPGRADING | 1 | 1180187.63 | 867967.43 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302379 | Southern Bugasong NHS | BUGASONG | 0 | 1 | UPGRADING | 1 | 1232482 | 1150672.42 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302348 | Bitadton NHS | CULASI | 0 | 1 | UPGRADING | 1 | 1560551.4094 | 1063790.67 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302349 | Buhang NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1468090.4044 | 1099736.23 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1552046.0944 | 1099736.23 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302358 | Gov. Julio V. Macuja MCHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1528613.09 | 1213982.18 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302356 | Governor Julian Fullon Pacificador National School | HAMTIC | 0 | 1 | UPGRADING | 2 | 1540311.71 | 1079396.57 | COMPLETED | 100% | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310701 | Guintas NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1576380.1594 | 1102389.47 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302366 | Moscoso-Rios NHS | HAMTIC | 0 | 1 | UPGRADING | 1 | 1644507.0994 | 1099736.23 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302351 | Col. Ruperto Abellon NHS | LAUA-AN | 0 | 1 | UPGRADING | 1 | 1654631.47 | 1185529.48 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310708 | Eastern Laua-an NHS (Maria NHS) | LAUA-AN | 0 | 1 | UPGRADING | 2 | 1555222.1 | 1172199.65 | COMPLETED | 100% | August 24, 2018 |  | R6-D2-2018BEFF-06A-E | R6-D2-2018BEFF-06A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Elaectrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302362 | Laua-an NHS | LAUA-AN | 0 | 1 | UPGRADING | 1 | 1546769.8444 | 1063973.99 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | UPGRADING | 1 | 1975998.14 | 1439565.2 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | UPGRADING | 1 | 1557322.3444 | 1073165.07 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302365 | Mag-aba NHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1543540.7794 | 1063790.67 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302369 | Pandan NVHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1844124.87 | 1331376.2 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302372 | Patria NS | PANDAN | 0 | 1 | UPGRADING | 1 | 1229855.65 | 918108.34 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | UPGRADING | 1 | 1494471.6544 | 1205431.84 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05D-E | R6-D2-2018BEFF-05D-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302343 | Aureliana NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 1459585.0894 | 999701.27 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302359 | Igburi NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 832310.3157 | 668041.78 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302364 | Lirio M. Escaño, Sr. NHS | PATNONGON | 0 | 1 | UPGRADING | 1 | 1329218.7011 | 1299724.65 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302375 | San Pedro NHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | 1 | 1457911.07 | 1133633.31 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05B-E | R6-D2-2018BEFF-05B-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302344 | Barangbang NHS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 1528253.2 | 1094086.08 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302357 | Gideon M. Cabigunda MS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 700909.9822 | 597725.96 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310707 | Gov. Evelio B. Javier MNHS | SAN REMIGIO | 0 | 1 | UPGRADING | 1 | 949316.1463 | 797834.36 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302377 | Sebaste HS | SEBASTE | 0 | 1 | UPGRADING | 1 | 1457911.07 | 1095657.93 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310710 | Dr. Luis E. Baraquia NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 634046.1785 | 549869.52 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302354 | Egaña NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 693745.6283 | 617849.38 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302370 | Pangpang NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 673996.0322 | 614584.85 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302373 | Pis-anan NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 1303808.4367 | 1071547.63 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310703 | Sibalom NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 1653380.373 | 1374861.34 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302378 | Sido-San Juan NHS | SIBALOM | 0 | 1 | UPGRADING | 1 | 610902.0933 | 489178.33 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05E-E | R6-D2-2018BEFF-05E-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302381 | Sta. Justa NHS | TIBIAO | 0 | 1 | UPGRADING | 1 | 1488330.0994 | 1057724.39 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 310702 | Tario Lim MHS | TIBIAO | 0 | 1 | UPGRADING | 1 | 1695162.5 | 1270558.12 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05F-E | R6-D2-2018BEFF-05F-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302345 | Barasanan NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1506206.0344 | 1098596.17 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1581682.35 | 1206038.48 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302353 | Diclum NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1166834.99 | 946551.84 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302360 | Igcado NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1379634.7568 | 1028762.01 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302371 | Pascual M. Osuyos MS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | 1 | 1327737.5618 | 1029816.89 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05A-E | R6-D2-2018BEFF-05A-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Antique | 302384 | Valderrama NHS | VALDERRAMA | 0 | 1 | UPGRADING | 1 | 1046325.6906 | 985225.09 | COMPLETED | 100% | October 23, 2018 |  | R6-D2-2018BEFF-05C-E | R6-D2-2018BEFF-05C-E | April 25, 2018 | May 2, 2018 | May 16, 2018 | May 30, 2018 | June 20, 2018 | Prefer Electrical Engineering & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1243711.98 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1198382.95 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1183857.74 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VI | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1102366.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1200557.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1043874.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | UPGRADING | 1 | 699622.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1099930.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 | 1 | UPGRADING | 1 | 684142.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 817515.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1529330.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | SOLAR PANEL | 1 | 1476567.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310802 | Dao National High School | DAO | 1 | 1 | UPGRADING | 1 | 577012.2934 | 570121.48 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115553 | Cabungahan Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115554 | Canapian ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115555 | Carataya ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115552 | Dominador T. Esmeralda ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115557 | East Villaflores ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302412 | East Villaflores NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 491147.8672 | 487116.68 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115558 | Fernandez ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302404 | Florentina B. Degala NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 577012.2934 | 570093.12 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115560 | Ilawod Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115561 | Indayagan PS | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115562 | Jebaca ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115563 | Maalan Primary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115564 | Maayon ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 849437.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302413 | Maayon NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 1169728.0681 | 1162433.4 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115565 | Manayupit ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 570194.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115566 | New Guia ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 794739.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115567 | Old Guia PS | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115568 | Palaguian ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115569 | Parallan Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115570 | Piña ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 570194.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115571 | Quevedo ES (ngalan es) | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115572 | Quinabonglan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 932922.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115573 | Quinat-uyan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115574 | Salgan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115575 | Tapulang Elementary School | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115576 | Tepacla ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115577 | Tuburan ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302403 | Tuburan NHS | MA-AYON | 1 | 1 | UPGRADING | 1 | 487575.6349 | 483682.9 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115578 | West Villaflores ES | MA-AYON | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302395 | Comsr. Luis R. Asis NHS | PANAY | 1 | 1 | UPGRADING | 1 | 487575.6349 | 483682.9 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302398 | Felix Balgos MNHS | PANAY | 1 | 1 | UPGRADING | 1 | 660495.2314 | 654695.2 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302410 | Leodegario D. Deocampo Sr. NHS | PANITAN | 1 | 1 | UPGRADING | 1 | 641705.0278 | 611148.81 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot1 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1 | 1 | UPGRADING | 1 | 645277.2601 | 611969.72 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302392 | Casanayan NHS | PILAR | 1 | 1 | UPGRADING | 1 | 745160.4082 | 740395.36 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302400 | Dulangan NHS | PILAR | 1 | 1 | UPGRADING | 1 | 660495.2314 | 654695.2 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302419 | Marciano M. Patricio (Pilar) | PILAR | 1 | 1 | UPGRADING | 1 | 800353.36 | 791538.42 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | CAPIZ | 302422 | San Nicolas NHS (Pilar) | PILAR | 1 | 1 | UPGRADING | 1 | 745160.4082 | 738002.63 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | UPGRADING | 1 | 491147.8672 | 487116.68 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302405 | Hipona NHS | PONTEVEDRA | 1 | 1 | UPGRADING | 1 | 748732.6405 | 743800.76 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302420 | Pontevedra NHS | PONTEVEDRA | 1 | 1 | UPGRADING | 1 | 658113.7432 | 652424.93 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302388 | Cabugcabug NHS | PRESIDENT ROXAS | 1 | 1 | UPGRADING | 1 | 665249.7025 | 659227.04 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115713 | Cubay-Ibaca ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115711 | DOMINGO M. LOCSIN ES (CABUGCABUG) | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115714 | Goce ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115715 | Madulano ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115716 | Manoling ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115717 | Marita ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115718 | Pandan ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115719 | Pondol ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115720 | Pres. Roxas East ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 904134.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115721 | Pres. Roxas West Elementary School | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115722 | Quiajo ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 656557.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115723 | Sangkal ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115724 | Vedasto T. Javellosa ES | PRESIDENT ROXAS | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 359385.49 | 297233.15 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-01 | R6-DepEd-Capiz-CY2018-Electrification-Lot2 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115416 | Bun-od Primary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 511754.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115417 | Carataya ES (cuartero) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115418 | Cuartero CES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302396 | Cuartero NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 896942.9884 | 890528.4 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115419 | Lunayan E/S | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115420 | Mahabang Sapa PS | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115421 | Mahunodhunod ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115422 | Maindang Elementary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310804 | Maindang NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 460476.3928 | 454038.44 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115423 | Mainit Elementary School | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115424 | Malagab-i ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115425 | Nagba ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115426 | Putian ES | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302421 | Putian NHS | CUARTERO | 2 | 1 | UPGRADING | 1 | 920469.9982 | 911404.75 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115427 | San Antonio ES (Cuartero) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 708376.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310808 | SAN ANTONIO NATIONAL HIGH SCHOOL | CUARTERO | 2 | 1 | UPGRADING | 1 | 720451.1596 | 711055.12 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115428 | SINABSABAN ELEMENTARY SCHOOL | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 653679.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302385 | Arturo Jugo NHS | DAO | 2 | 1 | UPGRADING | 1 | 593486.4343 | 568081.08 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302415 | Luis Escutin NHS | DAO | 2 | 1 | UPGRADING | 1 | 575821.5493 | 568986.35 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302414 | MALONOY NATIONAL HIGH SCHOOL (DAO) | DAO | 2 | 1 | UPGRADING | 1 | 722824.1425 | 713297.85 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-03 | R6-DepEd-Capiz-CY2018-Electrification-Lot3 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115441 | Manhoy ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 682466.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115442 | Mapulang Bato Primary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 540542.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115443 | Matagnop Elementary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115436 | Nicanor Escutin ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 765952.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115446 | Quinayuya Elementary School | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 598981.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 115447 | Tabuc ES | DAO | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 737164.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302401 | Concepcion Castro Garcia NHS (Dumalag NHS) Sta. Cruz | DUMALAG | 2 | 1 | UPGRADING | 1 | 661685.9755 | 655830.34 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310806 | Dumalag Central NHS | DUMALAG | 2 | 1 | UPGRADING | 1 | 886226.2915 | 877667.33 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302386 | Bungsuan NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 743969.6641 | 733287.85 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302402 | Estefania Montemayor NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 833406.3226 | 822785.16 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302416 | Manuel F. Onato NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 751114.1287 | 740041.9 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310814 | Presentacion Diez Gregorio NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 745160.4082 | 734413.53 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302417 | Ramon A. Benjamin Sr. NHS | DUMARAO | 2 | 1 | UPGRADING | 1 | 632196.7399 | 627717.72 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-04 | R6-DepEd-Capiz-CY2018-Electrification-Lot4 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310807 | Basiao NHS (formerly Ext. of Ivisan NHS) | IVISAN | 2 | 1 | UPGRADING | 1 | 829834.0903 | 819408.14 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | UPGRADING | 1 | 835787.8108 | 825036.51 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302408 | Jagnaya NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 665258.2078 | 659235.74 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302409 | Jamindan NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 671211.9283 | 659558.6 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302411 | Lucero NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 666448.9519 | 660370.87 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302407 | Macario Delfin Bermejo NHS | JAMINDAN | 2 | 1 | UPGRADING | 1 | 834605.572 | 823919.46 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302397 | David Moises MHS | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 889798.5238 | 881044.35 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310813 | Mambusao East NHS (ext. of David Moises) | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 883844.8033 | 875415.98 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310805 | MAMBUSAO NATIONAL HIGH SCHOOL | MAMBUSAO | 2 | 1 | UPGRADING | 1 | 890989.2679 | 882170.02 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310810 | Lonoy National High School | SAPI-AN | 2 | 1 | UPGRADING | 1 | 749774.8687 | 727257.71 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302424 | Sapian National High School | SAPI-AN | 2 | 1 | UPGRADING | 1 | 1228794.2095 | 1198341.71 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310815 | Mianay NHS | SIGMA | 2 | 1 | UPGRADING | 1 | 718069.6714 | 708803.77 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302399 | Vicente Andaya Sr. NHS | SIGMA | 2 | 1 | UPGRADING | 1 | 575821.5493 | 564432.92 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-05 | R6-DepEd-Capiz-CY2018-Electrification-Lot5 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310801 | Bagong Barrio NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302389 | Camburanan NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302390 | Candelaria NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 574630.8052 | 563307.25 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 311705 | Candelaria NHS- Roxas Ext. | TAPAZ | 2 | 1 | UPGRADING | 1 | 631014.5011 | 621557.81 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302393 | Col. Patrocinio Artuz NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | CAPIZ | 310809 | REV. TOMAS CONEJAR NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 302423 | San Nicolas NHS (Tapaz) | TAPAZ | 2 | 1 | UPGRADING | 1 | 575821.5493 | 568986.35 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Capiz | 310803 | Tapaz NHS | TAPAZ | 2 | 1 | UPGRADING | 1 | 578203.0375 | 571256.62 | COMPLETED | 100% | 2018-11-22 |  | R6-DepEd-Capiz-CY2018-Electrification-06 | R6-DepEd-Capiz-CY2018-Electrification-Lot6 | 2018-04-03 | 2018-04-10 | 2018-06-13 | 2018-07-11 | 2018-07-18 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | UPGRADING | 1 | 1141365.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Guimaras | 310901 | Ayangan National High School | SIBUNAG | 0 | 1 | UPGRADING | 1 | 3911646.12 | 3,660,995.52 | COMPLETED | 100% | Sept. 30, 2018 |  | 02-2018 -lot 1 |  | March 12, 2018 | April 3, 2018 | April 3, 2018 | April 18, 2018 | May 18, 2018 | Noe's Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302445 | Alejandro Firmeza MNHS | MIAGAO | 1 | 1 | UPGRADING | 1 | 3134244.08 | 3084214.84 | COMPLETED | 100% | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L1 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302531 | Miagao NHS | MIAGAO | 1 | 1 | UPGRADING | 1 | 4841253.95 | 4742100 | COMPLETED | 100% | 2018-11-06 | 2019-01-19 | R06-022-BEFF2918Electrification-B1-L2 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-18 | 2018-07-02 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302585 | Zarraga National High School | ZARRAGA | 2 | 1 | UPGRADING | 2 | 4863807.6433 | 4618492.77 | COMPLETED | 100% | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L1 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302514 | Jose Facultad MNHS | POTOTAN | 3 | 1 | UPGRADING | 1 | 2447822.13 | 4649551.37 | COMPLETED | 100% | 2019-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B1-L3 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302556 | Pototan National Comprehensive High School | POTOTAN | 3 | 1 | UPGRADING | 1 | 4063058.75 | 4012805.88 | COMPLETED | 100% | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L4 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4 | 1 | UPGRADING | 1 | 4136526.85 | 4100834.58 | COMPLETED | 100% | 2018-11-10 | 2019-03-29 | R06-022-BEFF2918Electrification-B1-L5 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-25 | 2018-07-06 | Direct Electriix Equiptment Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4 | 1 | UPGRADING | 1 | 3496108.79 | 3431471.35 | COMPLETED | 100% | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L6 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302490 | Dingle NHS | DINGLE | 4 | 1 | UPGRADING | 1 | 4041949.4 | 3991552.18 | COMPLETED | 100% | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L7 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 311008 | Rufino G. Palabrica, Sr. NHS | DINGLE | 4 | 1 | UPGRADING | 1 | 3116337.49 | 3066013.4 | COMPLETED | 100% | 2018-10-23 | 2018-10-31 | R06-022-BEFF2918Electrification-B1-L8 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-05-24 | 2018-06-18 | Culasi General merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302443 | Ajuy NHS | AJUY | 5 | 1 | UPGRADING | 2 | 4791597.203 | 4726996.64 | COMPLETED | 100% | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L2 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5 | 1 | UPGRADING | 2 | 4712460.5419 | 4649551.64 | COMPLETED | 100% | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L3 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5 | 1 | UPGRADING | 1 | 2546414.24 | 2514225.65 | COMPLETED | 100% | 2018-12-18 | 2018-12-20 | R06-022-BEFF2918Electrification-B1-L9 |  | 2018-03-01 | 2018-03-14 | 2018-03-27 | 2018-07-18 | 2018-08-13 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5 | 1 | UPGRADING | 2 | 5410620.46 | 5357379.26 | COMPLETED | 100% | 2018-01-02 | 2018-12-06 | R06-022-BEFF2918Electrification-B2-L4 |  | 2018-06-05 | 2018-06-13 | 2018-06-26 | 2018-09-03 | 2018-09-20 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | 0 | 1 | UPGRADING | 1 | 4475369.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1242920.54 | 1233763.67 | COMPLETED | 100% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1289994.35 | 1279684.23 | COMPLETED | 100% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1079432.83 | 1070675.04 | COMPLETED | 100% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117877 | Calabasahan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 524506.15 | 518045.22 | COMPLETED | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 735237.11 | 729079.2 | COMPLETED | 100% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1062593.61 | 1053919.59 | COMPLETED | 100% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1189719.39 | 1179653.73 | COMPLETED | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1121839.62 | 1111632.05 | COMPLETED | 100% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1470360.01 | 1459657.31 | COMPLETED | 100% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1235574.22 | 1222832.52 | COMPLETED | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117860 | Inapoy ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1118972.87 | 1107188.35 | COMPLETED | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117862 | Linao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 610781.59 | 602926.46 | COMPLETED | 100% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1524238.54 | 1510168.12 | COMPLETED | 100% | September 13,2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1674056.79 | 1661209.91 | COMPLETED | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117864 | Matama ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 886082.7 | 874897.42 | COMPLETED | 100% | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 739363.37 | 730730.71 | COMPLETED | 100% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117890 | Pacao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 823203.85 | 812381.19 | COMPLETED | 100% | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117867 | Pinaguinpinan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1405408.16 | 1393914.58 | COMPLETED | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1178458.45 | 1169522.29 | COMPLETED | 100% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1211309.76 | 1203264.7 | COMPLETED | 100% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 777804.47 | 771434.8 | COMPLETED | 100% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1125610.39 | 1113766.43 | COMPLETED | 100% | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117894 | Talubangi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1294087.86 | 1283512.02 | COMPLETED | 100% | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1066144.14 | 1058821.3 | COMPLETED | 100% | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1015085.74 | 1006648.06 | COMPLETED | 100% | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 2109898.02 | 2090797.87 | COMPLETED | 100% | September 13, 2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 8,2018 | Micro-asia Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 302801 | Tapi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1141365.67 | 1132714.04 | COMPLETED | 100% | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Kabankalan City | 117872 | Yanog ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 477986.55 | 471075.51 | COMPLETED | 100% | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 5285721.3 | 4974653.02 | COMPLETED | 100% |  |  | 5460136 | 18-09-013 | July 3, 2018 | July 11, 2018 | August 20, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3764775.05 | 3721032.46 | COMPLETED | 100% |  |  | 5460154 | 18-09-014 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3817604.51 | 3788330.6 | COMPLETED | 100% |  |  | 5605695 | 18-10-015 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 | 1 | UPGRADING | 1 | 5241938.17 | 5205258.47 | COMPLETED | 100% |  |  | 5605347 | 18-10-014 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | UPGRADING | 1 | 1274910.45 | 1249959.61 | COMPLETED | 100% |  |  | 5463534 | 18-09-017 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | UPGRADING | 1 | 3382586.69 | 3346741.14 | COMPLETED | 100% |  |  | 5460097 | 18-09-012 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | UPGRADING | 1 | 3817604.51 | 3780045.51 | COMPLETED | 100% |  |  | 5463520 | 18-09-016 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 473564.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 | 1 | SOLAR PANEL | 1 | 614377.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | UPGRADING | 1 | 5608104.57 | 5180471.84 | COMPLETED | 100% |  |  | 5460162 | 18-09-015 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | UPGRADING | 1 | 3745342.73 | 3461829.73 | COMPLETED | 100% |  |  | 5460063 | 18-09-011 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | UPGRADING | 1 | 2814054.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 612976.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 180521 | Dung-I ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | UPGRADING | 1 | 4406315.1 | 4372766.4 | COMPLETED | 100% |  |  | 5605736 | 18-10-016 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 875895.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1491653.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Passi City | 302806 | Efraim M. Santibanez National High School | CITY OF PASSI | 4 | 1 | UPGRADING | 1 | 3134244.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302755 | Bago NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 547749.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302756 | Balijuagan NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 578369.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 869082.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117652 | Barra ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 950120.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 978658.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117654 | Culasi ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 955368.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117667 | Don Amando Bayot, Sr. MS | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 869435.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 988944.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117656 | Don Ynocencio del Rosario MS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 579912.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 580044.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117685 | Lawa-an ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1104086.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117686 | Loctugan ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 986563.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311703 | Marcos Fuentes IS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 607797.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302760 | Milibili NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 578369.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117661 | Pres. Manuel Roxas MS - North | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 889037.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117662 | Pres. Manuel Roxas MS - South | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 890228.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 311702 | Roxas City School for Philippine Craftsmen | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 679412.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 500195 | Sofronio A. Cordovero Integrated School | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 913755.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 302761 | Tanque NHS | ROXAS CITY (Capital) | 1 | 1 | UPGRADING | 1 | 579559.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Roxas City | 117689 | Venancio Alba ES | ROXAS CITY (Capital) | 1 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 884274.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1191398.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302764 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302766 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1495260.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 311803 | Sagay NHS-Lopez Jaena Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 311802 | Sagay NHS-Rizal Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1271236.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1225112.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117759 | Gigalaman ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1793278.34 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2019 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117761 | Handalago ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1144542.09 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2020 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117778 | Lagha Elementary School - Extension | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 917691.67 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2021 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117797 | Pagbatangan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 3955732.52 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2022 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117798 | Paniagan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 928296.67 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2023 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1577032.92 |  | COMPLETED | 100% |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2018 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1678512.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1226572.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1223049.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VI | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | UPGRADING | 2 | 4612008.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | UPGRADING | 1 | 4097269.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bais City | 303216 | Bais City Science NHS | BAIS CITY | 2 | 1 | UPGRADING | 1 | 1627597.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | UPGRADING | 1 | 2638984.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | UPGRADING | 1 | 1435064.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1877651.65 | 1863296.59 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1499669.73 | 1487208.28 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | UPGRADING | 1 | 2410027.97 | 2393026.79 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120111 | Cabigti-an ES | BASAY | 3 | 1 | UPGRADING | 1 | 1813292.52 | 1768728.41 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1379975.04 | 1368108.92 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321911 | Abundio Agarpao, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1936621.59 | 1926822.56 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321908 | Antonio M. Lacson, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1725381.18 | 1716527.19 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321907 | Atilano B. Cabangal MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1286681.59 | 1275279.59 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321901 | Banaybanay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2306773.75 | 2290297.1 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321902 | Bayawan City Science HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1428522.8 | 1413910.11 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 4287728.97 | 4258888.02 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303238 | Bugay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2286399.4 | 2267516.46 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120146 | Canabuan PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1572433.82 | 1520756.68 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2168858.4 | 2157882.93 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303227 | Dawis NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2208937.86 | 2190447.83 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120150 | Guintana-an ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1216320.41 | 988325.04 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120153 | Hag-um PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 642505.31 | 435345.98 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2682519.69 | 2639904.02 | COMPLETED | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303237 | Kalumboyan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1920492.43 | 1905937.13 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120158 | Kangkawit PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1379061.37 | 1369638.42 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120131 | Kasla ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 767286.51 | 670969.06 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321905 | Lapay High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1992340.81 | 1974928.47 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 120159 | Lunoy Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1254280.16 | 1162458.67 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2560876.57 | 2514873.29 | COMPLETED | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303240 | Manduaw NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2623847.79 | 2582259.02 | COMPLETED | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321903 | Minaba HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1941999.9 | 1924840.35 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 232003 | Napo ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1260825.01 | 1109689.97 | COMPLETED | 100% |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303254 | Narra HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1881799.15 | 1872104.64 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303256 | Omod National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1559432.94 | 1551470.34 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321910 | Pagatban HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1892234.94 | 1877816.51 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321906 | San Jose HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1431785.89 | 1417162.97 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303241 | Tabuan PCHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2814862.39 | 2795857.65 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 303242 | Tayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2662911.37 | 2642161.1 | COMPLETED | 100% |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bayawan City | 321904 | Villasol HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1464300.14 | 1455818.07 | COMPLETED | 100% |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | UPGRADING | 2 | 2041601.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302850 | Fatima NHS | CORTES | 1 | 1 | UPGRADING | 1 | 934429.73 | 928930.49 | COMPLETED | 100% |  |  |  | 2018-INFRA-034 | 2018-07-30 | 2018-08-07 | 2018-08-20 | 2018-10-25 | Sept. 5, 2018 | MEGABLUE KONTRAK CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | UPGRADING | 1 | 2927879.56 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | UPGRADING | 1 | 1170845.23 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | UPGRADING | 1 | 1272128.36 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1 | 1 | UPGRADING | 1 | 2100247.26 | 2085170.52 | COMPLETED | 100% |  |  |  | 2018-INFRA-034 | 2018-07-30 | 2018-08-07 | 2018-08-20 | 2018-10-25 | 2018-09-05 | MEGABLUE KONTRAK CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | UPGRADING | 1 | 1841339.03 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | UPGRADING | 1 | 1831127.71 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | UPGRADING | 1 | 2244438.83 |  | COMPLETED | 100% | [9 empty] | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | UPGRADING | 1 | 2190473.84 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | UPGRADING | 1 | 1473448.07 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | UPGRADING | 1 | 1480446.26 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | UPGRADING | 1 | 1598514.16 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | UPGRADING | 1 | 1705970.03 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 1174611.91 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 312309 | JAPER Memorial High Shoool | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 1478617.91 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 2050773.44 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | UPGRADING | 2 | 1740854.71 | 1455092.1 | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | UPGRADING | 1 | 1998749.2 |  | COMPLETED | 100% | [9 empty] | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302816 | Biabas Trade High School | UBAY | 2 | 1 | UPGRADING | 1 | 1390322.41 |  | COMPLETED | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2 | 1 | UPGRADING | 1 | 1568580.44 |  | COMPLETED | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | UPGRADING | 1 | 2030908.29 |  | COMPLETED | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302914 | Union NHS | UBAY | 2 | 1 | UPGRADING | 1 | 1471889.96 |  | COMPLETED | 100% | [9 empty] | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | UPGRADING | 1 | 2241906.13 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302810 | Ambassador Pablo R. Suarez, Jr. NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 1064141.97 |  | COMPLETED | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 2806151.62 |  | COMPLETED | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN | 3 | 1 | UPGRADING | 1 | 1112355.22 |  | COMPLETED | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 312339 | Ponciano F. Ramasola Sr. High School | CARMEN | 3 | 1 | UPGRADING | 1 | 1294081.44 |  | COMPLETED | 100% | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | UPGRADING | 2 | 995481.66 | 855231.3 | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | UPGRADING | 2 | 1023687.84 | 834545.25 | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | UPGRADING | 1 | 2898887.62 |  | COMPLETED | 100% | [9 empty] | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302848 | Dusita High School | SIERRA BULLONES | 3 | 1 | UPGRADING | 1 | 1031990.82 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | UPGRADING | 1 | 2750227.21 |  | COMPLETED | 100% | [9 empty] | RONNYL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | UPGRADING | 1 | 2980751.81 |  | COMPLETED | 100% | [9 empty] | LTS BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2347731.87 | 2217698.26 | COMPLETED | 100% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CAN-ASUJAN NATIONAL HIGH SCHOOL (Lot 1) | 2018-eloectrification-carcar-lot1 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2031404 | 1873580.29 | COMPLETED | 100% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CARCAR CENTRAL NATIONAL HIGH SCHOOL (Lot 2) | 2018-eloectrification-carcar-lot2 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2770566.64 | 2327102.41 | COMPLETED | 100% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ MAXIMINO NOEL MEMORIAL NATIONAL HIGH SCHOOL (Lot 3) | 2018-eloectrification-carcar-lot3 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 1975444.19 | 1660698.44 | COMPLETED | 100% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ OCAÑA NATIONAL HIGH SCHOOL (Lot 4) | 2018-eloectrification-carcar-lot4 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2010499.34 | 1896106.26 | COMPLETED | 100% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL (Lot 5) | 2018-eloectrification-carcar-lot5 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 324904 | Tuyom National High School | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2089088.32 | 1743738.88 | COMPLETED | 100% | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ TUYOM NATIONAL HIGH SCHOOL (Lot 6) | 2018-eloectrification-carcar-lot7 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Carcar City | 303126 | Valencia VOCATIONAL NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2344712.74 | 2215627.09 | COMPLETED | 100% | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ VALENCIA VOCATIONAL NATIONAL HIGH SCHOOL (Lot 7) | 2018-eloectrification-carcar-lot6 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | UPGRADING | 2 | 1133120.63 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | UPGRADING | 2 | 955332.52 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 2 | 1 | UPGRADING | 2 | 1374105.86 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302928 | Balao NHS | BARILI | 3 | 1 | UPGRADING | 1 | 1282976.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | UPGRADING | 1 | 2547911.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 2 | 2647612.01 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 1 | 1250231.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 2 | 1337053.81 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | UPGRADING | 1 | 1244277.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303048 | San Agustin NHS | MADRIDEJOS | 4 | 1 | UPGRADING | 2 | 1413045.85 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | UPGRADING | 2 | 1600155.61 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303027 | Medellin National Science and Technology School | MEDELLIN | 4 | 1 | UPGRADING | 2 | 841720.41 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 500220 | Anapog IS | San Remegio | 4 | 1 | UPGRADING | 1 | 1347045.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 500221 | Busogon IS | San Remegio | 4 | 1 | UPGRADING | 1 | 1067155.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303030 | Lambusan NHS | SAN REMIGIO | 4 | 1 | UPGRADING | 1 | 1518405.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO | 4 | 1 | UPGRADING | 2 | 828800.91 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303046 | Luyang NHS | SAN REMIGIO | 4 | 1 | UPGRADING | 2 | 1237904.04 |  | COMPLETED | 100% | [9 empty] | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1792226.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303107 | Campusong NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1730711.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1751641.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | UPGRADING | 1 | 2388626.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | UPGRADING | 1 | 2468951.37 | 2448368.96 | COMPLETED | 100% |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-04 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-04 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302979 | Ceferino Sususco MNHS | CATMON | 5 | 1 | UPGRADING | 1 | 2525970.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | UPGRADING | 1 | 1541167.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | UPGRADING | 1 | 2018447.79 | 1995402.85 | COMPLETED | 100% |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303062 | Mulao NHS | COMPOSTELA | 5 | 1 | UPGRADING | 1 | 1428334.68 | 1413806.38 | COMPLETED | 100% |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 312407 | Arcelo Memorial National Night High School | LILOAN | 5 | 1 | UPGRADING | 2 | 456948.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302954 | Cabangahan NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1381008.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302988 | Consolacion NHS - Day Class | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1740293.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302989 | Consolacion NHS - Evening Class | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1593451.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 303010 | Garing NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 2014254.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302992 | Tolotolo NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 622369.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302993 | Tugbongan NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1130749.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | UPGRADING | 1 | 1284016.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303152 | Barrio Luz NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1358540.5692 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303136 | Busay National High School | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 492928.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 510261.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303139 | Lahug NHS (Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1386454.8506 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 390803.7096 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 995711.3531 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303137 | Paril NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 383685.6969 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2120006.304 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303134 | Bonbon NHS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 324999.5883 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303143 | Bulacao Community HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 465552.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1057985.3984 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1980550.9437 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303145 | Inayawan National High School | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1079973.4794 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303159 | Pardo NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 864341.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 858364.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | City of Naga, Cebu | 303120 | Tuyan National High School | CITY OF NAGA | 0 | 1 | UPGRADING | 2 | 1130846.69 |  | COMPLETED | 100% | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | City of Naga, Cebu | 303121 | Uling National High School | CITY OF NAGA | 0 | 1 | UPGRADING | 2 | 1361639.32 |  | COMPLETED | 100% | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | UPGRADING | 2 | 1877921.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Dumaguete City | 303168 | Dumaguete City HS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1552683.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Dumaguete City | 303169 | RTPM - Dumaguete Science HS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 821230.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 836109.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Guihulngan City | 120239 | Busay Elementary School | CITY OF GUIHULNGAN | 1 | 1 | SOLAR PANEL | 1 | 938136.67 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 1657858.69 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 1382422.08 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 2259021.5 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Guihulngan City | 120258 | Trinidad ES | CITY OF GUIHULNGAN | 1 | 1 | SOLAR PANEL | 1 | 1866055.02 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 1934925.66 | 1913070.65 | COMPLETED | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303177 | Lo-ok National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 1823236.74 | 2237468.87 | COMPLETED | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 2250748.96 | 1813193.79 | COMPLETED | 100% | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 1191779.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 923407.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 1196363.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | UPGRADING | 1 | 586439.48 | 580894.29 | terminated | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 50% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312949 | Ayungon Science High School | AYUNGON | 1 | 1 | UPGRADING | 1 | 484435.16 | 479852.65 | terminated | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 50% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | UPGRADING | 1 | 627304.52 | 621371.36 | terminated | 50% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 50% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303276 | Tambo National High School | AYUNGON | 1 | 1 | UPGRADING | 2 | 590808.68 | 587371.98 | terminated | 32% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 32% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 616259.07 | 610118.41 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303229 | Demetrio Alviola NHS - Nalundan Annex | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 457294.38 | 452742 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 2 | 1125370.28 | 1119476.6 | terminated | 34% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 34% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303251 | Manjuyod National High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 1027398.05 | 1009106.87 | COMPLETED | 100% | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312961 | Manjuyod Science High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 466436.24 | 461791.5 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 | 1 | UPGRADING | 1 | 596480.44 | 588081.49 | COMPLETED | 100% | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303255 | Negros Oriental High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 2 | 643928.75 | 634357.53 | terminated | 45% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 45% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659054.43 | 652943.57 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 577903.93 | 571012.457 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2 | 1 | UPGRADING | 2 | 637792.52 | 640485.86 | terminated | 47% | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 47% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312924 | Campanun-an Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 576820.9 | 570934.14 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312923 | Canggohob HS | MABINAY | 2 | 1 | UPGRADING | 1 | 479603.42 | 475162.71 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | UPGRADING | 1 | 605633.91 | 599603.8 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312951 | Mabinay Science High School | MABINAY | 2 | 1 | UPGRADING | 1 | 623832.57 | 616712.597 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2 | 1 | UPGRADING | 1 | 471654.73 | 466289.46 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 631634.17 | 624474.947 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 | 1 | UPGRADING | 1 | 663993.05 | 657672.6 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659889.99 | 653772.57 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303278 | Crisostomo O. Retes NHS (Tampi NHS) | SAN JOSE | 2 | 1 | UPGRADING | 1 | 769006.9 | 759164.24 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | UPGRADING | 1 | 566903.28 | 560064.537 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303266 | San Miguel NHS | BACONG | 3 | 1 | UPGRADING | 1 | 778525.78 | 768635.76 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental |  | Antonio B. Alejado MHS (Campus II) | DAUIN | 3 | 1 | UPGRADING | 2 | 516957.6 | 514088.84 | COMPLETED | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 | 1 | UPGRADING | 2 | 502304.6 | 499512.55 | COMPLETED | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303224 | Apolinar B. Macias MHS (Casile NHS) | DAUIN | 3 | 1 | UPGRADING | 1 | 674191.81 | 666821.297 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303225 | Dauin NHS | DAUIN | 3 | 1 | UPGRADING | 1 | 694285.21 | 686814.167 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312921 | Froilan A. Alanano MHS | DAUIN | 3 | 1 | UPGRADING | 1 | 541118.53 | 534418.067 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 | 1 | UPGRADING | 1 | 618741.84 | 611657.187 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303206 | Avocado Community High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 549572.35 | 544576 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303250 | Casiano Z. Napigkit NHS (Manalongon NHS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 755011.31 | 745225.04 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 633408.36 | 599043.49 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312932 | Eligio T. Monte De Ramos HS (Milagrosa HS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 642188.83 | 638347.21 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312933 | Kakha High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 569707.8 | 566218.9 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 661279.82 | 655171.5 | terminated | 27% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 27% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 685131.65 | 675674.96 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312935 | Sta. Catalina Science High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 682615.65 | 678509.1 | terminated | 35% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 35% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School (Cabangahan HS) | SIATON | 3 | 1 | UPGRADING | 2 | 563035.84 | 559881.45 | COMPLETED | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | UPGRADING | 2 | 698194.63 | 693171.23 | COMPLETED | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 | 1 | UPGRADING | 1 | 748699.97 | 740620.75 | terminated | 16% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | UPGRADING | 1 | 664886.16 | 657899.52 | terminated | 92% | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 92% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312908 | Balugo National High School | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 773368.09 | 763493.11 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 891964.53 | 881506.89 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | 2 | 855825.17 | 850910.43 | COMPLETED | 100% | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 | 1 | UPGRADING | 1 | 651972.91 | 644724.747 | COMPLETED | 100% | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | 1 | 2787612.5 | 2338366.12 | terminated | 55% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 55% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303303 | Basac National High School | LARENA | 0 | 1 | UPGRADING | 1 | 5937774.35 | 5314986.57 | terminated | 45% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 45% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303293 | Campalanas National High School | LAZI | 0 | 1 | UPGRADING | 1 | 2636170.21 | 2467591.87 | terminated | 75% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 75% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 | 1 | UPGRADING | 1 | 3700754.43 | 3399753.16 | terminated | 90% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303295 | Leon Parami High School | LAZI | 0 | 1 | UPGRADING | 1 | 5722840.8 | 5216947.16 | terminated | 90% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 120669 | Candaping Elementary School | MARIA | 0 | 1 | UPGRADING | 1 | 2800298.26 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Siquijor | 303305 | Catulayan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 2955591.79 | 2788223.92 | terminated | 65% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 65% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 3067762.82 | 2795296.97 | terminated | 80% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 80% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 2657032.83 | 2608113.44 | terminated | 90% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 120694 | Cang-alwang Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 | 1352254.37 | REVERTED | 90% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region VII | Siquijor | 303298 | San Antonio National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 8550699.35 | 8162560.7 | terminated | 80% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 80% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1606427.72 | 1353112.32 | terminated | 90% | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | terminated
ELECTRIFICATION 2018 | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | UPGRADING | 1 | 1682365.93 |  | COMPLETED | 100% | December 31, 2018 | [8 empty] | DOLCI Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 322204 | Bulacao NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 435845.86 | 432795.6713 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 119799 | Jaclupan ES | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 478753.59 | 475256.61 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 431634.01 | 428633.8283 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 509937.6 | 505787.3821 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 322201 | Maghaway NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 552344.64 | 547585.844 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303056 | Mohon NHS (Mohon Divino Amore NHS) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 415655.55 | 412816.1243 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 460428.75 | 456866.8163 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303088 | San Roque NHS ( Laray NHS - Jaclupan NHS Ext.) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 415293.38 | 412850.5643 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303111 | Tabunok Night HS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 475590.16 | 471024.6803 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 570530.15 | 566019.5863 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Talisay City | 322208 | Tapul NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 483053.92 | 479566.3253 | COMPLETED | 100% |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 120541 | Alangilan PS | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1170923.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 120543 | Ballacag ES | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1306144.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1361578.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 234004 | Mandalamon Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1157207.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1848529.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1499917.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303279 | Tanjay Legislated HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 960052.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1463896.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303283 | Tanjay Science HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 835379.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 120565 | Toyupan Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1870833.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 665880.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 312911 | Hunop Community High School | PAMPLONA | 2 | 1 | UPGRADING | 1 | 674059.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | UPGRADING | 1 | 883293.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Tanjay City | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1027752.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VII | Toledo City | 303308 | Bato NHS | TOLEDO CITY | 3 | 1 | UPGRADING | 2 | 858349.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 344593 | Baybay City Senior High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 1700496.67 |  | COMPLETED | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 313323 | Ciabu National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 2390942.48 |  | COMPLETED | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Baybay City | 313312 | Mailhi National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING | 2 | 2680839.11 |  | COMPLETED | 100% |  |  |  |  | 2018-05-28 | 2018-06-20 | 2018-06-25 | 2018-07-11 | 2018-07-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | UPGRADING | 2 | 1482557.79 | 1471181.88 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | W.B ALAGAO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | 0 | 1 | UPGRADING | 2 | 4379481.59 | 4345813.3 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | QYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303328 | Manlabang National High School | CAIBIRAN | 0 | 1 | UPGRADING | 2 | 4368287.45 | 4,304,00.00 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | UPGRADING | 2 | 4315524.95 | 4273054.68 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MKB BUILDERS & SUPPY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303327 | Lucsoon NHS | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 1573233.98 | 1554689.64 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | A & B ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 3051257.34 | 3017616 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | MB ANG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Biliran | 303331 | Naval School of Fisheries | NAVAL (Capital) | 0 | 1 | UPGRADING | 2 | 4724556.18 | 4685748.31 | COMPLETED | 100% | 2018-09-03 |  |  |  | 2018-05-17 | 2018-05-24 | 2018-05-08 | 2018-06-29 | 2018-07-03 | BNL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 313504 | Benowangan NHS (Lalawigan NHS - Benowangan Annex) | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 1481515.29 | 1468931.48 | COMPLETED | 100% | July 4, 2019 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 2 | CY 2018 - BEFF ELECTRIFICATION - 02 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 2534404.17 | 2501753.8 | COMPLETED | 100% | July 4, 2020 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 3 | CY 2018 - BEFF ELECTRIFICATION - 03 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Borongan City | 303526 | Maypangdan NHS | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | 1 | 2514611.87 | 2482032.29 | COMPLETED | 100% | July 4, 2018 |  | CY 2018 BEFF - ELECTRIFICATION OF UNENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 BORONGAN CITY - LOT 1 | CY 2018 - BEFF ELECTRIFICATION - 01 | February 26, 2018 | March 7, 2018 | March 20, 2018 | March 26, 2018 | March 29, 2018 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 500807 | Bagacay Integrated School | CALBAYOG CITY | 1 | 1 | UPGRADING | 2 | 2360813.61 |  | COMPLETED | 100% |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B2 | 2018-04-20 | 2018-04-21 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303644 | Mag-Ubay National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 978107.61 |  | COMPLETED | 100% |  |  | CAL ESUP CY2018 B1 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303645 | Malaga National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 1485553.14 |  | COMPLETED | 100% |  |  | CAL ESUP CY2018 B2 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 | 1 | UPGRADING | 1 | 1195826.77 |  | COMPLETED | 100% |  |  | CAL ESUP CY2018 B3 | CAL ESUP CY2018 B1 | 2018-04-21 | 2018-04-20 | 2018-05-11 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 313701 | Catbalogan NCHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 907149.62 | 892311.17 | COMPLETED | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L3 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-03 | 2018-09-28 | RNA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 313706 | Pangdan National High School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 978526.9 | 933000 | COMPLETED | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L2 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-09-16 | 2018-10-05 | J .Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Catbalogan City | 303623 | Silanga NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | 1 | 967974.4 | 953285.25 | COMPLETED | 100% |  |  | CY 2018- BEFF- ESUP- R8 - CC- L1 |  | 2018-07-05 | 2018-07-13 | 2018-08-01 | 2018-08-20 | 2018-08-31 | WC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID | 0 | 1 | UPGRADING | 2 | 3376983.67 |  | COMPLETED | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 2 - REBID | CY 2018-BEFF ELECTRIFICATION-02 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | UPGRADING | 2 | 2850070.88 |  | COMPLETED | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | 2018-04-16 | 2018-03-11 | 2018-05-31 |  |  | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | 0 | 1 | UPGRADING | 1 | 1899932.73 | 1883623.09 | COMPLETED | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 4 | CY 2018-BEFF ELECTRIFICATION-04 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303518 | Mercedes HS | MERCEDES | 0 | 1 | UPGRADING | 1 | 2174089.73 | 2133791.35 | COMPLETED | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 5 | CY 2018-BEFF ELECTRIFICATION-05 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | UPGRADING | 2 | 2549376.4 |  | COMPLETED | 100% |  |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2 ESAMAR-LOT 3- REBID | CY 2018-BEFF ELECTRIFICATION-03 | 2018-06-04 | 2018-06-14 | 2018-06-26 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303516 | Matarinao SOF | SALCEDO | 0 | 1 | UPGRADING | 1 | 2480957.29 | 2443569.47 | COMPLETED | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 3 | CY 2018-BEFF ELECTRIFICATION-03 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | DAY-BREAK ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303524 | San Julian NHS | SAN JULIAN | 0 | 1 | UPGRADING | 1 | 2683247.19 | 2659952.85 | COMPLETED | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 1 | CY 2018-BEFF ELECTRIFICATION-01 | March 16, 2018 | March 26, 2018 | April 10, 2018 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Eastern Samar | 303527 | Sulat NHS | SULAT | 0 | 1 | UPGRADING | 1 | 3227556.88 | 3199782.49 | COMPLETED | 100% | August 25, 2018 |  | CY 2018 BEFF-ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 1 ESAMAR-LOT 2 | CY 2018-BEFF ELECTRIFICATION-02 | March 16, 2018 | March 26, 2018 | April 10, 2019 | Arpil 17, 2018 | April 20, 2018 | LOBRIÑO'S CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303336 | Alangalang National High School | ALANGALANG | 1 | 1 | UPGRADING | 2 | 6177826.74 | 6036005.25 | COMPLETED | 100% |  |  | lot 5-cy-2018-E-B2-leyte | lot 5-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313398 | Borseth National High School | ALANGALANG | 1 | 1 | UPGRADING | 3 | 1190462.69 |  | COMPLETED | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303343 | Juan S. Tismo National High School (Babatngon National High School) | BABATNGON | 1 | 1 | UPGRADING | 2 | 1982220.18 | 1935484.34 | COMPLETED | 100% |  |  | lot 6-cy-2018-E-B2-leyte | lot 6-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MJM BUILDERS AND INTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121736 | Anahaway Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 591708.82 |  | COMPLETED | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303339 | Anahaway National High School | PALO | 1 | 1 | UPGRADING | 3 | 1277292.87 |  | COMPLETED | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121738 | Canhidoc Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 666114.39 |  | COMPLETED | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121739 | Capirawan Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 610371.35 |  | COMPLETED | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121740 | Castilla ElementarySchool | PALO | 1 | 1 | UPGRADING | 3 | 586218.65 |  | COMPLETED | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121741 | Gacao Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 622190.03 |  | COMPLETED | 100% | [9 empty] | FOUR K BUILDERS & CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121742 | Luntad Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 772659.86 |  | COMPLETED | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121743 | Palo I Central School | PALO | 1 | 1 | UPGRADING | 3 | 2496173.72 |  | COMPLETED | 100% | [9 empty] | HD GOLDEN BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303415 | Palo National High School | PALO | 1 | 1 | UPGRADING | 2 | 1967538.7 | 1922728.25 | COMPLETED | 100% |  |  | lot 7-cy-2018-E-B2-leyte | lot 7-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HD GOLDEN BULDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121744 | Salvacion Elementary School | PALO | 1 | 1 | UPGRADING | 3 | 399138.7 |  | COMPLETED | 100% | [9 empty] | LJPM BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1 | 1 | UPGRADING | 2 | 1690466.94 | 1658407.13 | COMPLETED | 100% |  |  | lot 9-cy-2018-E-B2-leyte | lot 9-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J.A. CONST. AND TRADING CORP. (Formerly: J.A. Construction ) |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313305 | Tanauan School of Arts and Trade | TANAUAN | 1 | 1 | UPGRADING | 2 | 1174573.79 | 1147827.61 | COMPLETED | 100% |  |  | lot 8-cy-2018-E-B2-leyte | lot 8-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | JELM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 897652.53 |  | COMPLETED | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 945617.42 |  | COMPLETED | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | UPGRADING | 3 | 750365.63 |  | COMPLETED | 100% | [9 empty] | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121181 | Arado Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 575754.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121154 | Burauen North Central School | BARAUEN | 2 | 1 | UPGRADING | 3 | 914305.38 |  | COMPLETED | 100% | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121185 | Burauen South Central School | BARAUEN | 2 | 1 | UPGRADING | 3 | 766640.52 |  | COMPLETED | 100% | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121199 | Paghudlan Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 795067.68 |  | COMPLETED | 100% | [9 empty] | AGB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121205 | San Isidro Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 567475.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121177 | Toloyao Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 513506.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121179 | Villa Rosas Elementary School | BARAUEN | 2 | 1 | UPGRADING | 3 | 855843.81 |  | COMPLETED | 100% | [9 empty] | H.A.H REVERIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313324 | Barugo National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 2013502.03 |  | COMPLETED | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303357 | Calingcaguing National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 1213545.38 |  | COMPLETED | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303363 | Celestino De Guzman Memorial National High School | BARUGO | 2 | 1 | UPGRADING | 2 | 1788212.64 | 1762836.24 | COMPLETED | 100% |  |  | lot 10-cy-2018-E-B2-leyte | lot 10-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | FJ. TIU & ASSOCIATES CONSTRUCTION & DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303433 | Sta. Rosa National High School | BARUGO | 2 | 1 | UPGRADING | 3 | 1876187.49 |  | COMPLETED | 100% | [9 empty] | FM4 BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303341 | Asuncion S. Melgar National High School | CAPOOCAN | 2 | 1 | UPGRADING | 2 | 1715056.46 | 1677900.42 | COMPLETED | 100% |  |  | lot 11-cy-2018-E-B2-leyte | lot 11-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303418 | Pinamopoan National High School | CAPOOCAN | 2 | 1 | UPGRADING | 3 | 1328911.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303362 | Carigara National Vocational School | CARIGARA | 2 | 1 | UPGRADING | 2 | 2036324.97 | 2000351.02 | COMPLETED | 100% |  |  | lot 13-cy-2018-E-B2-leyte | lot 13-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | LRD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313307 | Jugaban National High School | CARIGARA | 2 | 1 | UPGRADING | 2 | 1677277.16 | 1642209.33 | COMPLETED | 100% |  |  | lot 12-cy-2018-E-B2-leyte | lot 12-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | HARDLINES BUILDERS AND SALES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121319 | Bulod Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 589524.03 |  | COMPLETED | 100% | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303355 | Cabacungan National High School | DULAG | 2 | 1 | UPGRADING | 3 | 1333806.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121320 | Cabatoan Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 994077.4 |  | COMPLETED | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121321 | Calipayan Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 576756.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121350 | RIZAL ELEMENTARY SCHOOL | DULAG | 2 | 1 | UPGRADING | 3 | 758435.92 |  | COMPLETED | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121331 | San Agustin Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 807290.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121353 | San Miguel Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 748968.36 |  | COMPLETED | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121336 | Tabu Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 577762.85 |  | COMPLETED | 100% | [9 empty] | CAFRENCILLO ARCH DESIGN & BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 121337 | Tigbao Elementary School | DULAG | 2 | 1 | UPGRADING | 3 | 984888.74 |  | COMPLETED | 100% | [9 empty] | PALMERA BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303387 | Leyte Agro Industrial School | LEYTE | 3 | 1 | UPGRADING | 2 | 3214202.53 | 3139000 | COMPLETED | 100% |  |  | lot 14-cy-2018-E-B2-leyte | lot 14-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303434 | Tabango National High School | TABANGO | 3 | 1 | UPGRADING | 3 | 1241888.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313322 | Cahigan NHS | VILLABA | 3 | 1 | UPGRADING | 1 | 1104935.83 | 1086973.98 | COMPLETED | 100% |  |  | lot 3-cy-2018-E-B1-leyte | lot 3-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | NV& C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313345 | Sulpa NHS | VILLABA | 3 | 1 | UPGRADING | 1 | 1232603.71 | 1198725.5 | COMPLETED | 100% |  |  | lot 4-cy-2018-E-B1-leyte | lot 4-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | AGB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA | 3 | 1 | UPGRADING | 1 | 3162822.17 | 3098929.27 | COMPLETED | 100% |  |  | lot 2-cy-2018-E-B1-leyte | lot 2-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | D.L. AUREO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303389 | Villaba NHS (LNCAST) | VILLABA | 3 | 1 | UPGRADING | 1 | 1184101.21 | 1151115.37 | COMPLETED | 100% |  |  | lot 1-cy-2018-E-B1-leyte | lot 1-cy-2018-E-B1-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | R.M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4 | 1 | UPGRADING | 2 | 1655671.04 | 1616917.39 | COMPLETED | 100% |  |  | lot 15-cy-2018-E-B2-leyte | lot 15-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303406 | Matlang National High School | ISABEL | 4 | 1 | UPGRADING | 2 | 2134188.44 | 2091336.37 | COMPLETED | 100% |  |  | lot 16-cy-2018-E-B2-leyte | lot 16-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MAGA CONSTRUTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313306 | Palompon National High School | PALOMPON | 4 | 1 | UPGRADING | 3 | 1962688.7 |  | COMPLETED | 100% | [9 empty] | BCG DESIGN & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313315 | San Guillermo National High School | PALOMPON | 4 | 1 | UPGRADING | 3 | 1547694.85 |  | COMPLETED | 100% | [9 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303373 | Hampipila National High School | ABUYOG | 5 | 1 | UPGRADING | 3 | 1345005.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303365 | Concepcion National High School | HILONGOS | 5 | 1 | UPGRADING | 3 | 1493207.13 |  | COMPLETED | 100% | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | UPGRADING | 2 | 1666610.71 | 1619847.86 | COMPLETED | 100% |  |  | lot 17-cy-2018-E-B2-leyte | lot 17-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303431 | Sta. Margarita National High School | HILONGOS | 5 | 1 | UPGRADING | 3 | 1978115.07 |  | COMPLETED | 100% | [9 empty] | JAMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303379 | Javier National High School | JAVIER (BUGHO) | 5 | 1 | UPGRADING | 3 | 1504649.55 |  | COMPLETED | 100% | [9 empty] | VITHS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 303356 | Cahagnaan National High School | MATALOM | 5 | 1 | UPGRADING | 2 | 1673096.47 | 1636201.66 | COMPLETED | 100% |  |  | lot 18-cy-2018-E-B2-leyte | lot 18-cy-2018-E-B2-leyte | 2018-03-26 | 2018-04-02 | 2018-05-07 | 2018-06-04 | 2018-06-15 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Leyte | 313337 | Sta. Paz Integrated School | MATALOM | 5 | 1 | UPGRADING | 3 | 1898479.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Maasin City | 303454 | Dongon NHS | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | 2 | 1628954.86 | 1620850.61 | COMPLETED | 100% |  |  | ELECTRIFICATION-18-6-001 | ELECTRIFICATION-18-6-001 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | 2 | 1639879.93 | 1631721.33 | COMPLETED | 100% |  |  | ELECTRIFICATION-18-6-002 | ELECTRIFICATION-18-6-002 | 2018-06-11 | 2018-06-20 | 2018-07-02 | 2018-07-18 | 2018-12-10 | DAYBREAK ENTERPRISES ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303535 | Bobon School for Philippine Craftsmen | BOBON | 1 | 1 | UPGRADING | 1 | 3153787.21 | 2636473.12 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L1 | BEFF2018-B1-E-NS-L1 | June 6, 2018 | June 14, 2018 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303548 | Eladio T. Balite Memorial School of Fisheries | BOBON | 1 | 1 | UPGRADING | 1 | 2555079.02 | 2237178.28 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L2 | BEFF2018-B1-E-NS-L2 | June 6, 2019 | June 14, 2019 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303541 | Catarman National High School | CATARMAN (Capital) | 1 | 1 | UPGRADING | 1 | 3833968.6 | 3205230.91 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L3 | BEFF2018-B1-E-NS-L3 | June 6, 2020 | June 14, 2020 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1 | 1 | UPGRADING | 1 | 1149519.71 | 996008.08 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L5 | BEFF2018-B1-E-NS-L5 | June 6, 2022 | June 14, 2022 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303566 | Mondragon Agro-Ind'L HS | MONDRAGON | 1 | 1 | UPGRADING | 1 | 3334063.59 | 2918463.7 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L4 | BEFF2018-B1-E-NS-L4 | June 6, 2021 | June 14, 2021 | June 28, 2018 | 2018-07-25 |  | ROSS Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303577 | San Isidro Agro-Industrial High School | SAN ISIDRO | 1 | 1 | UPGRADING | 2 | 2694755.8 | 2252210.12 | COMPLETED | 100% |  |  | BEFF2018-B2-E-NS-L1 | BEFF2018-B2-E-NS-L1 | June 6, 2018 | June 14, 2018 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303580 | San Jose Technical HS | SAN JOSE | 1 | 1 | UPGRADING | 2 | 2123000.01 | 1774492.2 | COMPLETED | 100% |  |  | BEFF2018-B2-E-NS-L2 | BEFF2018-B2-E-NS-L2 | June 6, 2019 | June 14, 2019 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303556 | Laoang National Technical High School | LAOANG | 2 | 1 | UPGRADING | 2 | 2131770.4 | 2089873.18 | COMPLETED | 100% |  |  | BEFF2018-B2-E-NS-L3 | BEFF2018-B2-E-NS-L3 | June 6, 2020 | June 14, 2020 | 2018-07-02 | 2018-07-25 |  | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2 | 1 | UPGRADING | 2 | 2634837.55 | 2202290.21 | COMPLETED | 100% |  |  | BEFF2018-B2-E-NS-L4 | BEFF2018-B2-E-NS-L4 | June 6, 2021 | June 14, 2021 | 2018-07-02 | 2018-07-25 |  | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313609 | Cabatuan NHS | PALAPAG | 2 | 1 | UPGRADING | 1 | 954013.8 | 801753.1975 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2024 | June 14, 2024 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2 | 1 | UPGRADING | 1 | 1675760.29 | 1408308.9477 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L6 | BEFF2018-B1-E-NS-L6 | June 6, 2023 | June 14, 2023 | June 28, 2018 | 2018-07-25 |  | MAGA Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313621 | Zoilo T. Lobos Memorial High School | PAMBUJAN | 2 | 1 | UPGRADING | 1 | 1393081.21 | 1220283.63 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L7 | BEFF2018-B1-E-NS-L7 | June 6, 2025 | June 14, 2025 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2 | 1 | UPGRADING | 1 | 1577033.76 | 1381476.98 | COMPLETED | 100% |  |  | BEFF2018-B1-E-NS-L8 | BEFF2018-B1-E-NS-L8 | June 6, 2026 | June 14, 2026 | June 28, 2018 | 2018-07-25 | 2018-08-10 | SMU Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1576999.15 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c6 | 2018-beff-e-b2-c6 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124201 | Bagong Buhay Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1381598.37 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c7 | 2018-beff-e-b2-c7 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124202 | Cabintan Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 1293491.95 | 4495169.04 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313903 | Cabintan National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1654412.29 | 1620629.31 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c12 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | V.JYN Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124148 | Can-adieng Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 2245826.86 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c3 | 2018-beff-e-b2-c3 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 2757663.47 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c2 | 2018-beff-e-b2-c2 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124177 | Concepcion Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1478463.34 | 3602646.96 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124150 | Dolores Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 2493754.39 | 4495169.05 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3007642.38 | 2957771.42 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c5 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JB BautistaEnterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124151 | Don Carlos Rivilla Elemetary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1282939.18 | 3962356.38 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 1480326.64 | 3602646.96 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 1883203.55 | 3552520.68 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124153 | Gaas Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1277662.8 | 4495169.05 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C1 | 2018-BEFF-E-B3-C1 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | NV and C Construction and General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303661 | Genero B. Lureñana National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3292258.37 | 3200462.84 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c3 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | silverscket Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1582314.96 | 4614565.47 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124155 | Ipil Central School | ORMOC CITY | 4 | 1 | UPGRADING | 3 | 2878625.57 | 3962356.38 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303655 | Ipil National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2515883.21 | 2462794.19 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c6 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JRM Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313906 | Julian C. Gantuangco NHS | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1440097.15 | 1410802.45 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c14 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | JFR COnstrUction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2032322.68 | 1947137.8 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c10 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Tom bUilders & supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124195 | Linao Central School | Ormoc City | 4 | 1 | UPGRADING | 3 | 3128610.73 | 5180301.57 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303656 | Linao National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3128532.52 | 3081891.71 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c4 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124160 | Mabini Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1293491.95 | 3962356.38 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C2 | 2018-BEFF-E-B3-C2 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1592867.72 | 3602646.96 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C6 | 2018-BEFF-E-B3-C6 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303657 | Margen National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2153212.81 | 2121357.24 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c9 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313904 | Matica-a National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2381911.9 | 1799816.48 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c7 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Melgazo construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124196 | Naungan Elementary School | Ormoc City | 4 | 1 | UPGRADING | 3 | 2124989.86 | 5180301.57 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C4 | 2018-BEFF-E-B3-C4 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303658 | New Ormoc City National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3781284.86 | 3728200.82 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c1 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | QCC Consuction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 3776008.61 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c1 | 2018-beff-e-b2-c1 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313905 | Ormoc City Night High School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1282907.11 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c8 | 2018-beff-e-b2-c8 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2158792.3 | 2126853.5 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c8 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits. D.G. Builders Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124197 | Ormoc City SPED Center | Ormoc City | 4 | 1 | UPGRADING | 3 | 1628071.74 | 3552520.68 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1379888.1 | 3552520.68 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C5 | 2018-BEFF-E-B3-C5 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | Ross Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 313902 | Pedro G. Bañez National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 1551618.51 | 1476661.27 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c13 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Bench Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124198 | Punta Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1674516.68 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c5 | 2018-beff-e-b2-c5 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303660 | Rustico Capahi Sr. Memorial National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 2017943.15 | 1958299.41 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c11 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | HD Golden Buliders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124190 | San Jose Elementary School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 1774189.06 | 4614565.47 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124221 | San Pablo Elementary School (Simangan) | ORMOC CITY | 4 | 1 | UPGRADING | 2 | 1772034.2 |  | COMPLETED | 100% |  |  | 2018-beff-e-b2-c4 | 2018-beff-e-b2-c4 | 2018-04-26 | 2018-05-04 | 2018-05-16 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 124193 | Valencia Central School | Ormoc City | 4 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 3 | 2459994.63 | 4614565.47 | COMPLETED | 100% | April 7, 2019 |  | 2018-BEFF-E-B3-C3 | 2018-BEFF-E-B3-C3 | Sept. 13,2018 | Sept. 20, 2018 | Oct. 2, 2018 | Dec. 27, 2018 | Jan. 7, 2019 | HD Golden Builders and Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4 | 1 | UPGRADING | 1 | 3293173.99 | 3254055.18 | COMPLETED | 100% | Aug. 19 |  | 2018-beff-e-b1-c2 |  | 2018-03-06 | 2018-03-14 | 2018-03-26 | 2018-04-13 | 2018-05-21 | Vhits D.G. Builders Enterprise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 123498 | Beslig ES | GANDARA | 1 | 1 | UPGRADING | 2 | 655750.5 | 647586.2 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L1 | CY2018BEFF-ELB2-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 123509 | Gandara I CS | GANDARA | 1 | 1 | UPGRADING | 1 | 3200049.06 |  | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L1 | CY2018BEFF-ELB1-L1 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | ROS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303599 | Clarencio Calagos Mem SOF | SANTA MARGARITA | 1 | 1 | UPGRADING | 2 | 2280064.55 | 2253634.61 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L2 | CY2018BEFF-ELB2-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313727 | Mabini NHS | BASEY | 2 | 1 | UPGRADING | 1 | 1271594.45 |  | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303597 | CALBIGA NATIONAL HIGH SCHOOL | CALBIGA | 2 | 1 | UPGRADING | 1 | 2166391.77 | 2140444.93 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L3 | CY2018BEFF-ELB1-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS-Daram NHS Annex | DARAM | 2 | 1 | UPGRADING | 1 | 1725508.53 | 1710108.44 | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L5 | CY2018BEFF-ELB1-L5 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303601 | Daram NHS | DARAM | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1531224.89 | 1513553.01 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L4 | CY2018BEFF-ELB1-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 | 1 | UPGRADING | 2 | 2133635.11 | 2121485.36 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L3 | CY2018BEFF-ELB2-L3 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313710 | Malino National High School | JIABONG | 2 | 1 | UPGRADING | 1 | 965109.08 |  | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303611 | Marabut NHS | MARABUT | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 526801.85 |  | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB1-L2 | CY2018BEFF-ELB1-L2 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303596 | Calapi NHS | MOTIONG | 2 | 1 | UPGRADING | 1 | 1723736.2 | 1713315.58 | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L8 | CY2018BEFF-ELB1-L8 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303641 | Wright NHS | PARANAS (WRIGHT) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 793826.39 |  | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303631 | Sta. Rita NHS | SANTA RITA | 2 | 1 | UPGRADING | 2 | 2002105.61 | 1970291.48 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L4 | CY2018BEFF-ELB2-L4 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | MAGA Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 303605 | Guintarcan NHS | VILLAREAL | 2 | 1 | UPGRADING | 2 | 1535226.82 | 1511737.82 | COMPLETED | 100% | 2018-10-11 |  | CY2018BEFF-ELB2-L5 | CY2018BEFF-ELB2-L5 | 2018-04-03 | 2018-04-11 | 2018-04-23 | 2018-05-25 | 2018-06-13 | NV & C Const. Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313718 | Primitivo T. Torrechiva National High School | VILLAREAL | 2 | 1 | UPGRADING | 1 | 467199.47 |  | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L7 | CY2018BEFF-ELB1-L7 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Maga Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | UPGRADING | 1 | 504571.49 |  | COMPLETED | 100% | 2018-10-04 |  | CY2018BEFF-ELB1-L6 | CY2018BEFF-ELB1-L6 | March 6,2018 | March 14,2018 | March 26,2018 | 2018-04-16 | 2018-06-06 | Tubigan Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | 0 | 1 | UPGRADING | 2 | 2380206.32 | 2356522.67 | COMPLETED | 100% |  |  | 18-5-001 | 18-5-001 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | DAYBREAK ENTERPRISES - ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Southern Leyte | 303460 | Himbangan National High School | SAINT BERNARD | 0 | 1 | UPGRADING | 2 | 3051800.83 | 3021434.65 | COMPLETED | 100% |  |  | 18-5-002 | 18-5-002 | 2018-05-25 | 2018-06-01 | 2018-06-18 | 2018-07-04 | 2018-07-10 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 303663 | Leyte NHS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 1 | 3268867.99 | 3232604.53 | COMPLETED | 100% | 2018-07-23 |  | CY 2018_BEFF ELECTRIFICATION-Batch 1 | CY 2018_BEFF ELECTRIFICATION-Batch 1 | 2018-04-19 | 2018-04-26 | 2018-05-08 | 2018-05-15 | 2018-05-17 | JELM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 314005 | Scandinavian National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1530499.13 | 1507884.51 | COMPLETED | 100% | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C1 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region VIII | Tacloban City | 330503 | V&G National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1728949.63 | 1701750.55 | COMPLETED | 100% | 2018-07-30 |  | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | CY 2018_BEFF ELECTRIFICATION-Batch 2_C2 | 2018-04-26 | 2018-05-03 | 2018-05-15 | 2018-05-18 | 2018-05-22 | TITANYA CONSTRUCTION & DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 303968 | Libona NHS | LIBONA | 1 | 1 | UPGRADING | 1 | 421084.28 | 334843.13 | COMPLETED | 100% | 2022-12-29 | 2022-10-13 | 07-2018 | 28-2018 | 2018-08-07 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314901 | Dalirig NHS | MANOLO FORTICH | 1 | 1 | UPGRADING | 1 | 591286.35 | 588344.62 | COMPLETED | 100% | 2018-10-28 |  | 07-2018 | 29-2018 | 2018-08-08 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314903 | San Vicente NHS | SUMILAO | 1 | 1 | UPGRADING | 1 | 318600.41 | 285324.63 | COMPLETED | 100% | 2018-11-12 |  | 07-2018 | 30-2018 | 2018-08-09 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 303987 | Talakag NHS | TALAKAG | 1 | 1 | UPGRADING | 1 | 946827.8 | 753354.56 | COMPLETED | 100% | 2018-10-28 |  | 07-2018 | 31-2018 | 2018-08-10 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314908 | Cabulohan-Paradise NHS - Townsite Annex | CABANGLASAN | 2 | 1 | UPGRADING | 1 | 624418.88 | 558710.14 | ONGOING | 95% | 2024-06-15 |  | 07-2018 | 32-2018 | 2018-08-11 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation | Waiting for schedule of energization from Electric Coop (BUSECO) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2018 | Region X | Bukidnon |  | Lantapan Stand-Alone SHS | LANTAPAN | 2 | 1 | UPGRADING | 1 | 1811677.5 | 1622321.51 | COMPLETED | 100% | 2022-12-29 |  | 07-2018 | 33-2018 | 2018-08-12 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Bukidnon | 314907 | Halapitan NHS - Little Baguio Annex | SAN FERNANDO | 2 | 1 | UPGRADING | 1 | 564410.03 | 504908.55 | ONGOING | 90% | 2024-07-15 |  | 07-2018 | 34-2018 | 2018-08-13 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | Digos Constrak Corporation | Materials for inspection of electric coop; Work is halted due to financial constraint of contactor | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2018 | Region X | Bukidnon | 303948 | Bocboc NHS | DON CARLOS | 3 | 1 | UPGRADING | 2 | 1377615.56 | 1233103.87 | ONGOING | 90% | 2024-06-15 |  | 08-2018 | 35-2018 | 19 Sep 18 | 2018-08-08 | 2018-08-20 | 2018-08-30 | 2018-09-10 | DIGOS CONSTRAK CORPORATION | Materials for inspection of Electric coop; BOM from Electric Cooperative for revision; Current transformer and KWhr Meter for purchasing of the contractor | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304106 | Bayabas National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2935952.5 | 2911668.44 | COMPLETED | 100% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304108 | Bulua NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 1 | 1012007.31 | 989436.07 | COMPLETED | 100% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 315403 | Cagayan de Oro NHS - Balulang Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 1 | 3465288.73 | 3379251.62 | COMPLETED | 100% |  |  |  | 208-012 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304112 | Carmen National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2496894.65 | 2473358.01 | COMPLETED | 100% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304125 | Taglimao National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1534398.56 | 1516689.22 | COMPLETED | 100% |  |  |  |  | 2018-07-31 | 2018-08-08 | 2018-08-29 |  |  | BREMA CONSTRUCTON |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304104 | Agusan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 4433497.52 | 4323276.69 | COMPLETED | 100% |  |  |  | 208-013 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 315401 | Balubal NHS | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 3049898.1 | 2973777.69 | COMPLETED | 100% |  |  |  | 208-014 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1642134.89 | 1601120.29 | COMPLETED | 100% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Cagayan de Oro City | 304118 | Lapasan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1550067.26 | 1511066.11 | COMPLETED | 100% |  |  |  | 208-011 | 2018-05-04 | 2018-05-16 | 2018-06-03 | 2018-06-07 | 2018-07-03 | BRIMA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | 0 | 1 | UPGRADING | 1 | 1419115.71 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | 0 | 1 | UPGRADING | 1 | 8681319.02 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303992 | Lawigan-Bura National High School | CATARMAN | 0 | 1 | UPGRADING | 1 | 2682276.05 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | 0 | 1 | UPGRADING | 1 | 3019910.32 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | 0 | 1 | UPGRADING | 1 | 4812666.4 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303993 | SIXTO A. ABAO NHS | MAHINOG | 0 | 1 | UPGRADING | 1 | 6434149.04 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 13653985.18 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303996 | Tupsan NHS | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 2773140.02 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303997 | Yumbing National High School | MAMBAJAO (Capital) | 0 | 1 | UPGRADING | 1 | 5469760.43 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | 0 | 1 | UPGRADING | 1 | 4193168.3 |  | COMPLETED | 100% |  |  |  |  | 2018-07-24 | 2018-08-03 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | El Salvador | 304065 | Cogon NHS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | 2 | 3640724.85 | 3602767.26 | COMPLETED | 100% | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-06-05 | 2018-06-20 | 2018-06-28 | Joash AR Engineering |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | El Salvador | 315305 | Molugan NHS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | 1 | 2639714.7 | 2612299.53 | COMPLETED | 100% | 2018-11-05 |  |  | 2018-04-0087 | 2018-04-28 | 2018-05-15 | 2018-05-05 | 2018-06-20 | 2018-06-28 | JOASH AR ENG'G |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Gingoog City | 304136 | Jacinto D. Malimas Sr. National High School | GINGOOG CITY | 1 | 1 | UPGRADING | 2 | 1235494.03 |  | COMPLETED | 100% | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Gingoog City | 315502 | Odiongan NHS - Talisay NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | 2 | 1335344.6 |  | COMPLETED | 100% | 2018-11-05 |  |  |  |  | 2018-05-28 | 2018-06-03 | 2018-07-27 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1 | 1 | UPGRADING | 2 | 1575318.14 | 1550017.52 | COMPLETED | 100% | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2 | 1 | UPGRADING | 2 | 2290379.34 | 2233156.57 | COMPLETED | 100% | 2018-12-13 |  |  |  | 2018-06-08 | 2018-06-18 | 2018-07-03 | 2018-07-11 | 2018-07-18 | GREEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 395210.89 | 395210.89 | COMPLETED | 100% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303946 | Bangcud NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3156028.23 | 3156028.23 | COMPLETED | 100% | 2024-06-01 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303950 | Bukidnon NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3467155.4 | 3467155.4 | COMPLETED | 100% | 2024-06-01 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 473176.9 | 473176.9 | COMPLETED | 100% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314914 | Casisang NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 469166.48 | 469166.48 | COMPLETED | 100% |  |  |  |  | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | MEGABLUE KONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 303973 | Managok NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 3568524.3986 | 3568524.3986 | COMPLETED | 100% | 2022-12-29 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314920 | Managok NHS - Miglamin Annex | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 314861.94 | 314861.94 | COMPLETED | 100% | 2024-06-15 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | Complete Materials and schedule for coop re-installation of missing transformer onsite by jaunary, FOR ENERGIZATION-ready for submission of turn-on application; For application of ELectrical Permit from the City Engineer's Office, ELectrical Plan for signature of PEE. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 4.25 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Malaybalay City | 314905 | Silae NHS - Annex St. Peter | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | 1 | 355302.54 | 355302.54 | COMPLETED | 100% | 2024-06-15 |  | 02-INFRA-2018 | 02-INFRA-2018 | 2018-02-26 | 2018-05-21 | 2018-06-05 | 2018-06-11 | 2018-06-21 | DIGOS CONSTRAK CORPORATION | Complete Materials and installation onsite, FOR ENERGIZATION-ready for submission of turn-on application; Documentary requirements for application not yet complied | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1 | 1 | UPGRADING | 2 | 2803883.95 | 2786248.77 | COMPLETED | 100% | 2018-12-05 |  |  | 013-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 304037 | Jimenez NCHS | JIMENEZ | 1 | 1 | UPGRADING | 2 | 1149848.54 | 1140754.84 | COMPLETED | 100% | 2018-12-05 |  |  | 012-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-07-31 | JEFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Occidental | 315207 | Sibugon IS | LOPEZ JAENA | 1 | 1 | UPGRADING | 2 | 3088427.99 | 3059883.65 | COMPLETED | 100% | 2018-12-05 |  |  | 016-2018 | 2018-04-27 |  | 2018-05-10 | 2018-06-08 | 2018-08-03 | MAQUESERQ CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304077 | Kinoguitan NAHS | KINOGUITAN | 1 | 1 | UPGRADING | 1 | 5246873.25 | 481205.07 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1 | 1 | UPGRADING | 1 | 5813168.42 | 5007063.86 | COMPLETED | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304096 | Salay NHS | SALAY | 1 | 1 | UPGRADING | 1 | 5713806 | 5174548.22 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304093 | Talisayan NHS | TALISAYAN | 1 | 1 | UPGRADING | 1 | 5439018.9 | 4726011.85 | COMPLETED | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-10 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304073 | Jasaan NHS | JASAAN | 2 | 1 | UPGRADING | 1 | 5740187.25 | 5314879.97 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 315307 | Manticao NHS | MANTICAO | 2 | 1 | UPGRADING | 1 | 2269686.96 | 2014354.88 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 315303 | Naawan NHS | NAAWAN | 2 | 1 | UPGRADING | 1 | 2304636.87 | 2035580.88 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 341230 | Naawan SHS (Maputi ES Campus) | NAAWAN | 2 | 1 | UPGRADING | 1 | 2219343.3 | 1957650.56 | COMPLETED | 100% |  |  |  |  | 2018-07-23 | 2018-07-31 | 2018-08-14 |  | 2018-10-30 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Misamis Oriental | 304102 | Tagoloan NHS | TAGOLOAN | 2 | 1 | UPGRADING | 1 | 4013228.99 | 3571331.04 | COMPLETED | 100% |  |  |  |  | 2018-06-25 | 2018-07-03 | 2018-07-17 |  | 2018-09-06 | Meter King |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Oroquieta City | 304045 | Misamis Occidental NHS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | 1 | 4830487.89 | 4804355.61 | COMPLETED | 100% | 2018-10-18 |  | n/a | n/a | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | 1 | 2770270.4 | 2754387.96 | COMPLETED | 100% | 2018-09-18 |  | n/a | n/a | 2018-02-28 | 2018-03-08 | 2018-03-20 | 2018-04-12 | 2018-05-21 | J.C DELA VEGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Ozamis City | 304169 | Pulot National High School | OZAMIS CITY | 2 | 1 | UPGRADING | 2 | 2548844.06 |  | COMPLETED | 100% |  |  |  | 092-INFRA18-008 | 2018-08-16 | - | 2018-08-22 |  |  | EDTAHA BUILDERS, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Tangub City | 304041 | Lorenzo Tan NHS | TANGUB CITY | 2 | 1 | UPGRADING | 2 | 2506678.54 |  | COMPLETED | 100% |  |  |  |  | 2018-08-07 | 2018-08-20 | 2018-09-05 | 2018-09-08 | 2018-09-13 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Tangub City | 304171 | Tangub City NHS | TANGUB CITY | 2 | 1 | UPGRADING | 3 | 3504891.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region X | Valencia City |  | Valencia City NHS | CITY OF VALENCIA | 4 | 1 | UPGRADING | 2 | 4667328.3 | 4638510.61 | COMPLETED | 100% |  |  |  |  | 2018-06-08 | 2018-06-14 | 2018-07-02 | 2018-07-10 | 2018-08-07 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315819 | Bango NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1577775.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304187 | Gabi NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 2215840.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304196 | Maparat NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1842092.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304183 | San Miguel NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1536512.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304210 | Siocon NHS | COMPOSTELA | 1 | 1 | UPGRADING | 1 | 1982927.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304198 | Maragusan NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING | 1 | 2216542.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304213 | Tupaz NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING | 1 | 2049802.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304200 | Awao NHS | MONKAYO | 1 | 1 | UPGRADING | 1 | 1590494.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304202 | Montevista NHS | MONTEVISTA | 1 | 1 | UPGRADING | 1 | 2256983.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304206 | New Bataan NHS | NEW BATAAN | 1 | 1 | UPGRADING | 1 | 3230614.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304185 | Don Vicente Romualdez NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | 1 | 1815283.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315812 | San Antonio NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | 1 | 1611721.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304192 | Mabini NHS | MABINI (DOÑA ALICIA) | 2 | 1 | UPGRADING | 1 | 1967172.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315805 | Pindasan NHS | MABINI (DOÑA ALICIA) | 2 | 1 | UPGRADING | 1 | 1973452.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304193 | Atty. Orlando S. Rimando National High School | MACO | 2 | 1 | UPGRADING | 1 | 2108048.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1527258.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304195 | Manat NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1584788.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304205 | Nabunturan NCHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 2 | 4870283.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315818 | New Sibonga NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | 1 | 1656335.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304175 | Araibo NHS | PANTUKAN | 2 | 1 | UPGRADING | 2 | 1488006.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304179 | Bongabong NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1646320.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315807 | Magnaga NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1444563.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 315816 | Napnapan NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1739949.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 2390105.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Compostela Valley | 304211 | Tambongon NHS | PANTUKAN | 2 | 1 | UPGRADING | 1 | 1647295.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3755429.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129554 | Bolton ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3370166.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2693686.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129716 | Catalunan Pequeño Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 1880086.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 278196.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 316202 | Catalunan Pequeno National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2342306.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS (Matina NHS) | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3012928.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304360 | Davao City NHS | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 9527632.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304363 | Davao City Special National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 836317.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129640 | Don Manuel Gutierrez ES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2710768.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304377 | JESUS J. SORIANO NATIONAL HIGH SCHOOL | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 6449590.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 6321696.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 4949650.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304376 | Mabini NHS | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 525546.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3557366.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129648 | Matina CES | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 3501218.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129708 | STA. ANA CENTRAL ELEM. SCHOOL | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2927961.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304393 | Sta. Ana National High School | DAVAO CITY | 1 | 1 | UPGRADING | 4 | 2746820.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304396 | Talomo National High School | DAVAO CITY | 1 | 1 | UPGRADING | 2 | 1136880.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 316201 | Bernardino B. Bosque NHS | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 233327.26 |  | TERMINATED | 35% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304364 | E. Ramos NHS | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 317915.81 |  | TERMINATED | 95% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 95% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304379 | Malabog National High School | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 591519.51 |  | TERMINATED | 35% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304380 | Mandug NHS (Pablo Lorenzo NHS) | DAVAO CITY | 2 | 1 | UPGRADING | 2 | 412886.5 |  | TERMINATED | 35% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304350 | Binugao NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 499043.45 |  | TERMINATED | 95% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 95% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 129531 | Calinan Central ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4522920.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304354 | Calinan NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2924771.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304356 | CROSSING BAYABAS NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 3392495.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304361 | Dona Carmen Denia NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 1150615.64 |  | TERMINATED | 90% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 90% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304395 | Emilio J. Estipona- Guinga NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 366616.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129734 | Imelda Elementary School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4241723.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129735 | Los Amigos Elementary School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2517477.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 256124.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304373 | Los Amigos NHS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2150634.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4173960.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304342 | Ma. Cristina P. Belcar Agricultural High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 331453.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304381 | Marilog High School of Agriculture (Tech-Voc School) | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 695170.9 |  | TERMINATED | 95% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 95% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304382 | Marilog National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 380451.14 |  | TERMINATED | 95% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 95% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304385 | Mintal Comprehensive High School | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 1903999.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129738 | Mintal ES | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 1918342.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 370656.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304387 | Mintal NCHS - Tugbok National HS | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 2441028.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304388 | Optaciano Hilay NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 291703.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304392 | Sirib NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 329202.03 |  | TERMINATED | 95% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 95% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304386 | Sto. Niño National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 388721.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304394 | Tagakpan NHS | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 292433.51 |  | TERMINATED | 35% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao City | 304348 | Talandang National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 699926.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | UPGRADING | 4 | 4267840.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao City | 304355 | Wangan National High School | DAVAO CITY | 3 | 1 | UPGRADING | 2 | 515482.7 |  | TERMINATED | 35% | [10 empty] | WITH ORDER OF TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304217 | Asuncion National High School | ASUNCION (SAUG) | 1 | 1 | UPGRADING | 1 | 4595542.1 | 4565466.8962 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304252 | Sonlon NHS | ASUNCION (SAUG) | 1 | 1 | UPGRADING | 3 | 4621351.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304233 | Kapalong National High School | KAPALONG | 1 | 1 | UPGRADING | 1 | 7579333.47 | 7535212.4937 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304243 | Semong NHS | KAPALONG | 1 | 1 | UPGRADING | 1 | 2515559.99 | 2495918.5425 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304239 | Limbaan NHS | NEW CORELLA | 1 | 1 | UPGRADING | 1 | 2198146.77 | 2179840.7665 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304248 | New Corella NHS | NEW CORELLA | 1 | 1 | UPGRADING | 1 | 7374066.58 | 7330665.0978 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Norte | 304240 | Linao NHS | SAN ISIDRO | 1 | 1 | UPGRADING | 1 | 2119197.91 | 2101855.5785 | COMPLETED | 100% | June 15, 2019 |  |  | 2018-07-003 | May 21, 2018 | May 28, 2018 | June 11, 2018 | July 3, 2018 | July 12, 2018 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304286 | Marber NHS | BANSALAN | 1 | 1 | UPGRADING | 1 | 1637941.03 | 1596873.83 | COMPLETED | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304275 | Hagonoy NHS | HAGONOY | 1 | 1 | UPGRADING | 1 | 1776384.43 | 1739801.33 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304274 | Gov. N. Llanos NHS | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1258038.7 | 1250520.38 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304277 | Ihan NHS | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1059283.01 | 1052188.73 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316001 | Molopolo National High School | KIBLAWAN | 1 | 1 | UPGRADING | 1 | 1689841.2 | 1679718.85 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304270 | Davao Del Sur SOF | MALALAG | 1 | 1 | UPGRADING | 1 | 1532696.52 | 1523160.17 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304289 | Bangkal NHS | MATANAO | 1 | 1 | UPGRADING | 1 | 1438008.41 | 1541904.44 | COMPLETED | 100% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1 | 1 | UPGRADING | 1 | 3208710.59 | 2958144.97 | COMPLETED | 100% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316003 | SALUD CAGAS TECH.& VOC. H.S | MATANAO | 1 | 1 | UPGRADING | 1 | 1525198.43 | 1578855.9 | COMPLETED | 100% | 2018-11-28 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-08-02 | Optimun Equipment Management & Exchange Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316002 | Padada NHS | PADADA | 1 | 1 | UPGRADING | 1 | 1528067.29 | 1518730.69 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304295 | Bato NHS | SANTA CRUZ | 1 | 1 | UPGRADING | 1 | 1636984.63 | 1617487.41 | COMPLETED | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304294 | Sta. Cruz National High School | SANTA CRUZ | 1 | 1 | UPGRADING | 1 | 1931198.96 | 1916291.38 | COMPLETED | 100% | 2018-12-03 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-31 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 316005 | Felipe-Inocencia Deluao NHS | SULOP | 1 | 1 | UPGRADING | 1 | 1415134.64 | 1405605.54 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao del Sur | 304297 | Sulop NHS | SULOP | 1 | 1 | UPGRADING | 1 | 1673254.53 | 1663115.64 | COMPLETED | 100% | 2018-12-04 |  |  |  | 2018-04-16 | 2018-04-28 | 2018-05-07 | 2018-06-26 | 2018-07-28 | FFJJ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304272 | Don Marcelino NHS | DON MARCELINO | 0 | 1 | UPGRADING | 1 | 1196696.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304291 | Lawa NHS | DON MARCELINO | 0 | 1 | UPGRADING | 1 | 1369552.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304264 | Balangonan NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1247574.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304273 | Edna Guillermo MHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1407917.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304281 | Jose Abad Santos NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1912853.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304283 | Kalbay NHS | JOSE ABAD SANTOS (TRINIDAD) | 0 | 1 | UPGRADING | 1 | 1461438.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304271 | Demolok Valley NHS | MALITA | 0 | 1 | UPGRADING | 1 | 1406972.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304287 | Mariano Peralta NHS | MALITA | 0 | 1 | UPGRADING | 1 | 1586869.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304266 | Basiawan NHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 1403358.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304276 | Heracleo Casco MNHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 4916224.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Occidental | 304268 | Tubalan Comprehensive NHS | SANTA MARIA | 0 | 1 | UPGRADING | 1 | 1441567.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Oriental | 304300 | Baganga NHS | BAGANGA | 1 | 1 | UPGRADING | 2 | 3765128.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Davao Oriental | 304311 | Cateel Vocational High School | CATEEL | 1 | 1 | UPGRADING | 2 | 4353915.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Digos City | 129771 | Ramon Magsaysay CES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | 2 | 1574224.53 | 1566392.57 | COMPLETED | 100% | February 27, 2019 | February 27, 2019 | 18-04-059 | 18-04-059 | sept. 14-21, 2019 | sept.18, 2018 | sept. 21, 2018 | nov. 13, 2018 | Nov. 21, 2018 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 128598 | Angel Villarica CES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 2121738.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304216 | Anonang National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1720922.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 128599 | Balet ES | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1586670.16 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330003 | Bandera NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1321344.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304223 | Cogon NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1278338.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 323402 | Del Monte National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1376220.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304236 | Kaputian National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1719112.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330004 | Libertad NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1653793.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304245 | Mambago-B NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1994248.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304247 | Matanos NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1227424.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 323403 | Nieves Villarica NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1813766.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 330002 | San Jose NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1296202.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Island Garden City of Samal | 304259 | Tagbitan-Ag NHS | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | 1 | 1624588.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Mati City | 304326 | Mati SAT | CITY OF MATI (Capital) | 2 | 1 | UPGRADING | 2 | 6004556.65 | 5944653.73 | COMPLETED | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Mati City | 304321 | Lupon NCHS | LUPON | 2 | 1 | UPGRADING | 2 | 2039801.11 | 2024474.47 | COMPLETED | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Mati City | 304319 | Lupon Vocational High School | LUPON | 2 | 1 | UPGRADING | 2 | 6223202.35 | 6186729.69 | COMPLETED | 100% | 2019-01-24 |  |  |  | 2018-06-14 | 2018-05-29 | 2018-06-26 | 2018-07-10 | 2018-07-24 | MATT GLASS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Panabo City | 304405 | Don Manuel A. Javellana Memorial National High School | CITY OF PANABO | 2 | 1 | UPGRADING | 2 | 2086018.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Panabo City | 316401 | Southern Davao National High School | CITY OF PANABO | 2 | 1 | UPGRADING | 2 | 2972771.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Tagum City | 322401 | Canocotan National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 319590.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Tagum City | 304231 | Jose Tuason Jr. Memorial National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 884175.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Tagum City | 500426 | PANDAPAN INTEGRATED SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 195718.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XI | Tagum City | 304232 | Pipisan Maug National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | 2 | 523181.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Cotabato City | 304634 | Notre Dame Village National High School | COTABATO CITY | 1 | 1 | UPGRADING | 2 | 4427334.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 304646 | Gen. Santos City High School - Lanton High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2029337.58 |  | COMPLETED | 100% | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 500302 | General Santos City SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2502091.86 |  | COMPLETED | 100% | Oct. 21, 2018 | [5 empty] | May 15, 2018 |  | July 16, 2018 | Automatgeneric Trading and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 304650 | Labangal National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2441996.22 |  | COMPLETED | 100% | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | 2 | 4189628.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | UPGRADING | 2 | 5136663.58 | 4599881.29 | COMPLETED | 100% | January 24 2018 |  | GEPS 5410273 | I-2018-09-008 | June 8, 2018 | July 16, 2018 | July 30, 2018 | September 12, 2018 | September 24, 2018 | EC SOLICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304412 | Alamada NHS | ALAMADA | 1 | 1 | UPGRADING | 1 | 2028571.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304413 | Aleosan NHS | ALEOSAN | 1 | 1 | UPGRADING | 1 | 2024350.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 | 1 | UPGRADING | 1 | 2024562.0482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 | 1 | UPGRADING | 1 | 2024878.6232 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 | 1 | UPGRADING | 1 | 2028360.9482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304494 | Pikit NHS | PIKIT | 1 | 1 | UPGRADING | 1 | 2022240.4982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304415 | Antipas NHS | ANTIPAS | 2 | 1 | UPGRADING | 1 | 2029099.6232 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 | 1 | UPGRADING | 1 | 2035958.7482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304463 | Magpet NHS | MAGPET | 2 | 1 | UPGRADING | 1 | 2022768.1232 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304466 | Makilala NHS | MAKILALA | 2 | 1 | UPGRADING | 1 | 2021185.2482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2 | 1 | UPGRADING | 1 | 2023295.7482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | UPGRADING | 1 | 2041234.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 1992027.4212 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304444 | Kabacan NHS | KABACAN | 3 | 1 | UPGRADING | 1 | 2020129.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 | 1 | UPGRADING | 1 | 2024350.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304478 | Matalam NHS, Brgy Poblacion | MATALAM | 3 | 1 | UPGRADING | 1 | 2020129.9982 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 | 1 | UPGRADING | 1 | 2021712.8732 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | UPGRADING | 1 | 2025406.2482 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | South Cotabato | 304559 | Poblacion Polomolok NHS | POLOMOLOK | 1 | 1 | UPGRADING | 2 | 9864781.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | South Cotabato | 304556 | Maltana NHS | TAMPAKAN | 1 | 1 | UPGRADING | 2 | 6800902.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | UPGRADING | 2 | 3336871.31 | 2500055.17 | COMPLETED | 100% |  |  |  |  | Dec. 07, 2018 | Dec. 14, 2018 | Dec. 27, 2018 | Dec. 28, 2018 |  | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | UPGRADING | 2 | 4563975.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 | UPGRADING |  | 992187.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305078 | Boliney NHS | BOLINEY | 0 | 1 | UPGRADING |  | 1108709.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | UPGRADING |  | 1318849.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305089 | Luzong NHS | LUBA | 0 | 1 | UPGRADING |  | 1381279.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | 0 | 1 | UPGRADING |  | 1672920.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305083 | Dalit National High School | PILAR | 0 | 1 | UPGRADING |  | 1330923.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135128 | San Isidro CS | SAN ISIDRO | 0 | 1 | UPGRADING |  | 1336675.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135115 | Tubo CS | TUBO | 0 | 1 | UPGRADING |  | 1282350.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135167 | Villaviciosa CS | VILLAVICIOSA | 0 | 1 | UPGRADING |  | 1448062.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 4251489.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135230 | Butao ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 1441786.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135231 | Cadaclan ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 1431233.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305110 | Calanasan NHS | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135235 | Langnao Elementary School | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 388147.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135239 | Milagrosa ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2128382.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135242 | Namaltugan ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2144211.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 318804 | Tanglagan national high school | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135252 | Allangigan ES | CONNER | 0 | 1 | SOLAR PANEL | Batch 3 | 1441786.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 0 | 1 | UPGRADING | Batch 2 | 1152968.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135296 | Upper Atok ES | FLORA | 0 | 1 | SOLAR PANEL | Batch 3 | 367042.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135316 | Kalliat Elementary School | KABUGAO (Capital) | 0 | 1 | SOLAR PANEL | Batch 3 | 739360.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305119 | Mayor Bartolome Serut NATHS-Main | KABUGAO (Capital) | 0 | 1 | SOLAR PANEL | Batch 3 | 1447062.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 219009 | Lydia ES | PUDTOL | 0 | 1 | SOLAR PANEL | Batch 3 | 739360.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305109 | Sta. Marcela NHS | SANTA MARCELA | 0 | 1 | UPGRADING | Batch 2 | 1250284.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136403 | Apolinario Mabini ES | BAGUIO CITY | 0 | 1 | UPGRADING |  | 4509480.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305269 | Baguio City High School - Main | BAGUIO CITY | 0 | 1 | UPGRADING |  | 5022787.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305282 | Guisad Valley National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 5141432.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 2799253.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136413 | Loakan Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3789756.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136394 | Lucban Elementary school | BAGUIO CITY | 0 | 1 | UPGRADING |  | 4741551.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305281 | Pines City National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3198941.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3791913.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135372 | Adoyunan ES | ATOK | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135374 | Bilis Elementary School | ATOK | 0 | 1 | UPGRADING | Batch 3 | 443616.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135375 | Boneng ES | ATOK | 0 | 1 | UPGRADING | Batch 1 | 446782.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135400 | Ampusongan Elementary School | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135401 | Bagtangan ES | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135399 | Labinio-Mariano ES | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 444671.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135434 | Bisal ES | BOKOD | 0 | 1 | UPGRADING | Batch 3 | 445727.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135442 | Karao ES | BOKOD | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135447 | Naswak ES | BOKOD | 0 | 1 | UPGRADING | Batch 1 | 477385.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135457 | Abatan ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135459 | Alapang ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135460 | Amgaleyguey PS | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135461 | Amlimay ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135463 | Bacasen-Wakit ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451002.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135464 | Bad-ayan ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 448892.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135466 | Bangao Moreno ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 448892.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135468 | Bano-oy ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 3 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135469 | Bayoyo-Lukingan-Awal ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135501 | Baguio Gold Elementary School | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135502 | Binga ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135504 | Botic ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135505 | Gumatdang ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 999019.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135508 | Loacan ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135500 | Maximino Fianza Lopez ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135539 | Adaoay ES | KABAYAN | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135562 | Balakbak ES | KAPANGAN | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135563 | Beleng-Belis Barrio School | KAPANGAN | 0 | 1 | UPGRADING | Batch 3 | 445727.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135565 | Boklaoan ES | KAPANGAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135633 | Talinguroy ES | LA TRINIDAD (Capital) | 0 | 1 | UPGRADING | Batch 3 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135636 | Am-am ES | MANKAYAN | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135641 | Baguyos PS | MANKAYAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135673 | Bayabas MG School | SABLAN | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135672 | Omas Ampaguey ES | SABLAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135686 | Asin ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 444671.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135687 | Batuan ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135688 | Camp 3 ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135689 | Camp 4 ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135718 | Albis ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135719 | Ambongdolan ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135720 | Baayan ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | 0 | 1 | UPGRADING | Batch 3 | 442561.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135740 | Aguinaldo Central School | AGUINALDO | 0 | 1 | UPGRADING | Batch 3 | 1095258.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305166 | Aguinaldo NHS | AGUINALDO | 0 | 1 | UPGRADING | Batch 3 | 1000900 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319002 | Rufino I. Chungalao Science HS | AGUINALDO | 0 | 1 | UPGRADING | Batch 1 | 928926.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305194 | Ubao National High School | AGUINALDO | 0 | 1 | UPGRADING | Batch 1 | 1501140.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135763 | Alfonso Lista CS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | Batch 3 | 1403195.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305189 | Caragasan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | Batch 1 | 1088862.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | 0 | 1 | UPGRADING | Batch 1 | 1756050.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135788 | Asipulo CS | ASIPULO | 0 | 1 | UPGRADING | Batch 3 | 707990.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305175 | Camandag NHS | ASIPULO | 0 | 1 | UPGRADING | Batch 3 | 1003631.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135813 | Banaue CS | BANAUE | 0 | 1 | UPGRADING |  | 1166975.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305170 | Banaue National High School | BANAUE | 0 | 1 | UPGRADING | Batch 1 | 1219978.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305172 | Gohang NHS | BANAUE | 0 | 1 | UPGRADING |  | 1217067.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135836 | Hingyon CS | HINGYON | 0 | 1 | UPGRADING | Batch 3 | 730337.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305178 | Hingyon NHS | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 1414870.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 340118 | SHS within Namulditan ES | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 859787.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305179 | Southern Hingyon NHS | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 810052.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135855 | Hungduan CS | HUNGDUAN | 0 | 1 | UPGRADING | Batch 3 | 726572.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135871 | Kiangan Central School | KIANGAN | 0 | 1 | UPGRADING | Batch 1 | 1258608.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | 0 | 1 | UPGRADING | Batch 1 | 1414680.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305169 | Caba National High School | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 796168.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135887 | Lagawe Central School | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1359033.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319004 | Lagawe NHS | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 846712.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135891 | Ponghal ES | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1143534.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 500882 | ALUPAPAN INTEGRATED SCHOOL | LAMUT | 0 | 1 | UPGRADING | Batch 1 | 675569.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135902 | Lamut CS | LAMUT | 0 | 1 | UPGRADING | Batch 3 | 1368574.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319007 | Lawig National High School Extension | LAMUT | 0 | 1 | UPGRADING | Batch 3 | 581723.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305184 | Mongilit Ligmayo NHS | LAMUT | 0 | 1 | UPGRADING | Batch 1 | 803186.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135934 | Mayoyao Central School | MAYOYAO | 0 | 1 | UPGRADING | Batch 3 | 1135181.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305185 | Mayoyao NHS | MAYOYAO | 0 | 1 | UPGRADING | Batch 1 | 1424577.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305186 | Tulaed NHS | MAYOYAO | 0 | 1 | UPGRADING | Batch 1 | 675856.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305193 | Kalanguya NHS | TINOC | 0 | 1 | UPGRADING | Batch 1 | 1000900 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | 0 | 1 | UPGRADING | Batch 3 | 1013774.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 135962 | Balbalan Central School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 1263762.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 135985 | Tawang Elementary School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 704039.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 1044786.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136019 | Cagaluan Elementary School | PASIL | 0 | 1 | UPGRADING | Batch 1 | 776895.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136032 | Allaguia Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 712552.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305197 | Allaguia National High School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 1575692.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136048 | Magaogao Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 712552.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136056 | Pinococ Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 831588.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136061 | Socbot Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 834443.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 319109 | Socbot National High School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 1541808.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136038 | Wagud Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 756556 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136065 | Andarayan Elementary School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 3 | 726041.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305209 | Kinama National High School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 1 | 1707703.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136074 | Macutay Elementary School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 3 | 861477.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 220509 | Magtoma Elementary School | TANUDAN | 0 | 1 | UPGRADING | Batch 3 | 585916.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136134 | Bangad Elementary School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 721009.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136145 | Luplupa Elementary School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 787014.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305219 | Sumadel National High School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 1154886.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136185 | Barlig Central School | BARLIG | 0 | 1 | UPGRADING | Batch 3 | 817110.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136187 | KALEO ELEMENTARY SCHOOL | BARLIG | 0 | 1 | UPGRADING | Batch 3 | 895939.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136199 | Bagnen Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 840525.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305232 | Bagnen National High School | BAUKO | 0 | 1 | UPGRADING |  | 968605.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136198 | Bagnen Oriente Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 858186.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | 0 | 1 | UPGRADING |  | 923473.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305249 | Bansa National High School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 818364.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136202 | Bauko Central School | BAUKO | 0 | 1 | UPGRADING |  | 817110.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136204 | Bila Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 818364.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136205 | Binaka ES | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 817110.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305248 | Mabaay National High School | BAUKO | 0 | 1 | UPGRADING |  | 906852.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136231 | Tapapan Elementary School | BAUKO | 0 | 1 | UPGRADING |  | 818364.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305254 | Tipunan National High School | BAUKO | 0 | 1 | UPGRADING |  | 802231.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136234 | Banguitan Elementary School | BESAO | 0 | 1 | UPGRADING |  | 840525.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136244 | Panabungen Elementary School | BESAO | 0 | 1 | UPGRADING |  | 971201.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319208 | Tamboan National High School | BESAO | 0 | 1 | UPGRADING |  | 852145.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305228 | Albago National High School | BONTOC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 694164.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136270 | Layog-Ogtong Elementary School | NATONIN | 0 | 1 | UPGRADING | Batch 3 | 967491.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | 0 | 1 | UPGRADING | Batch 3 | 1022357.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136277 | Saliok Elementary School | NATONIN | 0 | 1 | UPGRADING |  | 874004.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319209 | Buringal National High School | PARACELIS | 0 | 1 | UPGRADING |  | 939565.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319202 | San Rafael National High School | PARACELIS | 0 | 1 | UPGRADING |  | 884625.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136321 | Lagan Elementary School | SABANGAN | 0 | 1 | UPGRADING |  | 852948.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136324 | Namatec Elementary School | SABANGAN | 0 | 1 | UPGRADING |  | 879716.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136328 | Sabangan Central School | SABANGAN | 0 | 1 | UPGRADING | Batch 3 | 759448.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | 0 | 1 | UPGRADING |  | 960056.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305229 | Antadao National High School | SAGADA | 0 | 1 | UPGRADING | Batch 3 | 819945.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136357 | Banaao Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 850750.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136362 | Cagubatan Elementary School | TADIAN | 0 | 1 | UPGRADING | Batch 3 | 821542.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136369 | Lubon Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 818364.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 1031773.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136085 | Agbannawag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1397703.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136000 | Appas Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1431378.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 1434875.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 3208494.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136004 | Casigayan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1459106.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136009 | Magsaysay Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1456894.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136089 | Southern Tabuk CS | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1459259.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 3208494.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 1617645.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317310 | E. G. Montilla NHS (Mat-I NHS Annex) | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 704990.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500048 | Lawan-Lawan IS (Secondary Level) | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 843620.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304690 | LINGAYAO NATIONAL HIGH SCHOOL | LAS NIEVES | 1 | 1 | UPGRADING |  | 940467.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304693 | Maningalao NHS | LAS NIEVES | 1 | 1 | UPGRADING | Batch 3 | 747559.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304695 | Mat-i NHS | LAS NIEVES | 1 | 1 | UPGRADING |  | 995143.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317314 | Abilan NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING | Batch 3 | 862491.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317315 | Agong-ong NHS (Buenavista NHS Annex | BUENAVISTA | 2 | 1 | UPGRADING |  | 1052871.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500047 | Buenavista SPED IS (Secondary Level) | BUENAVISTA | 2 | 1 | UPGRADING |  | 785900.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317305 | Lekda NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING | Batch 3 | 1118711.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317317 | Rizal NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | UPGRADING |  | 1641299.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317301 | Sangay National High School | BUENAVISTA | 2 | 1 | UPGRADING |  | 826272.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304683 | Simbalan NHS - Guinabsan NHS Annex | BUENAVISTA | 2 | 1 | UPGRADING |  | 1045919.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500311 | Manoligao IS (Secondary Level) | CARMEN | 2 | 1 | UPGRADING | Batch 3 | 777700.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 340204 | SHS in Carmen, Agusan Del Norte | CARMEN | 2 | 1 | UPGRADING |  | 1169355.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304702 | Vinapor NHS | CARMEN | 2 | 1 | UPGRADING | Batch 3 | 888563.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317319 | Bangonay NHS | JABONGA | 2 | 1 | UPGRADING | Batch 3 | 848076.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304678 | Cuyago NHS | JABONGA | 2 | 1 | UPGRADING |  | 737006.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304692 | Magdagooc NHS | JABONGA | 2 | 1 | UPGRADING |  | 752717.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317303 | San Vicente NHS | JABONGA | 2 | 1 | UPGRADING |  | 657461.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304687 | Jaliobong NHS | KITCHARAO | 2 | 1 | UPGRADING |  | 814349.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317308 | Culit National High School (Nasipit National Vocational School Annex) | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 888356.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 500314 | Hinandayan IS (Secondary Level) | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 864725.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | NOT-IN-NSBI | Nasipit NHS EXT. | NASIPIT | 2 | 1 | UPGRADING | Batch 3 | 760940.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 317311 | Balangbalang NHS (Agay NHS Annex) | REMEDIOS T. ROMUALDEZ | 2 | 1 | UPGRADING |  | 696535.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Norte | 304700 | Tinigbasan NHS | TUBAY | 2 | 1 | UPGRADING | Batch 3 | 944933.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 | 1 | UPGRADING |  | 5368286.81 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-001 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO | 2 | 1 | UPGRADING |  | 6924016.46 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-002 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304717 | Lapinigan National High School | SAN FRANCISCO | 2 | 1 | UPGRADING |  | 4151839.06 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-003 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304750 | Sta. Josefa National High School | SANTA JOSEFA | 2 | 1 | UPGRADING | Batch 3 | 7402004.11 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-004 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | UPGRADING |  | 4918248.24 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-005 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Agusan del Sur | 317445 | Veruela NHS Annex - Nueva Era HS | VERUELA | 2 | 1 | UPGRADING | Batch 3 | 3020197.72 |  | COMPLETED | 100% |  |  | 6311080 | 2019-02-006 | JULY 11, 2019 | JULY 17, 2019 | AUGUST 07, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304707 | Bayugan NCHS | CITY OF BAYUGAN | 1 | 1 | UPGRADING |  | 3628416.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304732 | Salvacion National High School | CITY OF BAYUGAN | 1 | 1 | UPGRADING | Batch 3 | 1669797.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bayugan City | 304735 | SAN JUAN NATIONAL HIGH SCHOOL | CITY OF BAYUGAN | 1 | 1 | UPGRADING | Batch 3 | 1457873.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 1521189.69 | 1049912.04 | COMPLETED | 100% | 2020-01-02 |  | Electrification-Cluster 1 | 2019E-005 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1645959.26 | 1474578 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132838 | Caramcam Central ES | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 892769.64 | 620890.22 | COMPLETED | 100% | December 3, 2019 |  | Electrification-Cluster 2 | 2019E-006 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1042710.07 | 1140961.06 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1391390.96 | 1246108 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1648913.07 | 936981.59 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132833 | Mangagoy CES | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 978905.45 | 676985.52 | COMPLETED | 100% | December 3, 2019 |  | Electrification-Cluster 2 | 2019E-006 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132843 | Plaza CES | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 803582.41 | 719848.67 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 1 | 2019E-003 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2 | 1 | UPGRADING | Batch 3 | 1350800.29 | 932482.36 | COMPLETED | 100% | 2020-01-02 |  | Electrification-Cluster 1 | 2019E-005 | June 28, 2019 | July 8, 2019 | July 22, 2019 | Aug. 16, 2019 | Aug. 28, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Bislig City | 304917 | Tabon M. Estrella National High School | CITY OF BISLIG | 2 | 1 | UPGRADING |  | 1270572.67 | 1479959.16 | COMPLETED | 100% | December 14, 2019 |  | Electrification-Cluster 2 | 2019E-004 | Oct. 26, 2018 | Nov. 6, 2018 | Nov. 19, 2018 | Aug. 02, 2019 | Aug. 09, 2019 | MAG Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 100% |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 132023 | Butuan Central Elementary School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1684905.35 | 1147508.93 | COMPLETED | 100% | 2020-01-03 |  | ESHS-2018-001 | ESHS-2018-001 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 100% |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 100% | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1663800.35 | 1654361.99 | COMPLETED | 100% |  |  | ESHS-2019-001 |  | 2019-06-03 | 2019-07-05 | 2019-07-08 | 2019-09-06 |  | Arcler Builder and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304764 | Los Angeles National High School | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 100% | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304767 | Maguinda NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1663800.35 | 1147508.93 | COMPLETED | 100% | 2020-01-03 |  | ESHS-2018-001 | ESHS-2018-001 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1684905.35 | 1146894.68 | COMPLETED | 100% | 2020-01-03 |  | ESHS-2018-002 | ESHS-2018-002 | 2018-12-06 | 2018-12-14 | 2018-12-27 | 2019-01-11 | 2019-09-05 | Maxter Resources Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | CITY OF CABADBARAN | 2 | 1 | UPGRADING |  | 2424321.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Cabadbaran City | 317307 | Del Pilar NHS | CITY OF CABADBARAN | 2 | 1 | UPGRADING | Batch 3 | 1819429.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 | 1 | UPGRADING | Batch 2 | 2963774.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 | 1 | UPGRADING | Batch 2 | 2442378.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | 0 | 1 | UPGRADING | Batch 2 | 2671625.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2643133.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317801 | Rosita National High School | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2442378.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 | 1 | UPGRADING | Batch 2 | 2641134.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304828 | Loreto National high school | LORETO | 0 | 1 | UPGRADING | Batch 2 | 2682178.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 2 | 2454098.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 | 1 | UPGRADING | Batch 2 | 2661072.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 | 1 | UPGRADING | Batch 3 | 3000000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1 | 1 | UPGRADING |  | 3050000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500574 | Cabangahan Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1127964.11 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304873 | Cantilan National High School | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1653184.94 | 1152745 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317928 | Cantilan National High School - Consuelo Annex | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1255260.45 | 874592.77 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500575 | Isla General Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1005489.5 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500570 | Palasao Integrated School | CANTILAN | 1 | 1 | UPGRADING | Batch 3 | 1466804.64 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304901 | Parang National High School | CANTILAN | 1 | 1 | UPGRADING | Batch 1 | 1314111.13 | 915662.23 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-018 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304875 | Carmen National Agricultural High School | CARMEN | 1 | 1 | UPGRADING | Batch 1 | 1221860.92 | 850951.6 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | NOT-IN-NSBI | Esperanza ISS (Carmen Nat'l. Agr'l. HS - Esperanza NHS Annex) | CARMEN | 1 | 1 | UPGRADING | Batch 3 | 1212892.15 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304857 | Adlay National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 1 | 1928978.57 | 1344126.05 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-019 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304877 | Carrascal National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 1 | 2851263.4 | 1985873.95 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-019 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304900 | Panikian National High School | CARRASCAL | 1 | 1 | UPGRADING | Batch 3 | 1375891.89 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304872 | Burgos National High School | CORTES | 1 | 1 | UPGRADING | Batch 1 | 1500271.3 | 1045028.28 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304886 | Felisberto Verano National high school | CORTES | 1 | 1 | UPGRADING | Batch 1 | 1538865.71 | 1073020.11 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-016 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500321 | Matho IS | CORTES | 1 | 1 | UPGRADING | Batch 3 | 1621790.35 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304887 | Tigao National High School | CORTES | 1 | 1 | UPGRADING | Batch 3 | 1750041.35 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500578 | Agsam Integrated School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1785447.51 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304885 | Florita Herrera-Irizari National High School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1294402.28 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500320 | Nurcia Integrated School | LANUZA | 1 | 1 | UPGRADING | Batch 3 | 1716311.05 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304897 | Madrid National High School | MADRID | 1 | 1 | UPGRADING | Batch 1 | 2374996.94 | 1655268.67 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-017 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317904 | Madrid NHS - Union NHS Annex | MADRID | 1 | 1 | UPGRADING | Batch 1 | 1137072.29 | 791731.33 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-017 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304863 | Javier National High School | BAROBO | 2 | 1 | UPGRADING | Batch 1 | 1129903.06 | 786377.82 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 317921 | Wakat National High School | BAROBO | 2 | 1 | UPGRADING | Batch 1 | 640212.7 | 445893.95 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 500572 | Bingcongan Integrated School | HINATUAN | 2 | 1 | UPGRADING | Batch 1 | 1435055.36 | 998411.64 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-014 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy National High School | HINATUAN | 2 | 1 | UPGRADING | Batch 1 | 1186757.78 | 828588.36 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-014 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304878 | Doña Carmen National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 3 | 1051052.86 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304882 | San Vicente II National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 3 | 1109868.75 |  | COMPLETED | 100% |  |  |  |  | AUGUST 30, 2019 | SEPTEMBER 11, 2019 | SEPTEMBER 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 | 1 | UPGRADING | Batch 1 | 1260411.86 | 878728.24 | COMPLETED | 100% | 2019-12-19 |  |  | 2019-015 | 2018-11-14 | 2018-11-23 | 2018-12-07 | 2019-04-10 | 2019-09-12 | Equator Energy |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304871 | Buenavista National High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1468612.62 |  | COMPLETED | 100% |  |  |  |  | July 29, 2019 | August 13, 2019 | August 29 2019 |  |  | MAG Constuction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304871 | Buenavista National High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING |  | 1548603.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CARAGA | Tandag City | 304922 | Tandag National Science High School | CITY OF TANDAG (Capital) | 1 | 1 | UPGRADING | Batch 2 | 1646127.05 |  | COMPLETED | 100% |  |  |  |  | July 29, 2019 | August 13, 2019 | August 29 2019 |  |  | MAG Constuction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | KALOOKAN CITY | 2 | 1 | UPGRADING | Batch 1 | 3589077.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | City of San Juan | 136749 | Kabayanan ES | CITY OF SAN JUAN | 0 | 1 | UPGRADING | Batch 1 | 2568525.8 | 2545618.14 | COMPLETED | 100% | NOVEMBER 29,2019 |  | PROJECT INFRA 2019-002 | DSJ-CY19-INFRA002 | JULY 31,2019 | AUGUST 7,2019 | AUGUST 19,2019 | AUGUST 28,2019 | OCT. 11, 2019 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | 0 | 1 | UPGRADING | Batch 3 | 1916775.3 | 1899112.96 | COMPLETED | 100% | NOVEMBER 29,2019 |  | PROJECT INFRA 2019-003 | DSJ-CY19-INFRA003 | JULY 19,2019 | AUGUST 7,2019 | AUGUST 19,2019 | AUGUST 28,2019 | OCT. 11, 2019 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 778980.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 1306702.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136838 | Tañong ES I | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 5804008.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | Batch 1 | 5897707.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC | 4 | 1 | UPGRADING | Batch 1 | 1099606.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5 | 1 | UPGRADING | Batch 1 | 1178788.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 136481 | J. Zamora Elementary School | PANDACAN | 6 | 1 | UPGRADING | Batch 1 | 2126244.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 492401.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 511212.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 717615.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 796014.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Muntinlupa City | 303450 | Cupang Senior High School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | Batch 1 | 3705688.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | UPGRADING | Batch 3 | 3141017.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | UPGRADING |  | 507323.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Alaminos City | 300157 | Alos NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 502151.58 | 498392.85 | COMPLETED | 100% | 0CT. 10, 2019 | SEPT. 16, 2019 | INFRA-2018-12-14 | INFRA-2018-12-14 | NOV. 21-28, 2018 | NOv. 27, 2018 | Dec. 12, 2018 | DEC. 18, 2018 | AUG. 12, 2019 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Alaminos City | 300253 | San Vicente NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1560326.86 | 1550655.04 | COMPLETED | 100% | 0CT. 10, 2019 | SEPT. 16, 2019 | INFRA-2018-12-14 | INFRA-2018-12-14 | NOV. 21-28, 2018 | NOv. 27, 2018 | Dec. 12, 2018 | DEC. 18, 2018 | AUG. 12, 2019 | ALCEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 2277028.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 279530.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100437 | Caterman Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 543662.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Candon City | 100440 | Darapidap Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 413843.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | UPGRADING | Batch 1 | 14039604.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1 | 1 | UPGRADING |  | 558498.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300004 | Banna National High School | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 650906.33 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300011 | Catagtaguen National High School | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 681708.79 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320805 | Currimao NHS (Pias-Gaang Campus) | CURRIMAO | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320808 | Dingras NHS/Lt. Edgar Foz Mem. NHS (San Marcos Campus) | DINGRAS | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320810 | SUYO NATIONAL HIGH SCHOOL | DINGRAS | 2 | 1 | UPGRADING |  | 650906.33 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320811 | Marcos NHS (Agunit Campus) | MARCOS | 2 | 1 | UPGRADING |  | 650906.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | UPGRADING |  | 650906.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon NHS | NUEVA ERA | 2 | 1 | UPGRADING |  | 589301.41 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 500594 | Uguis Integrated School | NUEVA ERA | 2 | 1 | UPGRADING |  | 681708.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2 | 1 | UPGRADING |  | 866523.57 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 300027 | Pinili NHS | PINILI | 2 | 1 | UPGRADING |  | 727912.49 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2 | 1 | UPGRADING |  | 727912.49 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320817 | Bagbag Solsona National High School | SOLSONA | 2 | 1 | UPGRADING |  | 620103.87 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Norte | 320818 | Talugtog Solsona National High School | SOLSONA | 2 | 1 | UPGRADING |  | 712511.26 |  | REVERTED | 0% | [10 empty] | TERMINATED | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | UPGRADING |  | 1365318.52 |  | COMPLETED | 100% | 2019-10-14 | 2019-10-15 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-15 | MA TEJADA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300057 | Magsingal NHS | MAGSINGAL | 1 | 1 | UPGRADING |  | 1402550.73 |  | COMPLETED | 100% | 2019-10-14 | 2019-10-15 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-15 | MA TEJADA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300058 | Manzante NHS | MAGSINGAL | 1 | 1 | UPGRADING |  | 1034183.81 |  | COMPLETED | 100% | 2019-10-20 | 2020-06-28 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-22 | RAMSA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300041 | Burgos National High School | BURGOS | 2 | 1 | UPGRADING |  | 1475986.51 |  | COMPLETED | 100% | 2019-10-20 |  |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-22 | RAMSA CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300046 | Cervantes NHS | CERVANTES | 2 | 1 | UPGRADING |  | 1306978.36 |  | COMPLETED | 100% | 2019-10-22 | 2020-01-17 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-24 | WWW. CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2 | 1 | UPGRADING |  | 1405288.56 |  | COMPLETED | 100% | 2019-10-11 | 2020-01-23 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-13 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 300085 | Suyo NHS | SUYO | 2 | 1 | UPGRADING |  | 1399465.28 |  | COMPLETED | 100% | 2019-10-22 | 2020-01-17 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-24 | WWW. CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Ilocos Sur | 500349 | Ambalayat IS | TAGUDIN | 2 | 1 | UPGRADING |  | 916943.61 |  | COMPLETED | 100% | 2019-10-11 | 2020-01-23 |  |  | 2018-11-12 | 2018-11-19 | 2018-12-05 | 2018-12-13 | 2019-08-13 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300095 | BACNOTAN NHS | BACNOTAN | 1 | 1 | UPGRADING |  | 1906451.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 500351 | Bitalag Integrated School | BACNOTAN | 1 | 1 | UPGRADING |  | 1544809.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300111 | PARAOIR NHS | BALAOAN | 1 | 1 | UPGRADING | Batch 3 | 1098395.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300114 | DOÑA FRANCISCA LACSAMANA DE ORTEGA MEMORIAL NATIONAL HIGH SCHOOL | BANGAR | 1 | 1 | UPGRADING |  | 1299958.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300132 | Regional Science HS, La Union | BANGAR | 1 | 1 | UPGRADING |  | 1012671.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300120 | LUNA NHS | LUNA | 1 | 1 | UPGRADING |  | 1370937.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300135 | San Gabriel Vocational High School | SAN GABRIEL | 1 | 1 | UPGRADING |  | 1885466.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 340825 | SHS within San Gabriel CS | SAN GABRIEL | 1 | 1 | UPGRADING |  | 850444.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300148 | Sudipen Voc'l Sch. | SUDIPEN | 1 | 1 | UPGRADING | Batch 3 | 1026903.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300139 | Dr. Manuel T. Cases Sr. National High School | AGOO | 2 | 1 | UPGRADING | Batch 3 | 1005801.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300129 | Pres. Elpidio. Quirino NHS | AGOO | 2 | 1 | UPGRADING |  | 1116662.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300094 | BACCUIT NHS | BAUANG | 2 | 1 | UPGRADING |  | 958860.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300104 | CABA NHS | CABA | 2 | 1 | UPGRADING | Batch 3 | 1083702.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300122 | Naguilian National HS | NAGUILIAN | 2 | 1 | UPGRADING |  | 1175756.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300131 | PUGO CENTRAL NHS | PUGO | 2 | 1 | UPGRADING | Batch 3 | 1047910.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300110 | ALIPANG NHS | ROSARIO | 2 | 1 | UPGRADING | Batch 3 | 755316.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 500002 | Rosario Integrated School | ROSARIO | 2 | 1 | UPGRADING |  | 1993175.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 300109 | DAMORTIS NHS | SANTO TOMAS | 2 | 1 | UPGRADING | Batch 3 | 1344792.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | La Union | 321010 | Sto. Tomas NHS | SANTO TOMAS | 2 | 1 | UPGRADING | Batch 3 | 1074660.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 500056 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1733471.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 305601 | Caaoacan High School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1293828.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2941485.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Laoag City | 300375 | Ilocos Norte Regional School of Fisheries | LAOAG CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2662684.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1 | 1 | UPGRADING | Batch 2 | 1167558.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500607 | Bacnit Integrated School | MABINI | 1 | 1 | UPGRADING | Batch 2 | 1212450.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan NHS | MABINI | 1 | 1 | UPGRADING | Batch 2 | 1184953.07 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500605 | Aguilar Integrated School | AGUILAR | 2 | 1 | UPGRADING | Batch 2 | 1591348.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300170 | BAYOYONG NHS | BASISTA | 2 | 1 | UPGRADING | Batch 2 | 1305064.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500610 | BUGALLON INTEGRATED SCHOOL | BUGALLON | 2 | 1 | UPGRADING | Batch 2 | 1424138.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300241 | POLONG NATIONAL HIGH SCHOOL | BUGALLON | 2 | 1 | UPGRADING | Batch 2 | 1409579.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300209 | Labrador NHS | LABRADOR | 2 | 1 | UPGRADING | Batch 2 | 1403799.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 500367 | Domalandan Center IS | LINGAYEN (Capital) | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300203 | Estanza NHS | LINGAYEN (Capital) | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300181 | Cabayaoasan NHS | MANGATAREM | 2 | 1 | UPGRADING | Batch 2 | 1424138.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300218 | Macarang National High School | MANGATAREM | 2 | 1 | UPGRADING | Batch 2 | 1364601.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300247 | Real National High School | URBIZTONDO | 2 | 1 | UPGRADING | Batch 2 | 1432831.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba NHS | SANTA BARBARA | 3 | 1 | UPGRADING | Batch 2 | 1350042.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan I, Lingayen | 300225 | Maticmatic NHS | SANTA BARBARA | 3 | 1 | UPGRADING | Batch 2 | 1305064.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300276 | Arboleda NHS | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1370898.6 | 1358579.39 | COMPLETED | 100% | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300288 | Bersamin Agro-Industrial HS | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1149498.32 | 1141250.33 | COMPLETED | 100% | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300335 | Pindangan National High School -Alcala | ALCALA | 5 | 1 | UPGRADING | Batch 3 | 1220551.4 | 1078561.27 | COMPLETED | 100% | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300286 | Bautista National High School | BAUTISTA | 5 | 1 | UPGRADING | Batch 3 | 1662857.3 | 1649849.92 | COMPLETED | 100% | 2020-02-02 | 1/30/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | UPGRADING | Batch 3 | 1643624.88 | 1623000.07 | COMPLETED | 100% | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300306 | Don Benito Agro-Industrial High School | POZORRUBIO | 5 | 1 | UPGRADING | Batch 3 | 864595.59 | 843721.68 | COMPLETED | 100% | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | WWW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300332 | Palguyod NHS | POZORRUBIO | 5 | 1 | UPGRADING | Batch 3 | 851898.63 | 739738.11 | COMPLETED | 100% | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300270 | Amagbagan Integrated School | SISON | 5 | 1 | UPGRADING | Batch 3 | 1101410.69 | 1093593.44 | COMPLETED | 100% | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | ILS POWER ENGINEERING SERVICES & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Pangasinan II, Binalonan | 300278 | Artacho NHS | SISON | 5 | 1 | UPGRADING | Batch 3 | 927791.35 | 871721.68 | COMPLETED | 100% | 2020-02-02 | 1/20/2020 |  |  | 9/23/2019 | 9/30/2019 | 10/14/2020 | 10/30/2019 | 2019-05-11 | WWW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 807410.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 968218.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 321001 | La Union NHS - Sacyud Annex | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 680650.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500530 | Nagyubuyuban IS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 973082.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500480 | Pagudpud IS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1251836.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 300126 | Pao National High School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 674265.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 101032 | Parparya ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 878446.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 101033 | Puspus ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 880015.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | San Fernando City | 500481 | SIBUAN-OTONG INTEGRATED SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1021285.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | UPGRADING |  | 1289747.82 |  | COMPLETED | 100% | December 26,2019 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Urdaneta City | 300403 | Mariano Q. Umipig NHS | CITY OF URDANETA | 5 | 1 | UPGRADING |  | 1160998.01 |  | COMPLETED | 100% | December 26, 2019 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Vigan City | 300088 | Vigan National High School East | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 1991860.37 | 1973058.97 | COMPLETED | 100% | November 19, 2019 |  | 2019-003-001 | INFRA-2019-004 | November 5, 2019 | November 12, 2019 | November 26, 2019 |  |  | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region I | Vigan City | 300089 | Vigan West NHS (Vigan NHS West) | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 1105485.98 | 1051695.11 | COMPLETED | 100% | November 19, 2019 |  | 2019-003-001 | INFRA-2019-004 | November 5, 2019 | November 12, 2019 | November 26, 2019 |  |  | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Batanes | 102316 | Itbayat Central School | ITBAYAT | 0 | 1 | UPGRADING | Batch 3 | 1380118.87 |  | TERMINATED | 85% | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 85% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | 0 | 1 | UPGRADING | Batch 1 | 1350673.21 |  | TERMINATED | 85% | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 85% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | UPGRADING | Batch 1 | 1499384.73 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2019 | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1 | 1 | UPGRADING | Batch 3 | 841345.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1 | 1 | UPGRADING |  | 518902.41 |  | TERMINATED | 85% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 85% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1 | 1 | UPGRADING |  | 571278.61 |  | TERMINATED | 40% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 40% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1 | 1 | UPGRADING | Batch 3 | 546120.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Cagayan | 306014 | LUBO NATIONAL HIGH SCHOOL | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING | Batch 3 | 570776.31 |  | TERMINATED | 40% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 40% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 300491 | Sto. Nino NHS | SANTO NIÑO (FAIRE) | 2 | 1 | UPGRADING |  | 570776.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 766345.96 |  | TERMINATED | 40% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 40% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 300453 | Bayabat NHS | AMULUNG | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | TERMINATED | 60% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 60% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3 | 1 | UPGRADING |  | 870957.81 |  | TERMINATED | 55% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 55% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3 | 1 | UPGRADING |  | 696444.35 |  | TERMINATED | 45% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | Y | 45% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2019 | Region II | Cagayan | 300427 | Dassun NHS | SOLANA | 3 | 1 | UPGRADING | Batch 3 | 660427.53 |  | COMPLETED | 100% | [10 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 4.25 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3 | 1 | UPGRADING | Batch 1 | 1131302.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300548 | Dappat Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1188658.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1285590.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500992 | Ilagan East Integrated SPED Center | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 1 | 1105333.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103402 | Ilagan South CS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 4454556.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300540 | Ilagan West NHS | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1051958.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 306149 | ISAT-Cabannungan Annex | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1210672.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1441858.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500078 | Manaring IS (Bangag-Manaring-Capo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1441858.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103428 | Naguilian Baculud Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1333997.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300543 | Rang-ayan NHS (Isabela NHS - Rang-ayan Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1179541.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 103375 | San Juan Rugao ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2704783.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500018 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1314275.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500074 | San Pedro Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 1951396.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300584 | San Rafael Nat'l & Voc'l HS (San Antonio NAIVHS-San Rafael Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING |  | 2788608.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 500731 | Sindun Bayabo ES | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1506073.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | City of Ilagan | 300602 | Sta. Isabel National High School | ILAGAN CITY (CAPITAL) | 1 | 1 | UPGRADING | Batch 3 | 1640651.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500072 | Villaluz Integrated School | BENITO SOLIVEN | 2 | 1 | UPGRADING | Batch 1 | 896259.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500067 | Dolores Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 1583860.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500082 | Sto. Domingo Integrated School | QUIRINO | 2 | 1 | UPGRADING | Batch 1 | 2207057.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1547472.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 2006254.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103643 | Roxas West Central School | ROXAS | 2 | 1 | UPGRADING | Batch 1 | 1834801.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103719 | San Manuel Central School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1841706.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103722 | Sandiat Elementary School | SAN MANUEL | 2 | 1 | UPGRADING | Batch 1 | 1950705.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500014 | Del Pilar Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1323664.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103742 | San Mariano Central School SPED Center | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1284553.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500095 | San Mariano II Central Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1042522.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1752890.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500069 | Sta. Filomena Integrated School | SAN MARIANO | 2 | 1 | UPGRADING | Batch 1 | 1272500.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103005 | Alicia Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1973948.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 102995 | Alicia East Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1442381.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 102988 | Alicia North Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1225691.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103006 | Alicia West Central School | ALICIA | 3 | 1 | UPGRADING | Batch 1 | 1538337.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103052 | Angadanan Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1640341.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103022 | Angadanan East Central School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1602022.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500017 | Fugaru Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1428785.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500023 | Sto. Niño Integrated School | ANGADANAN | 3 | 1 | UPGRADING | Batch 1 | 1747331.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103165 | Cabatuan East Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1808491.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103166 | Cabatuan West Central School | CABATUAN | 3 | 1 | UPGRADING | Batch 1 | 1743926.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103487 | Luna Central School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1909573.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 3 | 1 | UPGRADING | Batch 1 | 1491548.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103690 | San Guillermo Central School | SAN GUILLERMO | 3 | 1 | UPGRADING | Batch 1 | 1705607.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103788 | San Mateo East Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1183725.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103779 | San Mateo North Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1358662.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103789 | San Mateo West Central School | SAN MATEO | 3 | 1 | UPGRADING | Batch 1 | 1550060.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103258 | Cordon North Central School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103247 | Cordon South Central School-Main | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1674242.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING | Batch 1 | 1290802.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1649125.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1646429.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103311 | Echague South Central School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1231232.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 4 | 1 | UPGRADING | Batch 1 | 1135675.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1598089.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | UPGRADING | Batch 1 | 1551051.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 103469 | Jones West Central School Campus 1 | JONES | 4 | 1 | UPGRADING | Batch 1 | 1613921.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 300582 | San Agustin National High School | SAN AGUSTIN | 4 | 1 | UPGRADING | Batch 1 | 1695215.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 500091 | Cebu Integrated Sschool | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1592559.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 4 | 1 | UPGRADING | Batch 1 | 1283365.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300618 | Aritao National High School | ARITAO | 0 | 1 | UPGRADING | Batch 1 | 4500080.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | 0 | 1 | UPGRADING | Batch 1 | 2443832.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300631 | Kasibu National Agricultural School | KASIBU | 0 | 1 | UPGRADING | Batch 1 | 4982144.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | UPGRADING | Batch 1 | 5149791.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Nueva Vizcaya | 300646 | Solano High School | SOLANO | 0 | 1 | UPGRADING | Batch 3 | 12204160.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104238 | Aglipay East CS (Progreso ES) | AGLIPAY | 0 | 1 | UPGRADING |  | 929420.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104248 | Victoria Elementary School Annex | AGLIPAY | 0 | 1 | UPGRADING |  | 555784.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104247 | Victoria ES | AGLIPAY | 0 | 1 | UPGRADING |  | 637574.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104254 | Burgos Elementary School | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 757282.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104264 | Mangandingay ES | CABARROGUIS (Capital) | 0 | 1 | UPGRADING |  | 961848.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104280 | Diffun CS - Integrated SPED Center | DIFFUN | 0 | 1 | UPGRADING |  | 1038369.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104283 | Isidro Paredes ES | DIFFUN | 0 | 1 | UPGRADING |  | 598065.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104306 | Liwayway ES | DIFFUN | 0 | 1 | UPGRADING |  | 651551.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 300659 | Dipintin HS | MADDELA | 0 | 1 | UPGRADING |  | 724435.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104330 | Maddela North CS | MADDELA | 0 | 1 | UPGRADING |  | 1059099.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104323 | Maddela South CS | MADDELA | 0 | 1 | UPGRADING |  | 928669.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104334 | San Bernabe ES | MADDELA | 0 | 1 | UPGRADING |  | 699298.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104363 | Nagtipunan CS | NAGTIPUNAN | 0 | 1 | UPGRADING |  | 1384996.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | UPGRADING |  | 744922.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | 0 | 1 | UPGRADING |  | 926247.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Quirino | 104378 | Salvacion ES | SAGUDAY | 0 | 1 | UPGRADING |  | 564434.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Santiago City | 103812 | Batal ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 638253.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 408217.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Santiago City | 103814 | Luna ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 300024.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4 | 1 | UPGRADING |  | 499829.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104393 | Annafunan ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 523307.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104402 | Cataggamman ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1306164.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104391 | Tagga-Dadda ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 396711.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104392 | Tuguegarao East CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 925595.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104400 | Tuguegarao North CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 1249377.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104382 | Tuguegarao Northeast CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 902002.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 3 | 1332603.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region II | Tuguegarao City | 104407 | Ugac Elementary School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING | Batch 1 | 403936.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 345279 | Angeles City Senior High School | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 307203 | Claro M. Recto ICT High School | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500129 | Gov. Rafael L. Lazatin IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500132 | Malabanias IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500133 | Sto. Domingo IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 100% |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 4750801.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104535 | Mabatang ES | ABUCAY | 1 | 1 | UPGRADING | Batch 3 | 1297834.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104585 | Pagalanggang ES | DINALUPIHAN | 1 | 1 | UPGRADING | Batch 3 | 1007934.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 306602 | Morong NHS-Annex (Mabayo) | MORONG | 1 | 1 | UPGRADING | Batch 1 | 1284158.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104546 | Parang ES | BAGAC | 2 | 1 | UPGRADING | Batch 3 | 1229688.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 300700 | Saysain NHS | BAGAC | 2 | 1 | UPGRADING | Batch 1 | 1284158.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 306601 | Justice E.A.Gancayco MHS | ORION | 2 | 1 | UPGRADING | Batch 1 | 3303044.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300743 | Iba National High School | HAGONOY | 1 | 1 | UPGRADING | Batch 3 | 1614783.76 | 1444945.67 | COMPLETED | 100% | 2020-11-13 | 2020-10-09 | 19-08-029 | 19-10-037 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | UPGRADING | Batch 3 | 8532066.56 | 8469340.48 | COMPLETED | 100% | 2020-11-13 |  | 19-08-029 | 19-10-038 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | ADIMRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300749 | Salapungan NHS | SAN RAFAEL | 3 | 1 | UPGRADING | Batch 3 | 2288132.04 | 2226335.96 | COMPLETED | 100% | 2020-11-13 | 2020-03-06 | 19-08-029 | 19-10-039 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | UPGRADING | Batch 3 | 6307674.26 | 6196017.91 | COMPLETED | 100% | 2020-11-13 | 2020-03-06 | 19-08-029 | 19-10-040 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Gapan City | 300822 | Maruhat NHS | CITY OF GAPAN | 4 | 1 | UPGRADING |  | 1122771.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Malolos City | 104893 | Mambog ES | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 186661.35 |  | COMPLETED | 100% |  |  |  |  | 11/27-12/4/2020 | 2020-04-12 | 18/12/2020 | 28/12/2020 | 20/01/2021 | SAMENARA CONSTRACTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Malolos City | 104878 | Sta. Isabel ES | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 483647.78 |  | COMPLETED | 100% |  |  |  |  | 11/27-12/4/2020 | 2020-04-12 | 18/12/2020 | 28/12/2020 | 20/01/2021 | SAMENARA CONSTRACTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Olongapo City | 301056 | Kalalake NHS | OLONGAPO CITY | 1 | 1 | UPGRADING | Batch 1 | 911338.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | San Jose City | 300800 | San Jose City National High School (formerly Constancio Padilla National High School) | SAN JOSE CITY | 2 | 1 | UPGRADING | Batch 1 | 1445828.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300954 | Buenlag NHS | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106467 | Cardona ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300959 | Cardona NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 307007 | Corazon C. Aquino High School | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300965 | Gerona Western National High School | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106452 | Magaspac ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300995 | Tagumbao NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0% | 0% |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region IV-A | Antipolo City | 230006 | Paglitaw ES | CITY OF ANTIPOLO | 2 | 1 | UPGRADING | Batch 2 | 608772.6 | 603655 | COMPLETED | 100% |  |  |  |  | 2019-06-27 | 2019-07-04 | 2019-07-15 | 2019-07-22 | 2019-10-27 | Hakstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Bacoor City | 107888 | Queen's Row ES | BACOOR | 2 | 1 | UPGRADING | Batch 1 | 9405258.9 |  | COMPLETED | 100% |  |  |  |  | 2019-04-07 | 2019-12-07 | 07/30/2019 | 08/13/19 | 08/28/19 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Bacoor City | 107874 | Real Elementary School | BACOOR | 2 | 1 | UPGRADING | Batch 3 | 3773422.45 |  | COMPLETED | 100% |  |  |  |  | 2019-04-07 | 2019-12-07 | 07/30/2019 | 08/13/19 | 08/28/19 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 342219 | SHS in Sto. Tomas | SANTO TOMAS | 3 | 1 | UPGRADING |  | 2322221.07 |  | COMPLETED | 100% | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 1 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 1 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | UPGRADING |  | 2775039.26 |  | COMPLETED | 100% | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 2 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 2 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301069 | Alupay NHS | ROSARIO | 4 | 1 | UPGRADING | Batch 3 | 1926581.98 |  | COMPLETED | 100% | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 3 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 3 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301139 | Rosario NHS | ROSARIO | 4 | 1 | UPGRADING |  | 1898075.48 |  | COMPLETED | 100% | 2020-02-22 | 2020-02-22 | R4A – D2 – Electrification CY 2019 - Batch 2 | 43684 | R4A – D2 – Electrification CY 2019 - Batch 2 | 07/18/2019 | 2019-05-08 | 08/23/2019 | for issuance of NTP | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 342235 | Alangilan Senior High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1583219.45 | 1369441.57 | COMPLETED | 100% | ` |  | R4A-D1-BEFFII2019-2019-08-05I | R4A-D1-BEFFII2019-2019-08-05I | 2019-08-13 | 2019-08-19 | 2019-09-02 | 2019-09-17 | 2019-11-05 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301471 | Banaba West NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 855998.5 |  | COMPLETED | 100% | 12-14-2019 |  |  |  | 11/16/2018 | 11/22/2018 | 2018-06-12 | 2019-01-08 | 2019-09-08 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301472 | Batangas National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 1072624.09 | 788000 | ONGOING | 90% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-09I | R4A-D1-BEFF2019-2018-11-09I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | RM Tejada Construction & Supplies Corp. | Ready for Energization waiting for the schedule of Meralco Installed Transformer and waiting for the Meter | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308204 | Libjo National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 739207.4 | 677224.27 | COMPLETED | 100% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301475 | Pedro S. Tolentino MNHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 4000297.51 | 3650000 | COMPLETED | 100% | 2020-02-10 |  | R4A-D1-BEFFII2019-2019-089-03I | R4A-D1-BEFFII2019-2019-08-03I | 2019-08-13 | 08-19-2019 | 2019-09-02 | 2019-09-17 | 2019-11-05 | BOTEY CONSTRUCTION | Energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308203 | Sta. Rita NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 700932.53 | 678000 | COMPLETED | 100% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-09I | R4A-D1-BEFF2019-2018-11-09I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | RM Tejada Construction & Supplies Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301480 | STO. NIÑO NATIONAL HIGH SCHOOL | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3466113.53 |  | COMPLETED | 100% |  |  |  |  | 2019-09-08 | 08-19-2019 | 2019-02-09 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301482 | Talahib Pandayan NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 662657.66 | 632291.79 | ONGOING | 90% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | as per DE recompute for Bill Deposit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301483 | Talumpok NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 739207.4 | 687146.77 | ONGOING | 90% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | as per DE recompute for Bill Deposit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308202 | Tinga Sorosoro National High School (TISISI) | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 426203.99 | 401134.35 | COMPLETED | 100% | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342241 | Biñan City Senior High School - SPORTS (Sto. Tomas Campus) | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 3356919.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342240 | Biñan City Senior High School - TIMBAO | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 2252698.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342242 | Biñan City Senior High School-San Antonio Campus | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 4298158.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301516 | Camp Vicente Lim Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 1 | 5864118.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301521 | Kapayapaan Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 3 | 1852366.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301525 | Punta Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 3 | 1431951.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Laguna | 307927 | Dayap National Integrated High School | CALAUAN | 3 | 1 | UPGRADING | Batch 2 | 3144488.22 |  | ONGOING | 91% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | N | 91% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301487 | BOLBOK NATIONAL HIGH SCHOOL | LIPA CITY | 4 | 1 | UPGRADING |  | 3031713.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1911261.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy NHS | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 5995513.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 109680 | Mabini ES | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1103476 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1910980 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 2004214.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301499 | San Celestino National High School | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1666029.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 308113 | Regional Lead School for the Arts in Angono | ANGONO | 1 | 1 | UPGRADING | Batch 3 | 2358246.45 | 2305993.74 | COMPLETED | 100% |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 301453 | Pililla SHS | PILILLA | 2 | 1 | UPGRADING | Batch 3 | 2079707.23 | 2019022.19 | COMPLETED | 100% |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 308123 | Pantay NHS (Teresa NHS - Pantay Annex) | TERESA | 2 | 1 | UPGRADING | Batch 3 | 9206388.52 | 7726389.06 | COMPLETED | 100% |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Calapan City | 301797 | Community Vocational High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 1595784.93 | 1582805.23 | COMPLETED | 100% | November 1, 2019 |  |  |  | November 12, 2019 | November 19, 2019 | December 10, 2018 | December 21, 2018 | August 27, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Calapan City | 111539 | Lazareto ES | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING | Batch 3 | 617623.12 | 603780 | COMPLETED | 100% | January 10, 2020 |  |  |  | September 30, 2019 | October 7, 2019 | October 21, 2019 | October 29, 2019 | November 11, 2019 | CMSEL Construction and Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1 | 1 | UPGRADING |  | 2056773.01 | 2041436.28 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 098-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | NAUJAN | 1 | 1 | UPGRADING |  | 2130617.28 | 2113878.26 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 09-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia MNHS | NAUJAN | 1 | 1 | UPGRADING |  | 2511941.82 | 2493940.48 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 110535 | Porfirio G. Comia MES | NAUJAN | 1 | 1 | UPGRADING |  | 1304954.82 | 1295767.37 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301618 | Bansud NHS - Regional Science High School | BANSUD | 2 | 1 | UPGRADING |  | 1007628.26 | 1000767.73 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Oriental Mindoro | 301649 | Quinabigan NHS | PINAMALAYAN | 2 | 1 | UPGRADING |  | 237655.81 | 236022.89 | COMPLETED | 100% | Mar. 8,, 2020 | Mar. 6, 2020 | N/A | 099-2019 | Nov. 16, 2018 | Nov. 23, 2018 | Dec. 07,2018 | Dec. 17, 2018 | Oct 11, 2019 | ETVR Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110754 | Bohol Elementary School | DUMARAN | 1 | 1 | UPGRADING |  | 2225476.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110767 | Dumaran Central School | DUMARAN | 1 | 1 | UPGRADING |  | 2211333.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 301691 | Dumaran National High School | DUMARAN | 1 | 1 | UPGRADING |  | 2297517.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 110768 | Ilian Elementary School | DUMARAN | 1 | 1 | UPGRADING |  | 2197393.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 309135 | Ilian National High School | DUMARAN | 1 | 1 | UPGRADING |  | 2130380.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 301714 | Nicanor Zabala National High School | ROXAS | 1 | 1 | UPGRADING |  | 1147438.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Palawan | 111183 | Binga Elementary School | SAN VICENTE | 1 | 1 | UPGRADING |  | 2158156.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | 0 | 1 | UPGRADING |  | 4392551.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125945 | Aseniero ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303876 | Aseniero NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303877 | Barcelona National High School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 934650.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125925 | Baylimango CS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303878 | Baylimango NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 899475.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125926 | Canlucani ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125939 | Dapitan City Experimental ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 2341708.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125916 | Ilaya ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 500675 | Kauswagan Integrated School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125940 | Lawaan ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125948 | Opao ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125942 | Polo ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303883 | Potungan NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 904500.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125952 | Sigayan ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125943 | Sinonoc ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125935 | Taguilon ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125936 | Tag-ulo Elementary School | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'l. Sci. HS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 1012893.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303886 | Cogon NHS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 570502.66 | 566769.16 | COMPLETED | 100% | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 125982 | Dipolog Pilot Demonstration School | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 459044.78 | 449907.21 | COMPLETED | 100% | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 125972 | Galas ES | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 464377.98 | 461753.52 | COMPLETED | 100% | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. HS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 518849.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303891 | Punta National High School | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 560571.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 314603 | Baluno National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1572345.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126005 | Begang Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1423532.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126027 | Busay Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1534350.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126007 | Calvario Peak ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1129525.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1598589.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1537113.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126020 | Kaumpurnah Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1166796.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126032 | Lanote ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1102386.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126023 | Malamawi Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1283313.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126034 | Maligue Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1102839.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126036 | Sumagdang ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1170819.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126017 | Tabiawan ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1084294.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 133031 | Caro Elementary School | CITY OF ISABELA (Capital) | 1 | 1 | UPGRADING |  | 848184.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 126221 | Catalina Vda de Jalon MS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 100% | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303923 | Don Pablo A. Lorenzo MHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | Batch 3 | 2010050.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 126261 | Zamboanga East CS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1144423.15 |  | COMPLETED | 100% | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303914 | Arena Blanco NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 100% | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303922 | Maria Clara L. Lobregat NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1144423.15 |  | COMPLETED | 100% | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 314801 | Talon-Talon NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 100% | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303720 | Rizal National High School | RIZAL | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124651 | Sergio Osmeña Central School | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124525 | Linay CS | MANUKAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3 | 1 | UPGRADING |  | 2130358.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303721 | Salug National High School | SALUG | 3 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1 | 1 | UPGRADING | Batch 3 | 1850000 |  | COMPLETED | 100% |  |  |  |  | 2019-07-17 | 2019-08-02 | 2019-08-14 | 2019-08-26 |  | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 314203 | BONIAO NATIONAL HIGH SCHOOL | MAHAYAG | 1 | 1 | UPGRADING |  | 1600000 |  | COMPLETED | 100% | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303796 | Midsalip NHS- Main | MIDSALIP | 1 | 1 | UPGRADING |  | 1766000 |  | COMPLETED | 100% | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303814 | SAPA ANDING AGRICULTURAL VOCATIONAL TECHNICAL SCHOOL | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | UPGRADING |  | 1659000 |  | COMPLETED | 100% | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303811 | Tukuran Tech. Voc'l. HS | TUKURAN | 1 | 1 | UPGRADING |  | 1521000 |  | COMPLETED | 100% | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303774 | Dumalinao NHS | DUMALINAO | 2 | 1 | UPGRADING |  | 2092000 |  | COMPLETED | 100% | 2019-12-27 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303808 | Rebokon AVHS | DUMALINAO | 2 | 1 | UPGRADING |  | 1501000 |  | COMPLETED | 100% | 2019-12-27 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303784 | Kumalarang NHS | KUMALARANG | 2 | 1 | UPGRADING |  | 1672000 |  | COMPLETED | 100% | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303788 | Lapuyan NHS | LAPUYAN | 2 | 1 | UPGRADING | Batch 3 | 1580000 |  | COMPLETED | 100% |  |  |  |  | 2019-07-17 | 2019-08-02 | 2019-08-14 | 2019-08-26 |  | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303822 | Toribio Minor NHS | MARGOSATUBIG | 2 | 1 | UPGRADING |  | 1654000 |  | COMPLETED | 100% | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303791 | Betinan NHS | SAN MIGUEL | 2 | 1 | UPGRADING |  | 1524000 |  | COMPLETED | 100% | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303824 | ALICIA NHS | Alicia | 1 | 1 | UPGRADING |  | 4847218.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303825 | DAWA-DAWA NHS | Alicia | 1 | 1 | UPGRADING | Batch 3 | 3684763.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303829 | BUUG NHS | BUUG | 1 | 1 | UPGRADING | Batch 3 | 5650378.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303828 | DIPLAHAN NHS | DIPLAHAN | 1 | 1 | UPGRADING | Batch 3 | 3089516.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 314314 | DITAY NHS | DIPLAHAN | 1 | 1 | UPGRADING |  | 445687.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303837 | IMELDA NHS | IMELDA | 1 | 1 | UPGRADING |  | 3077673.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial HS | MABUHAY | 1 | 1 | UPGRADING |  | 726852.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303852 | MABUHAY NHS | MABUHAY | 1 | 1 | UPGRADING | Batch 3 | 2581516.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303845 | MALANGAS NHS | MALANGAS | 1 | 1 | UPGRADING |  | 2901868.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303851 | OLUTANGA NHS | OLUTANGA | 1 | 1 | UPGRADING |  | 2532995.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303856 | PAYAO NHS | PAYAO | 1 | 1 | UPGRADING | Batch 3 | 3031211.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303854 | ZAMBOANGA SIBUGAY NHS | IPIL | 2 | 1 | UPGRADING |  | 3089516.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303827 | Francisco Ramos NHS | KABASALAN | 2 | 1 | UPGRADING |  | 2072864.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303872 | TITAY NHS | TITAY | 2 | 1 | UPGRADING |  | 1140480.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303859 | PIONEER NHS | TUNGAWAN | 2 | 1 | UPGRADING |  | 411731.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303874 | TUNGAWAN NHS | TUNGAWAN | 2 | 1 | UPGRADING |  | 1927052.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301863 | Pili National High School | BACACAY | 1 | 1 | UPGRADING | Batch 3 | 2530593.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301878 | Sogod National High school | BACACAY | 1 | 1 | UPGRADING | Batch 3 | 2835628.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301827 | Estancia National High School | MALINAO | 1 | 1 | UPGRADING | Batch 3 | 1251780.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301815 | Bical High School | SANTO DOMINGO (LIBOG) | 1 | 1 | UPGRADING | Batch 3 | 1031796.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301872 | San Fernando National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | UPGRADING | Batch 3 | 1247258.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301830 | Jovellar National High School | JOVELLAR | 3 | 1 | UPGRADING | Batch 3 | 2020559.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Albay | 301873 | San Isidro National High School | JOVELLAR | 3 | 1 | UPGRADING | Batch 3 | 1113045.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1 | 1 | UPGRADING | Batch 3 | 3266647.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1 | 1 | UPGRADING | Batch 3 | 4043823.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | UPGRADING |  | 4043823.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3857618.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2 | 1 | UPGRADING |  | 4510135.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | UPGRADING |  | 14022233.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302046 | Sinuknipan NHS | DEL GALLEGO | 1 | 1 | UPGRADING | Batch 3 | 2089735.91 |  | COMPLETED | 100% | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur |  | Sinuknipan Senior High School | DEL GALLEGO | 1 | 1 | UPGRADING | Batch 3 | 1346316.56 |  | COMPLETED | 100% | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309751 | Ragay Science and Math Oriented High School | RAGAY | 1 | 1 | UPGRADING | Batch 3 | 2310948.95 |  | COMPLETED | 100% | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301927 | Anib National High School | SIPOCOT | 1 | 1 | UPGRADING | Batch 3 | 2458552.08 |  | COMPLETED | 100% | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309755 | Sacred Heart High School | SIPOCOT | 1 | 1 | UPGRADING | Batch 3 | 2318394.14 |  | COMPLETED | 100% | 2020-04-04 |  |  | 2019-10-051 | 2019-07-08 |  | 8/27/2019 |  | 2019-12-06 | PHILIAN CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301973 | Gainza National HS | GAINZA | 2 | 1 | UPGRADING | Batch 3 | 1566614.35 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301999 | Milaor National High School | MILAOR | 2 | 1 | UPGRADING | Batch 3 | 2319927.77 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301981 | Hobo National High School | MINALABAC | 2 | 1 | UPGRADING | Batch 3 | 2868966.33 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309757 | Cagbibi National High School | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 1223675.91 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309723 | Del Rosario National HS | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 1797949.17 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302021 | Ramon B. Felipe Sr. NHS (frmerly: San Vicente HS) | PAMPLONA | 2 | 1 | UPGRADING | Batch 3 | 2464359.02 |  | COMPLETED | 100% | April 10, 2020 |  |  | - | 2019-07-08 |  | 9/23/2019 |  | 2019-12-12 | ZKR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301983 | Jose De Villa NHS | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 2336338.97 |  | COMPLETED | 100% | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 2831480.62 |  | COMPLETED | 100% | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301954 | Sabang National High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3003112.73 |  | COMPLETED | 100% | [6 empty] | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 303542 | Severo High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3953216 |  | COMPLETED | 100% | April 4, 2020 |  |  | 2019-10-052 | 2019-07-08 |  | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302065 | Union National High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 1782299.84 |  | COMPLETED | 100% | [6 empty] | 8/27/2019 |  | 2019-06-12 | JERA CONST |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301955 | West Coast High School | CALABANGA | 3 | 1 | UPGRADING | Batch 3 | 3953216 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 500157 | Ponong Integrated School | MAGARAO | 3 | 1 | UPGRADING | Batch 3 | 1952525.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | UPGRADING | Batch 2 | 1816543.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3 | 1 | UPGRADING | Batch 3 | 1240932.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309719 | Dona Basilia S. Quilon Memorial High School (formerly:Bagong Sirang HS) | PILI (Capital) | 3 | 1 | UPGRADING | Batch 3 | 2134901.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301975 | Goa National High School | GOA | 4 | 1 | UPGRADING | Batch 2 | 3540417.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309741 | Juan L. Filipino Memorial High School | GOA | 4 | 1 | UPGRADING | Batch 3 | 3640861.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 | UPGRADING | Batch 2 | 2049381.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309715 | Nato National High School (Main Campus) | SAGÑAY | 4 | 1 | UPGRADING | Batch 2 | 1757233.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309715 | Nato National High School (San Isidro) | SAGÑAY | 4 |  | UPGRADING | Batch 2 | 1798703.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309752 | Tinorongan National High School (Formerly Sagñay Western HS) | SAGÑAY | 4 | 1 | UPGRADING | Batch 2 | 1449333.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302035 | Rangas-Ramos NHS (frmerly:Sn Jose Fish.Sch.) | SAN JOSE | 4 | 1 | UPGRADING | Batch 2 | 1706475.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309721 | Huyonhuyon HS | TIGAON | 4 | 1 | UPGRADING | Batch 2 | 2408143.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302015 | Partido Agro-Industrial NHS | TIGAON | 4 | 1 | UPGRADING | Batch 3 | 8309190.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302038 | San Rafael National High School | TIGAON | 4 | 1 | UPGRADING | Batch 3 | 3690189.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur |  | San Rafael National High School annex | Tigaon | 4 | 1 | UPGRADING | Batch 3 | 4921431.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302056 | Tamban NHS | TINAMBAC | 4 | 1 | UPGRADING | Batch 3 | 7264217.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | UPGRADING | Batch 3 | 2945467.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5 | 1 | UPGRADING | Batch 3 | 4586815.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309725 | Laganac High School | BALATAN | 5 | 1 | UPGRADING | Batch 3 | 2867429.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301997 | Masoli High School | BATO | 5 | 1 | UPGRADING | Batch 3 | 1885493.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 112421 | Tambo ES | BUHI | 5 | 1 | UPGRADING | Batch 3 | 2495578.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 | 1 | UPGRADING | Batch 3 | 1803929.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5 | 1 | UPGRADING | Batch 3 | 3061918.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | UPGRADING | Batch 3 | 1826009.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | UPGRADING | Batch 3 | 1255263.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | UPGRADING | Batch 3 | 2064135.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 0 | 1 | UPGRADING | Batch 3 | 1681122.6 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 | 1 | UPGRADING | Batch 3 | 2235281.45 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | UPGRADING | Batch 3 | 2692700.44 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302082 | Caramoran School of Fisheries | CARAMORAN | 0 | 1 | UPGRADING | Batch 3 | 2620441.03 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302102 | Supang-Datag National High School | CARAMORAN | 0 | 1 | UPGRADING | Batch 3 | 1273227.26 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 113314 | Tambongon CES | VIGA | 0 | 1 | UPGRADING | Batch 3 | 1494832.13 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 500031 | Buyo Integrated School | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 3186388.56 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1505771.78 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC (Capital) | 0 | 1 | UPGRADING |  | 6858553.63 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Catanduanes | 302093 | Palta NHS | VIRAC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1296398.92 |  | COMPLETED | 100% | 2020-04-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 500167 | Cristo Rey IS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 1586988.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302249 | Perpetual Help NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 1706777.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302252 | Sagrada NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 1 | 2343563.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Iriga City | 302256 | Sto. Niño NHS | IRIGA CITY | 5 | 1 | UPGRADING | Batch 3 | 3419385.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1408291.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 114470 | Cagbacong Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 545908.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1031464.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1085598.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1325598.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 916949.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1518683.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1280207.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2 | 1 | UPGRADING | Batch 3 | 2291424.79 | 2258907.83 | COMPLETED | 100% | 2020-03-05 |  | 2019-08-007 | 2019-09-028 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-28 | 2019-12-06 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | UPGRADING | Batch 3 | 1832115.23 | 1806924.42 | COMPLETED | 100% |  |  | 2019-08-007 | 2019-09-027 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Marabe Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | UPGRADING | Batch 3 | 1535130.08 | 1509666.23 | COMPLETED | 100% | 2020-02-26 |  | 2019-08-007 | 2019-09-029 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Ascentia Const. Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2 | 1 | UPGRADING | Batch 3 | 1897641.09 | 1869869.64 | COMPLETED | 100% | 2020-03-05 |  | 2019-08-007 | 2019-09-030 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-12-06 | Bryne Const. & Suppply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302158 | Pawican National High School | CATAINGAN | 3 | 1 | UPGRADING | Batch 3 | 4648037.22 | 4595455.84 | COMPLETED | 100% | 2020-02-27 |  | 2019-08-007 | 2019-09-033 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-29 | 144 Cubits Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3 | 1 | UPGRADING | Batch 3 | 1559451.65 | 1530475.91 | COMPLETED | 100% |  |  | 2019-08-007 | 2019-09-032 | 2019-07-30 | 2019-08-07 | 2019-08-19 |  |  | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3 | 1 | UPGRADING | Batch 3 | 2056294.37 | 2019815.85 | COMPLETED | 100% | 2020-03-08 |  | 2019-08-007 | 2019-09-031 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-29 | 2019-12-09 | Red Diamond Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302170 | San Ramon National High School | USON | 3 | 1 | UPGRADING | Batch 3 | 1461341.2 | 1435682.8 | COMPLETED | 100% | 2020-02-26 |  | 2019-08-007 | 2019-09-034 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-28 | Marabe Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Masbate | 302175 | Uson National High School | USON | 3 | 1 | UPGRADING | Batch 3 | 3979065.52 | 3932239.25 | COMPLETED | 100% | 2020-02-27 |  | 2019-08-007 | 2019-09-035 | 2019-07-30 | 2019-08-07 | 2019-08-19 | 2019-11-19 | 2019-11-29 | 144 Cubits Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Naga City | 302264 | Camarines Sur National High School | NAGA CITY | 3 | 1 | UPGRADING | Batch 3 | 10695533.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | UPGRADING | Batch 1 | 6715416.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | UPGRADING | Batch 2 | 2841488.36 | 1953845.12 | COMPLETED | 100% | Jan. 26, 2020 | March 24, 2020 |  | 19-07-002-01 |  | July 17, 2019 | July 29, 2019 | August 28, 2019 | Oct. 21, 2019 | SMU Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302242 | San Roque NHS | BULUSAN | 2 | 1 | UPGRADING | Batch 3 | 1128354.3 | 885797.77 | COMPLETED | 100% | Feb. 25, 2020 | Feb. 20, 2020 |  | 19-07-002-02 |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302182 | Bagacay NHS | GUBAT | 2 | 1 | UPGRADING | Batch 2 | 1686847.85 | 1342252.59 | COMPLETED | 100% | Feb. 25, 2020 | March 5, 2020 |  |  |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302185 | Bentuco NHS | GUBAT | 2 | 1 | UPGRADING | Batch 3 | 1307787.68 | 1032387.78 | COMPLETED | 100% | Feb. 25, 2020 | March 5, 2020 |  |  |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region V | Sorsogon | 302189 | Bulacao NHS | GUBAT | 2 | 1 | UPGRADING | Batch 3 | 1502223.77 | 1175612.71 | COMPLETED | 100% | Feb. 25, 2020 | March 5, 2020 |  | 19-07-002-03 |  | July 17, 2019 | July 29, 2019 | August 19, 2019 | Oct. 21, 2019 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500543 | Balete Integrated School | BALETE | 0 | 1 | UPGRADING |  | 1266873.53 | 1068886.54 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114660 | Banga ES | BANGA | 0 | 1 | UPGRADING |  | 2162134.07 | 1938079.79 | COMPLETED | 100% |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114678 | Torralba ES | BANGA | 0 | 1 | UPGRADING | Batch 3 | 1128105.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 0 | 1 | UPGRADING |  | 1642173.37 | 1385534.51 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114686 | Camaligan ES | BATAN | 0 | 1 | UPGRADING | Batch 3 | 1295560.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500184 | Mandong Integrated School | BATAN | 0 | 1 | UPGRADING | Batch 3 | 1287978.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500642 | Palay Integrated School | BATAN | 0 | 1 | UPGRADING |  | 1183233.32 | 998317.62 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500187 | Tabon Integrated School | BATAN | 0 | 1 | UPGRADING |  | 1230719.57 | 1038382.72 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C1-142-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 0 | 1 | UPGRADING | Batch 3 | 1211747.83 | 1195000 | COMPLETED | 100% |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C3-053-2019 |  | 2019-08-08 | 2019-08-15 | 2019-08-27 | 2019-08-29 | 2019-10-07 | First Makeen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | 0 | 1 | UPGRADING |  | 2162188.12 | 1824281.36 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114736 | Monlaque Elementary School | IBAJAY | 0 | 1 | UPGRADING | Batch 3 | 1060061.31 | 1045000 | COMPLETED | 100% |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C3-053-2019 |  | 2019-08-08 | 2019-08-15 | 2019-08-27 | 2019-08-29 | 2019-10-07 | First Makeen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114737 | Naile ES | IBAJAY | 0 | 1 | UPGRADING | Batch 3 | 1248621.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114738 | Naisud CS | IBAJAY | 0 | 1 | UPGRADING |  | 1559364.68 | 1315667.17 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114746 | Andagaw Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1139450.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114756 | Kalibo I ES | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1223263.26 | 1096446.46 | COMPLETED | 100% |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1183233.32 | 1096236.47 | COMPLETED | 100% |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114758 | Linabuan Norte ES | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1223263.26 | 1058883.25 | COMPLETED | 100% |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114752 | New Buswang Elementary School | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1223263.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114762 | Tinigaw ES | KALIBO (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1223263.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114856 | Yapak Elementary School | MALAY | 0 | 1 | UPGRADING | Batch 3 | 1186938.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114866 | Malinao ES | MALINAO | 0 | 1 | UPGRADING |  | 1301436.87 | 1166644.91 | COMPLETED | 100% |  | August 6, 2021 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C2-143-2018 |  | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114883 | LASERNA ELEMENTARY SCHOOL | NABAS | 0 | 1 | UPGRADING |  | 1275494.58 | 1076160.29 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 302337 | Toledo NHS | NABAS | 0 | 1 | UPGRADING |  | 1486724.18 | 1254378.93 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114895 | Unidos Elementary School | NABAS | 0 | 1 | UPGRADING | Batch 3 | 1359307 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 114896 | Union Elementary School | NABAS | 0 | 1 | UPGRADING | Batch 3 | 1275494.58 | 1129034.12? | COMPLETED | 100% |  |  | DepED-RO6-D1-BEFF2019ELEC.B2-C6-056-2019 |  | 2019-08-08 | 2019-08-08 | 2019-08-27 | 2019-08-29 | 2019-10-07 | KRIS DB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Aklan | 302340 | Union National High School | NABAS | 0 | 1 | UPGRADING |  | 1193785.82 | 1007220.97 | COMPLETED | 100% | 2020-01-04 |  | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | DepED-RO6-D1-2019BEFF(ELECTRIFICATION)-C3-144-2018 | 2018-11-12 | 2018-11-19 | 2018-12-03 | 2018-12-28 | 2019-08-01 | Hovert Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | 2.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114939 | Anini-y CS | ANINI-Y | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114958 | Barbaza Central School | BARBAZA | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114961 | Capoyu-an ES | BARBAZA | 0 | 1 | UPGRADING | Batch 3 | 1305579.42 | 1295902.67 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114973 | Belison CS | BELISON | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302342 | Antique Vocational School | BUGASONG | 0 | 1 | UPGRADING | Batch 1 | 3010746.02 | 2680652.5155 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114984 | Bugasong CS | BUGASONG | 0 | 1 | UPGRADING | Batch 1 | 1841129.22 | 1639233.1205 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 114991 | Jinalinan-Paliwan ES | BUGASONG | 0 | 1 | UPGRADING | Batch 3 | 2164419.44 | 2145894.44 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115033 | Bitadton ES | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1467887.06 | 1458367.7 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115038 | Culasi CS | CULASI | 0 | 1 | UPGRADING | Batch 1 | 1805242.29 | 1607264.3707 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115039 | Culasi North ES | CULASI | 0 | 1 | UPGRADING | Batch 1 | 1235709.96 | 1099907.0222 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500515 | Kawit Integrated School | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1284212.15 | 1274291.2 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500548 | Lipata-Lamputong Integrated School | CULASI | 0 | 1 | UPGRADING | Batch 3 | 1358635.52 | 1347905.79 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302367 | Northern Antique Vocational School | CULASI | 0 | 1 | UPGRADING | Batch 1 | 3080424.07 | 2743061.1626 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115064 | Buhang ES | HAMTIC | 0 | 1 | UPGRADING | Batch 3 | 1161286.59 | 1152020.72 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115069 | Hamtic Central School | HAMTIC | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115094 | Moscoso-Rios CS | HAMTIC | 0 | 1 | UPGRADING | Batch 3 | 1427278.86 | 1416377.96 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115106 | Guisijan ES | LAUA-AN | 0 | 1 | UPGRADING | Batch 3 | 1393463.69 | 1382565.37 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115110 | Laua-an CS | LAUA-AN | 0 | 1 | UPGRADING | Batch 1 | 1305579.42 | 1162557.5503 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115130 | Libertad Central School | LIBERTAD | 0 | 1 | UPGRADING | Batch 1 | 1501702.22 | 1337128.0484 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115161 | Pandan CS | PANDAN | 0 | 1 | UPGRADING | Batch 1 | 1805242.29 | 1607527.2385 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115162 | Patria ES | PANDAN | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187577.09 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115193 | Carit-an Central School | PATNONGON | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115179 | Col. Ruperto Abellon Sr. MS | PATNONGON | 0 | 1 | UPGRADING | Batch 1 | 1305579.42 | 1162586.7528 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115196 | Igbarawan-Mabasa Elementary School | PATNONGON | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 178509 | Antique Integrated School | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1473187.68 | 1462402.62 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302341 | Antique NS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 3849768.93 | 3426899.1597 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115212 | Assemblyman Segundo Moscoso MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1501702.22 | 1337201.0682 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115213 | Atabay ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1271764.26 | 1132163.4481 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115224 | Canuto B. Pefianco Sr. ES (Madrangca ES) | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1188312.05 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115218 | Delegate Angel Salazar Jr. MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1678988.95 | 1494833.2796 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115220 | Gov. Santos Capadocia MS | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1271764.26 | 1132163.4481 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115225 | Maybato ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187749.5 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115229 | Salazar ES (Funda Dalipe ES) | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187577.09 | COMPLETED | 100% | March 5, 2020 |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115231 | San Fernando ES | SAN JOSE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1186903.7 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115258 | BUGO CENTRAL SCHOOL | SAN REMIGIO | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 11888268.83 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115238 | Calag-itan CS | SAN REMIGIO | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366481.4991 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115285 | Sebaste CS | SEBASTE | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115315 | Egaña ES | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 500549 | Lacaron lntegrated School | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1358635.52 | 1347905.79 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115331 | Pis-anan Central School | SIBALOM | 0 | 1 | UPGRADING | Batch 3 | 1197340.89 | 1187750.03 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115306 | Sibalom Central ELementary School | SIBALOM | 0 | 1 | UPGRADING | Batch 1 | 1645006.42 | 1464325.0969 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115352 | Tibiao Central School | TIBIAO | 0 | 1 | UPGRADING | Batch 1 | 1534696.12 | 1366539.9132 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 302355 | Gamad-Sto. Tomas NHS | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING | Batch 3 | 2138907.08 | 2122370.86 | COMPLETED | 100% |  |  |  |  | July 26, 2019 | August 2, 2019 | August 15, 2019 | August 29, 2019 |  | Benzen Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Antique | 115408 | Valderama CES | VALDERRAMA | 0 | 1 | UPGRADING | Batch 1 | 1338573.32 | 1191829.2195 | COMPLETED | 100% | 2020-07-14 | 2021-12-27 | R6-D2-2019BEFF-09-E | R6-D2-2019BEFF-09-E | November 13, 2018 | November 20, 2018 | December 3, 2018 | February 8, 2019 | September 18, 2019 | Goldentec Contractor Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 662718.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 534638.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117498 | J.L. Araneta Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 500013.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117508 | L. De La Rama ES | BAGO CITY | 4 | 1 | UPGRADING |  | 216001.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117509 | Lag-asan ES | BAGO CITY | 4 | 1 | UPGRADING |  | 672967.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 755636.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 279050.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | UPGRADING |  | 332856.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3176131.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311406 | Burgos National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1402643.61 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1524721.65 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311401 | Caduha-an NHS - Luna Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1409045.19 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311402 | Caduha-an NHS - Tagbanon Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1602136.72 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311404 | Dr. Vicente F. Gustilo Memorial NHS - Daga Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1805687.43 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 4631699.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 311407 | V NHS-Sewahon Extension High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1610170.12 |  | COMPLETED | 100% | [10 empty] | Energized already | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Cadiz City | 302735 | Villacin National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3560415.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115547 | Aglimocon ES | MA-AYON | 1 | 1 | UPGRADING |  | 653679.04 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115548 | Alasaging ES | MA-AYON | 1 | 1 | UPGRADING |  | 624891.1 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115549 | Alayunan ES | MA-AYON | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115550 | Balighot Elementary School | MA-AYON | 1 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115551 | Batabat ES | MA-AYON | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115707 | Aranguel ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115708 | Badiangon ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115709 | Bayuyan ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115710 | Bliss Pantalan ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 570194.02 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 179002 | Cabugcabug ES (president roxas) | PRESIDENT ROXAS | 1 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115712 | Carmencita-Sto.Niño ES | PRESIDENT ROXAS | 1 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115409 | Agcabugao Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115410 | Agdahon ES | CUARTERO | 2 | 1 | UPGRADING |  | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115411 | Agnaga ES | CUARTERO | 2 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115412 | Angub Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 872467.38 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115413 | Balingasag PS | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115414 | Bito-on Elementary School | CUARTERO | 2 | 1 | UPGRADING | Batch 3 | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115429 | Agtambi PS | DAO | 2 | 1 | UPGRADING |  | 482966.56 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115430 | Agtanguay ES | DAO | 2 | 1 | UPGRADING |  | 708376.13 |  | COMPLETED | 100% | 2020-03-27 | 2020-01-29 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115435 | Alfonso E. Espiritu ES (aganan) | DAO | 2 | 1 | UPGRADING |  | 598981.96 |  | COMPLETED | 100% | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115444 | Andres E. Quintia Sr. ES (Nasunogan) | DAO | 2 | 1 | UPGRADING |  | 737164.07 |  | COMPLETED | 100% | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115445 | Antonio Abad ES (Quinabcaban) | DAO | 2 | 1 | UPGRADING |  | 624891.1 |  | COMPLETED | 100% | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115431 | Bita PS | DAO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115432 | Centro Primary School | DAO | 2 | 1 | UPGRADING | Batch 3 | 540542.44 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2 | 1 | UPGRADING |  | 872467.38 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115434 | Daplas Primary School | DAO | 2 | 1 | UPGRADING | Batch 3 | 482966.56 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115437 | Ilas Norte ES | DAO | 2 | 1 | UPGRADING |  | 794739.95 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115438 | Ilas Sur ES | DAO | 2 | 1 | UPGRADING | Batch 3 | 737164.07 |  | COMPLETED | 100% | 2020-03-27 | 2020-02-12 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115439 | Lacaron ES | DAO | 2 | 1 | UPGRADING |  | 737164.07 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Capiz | 115440 | Malonoy ES (dao) | DAO | 2 | 1 | UPGRADING | Batch 3 | 682466.98 |  | COMPLETED | 100% | 2020-03-27 | 2020-03-20 | [6 empty] | 2019-12-28 | RJZW Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302595 | Buenavista National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1708168.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Escalante City | 302627 | Tamlang National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1335649.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302427 | Agsanayan National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3034636.02 | 2483302.49 | COMPLETED | 100% | 9-Sept 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115821 | Buenavista Central School | BUENAVISTA | 0 | 1 | UPGRADING | Batch 3 | 2830060.1 | 2171152.9061 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-01 | 04-2019-01 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302426 | Buenavista National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 2985014.84 | 2441354.27 | COMPLETED | 100% | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3034636.02 | 2483302.49 | COMPLETED | 100% | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302431 | Getulio NHS | BUENAVISTA | 0 | 1 | UPGRADING |  | 3006120.37 | 2459196.23 | COMPLETED | 100% | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115844 | Supang Central School | BUENAVISTA | 0 | 1 | UPGRADING | Batch 3 | 2804695.36 | 2145914.9839 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-01 | 04-2019-01 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 310902 | Supang National High School | BUENAVISTA | 0 | 1 | UPGRADING |  | 3359179.9 | 2757662.01 | COMPLETED | 100% | 9-Sept. 2019 | 2020-06-02 | 08-2018-01 | 08-2018-01 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115864 | Jordan Central School | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2851165.63 | 2227237.9017 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115873 | San Miguel Central School | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2696555.69 | 2073401.0093 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115875 | Sta. Teresa ES | JORDAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2444481.89 | 1822587.579 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-02 | 04-2019-02 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA | 0 | 1 | UPGRADING | Batch 3 | 2861718.39 | 2105963.1007 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-03 | 04-2019-03 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302434 | Nueva Valencia National High School | NUEVA VALENCIA | 0 | 1 | UPGRADING |  | 3675064.98 | 3003559.14 | COMPLETED | 100% | 9-Sept. 2019 | 2020-06-02 | 08-2018-02 | 08-2018-02 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Goldentec contractor corporatrion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115915 | Salvacion Central School | NUEVA VALENCIA | 0 | 1 | UPGRADING | Batch 3 | 3618043.01 | 2858506.0891 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-03 | 04-2019-03 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 0 | 1 | UPGRADING |  | 3232550.05 | 3208500 | COMPLETED | 100% | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 | 1 | UPGRADING |  | 3232550.05 | 3208500 | COMPLETED | 100% | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115858 | Suclaran Central School | SAN LORENZO | 0 | 1 | UPGRADING | Batch 3 | 2521747.1 | 2007310.69 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-04 | 04-2019-04 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302425 | Alegria NHS | SIBUNAG | 0 | 1 | UPGRADING |  | 2995567.61 | 2973160.5 | COMPLETED | 100% | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 302429 | Desiderio C. Gange NHS | SIBUNAG | 0 | 1 | UPGRADING |  | 3221997.29 | 3198219.5 | COMPLETED | 100% | 2020-01-22 | 2019-12-26 | 08-2018-03 | 08-2018-03 | 10/26/2018 | 12/18/2018 | 12/18/2018 | 12/28/2018 | 2019-06-09 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Guimaras | 115879 | Liningwan Central School | SIBUNAG | 0 | 1 | UPGRADING | Batch 3 | 2448519.96 | 1949021.89 | COMPLETED | 100% | 2020-06-20 | 2020-11-25 | 04-2019-05 | 04-2019-05 | 6/22/2019 | 7/16/2019 | 7/16/2019 | 7/24/2019 | 9/17/2019 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302479 | CAMANGAHAN NATIONAL HIGH SCHOOL | GUIMBAL | 1 | 1 | UPGRADING | Batch 3 | 2448519.96 | 3232266.98 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L8 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1 | 1 | UPGRADING |  | 4499246.18 | 2916481.83 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L8 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302467 | Botong-Cabanbanan NHS | OTON | 1 | 1 | UPGRADING | Batch 3 | 2406308.91 | 4135434.57 | COMPLETED | 100% | 2020-10-12 | 2020-10-10 | R06-022-ELECBEFF2019-B2-L2 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302542 | Oton National High School | OTON | 1 | 1 | UPGRADING |  | 5412015.58 | 2128834.42 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L3 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302566 | SAN JOAQUIN SCHOOL OF FISHERIES | SAN JOAQUIN | 1 | 1 | UPGRADING | Batch 3 | 3248155.19 | 2790710.35 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311024 | Bagacay National High School | TIGBAUAN | 1 | 1 | UPGRADING | Batch 3 | 2480178.25 | 4369081.69 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN | 1 | 1 | UPGRADING |  | 5323135.66 | 5366544.79 | COMPLETED | 100% | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L14 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302583 | Tubungan NHS | TUBUNGAN | 1 | 1 | UPGRADING |  | 2935850.21 | 4867582.78 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L9 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302446 | Alimodian NCHS | ALIMODIAN | 2 | 1 | UPGRADING | Batch 3 | 5467471.36 | 3299648.81 | COMPLETED | 100% | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L11 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311017 | Bancal NHS | ALIMODIAN | 2 | 1 | UPGRADING | Batch 3 | 2893639.15 | 2198099.21 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302520 | Leganes National High School | LEGANES | 2 | 1 | UPGRADING |  | 4993078 | 4952016.94 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L7 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302522 | Leon National High School | LEON | 2 | 1 | UPGRADING |  | 3300919.01 | 5284471.01 | COMPLETED | 100% | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L11 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302539 | New Lucena National Comprehensive High School | NEW LUCENA | 2 | 1 | UPGRADING |  | 3438750.58 | 3174000 | COMPLETED | 100% | 2020-12-13 | 2020-12-03 | R06-022-ELECBEFF2019-B1-L10 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-11-12 | 2019-12-17 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302540 | New Lucena National High School | NEW LUCENA | 2 | 1 | UPGRADING | Batch 3 | 3470408.87 | 3278671.11 | COMPLETED | 100% | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L15 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302550 | Pavia National High School | PAVIA | 2 | 1 | UPGRADING |  | 5478024.13 | 3751760.78 | COMPLETED | 100% | 2019-12-25 | 2019-12-17 | R06-022-ELECBEFF2019-B1-L14 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302516 | Leonora S. Salapantan NHS | SAN MIGUEL | 2 | 1 | UPGRADING |  | 4704901.05 | 5683741.07 | COMPLETED | 100% | Deceber 19, 2019 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L12 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-23 | Culasi General Merchandising and Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3 | 1 | UPGRADING | Batch 3 | 3788609.81 | 3536380.54 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302465 | Bingawan NHS | BINGAWAN | 3 | 1 | UPGRADING |  | 3322024.54 | 2879319.26 | COMPLETED | 100% | 2020-11-05 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L6 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302447 | Ambrosio Maido MNHS | CABATUAN | 3 | 1 | UPGRADING | Batch 3 | 2985014.84 | 2218314.71 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L13 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302473 | Cabatuan NCHS | CABATUAN | 3 | 1 | UPGRADING |  | 5456918.6 | 5704794.05 | COMPLETED | 100% | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L15 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3 | 1 | UPGRADING |  | 5320306.79 | 1847005.4 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302512 | Janiuay NCHS | JANIUAY | 3 | 1 | UPGRADING |  | 5541340.71 | 4468748.95 | COMPLETED | 100% | 2019-12-25 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L1 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302517 | Lambunao National High School | LAMBUNAO | 3 | 1 | UPGRADING | Batch 3 | 3375434 | 5480179.03 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L9 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302524 | Maasin National Comprehensive High School | MAASIN | 3 | 1 | UPGRADING |  | 5509682.42 | 2484986 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L5 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302533 | Mina NHS | MINA | 3 | 1 | UPGRADING |  | 5530787.95 | 4503439.73 | COMPLETED | 100% | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L6 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302457 | Barotac Nuevo National Comprehensive High School | BAROTAC NUEVO | 4 | 1 | UPGRADING |  | 4760009.49 | 2722913.85 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L511 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302497 | Duenas General Comprehensive High School | DUEÑAS | 4 | 1 | UPGRADING |  | 5736096.31 | 7940700 | COMPLETED | 100% | Deceber 24, 2019 | 2020-03-20 | R06-022-ELECBEFF2019-B1-L5 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-05 | 2019-08-19 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302498 | Dumangas NHS | DUMANGAS | 4 | 1 | UPGRADING |  | 3858601.45 | 5454516.02 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L8 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311006 | P.D. Monfort National Science HS | DUMANGAS | 4 | 1 | UPGRADING | Batch 3 | 3858120.05 | 5488131.64 | COMPLETED | 100% | 2019-12-25 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L10 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302543 | Pagdugue National High School | DUMANGAS | 4 | 1 | UPGRADING |  | 2416861.67 | 2552677.34 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L4 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302564 | San Enrique NCHS | SAN ENRIQUE | 4 | 1 | UPGRADING | Batch 3 | 3279813.48 | 3092961.51 | COMPLETED | 100% | 2019-12-25 | 2019-12-16 | R06-022-ELECBEFF2019-B1-L6 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302486 | Culasi NHS | AJUY | 5 | 1 | UPGRADING | Batch 3 | 3257469.23 | 1814718.49 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302552 | Pili NHS | AJUY | 5 | 1 | UPGRADING | Batch 3 | 2942803.79 | 5018420.62 | COMPLETED | 100% | 2020-01-01 | 2020-03-01 | R06-022-ELECBEFF2019-B1-L2 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-23 | 2019-09-11 | Prefer E;ectrical and Engineering Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 | 1 | UPGRADING |  | 5404154.78 | 4971473.03 | COMPLETED | 100% | 2020-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L4 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-06 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5 | 1 | UPGRADING | Batch 3 | 4919628.81 | 3545169.62 | COMPLETED | 100% | 2020-03-25 | 2020-09-12 | R06-022-ELECBEFF2019-B2-L512 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-12 | 2019-11-19 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302482 | Cawayan NHS | CARLES | 5 | 1 | UPGRADING | Batch 3 | 3195391.37 | 5481530.74 | COMPLETED | 100% | 2020-11-27 | 2020-09-30 | R06-022-ELECBEFF2019-B2-L513 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2020-11-14 | 2020-12-27 | Wilkinson Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5 | 1 | UPGRADING |  | 3321680.24 | 2448015.06 | COMPLETED | 100% | 2020-11-05 | 2020-09-28 | R06-022-ELECBEFF2019-B2-L7 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302484 | Roberto H. Tirol High School | CONCEPCION | 5 | 1 | UPGRADING |  | 3778057.05 | 2452880.48 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5 | 1 | UPGRADING |  | 5757201.84 | 3284414.42 | COMPLETED | 100% | Deceber 24, 2019 | 2020-03-20 | R06-022-ELECBEFF2019-B1-L5 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-05 | 2019-08-19 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302521 | Lemery National High School | LEMERY | 5 | 1 | UPGRADING | Batch 3 | 3701324.06 | 1863148.86 | COMPLETED | 100% | 2020-10-12 | 2020-09-25 | R06-022-ELECBEFF2019-B2-L1 |  | 2019-07-13 | 2019-07-22 | 2019-08-05 | 2019-11-18 | 2019-11-18 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5 | 1 | UPGRADING | Batch 3 | 3597861.45 | 5273446.66 | COMPLETED | 100% | 2019-12-24 | 2019-12-20 | R06-022-ELECBEFF2019-B1-L3 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-08 | 2019-08-19 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo | 302541 | Nicomedes R. Tubar Sr. NHS | SAN DIONISIO | 5 | 1 | UPGRADING | Batch 3 | 5520235.18 | 2921170.95 | COMPLETED | 100% | 2019-12-25 | 2019-12-19 | R06-022-ELECBEFF2019-B1-L1 |  | 2018-10-29 | 2018-11-05 | 2018-11-20 | 2019-08-09 | 2019-08-20 | MICRO-ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1838904.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117605 | Graciano Lopez Jaena ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING | Batch 3 | 2039709.09 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1372197.71 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Iloilo City | 117617 | Mandurriao Elementary School | ILOILO CITY (Capital) | 0 | 1 | UPGRADING |  | 1890587.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117832 | Basak ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 628605.53 | 550460.45 | COMPLETED | 100% | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 262470.43 | 260100 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117879 | Candiacap ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 407822.33 | 331508.3 | COMPLETED | 100% | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117882 | Dr. Pablo Torre PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 446008.26 | 370031.25 | COMPLETED | 100% | [9 empty] | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 302794 | Inapoy NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 289754.27 | 287300 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117861 | Kabanyohan Elementary School | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 256850.37 | 253800 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 365146.42 | 362300 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117843 | Lorenzo Zayco ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 760560.62 | 665681.84 | COMPLETED | 100% | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117846 | NOAC ELEMENTARY SCHOOL | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 329604.62 | 237776.08 | COMPLETED | 100% | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117889 | Nursery PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 405171.76 | 311542.08 | COMPLETED | 100% | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 346562.59 | 343800 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 878730.89 | 872600 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117852 | Tagukon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 412868.5 | 409800 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117871 | Tampalon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 728041.35 | 722700 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 427403.76 | 424200 | COMPLETED | 100% | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | UPGRADING | Batch 1 | 2150211.82 | 1731414 | COMPLETED | 100% | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 2 | 1 | UPGRADING | Batch 1 | 1780753.92 | 2370390.96 | COMPLETED | 100% | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | UPGRADING | Batch 1 | 1708168.21 | 1697812.15 | COMPLETED | 100% | 2019-12-27 | [6 empty] | 2019-08-19 | 2019-08-19 | TMTC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | UPGRADING | Batch 1 | 2535306.24 | 1432540 | COMPLETED | 100% | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302803 | Gemumua-Agahon National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 2942803.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 500205 | Man-it Integrated School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 2942803.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302804 | Mulapula National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 2942803.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 117908 | Passi I Central School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 3 | 3195391.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302805 | Passi National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 5456918.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Passi City | 302807 | Salngan National High School | CITY OF PASSI | 4 | 1 | UPGRADING | Batch 1 | 3195391.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117690 | Alfredo E. Marañon Sr. ES | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 785518.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117724 | Bato Central Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117693 | Bulanon Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 596388.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117716 | Gil Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117696 | Jose B. Puey Sr. Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2632677.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 826799.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117721 | Maria Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2121705.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117700 | Old Sagay Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 2436633.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117704 | Raymundo Tupas Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 823050.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 343922 | Sagay City Senior High School (Stand Alone) | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 311801 | Sagay National High School - Old Sagay Ext. | SAGAY CITY | 2 | 1 | UPGRADING |  | 864251.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 767526.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117811 | Bongol ES | SILAY CITY | 3 | 1 | UPGRADING |  | 229262.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1105925.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1295636.98 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117807 | Gov. Emilio Gaston Memorial ES | SILAY CITY | 3 | 1 | UPGRADING |  | 1653365.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 117817 | Mambag-id ES | SILAY CITY | 3 | 1 | UPGRADING |  | 404044.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VI | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3 | 1 | UPGRADING |  | 663530.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bais City | 120083 | Basak ES | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 626888.75 |  | ONGOING | 95% | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 303214 | Dodong Escaño Memorial High School | BAIS CITY | 2 | 1 | UPGRADING |  | 669552.47 |  | ONGOING | 95% | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | UPGRADING |  | 702562.43 |  | ONGOING | 95% | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | UPGRADING |  | 576229.83 |  | ONGOING | 95% | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 323010 | LUCILA C. YARED NATIONAL HIGH SCHOOL | BAIS CITY | 2 | 1 | UPGRADING |  | 587257.24 |  | ONGOING | 95% | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 323012 | Mayor Praxedes P. Villanueva II Memorial High School | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 711104.26 |  | ONGOING | 95% | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bais City | 323008 | OKIOT NATIONAL HIGH SCHOOL | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 578323.59 |  | ONGOING | 95% | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region VII | Bayawan City | 120129 | Dita Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1329213.33 | 1321567.26 | COMPLETED | 100% |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bayawan City | 120160 | Mandu-aw Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1528962.97 | 1519355.67 | COMPLETED | 100% |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bayawan City | 120161 | Minaba Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1417540.05 | 1408664.46 | COMPLETED | 100% |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 312431 | Anonang Sur Tabaco Frasco National High School | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 764782.24 | 756394.8 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 312405 | Bartolome C.Pianar MNHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 694909.17 | 687119.16 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302931 | Binabag NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 1219758.42 | 1201604.17 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302932 | Cayang NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 990347.65 | 976920.87 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 500408 | Don Celestino Martinez Sr. Taytayan IS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1205778.44 | 1187851.32 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302933 | Don Potenciano Catarata MNHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 1181894.88 | 1150857.5 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302930 | Eduardo T. Oporto Memorial National High School | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1163306.89 | 1153023.49 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | May 10, 2019 | May 20, 2019 | June 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 2124036.52 | 2029454.29 | COMPLETED | 100% | Nov. 27, 2019 | Mar. 12, 2020 | [5 empty] | Jan. 11, 2019 | August 29,2019 | FE AND A |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1260924.03 | 1247945.84 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 2380700.33 | 2359221.93 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bogo City | 302937 | Odlot NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 885454.79 | 875318.51 | COMPLETED | 100% | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | UPGRADING |  | 1500130.47 | 1342928.34 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | ROMERO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | UPGRADING | Batch 3 | 1441092.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | UPGRADING |  | 1306035.61 | 1298492.96 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1 | 1 | UPGRADING | Batch 3 | 934808.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302877 | Mantacida National High School | CATIGBIAN | 1 | 1 | UPGRADING | Batch 3 | 1037282.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1 | 1 | UPGRADING |  | 1121295.01 | 1059900.95 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302853 | Gov. Jacinto Borja National High School | LOON | 1 | 1 | UPGRADING |  | 1279258.03 | 1122580.33 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | ROMERO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | UPGRADING |  | 1439183.94 | 1360376.14 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | WIL TAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | UPGRADING |  | 1121295.01 | 1114621.36 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | UPGRADING |  | 1622744.38 | 1453167.3 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | QUICKSILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302840 | Dagohoy NHS / Integrated SHS | DAGOHOY | 2 | 1 | UPGRADING | Batch 3 | 2044307.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302827 | Campao Oriental High School | GETAFE | 2 | 1 | UPGRADING |  | 1296500.39 | 1161015.54 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | QUICKSILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | UPGRADING |  | 1118740.94 | 1111579.64 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 500213 | Cabanugan IS | SAN ISIDRO | 2 | 1 | UPGRADING | Batch 3 | 1254384.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | UPGRADING |  | 1657336.99 | 1647049.98 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | UPGRADING |  | 1223518.06 | 1081533.6 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | HUSAIN CONSTRUCTION AND SUPPLY CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | UPGRADING |  | 1514170.88 | 1333198.44 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | HUSAIN CONSTRUCTION AND SUPPLY CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 312351 | Cagting High School | UBAY | 2 | 1 | UPGRADING | Batch 3 | 772287.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 500215 | Tubog IS | UBAY | 2 | 1 | UPGRADING | Batch 3 | 1395894.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | UPGRADING |  | 1679323.91 | 1668875.84 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | MABB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Carcar City | 303127 | Gelacio C. Babao, Sr. MNHS | CITY OF CARCAR | 1 | 1 | UPGRADING |  | 1864201.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Carcar City | 303072 | Perrelos NHS | CITY OF CARCAR | 1 | 1 | UPGRADING |  | 1998094.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | UPGRADING | Batch 3 | 1538720.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 | 1 | UPGRADING | Batch 3 | 893827.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303067 | Teodoro dela Vega Memorial National High School | SIBONGA | 1 | 1 | UPGRADING | Batch 3 | 741211.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302951 | Bulak NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 1334760.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 1804027.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302952 | Tubod Dugoan NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 985206.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 1772322.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 2050960.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303053 | Maya National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 665408.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 1109878.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 3003822.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303026 | Curva National High School | MEDELLIN | 4 | 1 | UPGRADING |  | 1076389.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | UPGRADING |  | 941659.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | UPGRADING |  | 684764.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303021 | Jose R. Martinez Memorial National High School | SAN REMIGIO | 4 | 1 | UPGRADING |  | 725929.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 500920 | Kinawahan Integrated School | SAN REMIGIO | 4 | 1 | UPGRADING |  | 710628.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119669 | San Remigio Central ES | SAN REMIGIO | 4 | 1 | UPGRADING |  | 1561178.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 500665 | Tambongon IS | SAN REMIGIO | 4 | 1 | UPGRADING |  | 1073551.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119141 | Borbon Central ES | BORBON | 5 | 1 | UPGRADING | Batch 3 | 1520194.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303108 | Doña Milagros MNHS | BORBON | 5 | 1 | UPGRADING |  | 1060183.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | UPGRADING | Batch 3 | 1871896.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302978 | Catmon NHS | CATMON | 5 | 1 | UPGRADING |  | 1394827.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5 | 1 | UPGRADING | Batch 3 | 1855667.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303063 | Compostela National High School(Day Class) | COMPOSTELA | 5 | 1 | UPGRADING |  | 2750363.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 312406 | Compostela Science & Technology High School | COMPOSTELA | 5 | 1 | UPGRADING |  | 830428.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | UPGRADING |  | 1973022.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303109 | Liki NHS | SOGOD | 5 | 1 | UPGRADING | Batch 3 | 1298572.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303110 | Mohon NHS | SOGOD | 5 | 1 | UPGRADING | Batch 3 | 1271670.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119240 | Garing ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1040435.13 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 2156222.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1004489.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 119244 | Nangka ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 842559.08 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 302991 | Pulpogan NHS | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1351102.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu | 303114 | Tayud National High School | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1336948.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500669 | Adlaon IS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 704596.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500043 | Agsungot IS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 761992.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1081846.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303131 | BINALIW NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 436612.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1362393.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303160 | Pit-os National High School | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1676992.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 540255.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303150 | Don Sergio Osmeña, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1486432.37 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500224 | Dr. Emilio Osmeña IS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 602168.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303146 | Mambaling NHS (Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1031692.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1631492.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500226 | Pamutan Integrated School | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 599065.32 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1301297.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 303163 | Sinsin NHS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 519287.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Cebu City | 500670 | Toong IS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 479897.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 325301 | Alpaco National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 976338.5 | 971405.34 | COMPLETED | 100% | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 900921.84 | 896366.92 | COMPLETED | 100% | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 303065 | Naga National High School | CITY OF NAGA | 1 | 1 | UPGRADING |  | 4383858.3 | 3808193.58 | COMPLETED | 100% | 2019-10-31 | 2019-10-31 | cityofnaga 2018-0002 | - | 2018-11-07 | 2018-11-13 | 2018-11-26 | 2018-12-19 | 2019-07-31 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 500218 | Naga Special Education Center Elementary | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 516631.46 | 513977.39 | COMPLETED | 100% | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 325303 | Tinaan National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 506001.94 | 503421.45 | COMPLETED | 100% | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Danao City | 302959 | Elpidio H. Perez Memorial Technical-Vocational High School | DANAO CITY | 5 | 1 | UPGRADING | Batch 3 | 2208910.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Danao City | 302956 | Estefa O. Monte Memo. National High School | DANAO CITY | 5 | 1 | UPGRADING |  | 2143925.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | UPGRADING |  | 2126360.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Danao City | 303039 | Ramon M. Durano Sr. MNHS | DANAO CITY | 5 | 1 | UPGRADING | Batch 3 | 2213442.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Dumaguete City | 303166 | Camanjac National High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 777148.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Dumaguete City | 303170 | Hermenegilda F. Gloria Memorial High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 773014.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Dumaguete City | 119939 | West City Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 843322.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 1031892.17 |  | COMPLETED | 100% | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 938636.74 |  | COMPLETED | 100% | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 1156419.11 |  | COMPLETED | 100% | [9 empty] | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING |  | 3693802.81 | 3391690.156 | COMPLETED | 100% |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 303178 | Mactan National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING |  | 3560873.36 | 3256413.0028 | COMPLETED | 100% |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | Batch 3 | 3178120.9 |  | COMPLETED | 100% |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | GOLDEN HAMMER CONST. AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | UPGRADING | Batch 3 | 1454413.14 | 1660967.69 | COMPLETED | 100% |  |  | 19-005 | 2019-005 | 2018-10-30 | 2018-11-09 | 2018-11-22 | 2018-12-03 |  | DBB Industrial Service |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303203 | Paknaan NHS | MANDAUE CITY | 6 | 1 | UPGRADING |  | 1703057.37 |  | COMPLETED | 100% |  |  | 19-009 |  | 2019-07-11 | 2019-07-18 | 2019-08-07 | 2019-08-09 |  | DBB Industrial Service |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc HS (Mandaue City CNHS - Subangdaku NHS Ext.) | MANDAUE CITY | 6 | 1 | UPGRADING | Batch 3 | 822903.96 | 1093151.38 | COMPLETED | 100% |  |  | 19-005 | 2019-005 | 2018-10-30 | 2018-11-09 | 2018-11-22 | 2018-12-03 |  | DBB Industrial Service |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303204 | Tipolo NHS | MANDAUE CITY | 6 | 1 | UPGRADING |  | 1098728.74 |  | COMPLETED | 100% |  |  | 19-008 |  | 2019-07-11 | 2019-07-18 | 2019-08-07 | 2019-08-09 |  | DBB Industrial Service |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 |  | UPGRADING | Batch 3 | 922397.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 | 1 | UPGRADING |  | 3988592.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303243 | La Libertad Technical-Vocational School | LA LIBERTAD | 1 | 1 | UPGRADING |  | 1863791.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303289 | Tayasan National High School (Main) | TAYASAN | 1 | 1 | UPGRADING | Batch 3 | 694554.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1 |  | UPGRADING | Batch 3 | 604060.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303208 | Jantianon National High School | AMLAN (AYUQUITAN) | 2 |  | UPGRADING | Batch 3 | 627950.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303234 | Inapoy High School | MABINAY | 2 |  | UPGRADING | Batch 3 | 675652.01 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | UPGRADING | Batch 3 | 910437.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 |  | UPGRADING | Batch 3 | 577473.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312901 | Maningcao National High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 551832.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312944 | Sibulan Science High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 406268.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312918 | Buntod High School | BACONG | 3 |  | UPGRADING | Batch 3 | 639294.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312920 | Dauin Science High School | DAUIN | 3 |  | UPGRADING | Batch 3 | 628569.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | UPGRADING |  | 1728758.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303264 | Obat High School | SANTA CATALINA | 3 |  | UPGRADING | Batch 3 | 606756.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303265 | Sta. Catalina National High School | SANTA CATALINA | 3 | 1 | UPGRADING | Batch 3 | 900675.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 |  | UPGRADING | Batch 3 | 693170.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312970 | Caticugan HS | SIATON | 3 |  | UPGRADING | Batch 3 | 597167.29 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312941 | Giligaon High School | SIATON | 3 |  | UPGRADING | Batch 3 | 622658.35 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 |  | UPGRADING | Batch 3 | 608533.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | UPGRADING | Batch 3 | 712287.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303268 | Siaton NHS | SIATON | 3 | 1 | UPGRADING |  | 1923841.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 312914 | Siaton Science HS | SIATON | 3 |  | UPGRADING | Batch 3 | 558999.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Negros Oriental | 303236 | Jose Marie Locsin MHS (Mayabon HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | Batch 3 | 666385.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120658 | Enrique Villanueva Central Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | Batch 3 | 291882.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 500232 | Cabulihan Integrated School ( Junior & Senior HS) | LARENA | 0 | 1 | UPGRADING |  | 142341.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120659 | Larena Central Elementary School | LARENA | 0 | 1 | UPGRADING |  | 422610.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120675 | Kimba Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 228294.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120676 | Kinamandagan Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 286904.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 303294 | Kinamandagan High School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 250257.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120677 | Lazi Central School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 372866.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | UPGRADING |  | 2389150.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120705 | San Juan Central School | SAN JUAN | 0 | 1 | UPGRADING |  | 532602.64 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120703 | Ponong Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 224400.12 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 303299 | Ponong High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 234567.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Siquijor | 120706 | Siquijor Central Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING |  | 268142.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tagbilaran City | 118708 | Dao Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 1913651.14 | 1652962.32 | COMPLETED | 100% | January 27, 2020 | January 9, 2020 |  |  |  |  | September 1, 2019 |  |  | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Talisay City | 119785 | Borromeo Brothers Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 574834.53 | 723962.8553 | COMPLETED | 100% |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Talisay City | 119788 | Maghaway Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 574200.11 | 570699.0793 | COMPLETED | 100% |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Talisay City | 119790 | San Roque Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 3 | 574200.11 | 569431.98 | COMPLETED | 100% |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Talisay City | 119791 | Talisay City Central Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 729760.29 | 569592.2953 | COMPLETED | 100% |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303281 | Azagra High School | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 813570.41 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1133550.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1194551.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1478797.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 312915 | Inawasan PCHS | PAMPLONA | 2 | 1 | UPGRADING |  | 568874.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 | 1 | UPGRADING |  | 690777.83 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | UPGRADING |  | 619053.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | UPGRADING |  | 1402437.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | UPGRADING |  | 949301.95 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3 | 1 | UPGRADING |  | 1442889.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 798288.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303311 | General Climaco NHS | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 1601790.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3 | 1 | UPGRADING |  | 910940.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303312 | Magdugo National High School | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 1068777.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303313 | Matab-ang NHS | TOLEDO CITY | 3 | 1 | UPGRADING |  | 1578804.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VII | Toledo City | 303316 | Toledo National Vocational School | TOLEDO CITY | 3 | 1 | UPGRADING |  | 854559.93 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 327501 | Banahao National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 833968.42 | 818355.58 | COMPLETED | 100% | NOV. 28, 2019 | [7 empty] | August 23, 2019 | NV&C Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1293654.95 | 1260802.44 | COMPLETED | 100% | NOV. 28, 2019 | October 30, 2019 | [6 empty] | August 23, 2019 | QCC Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121079 | Baybay I CS (Baybay North CS) | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 2027630.48 | 2007540.28 | COMPLETED | 100% | February 10.2020 |  | 2019-07-002 | 2019-07-002 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | JFR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303360 | Caridad National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2506936.93 | 2486132.63 | COMPLETED | 100% | NOV. 28, 2019 | [7 empty] | August 23, 2019 | HD Golden Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 500672 | Gabas Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 2368113.65 | 2329314.43 | COMPLETED | 100% | February 10.2020 |  | 2019-07-004 | 2019-07-004 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | QCC Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121121 | Maitum Elementary School | CITY OF BAYBAY | 5 | 1 | UPGRADING | Batch 3 | 794359.38 | 780000 | COMPLETED | 100% | February 10.2020 | January 8, 2020 | 2019-07-003 | 2019-07-003 | July 24, 2019 | August 5, 2019 | August 28, 2019 | August 30, 2019 | November 5, 2019 | J.Costurio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303419 | Plaridel National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2320890.78 | 2268965.73 | COMPLETED | 100% | NOV. 28, 2019 | [7 empty] | August 23, 2019 | AGB Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2698921.42 | 2602929.56 | COMPLETED | 100% | NOV. 28, 2019 | [7 empty] | August 23, 2019 | Melgazo Construcion and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Baybay City | 121099 | Pres. Carlos P. Garcia Elementary School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 552077.41 | 548181.4 | COMPLETED | 100% | NOV. 28, 2019 | November 25, 2019 | [6 empty] | August 23, 2019 | Kublai Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA | 0 | 1 | UPGRADING |  | 2474179.07 | 2451434.04 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-09-16 | VFD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120762 | Jamorawon ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 763488.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120763 | Lo-ok ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 596700.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120770 | TABUNAN ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 736334.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA | 0 | 1 | UPGRADING |  | 1674198.95 | 1643867.02 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-30 | G. BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120772 | Tamarindo ES | ALMERIA | 0 | 1 | UPGRADING | Batch 3 | 740876.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313201 | Western Biliran High School for the Arts and Culture | ALMERIA | 0 | 1 | UPGRADING |  | 1476540.44 | 1464153.21 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-16 | 5 STARS J CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | 0 | 1 | UPGRADING |  | 4315524.95 | 4262590.55 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-16 | QYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | UPGRADING | Batch 3 | 518226.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | 0 | 1 | UPGRADING |  | 1716408.95 | 1702869.6 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-14 | WB ALAGAO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303321 | Bool NHS | CULABA | 0 | 1 | UPGRADING |  | 2683076.97 | 2664076 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-22 | A&B ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 120827 | Baganito ES | KAWAYAN | 0 | 1 | UPGRADING | Batch 3 | 769843.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303326 | Kawayan National High School | KAWAYAN | 0 | 1 | UPGRADING | Batch 3 | 2683076.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | 0 | 1 | UPGRADING |  | 1658247.21 | 1634100 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-23 | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Biliran | 313204 | Naval Night High School | NAVAL (Capital) | 0 | 1 | UPGRADING |  | 1283291.55 | 1271575.43 | COMPLETED | 100% |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-21 | 2018-12-05 | 2019-08-28 | NB ANG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 371928.57 | 365497.76 | COMPLETED | 100% | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 1 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122392 | Bagong Barrio ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 344753.14 | 341857.58 | COMPLETED | 100% | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122394 | Baras ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1079665.66 | 1072602.03 | COMPLETED | 100% | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122357 | Calico-an ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 601189.1 | 594787.29 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122379 | Maypangdan ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 1918464.33 | 1898117.84 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 3 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122405 | Pinanag-an ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 443748.2 | 439836.86 | COMPLETED | 100% | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 2 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122381 | Punta Maria ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 585891.5 | 579210.98 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122383 | San Andres Lower PS | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 374798 | 371346.72 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122362 | San Gabriel ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1295134.72 | 1279785.59 | COMPLETED | 100% | 2020-01-02 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 2 | Electrification-Lot 1 | 2019-06-21 | 2019-07-01 | 2019-07-16 | 2019-08-09 | 2019-09-07 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122363 | San Jose ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 1120481.91 | 1106232.37 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Borongan City | 122388 | Sta. Fe ES | CITY OF BORONGAN (Capital) | 0 | 1 | UPGRADING |  | 593062.41 | 586638.66 | COMPLETED | 100% | 2019-12-03 |  | CY 2019 ELECTRIFICATION PROJECT-Batch 1 | Electrification-Lot 1 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 344634 | Calbayog Arts and Design School of Eastern Visayas | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1521797.1 | 1503534.84 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L6 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | PEDAB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313801 | Calbayog City National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 3167353.68 | 3120777.4 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L3 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | RNA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313806 | Calbayog City National High School - Carayman Campus | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2260062.51 | 2233700.43 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L5 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313811 | Malaga NHS - Pena I Annex School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 1756058.96 | 1467398.23 | COMPLETED | 100% |  |  | CY2019 BEFF-ESSM-CAL-L4 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 313802 | Migara National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2058442.24 | 2038083.44 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L4 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303648 | Pilar National Agricultural High School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 2764113.16 | 2061162.77 | COMPLETED | 100% |  |  | CY2019 BEFF-ESSM-CAL-L3 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303649 | R. Lentejas Mem. School Of Fisheries | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 3066543.55 | 2010360 | COMPLETED | 100% |  |  | CY2019 BEFF-ESSM-CAL-L2 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303650 | San Joaquin National HIgh School | CALBAYOG CITY | 1 | 1 | UPGRADING | Batch 3 | 3066543.55 | 2010360 | COMPLETED | 100% |  |  | CY2019 BEFF-ESSM-CAL-L1 | FOR ISSUANCE | JULY 25, 2019 | AUGUST 2, 2019 | AUGUST 14, 2019 | UNDER POSTQUAL | FOR ISSUANCE | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303651 | San Policarpo National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2864923.29 | 2835596.49 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Calbayog City | 303652 | Tarabucan National High School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2461682.77 | 2418917.79 | COMPLETED | 100% | NOV. 30, 2020 |  | BEFF 2019-MES-CAL-L2 | FOR ISSUANCE | NOVEMBER 21, 2018 | NOVEMBER 14, 2018 | DECEMBER 11, 2018 | FOR ISSUANCE | FOR ISSUANCE | TOM BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123419 | Bliss Community School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2347694.34 | 2310452.23 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L7 | CY 2019_ESUP_R8_CC-L7 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123408 | Bunu-Anan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1901559.27 | 1872996.44 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L3 | CY2019-BEFF-B2-ESUP-R8-CC-L3 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | SANGREE INDUSTRIAL SALES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123429 | Buri Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2043838.16 | 2021935.66 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L7 | CY2019-BEFF-B2-ESUP-R8-CC-L7 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123397 | Catbalogan I Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3073527.29 | 3032885.2 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L1 | CY 2019_ESUP_R8_CC-L1 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123423 | Catbalogan III Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3043381.6 | 2540401.82 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L8 | CY 2019_ESUP_R8_CC-L8 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-12 | LOBRIÑOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123431 | Catbalogan IV Central Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2853315.25 | 2818239.45 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L9 | CY 2019_ESUP_R8_CC-L9 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123416 | Catbalogan V CES (Mercedes ES) | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3024692.47 | 2462009.45 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L5 | CY 2019_ESUP_R8_CC-L5 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-12 | LOBRIÑOS CONSOLIDATED CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123410 | Darahuway Dako Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1946024.07 | 1919374.51 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L4 | CY2019-BEFF-B2-ESUP-R8-CC-L4 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-11 | ALPHAHAWK CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123411 | Darahuway Guti ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046394.53 | 2020776.32 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L5 | CY2019-BEFF-B2-ESUP-R8-CC-L5 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-11 | ALPHAHAWK CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123412 | Guinsorongan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1944453.82 | 1914317.18 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L2 | CY 2019_ESUP_R8_CC-L2 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 303621 | Guinsorongan NHS | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2013419.26 | 2002145.87 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L12 | CY 2019_ESUP_R8_CC-L12 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-04 | HEROES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123413 | Ibol Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2055580.5 | 2039541.59 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L3 | CY 2019_ESUP_R8_CC-L3 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123432 | Iguid Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2047016.35 | 2012943.09 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L8 | CY2019-BEFF-B2-ESUP-R8-CC-L8 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MJM BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123435 | Jose P. Casiño Sr. Memorial ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2046771.39 | 2011633.41 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L10 | CY 2019_ESUP_R8_CC-L10 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123425 | Lagundi ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046049.08 | 2005733.46 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L6 | CY2019-BEFF-B2-ESUP-R8-CC-L6 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123414 | Madalunot Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 1980883.65 | 1955629.43 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L4 | CY 2019_ESUP_R8_CC-L4 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123433 | New Mahayag Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046539.78 | 2011306.61 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L9 | CY2019-BEFF-B2-ESUP-R8-CC-L9 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123434 | Old Mahayag Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1899411.17 | 1859875.31 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L10 | CY2019-BEFF-B2-ESUP-R8-CC-L10 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123417 | Pangdan Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 2651694.99 | 2627508.24 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L6 | CY 2019_ESUP_R8_CC-L6 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-10 | BEECARTINE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123436 | Pupua Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1844919.52 | 1823554.86 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L11 | CY2019-BEFF-B2-ESUP-R8-CC-L11 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-15 | RICHMARK CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123404 | Salug Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2046834.2 | 2021528.48 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L1 | CY2019-BEFF-B2-ESUP-R8-CC-L1 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | HEROES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 303620 | Samar National School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 1 | 3287646.75 | 3255662.01 | COMPLETED | 100% |  |  | CY 2019_ESUP_R8_CC-L11 | CY 2019_ESUP_R8_CC-L11 | 2019-01-07 | 2019-01-15 | 2019-01-29 | 2019-03-04 | 2019-09-11 | MAGA CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123405 | San Andres Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2692019.04 | 2667429.97 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L2 | CY2019-BEFF-B2-ESUP-R8-CC-L2 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | HAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123437 | San Roque ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1885537.99 | 1870029.88 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L12 | CY2019-BEFF-B2-ESUP-R8-CC-L12 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | BENCH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Catbalogan City | 123438 | San Vicente Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1885066.91 | 1853736.47 | COMPLETED | 100% |  |  | CY2019-BEFF-B2-ESUP-R8-CC-L13 | CY2019-BEFF-B2-ESUP-R8-CC-L13 | 2019-09-02 | 2019-09-13 | 2019-09-27 | 2019-09-29 | 2019-10-14 | NV & C CONSTRUCTION AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122326 | Bato Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 591167.88 | 584236.31 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 1 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122327 | Beri Elementary School | ARTECHE | 0 | 1 | UPGRADING |  | 671405.64 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122328 | Bigo Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 370052.61 | 365763.68 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 1 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122335 | Concepcion Elementary School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 1082533.51 | 1070510.31 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 2 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 313522 | Concepcion National High School | ARTECHE | 0 | 1 | UPGRADING | Batch 3 | 717392.92 | 709489.69 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 2 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122452 | Gap-ang Elementary School | DOLORES | 0 | 1 | UPGRADING | Batch 3 | 889010.44 | 878349.39 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 7 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | UPGRADING | Batch 3 | 2154756.42 |  | COMPLETED | 100% | JAN. 12, 2020 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | [6 empty] | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 3 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303532 | Tubabao National High School | GUIUAN | 0 | 1 | UPGRADING | Batch 3 | 522514.14 | 519901.56 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 4 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122585 | Bacayawan Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 449935.04 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-7 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122586 | Banika Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 854696.08 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-7 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122591 | Canliwag Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 362954.05 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-8 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 1874589.86 | 2487265.11 | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-1 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | 0 | 1 | UPGRADING |  | 2516975.27 | 2487265.11 | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-1 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122597 | Minaanod Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 597804.62 | 591430.39 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122599 | Piliw Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 444381.23 | 441117.73 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122601 | San Miguel Elementary School | LLORENTE | 0 | 1 | UPGRADING | Batch 3 | 583019.28 | 577451.88 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 8 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122604 | Tabok Elementary School | LLORENTE | 0 | 1 | UPGRADING |  | 838595.58 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-8 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | 0 | 1 | UPGRADING |  | 893712.1 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-2 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122659 | Buntay Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 1126339.85 | 1114000 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 6 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122665 | Iwayan Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 726245.06 | 718961.17 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 9 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122639 | Japay Elementary School | ORAS | 0 | 1 | UPGRADING | Batch 3 | 678676.63 | 671038.83 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 9 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122642 | Malingon Elementary School | ORAS | 0 | 1 | UPGRADING |  | 384979.03 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122645 | Pangudtan Elementary School | ORAS | 0 | 1 | UPGRADING |  | 610470.56 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-3 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122649 | Saurong Elementary School | ORAS | 0 | 1 | UPGRADING |  | 569055.39 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-2 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122704 | Alog Elementary School | SALCEDO | 0 | 1 | UPGRADING | Batch 3 | 377979.21 | 375098.44 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 4 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 408504.58 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-4 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122710 | Burak Elementary School | SALCEDO | 0 | 1 | UPGRADING | Batch 3 | 1174080.38 | 1162000 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 5 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122718 | Matarinao Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 716067.2 |  | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-4 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | UPGRADING |  | 2937017.52 | 2907983.05 | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-5 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 122773 | San Pablo Elementary School | TAFT | 0 | 1 | UPGRADING | Batch 3 | 876030.76 | 871650.61 | COMPLETED | 100% | JAN. 12, 2020 |  | ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON-GRID SCHOOLS BATCH 2-LOT 7 |  | August 8, 2019 | August 14, 2019 | August 27, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | 0 | 1 | UPGRADING |  | 1867566.93 | 1843338.78 | COMPLETED | 100% | DEC. 17, 2019 |  | CY 2019 BEFF ELECTRIFICATION OF UN-ENERGIZED SCHOOLS AND MODERNIZATION OF ELECTRICAL SYSTEMS ON GRID SCHOOL LOT-6 |  | October 26, 2018 | November 7, 2018 | November 20, 2019 | August 6, 2019 | August 13, 2019 | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1 | 1 | UPGRADING |  | 2559647.31 | 2185607.3626 | COMPLETED | 100% |  |  | lot 1-cy-2019-E-B1-leyte | lot 1-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121009 | Gov. E. Jaro ES | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 898563.28 |  | COMPLETED | 100% |  |  | lot 3-cy-2019-E-B2-leyte | lot 3-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121013 | Malibago Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 1259097.68 |  | COMPLETED | 100% |  |  | lot 1-cy-2019-E-B2-leyte | lot 1-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121015 | Pagsulhugon Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 991832.39 | 1265105.9498 | COMPLETED | 100% |  |  | lot 2-cy-2019-E-B2-leyte | lot 2-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303413 | Pagsulhugon National High School | BABATNGON | 1 | 1 | UPGRADING |  | 1483471.57 | 1265105.9498 | COMPLETED | 100% |  |  | lot 2-cy-2019-E-B1-leyte | lot 2-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121018 | San Agustin Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 630906.23 |  | COMPLETED | 100% |  |  | lot 1-cy-2019-E-B2-leyte | lot 1-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121021 | Taguite Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 693222.65 |  | COMPLETED | 100% |  |  | lot 2-cy-2019-E-B2-leyte | lot 2-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121022 | Uban Elementary School | BABATNGON | 1 | 1 | UPGRADING | Batch 3 | 753618.11 |  | COMPLETED | 100% |  |  | lot 3-cy-2019-E-B2-leyte | lot 3-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303432 | STA. MESA NATIONAL HIGH SCHOOL | DAGAMI | 2 | 1 | UPGRADING |  | 3769162.06 | 3711756.32 | COMPLETED | 100% |  |  | lot 3-cy-2019-E-B1-leyte | lot 3-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | BLACK NAZARENE BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121527 | Julita Central School | JULITA | 2 | 1 | UPGRADING |  | 1227786.41 | 959815.3754 | COMPLETED | 100% |  |  | lot 4-cy-2019-E-B1-leyte | lot 4-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121572 | La Paz Central School | LA PAZ | 2 | 1 | UPGRADING |  | 1280880.53 | 1091706.8674 | COMPLETED | 100% |  |  | lot 5-cy-2019-E-B1-leyte | lot 5-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121576 | Mag-aso Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 886142.26 |  | COMPLETED | 100% |  |  | RFQ1-cy-2019-E-B2-leyte | RFQ1-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121582 | Rizal Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 632089.73 |  | COMPLETED | 100% |  |  | lot 4-cy-2019-E-B2-leyte | lot 4-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121584 | Sta. Ana Elementary School | LA PAZ | 2 | 1 | UPGRADING | Batch 3 | 1158603.62 |  | COMPLETED | 100% |  |  | lot 4-cy-2019-E-B2-leyte | lot 4-cy-2019-E-B2-leyte | 2019-06-24 | 2019-07-03 | 2019-07-15 | 2019-08-07 | 2019-08-09 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121701 | Burgos Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 692390.85 |  | COMPLETED | 100% |  |  | RFQ3-cy-2019-E-B2-leyte | RFQ3-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121705 | Liberty Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 654053.51 |  | COMPLETED | 100% |  |  | RFQ4-cy-2019-E-B2-leyte | RFQ4-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121707 | Mayorga Central School | MAYORGA | 2 | 1 | UPGRADING |  | 1340308.85 | 1091706.8674 | COMPLETED | 100% |  |  | lot 6-cy-2019-E-B1-leyte | lot 6-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | UPGRADING | Batch 3 | 916655.04 |  | COMPLETED | 100% |  |  | RFQ2-cy-2019-E-B2-leyte | RFQ2-cy-2019-E-B2-leyte | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Leyte | 303427 | Seguinon National High School | ALBUERA | 4 | 1 | UPGRADING |  | 2729312.17 | 2342487.9176 | COMPLETED | 100% |  |  | lot 7-cy-2019-E-B1-leyte | lot 7-cy-2019-E-B1-leyte | 2018-10-17 | 2018-10-24 | 2018-11-09 | 2019-08-07 | 2019-08-09 | GOLDENTEC CONTRACTOR CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 303464 | Libhu National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 3030279.24 | 2946977.22 | COMPLETED | 100% |  |  | ELECTRIFICTION-19-7-002 | ELECTRIFICTION-19-7-002 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 122135 | Maasin Central School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 3450000 | 3366284.2 | COMPLETED | 100% |  |  | ELECTRIFICTION-19-7-001 | ELECTRIFICTION-19-7-001 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Maasin City | 303469 | Manhilo National High School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING | Batch 2 | 2941716.74 | 2857629.21 | COMPLETED | 100% |  |  | ELECTRIFICTION-19-7-003 | ELECTRIFICTION-19-7-003 | 2019-07-30 | 2019-08-08 | 2019-08-22 | 2019-08-29 | 2019-11-21 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303570 | Polangi National HIgh School | CATARMAN (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2042069.78 | 2029870.49 | COMPLETED | 100% |  |  | BEFF2019-B2-ELEC-NS-L1 | BEFF2019-B2-ELEC-NS-L1 |  | Aug. 8, 2019 | Aug. 20, 2019 | Sept. 2, 2019 |  | HD GOLDEN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303573 | Rosario National High School | ROSARIO | 1 | 1 | UPGRADING |  | 1654345.69 | 1065752.65 | COMPLETED | 100% |  |  | BEFF2019-ELEC-NS-L1 | BEFF2019-ELEC-NS-L1 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303530 | Alegria NHS | SAN ISIDRO | 1 | 1 | UPGRADING |  | 1449724.7 | 936709.96 | COMPLETED | 100% |  |  | BEFF2019-ELEC-NS-L2 | BEFF2019-ELEC-NS-L2 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | JCAD ENGINEERING & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303544 | Catubig Valley NHS | CATUBIG | 2 | 1 | UPGRADING |  | 1941673.21 | 1254931.67 | COMPLETED | 100% |  |  | BEFF2019-ELEC-NS-L3 | BEFF2019-ELEC-NS-L3 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | JCAD ENGINEERING & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 313603 | Rawis National High School | LAOANG | 2 | 1 | UPGRADING |  | 2016055.02 | 1206281.85 | COMPLETED | 100% |  |  | BEFF2019-ELEC-NS-L4 | BEFF2019-ELEC-NS-L4 |  | Dec. 7, 2018 | Dec. 19, 2018 | Jan. 9, 2019 |  | ROSS ENGINEERING & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Northern Samar | 303546 | Don Juan F. Avalon National High School | SAN ROQUE | 2 | 1 | UPGRADING | Batch 3 | 1949178.92 | 1938010.69 | COMPLETED | 100% |  |  | BEFF2019-B2-ELEC-NS-L2 | BEFF2019-B2-ELEC-NS-L2 |  | Aug. 8, 2019 | Aug. 20, 2019 | Sept. 2, 2019 |  | SMU CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124204 | Curva Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | Batch 3 | 1694778.98 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B2-C3 | BEFF-2019-E-B2-C3 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124212 | Libertad Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 2366776.16 | 2307111.11 | COMPLETED | 100% | November 16, 2019 |  | BEFF-2019-E-B1-C1 | BEFF-2019-E-B1-C1 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | Melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124213 | Licuma Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 1257239.84 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B2-C1 | BEFF-2019-E-B2-C1 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124214 | Liloan Central School | Ormoc City | 4 | 1 | UPGRADING |  | 2263899.43 | 2230387.17 | COMPLETED | 100% | November 16, 2019 |  | BEFF-2019-E-B1-C2 | BEFF-2019-E-B1-C2 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124215 | Margen Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 2133592.31 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B2-C4 | BEFF-2019-E-B2-C4 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124216 | Mas-in Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 1967118.43 | 1944292.34 | COMPLETED | 100% | November 16, 2019 |  | BEFF-2019-E-B1-C3 | BEFF-2019-E-B1-C3 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 344795 | Ormoc City Sports Senior High School | Ormoc City | 4 | 1 | UPGRADING |  | 1184245.46 | 1148493.36 | COMPLETED | 100% | November 16, 2019 |  | BEFF-2019-E-B1-C5 | BEFF-2019-E-B1-C5 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | melgazo Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124218 | Salvacion Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 1984626.42 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B2-C5 | BEFF-2019-E-B2-C5 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124169 | San Antonio Elementary School | ORMOC CITY | 4 | 1 | UPGRADING | Batch 3 | 1700055.36 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B2-C2 | BEFF-2019-E-B2-C2 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124219 | San Isidro Elementary School | Ormoc City | 4 | 1 | UPGRADING |  | 2004096.7 | 1938938.91 | COMPLETED | 100% | November 16, 2019 |  | BEFF-2019-E-B1-C4 | BEFF-2019-E-B1-C4 | October 30, 2018 | November 7, 2018 | November 19, 2018 | November 22, 2018 | August 9, 2019 | QCC Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Ormoc City | 124223 | Sto. Nino Elementary School | Ormoc City | 4 | 1 | UPGRADING | Batch 3 | 2130360.89 |  | COMPLETED | 100% |  |  | BEFF-2019-E-B1-C6 | BEFF-2019-E-B2-C6 | July 2, 2019 | July 11 2019 | July 23, 2019 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 123507 | Concepcion ES | GANDARA | 1 | 1 | UPGRADING |  | 478258.94 | 469858.84 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 123516 | Nacube Elementary School | GANDARA | 1 | 1 | UPGRADING | Batch 3 | 482107.83 | 477979.53 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | H.A.H REVERIE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 313734 | Sto. Niño IS | GANDARA | 1 | 1 | UPGRADING |  | 1527702.63 | 1514910.82 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 313708 | San Jorge NHS | SAN JORGE | 1 | 1 | UPGRADING |  | 2158365.56 | 2135282.9 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | BENCH CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303629 | Sta. Margarita NHS | SANTA MARGARITA | 1 | 1 | UPGRADING | Batch 3 | 1382210.1 | 1354969.37 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | PABLO S. LABASBAS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303635 | OESTE NHS | TARANGNAN | 1 | 1 | UPGRADING | Batch 3 | 1026448.14 | 1010982.7 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | VFD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303634 | Tarangnan NHS | TARANGNAN | 1 | 1 | UPGRADING | Batch 3 | 2498105.12 | 2459837.45 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | TOM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303637 | Valeriano C. Yancha MAS | BASEY | 2 | 1 | UPGRADING |  | 6330348.24 | 6247643.19 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | MAGA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303606 | Hinabangan NHS | HINABANGAN | 2 | 1 | UPGRADING | Batch 3 | 2242201.28 | 2215897.49 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303614 | Osmeña NHS | MARABUT | 2 | 1 | UPGRADING |  | 3466907.47 | 3053776.52 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | BLACK NAZARENE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303640 | Quintin Quijano SAS | PINABACDAO | 2 | 1 | UPGRADING |  | 2055565.25 | 2040000.83 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303627 | San Sebastian NHS | SAN SEBASTIAN | 2 | 1 | UPGRADING | Batch 3 | 1417708.1 | 1400570.14 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303636 | Tominamos IS | SANTA RITA | 2 | 1 | UPGRADING |  | 1983478.83 | 1943204.7 | COMPLETED | 100% | OCT. 22, 2019 |  |  |  | October 18, 2018 |  | November 7, 2018 | 2019-08-09 | 2019-08-16 | PYUKEI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303639 | Villareal NHS | VILLAREAL | 2 | 1 | UPGRADING | Batch 3 | 2139035.77 | 2106294.45 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | UPGRADING | Batch 3 | 2142887.6 | 2120725.92 | COMPLETED | 100% |  |  |  |  | 2019-06-26 | 2019-07-03 | 2019-07-15 |  |  | NV&C CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 313403 | Bontoc National High School | BONTOC | 0 | 1 | UPGRADING | Batch 3 | 4978956.62 | 4890275.91 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L1 | BEFF-CY2019-B2-ELECTRIFICATION-L1 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN | 0 | 1 | UPGRADING | Batch 3 | 4266684.2 | 2759718.17 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L2 | BEFF-CY2019-B2-ELECTRIFICATION-L2 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 0 | 1 | UPGRADING | Batch 3 | 4069143.06 | 2429565.22 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L3 | BEFF-CY2019-B2-ELECTRIFICATION-L3 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 313409 | Liloan National Technical Vocational High School | LILOAN | 0 | 1 | UPGRADING |  | 8150875.02 | 8084882.48 | COMPLETED | 100% |  |  | BEFF-CY2019- ELECTRIFICATION-L1 | BEFF-CY2019- ELECTRIFICATION-L1 | Nov. 6, 2018 | Nov. 14, 2018 | Nov. 27, 2018 | Dec. 7, 2018 | 2019-08-22 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | 0 | 1 | UPGRADING | Batch 3 | 5162592.23 | 3184129.7 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L4 | BEFF-CY2019-B2-ELECTRIFICATION-L4 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Maxter Resources Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 0 | 1 | UPGRADING | Batch 3 | 5898252.2 | 5796677.51 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L5 | BEFF-CY2019-B2-ELECTRIFICATION-L5 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303461 | Hingatungan NHS | SILAGO | 0 | 1 | UPGRADING | Batch 3 | 4298980.85 | 4244575 | COMPLETED | 100% |  |  | BEFF-CY2019-B2-ELECTRIFICATION-L6 | BEFF-CY2019-B2-ELECTRIFICATION-L6 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Southern Leyte | 303486 | Silago NVHS | SILAGO | 0 | 1 | UPGRADING | Batch 3 | 5689118.46 | 5630573.22 | COMPLETED | 100% | 2020-04-10 |  | BEFF-CY2019-B2-ELECTRIFICATION-L7 | BEFF-CY2019-B2-ELECTRIFICATION-L7 | 2019-07-09 | 2019-07-17 | 2019-07-29 | 2019-08-28 | 2019-12-05 | Vhits D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124256 | City CS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1690724.22 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124257 | Kapangian Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1632794.18 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303664 | Marasbaras NHS | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 3214060.75 | 3166003.26 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 5138521.43 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124228 | Remedios T. Romualdez ES (Rizal Central Annex ES) | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1943458.18 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124229 | Sagkahan ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 3801154.14 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 3655037.55 | 2269553.71 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124249 | San Fernando Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2739384.28 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124250 | San Jose ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 5081529.16 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303667 | San Jose National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 5028520.62 | 4920358.77 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-14 | 2018-11-26 |  |  | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124260 | Sto. Nino SPED Center | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 3183652.83 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303670 | Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2748292.82 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 344881 | Tacloban City Stand Alone 1 Senior High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1599219.19 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 6049755.3 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region VIII | Tacloban City | 124230 | V & G Mem. ES | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 2285155.06 |  | COMPLETED | 100% |  |  |  |  | 2019-07-03 | 2019-07-10 | 2019-07-22 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303947 | Baungon National High School | BAUNGON | 1 | 1 | UPGRADING | Batch 3 | 804834.05 |  | COMPLETED | 100% |  |  |  |  | 2019-10-05 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303955 | Halapitan National High School | SAN FERNANDO | 2 | 1 | UPGRADING | Batch 1 | 775314.25 |  | COMPLETED | 100% | 2021-01-13 | 2021-08-21 |  |  | 2019-10-06 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 314910 | Dangcagan National High School - Miaray Annex | DANGCAGAN | 3 | 1 | UPGRADING | Batch 1 | 588498.6 |  | COMPLETED | 100% | 2020-12-21 | 2021-08-26 |  |  | 2019-10-07 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303953 | Dangcagan NHS | DANGCAGAN | 3 | 1 | UPGRADING | Batch 1 | 647341.99 |  | COMPLETED | 100% | 2020-12-21 | 2021-08-26 |  |  | 2019-10-08 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 314922 | New Nongnongan NHS - San Nicolas Annex | DON CARLOS | 3 | 1 | UPGRADING | Batch 1 | 538656.57 |  | COMPLETED | 100% | 2021-04-18 | 2021-08-22 |  |  | 2019-10-09 |  |  |  |  | Maxwell EECS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Bukidnon | 303961 | Kiburiao National High School | QUEZON | 3 | 1 | UPGRADING | Batch 3 | 853065.56 |  | COMPLETED | 100% | 2022-12-29 |  |  |  | 2019-10-10 |  |  |  |  | Ariane Construction and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127996 | Baikingon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 697653.39 |  | COMPLETED | 100% | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315412 | Bonbon National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1000263.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304109 | Canitoan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1255382.9 |  | COMPLETED | 100% | Awaiting schedule of local electric cooperative. |  |  |  | 2018-12-12 | 2018-12-26 | 2018-12-26 | 2019-01-04 | 2019-07-31 | Brima Cons. & Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1790256.84 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1941221.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304119 | Lumbia National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 2328026.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127999 | Pedro "Oloy" N. Roa, Sr. Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1439467.18 |  | COMPLETED | 100% | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127984 | Taglimao Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 947753.04 |  | COMPLETED | 100% | Awaiting schedule of local electric cooperative. |  |  |  | 2019-09-09 | 2019-09-16 | 2019-09-30 | 2019-11-21 | 2019-11-22 | CESCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315406 | Taglimao NHS-Tumpagon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 881941.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304123 | Tignapoloan NHS | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1335878.46 |  | COMPLETED | 100% | Awaiting schedule of local electric cooperative. |  |  |  | 2018-12-12 | 2018-12-26 | 2018-12-26 | 2019-01-04 | 2019-07-31 | Brima Cons. & Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127994 | Upper Carmen Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1031342.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304111 | CAGAYAN DE ORO NATIONAL HIGH SCHOOL | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 2342064.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315404 | Camaman-an National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1560623.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127943 | FS Catanico Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 547270.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315408 | Gusa NHS - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 853842.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1423490.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127965 | Indahag Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1621312.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127950 | Linangohan Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 856819.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304120 | Macabalan National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 2185874.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127957 | North City Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1504365.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127952 | Puerto Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1214394.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 315402 | Puerto National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 770450.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 127958 | St. John Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 416813.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Cagayan de Oro City | 304105 | Tablon National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | UPGRADING |  | 1355233.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127667 | Amoros ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5878705.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 4884049.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 6356922.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 8256610.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5889258.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7033670.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5887148.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 6356922.23 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7770416.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5346837.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5889258.72 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127669 | San Francisco de Asis ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7038947.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 7017841.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127680 | Taytay ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5539849.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | El Salvador City | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2 | 1 | UPGRADING | Batch 2 | 5362666.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 315505 | Gingoog City CNHS - Anakan NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 1 | 1134057.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 315504 | Gingoog City CNHS - PUNDASAN NHS Annex | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 1 | 1152391.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Gingoog City | 304137 | San Luis National High School | GINGOOG CITY | 1 | 1 | UPGRADING | Batch 3 | 1199571 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan HS Annex | ILIGAN CITY | 0 | 1 | UPGRADING | Batch 1 | 4287768.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1 | 1 | UPGRADING | Batch 3 | 3133952.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1 | 1 | UPGRADING | Batch 1 | 2730152.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City |  | Agalayan ES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 4753770.96 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City | 126558 | Bangcud CES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 5069639.71 |  | COMPLETED | 100% | 2022-10-25 |  | 001-INFRA-2019 | 001-INFRA-2019 |  |  |  |  | 2019-11-17 | Eriane Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City |  | Banglay NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2925354.21 |  | COMPLETED | 100% | 2022-10-25 |  | 001-INFRA-2019 | 001-INFRA-2019 |  |  |  |  | 2019-11-17 | Eriane Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Malaybalay City | 314904 | Malaybalay City National Science HS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 5689747.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Occidental | 304040 | LOOC NATIONAL HIGH SCHOOL | PLARIDEL | 1 | 1 | UPGRADING | Batch 1 | 4475570.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Occidental | 304028 | Bonifacio NHS | BONIFACIO | 2 | 1 | UPGRADING | Batch 3 | 2882425.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304061 | Baliwagan NHS | BALINGASAG | 1 | 1 | UPGRADING |  | 5788711.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1 | 1 | UPGRADING |  | 3139887.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304059 | Alubijid NCHS | ALUBIJID | 2 | 1 | UPGRADING |  | 5300533.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304072 | Initao NCHS | INITAO | 2 | 1 | UPGRADING |  | 5827967.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304078 | Laguindingan NHS | LAGUINDINGAN | 2 | 1 | UPGRADING |  | 5429912.66 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Misamis Oriental | 304094 | Opol NSTS | OPOL | 2 | 1 | UPGRADING |  | 5469168.94 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 5531661.99 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 6369752.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | UPGRADING | Batch 3 | 2701804.31 | 3656256.89 | COMPLETED | 100% | 2019-11-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 002 | 092-INFRA19-10 | 2019-07-12 | 2019-07-23 | 2019-08-05 | 2019-08-22 | 2019-10-22 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 5190029.02 | 5129078.87 | COMPLETED | 100% | 2019-12-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 003 | 092-INFRA19-11 | 2019-07-12 | 2019-07-23 | 2019-08-05 | 2019-08-22 | 2019-10-22 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | UPGRADING | Batch 3 | 5841193.64 | 5129078.87 | COMPLETED | 100% | 2019-12-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 001 | 092-INFRA19-08 | 2018-10-27 | 2018-11-05 | 2018-11-20 | 2019-01-04 | 2019-08-28 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Ozamis City | 304162 | Tabid National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 3684680.29 | 3656256.89 | COMPLETED | 100% | 2019-11-26 |  | ELEC 2019 - RX - OZAMIZ CITY - 004 | 092-INFRA19-09 | 2018-10-27 | 2018-11-05 | 2018-11-20 | 2019-01-04 | 2019-08-28 | JUNJING CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region X | Valencia City | 314906 | Lilingayon National High School | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2116192.85 |  | ONGOING | 70% | 2024-08-01 |  | 43191 | N/A | 2020-10-24 | Negotiated Procurement | 2018-12-21 | 2019-02-07 | 2019-08-28 | Angel & Sam Construction & General Merchandise | Variation Order and Electrical Layout finished. Resumption of work to be issued | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 70% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304181 | Compostela NHS | COMPOSTELA | 1 | 1 | UPGRADING |  | 6295882.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304184 | Consuelo M. Valderrama NHS | COMPOSTELA | 1 | 1 | UPGRADING |  | 1436256.7 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304182 | Mangayon NHS | COMPOSTELA | 1 | 1 | UPGRADING | Batch 3 | 1680049.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304197 | Mapawa NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING |  | 1585552 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315815 | New Albay NHS | MARAGUSAN (SAN MARIANO) | 1 | 1 | UPGRADING |  | 2843195.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304176 | Babag NHS | MONKAYO | 1 | 1 | UPGRADING |  | 2770431.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304199 | Monkayo NHS | MONKAYO | 1 | 1 | UPGRADING |  | 3251134.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304212 | Tubo-Tubo NHS | MONKAYO | 1 | 1 | UPGRADING |  | 1344195.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315808 | Ulip NHS | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 2954167 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304214 | Union NHS | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 2627910.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315809 | Union NHS-Mt. Diwata HS Annex | MONKAYO | 1 | 1 | UPGRADING | Batch 3 | 1499867.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304204 | Mayaon NHS | MONTEVISTA | 1 | 1 | UPGRADING |  | 2689411.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304203 | Montevista NHS - Annex (DNAS Campus) | MONTEVISTA | 1 | 1 | UPGRADING | Batch 3 | 3129371.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304177 | Bantacan NHS | NEW BATAAN | 1 | 1 | UPGRADING |  | 2833856.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304188 | Kapatagan NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING |  | 3157939.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304190 | Kidawa NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | Batch 3 | 3626561.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304189 | Laak NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING |  | 3027138.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315804 | Melale NHS | LAAK (SAN VICENTE) | 2 | 1 | UPGRADING | Batch 3 | 2915818.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304173 | Anibongan NHS | MACO | 2 | 1 | UPGRADING |  | 1449654.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304172 | Andili NHS | MAWAB | 2 | 1 | UPGRADING |  | 1353002.48 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315802 | Nuevo Iloco NHS | MAWAB | 2 | 1 | UPGRADING |  | 1580540.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315803 | Tuboran NHS | MAWAB | 2 | 1 | UPGRADING | Batch 3 | 2663450.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 315806 | Kao NHS | NABUNTURAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 2681581.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Compostela Valley | 304209 | Tagugpo NHS | PANTUKAN | 2 | 1 | UPGRADING | Batch 3 | 1238368.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1 | 1 | UPGRADING |  | 5622172.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1 | 1 | UPGRADING | Batch 3 | 5483946.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304228 | Doña Carmen Soriano National High School | KAPALONG | 1 | 1 | UPGRADING |  | 2952034.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304235 | Sua-on National High School | KAPALONG | 1 | 1 | UPGRADING | Batch 3 | 2635137.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304249 | Mesaoy NHS | NEW CORELLA | 1 | 1 | UPGRADING |  | 2837977.31 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1 | 1 | UPGRADING |  | 6298939.34 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Norte | 304257 | Sto. Nino NHS | TALAINGOD | 1 | 1 | UPGRADING |  | 5634420.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128812 | Bansalan Central Elem. School | BANSALAN | 1 | 1 | UPGRADING | Batch 1 | 2383359.59 | 2207451.03 | COMPLETED | 100% | December 22,2019 |  |  | 1-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304285 | Pedro A. Arches NHS | BANSALAN | 1 | 1 | UPGRADING | Batch 1 | 1447719.2 | 1411278.87 | COMPLETED | 100% | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128836 | Villa Doneza CES | BANSALAN | 1 | 1 | UPGRADING | Batch 3 | 2335932.4 |  | COMPLETED | 100% |  |  |  | DS EM 2019-01 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128870 | Guihing Central Elementary School | HAGONOY | 1 | 1 | UPGRADING | Batch 1 | 2150399.76 | 2028932.94 | COMPLETED | 100% | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128855 | Hagonoy Central Elementary School | HAGONOY | 1 | 1 | UPGRADING | Batch 3 | 2087722.19 |  | COMPLETED | 100% |  |  |  | DS EM 2019-02 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128905 | Kiblawan CES | KIBLAWAN | 1 | 1 | UPGRADING | Batch 3 | 2322173.05 |  | COMPLETED | 100% |  |  |  | DS EM 2019-03 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128923 | Barayong CES | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 3 | 2112248.8 |  | COMPLETED | 100% |  |  |  | DS EM 2019-04 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128936 | Magsaysay CES | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 3 | 2269964.75 |  | COMPLETED | 100% |  |  |  | DS EM 2019-05 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1 | 1 | UPGRADING | Batch 1 | 4471791.79 | 4160109.59 | COMPLETED | 100% | December 22,2019 |  |  | 1-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 128954 | Malalag CES | MALALAG | 1 | 1 | UPGRADING | Batch 3 | 2078178.95 |  | COMPLETED | 100% |  |  |  | DS EM 2019-06 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129041 | Manga CES | MATANAO | 1 | 1 | UPGRADING | Batch 3 | 2102644.57 |  | COMPLETED | 100% |  |  |  | DS EM 2019-07 | July 22, 2019, Monday, 8:00 A.M. | June 26, 2019 Wednesday, 9:30 A.M | August 13, 2019, Tuesday, 9:30 A.M. |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao del Sur | 129017 | Matanao CES | MATANAO | 1 | 1 | UPGRADING | Batch 1 | 2319612.99 | 2205974.51 | COMPLETED | 100% | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 304290 | Sinawilan NHS | MATANAO | 1 | 1 | UPGRADING | Batch 1 | 1538968.47 | 1492297.94 | COMPLETED | 100% | December 22,2019 |  |  | 2-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | NLC Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129049 | Padada CES | PADADA | 1 | 1 | UPGRADING | Batch 1 | 2369621.24 | 2232525.74 | COMPLETED | 100% | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Del Sur | 129146 | Sulop CES | SULOP | 1 | 1 | UPGRADING | Batch 1 | 2353750.85 | 2221067.45 | COMPLETED | 100% | December 24,2019 |  |  | 3-DS-EM19 | October 23, 2018, 8:00AM | October 30, 2018, 1:30PM | November 12, 2018, 9:30 AM. | 2019-08-08 | 2019-09-04 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 316007 | Benjamin Velasco Bautista Sr. National High School | MALITA | 0 | 1 | UPGRADING | Batch 3 | 1408615.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304267 | FISHING VILLAGE COMPREHENSIVE NHS | MALITA | 0 | 1 | UPGRADING |  | 1257921.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304293 | Ticulon NHS | MALITA | 0 | 1 | UPGRADING | Batch 3 | 1249661.24 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Occidental | 304296 | Sta. Maria NHS | SANTA MARIA | 0 | 1 | UPGRADING |  | 1250031.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304312 | Crispin E. Rojas National High School | BAGANGA | 1 | 1 | UPGRADING |  | 5914339.61 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304307 | Caraga National High School | CARAGA | 1 | 1 | UPGRADING | Batch 3 | 3808099.56 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304315 | Evaristo Moralizon National Vocational High School | MANAY | 1 | 1 | UPGRADING | Batch 3 | 3654778.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Davao Oriental | 304339 | Tarragona National High School | TARRAGONA | 1 | 1 | UPGRADING |  | 3970083.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Digos City | 129762 | Aplaya ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 272386.5 | 269983.44 | COMPLETED | 100% | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Digos City | 129774 | Binaton ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 195783.19 | 194098.66 | COMPLETED | 100% | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Digos City | 129757 | Pedro Basalan ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 1 | 462830.42 | 583893.06 | COMPLETED | 100% | March 22, 2020 | July 23, 2020 | 19-11-167 | 19-11-167 | None | December 13, 2019 | December 17, 2019 | Dec 27, 2019 | January 30, 2020 | Kuplaer Indsutries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Digos City | 129756 | Remedios N. Saplala ES (Matti ES) | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 1 | 205576.2 | 204548.32 | COMPLETED | 100% | Oct. 27, 2019 | Oct. 23, 2019 | 18-10-163 | 18-10-163 | March 1-8, 2019 | March 5, 2019 | March 8, 2020 | March 8, 2020 | Sept. 19, 2019 | NLC Const. and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Digos City | 129772 | San Miguel ES | CITY OF DIGOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 59571.4 | 58635.31 | COMPLETED | 100% | February 3, 2020 | February 2, 2020 | 19-06-044 | 19-06-044 | July 16-23, 2019 | July 24, 2019 | August 15, 2019 | Sept. 2, 2019 | November 28, 2019 | NLC Const. and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Island Garden City of Samal | 304220 | Balet National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | Batch 1 | 1586709.82 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Island Garden City of Samal | 323406 | Diosdado Alorro Sr. National High School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | UPGRADING | Batch 3 | 1336130.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Mati City | 304301 | Manuel B.Guiñez Sr. NHS | BANAYBANAY | 2 | 1 | UPGRADING | Batch 3 | 5729701.05 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Mati City | 304325 | Mati National Comprehensive High School | CITY OF MATI (Capital) | 2 | 1 | UPGRADING |  | 8131204.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Panabo City | 304403 | A. O. Floirendo National High School | CITY OF PANABO | 2 | 1 | UPGRADING | Batch 1 | 4196054.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Panabo City | 304408 | Quezon High School - Panabo NHS Annex | CITY OF PANABO | 2 | 1 | UPGRADING | Batch 3 | 1980612.04 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Tagum City | 500424 | Busaon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING | Batch 3 | 283755.57 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Tagum City | 304238 | La Filipina NHS | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 342147.58 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Tagum City | 304226 | Laureta National High School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 475540.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XI | Tagum City | 500425 | Liboganon Integrated School | CITY OF TAGUM (Capital) | 1 | 1 | UPGRADING |  | 378339.03 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304628 | CANIZARES NATIONAL HIGH SCHOOL- School of Arts and Trades | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 4427334.88 | 2835068.08 | COMPLETED | 100% | Dec.6,2019 | Dec.6,2019 | GEPS 6278991 | 2019DIVINFRA-10 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304630 | Cotabato City NHS - Main | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 2851424.58 | 2835068.08 | COMPLETED | 100% | Dec.6,2019 | Dec.6,2019 | GEPS 6278980 | 2019DIVINFRA-08 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304633 | J. Marquez NHS | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 2851424.58 | 4403093.11 | COMPLETED | 100% | Dec.6,2019 | Dec.6,2019 | GEPS 6278974 | 2019DIVINFRA-07 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304635 | Pilot Provincial Science and Technology High School | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 4427334.88 | 4403093.11 | COMPLETED | 100% | Dec.6,2019 | Dec.6,2019 | GEPS 6278987 | 2019DIVINFRA-09 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317003 | Baluan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1776026.61 |  | COMPLETED | 100% | December 30, 2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 131275 | Balunto Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1476152.55 |  | COMPLETED | 100% | December 30,2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304649 | Datu B. Balunto National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1222548.19 |  | COMPLETED | 100% | December 30, 2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304651 | Ligaya High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1210745.69 |  | COMPLETED | 100% | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 2917622.17 |  | COMPLETED | 100% | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317002 | Pao-Pao High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1560238.02 |  | COMPLETED | 100% | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317006 | Samboang-Ngilay High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1249822.23 |  | COMPLETED | 100% | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304656 | Amas National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3218081.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304658 | Ginatilan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3011164.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3006881.53 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304663 | Kalaisan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3007232.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | North Cotabato | 304418 | Mariano Untal HS | M'LANG | 3 | 1 | UPGRADING | Batch 1 | 4710444.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 | UPGRADING | Batch 2 | 8690370 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304569 | Sto. Niño NSAT | SANTO NIÑO | 2 | 1 | UPGRADING |  | 3094443.62 | 2399143.54 | COMPLETED | 100% | 2019-11-10 |  |  | 2019-08-019 | 2018-11-27 |  | 2018-12-17 | 2019-08-06 | 2019-09-11 | ISULAN ECT CONSTRUCTION & GEN. MDSE INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | UPGRADING |  | 7901621.66 | 6179079.1 | COMPLETED | 100% | 2019-12-10 |  |  | 2019-08-0120 | 2018-11-27 |  | 2018-12-17 | 2019-08-06 | 2019-09-11 | ISULAN ECT CONSTRUCTION & GEN. MDSE INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Sultan Kudarat | 304585 | Bambad National High School | ISULAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 3308950.98 | 3072155.74 | COMPLETED | 100% | Sept. 28, 2020 |  |  | 003-2020 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Dec. 23, 2019 | Mar. 16, 2020 | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | UPGRADING | Batch 1 | 3960641.93 | 3703302.54 | COMPLETED | 100% | Sept. 28, 2020 |  |  | 004-2020 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Dec. 23, 2019 | Mar. 16, 2020 | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 134975 | Sinalang Pilot ES | BANGUED (Capital) | 0 | 1 |  |  | 2325119.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 134989 | Bucay CS | BUCAY | 0 | 1 |  |  | 2530994.45 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 |  |  | 3124480.97 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305085 | Dugong National High School | BUCAY | 0 | 1 |  |  | 2205406.49 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | 0 | 1 |  |  | 2754618.97 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | 0 | 1 |  |  | 1941154.08 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 135163 | Pilar CS | PILAR | 0 | 1 |  |  | 2843351.03 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 | 1 |  |  | 3450379.29 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-027 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 500518 | Ananaao Integrated School | TAYUM | 0 | 1 |  |  | 2416943.12 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305086 | Gaddani NHS | TAYUM | 0 | 1 |  |  | 2095457.75 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 |  |  | 2294929.15 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305103 | Tiempo NHS | TUBO | 0 | 1 |  |  | 2052137.17 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-ABRA-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 318807 | GUINA-ANG NATIONAL HIGHSCHOOL | CONNER | 0 | 1 |  |  | 1946390.46 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-APAYAO-07 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 135270 | Manag ES | CONNER | 0 | 1 |  |  | 1932634.32 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-APAYAO-06 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 135335 | Dagupan ES | LUNA | 0 | 1 |  |  | 1898669.32 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-APAYAO-02 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 219023 | AURORA ELEMENTARY SCHOOL | PUDTOL | 0 | 1 |  |  | 1507195.69 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-APAYAO-04 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305271 | Bakakeng National High School | BAGUIO CITY | 0 | 1 |  |  | 3536740.13 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136400 | Dona Aurora Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4194111.6 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305283 | Magsaysay National High School | BAGUIO CITY | 0 | 1 |  |  | 3600644.7 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4010117.36 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305286 | PINGET NATIONAL HIGH SCHOOL | BAGUIO CITY | 0 | 1 |  |  | 3478361.02 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136387 | Quezon Hill Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4287937.2 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | 0 | 1 |  |  | 3835888.09 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-BAGUIO CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 305128 | AMPUSONGAN NATIONAL HIGH SCHOOL | BAKUN | 0 | 1 |  |  | 1148722.67 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135400 | AMPUSONGAN ELEMENTARY SCHOOL | BAKUN | 0 | 1 |  |  | 1376458.67 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135474 | BUYACAOAN ELEMENTARY SCHOOL | BUGUIAS | 0 | 1 |  |  | 921858.9 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 318903 | TAWANGAN-LUSOD NATIONAL HIGH SCHOOL | KABAYAN | 0 | 1 |  |  | 814995.99 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135569 | DATAKAN ELEMENTARY SCHOOL | KAPANGAN | 0 | 1 |  |  | 1008841.81 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135577 | Lomon ES | KAPANGAN | 0 | 1 |  |  | 1228139.29 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135578 | LONGBOY ELEMENTARY SCHOOL | KAPANGAN | 0 | 1 |  |  | 1437244 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 318916 | BENGUET NATIONAL HIGHSCHOOL ANNEX - PUGUIS | LA TRINIDAD | 0 | 1 |  |  | 1832563.75 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135623 | BUYAGAN ELEMENTARY SCHOOL | LA TRINIDAD | 0 | 1 |  |  | 2144617.49 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135624 | LA TRINIDAD CENTRAL SCHOOL | LA TRINIDAD | 0 | 1 |  |  | 2562477.97 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135737 | TUBLAY CENTRAL ELEMENTARY SCHOOL | TUBLAY | 0 | 1 |  |  | 1385694.8 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 305164 | TUBLAY SCHOOL OF HOME INDUSTRIES EXTENSION - CENTRAL | TUBLAY | 0 | 1 |  |  | 2134596.13 |  | COMPLETED | 100% |  |  | ELEC 2020 - CAR - BENGUET - 030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135776 | Namillangan ES | ALFONSO LISTA (POTIA) | 0 | 1 |  |  | 889922.77 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135854 | Hapao ES | HUNGDUAN | 0 | 1 |  |  | 855129.65 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 305180 | Hungduan National High School | HUNGDUAN | 0 | 1 |  |  | 779595 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135880 | Boliwong ES | LAGAWE (Capital) | 0 | 1 |  |  | 888564.87 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135899 | Hapid ES | LAMUT | 0 | 1 |  |  | 905829.18 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135920 | Balangbang ES | MAYOYAO | 0 | 1 |  |  | 993175.79 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-IFUGAO-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 135964 | BALBALASANG ELEMENTARY SCHOOL | BALBALAN | 0 | 1 | UPGRADING |  | 2121606.84 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 135978 | PANTIKIAN ELEMENTARY SCHOOL | BALBALAN | 0 | 1 | UPGRADING |  | 1903853.35 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | 0 | 1 | UPGRADING |  | 1185308.31 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136040 | Camalog Elementary School | PINUKPUK | 0 | 1 | UPGRADING |  | 1571899.4 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 305202 | Cawagayan National High School | PINUKPUK | 0 | 1 | UPGRADING |  | 1901551.09 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136050 | Malagnat Elementary School | PINUKPUK | 0 | 1 | UPGRADING |  | 1165665.29 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 319103 | Tappo Vocational High School | PINUKPUK | 0 | 1 | UPGRADING |  | 1208434.9 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 305224 | Tanudan National High School | TANUDAN | 0 | 1 | UPGRADING |  | 1092110.71 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-KALINGA-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305235 | BARLIG NATIONAL HIGH SCHOOL | BARLIG | 0 | 1 |  |  | 2505211.2 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136203 | BEBE ELEMENTARY SCHOOL | BAUKO | 0 | 1 |  |  | 1340937.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136210 | Guinzandan Norte Elementary School | BAUKO | 0 | 1 |  |  | 1496193.22 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305250 | LESEB NATIONAL HIGH SCHOOL | BAUKO | 0 | 1 |  |  | 1217330.66 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-033 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136214 | LETANG ELEMENTARY SCHOOL | BAUKO | 0 | 1 |  |  | 1447809.04 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305245 | TAPAPAN NATIONAL HIGH SCHOOL | BAUKO | 0 | 1 |  |  | 2200700.78 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319225 | AGAWA NATIONAL HIGH SCHOOL | BESAO | 0 | 1 |  |  | 1544204.81 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136239 | DANDANAC ELEMENTARY SCHOOL | BESAO | 0 | 1 |  |  | 1175205.75 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-056 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136248 | TAMBUAN ELEMENTARY SCHOOL | BESAO | 0 | 1 |  |  | 1164664.7 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-068 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305243 | GUINAANG NATIONAL HIGH SCHOOL | BONTOC | 0 | 1 |  |  | 2251884.32 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319203 | SALIOK NATIONAL HIGH SCHOOL | NATONIN | 0 | 1 |  |  | 1304043.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136283 | ANONAT ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1109293.72 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-049 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136284 | APALIS ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1627051.48 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-067 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136289 | BUTIGUE ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1378027.96 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136293 | CASSAG ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1382281.03 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | 0 | 1 |  |  | 1356533.94 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-058 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136312 | SAN EMILIO ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1180937.47 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-059 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136332 | ANABEL ELEMENTARY SCHOOL | SADANGA | 0 | 1 |  |  | 1439225.63 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319222 | BALUGAN NATIONAL HIGH SCHOOL | SAGADA | 0 | 1 |  |  | 1645221.87 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-062 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | 0 | 1 |  |  | 1032716.69 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-032 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305241 | Am-am National High School | TADIAN | 0 | 1 |  |  | 2300796.48 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136358 | BANTEY ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1670514.35 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-071 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319224 | BUNGA NATIONAL HIGH SCHOOL | TADIAN | 0 | 1 |  |  | 2735248.21 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-074 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136361 | CADAD-ANAN ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1078239.63 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319217 | DACUDAC NATIONAL HIGH SCHOOL | TADIAN | 0 | 1 |  |  | 2541346.68 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136373 | PANDAYAN ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1107598.7 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-052 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 |  |  | 1518648.2 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-063 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136376 | TADIAN CENTRAL SCHOOL | TADIAN | 0 | 1 |  |  | 1908705.51 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-MT. PROVINCE-075 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2619754.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 136091 | Bulo East Elementary School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2414958.05 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2563438.63 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305196 | Eastern Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1547084.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2737711.74 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-027 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305212 | Nambaran Agro. Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2677613.63 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305207 | Nambucayan National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1548818.55 |  | COMPLETED | 100% |  |  | ELEC 2020-CAR-TABUK CITY-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 220501 | Pa-o ES | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1620958.12 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 3296269.15 |  | COMPLETED | 100% |  |  | ELEC-2020-CAR-TABUK CITY-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2 | 1 |  |  | 1618651.77 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 304677 | Carmen NHS | CARMEN | 2 | 1 |  |  | 1243610.78 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131433 | Jabonga Central Elementary School | JABONGA | 2 | 1 |  |  | 1641775.98 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131450 | Kitcharao CES | KITCHARAO | 2 | 1 |  |  | 1464358.77 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131485 | Magallanes CES | MAGALLANES | 2 | 1 |  |  | 1462870.78 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 | 1 |  |  | 1459645.15 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131500 | Nasipit CES | NASIPIT | 2 | 1 |  |  | 1560825.23 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2 | 1 |  |  | 1526790.1 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Norte | 131546 | Santiago CES | SANTIAGO | 2 | 1 |  |  | 1745805.59 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-Agusan Del Norte -018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304722 | Lucena NHS | PROSPERIDAD | 1 | 1 |  |  | 3012416.33 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 317442 | Afga Nhs | SIBAGAT | 1 | 1 |  |  | 2615202.1 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304740 | SIBAGAT NATIONAL HIGH SCHOOL OF HOME INDUSTRIES | SIBAGAT | 1 | 1 |  |  | 5205167.22 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 |  |  | 3860458.02 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304718 | Libertad NHS | BUNAWAN | 2 | 1 |  |  | 3759806.31 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Agusan del Sur | 304716 | La Paz NHS | LA PAZ | 2 | 1 |  |  | 3998159.77 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-AGUSAN DEL SUR-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131615 | Agusan del Sur Pilot Laboratory School | CITY OF BAYUGAN | 1 | 1 |  |  | 1424202.62 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131616 | Bayugan Central Elem. School SPED Center | CITY OF BAYUGAN | 1 | 1 |  |  | 1400511.95 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 304729 | Calaitan NHS | CITY OF BAYUGAN | 1 | 1 |  |  | 1428228.4 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 131596 | East Bayugan CES | CITY OF BAYUGAN | 1 | 1 |  |  | 1320371.2 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 317420 | Magkiangkang National High School | CITY OF BAYUGAN | 1 | 1 |  |  | 1441439.83 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bayugan City | 304724 | Mt. Olive National High School | CITY OF BAYUGAN | 1 | 1 |  |  | 1400511.95 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BAYUGAN CITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132834 | Mangagoy East ES | CITY OF BISLIG | 2 | 1 |  |  | 1127986.47 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BISLIG CITY-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132837 | Mangagoy South ES | CITY OF BISLIG | 2 | 1 |  |  | 1442285.01 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BISLIG CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bislig City | 322501 | San Jose NHS | CITY OF BISLIG | 2 | 1 |  |  | 1310336.46 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BISLIG CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bislig City | 132636 | San Vicente ES | CITY OF BISLIG | 2 | 1 |  |  | 1270630.11 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BISLIG CITY-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Bislig City | 304868 | San Vicente NHS | CITY OF BISLIG | 2 | 1 |  |  | 1311681.51 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BISLIG CITY-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317517 | Alviola ISS | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1443590.17 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1995868.08 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 132027 | Ampayon CES | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1547996.57 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317511 | Ampayon National High School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 2021533.04 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317506 | La Trinidad Integrated Secondary School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1968534.69 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Butuan City | 317521 | Pigdaulan National High School | BUTUAN CITY (Capital) | 1 | 1 |  |  | 1980367.49 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-BUTUAN CITY-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | CITY OF CABADBARAN | 2 | 1 |  |  | 1635417.68 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-CABADBARAN CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 |  |  | 1695411.85 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-CABADBARAN CITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 | 1 |  |  | 1660594.07 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-CABADBARAN CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 | 1 |  |  | 2845996.85 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132305 | Albor CES | LIBJO (ALBOR) | 0 | 1 |  |  | 2465085.22 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Dinagat Island | 132559 | TUBAJON CENTRAL ELEMENTARY SCHOOL | TUBAJON | 0 | 1 |  |  | 2410255.07 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-DINAGAT ISLANDS-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 | 1 |  |  | 1356517.38 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 |  |  | 1339658.53 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 132129 | Don Enrique Navarro Memorial School | DAPA | 1 | 1 |  |  | 1405433.03 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 304791 | Union National High School | DAPA | 1 | 1 |  |  | 1223271.85 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 | 1 |  |  | 1095063.55 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 |  |  | 1379086.87 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 | 1 |  |  | 1092485.34 |  | COMPLETED | 100% |  |  | Elec2020-CARAGA-SIARGAO-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 |  |  | 1171837.37 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao City | 304806 | Zaragoza National High School | SURIGAO CITY (Capital) | 2 | 1 |  |  | 1095649.99 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO CITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 304811 | Alegria NHS | ALEGRIA | 2 | 1 | UPGRADING |  | 1869023.38 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 304832 | Bunyasan NHS | MALIMONO | 2 | 1 | UPGRADING |  | 1866251.64 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 317807 | Pananay-an NHS - Annex (Placer NHS) | PLACER | 2 | 1 | UPGRADING |  | 1071080.82 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | UPGRADING |  | 1247830.26 |  | COMPLETED | 100% |  |  | ELEC-2020-CARAGA-SURIGAO DEL NORTE-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1 | 1 |  |  | 1453178.46 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132661 | CANTILAN PILOT ELEMENTARY SCHOOL | CANTILAN | 1 | 1 |  |  | 1241487.93 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-040 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132695 | CARRASCAL CENTRAL ELEMTARY SCHOOL | CARRASCAL | 1 | 1 |  |  | 1276863.39 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-036 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304858 | Anibongan National High School | LIANGA | 1 | 1 |  |  | 1552815.65 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304859 | Lianga National Comprehensive National High School | LIANGA | 1 | 1 |  |  | 1487789.52 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago National High School | MARIHATAG | 1 | 1 |  |  | 1609273.47 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304898 | Marihatag National Agricultural High School | MARIHATAG | 1 | 1 |  |  | 1489951.03 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304904 | Salvacion National High School | SAN AGUSTIN | 1 | 1 |  |  | 1588834.02 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304906 | Bolhoon National High School | SAN MIGUEL | 1 | 1 |  |  | 1458950.67 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132887 | SAN MIGUEL CENTRAL ELEMENTARY SCHOOL | SAN MIGUEL | 1 | 1 |  |  | 1242738.86 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-034 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304905 | San Miguel National Comprehensive High School | SAN MIGUEL | 1 | 1 |  |  | 1483216.35 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304907 | San Miguel National Comprehensive High School - Sagbayan Annex | SAN MIGUEL | 1 | 1 |  |  | 1544768.82 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304908 | San Miguel National High School | SAN MIGUEL | 1 | 1 |  |  | 1552193.49 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-027 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132890 | TINA CENTRAL ELEMENTARY SCHOOL | SAN MIGUEL | 1 | 1 |  |  | 1206157.31 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-032 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 304889 | Gamut National High School (Tago) | TAGO | 1 | 1 |  |  | 1587621.61 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132572 | BAROBO CENTRAL ELEMENTARY SCHOOL | BAROBO | 2 | 1 |  |  | 1634468.1 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-041 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132597 | TAMBIS CENTRAL ELEMENTARY SCHOOL | BAROBO | 2 | 1 |  |  | 1207366.06 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Surigao del Sur | 132924 | TAGBINA CENTRAL ELEMENTARY SCHOOL | TAGBINA | 2 | 1 |  |  | 1206112.47 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-SURIGAO DEL SUR-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132960 | Bongtud Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1095896.21 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-TANDAG CITY-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1657965.1 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-TANDAG CITY-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132978 | Tandag Central Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1893947 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-TANDAG CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1343682.33 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-TANDAG CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CARAGA | Tandag City | 304893 | Vicente L. Pimentel Sr. National High School | CITY OF TANDAG (Capital) | 1 | 1 |  |  | 1165750.43 |  | COMPLETED | 100% |  |  | ELEC2020-CARAGA-TANDAG CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Caloocan City | 223503 | Camarin D ES - Unit II | KALOOKAN CITY | 1 | 1 | UPGRADING |  | 6390654.15 |  | COMPLETED | 100% | May 20, 2021 |  | Elec2020-NCR-CaloocanCity-001 | PCA-2020-Infra-002 | November 13, 2020 | November 25, 2020 | December 7, 2020 | December 10, 2020 | December 21, 2020 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Caloocan City | 319701 | Cielito Zamora Junior High School | KALOOKAN CITY | 1 | 1 | UPGRADING |  | 9750743.89 |  | COMPLETED | 100% |  |  | Elec2020-NCR-CaloocanCity-002 | [7 empty] | For Contract (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | 0 | 1 | UPGRADING |  | 15261269.07 |  | COMPLETED | 100% |  |  | Elec2020-NCR-SanJuanCity-001 | [7 empty] | WAITING FOR SIGNED CONTRACT (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | City of San Juan | 305423 | San Juan NHS | CITY OF SAN JUAN | 0 | 1 | UPGRADING |  | 6095379.83 | 4790825.4 | COMPLETED | 100% | May 23, 2021 |  | Elec2020-NCR-SanJuanCity-001 | 2019-PB-002 | January 21, 2020 | February 17, 2020 | March 2, 2020 | March 9, 2020 | December 7, 2020 | MRRM TRADING AND CONSTRUCTION | with suspension order dated May31, 2021 due to on-going retrofitting works of DPWH (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136775 | Gatchalian ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 5467118.17 |  | COMPLETED | 100% |  |  | Elec2020-NCR-LasPiñasCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136777 | Las Pinas ES Central | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 5467118.17 | 4811832.89 | COMPLETED | 100% | 2021-04-19 | 2021-04-14 | Elec2020-NCR-LasPiñasCity-003 | 2020-I15 | 2020-09-29 | 2020-10-07 | 2020-10-15 | 2020-10-29 | 2020-11-20 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136785 | Moonwalk ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 8627777.87 | 8587148.52 | COMPLETED | 100% | 2021-05-06 |  | Elec2020-NCR-LasPiñasCity-001 | 2020-I14 | 2020-11-17 | 2020-11-25 | 2020-12-03 | 2020-12-03 | 2020-12-07 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Malabon City | 500339 | Tañong IS | CITY OF MALABON | 0 | 1 | UPGRADING |  | 6975267.42 | 6949952.93 | COMPLETED | 100% | 2021-03-01 |  | Elec2020-NCR-MalabonCity-001 | 2020-INFRA-09-0004 | 2020-INFRA-09-0004 | 2020-01-17 | 2020-01-22 | 2020-02-10 | 2020-10-01 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING |  | 10629227.43 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MandaluyongCity-001 | [7 empty] | For NTP (report as of august 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Mandaluyong City | 500332 | Highway Hills Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING |  | 4972820.43 | 4947956.33 | COMPLETED | 100% | December 4, 2020 | December 4, 2020 | Elec2020-NCR-MandaluyongCity-002 | 2020-Mandaluyong-02 | January 27, 2020 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | New Rich General Contractor Services & Trading Company, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 319907 | Jesus Dela Pena National High School | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 616687.82 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 907202.63 | 894685.63 | COMPLETED | 100% | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-001 | N/A |  | N/A |  |  | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 370622.76 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 3234416.47 | 782092.77 | COMPLETED | 100% | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-009 | N/A |  | N/A |  |  | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elementary level | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 978444.34 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 2371106.74 | 3184336.38 | COMPLETED | 100% | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-006 | N/A |  | N/A |  |  | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 387534.38 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 401248.84 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305630 | SSS NHS | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 698494.31 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MarikinaCity-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 793288.91 | 2321078.17 | COMPLETED | 100% | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-007 | N/A |  | N/A |  |  | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 8991962.94 | 8944660.24 | COMPLETED | 100% | May 5, 2021 June 19, 2021 |  | Elec2020-NCR-MuntinlupaCity-002 |  | 11/25/20 |  | 12/16/20 | 12/18/20 | 2020-12-01 | Berto Lucci Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 6167285.42 |  | COMPLETED | 100% |  |  | Elec2020-NCR-MuntinlupaCity-004 | [7 empty] | WAITING FOR MERALCO APPROVAL OF ELECTRICAL PLANS (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 500438 | Lakeview Integrated School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 7803693.73 | 7771377.04 | COMPLETED | 100% | May 5, 2021 June 19, 2021 |  | Elec2020-NCR-MuntinlupaCity-005 |  | 11/25/20 |  | 12/16/20 | 12/18/20 | 2020-12-01 | Berto Lucci Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 341221.55 |  | COMPLETED | 100% | [10 empty] | WAITING FOR MERALCO APPROVAL OF ELECTRICAL PLANS (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | UPGRADING |  | 5194059.48 |  | COMPLETED | 100% |  |  | Elec2020-NCR-NavotasCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | 0 | 1 | UPGRADING |  | 4963659.48 |  | COMPLETED | 100% |  |  | Elec2020-NCR-NavotasCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | UPGRADING |  | 6204317.63 |  | COMPLETED | 100% |  |  | Elec2020-NCR-ParañaqueCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Paranaque City | 136763 | La Huerta ES | CITY OF PARAÑAQUE | 2 | 1 | UPGRADING |  | 7574686.3 |  | COMPLETED | 100% |  |  | Elec2020-NCR-ParañaqueCity-001 | [7 empty] | with NTP (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | PASIG CITY | 0 | 1 | UPGRADING |  | 4033871.98 |  | COMPLETED | 100% |  |  | Elec2020-NCR-PasigCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | UPGRADING |  | 2193830.67 |  | COMPLETED | 100% |  |  | Elec2020-NCR-QuezonCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 | 1 | UPGRADING |  | 3088839.61 |  | COMPLETED | 100% |  |  | Elec2020-NCR-QuezonCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 360868 | SHS within MH del Pilar ES | QUEZON CITY | 1 | 1 | UPGRADING |  | 2113145.1 |  | COMPLETED | 100% |  |  | Elec2020-NCR-QuezonCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 136558 | Eulogio Rodriguez, Sr. ES | QUEZON CITY | 3 | 1 | UPGRADING |  | 6201820.73 |  | COMPLETED | 100% |  |  | Elec2020-NCR-QuezonCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 136554 | Libis ES | QUEZON CITY | 3 | 1 | UPGRADING |  | 5246186.81 |  | COMPLETED | 100% |  |  | Elec2020-NCR-QuezonCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 320607 | Agripino Manalo National HS | PATEROS | 1 | 1 | UPGRADING |  | 1342366.69 | 1342366.69 | COMPLETED | 100% | March 16, 2021 | February 24, 2021 | Elec2020-NCR-TaguigCity&Pateros-001 | DTP-CY-INFRA-007 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | AYZARIZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | UPGRADING |  | 8301022.67 | 5644539.47 | COMPLETED | 100% | March 16, 2021 | March 1, 2021 | Elec2020-NCR-TaguigCity&Pateros-003 | DTP-CY-INFRA-006 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | LORBEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 305467 | Maria Concepcion Cruz HS | PATEROS | 1 | 1 | UPGRADING |  | 3781382.22 | 3781382.22 | COMPLETED | 100% | March 16, 2021 | February 24, 2021 | Elec2020-NCR-TaguigCity&Pateros-002 | DTP-CY-INFRA-007 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | AYZARIZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 136896 | Pateros ES | PATEROS | 1 | 1 | UPGRADING |  | 13616612.01 |  | COMPLETED | 100% |  |  | Elec2020-NCR-TaguigCity&Pateros-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | UPGRADING |  | 15850864.57 |  | COMPLETED | 100% |  |  | Elec2020-NCR-ValenzuelaCity-002 | [7 empty] | awarded (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | UPGRADING |  | 15549594.13 |  | COMPLETED | 100% | 2021-05-29 |  | Elec2020-NCR-ValenzuelaCity-001 | INFRA-EPA-BEFF-2020-09-0002(LII) | 2019-11-27 | 2019-12-05 | 2019-12-17 | 2019-12-27 | 2020-10-01 | Steven Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101166 | Alaminos City Central School | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2373427.65 | 2369840.85 | COMPLETED | 100% | AUG. 7, 2021 | 2021-06-23 | Elec2020-RI-Alaminos City-001 |  | APRIL 14-20, 2021 | 2021-04-19 | 2021-04-21 | 2021-04-27 | 2021-05-10 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101178 | Dulacac ES | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1717802.92 | 1668486.7 | COMPLETED | 100% | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-005 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2362809.82 | 2220937.34 | COMPLETED | 100% | DEC.28,2020 |  | Elec2020-RI-Alaminos City-006 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2880676.56 | 2815050.02 | COMPLETED | 100% | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-012 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-28 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 500564 | Pangapisan IS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 2874221.77 | 2830911.74 | COMPLETED | 100% | DEC.26,2020 | DEC. 15, 2020 | Elec2020-RI-Alaminos City-008 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | MANIMELDS CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Alaminos City | 300260 | Telbang NHS | CITY OF ALAMINOS | 1 | 1 | UPGRADING |  | 1853337.22 | 1757869.11 | COMPLETED | 100% | DEC.28,2020 |  | Elec2020-RI-Alaminos City-011 |  | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 320803 | City of Batac National high school Payao | CITY OF BATAC | 2 | 1 |  |  | 1608316.11 |  | COMPLETED | 100% |  |  | Elec2020-RI-Batac City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2 | 1 |  |  | 2288538.2 |  | COMPLETED | 100% |  |  | Elec2020-RI-Batac City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Batac City | 340747 | Gen. Artemio Ricarte SHS | CITY OF BATAC | 2 | 1 |  |  | 1071054.4 |  | COMPLETED | 100% |  |  | Elec2020-RI-Batac City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100433 | Calaoa-an Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 709938.7 | 693017.52 | COMPLETED | 100% |  |  | Elec2020-RI-Candon City-008 | [5 empty] | 2020-10-02 | ELKAN ENG'G SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100434 | Calongbuyan Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 872816.04 |  | COMPLETED | 100% |  |  | Elec2020-RI-Candon City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100436 | Candon South Central School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 1370324.42 |  | COMPLETED | 100% |  |  | Elec2020-RI-Candon City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100437 | Caterman Elementary Annnex | CITY OF CANDON | 2 | 1 | UPGRADING |  | 767711.01 |  | COMPLETED | 100% |  |  | Elec2020-RI-Candon City-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Candon City | 100445 | Patpata Elementary School | CITY OF CANDON | 2 | 1 | UPGRADING |  | 1006019.04 |  | COMPLETED | 100% |  |  | Elec2020-RI-Candon City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 587052.26 |  | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RI-Dagupan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300369 | Carael National HS | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 622206.26 |  | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RI-Dagupan City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Dagupan City | 300371 | Judge Jose de Venecia, Sr. Technical-Vocational Secondary School | DAGUPAN CITY | 4 | 1 | UPGRADING |  | 578295.4 |  | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RI-Dagupan City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1 | 1 | UPGRADING |  | 1003799.34 | 998014.28 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-018 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1 | 1 | UPGRADING |  | 1507479.95 | 1505285.32 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-006 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG | 1 | 1 | UPGRADING |  | 2630637.25 | 2623501.81 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-014 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 500591 | Florentino Camaquin Integrated School | VINTAR | 1 | 1 | UPGRADING |  | 3220991.48 | 3204753.86 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-009 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 500343 | Pallas IS | VINTAR | 1 | 1 | UPGRADING |  | 2255397.9 | 2234380.79 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-012 |  |  |  | 2021-04-05 |  |  | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300010 | Caribquib NHS | BANNA (ESPIRITU) | 2 | 1 | UPGRADING |  | 1251461.73 | 1243660.7 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-005 |  | 2019-11-11 | 11/21/2019 | 2019-03-12 | 01/13/2020 | 2020-08-10 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Norte | 300015 | Dingras NHS/Lt. Edgar Foz Mem. NHS | DINGRAS | 2 | 1 | UPGRADING |  | 1752386.54 | 1742020.97 | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Norte-007 |  | 2019-11-11 | 11/21/2019 | 2019-03-12 | 01/13/2020 | 2020-08-10 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1 | 1 | UPGRADING |  | 1370276.32 | 1214762.12 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-002 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 500595 | BINACUD INTEGRATED SCHOOL | SINAIT | 1 | 1 | UPGRADING |  | 885237.08 | 801750.54 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-009 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 100653 | SINAIT WEST CS | SINAIT | 1 | 1 | UPGRADING |  | 1070193.08 | 968510.5 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-004 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300033 | Alilem NHS (Alilem Daya HS) | ALILEM | 2 | 1 | UPGRADING |  | 1733147.33 |  | COMPLETED | 100% |  |  | Elec2020-RI-Ilocos Sur-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300059 | Nagbukel NHS | NAGBUKEL | 2 | 1 | UPGRADING |  | 1075430.82 | 962407.34 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-015 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 500596 | Lungog Integrated School | NARVACAN | 2 | 1 | UPGRADING |  | 1114866.18 | 1024071.12 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-011 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2 | 1 | UPGRADING |  | 1466231.35 | 1358951.5 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-012 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Ilocos Sur | 300078 | Santiago NHS | SANTIAGO | 2 | 1 | UPGRADING |  | 1176447.5 | 1072233.01 | COMPLETED | 100% | 2020-12-21 |  | Elec2020-RI-Ilocos Sur-013 |  | 2020-01-20 | 2020-01-27 | 2020-02-07 | 2020-07-13 | 2020-09-23 | JUA Electrical Services & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300143 | SINAPANGAN NATIONAL HIGH SCHOOL | BALAOAN | 1 | 1 |  |  | 1017979.19 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500354 | Bungro Sococ IS | LUNA | 1 | 1 |  |  | 1030250.42 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 |  |  | 1004521.35 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300125 | Old Sudipen NHS | SUDIPEN | 1 | 1 |  |  | 1027428.11 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300134 | San Francisco NHS | SUDIPEN | 1 | 1 |  |  | 1037406.9 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300130 | Don Eufemio F. Eriguel MNHS | AGOO | 2 | 1 |  |  | 1037406.9 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500563 | San Julian IS | AGOO | 2 | 1 |  |  | 1059422.31 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300149 | Suyo NHS | BAGULIN | 2 | 1 |  |  | 935015.42 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 300102 | Burgos National High School | BURGOS | 2 | 1 |  |  | 1002880.86 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | La Union | 500361 | Cabaruan IS | SANTO TOMAS | 2 | 1 |  |  | 940338.94 |  | COMPLETED | 100% |  |  | Elec2020-RI-La Union-040 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 102209 | Gabaldon Elementary School | LAOAG CITY (Capital) | 1 | 1 |  |  | 1689350.51 |  | COMPLETED | 100% |  |  | Elec2020-RI-Laoag City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 300372 | Gabu NHS | LAOAG CITY (Capital) | 1 | 1 | UPGRADING |  | 1647339.36 | 1457191.76 | COMPLETED | 100% | 2021-08-01 |  | Elec2020-RI-Laoag City-001 | [6 empty] | Elocin Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Laoag City | 500742 | San Mateo Integrated School | LAOAG CITY (Capital) | 1 | 1 | UPGRADING |  | 995334.64 | 898971.44 | COMPLETED | 100% | 2021-08-01 |  | Elec2020-RI-Laoag City-003 | [6 empty] | Elocin Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300250 | SAN JOSE NHS | ANDA | 1 | 1 |  |  | 848388.02 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 500370 | BOLINAO IS | BOLINAO | 1 | 1 |  |  | 3019424.51 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300167 | Basista NHS | BASISTA | 2 | 1 |  |  | 507212.72 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 500368 | Urbiztondo IS | URBIZTONDO | 2 | 1 |  |  | 2185427.09 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300171 | Beleng NHS | BAYAMBANG | 3 | 1 |  |  | 834713.32 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300178 | Buenlag NHS | CALASIAO | 3 | 1 |  |  | 1262019.34 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3 | 1 |  |  | 1231259.59 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan I, Lingayen | 300176 | BOTAO NHS | STA. BARBARA | 3 | 1 |  |  | 437584.21 |  | COMPLETED | 100% |  |  | Elec2020-RI-Pangasinan I-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 | 1 | UPGRADING |  | 1840504.84 | 1763912.4 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-002 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300302 | Coloscaoayan NHS | BAUTISTA | 5 | 1 | UPGRADING |  | 1136466.71 | 1131139.91 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-003 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | UPGRADING |  | 1840504.84 | 1834900.42 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-001 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 500377 | Bantay Insik Integrated School | SISON | 5 | 1 | UPGRADING |  | 1230907.65 | 1225195.32 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-012 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | SEPTEMBER 24, 2019 | SEPTEMBER 28, 2019 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300366 | Unzad NHS | VILLASIS | 5 | 1 | UPGRADING |  | 1181071.98 | 1049662.54 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-017 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 101721 | Asingan North CS | ASINGAN | 6 | 1 | UPGRADING |  | 1376176.68 | 1376176.68 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-005 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300314 | Guiling-Coliling NHS | ROSALES | 6 | 1 | UPGRADING |  | 1145326.09 | 1017086.71 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-004 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300293 | Cabalitian NHS | UMINGAN | 6 | 1 | UPGRADING |  | 871363.59 | 775221.1 | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-006 |  | SEPTEMBER 10, 2019 | SEPTEMBER 17, 2019 | OCTOBER 1, 2019 | DECEMBER 2, 2020 | DECEMBER 7, 2020 | INTERLINK POWER CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6 | 1 | UPGRADING |  | 3246650.99 |  | COMPLETED | 100% | APRIL, 2021 |  | Elec2020-RI-Pangasinan II-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Carlos City | 300376 | Abanon NHS | SAN CARLOS CITY | 3 | 1 |  |  | 824544.53 |  | COMPLETED | 100% |  |  | Elec2020-RI-San Carlos City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Carlos City | 500058 | Guelew Integrated School | SAN CARLOS CITY | 3 | 1 |  |  | 1226569.27 |  | COMPLETED | 100% |  |  | Elec2020-RI-San Carlos City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101037 | BUNGRO ELEMENTARY SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 977888.78 | 938549.36 | COMPLETED | 100% | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-007 | CSFLU-INFRA-002-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101023 | Cadaclan ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1255161.23 | 1179071.69 | COMPLETED | 100% | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-006 | CSFLU-INFRA-001-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101040 | Masicong ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1471804.45 | 1304865.03 | COMPLETED | 100% | 2020-12-08 | 2020-10-30 | Elec2020-RI-San Fernando-002 | CSFLU-INFRA-003-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | RHOB CONSTRUCTION & ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101031 | Pao ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1240642.07 | 1238781.1 | COMPLETED | 100% | 2021-03-29 | 2021-03-11 | Elec2020-RI-San Fernando-003 | CSFLU-INFRA-003-2020 | 2020-12-01 | 2020-12-07 | 2020-12-21 | 2020-12-23 | 2020-12-29 | JC ELECTROFIELDS POWER SYSTEMS, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | San Fernando City | 101042 | Sacyud E/S | CITY OF SAN FERNANDO (Capital) | 1 | 1 | UPGRADING |  | 1024641.48 | 1023583.28 | COMPLETED | 100% | 2020-12-08 | 2020-11-23 | Elec2020-RI-San Fernando-001 | CSFLU-INFRA-004-2020 | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | 2020-09-09 | AE SQUARE ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 102269 | Badipa ES | CITY OF URDANETA | 5 | 1 |  |  | 906936.71 |  | COMPLETED | 100% | April 16, 2021 |  | Elec2020-RI-Urdaneta City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 300394 | Badipa NHS | CITY OF URDANETA | 5 | 1 |  |  | 874157.03 |  | COMPLETED | 100% |  |  | Elec2020-RI-Urdaneta City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Urdaneta City | 300398 | Camantiles NHS | CITY OF URDANETA | 5 | 1 |  |  | 1273032.67 |  | COMPLETED | 100% | April 16, 2021 |  | Elec2020-RI-Urdaneta City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100783 | Ayusan-Paoa Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 1062858.04 | 1040441.5 | COMPLETED | 100% |  |  | Elec2020-RI-Vigan City-001 | INFR-202-001 | 2021-03-23 | 2021-03-31 | 2021-04-13 | 2021-04-15 | 2021-04-28 | ELKAN ENGINEERING SERVICES & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100784 | Bulala-Paratong Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 910539.26 |  | COMPLETED | 100% |  |  | Elec2020-RI-Vigan City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region I | Vigan City | 100793 | Nagsangalan ES | CITY OF VIGAN (Capital) | 1 | 1 | UPGRADING |  | 977580.91 |  | COMPLETED | 100% |  |  | Elec2020-RI-Vigan City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 4914160.07 |  | TERMINATED | 35% |  |  | ELEC-2020-RII-BATANES-006 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 1660529.16 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-BATANES-007 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Batanes | 102313 | Diptan Elementary School | BASCO (Capital) | 0 | 1 | UPGRADING |  | 2693654.15 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-BATANES-005 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Batanes | 102328 | Sabtang Central School | SABTANG | 0 | 1 | UPGRADING |  | 1633822.52 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-BATANES-004 | [7 empty] | Implementation not yet started due to the imposition of ecq and to the typhoon kiko and contractor is still in mainland and send letter in the division for the catch up plan in implementing the prjects | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1 | 1 | UPGRADING |  | 723016.85 |  | TERMINATED | 0% |  |  | ELEC-2020-RII-CAGAYAN-001 | [7 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2 | 1 | UPGRADING |  | 615683.6 |  | TERMINATED | 0% |  |  | ELEC-2020-RII-CAGAYAN-007 | [7 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2 | 1 | UPGRADING |  | 1019916.77 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-CAGAYAN-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Cagayan | 300491 | Sto. Nino NHS | STO. NINO | 2 | 1 | UPGRADING |  | 689117.88 |  | TERMINATED | 0% |  |  | ELEC-2020-RII-CAGAYAN-009 | [7 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Cagayan | 306424 | Gadu NHS- Nangalisan Extension | SOLANA | 3 | 1 | UPGRADING |  | 1222194.87 |  | TERMINATED | 0% |  |  | ELEC-2020-RII-CAGAYAN-003 | [7 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3 | 1 | UPGRADING |  | 807603.58 |  | TERMINATED | 0% |  |  | ELEC-2020-RII-CAGAYAN-010 | [7 empty] | Contract Termination is on Process | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1080843.25 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-CAUAYAN CITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1238184.17 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-CAUAYAN CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Cauayan City | 103233 | Cauayan West CS | CITY OF CAUAYAN | 3 | 1 | UPGRADING |  | 1204885.19 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-CAUAYAN CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103354 | Alinguigan 1st Elementary School | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 100% |  |  | Elec2020-R2-City of Ilagan-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103355 | Alinguigan 2nd ES | City of Ilagan | 1 | 1 | UPGRADING |  | 698964.52 |  | COMPLETED | 100% | Jan. 2021 |  | Elec2020-R2-City of Ilagan-003 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103361 | Capellan ES | City of Ilagan | 1 | 1 | UPGRADING |  | 727197.59 |  | COMPLETED | 100% | Jan. 2021 |  | Elec2020-R2-City of Ilagan-005 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | City of Ilagan | 103382 | Tangcul-San Isidro ES | City of Ilagan | 1 | 1 | UPGRADING |  | 677944.35 |  | COMPLETED | 100% | Jan. 2021 |  | Elec2020-R2-City of Ilagan-001 |  | Nov. 12, 2019 | Nov. 19, 2019 | Dec. 09, 2019 | Jan. 07, 2020 | Sept. 21, 2020 | SMT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 300521 | Alfreda Albano National High School - Magassi, Cabagan | CABANGAN | 1 | 1 | UPGRADING |  | 828610.6 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 300520 | Delfin Albano High School-Main | CABANGAN | 1 | 1 | UPGRADING |  | 976761.31 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 300597 | San Pablo National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 262626.38 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1 | 1 | UPGRADING |  | 961515.07 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 300551 | Lanna National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 503768.82 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 300609 | Tumauini National High School | TUMAUINI | 1 | 1 | UPGRADING |  | 593838.49 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | UPGRADING |  | 921481.88 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-ISABELA-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 103331 | Echague West Central School | ECHAGUE | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 103706 | San Isidro East Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 6 | 1 | UPGRADING |  | 937346.67 |  | COMPLETED | 100% |  |  | ELEC2020-RII-ISABELA-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300619 | Bagabag NHS | BAGBAG | 0 | 1 | UPGRADING |  | 5019524.37 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-NUEVA VIZCAYA-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | UPGRADING |  | 12887267.59 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-NUEVA VIZCAYA-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Nueva Vizcaya | 300635 | LAMO NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | 0 | 1 | UPGRADING |  | 5504683.46 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-NUEVA VIZCAYA-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Quirino | 104249 | Villa Pagaduan Elementary School | Aglipay | 0 | 1 | UPGRADING |  | 535526.76 |  | COMPLETED | 100% |  |  | ELEC2020-RII-QUIRINO-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Quirino | 104266 | San Marcos ES | Cabarroguis | 0 | 1 | UPGRADING |  | 680903.14 |  | COMPLETED | 100% |  |  | ELEC2020-RII-QUIRINO-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Quirino | 104281 | Gulac ES | Diffun | 0 | 1 | UPGRADING |  | 556535.75 |  | COMPLETED | 100% |  |  | ELEC2020-RII-QUIRINO-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Santiago City | 103837 | Calaocan ES | Santiago City | 1 | 1 | UPGRADING |  | 877681.63 |  | COMPLETED | 100% |  |  | Elec 2020-R II-Santiago City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Santiago City | 306124 | Patul National High School | Santiago City | 1 | 1 | UPGRADING |  | 810365.58 |  | COMPLETED | 100% |  |  | Elec 2020-R II-Santiago City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Santiago City | 325202 | Sagana National High School | Santiago City | 1 | 1 | UPGRADING |  | 864847.86 |  | COMPLETED | 100% |  |  | Elec 2020-R II-Santiago City-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Santiago City | 103841 | Sta. Rosa ES | Santiago City | 1 | 1 | UPGRADING |  | 661763.68 |  | COMPLETED | 100% |  |  | Elec 2020-R II-Santiago City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104384 | Balzain East ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 438364.85 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-TUGUEGARAO CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 157002 | Cataggaman Nuevo ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 218174.54 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-TUGUEGARAO CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 104403 | Pallua ES | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 445321.08 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-TUGUEGARAO CITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region II | Tuguegarao City | 306402 | Tuguegarao City West High School | TUGUEGARAO CITY(Capital) | 3 | 1 | UPGRADING |  | 311749.84 |  | COMPLETED | 100% |  |  | ELEC-2020-RII-TUGUEGARAO CITY-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104409 | Baler CS | BALER (Capital) | 0 | 1 | UPGRADING |  | 2754098.39 | 2150843.33 | COMPLETED | 100% | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-001 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104410 | Calabuanan ES | BALER (Capital) | 0 | 1 | UPGRADING |  | 2747466.86 | 2703973.25 | COMPLETED | 100% | 2020-11-29 | 2020-10-20 | Elect 2020-RIII-Aurora-014 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | MARVELOUS QUEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 500729 | Carmen T. Valenzuela IS | BALER (Capital) | 0 | 1 | UPGRADING |  | 2814470.95 | 1920347.77 | COMPLETED | 100% | 2020-11-29 | 2020-10-20 | Elect 2020-RIII-Aurora-017 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | FNR BUILDERS & SONS SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104418 | Suklayin ES | BALER (Capital) | 0 | 1 | UPGRADING |  | 2747466.86 | 2718464.72 | COMPLETED | 100% | 2021-01-21 | 2020-12-17 | Elect 2020-RIII-Aurora-015 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | ADROIT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104423 | Casiguran CS | CASIGURAN | 0 | 1 | UPGRADING |  | 2810360.13 | 2802325.7 | COMPLETED | 100% | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-002 |  | MAY 18-JUNE 8, 2020 | 2020-06-08 | 2020-06-08 |  | 2020-10-30 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104435 | Dilasag CS | DILASAG | 0 | 1 | UPGRADING |  | 2810360.13 | 2790107.8 | COMPLETED | 100% | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-003 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104528 | San Luis CS | SAN LUIS | 0 | 1 | UPGRADING |  | 4449330.67 | 4443037.53 | COMPLETED | 100% | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-008 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Balanga City | 104556 | Cataning Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 3532711.81 |  | COMPLETED | 100% |  |  | Elec2020-RIII-Balanga City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Balanga City | 104567 | Tenejero Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 3209203.21 |  | COMPLETED | 100% |  |  | Elec2020-RIII-Balanga City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300697 | BONIFACIO CAMACHO NHS | ABUCAY | 1 | 1 | UPGRADING |  | 2278518.41 | 2248093.68 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-022 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | BQA CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300704 | Jose C. Payumo Jr. MHS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 4192535.54 | 4172300.65 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-010 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 306604 | Magsaysay NHS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 2311861.84 | 2291845.85 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-011 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 306603 | Sta. Lucia HS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 2327471.15 | 2317468.92 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-007 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300701 | Balsik NHS | HERMOSA | 1 | 1 | UPGRADING |  | 3066886.3 | 3056859.34 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-012 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300713 | Morong NHS | MORONG | 1 | 1 | UPGRADING |  | 4671888.25 | 4651212.69 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-014 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300714 | Nagbalayong NHS | MORONG | 1 | 1 | UPGRADING |  | 1456968.28 | 1436554.48 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-003 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 104549 | Quinawan ES | BAGAC | 2 | 1 | UPGRADING |  | 562626.67 | 0 | COMPLETED | 100% | October, 2020 |  | Elec2020-RIII-Bataan-005 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300711 | MARIVELES NHS -POB. IPAG CAMPUS | MARIVELES | 2 | 1 | UPGRADING |  | 1401805.24 | 1391799.79 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-021 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300717 | Dr. Victoria B. Roman MHS | PILAR | 2 | 1 | UPGRADING |  | 2183855.55 | 2153139.33 | COMPLETED | 100% | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-002 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | BQA CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300729 | Masagana HS | PANDI | 2 | 1 | UPGRADING |  | 6750794.78 | 6604438.41 | COMPLETED | 100% | December, 2020 |  | Elec2020-RIII-Bulacan-003 |  | June , 2020 | July , 2020 | August , 2020 | August , 2020 | August , 2020 | EIRISH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300758 | Minuyan National High School | Norzagaray | 3 | 1 | UPGRADING |  | 6186616.21 | 6145855.2798 | COMPLETED | 100% | 2021-07-20 |  | Elec2020-RIII-Bulacan-001 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | UPGRADING |  | 5695225.24 | 5655064.2023 | COMPLETED | 100% | 2021-07-20 |  | Elec2020-RIII-Bulacan-006 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300767 | Pulong Buhangin NHS | SANTA MARIA | 4 | 1 | UPGRADING |  | 6527480.37 | 6480000 | COMPLETED | 100% | 2021-07-20 |  | Elec2020-RIII-Bulacan-002 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Gapan City | 300815 | Kapalangan National High School | Gapan City | 4 | 1 | UPGRADING |  | 326950.41 | 326138.2 | COMPLETED | 100% | 2020-01-22 | 2020-01-22 | Elec2020-RIII-GapanCity-001 |  | November 13, 2019 | November 22, 2019 | December 9, 2019 | Awating Release of SubAro | Awating Release of SubAro | JOYNIELTIN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 106077 | Dau Homesite ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 1420751.96 | 1419235.4 | COMPLETED | 100% | 2020-09-16 |  | Elec2020-RIII-Mabalacat City-002 |  | 2019-11-19 | 2019-11-26 | 2019-12-10 | 2019-12-27 | 2020-08-03 | R.S. DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 106065 | Haduan Negrito ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 1024241.55 |  | COMPLETED | 100% |  |  | Elec2020-RIII-Mabalacat City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 159529 | Monicayo ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 394039.1 | 391741.94 | COMPLETED | 100% | 2020-09-16 |  | Elec2020-RIII-Mabalacat City-006 |  | 2019-11-19 | 2019-11-26 | 2019-12-10 | 2019-12-27 | 2020-08-03 | R.S. DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306803 | BUKLOD PALAD HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 758189.03 | 758190 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-018 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300787 | FORT MAGSAYSAY HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 1206863.67 | 1206864 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-019 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300828 | PALAYAN CITY NAT. HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 843725.53 | 843726 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-008 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306801 | STA. ROSA NATIONAL HIGH SCHOOL (SHS) | STA. ROSA | 3 | 1 |  |  | 827454.32 | 827455 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-022 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija |  | Mariano Llanera NHS | CABIAO | 4 | 1 |  |  | 1109828.01 | 1109829 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-025 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306823 | STA. ISABEL HIGH SCHOOL | CABIAO | 4 | 1 |  |  | 925384.82 | 925385 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-014 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300808 | GEN. TINIO NAT. HIGH SCHOOL | GEN. TINIO | 4 | 1 |  |  | 983739.35 | 983740 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-002 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306821 | DR. JOSE LAPUZ SALONGA HIGH SCHOOL | SAN ANTONIO | 4 | 1 |  |  | 897358.69 | 897359 | COMPLETED | 100% | October , 2020 |  | Elec2020-RIII-Nueva Ecija-001 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300820 | MALLORCA NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 592471.04 | 592472 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-005 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300844 | SAN ANTON NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 472896.56 | 472897 | COMPLETED | 100% | October , 2020 |  | Elec2020-RIII-Nueva Ecija-010 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306833 | SAN LEONARDO NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 841861.57 | 841862 | COMPLETED | 100% |  |  | Elec2020-RIII-Nueva Ecija-012 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 160501 | Judd Hendricks Mem. Aeta School | SAN MARCELINO | 1 | 1 | SOLAR PANEL |  | 2180222.02 | 2173368.62 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-008 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 107020 | Subic Central School | SUBIC | 1 | 1 | UPGRADING |  | 1312135.13 | 1304339.82 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-001 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106869 | Amungan Elementary School | IBA (Capital) | 2 | 1 | UPGRADING |  | 537823.72 | 536327.13 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-006 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106863 | San Agustin Elementary Schools | IBA (Capital) | 2 | 1 | UPGRADING |  | 935743.25 | 931806.6 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-003 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106881 | Sta. Barbara Elementary School | IBA (Capital) | 2 | 1 | UPGRADING |  | 655900.23 | 654063.74 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-004 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106887 | Bani Relocation Elementary School | MASINLOC | 2 | 1 | UPGRADING |  | 429579.36 | 428409.44 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-005 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106893 | Masinloc Central Elementary School | MASINLOC | 2 | 1 | UPGRADING |  | 1020681.07 | 1016189.63 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-013 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106974 | Almasin Elementary School | SANTA CRUZ | 2 | 1 | SOLAR PANEL |  | 2167130.4 |  | COMPLETED | 100% | November 2020 |  | Elec2020-RIII-Zambales-011 |  | June 2020 | July 2020 | July 2020 | August 2020 | September 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106986 | Sta. Cruz North Central School | SANTA CRUZ | 2 | 1 | UPGRADING |  | 1014004.43 | 1009608.36 | COMPLETED | 100% | November 2020 | November 2020 | Elec2020-RIII-Zambales-002 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Antipolo City | 109360 | San Ysiro ES | CITY OF ANTIPOLO | 2 | 1 |  |  | 1081542.16 | 1077802.12 | COMPLETED | 100% | 2021-02-12 | 2021-02-10 | Elec2020-RIV-A-AntipoloCity-001 | SBP-2020-02 | 2020-02-25 | 2020-03-04 | 2020-03-16 | 2020-11-27 | 2020-12-14 | Hawkstow Const. and Dev. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 107877 | Aniban CS | BACOOR | 2 | 1 |  |  | 6216862.98 | 6216862.98 | COMPLETED | 100% | 2021-01-17 |  | Elec2020-RIVA-BacoorCity-005 | [5 empty] | Septermber 17, 2020 | MRRM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 307815 | Bacoor NHS - Villa Maria Annex | BACOOR | 2 | 1 |  |  | 2053906.38 | 2033867.14 | COMPLETED | 100% | 2021-12-08 |  | Elec2020-RIVA-BacoorCity-009 | [5 empty] | 2021-08-03 | 3CA Builders | For installation of Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu ES | BACOOR | 2 | 1 |  |  | 7543254.82 | 7543254.82 | COMPLETED | 100% | 2021-01-21 |  | Elec2020-RIVA-BacoorCity-002 | [5 empty] | Septermber 28, 2020 | R.A. del Rosario Construction | For installation of Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 342600 | SHS in San Nicholas III, Bacoor City | BACOOR | 2 | 1 |  |  | 7746040.86 | 7746040.86 | COMPLETED | 100% | 2021-01-17 |  | Elec2020-RIVA-BacoorCity-011 | [5 empty] | Septermber 17, 2020 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 342211 | SHS in Calatagan | CALATAGAN | 1 | 1 |  |  | 2952925.81 | 2952925.81 | COMPLETED | 100% | 2021-05-05 |  | Elec2020-RIVA-BatangasProvince-003 |  | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2021-12-07 | 2021-01-05 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 301079 | Bauan National Agricultural and Vocational High School | BAUAN | 2 | 1 |  |  | 7219880.01 | 7219880.01 | COMPLETED | 100% | 2021-05-05 |  | Elec2020-RIVA-BatangasProvince-002 |  | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2021-12-07 | 2021-01-05 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 301105 | Itlugan National High School | ROSARIO | 4 | 1 |  |  | 3310459.67 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-BatangasProvince-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas City | 342234 | Gulod Senior High School | BATANGAS CITY (Capital) | 5 | 1 |  |  | 2112972.37 | 1711499.24 | COMPLETED | 100% | 1-28-2021 |  | Elec2020-RIVA-BatangasCity-001 |  | 11-18-2019 | 11-26-2019 | 2019-09-12 | 2020-08-01 | 9-30-2020 | Marakesh Enterprises | Installed Transformer and waiting for the Meter | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cabuyao City | 108239 | Cabuyao CES | CABUYAO | 2 | 1 |  |  | 2905020.86 | 2892836.33 | COMPLETED | 100% | 2021-10-30 |  | Elec2020-RIV-A-CabuyaoCity-001 | [6 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Calamba City | 301511 | Bubuyan Integrated School | CITY OF CALAMBA | 2 | 1 |  |  | 1245565.31 | 1238996.78 | COMPLETED | 100% | 2022-01-27 | 2022-06-27 | Elec2020-RIV-A-CalambaCity-001 | Contract No. 1 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-09-14 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 6.22 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Calamba City | 301523 | Makiling Integrated School | CITY OF CALAMBA | 2 | 1 |  |  | 2787756.08 | 2787002.38 | COMPLETED | 100% | 2021-04-16 | 2021-10-19 | Elec2020-RIV-A-CalambaCity-002 | Contract No. 4 s. 2020 | Sept. 18, 2020 | Sept. 24, 2020 | 2020-10-06 | 11/25/2020 | 12/16/2020 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301180 | Bulihan NHS | SILANG | 5 | 1 |  |  | 11812616.22 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301202 | Lumil NHS | SILANG | 5 | 1 |  |  | 8070444.69 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 | 1 |  |  | 16899985.44 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 107842 | Buck Estate ES | ALFONSO | 7 | 1 |  |  | 2240416.22 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301199 | Lucsuhin National High School | ALFONSO | 7 | 1 |  |  | 7148861.63 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 108051 | Tulay ES | MARAGONDON | 7 | 1 |  |  | 5226723.94 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301168 | Anuling NHS | MENDEZ (MENDEZ-NUÑEZ) | 7 | 1 |  |  | 7190797.63 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301207 | Naic NHS | NAIC | 7 | 1 |  |  | 13738524.52 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 108078 | San Roque ES | NAIC | 7 | 1 |  |  | 7237316.71 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-CaviteProvince-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 109632 | Ladislao Diwa ES | CAVITE CITY | 1 | 1 |  |  | 9367762.14 | 9302305.48 | COMPLETED | 100% | 2021-12-26 | 2022-02-18 | Elec2020-RIVA-CaviteCity-004 |  | 2021-05-27 | 2021-06-03 | 2021-06-15 | 2021-06-22 | 2021-06-29 | RA Yolangco | 1 suspension due to meralco | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.22 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 109631 | Sangley Point ES | CAVITE CITY | 1 | 1 |  |  | 4425012.93 | 4403923.39 | COMPLETED | 100% | 2021-04-20 | 2021-04-20 | Elec2020-RIVA-CaviteCity-002 |  | 2019-11-22 | 2019-11-27 | 2019-12-18 | 2020-01-17 | 2020-12-21 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 |  |  | 2451288.88 | 2429212.9 | COMPLETED | 100% | 2021-04-20 | 2021-04-20 | Elec2020-RIVA-CaviteCity-003 |  | 2019-11-22 | 2019-11-27 | 2019-12-18 | 2020-01-17 | 2020-12-21 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 325902 | Paliparan II National High School | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 7260407.77 | ₱5,737,906.70 | COMPLETED | 100% | 2022-03-19 |  | Elec2020-RIVA-DasmariñasCity-006 | CY2020 BEFF ELEC Batch 2 | 2021-07-19 | 2021-07-27 | 2021-08-09 | 2021-08-25 | 2021-09-09 | MRRM Trading and Construction | Installation of transformer and energization by MERALCO is completed on October 12, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107908 | Paliparan III ES | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 9172054.59 | ₱7,279,567.94 | COMPLETED | 100% | 2022-03-19 |  | Elec2020-RIVA-DasmariñasCity-002 | CY2020 BEFF ELEC Batch 2 | 2021-07-19 | 2021-07-27 | 2021-08-09 | 2021-08-25 | 2021-09-09 | MRRM Trading and Construction | Installation of transformer and energization by MERALCO is completed on October 12, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107923 | Pintong Gubat Elementary School | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 4691477.87 | ₱11,153,105.62 | COMPLETED | 100% | 2021-12-16 |  | Elec2020-RIVA-DasmariñasCity-003 | CY2020 BEFF ELEC C1 | 2019-11-26 | 2019-12-06 | 2019-12-16 | 2020-01-13 | 2020-09-01 | R.A Del Rosario Construction | With Issued Suspension of Works due to the delay in the Installation of Transformer and Energization by MERALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107920 | Sta. Cruz ES (Dasmariñas BBES E) | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 11159076.6 | ₱4,671,893.24 | COMPLETED | 100% | 2021-12-16 |  | Elec2020-RIVA-DasmariñasCity-005 | CY2020 BEFF ELEC C1 | 2019-11-26 | 2019-12-06 | 2019-12-16 | 2020-01-13 | 2020-09-01 | R.A Del Rosario Construction | With Issued Suspension of Works due to the delay in the Installation of Transformer and Energization by MERALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | General Trias City | 107959 | Diego Mojica MS | CITY OF GENERAL TRIAS | 6 | 1 |  |  | 7340176.19 | 7290176.19 | COMPLETED | 100% | 2021-01-22 | 2021-01-22 | Elec2020-RIVA-GeneralTriasCity-001 | [6 empty] | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3 | 1 |  |  | 6162276.31 | 6121913.44 | COMPLETED | 100% | March 30, 2021 | "Dec. 19, 2022 | Elec2020-RIVA-ImusCity-008 | ITB - 2020 - 03 - 003 |  |  |  |  | Nov. 19, 2020 | 3CA Builders | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107972 | Buhay na Tubig Elementary School | IMUS | 3 | 1 |  |  | 5466782.73 | 5423748.42 | COMPLETED | 100% | March 30, 2021 | December 23, 2022 | Elec2020-RIVA-ImusCity-009 | ITB - 2020 - 03 - 002 | [6 empty] | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107984 | E. Villanueva ES | IMUS | 3 | 1 |  |  | 2877415.7 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-ImusCity-002 | [6 empty] | R.A. del Rosario Construction | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino ES | IMUS | 3 | 1 |  |  | 15347805.6 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-ImusCity-003 | [6 empty] | R.A. del Rosario Construction | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107979 | Tanzang Luma ES | IMUS | 3 | 1 |  |  | 5453366.85 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-ImusCity-006 | [7 empty] | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 |  |  | 1423668.82 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-Laguna-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301237 | Calumpang NHS - Lowland NHS Annex | NAGCARLAN | 3 | 1 |  |  | 2097625.91 |  | ONGOING | 90% | For installation of Transformer |  | Elec2020-RIV-A-Laguna-009 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301258 | Plaridel NHS | NAGCARLAN | 3 | 1 |  |  | 6883253.96 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-Laguna-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 | 1 |  |  | 6454363.01 |  | ONGOING | 90% | For installation of Transformer |  | Elec2020-RIV-A-Laguna-015 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301228 | Banca-Banca NHS - Integrated Senior High School | VICTORIA | 3 | 1 |  |  | 3703337.62 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-Laguna-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301250 | Masapang NHS | VICTORIA | 3 | 1 |  |  | 2799361.19 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-Laguna-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 307906 | Gov. Felicisimo T. San Luis Memorial National High School | SANTA CRUZ (Capital) | 4 | 1 |  |  | 6678071.91 |  | ONGOING | 90% | For installation of Transformer |  | Elec2020-RIV-A-Laguna-001 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 342362 | Santa Cruz SHS | SANTA CRUZ (Capital) | 4 | 1 |  |  | 2239194.37 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-Laguna-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301489 | Bulacnin NHS | LIPA CITY | 4 | 1 |  |  | 6283440.82 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109673 | Calamias ES | LIPA CITY | 4 | 1 |  |  | 2211352.69 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109663 | Lumbang ES | LIPA CITY | 4 | 1 |  |  | 2607629.33 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109693 | Padre Valerio Malabanan MS | LIPA CITY | 4 | 1 |  |  | 5596380.26 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109650 | San Celestino ES | LIPA CITY | 4 | 1 |  |  | 1681710.72 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School ( | LIPA CITY | 4 | 1 |  |  | 6180929.04 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109704 | Tangway ES | LIPA CITY | 4 | 1 |  |  | 2967880.83 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 |  |  | 2890060.15 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301495 | Lumbang NHS | LIPA CITY | 6 | 1 |  |  | 2249980.53 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301498 | Rizal NHS | LIPA CITY | 6 | 1 |  |  | 2015728.17 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109652 | San Isidro ES | LIPA CITY | 6 | 1 |  |  | 2005355.46 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109700 | San Salvador Loob ES | LIPA CITY | 6 | 1 |  |  | 2094338.39 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109654 | Sto. Niño ES | LIPA CITY | 6 | 1 |  |  | 2382897.67 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LipaCity-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109718 | Elvira Razon Aranilla ES | LUCENA CITY (Capital) | 2 | 1 |  |  | 5095322.69 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LucenaCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109717 | Gulang-gulang Elementary School | LUCENA CITY (Capital) | 2 | 1 |  |  | 5081068.66 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LucenaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 167502 | Isabang ES-Bocohan Annex | LUCENA CITY (Capital) | 2 | 1 |  |  | 1315373.14 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LucenaCity-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 |  |  | 15608257.02 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LucenaCity-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 | 1 |  |  | 10036454.29 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-LucenaCity-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 | 1 |  |  | 10684093.83 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 | 1 |  |  | 6929037.69 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308004 | Pagbilao NHS | PAGBILAO | 1 | 1 |  |  | 7361096.25 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 | 1 |  |  | 5811249.04 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301407 | Talipan NHS | PAGBILAO | 1 | 1 |  |  | 8389147.86 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308020 | GOV. ANACLETO C. ALCALA NATIONAL HIGH SCHOOL | SARIAYA | 2 | 1 |  |  | 4778606.09 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 |  |  | 4215205.75 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-039 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301310 | Catanauan NHS | CATANAUAN | 3 | 1 |  |  | 4181508.16 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308001 | Matandang Sabang NHS | CATANAUAN | 3 | 1 |  |  | 6233239.58 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-043 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301312 | Tagbacan NHS | CATANAUAN | 3 | 1 |  |  | 5028870.71 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-045 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301393 | San Isidro NHS, General Luna | GENERAL LUNA | 3 | 1 |  |  | 6053807.56 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-046 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 |  |  | 15652496.42 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 |  |  | 5045900.95 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301330 | Pakiing NHS | MULANAY | 3 | 1 |  |  | 3872684.15 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-048 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301280 | Abuyon NHS | SAN NARCISO | 3 | 1 |  |  | 5482964.64 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-041 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 |  |  | 7593809.65 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301357 | Malusak National High School | ATIMONAN | 4 | 1 |  |  | 4546052.94 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301402 | San Roque-Ilaya NHS, Calauag | CALAUAG | 4 | 1 |  |  | 4733950.85 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301404 | Sto. Domingo NHS | CALAUAG | 4 | 1 |  |  | 7074714.93 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301320 | Dungawan NHS | GUINAYANGAN | 4 | 1 |  |  | 5712244.35 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301331 | Gumaca IS | GUMACA | 4 | 1 |  |  | 6200927.2 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-034 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301372 | Panikihan NHS | GUMACA | 4 | 1 |  |  | 6258231.59 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-035 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301346 | Cogorin Ibaba NHS | LOPEZ | 4 | 1 |  |  | 4877395.52 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301316 | Concepcion NHS | PLARIDEL | 4 | 1 |  |  | 6868584.24 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301287 | Bagong Silang NHS | TAGKAWAYAN | 4 | 1 |  |  | 5684812.41 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308038 | Cabibihan National High School | TAGKAWAYAN | 4 | 1 |  |  | 4474396.04 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301338 | Kinatakutan NHS | TAGKAWAYAN | 4 | 1 |  |  | 4672613.34 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308002 | Mapulot National High School | TAGKAWAYAN | 4 | 1 |  |  | 4789843.8 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 |  |  | 5702333.09 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-Quezon-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Rizal | 301463 | Talim Point NHS | BINANGONAN | 1 | 1 |  |  | 3474859.92 | 3457278.19 | COMPLETED | 100% |  |  | Elec2020-RIV-A-Rizal-001 | INFRA-2019-006 | November 20, 2019 to December 9, 2019 | November 28, 2019 | December 10, 2019 | December 12, 2019 | October 21,2020 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109777 | Bagong Bayan Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 2337922.19 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo city-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109768 | Del Remedios Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 4512466.26 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo city-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109795 | San Antonio I ES | CITY OF SAN PABLO | 3 | 1 |  |  | 891949.45 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109797 | San Gregorio Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 885245.08 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109799 | San Isidro Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 1031759.94 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109772 | San Mateo Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 1253145.32 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 342575 | San Pablo Stand-Alone Senior High School - San Juan | CITY OF SAN PABLO | 3 | 1 |  |  | 3151848.48 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 308601 | Santissimo Rosario National High School | CITY OF SAN PABLO | 3 | 1 |  |  | 3941531.53 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109775 | Sta.Filomina Integrated National High School | CITY OF SAN PABLO | 3 | 1 |  |  | 2596779.99 |  | COMPLETED | 100% |  |  | Elec2020-RIV-A-San Pablo City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 321602 | BALELE INTEGRATED HIGH SCHOOL | TANAUAN CITY | 3 | 1 |  |  | 1586760.2 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-TanauanCity-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301113 | LUYOS NHS | TANAUAN CITY | 3 | 1 |  |  | 2703042.04 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-TanauanCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301133 | PANTAY NATIONAL HIGH SCHOOL | TANAUAN CITY | 3 | 1 |  |  | 2925876.19 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-TanauanCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301154 | TANAUAN SCHOOL OF FISHERIES | TANAUAN CITY | 3 | 1 |  |  | 5333861.6 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-TanauanCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS | 1 | 1 |  |  | 19660229.99 |  | COMPLETED | 100% |  |  | Elec2020-RIVA-TayabasCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Calapan City | 301805 | Managpi National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 571845.06 |  | COMPLETED | 100% |  |  | Elec2020-RIV-B-Calapan City -001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | UPGRADING |  | 1145148.62 |  | COMPLETED | 100% |  |  | Elec2020-RIV-B-Calapan City -002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 301531 | BANGBANG NATIONAL HIGH SCHOOL | GASAN | 0 | 1 |  |  | 967324.13 |  | COMPLETED | 100% |  |  | ELEC2020-RIV B - Marinduque - 001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 301563 | TAGUM NATIONAL HIGH SCHOOL | STA.CRUZ | 0 | 1 |  |  | 829485.25 |  | COMPLETED | 100% |  |  | ELEC2020-RIV B - Marinduque - 004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Marinduque | 110026 | MARLANGGA ELEMENTARY SCHOOL | TORRIJOS | 0 | 1 |  |  | 718943.51 |  | COMPLETED | 100% |  |  | ELEC2020-RIV B - Marinduque - 005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110656 | CALSAPA ELEMENTARY SCHOOL | SAN TEODORO | 1 | 1 |  |  | 929677.83 | 911843.35 | COMPLETED | 100% | Feb. 15, 2021 | Jan. 20, 2021 | ELEC2020-RIV B - Oriental Mindoro - 008 | 017-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | CMSEL Const. & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 301619 | Bayuin NHS | SOCORRO | 1 | 1 |  |  | 2713634.88 | 2705358.6 | COMPLETED | 100% | Feb. 15, 2021 | Feb. 15, 2021 | ELEC2020-RIV B - Oriental Mindoro - 0014 | 018-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | CMSEL Const. & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110402 | FIDEL REYES MEMORIAL ELEMENTARY SCHOOL | BONGABONG | 2 | 1 |  |  | 1175848.45 | 1145817.09 | COMPLETED | 100% | Feb. 15, 2021 | Feb. 08, 2021 | ELEC2020-RIV B - Oriental Mindoro - 006 | 019-2020 | Nov. 19, 2019 | Nov. 27, 2019 | Dec. 12, 2019 | March 4, 2020 | November 09, 2020 | ETVR Trading & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110449 | MALUSAK ELEMENTARY SCHOOL | GLORIA | 2 | 1 | UPGRADING |  | 1102581.15 | 1094932.31 | COMPLETED | 100% | Dec. 15, 2021 | Dec. 13, 2021 | ELEC2020-RIV B - Oriental Mindoro - 011 | 018-2021 | July 06, 2021 | July 14, 2021 | July 27, 2021 | Aug. 11, 2021 | Sept. 20, 2021 | TCC Powerserve Trading and Eng'g. Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Oriental Mindoro | 110630 | DANGAY ELEMENTARY SCHOOL | ROXAS | 2 | 1 | UPGRADING |  | 1550236.69 | 1541975.2 | COMPLETED | 100% | Dec. 15, 2021 | Dec. 13, 2021 | ELEC2020-RIV B - Oriental Mindoro - 007 | 017-2021 | July 06, 2021 | July 14, 2021 | July 27, 2021 | Aug. 11, 2021 | Sept. 20, 2021 | TCC Powerserve Trading and Eng'g. Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110964 | CAGAYANCILLO CS | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 2569207.37 |  | COMPLETED | 100% |  |  | Elec2020-RIVB-PALAWAN-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110967 | MAGSAYSAY ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1195876.16 |  | COMPLETED | 100% |  |  | Elec2020-RIVB-PALAWAN-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110968 | MAMPIO ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1008565.24 |  | COMPLETED | 100% |  |  | Elec2020-RIVB-PALAWAN-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110970 | STA. CRUZ ES | CAGAYANCILLO | 1 | 1 | UPGRADING |  | 1274852.97 |  | COMPLETED | 100% |  |  | Elec2020-RIVB-PALAWAN-032 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Palawan | 110940 | LAMUD ELEMENTARY SCHOOL | CULION | 1 | 1 | UPGRADING |  | 856352.76 |  | COMPLETED | 100% |  |  | Elec2020-RIVB-PALAWAN-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 171502 | Talaudyong Elementary School | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  |  | 1777613.88 |  | COMPLETED | 100% |  |  | ELEC2020-RIV-B-PUERTO PRINCESA -003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 111514 | Kandes Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 |  |  | 653089.58 |  | COMPLETED | 100% | January 3, 2021 |  | ELEC2020-RIV-B-PUERTO PRINCESA -001 |  | Nov. 26, 2019 | Dec. 3, 2019 | Dec. 16, 2019 | January 31, 2020 | Sept. 28, 2020 | Ian Jason Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Puerto Princesa City | 111492 | Sicsican Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 |  |  | 1801632.05 |  | COMPLETED | 100% | January 3, 2021 |  | ELEC2020-RIV-B-PUERTO PRINCESA -002 |  | Nov. 26, 2019 | Dec. 3, 2019 | Dec. 16, 2019 | January 31, 2020 | Sept. 28, 2020 | Ian Jason Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Romblon | 301767 | Macario Molina NHS | ROMBLON (Capital) | 0 | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools |  | 1795333.47 |  | COMPLETED | 100% |  |  | Elec2020-RIV-B-ROMBLON-006 | INF-EUP-2021-07 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2021-12-10 | 2022-01-28 | TCC POWER SERVE TRADING AND ENGINEERING SERVICES | Ongoing fabrication of steel posts and its plate, fabrication of steel bars for concrete pedestal and preparation of formworks for concrete pedestal. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2020 | Region IV-B | Romblon | 301770 | Romblon NHS, Romblon | ROMBLON (Capital) | 0 | 1 |  |  | 4253061.64 |  | COMPLETED | 100% |  |  | Elec2020-RIV-B-ROMBLON-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 303879 | Dakak NHS | Dapitan City | 1 | 1 | UPGRADING |  | 2428476.92 | 2421854.57 | COMPLETED | 100% | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-015 | 2020-09-002 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 125938 | Dapitan City Central School | Dapitan City | 1 | 1 | UPGRADING |  | 2401488.84 | 2397806.37 | COMPLETED | 100% | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-013 | 2020-09-001 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 125949 | Potungan CS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 555088.13 | 538357.75 | COMPLETED | 100% | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-001 | 2020-07-017 | 2020-08-04 | 2020-08-11 | 2020-10-08 | 2021-07-06 | 2021-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 303884 | Sulangon NHS | Dapitan City | 1 | 1 | UPGRADING |  | 1055605.94 | 1047599.32 | COMPLETED | 100% | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-016 | 2020-09-001 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dipolog | 125972 | GALAS ES | DIPOLOG CITY (Capital) | 2 | 1 | CONNECTION TO GRID |  | 336785.55 | 334127.34 | COMPLETED | 100% | 2020-11-01 | 2020-11-01 | Elec2020-RIX-Dipolog City-001 | DepEd-20-IX-Dip-Electrification-Galas ES | 2020-02-12 | 2020-02-20 | 2020-03-04 | 2020-09-16 | 2020-10-01 | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dipolog | 125973 | MAGSAYSAY ES | DIPOLOG CITY (Capital) | 2 | 1 | CONNECTION TO GRID |  | 352333.99 | 351065.88 | COMPLETED | 100% | 2020-11-01 | 2020-11-01 | Elec2020-RIX-Dipolog City-003 | DepEd-20-IX-Dip-Electrification-Magsaysay ES | 2020-02-12 | 2020-02-20 | 2020-03-04 | 2020-09-16 | 2020-10-01 | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 314602 | Calvario Peak National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1771369.36 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126030 | Campo Barn Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1614846.64 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 303899 | Kumalarang NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1695111.32 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126011 | Latuan Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1580611.32 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126024 | Marang Marang ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1541507.12 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 303898 | Tandung Ahas NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1188377.64 |  | COMPLETED | 100% |  |  | Elec2020-R IX-Isabela City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126062 | Dominador Yocogo Sr. ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 949924.61 | 947680.75 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-003 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126089 | Kahayagan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 875691.26 | 874881.35 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-017 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126064 | Lenienza ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1152429.2 | 1149205.1 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-006 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 314704 | Pagadian Science HS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1910916.87 | 1910199.19 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-011 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 314703 | Tulawas IS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1795381.01 | 1794735.05 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-015 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 303913 | ZSSAT | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2076882.04 | 2070159.48 | COMPLETED | 100% | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-016 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 303913 | ZSSAT | PAGADIAN CITY (Capital) | 1 |  |  |  | 1758285.76 | 1757058.54 | COMPLETED | 100% | 2021-08-27 | 2021-08-27 | Elec2020-RIX-Pagadian City-009 | DepEd-Elec-2020-IX-PAG-3 | 2020-10-01 | 2020-10-08 | 2020-10-20 | 2020-11-11 | 2021-06-09 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1600000 | 1597362.46 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-005 | ZC-ELEC-2020-02 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303924 | Ramon Enriquez HS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1400000 | 1397175.24 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-016 | ZC-ELEC-2020-04 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303943 | Regional Science HS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1200000 | 1197298.55 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-023 | ZC-ELEC-2020-06 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126104 | Sinunuc ES | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 2200000 | 2197363.75 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-002 | ZC-ELEC-2020-01 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126220 | Sta. Maria CS SPED Center | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1600000 | 1597972.47 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-010 | ZC-ELEC-2020-05 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 314807 | Tulungatung NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1200000 | 1197793.24 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-025 | ZC-ELEC-2020-03 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303917 | Bolong NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1796813.9 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-015 | ZC-ELEC-2020-07 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 314802 | Lubigan NHS, Curuan Annex | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1200000 | 1197298.55 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-024 | ZC-ELEC-2020-08 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303930 | Sangali NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1650685.58 | COMPLETED | 100% | 2020-11-24 | 2020-11-30 | Elec2020-R IX-Zamboanga City-017 | ZC-ELEC-2019 SAVING | 2020-07-07 | 2020-07-14 | 2020-07-28 | 2020-08-18 | Sept 10,2020 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126229 | Tetuan Central School | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1794918.54 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-014 | ZC-ELEC-2020-09 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303940 | Zamboanga City HS, Main | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 3700000 | 3693624.79 | COMPLETED | 100% | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-021 | ZC-ELEC-2020-10 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314105 | Polanco NHS Ext. - ISIS | POLANCO | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-001 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303725 | SAN PEDRO NHS | POLANCO | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-002 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303726 | SEBACA NHS | RIZAL | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-003 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303723 | San Isidro NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-006 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303724 | San Jose NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-007 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303694 | KANIM NHS | SIBUTAD | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-004 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303695 | SAWANG NHS | SIBUTAD | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-005 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303709 | MANAWAN NHS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-014 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303698 | DON TEOTIMO Z. OCHOTORENA NHS | KATIPUNAN | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-009 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 124381 | Malugas ES | KATIPUNAN | 2 | 1 | UPGRADING |  | 947000 | 851148 | COMPLETED | 100% | 2021-03-17 | 2021-03-05 | Elec2020-R IX-Zamboanga Del Sur-001 | ELEC-2020-BEFF-RIX ZDN | 2019-11-27 | 2020-02-28 | 2020-03-12 | 2020-03-16 | Sept. 16, 2020 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314104 | Matam NHS | KATIPUNAN | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-008 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314115 | GODOD NHS- SIANAN | GODOD | 3 | 1 | UPGRADING |  | 755153.2 | 753773 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-025 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314107 | Cawit-Cawit National High School | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-037 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303708 | Malayal NHS | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-038 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303735 | Sibuco NHS Annex - Lunday | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-036 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 | 1 | UPGRADING |  | 781403.2 | 777806 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-035 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303743 | Dacon National High School (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | UPGRADING |  | 770903.2 | 766149 | COMPLETED | 100% | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-033 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1 | 1 | UPGRADING |  | 3012000 | 2625502.7 | COMPLETED | 100% | 2021-04-27 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-003 | ZDS-20-E-02 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | UPGRADING |  | 2612000 | 2244500.05 | COMPLETED | 100% | 2021-04-27 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-004 | ZDS-20-E-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | JJFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 314217 | Bibilik NHS | DUMALINAO | 2 | 1 | UPGRADING |  | 1750000 | 1502483.79 | COMPLETED | 100% | 2021-03-28 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-005 | ZDS-20-E-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | JJFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125510 | Alicia CES | ALICIA | 1 | 1 | UPGRADING |  | 410723.03 | 410563.18 | COMPLETED | 100% | Sept. 27, 2021 | - | Elec2020-R IX-Zamboanga Sibugay-001 | ZSY-2020Eadd-01 | 2021-04-20 | 2021-04-28 | 2021-05-10 | 2021-06-23 | 2021-06-29 | CPAN Engineering and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% | 5.24 | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125566 | Diplahan CES | Diplahan | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-004 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125673 | Mabuhay CES | Mabuhay | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-006 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125743 | Olutanga CES | OLUTANGA | 1 | 1 | UPGRADING |  | 435923.03 | 376500.98 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-009 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125774 | Payao CES | PAYAO | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-010 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125617 | Ipil CES | IPIL | 2 | 1 | UPGRADING |  | 443459.47 | 384984.19 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-012 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 196519 | Ipil SPED School | IPIL | 2 | 1 | UPGRADING |  | 409673.03 | 356314.16 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-013 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125804 | Surabay CES | ROSELLER LIM | 2 | 1 | UPGRADING |  | 445787.53 | 387074.19 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-018 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 303864 | Siay NHS | SIAY | 2 | 1 | UPGRADING |  | 1063897.79 | 913527.99 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-024 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125882 | Titay CES | TITAY | 2 | 1 | UPGRADING |  | 447887.53 | 387074.15 | COMPLETED | 100% | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-021 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1 | 1 |  |  | 5739686.34 |  | COMPLETED | 100% |  |  | Elec2020-RV-Albay-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1 | 1 |  |  | 4767789.44 |  | COMPLETED | 100% |  |  | Elec2020-RV-Albay-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 309518 | Kilicao High School | DARAGA | 2 | 1 |  |  | 1994809.2 |  | COMPLETED | 100% |  |  | Elec2020-RV-Albay-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Albay | 500155 | San Agustin Integrated School | LIBON | 3 | 1 |  |  | 2647671.69 |  | COMPLETED | 100% |  |  | Elec2020-RV-Albay-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 112110 | CAPALONGA CS | CAPALONGA | 1 | 1 | UPGRADING |  | 2122922.96 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -003 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 | 1 | UPGRADING |  | 1478435.03 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -012 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309619 | GAWAD KALINGA HS | JOSE PANGANIBAN | 1 | 1 | UPGRADING |  | 1501403.36 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -007 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 112163 | LARAP ES | JOSE PANGANIBAN | 1 | 1 | UPGRADING |  | 1855583.04 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -010 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1 | 1 | UPGRADING |  | 2241623.93 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -002 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1 | 1 |  |  | 2822880.47 | RIDERSCORNER CONST AND GEN. MDSE. | COMPLETED | 100% |  |  | ELEC 2020-RV-CAMARINES NORTE -005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 309611 | Dominador Narido High School | BASUD | 2 | 1 | UPGRADING |  | 1416336.07 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -004 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Norte | 301915 | SAN FELIPE NHS | BASUD | 2 | 1 | UPGRADING |  | 2049490.27 | PHILIANS ENGINEERING AND CONSTRUCTION SUPPLY | COMPLETED | 100% | 2021-03-18 | 2021-03-18 | ELEC 2020-RV-CAMARINES NORTE -013 |  |  | 2019-11-26 |  | 2019-12-16 | 2020-02-28 | 44098 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | Cabusao | 1 | 1 | CONNECTION TO GRID |  | 2911700.15 | 2910674.68 | COMPLETED | 100% | March 31, 2021 |  | Elec2020-RV-Camarines Sur-015 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301966 | Del Gallego National High School | Del Gallego | 1 | 1 | CONNECTION TO GRID |  | 1592231.34 | 1591647.37 | COMPLETED | 100% | March 31, 2021 |  | Elec2020-RV-Camarines Sur-007 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur |  | Del Gallego National High School Annex | Del Gallego | 1 | 1 | CONNECTION TO GRID |  | 1957347.8 | 1955677.95 | COMPLETED | 100% | March 31, 2021 |  | Elec2020-RV-Camarines Sur-008 | 2020-09-023 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | December 1, 2020 | PHILIANS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302000 | Minalabac NHS | Minalabac | 2 | 1 | CONNECTION TO GRID |  | 3604535.82 | 3602124.45 | COMPLETED | 100% | March 20, 2021 |  | Elec2020-RV-Camarines Sur-016 | 2020-09-024 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | POWER COMPACT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302066 | Villamayor HS | Minalabac | 2 | 1 | CONNECTION TO GRID |  | 2503436.38 | 2501044.46 | COMPLETED | 100% | March 20, 2021 |  | Elec2020-RV-Camarines Sur-020 | 2020-09-024 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | POWER COMPACT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301952 | Calabanga NHS | Calabanga | 3 | 1 | CONNECTION TO GRID |  | 4114962.51 | 4110870 | COMPLETED | 100% | March 24, 2021 |  | Elec2020-RV-Camarines Sur-032 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301953 | Quipayo National High School | Calabanga | 3 | 1 | CONNECTION TO GRID |  | 2447903.07 | 2445470 | COMPLETED | 100% | March 24, 2021 |  | Elec2020-RV-Camarines Sur-028 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301995 | Mangayawan High School | Canaman | 3 | 1 | CONNECTION TO GRID |  | 1686327.33 | 1684650 | COMPLETED | 100% | March 24, 2021 |  | Elec2020-RV-Camarines Sur-030 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302049 | Sta. Cruz National High School | Canaman | 3 | 1 | CONNECTION TO GRID |  | 1809880.88 | 1808080 | COMPLETED | 100% | March 24, 2021 |  | Elec2020-RV-Camarines Sur-027 | 2020-09-025 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 24, 2020 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112621 | Goa Central School | Goa | 4 | 1 | CONNECTION TO GRID |  | 9179224.88 | 9163937.96 | COMPLETED | 100% | March 20, 2021 |  | Elec2020-RV-Camarines Sur-021 | 2020-09-026 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | 3CA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112989 | Sagñay CS | SAGÑAY | 4 | 1 |  |  | 6179932.82 |  | COMPLETED | 100% |  |  | Elec2020-RV-Camarines Sur-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 113028 | San Jose CS | San Jose | 4 | 1 |  |  | 4907678.18 | 4889355.15 | COMPLETED | 100% | March 20, 2021 |  | Elec2020-RV-Camarines Sur-023 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | November 27, 2020 | November 20, 2020 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 113108 | Tigaon CS | TIGAON | 4 | 1 |  |  | 5426681.526 |  | COMPLETED | 100% |  |  | Elec2020-RV-Camarines Sur-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112318 | Antipolo Elementary School | BAAO | 5 | 1 |  |  | 506762.51 |  | COMPLETED | 100% |  |  | Elec2020-RV-Camarines Sur-034 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 |  |  | 1656333.25 |  | COMPLETED | 100% |  |  | Elec2020-RV-Camarines Sur-035 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur |  | Caranday NHS (ANNEX) | Baao | 5 | 1 |  |  | 624105 |  | COMPLETED | 100% |  |  | Elec2020-RV-Camarines Sur-036 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112344 | Balatan CS | Balatan | 5 | 1 |  |  | 2855369.48 | 2831391.45 | COMPLETED | 100% | 2021-03-20 |  | Elec2020-RV-Camarines Sur-002 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 302044 | Bato National High School | Bato | 5 | 1 |  |  | 2833256.3 | 2812684.51 | COMPLETED | 100% | 2021-03-20 |  | Elec2020-RV-Camarines Sur-004 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | Buhi | 5 | 1 |  |  | 1290531.45 | 1263196.55 | COMPLETED | 100% | 2021-03-20 |  | Elec2020-RV-Camarines Sur-033 | 2020-09-027 | Nov. 19, 2019 | Nov. 26, 2019 | Dec. 9, 2019 | 2020-11-27 | 2020-11-20 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | Panganiban | 0 | 1 |  |  | 1267004.79 |  | COMPLETED | 100% |  |  | Elec2020-RV-Catanduanes-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Catanduanes | 302071 | Antipolo NHS | Virac | 0 | 1 |  |  | 1211985.1 |  | COMPLETED | 100% |  |  | Elec2020-RV-Catanduanes-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Iriga City | 302254 | San Antonio NHS | Iriga City | 5 | 1 |  |  | 3028350.73 |  | COMPLETED | 100% |  |  | Elec2020-RV-Iriga City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 310201 | Arimbay HS | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 898841.35 |  | COMPLETED | 100% |  |  | Electrification2020-RV-Legazpi City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114466 | Bagumbayan CS | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 1161596.4 |  | COMPLETED | 100% |  |  | Electrification2020-RV-Legazpi City-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114477 | Cabangan ES | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 858841.35 |  | COMPLETED | 100% |  |  | Electrification2020-RV-Legazpi City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 302260 | Cabangan High School | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 898841.35 |  | COMPLETED | 100% |  |  | Electrification2020-RV-Legazpi City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Legazpi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 |  |  | 858841.37 |  | COMPLETED | 100% |  |  | Electrification2020-RV-Legazpi City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301807 | Amtic HS | CITY OF LIGAO | 3 | 1 |  |  | 2155034.09 | 2141863.49 | COMPLETED | 100% | 2021-02-24 |  | Elec2020-RV-Ligao City-005 | 2020-INFRA-07 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301811 | Barayong HS | CITY OF LIGAO | 3 | 1 |  |  | 2158793.3 | 2147561.84 | COMPLETED | 100% | 2021-02-24 |  | Elec2020-RV-Ligao City-003 | 2020-INFRA-08 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 321701 | Ligao City National Technical Vocational HS | CITY OF LIGAO | 3 | 1 |  |  | 4369183.28 | 4343254.57 | COMPLETED | 100% | 2021-03-13 |  | Elec2020-RV-Ligao City-009 | 2020-INFRA-09 | 2020-02-12 | 2020-02-17 | 2020-03-03 | 2020-11-16 | 2020-12-07 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 321702 | Maonon HS | CITY OF LIGAO | 3 | 1 |  |  | 1426727.79 | 1414844.41 | COMPLETED | 100% | 2021-02-24 |  | Elec2020-RV-Ligao City-002 | 2020-INFRA-06 | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-10-12 | 2020-11-20 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 |  |  | 6307451.22 | 6279746.66 | COMPLETED | 100% | 2021-03-13 |  | Elec2020-RV-Ligao City-010 | 2020-INFRA-09 | 2020-02-12 | 2020-02-17 | 2020-03-03 | 2020-11-16 | 2020-12-07 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 302111 | Aroroy NHS | AROROY | 2 | 1 |  |  | 3323805.99 |  | COMPLETED | 100% |  |  | Elec2020-RV-Masbate-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 309941 | Cristeta Bagano MHS | MOBO | 2 | 1 |  |  | 2061671.6 |  | COMPLETED | 100% |  |  | Elec2020-RV-Masbate-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate | 302112 | Badiang National High School | CATAINGAN | 3 | 1 |  |  | 2928720.02 |  | REVERTED | 0% |  |  | Elec2020-RV-Masbate-001 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2020 | Region V | Masbate City | 113665 | Amancio Aguilar ES | Masbate City | 2 | 1 |  |  | 1390755.98 |  | COMPLETED | 100% |  |  | Electrification 2020-RV-Masbate City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate City | 321801 | BOLO NATIONAL HIGH SCHOOL | Masbate City | 2 | 1 |  |  | 1486953.42 |  | COMPLETED | 100% |  |  | Electrification 2020-RV-Masbate City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Masbate City | 113702 | NURSERY ELEMENTARY SCHOOL | Masbate City | 2 | 1 |  |  | 1314418.1 |  | COMPLETED | 100% |  |  | Electrification 2020-RV-Masbate City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 |  |  | 2265761.12 |  | TERMINATED | 35% |  |  | Elec2020-RV-Naga City-002 | [7 empty] | For termination | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 35% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region V | Naga City | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 |  |  | 2002874.73 |  | COMPLETED | 100% |  |  | Elec2020-RV-Naga City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Naga City | 310301 | Tinago National High School | NAGA CITY | 3 | 1 |  |  | 1876681.88 |  | COMPLETED | 100% |  |  | Elec2020-RV-Naga City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302198 | Castilla NHS | Castilla | 1 | 1 |  |  | 1901616.96 | 1890066.04 | COMPLETED | 100% | 2021-01-04 |  | Elec2020-RV-Sorsogon-003 | 19-11-008-01 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302204 | Donsol National Comprehensive HS | Donsol | 1 | 1 |  |  | 3637178.2 | 3625248.47 | COMPLETED | 100% | 2021-01-11 |  | Elec2020-RV-Sorsogon-002 | 19-11-008-01 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302215 | Irosin North NHS | Irosin | 2 | 1 |  |  | 1754680.59 | 1743618.53 | COMPLETED | 100% | 2021-01-04 |  | Elec2020-RV-Sorsogon-007 | 19-11-008-02 |  |  |  |  | 2020-10-02 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon | 302232 | Prieto Diaz National High School | Prieto Diaz | 2 | 1 |  |  | 2955787.8 | 1964635.34 | COMPLETED | 100% | 2025-02-10 | 2025-02-10 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-11-13 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon City | 114568 | BUENAVISTA ELEMENTARY SCHOOL | SORSOGON WEST | 1 | 1 |  |  | 3266250.7 |  | COMPLETED | 100% |  |  | Elec2020-RV-Sorsogon City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Sorsogon City | 310402 | PANLAYAAN TECHNICAL VOCATIONAL SCHOOL | SORSOGON WEST | 1 | 1 |  |  | 5394521.59 |  | COMPLETED | 100% |  |  | Elec2020-RV-Sorsogon City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Tabaco City | 302281 | Bantayan High School | Tabaco City | 1 | 1 |  |  | 2182084.78 | 1818000 | COMPLETED | 100% | 2024-12-23 | 2024-12-23 | Elec2020-RV-Tabaco City-002 |  |  |  | 13/11/2019 |  | 16/12/2020 | RANP Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region V | Tabaco City | 302285 | Tabaco National High School | Tabaco City | 1 | 1 |  |  | 1818217.28 | 2182000 | COMPLETED | 100% | 2022-12-23 | 2022-12-23 | Elec2020-RV-Tabaco City-001 |  |  |  | 13/11/2019 |  | 16/12/2020 | RANP Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302287 | Justicia Morales-Young National High School | ALTAVAS | 0 | 1 | UPGRADING |  | 2225930.09 | 2222722.79 | COMPLETED | 100% | 2021-01-20 | 2020-11-23 | ELEC2020-RVI-AKLAN-015 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 310601 | LUPO NATIONAL HIGH SCHOOL | ALTAVAS | 0 | 1 | UPGRADING |  | 1799319.29 | 1799035.72 | COMPLETED | 100% | 2021-01-20 | 2020-11-23 | ELEC2020-RVI-AKLAN-020 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302307 | Father Julian C. Rago Memorial NHS | BALETE | 0 | 1 | UPGRADING |  | 2153200.79 | 2150859.95 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-042 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114670 | Mangga Primary School | BANGA | 0 | 1 | SOLAR PANEL |  | 899472.82 | 898607.75 | COMPLETED | 100% | 2021-01-20 | 2021-11-10 | ELEC2020-RVI-AKLAN-047 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114711 | Tag-osip Elementary School | BURUANGA | 0 | 1 | SOLAR PANEL |  | 920472.82 | 917972.82 | COMPLETED | 100% | 2021-01-20 | 2021-04-26 | ELEC2020-RVI-AKLAN-046 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114722 | Malindog PS | IBAJAY | 0 | 1 | SOLAR PANEL |  | 600993.23 | 599356.54 | COMPLETED | 100% | 2021-01-20 | 2021-12-01 | ELEC2020-RVI-AKLAN-060 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-20 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | 0 | 1 | UPGRADING |  | 2082046.49 | 2080046.49 | COMPLETED | 100% | 2021-01-20 | 2021-05-03 | ELEC2020-RVI-AKLAN-033 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114735 | Mina-a ES | IBAJAY | 0 | 1 | SOLAR PANEL |  | 930972.82 | 929500.43 | COMPLETED | 100% | 2021-01-20 | 2021-12-01 | ELEC2020-RVI-AKLAN-049 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-20 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1454991.76 | 1452460.32 | COMPLETED | 100% | 2021-01-20 | 2021-05-25 | ELEC2020-RVI-AKLAN-010 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 0 | 1 | UPGRADING |  | 1944227.69 | 1942149.56 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-011 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114770 | Agbatuan PS | LIBACAO | 0 | 1 | SOLAR PANEL |  | 1019823.4 | 1018131.51 | COMPLETED | 100% | 2021-01-20 | 2021-11-25 | ELEC2020-RVI-AKLAN-051 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 310617 | Alfonso XII NHS | LIBACAO | 0 | 1 |  |  | 1927485.357 | 1828000 | COMPLETED | 100% | 2021-11-17 |  | ELEC2020-RVI-AKLAN-008 |  | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | Rism Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114789 | Manika ES | LIBACAO | 0 | 1 | SOLAR PANEL |  | 1275359.67 | 1274184.19 | COMPLETED | 100% | 2021-01-20 | 2021-11-25 | ELEC2020-RVI-AKLAN-048 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500174 | Ortega Integrated School | LIBACAO | 0 | 1 | UPGRADING |  | 1898395.19 | 1897093.12 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-030 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500641 | Ma. Cristina IS | MADALAG | 0 | 1 | SOLAR PANEL |  | 1243859.67 | 1243734.19 | COMPLETED | 100% | 2021-01-20 | 2021-11-11 | ELEC2020-RVI-AKLAN-059 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | MAKATO | 0 | 1 | UPGRADING |  | 1959131.39 | 1956094.61 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-014 |  | 2019-11-20 | 2019-12-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114846 | Balabag ES | MALAY | 0 | 1 | UPGRADING |  | 1856395.19 | 1855104.93 | COMPLETED | 100% | 2021-01-20 | 2021-01-21 | ELEC2020-RVI-AKLAN-006 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 0 | 1 | UPGRADING |  | 1785240.89 | 1781167.55 | COMPLETED | 100% | 2021-01-20 | 2021-01-21 | ELEC2020-RVI-AKLAN-007 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 500175 | Kinalangay Viejo IS | MALINAO | 0 | 1 | UPGRADING |  | 2149935.29 | 2148277.79 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-018 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302312 | Lilo-an National High School | MALINAO | 0 | 1 | UPGRADING |  | 1736535.59 | 1734618.22 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-019 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 114869 | Osman Elementary School | MALINAO | 0 | 1 | SOLAR PANEL |  | 920472.82 | 919945.43 | COMPLETED | 100% | 2021-01-20 | 2021-11-11 | ELEC2020-RVI-AKLAN-044 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302334 | Rosario National High School | MALINAO | 0 | 1 | UPGRADING |  | 1784272.79 | 1783548.22 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-023 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302335 | Solido National High School | NABAS | 0 | 1 | UPGRADING |  | 2082046.49 | 2076911.03 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-031 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Aklan | 302339 | Unidos NHS | NABAS | 0 | 1 | UPGRADING |  | 1489848.59 | 1488973.71 | COMPLETED | 100% | 2021-01-20 | 2021-02-26 | ELEC2020-RVI-AKLAN-032 |  | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-17 | 2020-09-15 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114957 | Bahoyan-Yapo ES | BARBAZA | 0 | 1 | UPGRADING |  | 1311509.98 | 1217440.1 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-007 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114965 | Ipil-Jinalinan ES | BARBAZA | 0 | 1 | UPGRADING |  | 1457460.09 | 1619558.3 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-009 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114983 | Bagtason ES | BUGASONG | 0 | 1 | UPGRADING |  | 1311509.98 | 1216823.95 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-014 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114986 | Camangahan ES | BUGASONG | 0 | 1 | UPGRADING |  | 1311509.98 | 1230145.88 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-015 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 114995 | Pangalcagan ES | BUGASONG | 0 | 1 | UPGRADING |  | 1337759.98 | 1251601.86 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-019 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115002 | Zaragoza Elementary School | BUGASONG | 0 | 1 | UPGRADING |  | 1457460.09 | 1372624.8 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-021 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115007 | Caluya Central School | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598426.76 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-022 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 302350 | Caluya NHS | CALUYA | 0 | 1 | UPGRADING |  | 1884833.19 | 1822166.08 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-110 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115019 | Semirara Elementary School | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598776.75 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-027 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 310705 | Semirara NHS | CALUYA | 0 | 1 | UPGRADING |  | 1884833.19 | 1825505.96 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-112 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115025 | Tinogboc ES | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1598776.75 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-028 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 302382 | Tinogboc NHS | CALUYA | 0 | 1 | UPGRADING |  | 1865933.19 | 1808248.27 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-111 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115026 | Villarises ES | CALUYA | 0 | 1 | UPGRADING |  | 1646460.09 | 1591929.5 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | Elec2020-RVI-ANTIQUE-029 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115036 | Camancijan ES | CULASI | 0 | 1 | UPGRADING |  | 1311509.98 | 1316920.74 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-031 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115053 | San Juan ES | CULASI | 0 | 1 | UPGRADING |  | 1235384.9193 | 1160151.52 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC 2020-RVI-Antique-034 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115086 | Fabrica ES | HAMTIC | 0 | 1 | UPGRADING |  | 1310428.48 | 1308726.01 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-042 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115087 | Guintas ES | HAMTIC | 0 | 1 | UPGRADING |  | 1389211.51 | 1388009.23 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-043 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115075 | Malandog ES | HAMTIC | 0 | 1 | UPGRADING |  | 1304974.78 | 1302758.68 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-040 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115093 | Mapatag ES | HAMTIC | 0 | 1 | UPGRADING |  | 1236469.36 | 1235954.53 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-047 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115105 | Guinbanga-an ES | LAUA-AN | 0 | 1 | UPGRADING |  | 1331663.68 | 1253331.14 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-050 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115136 | San Roque ES | LIBERTAD | 0 | 1 | UPGRADING |  | 1312628.86 | 1259349.44 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-057 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115152 | Guia Elementary School | PANDAN | 0 | 1 | UPGRADING |  | 1350547.93 | 1331069.9 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-061 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115176 | Aureliana ES | PATNONGON | 0 | 1 | UPGRADING |  | 1309873.03 | 1617392.77 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-062 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115244 | La Union ES | SAN REMIGIO | 0 | 1 | UPGRADING |  | 1337759.98 | 1338505.6 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-063 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115272 | Sinondolan ES | SAN REMIGIO | 0 | 1 | UPGRADING |  | 1343009.98 | 1404637.91 | COMPLETED | 100% | 2021-01-30 | 2021-12-31 | ELEC2020-RVI-Antique-064 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115280 | Bacalan ES | SEBASTE | 0 | 1 | UPGRADING |  | 1319809.6 | 1231875.16 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-067 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115282 | Idio ES | SEBASTE | 0 | 1 | UPGRADING |  | 1310494.42 | 1231342.93 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-071 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115307 | Sido-San Juan ES | SIBALOM | 0 | 1 | UPGRADING |  | 1311509.98 | 1316593.48 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-075 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115348 | San Francisco Norte ES | TIBIAO | 0 | 1 | UPGRADING |  | 1311509.98 | 1231342.93 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-076 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115350 | Sta. Justa ES | TIBIAO | 0 | 1 | UPGRADING |  | 1457460.09 | 1336577.08 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-078 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115354 | Tuno Elementary School | TIBIAO | 0 | 1 | UPGRADING |  | 1311509.98 | 1314659.17 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-079 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115355 | Abaca ES | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1311509.98 | 1245177.73 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-080 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115359 | Barasanan ES | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1457460.09 | 1234417.33 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | ELEC2020-RVI-Antique-081 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115364 | Dao Central School | TOBIAS FORNIER (DAO) | 0 | 1 | UPGRADING |  | 1457460.09 | 1341188.68 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-082 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115393 | Buluangan I ES | VALDERRAMA | 0 | 1 | UPGRADING |  | 1311509.98 | 1316920.74 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-084 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115151 | Fragante ES | PANDAN | 1 | 1 | UPGRADING |  | 1307767.57 | 1511958.48 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-085 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115153 | Idiacacan ES | PANDAN | 1 | 1 | UPGRADING |  | 1325739.58 | 1239176.59 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-086 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115157 | Mag-aba ES | PANDAN | 1 | 1 | UPGRADING |  | 1307566.22 | 1235333.74 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | ELEC2020-RVI-Antique-087 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115214 | Loreto-Joaquin Delgado ES (Badiang ES) | SAN JOSE (Capital) | 1 | 1 | UPGRADING |  | 1233084.75 | 1310444.68 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-090 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115235 | Barangbang ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1318150.85 | 1730043.63 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-094 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115237 | Cadolonan ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1232610.82 | 1461668.23 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-095 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115245 | Magdalena ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1316729.3 | 1231875.16 | COMPLETED | 100% | 2021-01-30 | 2022-11-04 | Elec2020-RVI-ANTIQUE-097 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | 11.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115246 | Maragubdub ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1245845.54 | 1310444.68 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-098 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115271 | San Rafael ES | SAN REMIGIO | 1 | 1 | UPGRADING |  | 1235911.39 | 1456350.58 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-099 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115279 | Aras-asan ES | SEBASTE | 1 | 1 | UPGRADING |  | 1309235.12 | 1456350.58 | COMPLETED | 100% | 2021-02-27 | 2021-12-24 | Elec2020-RVI-ANTIQUE-100 |  | 2019-12-02 | 2019-12-09 | 2019-12-23 | 2020-01-13 |  | PAR BUILDERS, ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Antique | 115281 | Callan ES | SEBASTE | 1 | 1 | UPGRADING |  | 1231205.96 | 1311510 | COMPLETED | 100% | 2021-07-22 | 2021-08-06 | Elec2020-RVI-ANTIQUE-105 | [6 empty] | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115611 | Agbalo ES | PANAY | 1 | 1 |  |  | 1118912.76 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115623 | Calapawan ES | PANAY | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115636 | Panay CS | PANAY | 1 | 1 |  |  | 1485555.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115637 | Pawa ES | PANAY | 1 | 1 |  |  | 1000040.16 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115624 | Ricardo Bernas ES (calitan) | PANAY | 1 | 1 |  |  | 1027251.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115638 | Tanza Norte ES | PANAY | 1 | 1 |  |  | 1302234.36 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115644 | Ambilay Elem. Sch. | PANITAN | 1 | 1 |  |  | 1091700.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115645 | Bahit Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115652 | Cogon Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115653 | Conciencia Elem. Sch. | PANITAN | 1 | 1 |  |  | 1118912.76 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115656 | Jesus Gonzalo Albana ES | PANITAN | 1 | 1 |  |  | 1043709.24 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115657 | Maluboglubog Elem. Sch. | PANITAN | 1 | 1 |  |  | 1210573.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115658 | Panit-an Elem. Sch. | PANITAN | 1 | 1 |  |  | 1550004.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115499 | Agustin P. Navarra Elemenatary School | IVISAN | 2 | 1 |  |  | 1302234.36 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-037 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115502 | BASIAO ELEMENTARY SCHOOL | IVISAN | 2 | 1 |  |  | 1275022.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115503 | Cabugao ES (ivisan) | IVISAN | 2 | 1 |  |  | 1393895.16 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-039 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115505 | Catalino Andrada MS | IVISAN | 2 | 1 |  |  | 1421106.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-040 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115504 | Cudian ES | IVISAN | 2 | 1 |  |  | 1413945.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-045 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115507 | Ivisan ES | IVISAN | 2 | 1 |  |  | 1760538.36 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-046 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115506 | Juan S. Jarencio MS | IVISAN | 2 | 1 |  |  | 1091700.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115509 | Mahayag Elementary School | IVISAN | 2 | 1 |  |  | 1366683.36 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-051 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115510 | Malocloc ES | IVISAN | 2 | 1 |  |  | 1275022.56 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-053 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115511 | Panfilo Mendoza ES | IVISAN | 2 | 1 |  |  | 1550004.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-054 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115508 | Victor A. Umiten Elementary School | IVISAN | 2 | 1 |  |  | 1570055.76 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 501088 | Antonio Belo ES | PANITAN | 2 | 1 |  |  | 1485555.96 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-057 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Capiz | 115650 | Capagao ES | PANITAN | 2 | 1 |  |  | 1118912.76 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-CAPIZ-058 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | 0 | 1 |  |  | 8683062.82 |  | COMPLETED | 100% | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | 0 | 1 |  |  | 8452649.92 |  | COMPLETED | 100% | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302428 | Cabalagnan National High School | NUEVA VALENCIA | 0 | 1 |  |  | 6601348.58 |  | COMPLETED | 100% | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302435 | Calaya National High School | NUEVA VALENCIA | 0 | 1 |  |  | 8222237.02 |  | COMPLETED | 100% | 2021-12-12 | 2021-12-12 | Elec2020-RVI-Guimaras-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302436 | Salvacion National High School | NUEVA VALENCIA | 0 | 1 |  |  | 5193167.94 |  | COMPLETED | 100% | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | 0 | 1 |  |  | 7070172.53 |  | COMPLETED | 100% | 2021-02-19 | 2021-02-19 | Elec2020-RVI-Guimaras-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302509 | Iloilo NHS | ILOILO CITY (Capital) | 0 | 1 |  |  | 21603497.96 | 5081769.4 | COMPLETED | 100% | 2021-12-02 | 2021-01-13 | ELEC2020-RVI-ILOILO-032 | ELEC2020-RVI-ILOILO-032 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-15 | NOE'S BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302495 | Don Felix Serra NHS | SAN JOAQUIN | 1 | 1 |  |  | 9086311.69 | 4660059.52 | COMPLETED | 100% | 2021-02-02 | 2021-01-12 | ELEC2020-RVI-ILOILO-005 | ELEC2020-RVI-ILOILO-005 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-05 | MJ Barcelona Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302459 | Barroc NHS | TIGBAUAN | 1 | 1 |  |  | 6124419.12 | 21538687.47 | COMPLETED | 100% | 2021-10-02 | 2021-02-16 | ELEC2020-RVI-ILOILO-019 | ELEC2020-RVI-ILOILO-019 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-13 | MICRO ASIA BUILDERS CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302487 | Daga-Barasan NHS | SANTA BARBARA | 2 | 1 |  |  | 4217214.52 | 8683035.31 | COMPLETED | 100% | 13/02/2021 | 2021-01-15 | ELEC2020-RVI-ILOILO-026 | ELEC2020-RVI-ILOILO-026 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302580 | Tina National High School | BADIANGAN | 3 | 1 |  |  | 4843463.92 | 13734009.49 | COMPLETED | 100% | 13/02/2021 | 2021-01-07 | ELEC2020-RVI-ILOILO-028 | ELEC2020-RVI-ILOILO-028 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302546 | PALANGUIA NATIONAL HIGH SCHOOL | POTOTAN | 3 | 1 |  |  | 6903244.43 | 4972203.86 | COMPLETED | 100% | 2021-09-02 | 2021-02-04 | ELEC2020-RVI-ILOILO-016 | ELEC2020-RVI-ILOILO-016 | 2019-12-21 | 2019-12-27 | 2020-01-10 | Septmber 25, 2020 | 2020-10-12 | NOE'S BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302563 | San Enrique Manuel Paluay, Sr. MHS | SAN ENRIQUE | 4 | 1 |  |  | 5111080.79 | 8996000 | COMPLETED | 100% | 2021-02-02 | 2021-01-12 | ELEC2020-RVI-ILOILO-033 | ELEC2020-RVI-ILOILO-033 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-05 | RISM BULDERS & CONSTRUCTION SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5 | 1 |  |  | 13773244.05 | 4757857.58 | COMPLETED | 100% | 16/02/2021 | 2020-02-16 | ELEC2020-RVI-ILOILO-014 | ELEC2020-RVI-ILOILO-014 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-19 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | SAN RAFAEL | 5 | 1 |  |  | 8745250.93 | 3693373.72 | COMPLETED | 100% | 28/10/2021 | 2021-10-26 | ELEC2020-RVI-ILOILO-024 | ELEC2020-RVI-ILOILO-024 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2021-06-07 | 2021-06-30 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo | 302525 | Malapaya NHS | SARA | 5 | 1 |  |  | 5776411.41 | 3574085.65 | COMPLETED | 100% | 13/02/2021 | 2021-06-07 | ELEC2020-RVI-ILOILO-006 | ELEC2020-RVI-ILOILO-006 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-09-30 | 2020-10-16 | CULASI GENERAL MERCHANDISING AND CONSTRUCTION SERICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) | 0 | 1 |  |  | 10933410.95 |  | COMPLETED | 100% |  |  | Elec2020-RVI-ILOILOCITY-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117606 | La Paz ES I | ILOILO CITY (Capital) | 0 | 1 |  |  | 8740315.64 |  | COMPLETED | 100% |  |  | Elec2020-RVI-ILOILOCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 117607 | La Paz ES II | ILOILO CITY (Capital) | 0 | 1 |  |  | 6327540.57 |  | COMPLETED | 100% |  |  | Elec2020-RVI-ILOILOCITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Iloilo City | 302749 | Mandurriao NHS | ILOILO CITY (Capital) | 0 | 1 |  |  | 7826181.84 |  | COMPLETED | 100% |  |  | Elec2020-RVI-ILOILOCITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117829 | Badiangay ES | CITY OF KABANKALAN | 6 | 1 |  |  | 996308.04 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-KABANKALANCITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 | 1 |  |  | 2918681.94 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-KABANKALANCITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117856 | Camansi ES | CITY OF KABANKALAN | 6 | 1 |  |  | 1640793.7 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-KABANKALANCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Kabankalan City | 117849 | Pitgong ES | CITY OF KABANKALAN | 6 | 1 |  |  | 479345.9 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-KABANKALANCITY-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302603 | Calatrava NHS | CALATRAVA | 1 | 1 |  |  | 5349237.01 |  | COMPLETED | 100% |  |  | Elec2020-R6-Negros Occidental-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302624 | ENRIQUETA MONTILLA DE ESTEBAN MEMORIAL HIGH SCHOOL | PULUPANDAN | 4 | 1 |  |  | 6176278.18 | 6140194.07 | COMPLETED | 100% | 2020-12-30 |  | Elec2020-R6-Negros Occidental-006 | 20-09-007 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 | 1 |  |  | 4601842.13 |  | COMPLETED | 100% |  |  | Elec2020-R6-Negros Occidental-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Negros Occidental | 302600 | Bilbao-Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 |  |  | 8670357.39 | 3296807.84 | COMPLETED | 100% | 2020-12-30 |  | Elec2020-R6-Negros Occidental-004 | 20-09-006 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply | Energized already on OCT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117653 | COGON IS | ROXAS CITY | 1 | 1 |  |  | 1138963.56 | 1081502.38 | COMPLETED | 100% | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-010 | CON-2020-092/1 |  |  | 2020-10-20 | 2020-10-23 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117668 | DON FRANCISCO DINGLASAN MS | ROXAS CITY | 1 | 1 |  |  | 1193387.16 | 1133810.02 | COMPLETED | 100% | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-008 | CON-2020-092/3 |  |  | 2020-10-22 | 2020-10-25 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117682 | DONA EMILIANA ALBA MS | ROXAS CITY | 1 | 1 |  |  | 1275022.56 | 1211968.04 | COMPLETED | 100% | 2021-09-19 | 2021-07-15 | ELEC2020-RVI-ROXAS CITY-003 |  | 2021-04-13 | 2021-04-21 | 2021-05-05 |  |  | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117683 | DONA VICENTA P.HONTIVEROS MS | ROXAS CITY | 1 | 1 |  |  | 1302234.36 | 1238425.3 | COMPLETED | 100% | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-001 | CON-2020-092/4 |  |  | 2020-10-23 | 2020-10-26 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | ROXAS CITY | 117657 | DUMOLOG ES | ROXAS CITY | 1 | 1 |  |  | 1166175.36 | 1107656.2 | COMPLETED | 100% | 2021-04-09 | 2021-04-07 | ELEC2020-RVI-ROXAS CITY-009 | CON-2020-092/2 |  |  | 2020-10-21 | 2020-10-24 | 2020-12-17 | RJZW ELECTRICAL ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117691 | Alfredo E. Maranon Sr. ES- School of the Future | Sagay City | 2 | 1 |  |  | 1193711.9 | 893000 | COMPLETED | 100% | September 16, 2021 | August 21, 2021 | ELEC2020-RVI-SAGAYCITY-001 | 43831 | February 25- March 16, 2020 | 2020-03-03 | 2020-03-16 | 2021-05-31 | 2021-07-16 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117695 | Buenaventura Rodriguez Elem School | Sagay City | 2 | 1 |  |  | 946032.78 | 793222.9845 | COMPLETED | 100% | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-002 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Sagay City | 117739 | Rufino T. Halipa Sr. Elem School | Sagay City | 2 | 1 |  |  | 662421.31 | 555335.4289 | COMPLETED | 100% | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-003 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Silay City | 302780 | Doña Montserrat Lopez Memorial National High School (JHS) | SILAY CITY | 3 | 1 |  |  | 2028763.71 |  | COMPLETED | 100% |  |  | ELEC2020-RVI-SILAYCITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VI | Silay City | 117804 | Silay South ES | SILAY CITY | 3 | 1 |  |  | 2266185.32 |  | ONGOING | 95% |  |  | ELEC2020-RVI-SILAYCITY-001 | [7 empty] | transformer requirements. As per PO, 100kva single phase Max allowed by COOP for a single phase is only 50kva...for VO as end of January | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region VII | Bayawan City | 120107 | Basay Central School | BASAY | 3 | 1 |  |  | 1349567.05 |  | COMPLETED | 100% |  |  | Elec2020-RVII-BAYAWAN-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bayawan City | 120123 | Bayawan City East Central School | CITY OF BAYAWAN (TULONG) | 3 | 1 |  |  | 4632554.88 |  | COMPLETED | 100% |  |  | Elec2020-RVII-BAYAWAN-001 |  | 2/13/2020 | 2/21/2020 | 2020-04-03 | 2020-11-03 | 2020-11-12 | H.I.T. CPNTRACTORS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bayawan City | 120165 | Tayawan Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 |  |  | 1536168.85 |  | COMPLETED | 100% |  |  | Elec2020-RVII-BAYAWAN-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302900 | San Roque National High School | ALBURQUERQUE | 1 | 1 |  |  | 3167392.32 | 2491290.6 | TERMINATED | 25% |  |  | ELEC2020-RVII-BOHOL-005 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | TERMINATED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 25% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 |  |  | 2466194.59 | 1964481.18 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-001 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302838 | Cong. Pablo Malasarte NHS | BALILIHAN | 1 | 1 |  |  | 2843579.25 | 2266156.83 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-003 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302856 | Hanopol NHS | BALILIHAN | 1 | 1 |  |  | 2843093.18 | 2257691.98 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-004 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302883 | Calape National High School | CALAPE | 1 | 1 |  |  | 2835435.15 | 2257691.98 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-002 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 312304 | Dauis National High School | DAUIS | 1 | 1 |  |  | 2500340.23 |  | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-006 | [7 empty] | ONGOING NEGOTIATION WITH THE SERVICE PROVIDER | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302896 | SIKATUNA NATIONAL AGRICULTURAL HIGH SCHOOL | TALIBON | 2 | 1 |  |  | 2941545.98 | 2342694.72 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-010 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 |  |  | 3275154.24 | 2591610.27 | TERMINATED | 25% |  |  | ELEC2020-RVII-BOHOL-009 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | TERMINATED on july 12, 2022 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 25% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 |  |  | 2423626.17 | 1848253.65 | TERMINATED | 90% |  |  | ELEC2020-RVII-BOHOL-019 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | Recommended for termination | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 90% | 0% |  |  | UPGRADING |  |  | TERMINATED
ELECTRIFICATION 2020 | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 |  |  | 2871885.8 | 2288311.28 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-023 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 |  |  | 2863499.44 | 2282871.03 | COMPLETED | 100% |  |  | ELEC2020-RVII-BOHOL-025 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 | 1 | UPGRADING |  | 1589621.19 | 1426884.26 | COMPLETED | 100% | 2021-02-25 | 2020-12-10 | Elec2020-RVII-CEBU-008 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-04 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services | ONGOING NEGOTIATION WITH THE SERVICE PROVIDER | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | UPGRADING |  | 2927126.25 | 2471043.22 | COMPLETED | 100% |  |  | Elec2020-RVII-CEBU-016 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-05 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | JY BONTILAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 302997 | Dalaguete National High School | DALAGUETE | 2 | 1 | UPGRADING |  | 2174862.7 | 1638877.59 | COMPLETED | 100% | 2021-02-25 | 2020-12-10 | Elec2020-RVII-CEBU-006 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-04 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 303098 | Argao National High School | Santander | 2 | 1 | UPGRADING |  | 1389209.52 |  | COMPLETED | 100% |  |  | Elec2020-RVII-CEBU-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 312409 | Patao NHS | Bantayan | 4 | 1 | UPGRADING |  | 1617091.23 | 1305979.12 | COMPLETED | 100% | 2021-03-07 | 2020-12-16 | Elec2020-RVII-CEBU-022 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-03 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 303094 | Santa Fe NHS | Santa Fe | 4 | 1 | UPGRADING |  | 1260998.3 | 1021501.56 | COMPLETED | 100% | 2021-03-07 | 2020-12-16 | Elec2020-RVII-CEBU-023 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-03 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 303091 | Arcelo MNHS | LILOAN | 5 | 1 | UPGRADING |  | 1037093.99 | 899518.34 | COMPLETED | 100% | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-018 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 500423 | Calero IS | LILOAN | 5 | 1 | UPGRADING |  | 1198633.89 | 1196633 | COMPLETED | 100% | 2021-02-28 |  | Elec2020-RVII-CEBU-003 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU | 2020-11-29 | 2020-11-26 | 2020-12-09 | 2020-12-14 | 2020-12-22 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 119414 | Liloan CS | LILOAN | 5 | 1 | UPGRADING |  | 1076432.22 | 902702.9 | COMPLETED | 100% | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-002 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 119423 | Yati ES | LILOAN | 5 | 1 | UPGRADING |  | 967688.14 | 732367.05 | COMPLETED | 100% | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-001 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu | 302955 | Cordova NHS | CORDOVA | 6 | 1 | UPGRADING |  | 970303.71 | 965750 | COMPLETED | 100% | 2021-04-12 |  | Elec2020-RVII-CEBU-017 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-RFQ | - | - | - | - | 2021-01-04 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Cebu City | 119930 | Regino Mercado ES | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1558067.85 |  | COMPLETED | 100% |  |  | Elec-2020-RVII-CEBUCITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Dumaguete City | 119934 | Batinguel Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 774652.63 | 774152.62 | COMPLETED | 100% | 2021-10-29 |  | Elec2020-RVII-DUMAGUETE-005 | Elec2020-RVII-DUMAGUETE-005 | 2020-03-05 | 2020-03-20 | 2020-04-01 | 2020-04-23 | 2021-06-24 | PINS CONSTRUCTION | Energized already but still for final inspection; waiting for the availability of the contractor. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Dumaguete City | 303167 | Junob National High School | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 831614.36 |  | COMPLETED | 100% |  |  | Elec2020-RVII-DUMAGUETE-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 779998.96 |  | COMPLETED | 100% |  |  | Elec2020-RVII-DUMAGUETE-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Lapu-Lapu City | 303180 | Marigondon National High School | LAPU-LAPU CITY (OPON) | 6 | 1 |  |  | 5969870.35 |  | COMPLETED | 100% |  |  | Elec2020-RVII-LAPULAPU-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Mandaue City | 120004 | Banilad ES | MANDAUE CITY | 6 | 1 |  |  | 1697087.76 |  | COMPLETED | 100% |  |  | ELEC2020-RVII-MANDAUE-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Mandaue City | 312810 | Tingub High School | MANDAUE CITY | 6 | 1 |  |  | 2447039.44 | 2046593.18 | COMPLETED | 100% | 2021-10-16 |  | ELEC2020-RVII-MANDAUE-002 | 2021-06-043 | 21-Apr-21 | 28-Apr-21 | 10-May-21 | 03-Jun-21 | 2021-06-18 | CCO Eng'g. Const. & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 | 1 |  |  | 3171684.86 |  | COMPLETED | 100% |  |  | Elec2020-RVII-NEGROSORIENTAL-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 | 1 |  |  | 721415.76 |  | COMPLETED | 100% |  |  | Elec2020-RVII-NEGROSORIENTAL-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 | 1 |  |  | 850816.56 | 764758.06 | COMPLETED | 100% |  |  | Elec2020-RVII-NEGROSORIENTAL-013 | [5 empty] | 2021-09-02 | Tribata Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 119797 | Candulawan ES | Talisay City | 1 | 1 |  |  | 551154.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 130922 | Dumlog ES | Talisay City | 1 | 1 |  |  | 513643.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 119798 | Iba ES | Talisay City | 1 | 1 |  |  | 487735.26 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 119800 | Lagtang ES | Talisay City | 1 | 1 |  |  | 549981.44 | 548254.3433 | COMPLETED | 100% | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 233501 | Linao ES | Talisay City | 1 | 1 |  |  | 536318.54 | 534342.6226 | COMPLETED | 100% | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 119802 | San Isidro ES | Talisay City | 1 | 1 |  |  | 534308.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 322205 | Talisay City Science HS | Talisay City | 1 | 1 |  |  | 504372.41 | 502338.883 | COMPLETED | 100% | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Talisay City | 312402 | Tangke NHS | Talisay City | 1 | 1 |  |  | 496419.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Toledo City | 303310 | DAS NHS | Toledo | 3 | 1 |  |  | 1499034.41 |  | COMPLETED | 100% |  |  | Elec2020RVII-Toledo City | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Toledo City | 303311 | Gen. Climaco NHS | Toledo | 3 | 1 |  |  | 3128056.8 |  | COMPLETED | 100% |  |  | Elec2020 RVII-Toledo City | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VII | Toledo City | 303312 | Magdugo NHS | Toledo | 3 | 1 |  |  | 1697679.38 |  | COMPLETED | 100% |  |  | Elec2020-Toledo City | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 121102 | BAYBAY II CS | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1702836.12 | 1654979.75 | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-001 | 2019-11-009 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | BENCH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303349 | Bitanhuan National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1359964.45 | 1204857.41 | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-003 | 2019-11-010 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | JUNVILL ENTERPRISES & CONSTRUCTION SERVICE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303351 | Bunga National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 2176912.05 | 2155874.84 | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-004 | 2019-11-011 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 500673 | Kabunga-an Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1649632.87 | 1853375.18 | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-006 | 2019-11-012 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 303400 | Makinhas National High School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 1876325.75 | 1508346.81 | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-007 | 2019-11-013 | November 21, 2019 | November 29, 2019 | December 11, 2019 | December 18, 2019 |  | JUNVILL ENTERPRISES & CONSTRUCTION SERVICE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Baybay City | 500746 | Mapgap Integrated School | CITY OF BAYBAY | 5 | 1 | UPGRADING |  | 488908.05 |  | COMPLETED | 100% |  |  | ELEC2020-R8-BAYBAY CITY-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120774 | BILIRAN CS | BILIRAN | 0 | 1 | UPGRADING |  | 1612387.81 | 1597243.65 | COMPLETED | 100% | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-002 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120788 | CABUCGAYAN CS | CABUCGAYAN | 0 | 1 | UPGRADING |  | 1845539.23 | 1840527.68 | COMPLETED | 100% | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-003 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 303323 | CABUCGAYAN NHS | CABUCGAYAN | 0 | 1 | UPGRADING |  | 2094055.88 | 2086877.03 | COMPLETED | 100% | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-004 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 500411 | INASUYAN IS | KAWAYAN | 0 | 1 | UPGRADING |  | 1719745.19 | 1714750.25 | COMPLETED | 100% | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-009 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120834 | KAWAYAN CS | KAWAYAN | 0 | 1 | UPGRADING |  | 1592369.85 | 1586595.66 | COMPLETED | 100% | 12/28/20 | 12/28/20 | ELEC2020-R8-BILIRAN-010 | [6 empty] | MB Ang Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Biliran | 120860 | NAVAL CS | NAVAL | 0 | 1 | UPGRADING |  | 2655167.6 |  | COMPLETED | 100% |  |  | ELEC2020-R8-BILIRAN-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122372 | BUGAS ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 1551977.85 | 1550000 | COMPLETED | 100% | JAN. 17, 2021 | DEC. 15, 2020 | ELEC2020 - R8 - BORONGAN CITY - 001 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | NOV. 9, 2020 | NOV. 11, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122404 | SAN SATURNINO ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 1424913.98 | 860000 | COMPLETED | 100% | DEC. 4, 2020 | NOV. 30, 2020 | ELEC2020 - R8 - BORONGAN CITY - 004 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn - Lot 2 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | AUG. 28, 2020 | SEPT. 1, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Borongan City | 122407 | SURIBAO ELEMENTARY SCHOOL | Borongan City | 0 | 1 | UPGRADING |  | 869954.57 | 1415000 | COMPLETED | 100% | DEC. 4, 2020 | NOV. 30, 2020 | ELEC2020 - R8 - BORONGAN CITY - 003 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schoolsn - Lot 3 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 | AUG. 28, 2020 | SEPT. 1, 2020 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 956248.5 | 946443.2 | COMPLETED | 100% |  |  | ELEC-2020 - R8-CALBAYOG CITY-001 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124006 | Calbayog East Central Elementary School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 2062355.88 | 2042815.11 | COMPLETED | 100% |  |  | ELEC-2020 - R8-CALBAYOG CITY-002 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124137 | Malaga Central Elementary School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 999370.74 | 986852.45 | COMPLETED | 100% |  |  | ELEC-2020 - R8-CALBAYOG CITY-003 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124070 | Oquendo Central School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1882118.05 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-CALBAYOG CITY-004 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Calbayog City | 124048 | San Policarpo Central Elem. School | CALBAYOG CITY | 1 | 1 | UPGRADING |  | 1931678.07 | 1920026.8 | COMPLETED | 100% |  |  | ELEC-2020 - R8-CALBAYOG CITY-006 |  | Oct. 27, 2020 | Oct. 30, 2021 | Nov. 3, 2020 | Dec. 11, 2020 |  | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Catbalogan City | 123439 | Silanga Elementary School | Catbalogan City | 2 | 1 | UPGRADING |  | 985061.87 |  | COMPLETED | 100% |  |  | ELEC2020 - R8 - CATBALOGAN CITY - 001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Catbalogan City | 123428 | Socorro Elementary School | Catbalogan City | 2 | 1 | UPGRADING |  | 870579.39 |  | COMPLETED | 100% |  |  | ELEC2020 - R8 - CATBALOGAN CITY - 002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 313520 | Carapdapan National High School | ARTECHE | 0 | 1 | UPGRADING |  | 1491278.49 |  | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational High School | DOLORES | 0 | 1 | UPGRADING |  | 1082114.71 | 1070000 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 011 | ELEC2020 - R8 - EASTERN SAMAR - 012 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122534 | Banahao Elementary School | GUIUAN | 0 | 1 | UPGRADING |  | 591827.37 | 590146.95 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 002 | ELEC2020 - R8 - EASTERN SAMAR - 003 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122521 | Campoyong Elementary School | GUIUAN | 0 | 1 | UPGRADING |  | 1277433.98 | 1269853.05 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 004 | ELEC2020 - R8 - EASTERN SAMAR - 005 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 0 | 1 | UPGRADING |  | 1774394.72 | 1768000 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 027 | ELEC2020 - R8 - EASTERN SAMAR - 028 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 500235 | Dao Integrated School | ORAS | 0 | 1 | UPGRADING |  | 1228899.12 | 1218000 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 026 | ELEC2020 - R8 - EASTERN SAMAR - 027 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122708 | Buabua Elementary School | SALCEDO | 0 | 1 | UPGRADING |  | 1939734.44 | 1930000 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 003 | ELEC2020 - R8 - EASTERN SAMAR - 004 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122731 | San Julian Central Elementary School | SAN JULIAN | 0 | 1 | UPGRADING |  | 1595953.93 | 1594579.11 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 028 | ELEC2020 - R8 - EASTERN SAMAR - 029 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Eastern Samar | 122774 | San Rafael Elementary School | TAFT | 0 | 1 | UPGRADING |  | 302045.74 | 295420.89 | COMPLETED | 100% |  |  | ELEC2020 - R8 - EASTERN SAMAR - 021 | ELEC2020 - R8 - EASTERN SAMAR - 016 | Nov. 22, 2019 | Nov. 29, 2019 | December 11, 2019 |  |  | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303386 | Kiling National High School | TANAUAN | 1 | 1 | UPGRADING |  | 1329322.98 | 1297441.71 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-010 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303391 | Daniel Z. Romualdez State Comprehensive School of Fisheries | TOLOSA | 1 | 1 | UPGRADING |  | 805004.86 | 792280.74 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-043 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303354 | Burauen National High School | BARAUEN | 2 | 1 | UPGRADING |  | 1677259.6 | 1198763.13 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-003 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313325 | Hibunauan National High School | BARAUEN | 2 | 1 | UPGRADING |  | 1001808.54 | 716151.59 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-022 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303367 | Don Mariano Salvacion Memorial National High School | CAPOOCAN | 2 | 1 | UPGRADING |  | 873899.3 | 503770.13 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-005 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303369 | Dulag National High School | DULAG | 2 | 1 | UPGRADING |  | 743766.1 | 541761.61 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-006 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303428 | Sta. Ana National High School | LA PAZ | 2 | 1 | UPGRADING |  | 1397248.46 | 1025969.38 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-017 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | MASS CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR | 2 | 1 | UPGRADING |  | 1797196.33 | 1041227.93 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-015 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | UPGRADING |  | 2970335.67 | 1724004.22 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-009 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303358 | Calubian National High School (Calubian Nat'l. Voc'l. School) | CALUBIAN | 3 | 1 | UPGRADING |  | 2367360.56 | 1373016.19 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-026 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303378 | Isabel National High School | ISABEL | 4 | 1 | UPGRADING |  | 2563699.74 | 1487565.01 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-008 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303422 | San Francisco National High School | ISABEL | 4 | 1 | UPGRADING |  | 995962.3 | 574966.58 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-020 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303335 | Abuyog National High School | ABUYOG | 5 | 1 | UPGRADING |  | 2546085.48 | 1489874.66 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-001 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 120904 | Bernardo V. Closa Central School | ABUYOG | 5 | 1 | UPGRADING |  | 995109.23 | 711515.82 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-023 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313313 | Libertad National High School | ABUYOG | 5 | 1 | UPGRADING |  | 798007.3 | 570597.94 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-012 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | NETS ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5 | 1 | UPGRADING |  | 1687480.85 |  | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303347 | Bato School of Fisheries | BATO | 5 | 1 | UPGRADING |  | 2163896.08 | 1692178.29 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-032 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 | 1 | UPGRADING |  | 1537927.06 | 913047.8 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-002 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 313329 | Capudlosan National High School | HINDANG | 5 | 1 | UPGRADING |  | 889891.86 | 696900.42 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-004 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | BCG DESIGN AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Leyte | 303405 | Matalom National High School | MATALOM | 5 | 1 | UPGRADING |  | 1703686.08 | 1012030.8 | COMPLETED | 100% |  |  | ELEC2020-R8-LEYTE-014 |  | 2019-12-01 | 2019-12-09 | 2019-12-20 |  | 2019-10-14 | HD GOLDEN BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122129 | Guadalupe Elementary School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 477093.71 | 470814.34 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-001 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 313401 | Maasin City NHS | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 2862262.71 | 2147479.63 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-004 | ELECTRIFICATION-20-Batch 2-001 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-07-30 | 2021-08-12 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122139 | Manhilo ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 495031.46 | 488407.87 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-005 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 501050 | Maria Clara Integrated School | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 685660.96 | 676528.93 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-006 | ELECTRIFICTION-20-002 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122174 | San Rafael ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 751393.08 | 740070.54 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-007 | ELECTRIFICTION-20-002 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Maasin City | 122146 | Tam-Is ES | CITY OF MAASIN (Capital) | 0 | 1 | UPGRADING |  | 441197.89 | 433917.53 | COMPLETED | 100% |  |  | ELEC2020-R8-MAASIN CITY-008 | ELECTRIFICTION-20-001 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2020-02-13 | 2020-10-09 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303531 | Allen National High School | ALLEN | 1 | 1 | UPGRADING |  | 4179247.27 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1 | 1 | UPGRADING |  | 3153143.95 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303551 | Gala Vocational School | GAMAY | 2 | 1 | UPGRADING |  | 4181233.91 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303538 | Cahayagan NHS | LAOANG | 2 | 1 | UPGRADING |  | 1263351.56 |  | REVERTED | 0% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-015 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303559 | Lorenzo S. Menzon AIS | LAPINIG | 2 | 1 | UPGRADING |  | 2782521.44 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Northern Samar | 303584 | SUMOROY AGRO-INDUSTRIAL SCHOOL | PALAPAG | 2 | 1 | UPGRADING |  | 4842800.53 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-NORTHERN SAMAR-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124200 | Airport Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1108047.84 | 1092971.7328 | COMPLETED | 100% |  |  | ELEC2020-R8-ORMOC CITY-002 | [6 empty] | SILVERSOCKET ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124210 | Lao Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1103219.18 | 1088087.5383 | COMPLETED | 100% |  |  | ELEC2020-R8-ORMOC CITY-003 | [6 empty] | VHITS D.G. Builders & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Ormoc City | 124161 | Macabug Elementary School | ORMOC CITY | 4 | 1 | UPGRADING |  | 1106855.79 | 1085999.9864 | COMPLETED | 100% |  |  | ELEC2020-R8-ORMOC CITY-001 | [6 empty] | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303618 | Ramon T. Diaz NHS | GANDARA | 1 | 1 | UPGRADING |  | 4258691.09 | 4156897.2 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-014 | Electrical System Upgrade and Rewiring -L1 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | ROSS ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO | 1 | 1 | UPGRADING |  | 1157628.07 | 1254211.56 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-025 | Electrical System Upgrade and Rewiring - L2 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | VHITS DG BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan NHS | PAGSANGHAN | 1 | 1 | UPGRADING |  | 2062902.13 | 2042871 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-013 | Electrical System Upgrade and Rewiring - L3 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | NV&C Construction & General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303630 | Napuro NHS | SANTA MARGARITA | 1 | 1 | UPGRADING |  | 963427.41 | 960465 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-016 | Electrical System Upgrade and Rewiring - L4 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | NV&C Construction & General Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303592 | BASEY NHS | BASEY | 2 | 1 | UPGRADING |  | 5045609.5 | 5024994.19 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-004 | Electrical System Upgrade and Rewiring - L5 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | MAGA CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | UPGRADING |  | 2670135.96 | 2655120.6 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-027 | Electrical System Upgrade and Rewiring - L6 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | GPUY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 313730 | Baclayan NHS | DARAM | 2 | 1 | UPGRADING |  | 911420.18 | 939520.89 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-001 | Electrical System Upgrade and Rewiring - L7 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | GPUY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303595 | Birawan NHS | DARAM | 2 | 1 | UPGRADING |  | 2105612.71 |  | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 313716 | Anibongon IS | SANTA RITA | 2 | 1 | UPGRADING |  | 2635204.16 | 2616137.74 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-005 | Electrical System Upgrade and Rewiring - L8 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Samar (Western Samar) | 303607 | Igot National High School | VILLAREAL | 2 | 1 | UPGRADING |  | 1848306.15 | 1832939.66 | COMPLETED | 100% |  |  | ELEC-2020 - R8-WESTERN SAMAR-010 | Electrical System Upgrade and Rewiring - L9 | Nov. 20, 2019 | Nov. 27, 2019 | Dec. 11, 2019 | SEPT. 29, 2020 | OCT. 2, 2020 | RICHMARK CONST. INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303462 | ICHON NATIONAL HIGH SCHOOL | Macrohon | 0 | 1 | UPGRADING |  | 4139395.23 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 01 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303492 | VILLA JACINTA NATIONAL VOCATIONAL HIGH SCHOOL | MACROHON | 0 | 1 | UPGRADING |  | 3185646.9 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 03 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Southern Leyte | 303453 | DON AGUSTIN F. ESCANO NATIONAL HIGH SCHOOL | TOMAS UPPOS | 0 | 1 | UPGRADING |  | 3008879.86 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020 - R8- SOUTHERN LEYTE - 02 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 314003 | Antonio Balmes National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1264277.79 | 1254382.6 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-006 | [6 empty] | NV&C CONST. AND GENERAL SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 124233 | BAYANIHAN ELEMENTARY SCHOOL | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 736784.62 | 718870.99 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-014 | [6 empty] | VHITS D. G BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 303665 | Cirilo Roy Montejo National High School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1616282.66 | 1598300.63 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-005 | [6 empty] | RM PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500892 | Guadalupe Heights Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1298916.72 | 1290428.29 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-004 | [6 empty] | RM PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500490 | Kapuso Village Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1261385.86 | 1237160 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-002 | [6 empty] | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500891 | North Hill Arbours Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1256136.19 | 1240000 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-003 | [6 empty] | J. COSTURIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 500489 | Ridge View Park Integrated School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2416007.52 | 2386007.45 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-001 | [6 empty] | MASS CONST. AND CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region VIII | Tacloban City | 124227 | Rizal Central School | TACLOBAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1280537.69 | 1265362.68 | COMPLETED | 100% |  |  | ELEC2020-R8-TACLOBAN CITY-007 | [6 empty] | BELGES CONST. AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 314925 | Baungon NHS - Danatag Annex | BAUNGON | 1 | 1 | UPGRADING |  | 3140634.91 |  | COMPLETED | 100% |  |  | Elec2020-RX-Bukidnon-001 | 05-2020 | 2019-12-14 |  |  | 2020-09-14 | 2020-10-05 | METERKING, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 303972 | Malitbog Nat. Agr'I. HS | MALITBOG | 1 | 1 | UPGRADING |  | 4012505.61 |  | ONGOING | 90% | 2024-08-01 |  | Elec2020-RX-Bukidnon-002 | 08-2021 | 2021-08-11 | 2021-08-19 | 2021-08-31 | 2021-09-28 | 2021-10-12 | CCO Construction & Supply | Ongoing execution of MOA. Additional materials to be purchased. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region X | Bukidnon | 314921 | Dologon NHS - Kiharong Annex | MARAMAG | 3 | 1 |  |  | 1134744.87 |  | COMPLETED | 100% | 2021-04-02 |  | Elec2020-RX-Bukidnon-008 | 10-2020 | 2019-12-16 |  |  | 2020-11-25 | 2020-12-11 | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 314912 | Quezon National High School | QUEZON | 3 | 1 | UPGRADING |  | 1805170.52 |  | COMPLETED | 100% |  | 2021-04-29 | Elec2020-RX-Bukidnon-004 | 06-2020 | 2019-12-17 |  |  | 2020-09-14 | 2020-10-05 | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Bukidnon | 303979 | Salawagan NHS | QUEZON | 3 | 1 | UPGRADING |  | 4112740.21 |  | COMPLETED | 100% | June 1. 2021 | 2021-08-23 | Elec2020-RX-Bukidnon-006 | 11-2020 | 2019-12-18 |  |  |  |  | AN Escalante Construction, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 127991 | Fr. William F. Masterson, SJ., Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 |  |  | 2416291.82 |  | COMPLETED | 100% |  |  | Elec2020-RX-Cagayan de Oro City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 315409 | Iponan NHS - San Simon Annex | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | UPGRADING |  | 1825787.25 |  | COMPLETED | 100% |  |  | Elec2020-RX-Cagayan de Oro City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Cagayan de Oro City | 304121 | Mambuaya National High School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 |  |  | 1910588.72 |  | COMPLETED | 100% |  |  | Elec2020-RX-Cagayan de Oro City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 111422 | BALAY HA TAGNAUWAN TA BAYUNGON ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 |  |  | 588467.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 304131 | Gingoog City CNHS - BACKKISMI NHS Annex | GINGOOG CITY | 1 | 1 |  |  | 1972266.91 |  | COMPLETED | 100% |  |  | Elec2020-RX-Gingoog City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 315507 | Lunao National High School | GINGOOG CITY | 1 | 1 |  |  | 2174179.03 |  | COMPLETED | 100% |  |  | Elec2020-RX-Gingoog City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Gingoog City | 111804 | PIGNANAW SA BANUGAN ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 |  |  | 588467.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Iligan City | 304143 | Dalipuga National High School | ILIGAN CITY | 0 | 1 |  |  | 4684897.73 |  | COMPLETED | 100% |  |  | Elec2020-RX-Iligan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Iligan City | 128081 | Tambo Central School | ILIGAN CITY | 0 | 1 |  |  | 4936023.01 |  | REVERTED | 0% |  |  | Elec2020-RX-Iligan City-002 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304000 | Binuni-Demologan NHS | BACOLOD | 1 | 1 |  |  | 3433612.21 |  | COMPLETED | 100% |  |  | Elec2020-RX-Lanao del Norte-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1 | 1 |  |  | 2706081.19 |  | COMPLETED | 100% |  |  | Elec2020-RX-Lanao del Norte-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 304010 | Maigo NHS | MAIGO | 1 | 1 | UPGRADING |  | 2443266.05 |  | COMPLETED | 100% |  |  | Elec2020-RX-Lanao del Norte-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 |  |  | 3201586.1 |  | COMPLETED | 100% |  |  | Elec2020-RX-Lanao del Norte-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 126580 | Dalwangan ES | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 3489637.43 |  | COMPLETED | 100% |  |  | Elec2020-RX-Malaybalay City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 126547 | Managok CS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 2838644.05 |  | COMPLETED | 100% |  |  | Elec2020-RX-Malaybalay City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Malaybalay City | 303982 | San Martin Agro-Industrial NHS | CITY MALAYBALAY (Capital) | 2 | 1 | UPGRADING |  | 2443792.12 |  | COMPLETED | 100% | September 30, 2022 |  | Elec2020-RX-Malaybalay City-005 | [7 empty] | Complete installation onsite, FOR ENERGIZATION, with reinstallation issue due to error of BUSECO contractor, complied unlisted for BOM of BUSECO lacking materials by contractor. ready for submission of turn-on application | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Occidental | 304031 | Clarin NHS | CLARIN | 2 | 1 | UPGRADING |  | 4458236.13 | 4403098.14 | COMPLETED | 100% | 2022-11-04 |  | Elec2020-RX-Misamis Occidental-002 | [5 empty] | 2020-12-14 | RAKZ Builders | - For energization, lacking building permit, Occupancy permit. School has pending accounts payable to Electric Cooperative which cause delay to energization. informed to settle the account tru LSB 2022 funding. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | UPGRADING |  | 4464139.66 | 4375021.2 | COMPLETED | 100% | September 30, 2022 | 2022-10-03 | Elec2020-RX-Misamis Occidental-001 | [5 empty] | 2021-08-11 | ESL Milestone Builders INC. | -Waiting for the schools payment for previous billing. Subject for processing for energization. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304069 | Dr. Gerardo Sabal MNHS | CLAVERIA | 2 | 1 | UPGRADING |  | 5357548.51 | METER KING INC. | COMPLETED | 100% | December 28, 2020 |  | Elec2020-RX-Misamis Oriental-002 |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2 | 1 | UPGRADING |  | 5234970.56 | METER KING INC. | COMPLETED | 100% | December 28, 2020 |  |  |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304099 | Sta. Ana NHS | TAGOLOAN | 2 | 1 | UPGRADING |  | 5026839.59 | METER KING INC. | COMPLETED | 100% | December 28, 2020 |  | Elec2020-RX-Misamis Oriental-004 |  |  | January 24,2020 | February 3, 2020 | February 17,2020 | March 2, 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Misamis Oriental | 304074 | Kalingagan NHS | VILLANUEVA | 2 | 1 |  |  | 5229319.62 |  | REVERTED | 0% |  |  | Elec2020-RX-Misamis Oriental-008 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2020 | Region X | Ozamis City | 304166 | Montol National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 4233597.89 |  | COMPLETED | 100% |  |  | Elec2020-RX-Ozamis City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Ozamis City | 128164 | Ozamiz City Central School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 4472059.05 | DBB INDUSTRIAL SERVICES | COMPLETED | 100% | 2021-10-14 | - | Elec2020-RX-Ozamis City-002 | ELEC2020-RX-OZAMIZCITY-002 | 092-INFRA2021-001 | 2021-04-20 | 2021-04-28 | 2021-05-11 | 2021-05-21 | 44357 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Ozamis City | 304165 | San Antonio National High School | OZAMIS CITY | 2 | 1 | UPGRADING |  | 3847284.76 |  | COMPLETED | 100% |  |  | Elec2020-RX-Ozamis City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 304054 | Caniangan NHS | TANGUB CITY | 2 | 1 | UPGRADING |  | 3028449.97 | 2574180 | COMPLETED | 100% |  | 2/15/2021 | Elec2019-RX-Tangub City-001 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 2020-10-07 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 500750 | Maloro Integrated School | TANGUB CITY | 2 | 1 | UPGRADING |  | 1891404.49 | 1664430 | COMPLETED | 100% |  | 2/15/2021 | Elec2020-RX-Tangub City-005 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 2020-10-07 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 500752 | Pangabuan Integrated School | TANGUB CITY | 2 | 1 | UPGRADING |  | 3888115.7 |  | COMPLETED | 100% | April 2, 2020 | 2021-03-06 | Elec2020-RX-Tangub City-003 |  |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 44166 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Tangub City | 304050 | Santa Maria NHS | TANGUB CITY | 2 | 1 | UPGRADING |  | 4006045.9 | Rakz Buikders and Supply | COMPLETED | 100% | December 1, 2020 | 2021-03-06 | Elec2020-RX-Tangub City-004 |  |  | 2020-01-14 | 2020-01-24 | 2020-02-05 | 2020-06-12 | 44111 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City |  | Bagontaas NHS | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2581100.71 | 2045609.11 | COMPLETED | 100% | October 31, 2022 |  | Elec2020-RX-Valencia City-001 |  | April 19, 2021 | April 27, 2021 | May 10, 2021 | May 12, 2021 | 2021-05-14 | CCO Construction & Supply | Contractor partially complied with FIBECO's requirements for energization. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 501120 | Batangan CES | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2533608.48 | A N Escalante Construction Inc. | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RX-Valencia City-002 | Elec2020-RX-Valencia City-002 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 3240736.13 | A N Escalante Construction Inc. | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RX-Valencia City-008 | Elec2020-RX-Valencia City-008 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region X | Valencia City | 501124 | SUGOD ES | CITY OF VALENCIA | 4 | 1 | UPGRADING |  | 2574141.98 | A N Escalante Construction Inc. | COMPLETED | 100% | April 6, 2021 |  | Elec2020-RX-Valencia City-003 | Elec2020-RX-Valencia City-003 | 02-2020 | 2020-08-19 | 2020-08-25 | 2020-09-11 | 2020-10-21 | 44165 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128263 | Compostela Central Elementary School SPED Center | COMPOSTELA | 1 | 1 |  |  | 1560677.62 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128471 | Montevista CES | MONTEVISTA | 1 | 1 |  |  | 1523927.62 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 128353 | Maco CES | MACO | 2 | 1 |  |  | 1718201.62 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 315811 | New Leyte NHS | MACO | 2 | 1 |  |  | 1653399.34 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 304191 | Lorenzo S. Sarmiento Sr. High School | Mawab | 2 | 1 |  |  | 2310998.15 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Compostela Valley | 304178 | Bayabas NHS | NABUNTURAN (Capital) | 2 | 1 |  |  | 1705680.41 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Compostela Valley-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao City | 129684 | Batolusa ES | DAVAO CITY | 3 | 1 |  |  | 651274.85 |  | REVERTED | 0% |  |  | Elec2020-RXI-Davao City-005 | [8 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2020 | Region XI | Davao City | 304362 | J. V. Ferriols National High School | DAVAO CITY | 3 | 1 |  |  | 913273.2 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304234 | Baltazar Nicor Valenzuela NHS | KAPALONG | 1 | 1 |  |  | 7489046.81 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Norte-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304241 | Luna National High School | KAPALONG | 1 | 1 |  |  | 6751858.56 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Norte-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304242 | Mabantao National High School | KAPALONG | 1 | 1 |  |  | 4689161.56 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Norte-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2 | 1 |  |  | 4793017.8 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Norte-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Norte | 315903 | Anibongan NHS | CARMEN | 2 | 1 |  |  | 4692273.78 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Norte-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 316004 | SACUB National High School | HAGONOY | 0 | 1 |  |  | 1972000 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Sur-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304265 | Barayong National High School | MAGSAYSAY | 0 | 1 |  |  | 1855000 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Sur-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304284 | Lower Bala NHS | MAGSAYSAY | 0 | 1 |  |  | 2032000 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Sur-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao del Sur | 304278 | Inawayan National High School | SANTA CRUZ | 0 | 1 |  |  | 1885000 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao del Sur-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 128984 | Julian M. Turado Elementary School | MALITA | 0 | 1 |  |  | 2533221.94 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao Occidental-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% | 5.24 | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 129002 | Mana CES | MALITA | 0 | 1 |  |  | 1596018.47 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao Occidental-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 128978 | Mariano Peralta Elementary School | MALITA | 0 | 1 |  |  | 2284424.31 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao Occidental-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Occidental | 129103 | Basiawan CES | SANTA MARIA | 0 | 1 |  |  | 2386647.34 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Davao Occidental-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304299 | BACULIN NATIONAL HIGH SCHOOL | BAGANGA | 1 | 1 |  |  | 8618757.26 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304316 | DR. BEATO C. MACAYRA NATIONAL HIGH SCHOOL | BAGANGA | 1 | 1 |  |  | 8412844.35 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304333 | SAN LUIS NATIONAL HIGH SCHOOL | CARAGA | 1 | 1 |  |  | 7901843.39 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304324 | MANAY NATIONAL HIGH SCHOOL | MANAY | 1 | 1 |  |  | 8914736.56 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304336 | SIGABOY AGRI. VOCATIONAL HIGH SCHOOL | GOV. GENEROSO | 2 | 1 |  |  | 9768019.9 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Davao Oriental | 304332 | SAN ISIDRO NATIONAL HIGH SCHOOL | SAN ISIDRO | 2 | 1 |  |  | 9575438.29 |  | COMPLETED | 100% |  |  | ELECTRICAL 2020 - RXI - DAVAO ORIENTAL - 005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1 | 1 |  |  | 1297472.16 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Digos City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1 | 1 |  |  | 15116168.56 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Digos City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Panabo City |  | Cagangohan Vicente NHS | CITY OF PANABO | 2 | 1 |  |  | 4037769.03 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Panabo City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Panabo City | 316402 | San Vicente National High School | CITY OF PANABO | 2 | 1 |  |  | 3815398.53 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Panabo City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Tagum City | 305519 | Magdum NHS | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 468969.95 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Tagum City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Tagum City | 128780 | NUEVA FUERZA ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 326769.68 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Tagum City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Tagum City | 128781 | PAGSABANGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 697323.98 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Tagum City-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Tagum City | 128797 | SAN ISIDRO ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 687687.18 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Tagum City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XI | Tagum City | 128785 | UNION ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 |  |  | 635797.78 |  | COMPLETED | 100% |  |  | Elec2020-RXI-Tagum City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Cotabato City | 316907 | CCNHS - Annex (Don E. Sero Site) | COTABATO CITY | 1 | 1 | UPGRADING |  | 2837168.08 | 2837150.43 | COMPLETED | 100% | Dec. 4, 2020 | Dec. 4, 2020 | Elec2019-RXII-Kidapawan City-002 | 2020DIVINFRA-04 | January 4, 2020 | Jannuary 10, 2020 | January 20, 2020 | January 23, 2020 | Sept. 14, 2020 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 8424149.47 | Kupler Industries Inc. | COMPLETED | 100% |  |  | Elec2020-R12-GENSAN-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 6012095.58 | Kupler Industries Inc. | COMPLETED | 100% |  |  | Elec2020-R12-GENSAN-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 304637 | Tinagacan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 5964667.21 | Kupler Industries Inc. | COMPLETED | 100% |  |  | Elec2020-R12-GENSAN-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Memorial National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 |  |  | 2991847.12 |  | COMPLETED | 100% |  |  | Elec2019-RXII-Kidapawan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Koronadal City | 131406 | Koronadal Central I ES | CITY OF KORONADAL (Capital) | 2 | 1 |  |  | 4367788.32 |  | COMPLETED | 100% |  |  | Elec 2020-RXII-Koronadal City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304435 | Dualing High School | Aleosan | 1 | 1 |  |  | 3436815.02 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020-RXII-COTABATO-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 316502 | Katalicanan High School | Aleosan | 1 | 1 |  |  | 3449323.79 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020-RXII-COTABATO-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 1 | 1 |  |  | 3072490.97 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020-RXII-COTABATO-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304456 | Kisante National High School | Makilala | 2 | 1 |  |  | 3058840.97 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020-RXII-COTABATO-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | Makilala | 2 | 1 |  |  | 3056740.97 |  | COMPLETED | 100% |  |  | ELECTRIFICATION 2020-RXII-COTABATO-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304557 | Norala NHS | Norala | 2 | 1 |  |  | 6074475.44 |  | COMPLETED | 100% |  |  | Elec2020-R12-South Cotabato-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304568 | Sto. Niño NHS | SANTO NIÑO | 2 | 1 |  |  | 3274525.52 |  | COMPLETED | 100% |  |  | Elec2020-R12-South Cotabato-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 |  |  | 2881823.41 |  | COMPLETED | 100% |  |  | Elec2020-R12-South Cotabato-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO | 1 | 1 | UPGRADING |  | 6202395.91 |  | COMPLETED | 100% |  |  | Elec 2020-RXII-Sultan Kudarat-001 |  | July 23, 2021 | July 30, 2021 | August 11, 2021 |  |  | CCO Engineering Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305078 | Boliney NHS | BOLINEY | Lone | 1 | Upgrading of Electrical System | 1 | 2573112.03 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135003 | Patoc ES | BUCAY | Lone | 1 | Upgrading of Electrical System | 1 | 2700303.62 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | Lone | 1 | Upgrading of Electrical System | 1 | 2893061.4 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135036 | Manganip ES | DANGLAS | Lone | 1 | Upgrading of Electrical System | 1 | 2515595.69 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135038 | Nagaparan ES | DANGLAS | Lone | 1 | Upgrading of Electrical System | 1 | 2698048.96 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135064 | Lacub CS | LACUB | Lone | 1 | Upgrading of Electrical System | 1 | 2556039.77 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | Lone | 1 | Upgrading of Electrical System | 1 | 3035960.33 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135212 | Lagayan CS | LAGAYAN | Lone | 1 | Upgrading of Electrical System | 1 | 2755098.52 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | Lone | 1 | Upgrading of Electrical System | 1 | 2516605.59 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135046 | Licuan-Baay Central School | LICUAN-BAAY (LICUAN) | Lone | 1 | Upgrading of Electrical System | 1 | 2630426.29 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135105 | Luzong ES | LUBA | Lone | 1 | Upgrading of Electrical System | 1 | 2872212.71 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | Upgrading of Electrical System | 1 | 3403470.89 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | Lone | 1 | Upgrading of Electrical System | 1 | 3111511.93 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2644958.28 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2692850.72 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2886079.19 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | Upgrading of Electrical System | 1 | 2519635.29 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135144 | San Quintin CS | SAN QUINTIN | Lone | 1 | Upgrading of Electrical System | 1 | 2527039.76 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135110 | Supo ES | TUBO | Lone | 1 | Upgrading of Electrical System | 1 | 2614068.81 |  | COMPLETED | 100% | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2749682.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501104 | Tuquib Integrated School | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2683393.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135167 | Villaviciosa CS | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2833196.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135677 | Michael G. Angel Elementary School | SABLAN | Lone | 1 | Upgrading of Electrical System | 1 | 1592741.16 |  | COMPLETED | 100% | [10 empty] | Under 3rd re-procurement-Failed-For Rebidding | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135681 | Sablan CS | SABLAN | Lone | 1 | Upgrading of Electrical System | 1 | 1639418.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135726 | Becday Chasoras Lamsis ES (Baayan ES-Annex) | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1943884.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135725 | Dorencio ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1622500.76 |  | COMPLETED | 100% | [10 empty] | Under Procurement-(For Post Qualification Inspection) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135733 | Paoad ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 3327449.81 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135734 | Pontino ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1879395.18 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 305162 | Tublay School of Home Industries | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 6325754.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Ifugao | 135843 | Piwong ES | HINGYON | Lone | 1 | Upgrading of Electrical System | 1 | 2575936.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Kalinga | 136027 | Pasil Central School | PASIL | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2403614.63 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3026925.85 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136189 | Lias Elementary School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1544622.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1552384.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136192 | Lunas Primary School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1213229.36 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136200 | Banao Elementary School | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 2566648.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136201 | Bansa Elementary School | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 1923975.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136235 | Besao Central School | BESAO | Lone | 1 | Upgrading of Electrical System | 1 | 2943575.88 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | Lone | 1 | Upgrading of Electrical System | 1 | 3014573.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136314 | Bun-ayan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1111821.02 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136316 | Capinitan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1358370.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136319 | Gayang Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 961217.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136320 | Labbay Primary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1036764.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136322 | Legleg Primary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 961217.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1839246.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136331 | Tambingan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1117193.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | Upgrading of Electrical System | 1 | 1105334.54 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136344 | Antadao Elementary School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 951746.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136346 | Bangaan Elementary School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 1262778.22 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305234 | Bangaan National High School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 3308154.67 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136368 | Lenga Elementary School | TADIAN | Lone | 1 | Upgrading of Electrical System | 1 | 1662571.78 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136155 | Bado Dangwa Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3494237.89 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 319108 | Balong National High School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2929014.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2977893.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4594038.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 501971 | Lacnog Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2881584.45 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136007 | Laya East Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4036192.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3525638.47 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136108 | Namnama Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3466143.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 502124 | San Pablo Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2868127.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136112 | Tannubong Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2733038.77 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | Lone | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1433633.85 | 1103616.34 | COMPLETED | 100% | 2023-10-20 | 2022-10-20 | INFRA23-003-02 |  | 2023-07-07 | 2023-07-17 | 2023-07-27 | 2023-08-07 | SEPT 8, 2023 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.22 | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | Lone | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1566338.6089 | 1076466.49 | COMPLETED | 100% | 2023-10-20 | 2022-10-20 | INFRA23-003-01 |  | 2023-07-07 | 2023-07-17 | 2023-07-27 | 2023-08-07 | SEPT 8, 2023 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.22 | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1281098.66 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1328462.22 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1471012.92 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1328154.13 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 304777 | General Luna NHS | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3034314.86 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132153 | La Januza ES | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1447674.25 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132156 | Malinao Elementary Schol | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1269995.33 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132157 | Mam-on PS | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1263766.73 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1308743.46 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132160 | Suyangan ES | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1644323.14 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1771044.48 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1329571.32 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1271107.91 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1330680.43 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 317607 | Alegria National High School | SANTA MONICA (SAPAO) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1308743.46 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1301948.31 |  | COMPLETED | 100% | 2023-12-20 | 2023-11-29 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304813 | Bacuag National Agro-Industrial School | BACUAG | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1197266.56 | 1189766.47 | COMPLETED | 100% | 2023-01-21 | 2023-01-23 | 001-ELECTRIFICATION 2023-Caraga | 025-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | A N ESCALANTE CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1112775.27 | 1107766.21 | COMPLETED | 100% | 2023-01-18 | 2023-01-20 | 002-ELECTRIFICATION 2023-Caraga | 026-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304831 | Masgad National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1164972.94 | 1159944.78 | COMPLETED | 100% | 2023-01-18 | 2023-01-20 | 003-ELECTRIFICATION 2023-Caraga | 027-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304819 | Pili National High School | MALIMONO | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1196841.18 | 1191824.36 | COMPLETED | 100% | 2023-01-18 | 2023-01-20 | 004-ELECTRIFICATION 2023-Caraga | 028-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 317808 | Dakung Patag National High School | SISON | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1098526.93 | 1090371.12 | COMPLETED | 100% | 2023-01-21 | 2023-01-23 | 005-ELECTRIFICATION 2023-Caraga | 029-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | A N ESCALANTE CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -50 KVA Transformer | 1 | 1129402.34 | 1128350.96 | COMPLETED | 100% | 2023-01-18 | 2023-01-20 | 006-ELECTRIFICATION 2023-Caraga | 030-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2nd | 1 | Upgrading of Electrical System and Installation of 1 -37.5 KVA Transformer | 1 | 1096269.78 | 1128350.96 | COMPLETED | 100% | 2023-01-18 | 2023-01-20 | 007-ELECTRIFICATION 2023-Caraga | 031-2023 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-12-01 | 2023-12-04 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132601 | Bayabas Central Elementary School | BAYABAS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1637648.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132602 | Cabugo Elementary School | BAYABAS | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1450037.55 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | CARAGA | Surigao del Sur | 132685 | Gacub Elementary School | CARMEN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 1265305.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region I | Ilocos Sur | 300036 | Sugpon NHS | SUGPON | 2nd | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3187890.68 | 3124132.87 | COMPLETED | 100% | 2023-12-03 | 2024-04-24 | 2023-07-005-PB-Works |  | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-25 | 2023-09-04 | WWW.Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region II | Batanes | 102329 | Savidug Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1030909.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 821127.21 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region II | Cagayan | 300464 | Illuru National High School | RIZAL | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1429293.86 | 1406356.97 | COMPLETED | 100% | November 3, 2023 | 1900-03-25 | ELEC 2023-RII-Cagayan o1 | INFRA 2023-046 | May 8, 2023 | May 15, 2023 | May 29, 2023 |  | June 08, 2023 | WWW. Constrution |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137029 | Hiket Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620439.1 |  | COMPLETED | 100% | January 23, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT2-HIKET ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.24 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO | Lone | 1 | Provision of Solar-Powered Energy System | 1 | 2620965.54 |  | COMPLETED | 100% | January 16, 2024 | March 12, 2024 | PB06-004-SDONV-CY2023-BEFF-ELEC-LOT1-PIHIPI ES |  | June 22, 2023 |  | July 14, 2023 | August 18, 2023 | September 25, 2023 | Mighty Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.24 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 704044.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300823 | Mataas Na Kahoy National High School | GENERAL MAMERTO NATIVIDAD | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 731715.27 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. HS | LAUR | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 592087.44 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 371795.43 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 524063.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 342201 | Primitivo Kalaw Senior High School | BALETE | 3rd | 1 | Upgrading of Electrical System | 1 | 2998674.2 | 2994666.11 | COMPLETED | 100% | 2024-01-30 |  | Elec2023-RIVA-BatangasProvince-001 | Elec2023-RIVA-BatangasProvince-001 |  |  | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 307729 | Aplaya National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 594728.0229 | 582050.49 | COMPLETED | 100% | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 6.24 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 301094 | Calubcob I National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 656627.2153 | 645856.69 | COMPLETED | 100% | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 6.24 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 301160 | Tipas Integrated National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 747686.9341 | 727426.71 | COMPLETED | 100% | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Cavite | 301191 | Gen. Emilio Aguinaldo-Bailen Integrated School | GENERAL EMILIO AGUINALDO | 8th | 1 | Electrification of Unenergized School and Modernized of Electrical System of On-Grid Schools | 1 | 6290439.38 | 4898453.46 | COMPLETED | 100% | 2024-04-09 |  | Elec.2023RIVACavite-001 |  |  | 2023-08-01 | 2023-08-15 | 2023-10-03 | 2023-10-12 | 3CA BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109671 | Anilao ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3905532.01 |  | COMPLETED | 100% | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -005 | ELEC 20223-RIVA-LIPA CITY -005 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 501184 | Cumba-Quezon Integrated School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3921383.41 |  | COMPLETED | 100% | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -003 | ELEC 20223-RIVA-LIPA CITY -003 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 301494 | LodLod NHS | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 6673701.15 |  | COMPLETED | 100% | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -009 | ELEC 20223-RIVA-LIPA CITY -009 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109684 | Rizal Elementary School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3679809.77 |  | COMPLETED | 100% | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -002 | ELEC 20223-RIVA-LIPA CITY -002 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109648 | San Adriano MES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 4159841.48 |  | COMPLETED | 100% | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -004 | ELEC 20223-RIVA-LIPA CITY -004 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 501185 | San Jose Integrated School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 4944300.44 |  | COMPLETED | 100% | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -007 | ELEC 20223-RIVA-LIPA CITY -007 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109699 | San Salvador ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3957039.95 |  | COMPLETED | 100% | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -001 | ELEC 20223-RIVA-LIPA CITY -001 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | GS MOTAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 5322651.55 |  | COMPLETED | 100% | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -008 | ELEC 20223-RIVA-LIPA CITY -008 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3912335.9 |  | COMPLETED | 100% | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -006 | ELEC 20223-RIVA-LIPA CITY -006 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Quezon | 109085 | Sampaloc Elementary School (Main) | SAMPALOC | 1st | 1 | Modernization of Electrical System On-Grid Schools | 1 | 4627751.06 |  | COMPLETED | 100% | 2023-12-16 |  | ELEC 2023 - RIVA - QUEZON PROVINCE - 001 |  | 2023-05-26 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-19 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Tayabas City | 109243 | Tayabas East CS I | CITY OF TAYABAS | 1st | 1 | Modernization of Electrical System On-Grid Schools | 1 | 5108295.16 | 3958936.07 | ONGOING | 86% | 2024-03-26 |  | INFRA-2023-001 |  | 2023-07-25 | 2023-08-02 | 2023-08-14 | 2023-09-01 | 2023-09-28 | 3CA BUILDERS CORPORATION | Processing of MERALCO application | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 86% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1490439.83 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110743 | Diit Elementary School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1204739.14 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110745 | Matarawis Elementary School | AGUTAYA | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 679038.39 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110925 | Barangonan Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 571490.34 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110952 | New Colaylayan Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 1251132.87 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-B | Palawan | 110956 | Pical Elementary School | LINAPACAN | 1st | 1 | Provision of Solar-Powered Energy System | 1 | 803159.43 |  | COMPLETED | 100% | [10 empty] | Obligated | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Norte | 124614 | Sipaon ES | RIZAL | 1st | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1st | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2nd | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% | 5.24 | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3000000 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6000000 | 3171449.81 | COMPLETED | 100% | October, 2023 | 2023-09-27 | ELEC 2023-RV-CAMARINES NORTE -001 |  | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-22 | 2023-07-03 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Camarines Sur | 302003 | Victor Bernal Provincial High School | NABUA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2970850.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2999264.19 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302199 | Buenavista National High School, Castilla | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 1851079.02 | 1826821.12 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302202 | Dinapa National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 3132700.94 | 3097564.37 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302219 | Macalaya NHS | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 1802734.29 | 1799378.79 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302226 | Mayon National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2437103.64 | 2405176.47 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302227 | Milagrosa National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2246530.38 |  | ONGOING | 0% | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1st | 1 | Upgrading of Electrical System | 1 | 2408030.17 | 2381423.69 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302205 | Banuang Gurang National High School | DONSOL | 1st | 1 | Upgrading of Electrical System | 1 | 2038013.08 |  | ONGOING | 0% | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 310007 | Biton High School | MAGALLANES | 1st | 1 | Upgrading of Electrical System | 1 | 2785510.24 | 2771906.78 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 1609696.98 | 1585882.05 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region V | Sorsogon | 302180 | Bayasong National High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 2430063.83 |  | ONGOING | 0% | [10 empty] | obligated by December 2024; undergone 2 failed biddings | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2023 | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR | 1st | 1 | Upgrading of Electrical System | 1 | 8331388.84 | 8289992.3 | COMPLETED | 100% | 2024-05-27 | 2024-05-27 | 23-10-001 | 23-10-001 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2024-01-04 | 2024-01-10 | Araphil Construction and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 500182 | Habana Integrated School | Buruanga | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2863138.92 | 2313786.71 | COMPLETED | 100% | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114706 | Katipunan Elementary School | Buruanga | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2098033.87 | 1544660.91 | COMPLETED | 100% | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114764 | Bugasongan Elementary School | Lezo | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1937047.27 | 1441852.73 | COMPLETED | 100% | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114934 | Tagas Elementary School | Tangalan | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1940940.88 | 1439641.39 | COMPLETED | 100% | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Aklan | 114936 | Tangalan Elementary School | Tangalan | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2299400.96 | 1707060.99 | COMPLETED | 100% | 18-Sept-2023 |  | DEPED-RO6-D1-2023BEFF(ELEC0-20-2023 |  |  | 2023-05-03 | 2023-05-15 |  | 2023-06-28 | AGM SILVER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114974 | Borocboroc-Delima-Ipil ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1172908.53 | 950500.95 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114975 | Buenavista ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169478.37 | 945248.85 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114976 | Concepcion ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1205748.51 | 982013.55 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114977 | Maradiona Elementary School | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1265643.85 | 1024030.35 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114978 | Mojon ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1135093.88 | 929492.55 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114979 | Rombang ES | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1175619.87 | 955753.05 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 114980 | Sinaja-Salvacion Elementary School | BELISON | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1176139.57 | 955753.05 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-1 | R6-D2-BEFF2023-16-E-1 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115127 | Bulanao ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1178608.98 | 897475.43 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115128 | Codiong ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1139519.44 | 867884.33 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115131 | Lindero ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1263237.47 | 961589.48 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115133 | Paz ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169577.93 | 887611.73 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115134 | Pucio ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1180978.83 | 902407.28 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115137 | Taboc ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1169353.93 | 887611.73 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115138 | Tinigbas ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1106828.79 | 849612.23 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VI | Antique | 115140 | Union ES | LIBERTAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1302154.64 | 996597.53 | COMPLETED | 100% | 2024-09-09 | 2024-09-19 | R6-D2-BEFF2023-16-E-2 | R6-D2-BEFF2023-16-E-2 | 2023-09-05 | 2023-09-12 | 2023-09-26 | 2023-11-28 | 2024-01-02 | Benzen Construction | Completed as per POW and Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | bbm 2024 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA | 3rd | 1 | Upgrading of Electrical System | 1 | 4000000 | 3400799.37 | COMPLETED | 100% | 2024-04-14 | 2024-03-22 | [8 empty] | Has just inspected on Nov 22, 2023 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VII | Cebu | 500650 | Pasol-Pugalo IS | ALCOY | 2nd | 1 | Modernization of Electrical System On-grid Schools | 1 | 1353368.18 | 1348287.91 | COMPLETED | 100% | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-01 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2nd | 1 | Modernization of Electrical System On-grid Schools | 1 | 1480733.8 | 1476640.36 | COMPLETED | 100% | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-02 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 7th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1619602.19 | 1617873.04 | COMPLETED | 100% | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-03 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 120768 | Salangi Elementary School | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1442658.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1379400.25 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1895091.39 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1601371.47 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1669964.83 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122504 | Tugop Elementary School | GENERAL MACARTHUR | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2085746.9 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | TUBIGAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122509 | Gigoso Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2776436.97 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122512 | Malabag Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2086104.03 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122513 | Parena Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3052462.8 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1877521.63 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1877521.63 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-08-26 | NV&C CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2120060.66 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | MASLOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1878403.25 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122673 | Bagte Elementary School | QUINAPONDAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2262757.36 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122682 | Paco Elementary School | QUINAPONDAN | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1580167.51 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2149692.2 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-06-28 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122698 | Naparaan Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1741352.23 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-08-26 | NV&C CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Eastern Samar | 122703 | Talangdawan Elementary School | SALCEDO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1669316.14 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-04-11 | 2023-05-03 |  | 2023-05-26 | YFL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121877 | San Juan Elementary Shool | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 772727.25 |  | COMPLETED | 100% | 2023-11-04 | 2023-09-25 | CY2023-BEFF-ELEC-LOT0 | CY2023-BEFF-ELEC-LOT1 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-20 | 2023-06-30 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121879 | San Roque Elementary School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 918692.87 |  | COMPLETED | 100% | 2023-11-04 | 2023-10-16 | CY2023-BEFF-ELEC-LOT0 | CY2023-BEFF-ELEC-LOT1 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-20 | 2023-06-30 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121880 | Sta. Fe Central School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1987746.66 |  | COMPLETED | 100% | 2024-01-03 | 2023-12-01 | CY2023-BEFF-ELEC-LOT1 | CY2023-BEFF-ELEC-LOT2 | 2023-07-18 | 2023-05-03 | 2023-07-26 | 2023-08-17 | 2023-08-29 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2492793.04 |  | COMPLETED | 100% | 2023-11-22 | 2023-11-20 | CY2023-BEFF-ELEC-LOT2 | CY2023-BEFF-ELEC-LOT3 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-23 | VHITS D. G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121881 | Tibak Elementary School | SANTA FE | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 776428.1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4080740.11 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121520 | Calbasag Elementary School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 818344.49 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1471270.79 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte |  | JULITA SENIOR HIGH SCHOOL | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1526774.3 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121530 | Sto. Nino Elementary School | JULITA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 721700.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2249725.59 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313332 | Buracan National High School | LA PAZ | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1371927.76 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121625 | Palale Elementary School | MACARTHUR | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1269846.62 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1220104.17 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313343 | Macalpi-ay National High School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1426504.68 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 313330 | Manaybanay National High School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1727293.8 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121825 | Pastrana Central School | PASTRANA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2010412.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121961 | Capahuan ES | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 777292.87 |  | COMPLETED | 100% | 2023-10-28 |  | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-23 |  |  |  | Realigned from Himokilan ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121912 | Guingauan Elementary School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 699542.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121916 | San Pablo Elementary School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 725225.28 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121917 | Tabontabon Central School | TABONTABON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2156995.46 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2831680.38 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121961 | Tunga Central School | TUNGA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2291156.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121716 | Calunangan Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 833971.87 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121721 | Casilda Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1253532.73 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303393 | Libas National High School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1267471.33 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121725 | Lundag Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 890533.2 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121727 | Mahalit Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 768212.5 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121732 | Puerto Bello Elementary School | MERIDA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1030561.74 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121403 | Capudlosan Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 869012.14 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121408 | Hindang Central School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1786409.06 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2134736.69 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121411 | Mabagon Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 884879.6 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121413 | Tabok Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 917163.92 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 121414 | Tagbibi Elementary School | HINDANG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 885977.15 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Leyte | 303399 | MAHAPLAG NHS-UPPERS | MAHAPLAG | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2824737.5 | 2774367.1 | COMPLETED | 100% | 2023-12-27 |  | 2023-07-18 | N/A | 2023-07-26 | 2023-08-16 | 2023-08-22 | HD GOLDEN BUILDERS & SUPPLY | Re-bid |  | Realigned from Himokilan ES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4489207.93 |  | COMPLETED | 100% |  | 2023-11-29 | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-05-18 | 2023-05-30 |  | 2023-08-01 | HD GOLDEN BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Northern Samar | 313622 | Magtaon NHS | MAPANAS | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2135962.33 |  | COMPLETED | 100% |  |  | BEFF CY 2023 ELECTRIFICATION |  |  | 2023-10-06 | 2023-10-18 | 2023-10-25 | 2023-11-03 | J. CUSTORIO CONSTRUCTION & SUPPLY | rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123289 | Guin-ansan Elementary School | ALMAGRO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3312421.71 |  | COMPLETED | 100% | ############# | 2023-09-08 | CY2023BEFFELECLOT1 | 2023-014 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123292 | Lunang I Elementary School | ALMAGRO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3498488.78 |  | COMPLETED | 100% | ############# | 2023-09-08 | CY2023BEFFELECLOT2 | 2023-015 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 313713 | Villahermosa Integrated School | PAGSANGHAN | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2053376.78 |  | COMPLETED | 100% | ############# | 2023-09-21 | CY2023BEFFELECLOT3 | 2023-016 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Samar (Western Samar) | 123593 | Jiabong Central Elementary School | JIABONG | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2745446.97 |  | COMPLETED | 100% | ############# | 2023-09-21 | CY2023BEFFELECLOT4 | 2023-017 | 2023-04-06 | 2023-04-14 | 2023-04-28 | 2023-05-23 | 2023-06-19 | 3CA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2023 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Southern Leyte | 303465 | LIMASAWA NATIONAL HIGH SCHOOL | LIMASAWA | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3615152.31 | 3437262.47 | COMPLETED | 100% | 2024-02-16 | Not yet completed | CY2023-ELECTRIFICATION-L1 | CY2023-ELECTRIFICATION-L1 | 2023-06-20 | 2023-06-29 | 2023-07-11 |  | 2023-10-19 | Victoria Development and Ventures Corp. | Contract Expired | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2575774.71 | 2449982.31 | COMPLETED | 100% | 2024-01-17 | Not yet completed | CY2023-ELECTRIFICATION-L2 | CY2023-ELECTRIFICATION-L2 | 2023-06-20 | 2023-06-29 | 2023-07-11 |  | 2023-10-19 | Victoria Development and Ventures Corp. | Contract Expired | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | Lone | 1 | Upgrading of Electrical System (Underground System) | 1 | 2353935.51 | 2232071.69 | COMPLETED | 100% | [9 empty] | Elettro Engineering Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region X | Misamis Occidental | 304051 | Sapang Dalaga National High School | SAPANG DALAGA | 1st | 1 | Energization and Upgrading of Electrical System | 1 | 2196264.4 | 2172379.71 | COMPLETED | 100% | 2024-01-17 |  | ELEC 2023-REGION X-MISAMIS OCCIDENTAL-001 | 009-2023 | 2023-05-20 | 2023-05-29 | 2023-06-13 | 2023-08-08 | 2023-09-12 | ESL Milestone Builders and Supply, Inc. | Turned Over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 5.24 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 6000000 | 5991584.84 | COMPLETED | 100% | 2024-05-12 |  | G2PB - Electrification-2023-001 | 4610718 | 2023-11-05 | 2023-11-20 | 2023-12-04 | 2024-01-03 | 2024-01-18 | Meter King Inc. | Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region XI | Mati City | 305680 | City of Mati National High School | CITY OF MATI (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 5726197.75 | 5692850.92 | COMPLETED | 100% | June 10,2024 | June 10,2024 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | September 06, 2023 | AN Escalante Group Of Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2023 | Region XI | Mati City | 304313 | Dawan NHS | CITY OF MATI (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 6181854.59 | 6152414.48 | COMPLETED | 100% | June 10,2024 | June 10,2024 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | September 06, 2023 | AN Escalante Group Of Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 4977704.97 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Apayao | 305122 | Pio Dalim Memorial SAT Main | Calanasan | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4525076.03 |  | COMPLETED | 100% |  |  | 2023-ITB-011 |  | August 12,2024 |  | August 19,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 30% | 70% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | CAR | Baguio City | 340055 | BAGUIO CITY NATIONAL SCIENCE HIGHSCHOOL | BAGUIO CITY | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 17088567.41 |  | COMPLETED | 100% | [10 empty] | Suspemded due to Transformer Issue (BENECO cannot still provide) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Benguet | 305143 | Gov. Bado Dangwa Agro-Industrial School | KAPANGAN | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 6325754.86 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Ifugao | 135799 | Namal ES | ASIPULO | Lone | 1 | Upgrading of Electrical System | 1 | 6148782.53 | 6144549.31 | COMPLETED | 100% | 2024-10-12 |  |  | 2024-05 | 2023-11-28 | 2023-12-05 | 2023-12-18 | 2024-01-02 | 2024-06-08 | MSMV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Kalinga | 136169 | BAGTAYAN ELEMENTARY SCHOOL | PASIL | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 2562806.65 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Mt. Province | 136202 | BAUKO CENTRAL SCHOOL | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 2924532.38 | 2820821 | COMPLETED | 100% | 2024-08-02 | August 2, 2024 | INFRA-2023-006 | INFRA-2023-006 | 11/25/23 | 2023-04-12 | 12/18/2023 | 2024-08-01 | 2024-07-03 | DMYA Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Tabuk City | 136101 | MADOPDOP ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4524148.42 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Agusan del Norte | 131506 | Abilan ES | BUENAVISTA | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3880778.58 |  | ONGOING | 5% | [10 empty] | realigned from Mateo B. Abao CES realigned to Abilan ES | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 5% | 0% |  |  | SOLAR |  |  | ONGOING
ELECTRIFICATION 2024 | CARAGA | Bayugan City | 131632 | Maygatasan Elementary School | CITY OF BAYUGAN | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1645288.94 |  | ONGOING | 95% | [10 empty] | Realigned from Noli CES to Maygatasan ES | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | CARAGA | Bislig City | 304867 | Mone National High School | CITY OF BISLIG | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3867121.91 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Cabadbaran City | 131529 | Antonio C Dagani Central Elementary School | CITY OF CABADBARAN | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2439348.64 | 2157571.43 | COMPLETED | 100% | 2024-09-06 |  | 10312261 | 10312261 | 2023-11-13 | 2023-11-09 | 2023-12-06 | 2024-05-24 | 2024-06-06 | MCLA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Dinagat Island | 132501 | Omay Edradan Elementary School | Basilisa | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2494859.88 | 1904114.72 | COMPLETED | 100% | 2024-08-08 | 2024-07-31 | 2023-006-1 |  | 2023-12-05 | 2023-12-11 | 2024-01-03 | 2024-01-11 | 2024-06-10 | MCLA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Dinagat Island | 132492 | F. S. Matugas Elementary School | BASILISA (RIZAL) | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2504295.38 | 1924729.44 | COMPLETED | 100% | 2024-08-09 | 2024-07-31 | 2023-006-2 |  | 2023-12-05 | 2023-12-11 | 2024-01-03 | 2024-01-11 | 2024-06-11 | MCLA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Siargao | 132129 | Don E.Navarro MS | Dapa | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2511786.84 | 2496984.68 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Siargao | 132236 | Pamosaingan ES | Socorro | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2515687.73 | 2509599.6 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Surigao City | 304806 | Zaragoza National High School | SURIGAO CITY (Capital) | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2593727.4 | 1894155.62 | COMPLETED | 100% | Septemebr 28, 2024 |  | 2023-11-574 | FY-2023-INFRA-012 | 2023-12-12 | 2023-12-18 | 2024-01-05 | 2024-07-26 | 2024-08-09 | MLCA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Surigao del Norte | 501680 | Hinatuan Integrated School | GIGAQUIT | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3890654.59 | 3887576.96 | COMPLETED | 100% | 2024-07-12 |  | 2024-(001)- ELECTRIFICATION-CARAGA | INFRA004-2024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2024-05-09 | 2024-05-13 | RJB CONSTRUCTION AND SUPPLY | With Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Surigao del Sur | 132647 | Cempron Elementary School | CAGWAIT | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2580764.37 |  | COMPLETED | 100% | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Surigao del Sur | 132734 | Hinatuan North Central Elementary School | HINATUAN | 2nd | 1 | Upgrading of Electrical System | 1 | 2633549.54 |  | COMPLETED | 100% | [10 empty] | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CARAGA | Tandag City | 136972 | Pag-asa Tribal Community Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3850173.23 | 3049107.82 | COMPLETED | 100% | 2024-09-10 |  | 2023-11-202 |  | 2023-11-29 | 2023-12-07 | 2023-12-27 | 2024-01-10 | 2024-07-11 | HPS Electrical Engineering Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | NCR | City of San Juan | 136749 | Kabayanan ES | CITY OF SAN JUAN | Lone | 1 | Upgrading of Electrical System | 1 | 3995816.45 | 3882858.23 | COMPLETED | 100% | 2025-05-09 | 2025-04-25 | ELEC2024-NCR-SAN JUAN-001 | INFRA2024-003 | 2024-06-19 | 2024-06-27 | 2024-07-09 | 2024-10-22 | 2024-12-20 | Sherf Builders Corp. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Las Piñas City | 320303 | Las Piñas National High School - Gatchalian Annex | CITY OF LAS PIÑAS | Lone | 1 | Upgrading of Electrical System | 1 | 2190261.83 | 2183370.17 | COMPLETED | 100% | 2024-12-25 |  | 2024-06-I-03 | 2024-06-I-03 | 27/06/2024 | 2024-07-05 | 2024-07-18 | 2024-08-01 | 2024-08-27 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1st | 1 | Upgrading of Electrical System | 1 | 6771638.93 | 6042143.96 | ONGOING | 50% | 2025-07-27 |  | PB-SDO-MKT-2024-007 | SDO-MKT-25-005 | November 9, 2024 | November 15, 2024 | November 27, 2024 | December 2, 2024 | 2025-02-27 | Zaneya Builders & Supply | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 50% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2nd | 1 | Upgrading of Electrical System | 1 | 7896898.69 | 7105888.76 | ONGOING | 50% | 2025-08-26 |  | PB-SDO-MKT-2024-006 | SDO-MKT-25-004 | November 9, 2024 | November 15, 2024 | November 27, 2024 | December 2, 2024 | 2025-02-27 | Zaneya Builders & Supply | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 50% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | Lone | 1 | Electrical Service Entrance Upgrade | 1 | 13000000 | 12940519.92 | ONGOING | 70% |  |  |  | 2024-infra-08-0001 | 2024-06-28 | 2024-07-05 | 2024-07-19 | 2024-07-25 | 2024-07-29 | MRRM Trading and Construction | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 70% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Mandaluyong City | 136656 | Dona Basilica Yangco ES | CITY OF MANDALUYONG | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2583423.88 | 2544672.53 | ONGOING | 95% | 2025-05-06 | 2025-05-06 | ELEC-2024-MANDALUYONG-001 | OSEC-NCR-24-7842 | 2024-10-24 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2025-01-06 | E. AGLAHI URBAN BUILDERS | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1st | 1 | Upgrading of Electrical System | 1 | 1577374.98 | 1527148.22 | COMPLETED | 100% | 2024-12-02 | 2024-12-17 |  |  | 2024-05-08 | 2024-05-18 | 2024-05-28 | 2024-06-25 | 2024-09-02 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | Upgrading of Electrical System | 1 | 7230312.11 | 7185247.61 | ONGOING | 95% | 2025-03-02 |  |  |  | 2024-05-08 | 2024-05-18 | 2024-05-28 | 2024-06-25 | 2024-09-02 | AYZARIS CORPORATION | Currently applied a load upgrade in Meralco. Subject for final inspection and punchlisting | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4th | 1 | Upgrading of Electrical System | 1 | 7110414.41 | 7096791.7 | ONGOING | 65% | June, 2025 | [8 empty] | JKK CONSTRUCTION SERVICES | dates of NOA, Contract and NTP will be revised due to late issunace of SARO and obligation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 65% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | Lone | 1 | Upgrading of Electrical System | 1 | 22251970.63 | 22199967.28 | COMPLETED | 100% | 2025-02-07 |  | N/A | # 07-02 | 2024-05-08 | 2024-05-16 | 2024-05-29 | 2024-06-14 | 2024-07-31 | Marakesh Enterprise | Date Started: 8/20/24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | Lone | 1 | Upgrading of Electrical System | 1 | 5240523.38 | 5214577.9 | ONGOING | 98% | 2024-10-31 |  | BAC-PB-2024-2 | BAC-PB-2024-2 | 2024-05-16 | 2024-06-04 | 2024-06-18 | 2024-06-25 | 2024-07-22 | MRRM Trading and Construction | With approved Time Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 98% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Paranaque City | 136762 | Don Galo Elementary School | CITY OF PARAÑAQUE | 1st | 1 | Upgrading of Electrical System | 1 | 3808280.23 | 3758684.08 | COMPLETED | 100% | 2025-05-05 | 2025-05-02 | 038B | 038B | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-05 | 2025-02-10 | Open Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 60% | 40% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | Lone | 1 | Upgrading of Electrical System | 1 | 1850561.24 | 1280750.73 | COMPLETED | 100% | 2024-10-27 |  | SDOPC 2024-5-008-PB | CA-2024-08-012 | 2024-05-02 | 2024-05-10 | 2024-05-28 | 2024-06-13 | 2024-08-07 | Open Builders | on going construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 10061720.23 | 9995257.7 | COMPLETED | 100% | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 4) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136564 | Pura V. Kalaw ES | QUEZON CITY | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 11242015.08 | 11210528.83 | COMPLETED | 100% | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136583 | Aurora A. Quezon ES | QUEZON CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 8426070.39 | 8412019.86 | COMPLETED | 100% | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136573 | Pinyahan ES | QUEZON CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 9221987.36 | 9175352.54 | COMPLETED | 100% | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 10806050.43 | 10589934.13 | ONGOING | 35% | 2025-01-13 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 5) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-07-17 | E.M. CUERPO, INC. | mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 35% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Quezon City | 136519 | Lucas R. Pascual Memorial Elementary School | QUEZON CITY | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 9211007.25 | 9026791.12 | ONGOING | 50% | 2025-01-13 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 5) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-07-17 | E.M. CUERPO, INC. | mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 50% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Quezon City | 136513 | New Era ES | QUEZON CITY | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 8400050.23 | 8388831.82 | COMPLETED | 100% | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 4) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Taguig City and Pateros | 136879 | Ususan Elementary School | TAGUIG CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2508500.44 | 2486910.13 | COMPLETED | 100% |  |  |  | DTP-CY2024-INFRA-001 | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-31 | Sherf Builders Corp. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 95% | 5% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Taguig City and Pateros | 320612 | Gat. Andres Bonifacio High School | TAGUIG CITY | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4579971.25 | 4558777.19 | COMPLETED | 100% |  |  |  | DTP-CY2024-INFRA-001 | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-31 | ST. GABRIEL BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Valenzuela City | 136823 | Constantino Elementary School | CITY OF VALENZUELA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5169323.52 | 5139323 | ONGOING | 40% |  |  |  | SDO-VAL-PB-BEFF-ELECT-2024-12-0003 | Sept. 20, 2024 | Sept. 30, 2024 | Oct . 14, 2024 | Oct. 17, 2024 | Dec. 27, 2024 | Hawkstow Cosntruction and Development | 120 CD | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 40% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Valenzuela City | 136817 | Paso de Blas Elementary School | CITY OF VALENZUELA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 7579323.14 | 7549323 | ONGOING | 40% |  |  |  | SDO-VAL-PB-BEFF-ELECT-2024-12-0003 | Sept. 20, 2024 | Sept. 30, 2024 | Oct . 14, 2024 | Oct. 17, 2024 | Dec. 27, 2024 | Hawkstow Cosntruction and Development | 120 CD | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 40% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region I | Alaminos City | 300240 | Polo National High School | CITY OF ALAMINOS | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2987931.48 | COMPLETED | 100% | 2025-04-21 | 2025-04-15 | PB-infra- 2024-12 |  | 2024-07-08 | 2024-07-17 | 2024-07-29 | 2024-08-06 | 2024-12-23 | MANIMELDS CONSTRUCTION & IRON WORKS | for punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 300250 | San Jose NHS (Anda) | ANDA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2814072.69 | COMPLETED | 100% |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 |  | 3CA Builders Corporation | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 500366 | Tampac IS | AGUILAR | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1490191.68 | ONGOING | 95% |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 |  | Caixia Construction | With SARO, Waiting for NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region I | Pangasinan I, Lingayen | 101422 | Calasiao Central School | CALASIAO | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1490287.22 | ONGOING | 90% |  |  | 2024-06-002-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 |  |  | ILS Power Engineering Services and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 80% | 10% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500000 | 1448491.14 | COMPLETED | 100% | 2024-10-18 | 2024-09-20 | CSFLU-INFRA-03-01-2024 | CSFLU-INFRA-03-01-2024 | 2024-04-11 | 2024-04-19 | 2024-05-02 | 2024-05-08 | 2024-06-13 | AE Square Enterprises | With approved modification of school recipient from Apolonia es to Paso De Blas es and Constantino es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | Lone | 1 | Energization of Electrical System (Underground System) | 1 | 1943508.93 |  | not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | not yet started
ELECTRIFICATION 2024 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2336832.19 | COMPLETED | 100% | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1429293.86 | 1115481.12 | COMPLETED | 100% | SEPTEMBER 25, 2024 |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2023-124-LOT 1 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 13, 20224 | MAY 29, 2024 | CONSTUIRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 689117.88 | 688117.88 | ONGOING | 95% |  |  | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | INFRA 2024-075 | JULY 9, 2024 | JULY 15, 2024 | JULY 15, 2024 | JULY 16, 2024 |  | GCPK Construction & Supply | for final inspection | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 65% | 30% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | ONGOING | 30% |  |  | UPGRADING OF ELECTRICAL SYSTEM (OVERHEAD SYSTEM) OF CAUAYAN CITY NATIONAL HIGH SCHOOL | CW-003 S. 2025 | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 |  |  | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 5% | 25% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region II | City of Ilagan | 103384 | Aggassian Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 3071337.63 | Completed | 100% | 2024-10-03 |  | 10398574 | INF-2024-01 | 2023-12-04 | 2023-12-13 | 2023-12-27 | 2024-12-29 | 2024-06-24 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | ENERGIZATION | BBM 2025 ONGRID |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 501434 | CUBAG INTEGRATED SCHOOL | CABAGAN | 1st | 1 | Upgrading Electrical System On Grid Schools | 1 | 1670752.61 | 1649364.22 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 103536 | BISAG ELEMENTARY SCHOOL | PALANAN | 2nd | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 2338294.94 | 2335479.45 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | SOLAR | BBM 2025 SOLAR |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 306115 | LFG DIAMANTINA NATIONAL HIGH SCHOOL | CABATUAN | 3rd | 1 | Upgrading Electrical System On Grid Schools | 1 | 1563047.81 | 1535336.98 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 501316 | Taliktik Integrated School | CORDON | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2383413.13 | 2368626.76 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | ENERGIZATION | BBM 2025 ONGRID |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 500084 | MACANIAO INTEGRATED SCHOOL | ANGADANAN | 5th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1273865.41 | 1253721.61 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | Completed
ELECTRIFICATION 2024 | Region II | Isabela | 500022 | RIZAL INTEGRATED SCHOOL | SAN GUILLERMO | 6th | 1 | Upgrading Electrical System On Grid Schools | 1 | 1690299.17 | 1679845.08 | Completed | 100% | 2024-08-20 |  |  | 2024-0505 | November 11,2023 | November 20,2023 | 2023-12-05 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | Completed
ELECTRIFICATION 2024 | Region II | Nueva Vizcaya | 104205 | Mandunot ES | ALFONSO CASTANEDA | Lone | 1 | Provision of Solar-Powered Energy System to Schools Off-Grid | 1 | 4053012.33 | 4048810.29 | COMPLETED | 100% | November 10, 2024 |  | PB03-002-SDONV-CY2024EP |  | March 19, 2024 | March 18, 2024 | April 15, 2024 | April 26, 2024 | June 13, 2024 | Mighty Construction | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region II | Quirino | 300655 | Burgos NHS | CABARROGUIS (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 | 2547939.16 | COMPLETED | 100% | 2024-08-06 |  | ELEC-2024-REGION II - QUIRINO - 002 | 09-02-16-2024 | 2024-02-16 | 2024-02-23 | 2024-03-06 | 2024-03-15 | 2024-06-07 | GCPK Construction & Supply | with Time Extension / awaiting for the installation of Transformer from the Local Cooperative | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 75% | 25% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region II | Santiago City | 103835 | Baluarte ES | CITY OF SANTIAGO | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | not yet started | 0% | [10 empty] | alredy submitted RTA to CO; Awaiting downloading of subaro | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | not yet started
ELECTRIFICATION 2024 | Region II | Tuguegarao City | 300668 | Cagayan National High School - Junior HS | TUGUEGARAO CITY(Capital) | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3077073.36 |  | Under Procurement | 0% | [10 empty] | no subaro yet; for request of realignment | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | Under Procurement
ELECTRIFICATION 2024 | Region III | Aurora | 104408 | Anacleto V. Mijares ES | BALER (Capital) | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2929449.51 | 2922317.53 | COMPLETED | 100% | 2024-10-25 | 2024-10-23 | 23-10-472 | SGOD-INFRA-97-1 | May 30,2024 | 2024-06-07 | June 19,2024 | August 9,2024 | 2024-08-14 | A. DELA CRUZ BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Aurora | 104422 | Calantas ES | CASIGURAN | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2010000 | 2005382.11 | COMPLETED | 100% | 2024-10-25 | 2024-10-23 | 23-10472 | SGOD-INFRA-97-2 | May 30,2024 | 2024-06-07 | June 19,2024 | August 9,2024 | 2024-08-14 | A. DELA CRUZ BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Balanga City | 104560 | G.L. David Memorial Elementary School | CITY OF BALANGA (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 2467323.4 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1219998.48 | 993809.21 | COMPLETED | 100% | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 104683 | Pablo R. Roman ES | ORION | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2627403.15 | 2139885.82 | COMPLETED | 100% | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 104593 | San Benito ES | DINALUPIHAN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2491679.75 | 2030190.71 | COMPLETED | 100% | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300768 | Calumpit NHS (San Marcos NHS) | CALUMPIT | 1st | 1 | Upgrading of Electrical System | 1 | 5389963.56 | 3937612.4 | COMPLETED | 100% | 2025-04-27 |  | PB-24-006 | PB-24-07-012 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 306708 | Maronquillo National High School | SAN RAFAEL | 3rd | 1 | Upgrading of Electrical System | 1 | 3885106.25 | 3843446.74 | COMPLETED | 100% | 2025-04-27 |  | PB-24-003 | PB-24-07-014 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300763 | Obando NHS | OBANDO | 4th | 1 | Upgrading of Electrical System | 1 | 3787938.56 | 3735985.38 | COMPLETED | 100% | 2025-03-09 |  | PB-24-005 | PB-24-05-009 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-06-05 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300728 | Bunsuran NHS | PANDI | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4759527.1 | 4721263.03 | COMPLETED | 100% | 2025-04-27 |  | PB-24-007 | PB-24-07-013 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Malolos City | 104877 | Santor ES | CITY OF MALOLOS (Capital) | 1st | 1 | Upgrading of Electrical System | 1 | 709634.11 | 709634.11 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Meycauayan City | 500965 | Saluysoy Integrated School | CITY OF MEYCAUAYAN | 3rd | 1 | Upgrading of Electrical System | 1 | 7000000 | 6816900.88 | ONGOING | 80% | 2024-08-30 |  | 2023-002-Infra |  |  |  | 2023-12-15 |  | 2024-06-25 | 3CA BUILDERS CORPORATION | With Time Extension Request | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 80% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 305948 | Simimbaan High School | CUYAPO | 1st | 1 | Installation of Solar Panels | 1 | 997275.75 | 995605.71 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 300870 | Llanera National High School | LLANERA | 2nd | 1 | Installation of Solar Panels | 1 | 1254762.94 | 1250915.91 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 306813 | Bongabon NHS Annex (Vega HS) | BONGABON | 3rd | 1 | Installation of Solar Panels | 1 | 997275.75 | 995605.71 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 305811 | St. Joseph National High School | CABIAO | 4th | 1 | Installation of Solar Panels | 1 | 961963.82 | 960293.78 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Olongapo City | 301051 | Olongapo City National High School | OLONGAPO CITY | 1st | 1 | Upgrading of Electrical System | 1 | 10000000 |  | COMPLETED | 100% |  |  | 2024-06-208 | 2024-06-208 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-01 | 2024-09-18 | EIRISH BUILDERS AND SUPPLY INC. | Awaiting SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Tarlac | 300996 | Tarlac National High School | CITY OF TARLAC (Capital) | 2nd | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 5072444.44 | 5032432.46 | ONGOING | 0% |  |  |  |  | August 23, 2024 | August 30, 2024 | September 12, 2024 | September 17, 2024 |  | ARESBI CONSTRUCTION | Suspended, with conflict with the protocols of electric cooperatives | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region III | Tarlac City | 300971 | Tibag HS | CITY OF TARLAC (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2667884.73 | 2507500 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Zambales | 106866 | Sta. Maria Elementary School | CASTILLEJOS | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1211806.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Zambales | 106896 | San Salvador Elementary School | MASINLOC | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1766126.9 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Antipolo City | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2nd | 1 | Upgrading of Electrical System (Underground System) | 1 | 13988227.07 | 13970000 | ONGOING | 0% | 2025-03-14 |  |  | BEFF-ANT-2024-03 | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-07 | 2024-10-15 | Hawkstow Const. and Devt. | SUSPENDED, Awaiting Electrification Permit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Bacoor City | 107878 | Bayanan Elementary School | BACOOR | 2nd | 1 | Modernization of Electrical Systems of On-Grid Schools | 1 | 8852615.57 | 8835874.64 | ONGOING | 85% | 2024-11-29 |  | ELEC2023-0001 | 2023-0018 | November 30,2023 | 2023-12-07 | 2023-12-20 | 2023-12-27 | 2024-06-03 | MRRM TRADING AND CONSTRUCTION | Suspended due to Meralco | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 70% | 15% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 342206 | Lian Senior High School | LIAN | 1st | 1 | Upgrading of Electrical System | 1 | 12024847.46 | 11956875.42 | ONGOING | 60% |  |  | ELEC 2024 - RIVA - BATANGAS - 003 | ELEC 2024 - RIVA - BATANGAS - 003 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Marakesh Enterprises | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 60% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301115 | Anselmo A. Sandoval Memorial NHS | MABINI | 2nd | 1 | Upgrading of Electrical System | 1 | 11288429.5 | 11200000 | ONGOING | 60% |  |  | ELEC 2024 - RIVA - BATANGAS - 002 | ELEC 2024 - RIVA - BATANGAS - 002 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Botey Construction | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 60% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301149 | Sta. Teresita NHS | STA. TERESITA | 3rd | 1 | Upgrading of Electrical System | 1 | 10770775.87 | 10702805.3 | ONGOING | 60% |  |  | ELEC 2024 - RIVA - BATANGAS - 001 | ELEC 2024 - RIVA - BATANGAS - 001 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Marakesh Enterprises | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 60% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301098 | Dagatan NHS | TAYSAN | 4th | 1 | Upgrading of Electrical System | 1 | 13317186 | 13250000 | ONGOING | 80% |  |  | ELEC 2024 - RIVA - BATANGAS - 004 | ELEC 2024 - RIVA - BATANGAS - 004 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Botey Construction | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 80% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas City | 109615 | Jose C. Pastor MES | BATANGAS CITY (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical System of On-Grid Schools | 1 | 7208674.94 | 7000000 | ONGOING | 88.75% | 2024-10-07 |  | 2023-10-003-PB-INFRA | 05-001-2024 INFRA | 2023-10-24 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-05-31 | Botey Construction | with Suspension Order | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 88.75% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Binan City | 108213 | Biñan CES (Doña Aurora ES) | CITY OF BIÑAN | 1st | 1 | Upgrading of Electrical System | 1 | 16787346.89 | 16737346.89 | ONGOING | 96% | 2025-01-19 |  | R4A-BNN-2023-04 | R4A-BNN-2023-04 | December 27, 2023 - January 16, 2024 | 2024-01-04 | 2024-01-16 | 2024-02-07 | 2024-05-24 | Marakesh Enterprises |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 96% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Calamba City | 109815 | E. Barretto Sr. ES | CITY OF CALAMBA | Lone | 1 | Upgrading of Electrical Facilities | 1 | 4500000 | 4489385.57 | ONGOING | 20% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 20% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 108016 | AGUINALDO ELEMENTARY SCHOOL | KAWIT | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6978426.71 | 6955504.45 | ONGOING | 55% | [10 empty] | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 55% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107892 | Bancal Elementary School | CARMONA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 7475122.6 | 7443971.23 | ONGOING | 55% |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 55% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107860 | Loma Elementary School | AMADEO | 7th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6984796.05 | 6963039.13 | ONGOING | 55% |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 55% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107926 | BAILEN ES | GEA | 8th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 11155889.25 | 11118914.41 | ONGOING | 55% |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 55% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite City | 109628 | Garita ES | CAVITE CITY | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 9808334.02 | 9000000 | COMPLETED | 100% | 2025-02-06 |  | 2024-06-0005 | 2024-06-0005 | 2024-06-04 | 2024-06-13 | 2024-06-26 | 2024-07-04 | 2024-09-26 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Dasmarinas City | 107917 | Dasmariñas II CS (Dasmariñas BBES B) | CITY OF DASMARIÑAS | 4th | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 22396279.87 | 22342252.33 | ONGOING | 75% | 2025-07-10 |  | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | August 26-September 13, 2024 | 2024-09-25 | 2024-10-11 | 2025-01-15 | 3CA Builders Corporation | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 75% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Dasmarinas City | 107913 | V. P. Villanueva MS (Palapala) | CITY OF DASMARIÑAS | 4th | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 7530097.97 | 7524654.77 | ONGOING | 75% | 2025-07-10 |  | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | August 26-September 13, 2024 | 2024-09-25 | 2024-10-11 | 2025-01-15 | 3CA Builders Corporation | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 75% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | General Trias City | 107944 | Angel L. Bawalan ES | CITY OF GENERAL TRIAS | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5348091.76 | 5300303.11 | ONGOING | 80% | 2025-06-27 |  | 2024-12-002 | 2024-12-002 | 2024-07-18 | 2024-07-26 | 2024-08-07 | 2024-08-13 | 2024-12-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 80% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Imus City | 107968 | Anabu I Elementary School | IMUS | 3rd | 1 | Modernization of Electrical Systems of On-Grid Schools | 1 | 6760877.85 | 6739888.88 | ONGOING | 75% | Aug. 20, 2025 |  | 2024-10-004 | 2024-10-004 | August 8, 2024 | August 27, 2024 | September 9, 2024 | September 30, 2024 |  | 144 cubits builders and supply | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 75% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Laguna | 108305 | Bernaldo N. Calara ES | Los Baños | 2nd | 1 | Upgrading of Electrical System | 1 | 4907472.04 | 3809235.44 | Under procurement | 0% | [9 empty] | EBLL Electrical Engineering Services | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Laguna | 108256 | Dayap ES | Calauan | 3rd | 1 | Upgrading of Electrical System | 1 | 10272779.81 | 8024471.98 | Under procurement | 0% | [9 empty] | EBLL Electrical Engineering Services | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Laguna | 301232 | Buenavista INHS | Magdalena | 4th | 1 | Upgrading of Electrical System | 1 | 7572083.57 | 6661782.89 | Under Procurement | 0% | [9 empty] | AYZARIZ Corporation | RTA submitted to CO- waiting for SARO | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109658 | Abundio Torre Memorial Elementary School | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 8931838.41 | 8915317.29 | COMPLETED | 100% | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-024 | ELEC 2024-RIVA-LIPA CITY-024 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 5465282.4 | 5455051.2 | COMPLETED | 100% | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-007 | ELEC 2024-RIVA-LIPA CITY-007 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109660 | Bulacnin ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 12025935 | 11975546.02 | COMPLETED | 100% | 2024-12-31 |  | ELEC 2024-RIVA-LIPA CITY-001 | ELEC 2024-RIVA-LIPA CITY-001 | 2024-06-11 | 2024-06-19 | 2024-07-01 | 2024-07-17 | 2024-09-02 | 144 cubits builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109646 | Malitlit ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 8729469.09 | 8719457.3 | COMPLETED | 100% | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-015 | ELEC 2024-RIVA-LIPA CITY-015 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 7993270.23 | 7943210.95 | COMPLETED | 100% | 2024-12-31 |  | ELEC 2024-RIVA-LIPA CITY-006 | ELEC 2024-RIVA-LIPA CITY-006 | 2024-06-11 | 2024-06-19 | 2024-07-01 | 2024-07-17 | 2024-09-02 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lucena City | 109715 | Lucena East VIII Elementary School | LUCENA CITY (Capital) | 2nd | 1 | Upgrading of Electrical System | 1 | 3983306.63 | 3963665.7 | COMPLETED | 100% |  | 2024-08-30 | ELEC 2023-LUCENA CITY - 001 |  | November 22,2023 - December 12, 2023 | 2023-11-30 | 2023-12-12 |  | 2024-07-03 | 144 cubits builders and supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 109074 | REAL CENTRAL ELEMENTARY SCHOOL | REAL | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 12022005.85 | 11990000 | ONGOING | 83% | November 17, 2024 |  |  | 2023-07-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 22, 2024 | Hawstow Construction and Development |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 83% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Quezon | 301380 | RECTO MEMORIAL NATIONAL HIGH SCHOOL | TIAONG | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 34238345.22 | 34163589.19 | COMPLETED | 100% | 2024-12-22 | [7 empty] | 2024-05-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 12086998.27 | 9609287.1 | COMPLETED | 100% | 2024-11-16 | 2024-10-07 | [6 empty] | 2024-05-21 | EBLL Electrical Engineering Services | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 301325 | Gumaca National High School | GUMACA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 47697923.85 | 47594367.01 | COMPLETED | 100% | 2025-01-21 | [7 empty] | 2024-05-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Rizal | 109535 | Taytay Elementary School | Taytay | 1st | 1 | Upgrading of Electrical System (Undergound System) | 1 | 7488492.59 | 7288533.09 | Under procurement | 0% |  |  |  |  | November 15, 2024 | November 22, 2024 | December 6, 2024 | December 11, 2024 |  | NMDC Construction Corporation | for award | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Rizal | 301454 | Quisao National High School | Pililla | 2nd | 1 | Upgrading of Electrical System (Undergound System) | 1 | 12472902.42 | 10976154.7 | ONGOING | 35% |  |  |  |  | 2024-09-23 | 2024-10-01 | 2024-10-15 | 2024-11-11 | 2025-01-20 | NMDC Construction Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 30% | 5% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | San Pablo City | 109806 | Guerilla Elementary School | SAN PABLO CITY | 3rd | 1 | Upgrading of Electrical System | 1 | 10000000 | 5119388.4 | COMPLETED | 100% | 2024-11-30 |  | BEFF-E-001 | BEFF-E-001 | 2023-12-01 | 2023-12-12 | 2023-12-27 | 2024-01-12 | 2024-07-02 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Tanauan City | 107753 | Bernardo Lirio Memorial Central School | CITY OF TANAUAN | 3rd | 1 | Upgrading of Electrical System | 1 | 14314741.51 | 14296923.19 | ONGOING | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Tayabas City | 109232 | Busal ES | CITY OF TAYABAS | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 4560947.36 | 4552000 | ONGOING | 95% | February 13, 2025 as to approved extension by the SDO | N/A | ITB-INFRA-2024-004 | ITB-INFRA-2024-004 | 2024-03-28 | 2024-04-05 | 2024-04-17 | 2024-06-11 | 2024-07-24 | Hawstow Construction and Development | Pending on the completion of the punchlist item due to access and weather condition Conducted inspection last April 14, 2025 (with remaining punchlist) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | SOLAR |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-B | Calapan City | 111570 | Adriatico Memorial School | CITY OF CALAPAN (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 975022.82 | 907608 | COMPLETED | 100% | 2024-07-12 | 2024-12-12 | 2023-11-140 | 2023-11-140 | 2023-11-23 | 2023-11-29 | 2023-11-29 | 2023-12-18 | 2024-05-14 | PACE General Merch. | Build Platform for Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-B | Marinduque | 301554 | Marinduque NHS | BOAC (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | COMPLETED | 100% | [10 empty] | COMPLETED BUT WITH RECTRIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-B | Occidental Mindoro | 110053 | Kulanguan PS | ABRA DE ILOG | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 |  | Under procurement | 0% | [10 empty] | for procurement with Approved Project Modification | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | Under Procurement
ELECTRIFICATION 2024 | Region IV-B | Oriental Mindoro | 110453 | Pakpaklawin Elementary School | GLORIA | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | NOT YET started | 0% |  |  |  |  | 2025-03-19 | 2025-03-27 | 2025-04-08 | 2025-04-21 |  |  | Waiting for Sub-ARO | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-B | Palawan | 110752 | Baeng Elementary School | Araceli | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1500224.29 |  | ONGOING | 0% | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-B | Palawan | 110794 | Banglos Elementary School | BALABAC | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1063409.85 |  | ONGOING | 0% | [10 empty] | MOBILIZATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-B | Puerto Princesa City | 111475 | Bualbualan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1245436.28 |  | COMPLETED | 100% | August 18, 2024 |  | ELEC 2024 - R IVB - PUERTO PRINCESA CITY - 001 | INFRA 2024-01-001 | Nov. 22, 2024 | Nov. 28, 2014 | Dec. 11, 2024 | Jan. 30, 2024 | May 13, 2024 | Ian Jason Construction | 1240436.28 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Dapitan City | 501790 | Selinog IS | DAPITAN CITY | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3054986.49 | 3012306.2 | COMPLETED | 100% | August 29, 2024 | - | SDODAP-INFRA-2023-006 | SDODAP-INFRA-2023-006 | November 14, 2023 | November 21, 2023 | December 07, 2023 | June 10, 2024 | June 14, 2024 | MORTE CONSTRUCTION | Island school - limited accessibility going to school site | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Dipolog City | 197502 | Kepiyanan Elementary School | DIPOLOG CITY | 2nd | 1 | For Supply and installation of Solar PV Energy System | 1 | 3490869.25 | 3206594.87 | COMPLETED | 100% | August 29, 2024 | 2024-10-25 | INFRA-January2024-01 | ELEC2024-RIX-DIPOLOGCITY | January 09, 2024 | January 05, 2024 | January 30, 2024 | May 21, 2024 | May 31, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3027278.06 | 2534155.19 | COMPLETED | 100% | 2024-12-10 | - | INFRAEPA2024-02 | - | - | - | 2023-12-04 | 2024-05-13 | September 10,2024 | CLA ONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Pagadian City | 303902 | Lourdes National High School | PAGADIAN CITY (Capital) | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3012633.52 | 3000682 | COMPLETED | 100% | August 17, 2024 | - | ELEC-2024-RIX-PAGADIANCITY-01 | ELEC-2024-RIX-PAGADIANCITY-01 | November 13, 2023 | November 21, 2023 | December 04, 2023 | December 11, 2023 | June 03, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 124659 | LEBOTE ES | SERGIO OSMEÑA SR. | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5696151.71 | 5663568.2 | COMPLETED | 100% | August 27, 2024 | - | 2024-007-CBZN | CB-2024-021 | December 14, 2023 | December 21, 2023 | January 03, 2024 | January 10, 2024 | May 27, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 501156 | BULAWAN INTEGRATED SCHOOL | KATIPUNAN | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5630939.28 | 5612008.6 | COMPLETED | 100% | August 27, 2024 | - | 2024-008-CBZN | CB-2024-022 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 27, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 124447 | CAUSWAGAN ES | LILOY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5699878.14 | 5682921.41 | COMPLETED | 100% | July 27, 2024 | - | 2024-009-CBZN | CB-2024-023 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 27, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Sur | 303786 | Lantungan National High School | AURORA | 1st | 1 | Electrification and Modernization of Electrical Systems in various Schools (Single Phase) | 1 | 2276315.86 | 2111249.23 | COMPLETED | 100% | August 27, 2024 | 2024-10-21 | ZDS-24-E-01 | ZDS-24-E-01 | November 13, 2023 | November 21, 2023 | December 4, 2023 | January 03, 2024 | May 29, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Sur | 303769 | Culabay NHS | TABINA | 2nd | 1 | Electrification and Modernization of Electrical Systems in various Schools (Single Phase) | 1 | 3223678.46 | 3054897.86 | COMPLETED | 100% | August 27, 2024 | 2024-10-23 | ZDS-24-E-02 | ZDS-24-E-02 | November 13, 2023 | November 21, 2023 | December 4, 2023 | January 03, 2024 | May 29, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga Sibugay | 125538 | Agutayan ES | Buug | 1st | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 1951565.58 | 1803105.87 | COMPLETED | 100% | September 30, 2024 | 2024-10-25 | ZSY-2024ELEC-01 | ZSY-2024ELEC-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | July 03, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga Sibugay | 196512 | Logdeck PS | Kabasalan | 2nd | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 1881036.92 | 1716664.17 | COMPLETED | 100% | September 30, 2024 | - | ZSY-2024ELEC-02 | ZSY-2024ELEC-02 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | July 03, 2024 | ELETTRO ENGINEERING ENTERPRISES | Logistical constraints apply due to the four (4) - hour walking distance and difficult terrain | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Albay | 301816 | Bonga National High School | BACACAY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4220515.61 |  | COMPLETED | 100% | [9 empty] | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | NTP issued & precon was just conducted | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 32.41% | 67.59% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Albay | 301832 | Lacag National High School | DARAGA (LOCSIN) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4361764.39 |  | COMPLETED | 100% | [9 empty] | POWER COMPACT ENTERPRISES | NTP issued & precon was just conducted | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 85% | 15% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Albay | 111937 | Oas South Central School | OAS | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5368731.33 |  | ONGOING | 85% | [9 empty] | POWER COMPACT ENTERPRISES | NTP issued & precon was just conducted | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 85% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Norte | 301896 | Gonzalo Aler National High School | CAPALONGA | 1st | 1 | Upgrading of Electrical Lines (Overhead System) | 1 | 6222526.26 | 6201814.54 | COMPLETED | 100% | 2024-08-29 | 2024-08-28 | INFRA08-11-2023CN | INFRA08-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-05-31 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Camarines Norte | 301924 | Vicente L. Basit Memorial High School | DAET (Capital) | 2nd | 1 | Upgrading of Electrical Lines (Overhead System) | 1 | 6628846.65 | 6608986.67 | COMPLETED | 100% | 2024-08-29 | 2024-08-29 | INFRA08-11-2023CN | INFRA08-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-05-31 | Meltri Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112458 | Cabusao Central School | CABUSAO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2836477.79 | 2766050.8708 | COMPLETED | 100% |  |  | 45086 | 2024-05-041 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2024-01-02 | 2024-06-13 | 144 CUBITS BUILDERS AND SUPPLY | ON-GOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 309736 | Dr. Nelson A. Mejia HS | LIBMANAN | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3232966.57 | 3173104.1233 | COMPLETED | 100% |  |  | 45086 | 2024-05-041 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2024-01-02 | 2024-06-13 | 144 CUBITS BUILDERS AND SUPPLY | ON-GOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3583352.2 | 3497369.19 | ONGOING | 90% |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 301978 | Guijalo National High School | CARAMOAN | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2318362.34 | 2252529.88 | ONGOING | 90% |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 301976 | Pinaglabanan NHS | GOA | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3286760.16 | 3240369.6 | ONGOING | 95% |  |  | 45086 | 2024-05-042 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ENERGIZED, READY FOR FINAL INSPECTION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 5% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Camarines Sur | 112320 | Baao West CS | BAAO | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2844612.64 | 2493603.89 | ONGOING | 95% |  |  | 45086 | 45416 | June 14, 2023-July 3, 2023 | 2023-07-03 | 2023-07-03 | 2023-12-29 | 2024-06-11 | 3CA BUILDERS CORPORATION | ENERGIZED, READY FOR FINAL INSPECTION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 5% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6758699.45 | 6711962.92 | COMPLETED | 100% | 2024-11-04 | 2024-10-04 | [7 empty] | Hi-Tone Const. & Dev. Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | Rinconada National Technical Vocational School - Main Campus | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 11786820.47 | 10593622.98 | ONGOING | 95% | 2024-12-24 |  | 2024-2-8-PR-026 | INFRA-24-06-06-002 | February 20, 2024 - March 12, 2024 | 2024-02-28 | 2024-03-12 | 2024-03-26 | 2024-06-18 | ACF Power Enterprises | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Legaspi City | 114458 | Bogna Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2496770.75 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Ligao City | 111821 | Ligao East CS | CITY OF LIGAO | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5020227.53 | 5000742.18 | COMPLETED | 100% | 2024-09-30 |  | 2023-INFRA-02 | 2023-INFRA-02 | 2024-11-20 | 2024-12-04 | 2023-12-18 | 2024-05-15 | 2024-06-03 | La Abel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 95% | 5% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113763 | Dalakit ES | MONREAL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3990123.74 | 3976095.9 | COMPLETED | 100% | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 002 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 93% | 7% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3990123.74 | 3976095.9 | COMPLETED | 100% | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 003 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113876 | San Fernando CS | SAN FERNANDO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2527435.61 | 2509991.4 | COMPLETED | 100% | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 004 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 94% | 6% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 113897 | Piña Elementary School | SAN JACINTO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2060087.73 | 2049343.8 | COMPLETED | 100% | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 005 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 94% | 6% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 8167511.59 | 8135502.9 | ONGOING | 90% | 2024-10-03 |  | INFRA 2023 - 12 -004 | INFRA - 2024 - 006 | 2023-12-18 | 2023-12-27 | 2024-01-08 | 2024-05-09 | 2024-05-21 | EJ CANTORIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 70% | 20% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Masbate City | 321802 | Usab High School | CITY OF MASBATE (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3500000 | 3432938.53 | COMPLETED | 100% | 2024-09-11 |  | 2024-RV-MASBATE CITY-001 | 2024-RV-MASBATE CITY-001 | 2024-02-07 | 2024-02-21 | 2024-03-04 | 2024-03-11 | 2024-06-14 | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Naga City | 114500 | Naga Central School I | NAGA CITY | 3rd | 1 | Upgrading Electrical System On Grid Schools | 1 | 5983578.39 | 5275924.3 | COMPLETED | 100% |  |  | 2023-11-001 | 2024-05-002 |  |  |  |  | 2024-05-28 | Jurassic Construction and Supply | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 95% | 5% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon | 302240 | San Juan National High School | CASIGURAN | 1st | 1 | Upgrading of Electrical System | 1 | 2338851.59 | 1964635.34 | COMPLETED | 100% | 2025-02-10 | 2025-02-10 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-11-13 | 3CA Builders Corporation | For NOA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 80% | 20% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5881147.23 | 4976747.14 | COMPLETED | 100% | 2025-04-25 | 2025-04-25 | 24-06-003 | 24-06-003 | 2024-06-29 | 2024-07-24 | 2024-08-06 | 2024-08-27 | 2024-12-27 | 144 Cubits Builders and Supply | RTA submitted on September 20, 2024 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0% | 100% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Sorsogon City | 302279 | Sorsogon National High School | CITY OF SORSOGON (Capital) | 1st | 1 | Upgrading of Electrical System | 1 | 5445327.45 | 5394797.8 | COMPLETED | 100% | 2024-10-01 | 2024-10-30 | 001-24-INFRA-BEFF ELECTRIFICATION | 008-2024 | 2024-01-10 | 2024-01-18 | 2024-01-30 | 2024-05-18 | 2024-05-27 | Araphil Construction & Development Corporation | Short of Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region V | Tabaco City | 302282 | San Antonio National High School, Tabaco | CITY OF TABACO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5776290.29 | 3636154.29 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90.61% | 9.39% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region V | Tabaco City | 302283 | San Lorenzo National High School | CITY OF TABACO | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6944292.01 | 4641484 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 92.16% | 7.84% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Aklan | 114786 | Libacao Central ES | LIBACAO | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2736068.52 | 1767672.15 | COMPLETED | 100% | 2024-09-26 |  | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-1 | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-2 | 2023-11-14 | 2023-11-21 | 2023-12-04 | 2023-12-29 | 2024-05-27 | NEM CONSTRUCTION SUPPLIES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Aklan | 500643 | San Roque Integrated School | MALINAO | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2372783.92 | 1517286.95 | COMPLETED | 100% | 2024-09-27 |  | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-2 | DEPED-RO6-DI-EPA-2024 BEFF (ELEC)-058-2023 LOT-3 | 2023-11-15 | 2023-11-22 | 2024-12-04 | 2023-12-29 | 2024-05-27 | NEM CONSTRUCTION SUPPLIES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Antique | 115344 | Malabor ES | TIBIAO | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1794268.13 | 1235734.5 | COMPLETED | 100% | 2024-09-29 | 2024-09-02 | R6-D2-GAA2024-09-E | R6-D2-GAA2024-09-E | 2024-01-26 | 2024-02-02 | 2024-02-16 | 2024-04-05 | 2024-07-19 | RANP Construction Supply and Services | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Bacolod City | 181005 | Handumanan Elementary School II | BACOLOD CITY (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2179424.96 |  | Under Procurement | 0% | [10 empty] | no subaro yet; issue with the compliance of local cooperative; fund insufficient | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | Under Procurement
ELECTRIFICATION 2024 | Region VI | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3809119.24 |  | Under Procurement | 0% | [10 empty] | no subaro yet; CO awaiting submission of RTA from division office to download subaro | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | Under Procurement
ELECTRIFICATION 2024 | Region VI | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2nd | 1 | Installation of primary Poles and Service Lines with Transformers and Complete Accessories | 1 | 4175702.24 | 4127265.51 | COMPLETED | 100% | 2025-02-20 |  |  |  | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-07-31 | 2024-09-16 | PAR BUILDERS ELECTRICAL AND CONST. SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Capiz | 115667 | Casanayan ES | PILAR | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2156909.78 | 2150000 | NOT YET started | 0% |  |  | R6-DEPED-CAPIZ-CY2024-BEFF-CASANAYANES-LOT1-(Re-Bid) |  | 2024-10-17 | 2024-10-25 | 2024-11-06 |  |  | RJZW ELECTRICAL ENGINEERING SUPPLY | FOR ISSUANCE OF AWARD AND NTP, SARO Received last February 28, 2025 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Capiz | 115590 | Ilawod ES (mambusao east) | MAMBUSAO | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2601712.15 | 2595200 | COMPLETED | 100% | 2025-05-03 |  | R6-DEPED-CAPIZ-CY2024-BEFF-ILAWODES-LOT2 | CB No. 2024 - 030 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-19 | 2024-12-27 | RJZW ELECTRICAL ENGINEERING SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 25% | 75% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Escalante City | 117043 | Escalante Central Elementary School | CITY OF ESCALANTE | 1st | 1 | Upgrading of Electrical System | 1 | 3692973.81 | 3508000 | ONGOING | 95% | 2025-03-09 |  | Project 02-2024 | Project 02-2024 | 2024-06-29 | 2024-07-08 | 2024-07-19 |  | 2024-10-09 | PAR BUILDERS | Waiting for the Cooperative schedule to energize | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 70% | 25% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Guimaras | 115892 | Calaya Elementary School | NUEVA VALENCIA | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3369617.68 | 3358846.89 | COMPLETED | 100% | 2024-10-22 | 2024-07-17 | No. 07-2023 | No. 07-2023 | 2023-10-16 | 2023-10-24 | 2023-11-06 | 2024-05-13 | 2024-05-20 | AGM Silver Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5552051.97 | 3495252.08 | ONGOING | 80% | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L3 | BEFF2024-RVI-022-ILOILO-ELEC-L3 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 47% | 33% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302470 | Buga National High School | LEON | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2868850.32 | 2847447.4 | ONGOING | 80% | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L4 | BEFF2024-RVI-022-ILOILO-ELEC-L4 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 78% | 2% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302471 | Burak NHS | MAASIN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3310765.64 | 2083965.51 | ONGOING | 75% | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L1 | BEFF2024-RVI-022-ILOILO-ELEC-L1 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 64% | 11% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 302449 | Anilao NHS | ANILAO | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4425596.02 | 2778779.59 | ONGOING | 95% | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L5 | BEFF2024-RVI-022-ILOILO-ELEC-L5 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 84% | 11% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4962542.47 | 3124171.36 | ONGOING | 90% | 2025-07-01 |  | BEFF2024-RVI-022-ILOILO-ELEC-L2 | BEFF2024-RVI-022-ILOILO-ELEC-L2 | 2024-07-23 | July 10, 10, 2024 | 2024-07-22 | 2024-08-06 | 2025-03-03 | EARLY RISER CONSTRUCTION | RTA submitted to CO, waiting for sub-aro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 63% | 27% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 594034.64 |  | not yet started | 0% |  |  |  |  | 2024-08-05 | 2024-08-12 | 2024-08-24 | Sept. 26, 2024 |  |  | RTA submitted to CO, waiting for sub-aro | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 20047981.78 |  | not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3233807.07 | 3223059.63 | COMPLETED | 100% | 2025-02-02 | 2025-04-17 | 23-11-33 | 24-09-002 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 80% | 20% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3416277.7 | 3394508.88 | COMPLETED | 100% | 2025-02-02 | 2025-04-02 | 23-11-30 | 24-08-001 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 90% | 10% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Passi City | 302806 | EFRAIM M. SANTIBAÑEZ NATIONAL HIGH SCHOOL | CITY OF PASSI | 4th | 1 | Upgrading of Electrical System | 1 | 1212555.45 | 972508.03 | COMPLETED | 100% | 2024-09-24 | 2024-08-30 | BEFF-ELECTRIFICATION | RO6-D14-FY2024-BEFF-UES-EMSNHS | 2024-02-12 | 2024-02-21 | 2024-03-03 | 2024-04-05 | 2024-07-04 | Early Riser Construction | 100% Disbursement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | Roxas City | 117670 | Mongpong ES | ROXAS CITY (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1674765.43 | 1608191.95 | NOT YET started | 0% |  |  | 2024-050 | Con-2024-050 | 2024-06-28 | 2024-07-08 | 2024-07-22 | 2024-11-27 |  | RJZW Elect. Eng'g. Svs. | for issuance of NOA after lifting of banning | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | not yet started
ELECTRIFICATION 2024 | Region VI | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3575492.35 | 2789804.67 | COMPLETED | 100% |  |  | 45352 | 45352 | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-09-28 | 2025-01-06 | CAPRICORN GENERAL MERCHANDISING & SERVICES | already downloaded subaro | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VI | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1st | 1 | Upgrading of Electrical System | 1 | 2426232.73 | 2370639.42 | ONGOING | 98% | 2024-09-12 |  | 2023-10-0094 | 10389058-2023-10-0094 | 2023-12-03 | 2023-12-18 | Decemebr 27, 2023 | 2024-01-18 | 2024-06-07 | 2023 BEFF Upgrading of Electrical System ( Overhead System) | waiting of electric cooperative to energized | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 98% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Silay City | 302781 | Brgy. E. Lopez NHS (SHS) | SILAY CITY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3024557.77 | 2975811 | Completed | 100% | 2025-05-06 |  | 2024-07-ELNHS-002 | 2024-C-005 | 2024-06-29 | 2024-07-07 | 2024-07-30 | 2024-08-05 | 2025-01-06 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 5% | 95% |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VI | Sipalay City | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3546699.83 |  | Under Procurement | 0% | [10 empty] | CO awaiting submission of RTA from division office to download subaro | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | ENERGIZATION |  |  | not yet started
ELECTRIFICATION 2024 | Region VI | Victorias City | 117447 | Victorias North ES | CITY OF VICTORIAS | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3479568.81 | 2999675.4 | ONGOING | 98% | 2025-03-31 |  | SDOVC-INFRA2024-001 | SDOVC-INFRA2024-001 | 2024-07-11 | 2024-07-19 | 2024-07-31 | 2024-08-22 | 2024-08-27 | Nem Construction Supplies and Services | On-going project | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 70% | 28% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VII | Bayawan City | 120108 | Bongalonan Elementary School | BASAY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2362253.92 | 2138763.97 | COMPLETED | 100% | 2024-08-30 |  | 2024-BEFF-ELEC-001 | 2024-BEFF-ELEC-001 | 2023-11-27 | 2024-12-04 | 2024-12-18 | 2024-01-09 | 2024-05-31 | Global Power Equipment Marketing Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Bogo City | 119118 | Bogo II Central ES | CITY OF BOGO | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2403087.48 | 2393306.37 | COMPLETED | 100% | 2024-10-14 |  | ITB202310-03 | ITB202310-03 | 2023-10-27 | 2023-11-06 | 2023-11-20 | 2023-11-23 | 2024-07-09 | CCO Engineering Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2nd | 1 | Upgrading of Electrical System | 1 | 3005471.66 | 2000000 | not yet started | 0% | [5 empty] | 2024-06-06 | 2024-06-19 |  |  |  | received saro September 19, 2024. For preparation of contract. | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3rd | 1 | Upgrading of Electrical System | 1 | 5841150.25 | 4000000 | not yet started | 0% | [5 empty] | 2024-06-06 | 2024-06-19 |  |  |  | received saro September 19, 2024. For preparation of contract. | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region VII | Carcar City | 119158 | CARCAR CENTRAL ELEMENTARY SCHOOL | Carcar City | 2nd | 1 | Upgrading of Electrical System | 1 | 3018081.07 | 2594330.24 | COMPLETED | 100% | 2024-09-26 |  | Electrification24-01Carcar | BEFF 2024-Electrification Program-Upgrading of Electrical System (Overhead System) at Carcar Central Elementary School | 2024-03-13 | 2024-03-19 | 2024-04-03 | 2024-04-17 | 2024-06-21 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu | 312401 | BALUD NATIONAL HIGH SCHOOL | SAN FERNANDO | 1st | 1 | Modernization of Electrical System On-grid Schools | 1 | 1588869.78 | 1578017.31 | COMPLETED | 100% |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-01 | CY 2024 BEFF Electrification-DepED-R7-Cebu-01 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2nd | 1 | Upgrading Electrical System On Grid Schools | 1 | 1405321.08 | 1401580.92 | COMPLETED | 100% |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-02 | CY 2024 BEFF Electrification-DepED-R7-Cebu-02 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu | 119048 | Bantayan Central ES | BANTAYAN | 4th | 1 | Upgrading Electrical System On Grid Schools | 1 | 2297427.36 | 2272717.96 | COMPLETED | 100% |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-03 | CY 2024 BEFF Electrification-DepED-R7-Cebu-03 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu | 119421 | Tayud Elementary School | LILOAN | 5th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1066650.16 | 916643.04 | COMPLETED | 100% |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-04 | CY 2024 BEFF Electrification-DepED-R7-Cebu-04 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu | 118866 | Alcantara Central ES | ALCANTARA | 7th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1313160.75 | 1307416.92 | COMPLETED | 100% |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-05 | CY 2024 BEFF Electrification-DepED-R7-Cebu-05 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu City | 119923 | Paril ES | CEBU CITY (Capital) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2250000 | 1949622.05 | COMPLETED | 100% | Nov. 11, 2024 |  | ELECT 2024 - REGION VII - CEBU CITY - 001 | DEPED CCD 2024 - 02 | Nov. 24, 2023 | Dec. 4, 2023 | Dec. 15, 2023 | Dec. 29, 2023 | August 7, 2024 | CCO ENGINEERING CONSTRUCTION AND SUPPLY | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Cebu City | 119908 | Mangabon ES | CEBU CITY (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2100000 | 1800639.08 | COMPLETED | 100% | Nov. 11, 2024 |  | ELECT 2024 - REGION VII - CEBU CITY - 003 | DEPED CCD 2024 - 03 | Nov. 24, 2023 | Dec. 4, 2023 | Dec. 15, 2023 | Dec. 29, 2023 | August 7, 2024 | CCO ENGINEERING CONSTRUCTION AND SUPPLY | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | City of Naga, Cebu | 303035 | Placido L. Senor National High School | CITY OF NAGA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1690172.56 | 1689762.64 | ONGOING | 40% | 2024-09-28 |  | cityofnaga 2023-003 | 45463 | 2023-11-21 | 2023-11-28 | 2023-12-11 | 2023-12-19 | 2024-06-24 | DBB INDUSTRIAL SERVICES |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 40% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region VII | Dumaguete City | 119937 | Magsaysay MES | DUMAGUETE CITY (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2339992.66 | COMPLETED | 100% | 2024-10-16 |  | 2024-001 | 2024-001 | 2024-03-13 | 2024-04-01 | 2024-04-11 | 2024-04-22 | 2024-07-11 | Global Power Equipment Marketing Corporation | awaiting schedule with the electric cooperative for energization of the transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Guihulngan City | 120236 | Bonbon ES | Guihulngan City | 1st | 1 | Off-grid (Solar PV Energy System) | 1 | 7595594.13 |  | not yet started | 0% | [10 empty] | waiting for the lifting of election ban | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | SOLAR |  |  | not yet started
ELECTRIFICATION 2024 | Region VII | Lapu-Lapu City | 119953 | Cawhagan Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 966934.52 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2142278.63 | 1757499.69 | COMPLETED | 100% | 2024-08-03 | 2024-08-09 | 2023ELEC01 | 2024-01 | 2023-12-11 | 2023-12-18 | 2024-01-02 | 2024-01-10 | 2024-05-20 | DBB Industrial Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Siquijor | 120655 | Basac ES | Larena | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2497039.92 | 2068253.96 | COMPLETED | 100% | 2024-08-21 |  | 10336674 | 2023-90 | 2023-11-20 | 2023-11-28 | 2023-12-11 | 2023-12-12 | 2024-05-21 | Global Power Equipment Marketing Corporation | for approval from local cooperative | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Tagbilaran City | 118711 | Mansasa Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | Upgrading/ Modernization of Electrical System | 1 | 5946563.06 | 4346783.45 | COMPLETED | 100% | 2024-10-02 | 2024-10-16 | 2023-001-Services | 2023-001-Services | 2023-11-08 | 2023-11-17 | 2023-11-29 | 2023-12-04 | 2024-05-28 | CCO Engineering Construction and Supply | With VO No. 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VII | Talisay City | 233502 | Lawaan III Elementary School | CITY OF TALISAY | 1st | 1 | Upgrading of Electrical System | 1 | 1915741.65 | 1909888 | COMPLETED | 100% | 2024-09-25 | 2024-09-25 | 2024-002 | 45469 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-06-27 | Quirante Construction Corporation | On going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Baybay City | 121089 | Kilim Elementary School | CITY OF BAYBAY | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1011775.91 | 940447.2 | COMPLETED | 100% | 2024-08-25 | 2024-07-05 | 2023-12-I002 | 2023-12-I002 |  | 2023-12-11 | 2023-12-27 | 2024-05-23 | 2024-05-27 | J.A. CONSTRUCTION AND TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1956456.51 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Borongan City | 122386 | SAN PABLO ES | BORONGAN CITY | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 1910064.17 | 1889381.54 | COMPLETED | 100% | [6 empty] | 2024-11-07 |  | 2024-05-07 | Lobrinos Consolidated Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 7.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Calbayog City | 124128 | Tinambacan Central School | CALBAYOG CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2733516.07 | 2711092.15 | COMPLETED | 100% | 2024-11-01 | 2024-08-27 | 2024-RVIII-CALBAYOG-EP |  | 2024-03-26 | 2024-04-03 | 2024-05-15 | 2024-05-27 | 2024-07-19 | JFR CONSTRUCTION, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Catbalogan City | 123399 | Libas Elementary School | CITY OF CATBALOGAN (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 895038.5 |  | Under Procurement | 0% | [10 empty] | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region VIII | Eastern Samar | 122325 | Arteche Central Elementary School | ARTECHE | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3336938.1 | 3316854.65 | COMPLETED | 100% | 2024-08-21 |  | CY2024-BEFF-ELEC-ES-C1 | CY2024-BEFF-ELEC-ES-C1 | 2023-10-13 | 2023-10-24 | 2023-11-08 | 2024-05-09 | 2024-05-16 | YFL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Eastern Samar | 313522 | Concepcion National High School | ARTECHE | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 1886379.12 | 1866325.43 | COMPLETED | 100% | 2024-08-21 | 2024-08-20 | CY2024-BEFF-ELEC-ES-C2 | CY2024-BEFF-ELEC-ES-C2 | 2023-10-13 | 2023-10-24 | 2023-11-08 | 2024-05-09 | 2024-05-16 | YFL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 303429 | Sta. Cruz National High School | SAN MIGUEL | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2459541.74 | 1498109.28 | COMPLETED | 100% | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 303361 | Carigara National High School | CARIGARA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2982440.59 | 2962361.35 | COMPLETED | 100% |  |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-01-18 | 2024-06-05 | HD GOLDEN BUILDERS AND SUPPLY, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 121600 | Macupa Central School | LEYTE | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1796111.56 | 1109313.84 | COMPLETED | 100% | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 313328 | Kananga National High School - Montebello Annex | KANANGA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1397251.53 | 862667.04 | COMPLETED | 100% | 2024-12-25 |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-07-02 | 2024-08-20 | J.CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Leyte | 121378 | Baas Elementary School | HILONGOS | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 998861.08 | 848777.46 | COMPLETED | 100% |  |  |  |  | 2024-11-09 | 2024-11-17 | 2023-12-04 | 2024-01-18 | 2024-06-05 | HD GOLDEN BUILDERS AND SUPPLY, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Maasin City | 323103 | Lunas National High School | CITY OF MAASIN (Capital) | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2950439.41 | 2766444.12 | ONGOING | 95% |  |  | INFRA-2024-02 | INFRA-2024-02 | 2024-02-27 | 2024-03-12 | 2024-03-27 | 2024-05-27 |  | M.G. VILLAMIN CONSTRUCTION | For Variation Order | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region VIII | Northern Samar | 303534 | BIRI NATIONAL HIGH SCHOOL | BIRI | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3162928.14 | 3162928.14 | COMPLETED | 100% | [6 empty] | 2023-11-20 |  |  | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Northern Samar | 313613 | La Perla NHS | LAOANG | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2394649.4 | 2394649.4 | COMPLETED | 100% | [6 empty] | 2023-11-20 |  |  | HD Golden Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Ormoc City | 305904 | Salvacion National High School | ORMOC CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1565073.02 | 1317783.58 | COMPLETED | 100% | 2024-09-06 | 2024-08-30 | ELEC-2024-RVIII-ORMOC-001 | BEFF-CY-2024-ELECTRIFICATION-L1 | 2024-01-25 | 2024-02-01 | 2024-02-13 | 2024-02-24 | 2024-06-06 | JA Construction and Trading Corporation | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Samar (Western Samar) | 123542 | Gandara II Central Elementary School | GANDARA | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2120724.46 | 2109908.47 | COMPLETED | 100% | 2024-08-27 | 2024-09-11 | elec-2024-samar-lot1 | 2024-001 |  | 2024-11-08 | 2024-12-01 |  | 2024-05-22 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Samar (Western Samar) | 303608 | Talalora National High School | TALALORA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2175763.84 | 2155204.63 | COMPLETED | 100% | 2024-08-27 | 2024-09-23 | elec-2024-samar-lot2 | 2024-002 |  | 2024-11-08 | 2024-12-01 |  | 2024-05-22 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 303458 | Hilaan NHS | BONTOC | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3108855.25 | 2086463 | COMPLETED | 100% | 2024-10-11 |  | CY2024-BEFF-ELECTRIFICATION-L1 | CY2024-BEFF-ELECTRIFICATION-L1 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | VHITS D. G. BUILDERS AND ENTERPRISES | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2621273.29 | 1760901.44 | COMPLETED | 100% | 2024-10-11 |  | CY2024-BEFF-ELECTRIFICATION-L2 | CY2024-BEFF-ELECTRIFICATION-L2 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | VHITS D. G. BUILDERS AND ENTERPRISES | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4461051.31 | 2737144.42 | COMPLETED | 100% | 2024-11-10 |  | CY2024-BEFF-ELECTRIFICATION-L3 | CY2024-BEFF-ELECTRIFICATION-L3 | 2023-10-20 | 2023-10-27 | 2023-11-09 |  | 2024-06-13 | HD GOLDEN BUILDERS AND SUPPLY INC. | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region VIII | Tacloban City | 124245 | Dr. AP Banez Memorial School | TACLOBAN CITY (Capital) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1750534.4 | 1730780.61 | COMPLETED | 100% | 2024-09-15 | 2024-08-20 | CY 2024 BEFF_SCHOOL ELECTRIFICATION-02 | 02-2024 BEFF SE-02 | 2024-11-07 | 2023-11-14 | 2023-11-27 | 2023-11-30 | 2024-06-11 | KAMARI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Bukidnon | 303978 | Pangantucan NHS | PANGANTUCAN | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1944415.44 | 1625855.39 | ONGOING | 85% | 2024-12-23 | - | PB-02-11-2023-0024-A | 015-2024 | PR 2024-02-040 dated February 27, 2024 | Negotiated Procurement due to 2 failed bidding | 2024-03-15 | 2024-04-12 | 2024-06-26 | AN Escalante Construction, Inc. | Ongoing, Done survey by Electric Coop, waiting for BOM | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 85% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Bukidnon | 303952 | Cabulohan-Paradise NHS | CABANGLASAN | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2513688.52 | 2257543 | ONGOING | 95% | 2025-08-30 | - | PB-02-11-2023-0024 | 013-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-29 | White Beard Construction | Still consolidating documentary requiremets for Electrical Permit and application for turn-on, need to secure Land disposition and Form V-37 in lieu of the title, | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 5% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Bukidnon | 303976 | Old Damulog NHS | DAMULOG | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1792243.8 | 1789757.96 | ONGOING | 92% | 2025-06-30 | - | PB-02-11-2023-0024 | 014-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-29 | Meter King Inc. | Scheduled to be energized on June 10, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 85% | 7% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Cagayan de Oro City | 127960 | Bonbon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3140673.42 | 2830507.8 | COMPLETED | 100% | 2024-09-08 | - | Elec 2024-RX-Cagayan de Oro - 001 | 2024-009 | 2023-11-16 | 2024-11-28 | 2023-12-14 | 2023-12-28 | 2024-06-06 | F.B. Batucan Electrical Services | Awaiting for the approval of RO to convert Customer Own to Commercial Own contract with CEPALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Cagayan de Oro City | 127944 | Gusa Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | Upgrading of Electrical System | 1 | 4314432.5 | 3884668.52 | COMPLETED | 100% | 2024-09-08 | - | Elec 2024-RX-Cagayan de Oro - 002 | 2024-008 | 2023-11-16 | 2024-11-28 | 2023-12-14 | 2023-12-28 | 2024-06-06 | F.B. Batucan Electrical Services | Awaiting for the approval of RO to convert Customer Own to Commercial Own contract with CEPALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | Upgrading of Electrical System (Underground System) | 1 | 4518164.06 | 4175658.37 | COMPLETED | 100% | 2024-09-26 | 2024-10-20 | Infra-01-02-2024 | Infra-01-02-2024 | 2023-11-24 | 2023-12-01 | 2023-12-14 | 2024-01-24 | 2024-05-29 | Elettro Engineering Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2753266.37 | 2748058.88 | COMPLETED | 100% | 2024-10-15 | 2024-10-24 | 2024-01-0001 | 2024-02-0001 | 2024-01-04 | 2024-01-23 | 2024-02-07 | 2024-05-09 | 2024-05-23 | CCO Engineering and Construction Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Gingoog City | 111852 | Kalandang ta Anahaw ES | GINGOOG CITY | 1st | 1 | Installation of hybrid Solar Power System 8 kw and its electrical fixtures, wiring,switches and outlets | 1 | 1845640.12 | 1797132.63 | COMPLETED | 100% | 2024-11-11 | - | ELEC 2024 - REGION X - GINGOOG CITY - 001 | BEFF-2024-Anahaw ES | 2023-11-03 | 2023-11-10 | 2023-11-21 | 2024-05-21 | 2024-06-07 | Greenergy Development Corp. | On-going (under time suspesion - waiting for advice to use of military chopper for transport of euipment and materials for the project) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Iligan City | 304146 | Iligan City East National HS (Sta. Filomena) | ILIGAN CITY | Lone | 1 | Modernization of Electrical System On-grid Schools | 1 | 4590704.23 | 4361177.7 | COMPLETED | 100% | 2024-10-22 | - | INFRA-2023-11-02 | INFRA-2023-11-02 | 2023-11-28 | 2023-12-06 | 2024-02-19 | 2024-03-04 | 2024-05-31 | Brima Construction and Enterprise | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Lanao del Norte | 304001 | Diosdado Yap Sr. National High School | BAROY | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2136858.59 | 2135747.42 | COMPLETED | 100% | 2025-01-01 | 2025-05-30 | 2024-03(Infra) | 2024-03(Infra) | 2024-04-30 | 2024-05-10 | 2024-05-24 | 2024-06-10 | 2024-08-15 | HPS Engineering and Electrical Services | Checking of Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 95% | 5% |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1408996.7 | 1408545.54 | ONGOING | 95% | 2025-01-01 | - | 2024-03(Infra) | 45353 | 2024-04-30 | 2024-05-10 | 2024-05-24 | 2024-06-10 | 2024-08-15 | HPS Engineering and Electrical Services | Contractor to receive the NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Malaybalay City | 126561 | Cabangahan ES | CITY MALAYBALAY (Capital) | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2041033.97 | 1769898 | ONGOING | 90% | 2025-07-30 | - | 002-INFRA-2023 | 002-INFRA-2023 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2023-12-27 | 2024-08-01 | WHITE BEARD CONSTRUCTION | Drafting of Final MOA with local electric cooperative | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 85% | 5% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1st | 1 | Energization and Upgrading of Electrical System | 1 | 4007184.23 | 3962812.64 | ONGOING | 95% | 2024-12-06 | - | ELEC 2024 - REGION X - MISAMIS OCCIDENTAL - 002 | 012-2024 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2024-01-16 | 2024-07-25 | ESL MILESTONE BUILDERS & SUPPLY, INC. | ongoing - lacking transformer & post | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Occidental | 304034 | Diwat NHS | Bonifacio | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2601401.55 | 2573283.1 | COMPLETED | 100% | 2024-11-12 | - | ELEC 2024 - REGION X - MISAMIS OCCIDENTAL - 001 | 008-2024 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2024-01-16 | 2024-07-03 | ELETTRO ENGINEERING ENTERPRISES | Completed and Energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5185403.57 | 5132617.21 | ONGOING | 95% | 2024-11-09 | - | G2PB - Electrification-2024-001 |  | 2024-03-11 | 2024-03-18 | 2024-04-01 | 2024-04-11 | 2024-07-05 | Meter King Inc. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Misamis Oriental | 304088 | Mat-i (Naawan) NHS | NAAWAN | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5091534.32 | 5058911.8 | ONGOING | 95% | 2024-11-09 | - | G2PB - Electrification-2024-002 |  | 2024-03-11 | 2024-03-18 | 2024-04-01 | 2024-04-11 | 2024-07-05 | Meter King Inc. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region X | Oroquieta City | 304052 | Senote NHS | Oroquita City | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2330287.76 | 2307037.69 | COMPLETED | 100% | ‎18‎ ‎September‎ ‎2024 | - | N/A | N/A | 2023-11-29 | 2023-12-06 | 2024-01-16 | 2024-05-10 | 2024-05-21 | ESL Milestone Builders & Supply INC | for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Ozamis City | 304164 | Jose Lim Ho National High School | OZAMIS CITY | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 3001645.2 | 2991544.11 | COMPLETED | 100% | 2024-10-25 | - | 092-CIVIL 2023-001 (EPA) | 092-CIVIL 2023-001 (EPA) | 2023-11-22 | 2023-11-29 | 2023-12-15 | 2024-01-04 | 2024-06-27 | Elletro Engineering Enterprises | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Tangub City | 128217 | Tangub City CS | TANGUB CITY | 2nd | 1 | Modernization or Upgrading of Existing Electrical Distribution System | 1 | 2446851.19 | 2422378.91 | COMPLETED | 100% | 2024-10-26 | - | ELEC 2023-Region X-Tangub 001 | N/A | 2024-11-23 | 2024-11-30 | 2023-12-12 | 2023-12-20 | 2024-07-04 | ESL Milestone Builders INC | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region X | Valencia City | 126863 | VALENCIA CITY CS | VALENCIA CITY | 4th | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 5591647.46 | 4725764.09 | ONGOING | 90% | 2024-10-21 | - | 45323 | 011 s. 2024 | 2024-02-05 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-22 | AN ESCALANTE CONSTRUCTION, INC. | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 90% | 0% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2246820.76 | 2157934.14 | COMPLETED | 100% | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao City | 129167 | Jose Porras ES | DAVAO CITY | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1646373.74 | 1018018.77 | COMPLETED | 100% | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao City | 129605 | Datu Lompipi ES | DAVAO CITY | 3rd | 1 | Installation of Solar Panel | 1 | 3500000 |  | COMPLETED | 100% |  |  | BEFF-L005-2024 |  | June 28-July 18, 2024 | July 5, 2024 | July 18, 2024 |  |  |  | On going procurement process | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao City | 129740 | Tacunan Elementary | DAVAO CITY | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 813791.45 | 796189.62 | COMPLETED | 100% | Oct.3, 2024 |  | BEFF-L001-2024 | #2 s.2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | June 6, 2024 | CCO Engineering | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao De Oro | 500456 | Panansalan Integrated School | COMPOSTELA | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 4500000 | 3250176.26 | Under Procurement | 0% |  |  | SDDO-010-2024 |  | August 08, 2024 | August 16, 2024 | August 29,2024 |  |  |  | on-going docs process of award,contract and ntp previous remarks:RE-BID; | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | Under Procurement
ELECTRIFICATION 2024 | Region XI | Davao De Oro | 128308 | Laak CES | LAAK (SAN VICENTE) | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 4000000 | 3001391.69 | Under Procurement | 0% |  |  | SDDO-018-2024 |  | Sept. 06, 2024 | sept. 18, 2024 |  |  |  |  | on-going docs process of award,contract and ntp previous remarks:RE-BID; | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | Under Procurement
ELECTRIFICATION 2024 | Region XI | Davao del Norte | 501766 | New Casay Integrated School | BRAULIO E. DUJALI | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2992389.58 | ONGOING | 98% |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Magnum Builders Corp | this school belongs to the 2nd dist of davao del norte, for energization of DAVAOLIGHT | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 98% | 0% |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2nd | 1 | Rewiring/Upgrading of Electrical Facilities of 32CL & Installation of 8 Units 25 KVA Transformer | 1 | 7443073.18 | 7435389.58 | ONGOING | 98% |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Magnum Builders Corp | for energization of DAVAOLIGHT | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 95% | 3% |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region XI | Davao del Sur | 129099 | SANTA CRUZ CES | SANTA CRUZ | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 4522561.72 | 4501868.55 | COMPLETED | 100% |  |  | DS-SCHLBLDG-2024-G |  |  | July 16, 2024 | July 26, 2024 | August 09, 2024 |  | CCO ENGINEERING CONSTRUCTION & SUPPLY | for issuance of NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao Occidental | 128845 | Lawa Central Elementary School | DON MARCELINO | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3790450.02 | 3688458.36 | COMPLETED | 100% | January 16, 2025 |  | ITB W-04-2024 | contract no. 2024-010 | May 24, 2024 - June 05, 2024 | June 03, 2024 | June 05, 2024 | resolution no. 18,s. 2024 dated June 24, 2024 | September 18, 2024 | KUPLER INDUSTRIES INCORPORATED | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao Oriental | 129157 | Lambajon Central Elementary School SPED Center | BAGANGA | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 6099890.87 | 3778403.13 | COMPLETED | 100% | October 4, 2024 |  |  | 2024-013 | March 7, 2024 | March 14, 2024 | March 26, 2024 | April 8, 2024 | June 5, 2024 | CCO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Davao Oriental | 316108 | Lavigan National High School | GOVERNOR GENEROSO | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 2403408.83 | 1753059.4 | COMPLETED | 100% | October 4, 2024 |  |  | 2024-013 | March 7, 2024 | March 14, 2024 | March 26, 2024 | April 8, 2024 | June 5, 2024 | CCO | w/ Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 12.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1st | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 2593390.9 | 2525174.99 | COMPLETED | 100% | 90 CD from receipt of NTP | [8 empty] | KUPLER INDUSTRIES INCORPORATED | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Island Garden City of Samal | 128736 | Peñaplata Central Elementary School SPED Center | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | Upgrading & Modernization of School Electrical Distribution System | 1 | 7252344.46 |  | not yet started | 0% |  |  |  |  | 2024-10-15 | October 21, 2024 | 2024-11-04 |  |  |  | Issued short of award due to elction ban | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region XI | Mati City | 325106 | Mayo NHS | CITY OF MATI (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5497950.57 | 4062113.3427 | COMPLETED | 100% | March 01, 2025 |  |  |  | May 27, 2024 | June 04, 2024 | June 17,2024 | September 25, 2024 | October 02, 2024 | ABM1 BUILDERS & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Panabo City | 304408 | Panabo City National High School | CITY OF PANABO | 2nd | 1 | Upgrading of Electrical System (Underground System) | 1 | 9447723.66 | 8581388.7 | COMPLETED | 100% | 03/30/2025 |  |  |  | JUNE 28, 2024 | July 3, 2024 | JULY 18,2024 | August 8, 2024 | October 4, 2024 | RC CAPA ENGINEERING WORKS AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region XI | Tagum City | 128791 | HERCULINA L. EDIG ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 | Construction of Single Phase Line | 1 | 947410.22 |  | not yet started | 0% |  |  |  |  | 2024-06-28 | 2024-07-08 | 2024-07-22 |  |  |  | for issuance of NTP | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  | 0% | 0% |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region XII | General Santos City | 304654 | Lagao National High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | Upgrading of Electrical System | 1 | 5581077.08 |  | COMPLETED | 100% | 120CD |  |  | 010-2024 | 2024-09-11 | 2024-09-23 | 2024-10-07 | 2024-10-11 | 2024-01-24 | KUPLER INDUSTRIES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100% | 0% |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
Note on M416: ====== ID#AAAAhHpJccE User (2022-09-30 02:36:18) For termination. Far Flung.
Note on AT416: ====== ID#AAAAhHpJccE User (2022-09-30 02:36:18) For termination. Far Flung.
Note on M417: ====== ID#AAAAhHpJcSM User (2022-09-30 02:36:18) r: For termination. Far flung
Note on AT417: ====== ID#AAAAhHpJcSM User (2022-09-30 02:36:18) r: For termination. Far flung
Note on M418: ====== ID#AAAAhHpJcfc User (2022-09-30 02:36:18) For termination. Far flung
Note on AT418: ====== ID#AAAAhHpJcfc User (2022-09-30 02:36:18) For termination. Far flung
Note on N878: ====== ID#AAAAhHpJcio User (2022-09-30 02:36:18) Terminated
Note on AM878: ====== ID#AAAAhHpJcio User (2022-09-30 02:36:18) Terminated
Note on N879: ====== ID#AAAAhHpJcf4 User (2022-09-30 02:36:18) Terminated
Note on AM879: ====== ID#AAAAhHpJcf4 User (2022-09-30 02:36:18) Terminated
Note on N880: ====== ID#AAAAhHpJcUo User (2022-09-30 02:36:18) Terminated
Note on AM880: ====== ID#AAAAhHpJcUo User (2022-09-30 02:36:18) Terminated
Note on E888: ====== ID#AAAAhHpJcWY User (2022-09-30 02:36:18) Re-ALLIGN TO ANOMAR AND CARAGA RSHS
Note on M970: ====== ID#AAAAhHpJccY Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on AT970: ====== ID#AAAAhHpJccY Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on M973: ====== ID#AAAAhHpJchA Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on AT973: ====== ID#AAAAhHpJchA Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on M975: ====== ID#AAAAhHpJcTs Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on AT975: ====== ID#AAAAhHpJcTs Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on M976: ====== ID#AAAAhHpJcVE Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on AT976: ====== ID#AAAAhHpJcVE Crisan P. Coronel (2022-09-30 02:36:18) meralco issue
Note on M980: ====== ID#AAAAhHpJcQk Andrelina P. Coronel (2022-09-30 02:36:18) Waiting for MERALCO Transformer
Note on AT980: ====== ID#AAAAhHpJcQk Andrelina P. Coronel (2022-09-30 02:36:18) Waiting for MERALCO Transformer
Note on N1057: ====== ID#AAAAhHpJcWs User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on AM1057: ====== ID#AAAAhHpJcWs User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on N1060: ====== ID#AAAAhHpJcZo User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on AM1060: ====== ID#AAAAhHpJcZo User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on N1061: ====== ID#AAAAhHpJcWk User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on AM1061: ====== ID#AAAAhHpJcWk User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on N1062: ====== ID#AAAAhHpJcRo User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on AM1062: ====== ID#AAAAhHpJcRo User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on N1080: ====== ID#AAAAhHpJcSw User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on AM1080: ====== ID#AAAAhHpJcSw User (2022-09-30 02:36:18) FOR TAPPING OF THE COOP
Note on N1109: User: 98% from previous (typo?)
Note on N1406: ====== ID#AAAAhHpJcfg User (2022-09-30 02:36:18) Reported as 80% at July 2022, hence already repaorted as 90% as of June 2022 Targeted to be completed by March 2024 as per school visit dated Janaury 30-31, 2024
Note on AM1406: ====== ID#AAAAhHpJcfg User (2022-09-30 02:36:18) Reported as 80% at July 2022, hence already repaorted as 90% as of June 2022
Note on N1407: ====== ID#AAAAhHpJcVw User (2022-09-30 02:36:18) User: Targeted to be completed by March 2024 as per school visit dated Janaury 30-31, 2024
Note on AM1407: ====== ID#AAAAhHpJcVw User (2022-09-30 02:36:18) User:
Note on M1435: ====== ID#AAAAhHpJcjQ User (2022-09-30 02:36:18) error on reporting. Reported as ONGOING (ongoing procurement) . Reported failed bidding August 7, 2019.
Note on AT1435: ====== ID#AAAAhHpJcjQ User (2022-09-30 02:36:18) error on reporting. Reported as ONGOING (ongoing procurement) . Reported failed bidding August 7, 2019.
Note on M1462: ====== ID#AAAAhHpJcSk User (2022-09-30 02:36:18) Issue on LEC connection
Note on AT1462: ====== ID#AAAAhHpJcSk User (2022-09-30 02:36:18) Issue on LEC connection
Note on M1520: ====== ID#AAAAhHpJccA User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1520: ====== ID#AAAAhHpJccA User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1521: ====== ID#AAAAhHpJcXM User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1521: ====== ID#AAAAhHpJcXM User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1522: ====== ID#AAAAhHpJcck User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1522: ====== ID#AAAAhHpJcck User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1523: ====== ID#AAAAhHpJchY User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1523: ====== ID#AAAAhHpJchY User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1524: ====== ID#AAAAhHpJcXQ User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1524: ====== ID#AAAAhHpJcXQ User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1525: ====== ID#AAAAhHpJce8 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1525: ====== ID#AAAAhHpJce8 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1526: ====== ID#AAAAhHpJcQs User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1526: ====== ID#AAAAhHpJcQs User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1527: ====== ID#AAAAhHpJci0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1527: ====== ID#AAAAhHpJci0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1528: ====== ID#AAAAhHpJcX0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1528: ====== ID#AAAAhHpJcX0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1529: ====== ID#AAAAhHpJcf0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1529: ====== ID#AAAAhHpJcf0 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1530: ====== ID#AAAAhHpJci4 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1530: ====== ID#AAAAhHpJci4 User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1531: ====== ID#AAAAhHpJciA User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on AT1531: ====== ID#AAAAhHpJciA User (2022-09-30 02:36:18) for terimnation as of March 2022
Note on M1603: ====== ID#AAAAhHpJcTc User (2022-09-30 02:36:18) NOT PROCURED; for issuance of Negative Sub-ARO
Note on AT1603: ====== ID#AAAAhHpJcTc User (2022-09-30 02:36:18) NOT PROCURED; for issuance of Negative Sub-ARO
Note on E1634: ====== ID#AAAAhHpJcU4 Lenovo (2022-09-30 02:36:18) Not included in SARO
Note on M1634: ====== ID#AAAAhHpJcS8 Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on AT1634: ====== ID#AAAAhHpJcS8 Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on E1640: ====== ID#AAAAhHpJciY Lenovo (2022-09-30 02:36:18) Not included in SARO
Note on M1640: ====== ID#AAAAhHpJchk Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on AT1640: ====== ID#AAAAhHpJchk Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on N1726: ====== ID#AAAAhHpJci8 Andrelina P. Coronel (2022-09-30 02:36:18) For Termination Project Abandoned
Note on AM1726: ====== ID#AAAAhHpJci8 Andrelina P. Coronel (2022-09-30 02:36:18) For Termination Project Abandoned
Note on N1728: ====== ID#AAAAhHpJcSU Andrelina P. Coronel (2022-09-30 02:36:18) For Termination Project Abandoned
Note on AM1728: ====== ID#AAAAhHpJcSU Andrelina P. Coronel (2022-09-30 02:36:18) For Termination Project Abandoned
Note on M2090: ====== ID#AAAAhHpJcQg Crisan P. Coronel (2022-09-30 02:36:18) TERMINATED AND REBIDDED (ONGOING)
Note on AT2090: ====== ID#AAAAhHpJcQg Crisan P. Coronel (2022-09-30 02:36:18) TERMINATED AND REBIDDED (ONGOING)
Note on M2094: ====== ID#AAAAhHpJcfo Crisan P. Coronel (2022-09-30 02:36:18) TERMINATED AND REBIDDED (ONGOING)
Note on AT2094: ====== ID#AAAAhHpJcfo Crisan P. Coronel (2022-09-30 02:36:18) TERMINATED AND REBIDDED (ONGOING)
Note on E2151: ====== ID#AAAAhHpJcao User (2022-09-30 02:36:18) Cantumog NHS
Note on M2248: ====== ID#AAAAhHpJcRg Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on AT2248: ====== ID#AAAAhHpJcRg Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on M2252: ====== ID#AAAAhHpJcYc Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on AT2252: ====== ID#AAAAhHpJcYc Crisan P. Coronel (2022-09-30 02:36:18) Not included in SARO
Note on M2253: ====== ID#AAAAhHpJcSg User (2022-09-30 02:36:18) already completed from previous submission, hence, still ongoing for july 2022 submission
Note on AT2253: ====== ID#AAAAhHpJcSg User (2022-09-30 02:36:18) already completed from previous submission, hence, still ongoing for july 2022 submission
Note on N2445: ====== ID#AAAAhHpJcXw User (2022-09-30 02:36:18) Transformer installed on-site. Contractor for submission of remaining electrical materials for scheduling of line construction. 12/03/21
Note on AM2445: ====== ID#AAAAhHpJcXw User (2022-09-30 02:36:18) Transformer installed on-site. Contractor for submission of remaining electrical materials for scheduling of line construction. 12/03/21
Note on N2448: ====== ID#AAAAhHpJccc DepEd (2022-09-30 02:36:18) Equipment and Material Testing by MORESCO. 11/03/2021 Constructed load-side distribution wires and poles, panel boards ongoing. 50kVA transformer and other materials for delivery and testing by MORESCO 12/03/2021
Note on AM2448: ====== ID#AAAAhHpJccc DepEd (2022-09-30 02:36:18) Equipment and Material Testing by MORESCO. 11/03/2021 Constructed load-side distribution wires and poles, panel boards ongoing. 50kVA transformer and other materials for delivery and testing by MORESCO 12/03/2021
Note on N2449: ====== ID#AAAAhHpJcaY DepEd (2022-09-30 02:36:18) Ongoing. Negotiating for ROW Grant. BUSECO to prepare the MOA. (october) Same remarks as of 12/03/2021
Note on AM2449: ====== ID#AAAAhHpJcaY DepEd (2022-09-30 02:36:18) Ongoing. Negotiating for ROW Grant. BUSECO to prepare the MOA. (october) Same remarks as of 12/03/2021
Note on N2450: ====== ID#AAAAhHpJcR0 DepEd (2022-09-30 02:36:18) CONSTRUCTED 1 SPAN, 35 FEET STEEL, 1 PHASE, 75 KVA. Reasessed by BUSECO due to revision of Electrical Plan based on actual condition. (as of october) Same remarks as of December 3, 2021
Note on AM2450: ====== ID#AAAAhHpJcR0 DepEd (2022-09-30 02:36:18) CONSTRUCTED 1 SPAN, 35 FEET STEEL, 1 PHASE, 75 KVA. Reasessed by BUSECO due to revision of Electrical Plan based on actual condition. (as of october) Same remarks as of December 3, 2021
Note on N2451: ====== ID#AAAAhHpJceQ DepEd (2022-09-30 02:36:18) Civil works on-site. For compliance of load computation and transformer hang-up. Same remarks as of 12/03/21
Note on AM2451: ====== ID#AAAAhHpJceQ DepEd (2022-09-30 02:36:18) Civil works on-site. For compliance of load computation and transformer hang-up. Same remarks as of 12/03/21
Note on N2452: ====== ID#AAAAhHpJcfw DepEd (2022-09-30 02:36:18) On-going construction of load side c/o contractor. MSB for inspection c/c FIBECO.
Note on AM2452: ====== ID#AAAAhHpJcfw DepEd (2022-09-30 02:36:18) On-going construction of load side c/o contractor. MSB for inspection c/c FIBECO.
Note on N2474: ====== ID#AAAAhHpJcXU DepEd (2022-09-30 02:36:18) For Hang-Up
Note on AM2474: ====== ID#AAAAhHpJcXU DepEd (2022-09-30 02:36:18) For Hang-Up
Note on N2475: ====== ID#AAAAhHpJcgc DepEd (2022-09-30 02:36:18) For Hang-Up
Note on AM2475: ====== ID#AAAAhHpJcgc DepEd (2022-09-30 02:36:18) For Hang-Up
Note on N2476: ====== ID#AAAAhHpJcYg DepEd (2022-09-30 02:36:18) For punhlisting & occupancy permit
Note on AM2476: ====== ID#AAAAhHpJcYg DepEd (2022-09-30 02:36:18) For punhlisting & occupancy permit
Note on N2479: ====== ID#AAAAhHpJcR4 User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2479: ====== ID#AAAAhHpJcR4 User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on N2480: ====== ID#AAAAhHpJcas User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2480: ====== ID#AAAAhHpJcas User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on N2482: ====== ID#AAAAhHpJcfI User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2482: ====== ID#AAAAhHpJcfI User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2483: ====== ID#AAAAhHpJchc User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on N2484: ====== ID#AAAAhHpJch8 User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2484: ====== ID#AAAAhHpJch8 User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on N2485: ====== ID#AAAAhHpJcaA User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on AM2485: ====== ID#AAAAhHpJcaA User (2022-09-30 02:36:18) Same remarks from october accomp as of December 3, 2021
Note on N2501: ====== ID#AAAAhHpJcXY DepEd (2022-09-30 02:36:18) lacking occupancy permit
Note on AM2501: ====== ID#AAAAhHpJcXY DepEd (2022-09-30 02:36:18) lacking occupancy permit
Note on N2502: ====== ID#AAAAhHpJcgI DepEd (2022-09-30 02:36:18) lacking occupancy permit
Note on AM2502: ====== ID#AAAAhHpJcgI DepEd (2022-09-30 02:36:18) lacking occupancy permit
Note on N2548: ====== ID#AAAAhHpJcVs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2548: ====== ID#AAAAhHpJcVs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2549: ====== ID#AAAAhHpJciE User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2549: ====== ID#AAAAhHpJciE User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2550: ====== ID#AAAAhHpJcSo User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2550: ====== ID#AAAAhHpJcSo User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2551: ====== ID#AAAAhHpJcXs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2551: ====== ID#AAAAhHpJcXs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2552: ====== ID#AAAAhHpJcZA User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2552: ====== ID#AAAAhHpJcZA User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2556: ====== ID#AAAAhHpJcbQ User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2556: ====== ID#AAAAhHpJcbQ User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2564: ====== ID#AAAAhHpJcZk User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2564: ====== ID#AAAAhHpJcZk User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2565: ====== ID#AAAAhHpJcgo User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2565: ====== ID#AAAAhHpJcgo User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2571: ====== ID#AAAAhHpJcdc User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2571: ====== ID#AAAAhHpJcdc User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2573: ====== ID#AAAAhHpJcX4 User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2573: ====== ID#AAAAhHpJcX4 User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on N2576: ====== ID#AAAAhHpJcUs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on AM2576: ====== ID#AAAAhHpJcUs User (2022-09-30 02:36:18) Needs instruction from the CO on what to do to the remaining project works. Needs additional fund (to validate)
Note on M2600: ====== ID#AAAAhHpJcgE Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2600: ====== ID#AAAAhHpJcgE Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2601: ====== ID#AAAAhHpJcRc Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2601: ====== ID#AAAAhHpJcRc Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2602: ====== ID#AAAAhHpJceI Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2602: ====== ID#AAAAhHpJceI Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2603: ====== ID#AAAAhHpJcbc Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2603: ====== ID#AAAAhHpJcbc Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2604: ====== ID#AAAAhHpJcSE Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on N2604: ====== ID#AAAAhHpJcWw User (2022-09-30 02:36:18) For DU Tapping as of November report and as of December 2021 Still For DU Tapping as of JLY 2022
Note on AM2604: ====== ID#AAAAhHpJcWw User (2022-09-30 02:36:18) For DU Tapping as of November report and as of December 2021 Still For DU Tapping as of JLY 2022
Note on AT2604: ====== ID#AAAAhHpJcSE Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2606: ====== ID#AAAAhHpJcjI Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2606: ====== ID#AAAAhHpJcjI Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2608: ====== ID#AAAAhHpJcds Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on AT2608: ====== ID#AAAAhHpJcds Andrelina P. Coronel (2022-09-30 02:36:18) For Tapping on DU
Note on M2614: ====== ID#AAAAhHpJcV8 Acer (2022-09-30 02:36:18) as of october 2020, reported as completedc/o Engr Jay Amor Gardose
Note on AT2614: ====== ID#AAAAhHpJcV8 Acer (2022-09-30 02:36:18) as of october 2020, reported as completedc/o Engr Jay Amor Gardose
Note on N3034: User: 85% from previous (tyypo?)
Note on N3037: User: 98% from previous (tyypo?)
Note on N3039: User: 60% from previous (tyypo?)