## LMS 2020-2024
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel
LMS 2020 | CAR | Abra | 135114 | Tillilo PS | LUBA | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOIL PROTECTION, AND WATER SYSTEM | 18778535.1102 | 18761650.97 | Completed | 1 | 2022-05-12 | 2022-04-12 | 0 | CAR-ABRA-2021-07 | 2021-07-14 | 2021-07-21 | 2021-08-03 | 2021-08-13 | 2021-09-01 | Lonnie Construction/Lonnie Moun B.Quilloy | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | CAR | Abra | 135170 | Bantay Primary School | SALLAPADAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOIL PROTECTION, AND WATER SYSTEM | 9593256.5077 | 9578381.72 | Completed | 1 | 2022-06-01 | 2022-03-12 | 0 | CAR-ABRA-2021-09 | 2021-07-14 | 2021-07-21 | 2021-08-03 | 2021-08-13 | 2021-09-01 | HGW=3 Engineering & Construction/ Hilbert B. Willie | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0
LMS 2020 | CAR | Abra | 135101 | Likowan PS | TUBO | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOIL PROTECTION AND WATER SYSTEM | 18135713.2491 | 18121787.12 | Completed | 1 | 2022-06-11 | 2022-06-27 | 0 | CAR-ABRA-2021-10 | 2021-07-14 | 2021-07-21 | 2021-08-03 | 2021-08-13 | 2021-09-01 | HOPE EFG Builders/Esther P. Sangcaan | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | CAR | Abra | 218508 | Gacab PS | MALIBCONG | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND SLOPE PROTECTION | 21387725.206 | 21372483.54 | Completed | 1 | 2022-07-01 | 2022-03-12 | 0 | CAR-ABRA-2021-08 | 2021-07-14 | 2021-07-21 | 2021-08-03 | 2021-08-13 | 2021-09-01 | Baje Construction/Ernesto B. Baje | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | CAR | Apayao | 135231 | Cadaclan ES | CALANASAN (BAYAG) | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE, RAIN WATER COLLECTOR AND SOLAR PV ENERGY SYSTEM | 18186711.6621 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | LMS-2020-001 | 0 | July 1,2021 | July 7,2021 | July 19,2021 | 00:00:00 | 00:00:00 | 0 | Contract Preparation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CAR | Apayao | 135231 | Cadaclan ES | CALANASAN (BAYAG) | 0 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE, RAIN WATER COLLECTOR AND SOLAR PV ENERGY SYSTEM |  | 0 | Completed | 1 | 00:00:00 | 00:00:00 | LMS-2020-001 | 0 | July 1,2021 | July 7,2021 | July 19,2021 | 00:00:00 | 00:00:00 | 0 | Contract Preparation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CAR | Benguet | 135556 | Mongoto Elementary School | Kabayan | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM AND RETAINING WALL | 20828590.3407 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Delay was caused by the collapsed retaining wall | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | 1 | [5 empty] | CY 2023 |  |  | 1
LMS 2020 | CAR | Ifugao |  | Lubo-ong ES- Extension | HUNGDUAN | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE , WATER SYSTEM AND SLOPE PROTECTION | 14038425.3807 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-27 | 2021-08-03 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2020 | CAR | Ifugao |  | Jolowon ES-Annex | Lamut | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SLOPE PROTECTION AND WATER SYSTEM | 18410762.9113 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-27 | 2021-08-03 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | The project was terminated due to more than 10% slippage and LD to other DepEd Projects | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | 1 | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2020 | CAR | Kalinga | 136128 | Pangol Elementary School | TANUDAN | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, RAIN WATER COLLECTOR AND WATER SYSTEM | 11333380.9021 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | For Posting Due to Revalidation of the Project Site and Program Revision on Site Adoptation. (Target for posting August 17, 2021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2020 | CAR | Kalinga | 136151 | Tulgao East Elementary School | TINGLAYAN | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20714406.0614 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | CAR | Kalinga | 136151 | Tulgao East Elementary School | TINGLAYAN | 0 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM |  | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | CAR | Mt. Province | 136284 | Apalis Elementary School | PARACELIS | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND SLOPE PROTECTION | 27229155.3076 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | August 9,2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | CAR | Mt. Province | 136284 | Apalis Elementary School | PARACELIS | 0 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM,WATER SYSTEM, & SLOPE PROTECTION |  | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | August 9,2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | CAR | Tabuk City | 136157 | Balatoc Primary School | TABUK CITY | 0 | 1 | 4 | CONSTRUCTION OF ONE STOREY FOUR CLASSROOM SCHOOL BUILDING (WITH COMMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE, AND WATER SYSTEM | 15304902.1749 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0
LMS 2020 | CAR | Tabuk City | 136182 | Tangbay Primary School | Tabuk City | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), AND WATER SYSTEM | 15364666.0798 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-08 | 2021-07-14 | 2021-07-27 | 00:00:00 | 00:00:00 | 0 | ongoing lay out of cr tiles, ground clearing, installation of electrical fixture, installation of window glass and concreting of concrete infront of the building | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | 1 | [5 empty] | CY 2023 |  |  | 0
LMS 2020 | CARAGA | Agusan del Norte | 131592 | Tinigbasan ES | TUBAY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21247319.3187 | 0 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-015 | 0 | August 3, 2021 | August 11, 2021 | August 23, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Norte | 131592 | Tinigbasan ES | TUBAY | 2 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM |  | 0 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-015 | 0 | August 3, 2021 | August 11, 2021 | August 23, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Sur | 305479 | Kolambugan National High School | SIBAGAT | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21060050.7338 | 21014420.71 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 | 00:00:00 | 00:00:00 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Agusan del Sur | 305479 | Kolambugan National High School | SIBAGAT | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM |  | 21014420.71 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 | 00:00:00 | 00:00:00 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bayugan City | 131607 | New Salem ES | CITY OF BAYUGAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21432580.1464 | 21382541.73 | Completed | 1 | 00:00:00 | 00:00:00 | 2021-008 | 2021-008 | July 13, 2021 | July 21, 2021 | August 2, 2021 | August 6, 2021 | 00:00:00 | Thearis Builders and Supply | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bayugan City | 131607 | New Salem ES | CITY OF BAYUGAN | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM |  | 21382541.73 | Completed | 1 | 00:00:00 | 00:00:00 | 2021-008 | 2021-008 | July 13, 2021 | July 21, 2021 | August 2, 2021 | August 6, 2021 | 00:00:00 | Thearis Builders and Supply | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Bislig City | 132626 | Pamaypayan ES | CITY OF BISLIG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19163303.3063 | 19125272.89 | COMPLETED | 1 | 2022-01-11 | 2022-03-02 | LMS_BISLIG CITY_001 | LMS_BISLIG CITY_001 | 2021-07-13 | 2021-07-21 | 2021-08-03 | 2021-08-10 | 2021-08-23 | MN Bayalas Construction | PCAB Category "B", Lic. No.: 34251 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Dinagat Island | 132391 | A. Ecleo Elementary School | DINAGAT | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19402338.5115 | 14100000 | Completed | 1 | 2021-12-01 | 2022-01-12 | CONSTRUCTION INFRA21-002 | 0 | 2021-07-13 | 2021-07-23 | 2021-08-05 | 2021-09-27 | 2021-10-01 | RJB CONSTRUCTION | COMPLETED\ | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Siargao | 132196 | Pacifico Primary School | SAN ISIDRO | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21210000 | 19000000 | Completed | 1 | 2021-11-24 | 00:00:00 | BEFF-INFRA2021-004 | 0 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-08-03 | 2021-08-13 | WINDFALL | contract duration extended | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao City | 132276 | Arturo Borja ES | SURIGAO CITY (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18560762.8515 | 18532126.31 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-08-10 | FOR ISSUANCE | RJB Construction & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Norte | 214011 | Tiltilan Elementary School | GIGAQUIT | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15998830.9734 | 15971550.75 | completed | 1 | 2021-11-02 | 00:00:00 | 2021-005-BEFF-CARAGA | 005-2021 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-02 | 2021-08-04 | RJB CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Norte | 132429 | Cantugas Cul. Minorities ES | MAINIT | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19223342.8674 | 19150635.95 | completed | 1 | 2021-12-09 | 00:00:00 | 2021-004-BEFF-CARAGA | 004-2021 | 2021-07-07 | 2021-07-14 | 2021-07-26 | 2021-08-09 | 2021-08-11 | CHIVES CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Surigao del Sur | 132803 | Napanpanan Elementary School | Lingig | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19892960.4848 | 19859577 | Completed | 1 | December 28, 2021 | December 20, 2021 | LMS 2020 - R XIII - SURIGAO DEL SUR - 001 | 2021 - 15 | July 15, 2021 | July 27, 2021 | August 5, 2021 | August 24, 2021 | September 07, 2021 | RELY CONSTRUCTION AND SUPPLY | Completed on time | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | CARAGA | Tandag City | 132958 | Banahao Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15432866.1651 | 0 | Completed | 1 | December 15, 2021 | 00:00:00 | 0 | 0 | July 8, 2021 | July 22, 2021 | August 2, 2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region I | Pangasinan I, Lingayen | 500372 | Siapar Integrated | ANDA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM & STEEL GATES | 18456468.1348 | 18371467.59 | completed | 1 | May 4, 2022 | 00:00:00 | 2021-07-003-INFRA | 0 | 00:00:00 | 00:00:00 | August 11, 2021 | August 25, 2021 | September 6, 2021 | ABC East Multi Builders and Traders | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Cagayan | 102348 | Sawang ES | ABULUG | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 8071210.2629 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | Aug.1,2021 | 2021-08-09 | Aug.23,2021 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | 1 | [5 empty] | CY 2023 |  |  | 0
LMS 2020 | Region II | Isabela | 500467 | Sto. Tomas Integrated School | NAGUILIAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17304310.2869 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 2021-08-26 | 2021-09-08 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 103989 | Dulli ES | AMBAGUIO | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19382746.9758 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | With punchlist of corrective works for rectification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 156003 | Hamhamaan PS | AMBAGUIO | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15156145.7692 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | With punchlist of corrective works for rectification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 104087 | Kakiduguen Elementary School | KASIBU | 0 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY -TWO (2) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE AND WATER SYSTEM | 14875664.45 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | With punchlist of corrective works for rectification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 104087 | Kakiduguen ES | KASIBU | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19332225.9827 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | With punchlist of corrective works for rectification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 304675 | Pinayag NHS | KAYAPA | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15331022.2192 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Nueva Vizcaya | 304675 | Pinayag NHS | KAYAPA | 0 |  | 2 | CONSTRUCTION OF ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15331022.2192 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-07-28 | 2021-08-05 | 2021-08-17 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region II | Quirino | 156512 | Tamsi Elementary School | NAGTIPUNAN | 0 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND RETAINING WALL | 17274749.0089 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 2021-06-30 | 2021-07-06 | 2021-07-19 | 00:00:00 | 00:00:00 | NTL Builders & Developer | The building is almost complete, solar panels were already installed; ongoing works includes const. of retaining walls, fence, gates, flagpole and water system. The school is inaccessible during rainy days. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2020 | Region IV-A | Quezon | 108792 | Miyunod ES | INFANTA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18842695.7125 | 18830000 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-60 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | BOTEY CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-A | Quezon | 109039 | Pag-itan E/S | PANUKULAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM (for 4CL), AND WATER SYSTEM (for 4CL) | 21194223.6405 | 21163075.84 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-61 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | N.T SOTELO CONSTRUCTION & SUPPLY CORPORATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-A | Quezon | 109039 | Pag-itan E/S | PANUKULAN | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE |  | 21163075.84 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-61 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | N.T SOTELO CONSTRUCTION & SUPPLY CORPORATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region IV-A | Quezon | 109088 | Alibahaban ES (Alibihaban ES) | SAN ANDRES | 3 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15610253.566 | 15590167 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-62 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | M.G VILLAMIN CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-A | Quezon | 108830 | Villaminda ES | LOPEZ | 4 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15080003.5679 | 15059979 | completed | 1 | 2021-11-25 | 00:00:00 | 0 | 2021-63 | July 2-21, 2021 | 2021-07-09 | 2021-07-21 | 2021-07-23 | 2021-07-28 | M.G VILLAMIN CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-A | Rizal | 109468 | San Rafael ES - Inigan ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15419235.0738 | 15110797.65 | completed | 1 | 00:00:00 | 00:00:00 | INFRA-2021-002 | INFRA-2021-002 | July 19, 2021 | July 27, 2021 | August 9, 2021 | Setpember 1, 2021 | Setpember 14, 2021 | A. Suelila Constructiomn | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-B | Marinduque | 109901 | Tambunan ES | BOAC (Capital) | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF 1STY4CL SCHOOL BLDG (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20455972.2891 | 0 | Completed | 1 | 2022-08-15 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-B | Oriental Mindoro | 110339 | Mamalao Mangyan School | BACO | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 20188286.0327 | 20087944.35 | completed | 1 | April 05, 2022 | March 07, 2022 | LMS 2020 - R IV-B - Oriental Mindoro - 001 | 015-2021 | July 06, 2021 | July 14, 2021 | July 26, 2021 | Aug. 11, 2021 | Aug. 31, 2021 | CMSEL Construction and Developer | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-B | Oriental Mindoro | 170036 | Bailan ES | BULALACAO (SAN PEDRO) | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 19229984.4143 | 18180121.46 | Completed | 1 | June 15, 2022 | June 14, 2022 | LMS 2020 - R IV-B - Oriental Mindoro - 002 | 019-2021 | July 06, 2021 | July 14, 2021 | July 26, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Orient Star Construction Inc. | with contract time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IV-B | Puerto Princesa City | 111525 | Nasuduan ES | Puerto Princesa City | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19185222.7994 | 17849626.85 | Completed | 1 | May 19, 2022 Revised: June 18, 2022 | 2022-06-15 | 0 | INFRA 2021-03 | July 27,2021 | August 3,2021 | 2021-08-16 | Sept. 10, 2021 | Sept. 14, 2021 | Maryknoll Builders and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Isabela City | 305549 | Lampinigan National High School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19525553.3757 | 19417116.63 | COMPLETED | 1 | 2021-12-30 | 2022-06-23 | INFRA2021-01 | INFRA2021-01 | July 4-11, 2021 | July 12, 2021 | July 26, 2021 | July 29, 2021 | August 3, 2021 | 2M CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Zamboanga City | 126155 | Camp Socorro | ZAMBOANGA CITY | 2 | 1 | 4 | PROPOSED CONSTRUCTION ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22006289 | 21998288.85 | COMPLETED | 1 | 2021-12-04 | 2022-05-04 | 06-0030-21 | 06-0030-21 | 2021-07-02 | 2021-07-09 | 2021-07-21 | 2021-08-11 | 2021-08-21 | Zamboanga 3VC CONSTRUCTION INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Zamboanga del Norte | 303702 | Sitog NHS Ext - Dabiak | Katipunan | 2 | 1 | 2 | CONSTRUCTION OFONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20686643.261 | 10204006.09 | COMPLETED | 1 | 2021-12-31 | 2021-12-31 | CB 2021-023 | CB 2021-023 | July 1, 2021 | July 9, 2021 | July 22, 2021 | July 27, 2021 | Aug. 4, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Zamboanga del Norte | 303702 | Sitog NHS Ext - Dabiak | Katipunan | 2 |  | 2 | CONSTRUCTION OFONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM |  | 10204006.09 | COMPLETED | 1 | 2021-12-31 | 2021-12-31 | CB 2021-023 | CB 2021-023 | July 1, 2021 | July 9, 2021 | July 22, 2021 | July 27, 2021 | Aug. 4, 2021 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Zamboanga del Sur | 124885 | Bag-Ong Mandaue IPS | AURORA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18695810.1265 | 18684761.34 | COMPLETED | 1 | 2021-12-31 | 2022-03-02 | ZDS- 20- LMS-01 | ZDS- 20- LMS-01 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-05 | 2021-08-11 | GENETIAN BUILDERS AND ENTERPRISES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region IX | Zamboanga Sibugay | 125746 | San Jose PS | OLUTANGA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19309086.9083 | 19290632.4 | COMPLETED | 1 | On-going Suspension Order since March 02, 2022 | - | ZSY-2020LMS-01 | ZSY-2020LMS-01 | June 29, 2021 | July 17, 2021 | July 19, 2021 | 2021-07-30 | 2021-08-26 | CPAN Engineering & Enterprises | Change Order (Water Pump Solar Panel) for C.O. approval | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region V | Camarines Sur | 112696 | Tampuhan ES | LIBMANAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 8580284.0651 | 0 | Reverted | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | resolution to cancel due to time constraint for procurement activities | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
LMS 2020 | Region V | Catanduanes | 113171 | San Miguel Elementary School | BARAS | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m) | 8140400.6798 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region V | Catanduanes | 113339 | Dugui San Isidro Elementary School | VIRAC (Capital) | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 8140400.6798 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region V | Masbate | 113458 | Mapitogo Elementary School | BALUD | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10351655.5952 | 10298568.14 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 3R3M Const. and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VI | Antique | 114985 | Caloy-ahan PS | Bugasong | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23766742.205 | 19613104.9 | Completed | 1 | 2022-10-30 | 2023-07-14 | R6-D2-2020BEFF-13-NC | R6-D2-2020BEFF-13-NC | 2021-07-12 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 00:00:00 | Nesmark Construction Enterprises | Nearly completion on finishing works, and delivery of school furnitures. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | Region VI | Capiz | 115627 | Jamul-awon ES | PANAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 20180339.2794 | 13027738.3 | Completed | 1 | April 19, 2022 | 00:00:00 | R6-DepED-Capiz-CY2020-Last Mile School-Lot 2 | 0 | August 23, 2021 | September 1, 2021 | September 14, 2021 | October 11, 2021 | October 21, 2021 | ORANGEKONSTRUCT CIVIL ENGINEERING SERVICES | Schedule of pre-procurement 8/17/2021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 18733377.0103 | 11945444.38 | Completed | 1 | May 2, 2022 | 00:00:00 | R6-DepED-Capiz-CY2020-Last Mile School-Lot 1 | 0 | August 23, 2021 | September 1, 2021 | September 14, 2021 | October 11, 2021 | November 3, 2021 | GREATMAN BUILDERS | Schedule of pre-procurement 8/17/2021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VI | Guimaras | 115914 | Panobolon ES | Nueva Valencia | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20808548.5734 | 20660439.7 | completed | 1 | March 27, 2022 | 2022-07-05 | 06-2021 | 06-2021 | June 22, 2021 | July 13, 2021 | July 27, 2021 | August 8, 2021 | August 24, 2021 | EZ Gold Construction and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VI | Iloilo | 501244 | Barasalon Integrated School | Janiuay I | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20311610.0883 | 17258671.73 | completed | 1 | 2022-02-26 | 2024-12-06 | LMS2020-RVI-022-ILOILO-B1-L1 | LMS2020-RVI-022-ILOILO-B1-L1 | 2021-07-27 | 2021-08-02 | 2021-08-17 | 2021-09-07 | 2021-09-29 | NOE'S Builders | -as of Feb2024- Liquidated damages were imposed; -For Termination; low paced workmasnhip; Based on the actual ocular | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | 1 | 1 | [7 empty] | 1
LMS 2020 | Region VII | Bohol | 300519 | Mahanay High School | TALIBON | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 9750782.823 | 7050000 | Completed | 1 | 2022-03-17 | 2022-08-05 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | Inabanga Drilling Conts Steel Fab and Gen Mdse | Request Extension due to destruction of port due to Typhoon Odette(not ganted by the BAC) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Biliran | 120823 | Patag PS | CULABA | 0 |  | 2 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21651795.6852 | 21598532.41 | Completed | 1 | 2021-12-16 | 2021-12-16 | 0 | 0 | 44383 | 44393 | 44406 | 44413 | 44419 | BNL CONSTRUCTION | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Biliran | 120823 | Patag PS | CULABA | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM |  | 21598532.41 | Completed | 1 | 2021-12-16 | 2021-12-16 | 0 | 0 | 44383 | 44393 | 44406 | 44413 | 44419 | BNL CONSTRUCTION | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Eastern Samar | 122351 | Maybunga Elementary School | BALANGIGA | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19420561.689 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 44382 | 44391 | 44403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Eastern Samar | 122447 | Cabago-an Elementary School | Dolores II | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 18541208.7644 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 44382 | 44391 | 44403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VIII | Eastern Samar | 122482 | Domrog ES | General Macarthur-Hernani | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 16635123.7455 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 44382 | 44391 | 44403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VIII | Eastern Samar | 122670 | Trinidad Elementary School | ORAS | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 15021428.6362 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 44382 | 44391 | 44403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VIII | Eastern Samar | 122716 | Jagnaya Elementary School | SALCEDO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM (ISLAND SCHOOL) | 17042109.1641 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 44382 | 44391 | 44403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Leyte | 120941 | Bato Primary School | ALANGALANG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16960825.7074 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | July 7,2021 | July 16,2021 | July 28,2021 | 0 | 0 | 0 | Under Procurement (Post Qualification) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Leyte | 121670 | San Sebastian Primary School | MATAG-OB | 4 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20788630.0907 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | July 7,2021 | July 16,2021 | July 28,2021 | 0 | 0 | 0 | Under Procurement (Post Qualification) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Leyte | 121670 | San Sebastian Primary School | MATAG-OB | 4 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM |  | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | July 7,2021 | July 16,2021 | July 28,2021 | 0 | 0 | 0 | Under Procurement (Post Qualification) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Leyte | 120883 | Bagacay Elementary School | ABUYOG | 5 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16938129.654 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | July 7,2021 | July 16,2021 | July 28,2021 | 0 | 0 | 0 | Under Procurement (Post Qualification) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Northern Samar | 122789 | Sta. Rita Elementary School | ALLEN | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17217117.1363 | 17212110.08 | Completed | 1 | 2021-12-09 | 2021-12-09 | LMS2020-RVIII-NS-002 | 0 | July 1, 2021 | July 9, 2021 | July 21, 2021 | July 28, 2021 | July 29, 2021 | SAL Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Northern Samar | 122834 | Cularima Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17394423.5653 | 17388058.37 | Completed | 1 | 2021-12-09 | 2021-12-09 | LMS2020-RVIII-NS-003 | 0 | July 1, 2021 | July 9, 2021 | July 21, 2021 | July 28, 2021 | July 29, 2021 | SAL Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Northern Samar | 122906 | Nago-ocan ES | CATUBIG | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17387809.9037 | 17382746.57 | Completed | 1 | 2021-12-09 | 2021-12-09 | LMS2020-RVIII-NS-001 | 0 | July 1, 2021 | July 9, 2021 | July 21, 2021 | July 27, 2021 | August 2, 2021 | SAL Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Samar (Western Samar) | 303484 | Patong National High School | CALBIGA | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19412032.2996 | 19391493.63 | Completed | 1 | 2021-12-10 | 2021-12-10 | 2020 RVIII(SAMAR) LMSP-NEWCON-L2 | 2020 RVIII(SAMAR) LMSP-NEWCON-L2 | 44384 | 44391 | 44403 | 44407 | 44387 | JFR CONSTRUCTION INC | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Samar (Western Samar) | 313731 | BONGA NHS | MOTIONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19465057.2996 | 19415053.12 | Completed | 1 | 2022-03-26 | 2022-04-13 | 2020 RVIII(SAMAR) LMSP-NEWCON-L1 | 2020 RVIII(SAMAR) LMSP-NEWCON-L1 | 44384 | 44391 | 44403 | 44407 | 44418 | GPUY CONSTRUCTION & SUPPLIES | WITH TIME EXTENSIONS AND WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Southern Leyte | 122006 | Himakilo Primary School | BONTOC | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 19945713.3403 | 19879801.57 | Completed | 1 | 2022-01-02 | 2022-07-05 | CY2020-LMS-L1 | CY2020-LMS-L1 | 44379 | 44386 | 44398 | 44402 | 44431 | VHITS D.G. BUILDERS & ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VIII | Southern Leyte | 122006 | Himakilo Primary School | BONTOC | 0 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM |  | 19879801.57 | Completed | 1 | 2022-01-02 | 2022-07-05 | CY2020-LMS-L1 | CY2020-LMS-L1 | 44379 | 44386 | 44398 | 44402 | 44431 | VHITS D.G. BUILDERS & ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0
LMS 2020 | Region VIII | Southern Leyte | 305533 | Malitbog National High School | MALITBOG | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17027925.1786 | 16962557.49 | Completed | 1 | 2022-01-02 | 2022-07-05 | CY2020-LMS-L2 | CY2020-LMS-L2 | 44379 | 44386 | 44398 | 44402 | 44431 | VHITS D.G. BUILDERS & ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region VIII | Southern Leyte | 122263 | Hindangan PS | SOGOD | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 14023567.0586 | 13973360.17 | Completed | 1 | 2021-12-18 | 2022-05-10 | CY2020-LMS-L3 | CY2020-LMS-L3 | 44379 | 44386 | 44398 | 44402 | 44431 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2020 | Region X | Bukidnon | 113623 | Lumatong Pangukayan Ta Apu Manohay | MARAMAG | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18157630.9036 | 13617950.39 | Ongoing | 0.89 | 2025-03-30 | 00:00:00 | PB-02-05-2024-005 | 0016-2024 | 2024-05-11 | 2024-05-20 | 2024-06-03 | 2024-06-06 | 2024-06-28 | CQ Haribon Construction | Terminated Contract No. 08-2021 with FFJJ Construction, New Contract No. 0016-2024, Php 4,579,658.48 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.89 | 0 |  | 1 | 1 | [7 empty] | 1
LMS 2020 | Region X | Gingoog City | 128071 | Mimbuntong Elementary School | GINGOOG CITY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,\ SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19025682.2429 | 17827523.07 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 2021-08-26 | 2021-08-28 | 2021-08-31 | IMBDC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1
LMS 2020 | Region X | Lanao del Norte | 127123 | Sta. Cruz ES | MAIGO | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 16818990.1918 | 13774087.91 | completed | 1 | 2021-02-28 | 2021-05-24 | 2020-01(Infra) | 43831 | 2020-08-19 | 2020-08-27 | 2020-09-21 | 2020-10-12 | 2020-11-23 | Lanao Genesis Construction Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2020 | Region X | Lanao del Norte | 200523 | Pelingkingan PS | TANGCAL | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 19741282.5164 | 0 | Reverted | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | failure of bid (under negotiation); return of funds | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0
LMS 2020 | Region XI | Davao De Oro | 204004 | Kaluyapi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17551559.7796 | 0 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | 1 | [5 empty] | CY 2023 |  |  | 1
LMS 2020 | Region XII | North Cotabato | 130239 | Dungoan ES | M'LANG | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20128417.6491 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2020 | Region XII | North Cotabato | 100863 | Colonsalnafil Elementary School | TULUNAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19394758.1121 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | 1 | [5 empty] | CY 2023 |  |  | 1
LMS 2020 | Region XII | South Cotabato | 136932 | Lemkati ES | Tboli | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH TOILET AND ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE AND SOLAR ENERGY SYSTEM | 16334333.676 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs |  | 1 | [7 empty] | 1
LMS 2020 | Region XII | South Cotabato | 136932 | Lemkati ES | Tboli | 2 |  | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH TOILET AND ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF SCHOOL FURNITURE AND SOLAR ENERGY SYSTEM | 16334333.676 | 0 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | previous yrs |  | 0 | [7 empty] | 1
LMS 2021 | CAR | Apayao | 135261 | Daga ES | CONNER | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE(3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHTING SYSTEM AND WATER SYSTEM | 10705275.29 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CAR | Apayao | 219014 | San Mariano ES | PUDTOL | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAIN WATER COLLECTOR,SCHOOL FURNITURE AND WATER SYSTEM | 8222048.5499 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | CAR | Benguet | 318918 | Adaoay National High School-Abucot Extn. | KABAYAN | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE(1) STOREY TWO(2) CLASSROOMS SCHOOL BUILDINGS (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM AND RETAINING WALL | 10887942 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CAR | Benguet | 135708 | Saguitlang Elementary School | TUBA | 0 | 1 | 4 | CONSTRUCTION OF ONE(1) STOREY FOUR(4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17529648.15 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CAR | Kalinga | 135970 | Bullalayao Primary School | BALBALAN | 0 | 1 | 1 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, RAIN WATER COLLECTOR AND WATER SYSTEM | 10930337.182 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CAR | Mt. Province | 136286 | Bagabag Elementary School | PARACELIS | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 13914381.12 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CAR | Tabuk City | 136172 | Mabato Elementary School | TABUK CITY | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12054411.3855 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CARAGA | Butuan City | 281539 | Salvacion Indigenous Community Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15725955.42 | 0 | Ongoing | 0.48 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.48 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | CARAGA | Cabadbaran City | 131524 | Mahaba Elementary school | CITY OF CABADBARAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18753240.13 | 0 | Ongoing | 0.4 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16963583.65 | 0 | Ongoing | 0.25 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region I | Ilocos Norte | 100034 | Morong ES | BADOC | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 18686642.15 | 0 | Ongoing | 0.25 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region I | Ilocos Sur | 100577 | Matue PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15489664.3886 | 13617950.39 | Abandoned | 0.45 | 2023-12-30 | 00:00:00 | PB-07-07-2021-0001 | 08 - 2021 | 2021-07-13 | 2021-07-21 | 2021-08-02 | ############### | 2021-10-06 | FFJJ Construction | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0.45 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region I | La Union | 101119 | Daeng ES | TUBAO | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, , SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 14037218.56 | 0 | Abandoned | 0.1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CENTRAL OFFICE IMPLEMENTED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region I | Pangasinan I, Lingayen | 101520 | Dalupang ES | MABINI | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17662294.1851 | 17662294.1851 | Abandoned | 0.6 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | no movement/accomplishment as of February 2023 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.6 | 0 |  |  | 1 | [7 empty] | 1
LMS 2021 | Region II | Cagayan | 501171 | Taguing Integrated School | BAGGAO | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 10068697.37 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | For Termination (CO Implemented/ WERR Construction) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region II | Cagayan | 102736 | Tucalana ES | LAL-LO | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SCHOOL FURNITURE, AND WATER SYSTEM | 10668836.2141 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | For Termination (CO Implemented/ WERR Construction) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region II | Isabela | 500501 | San Isidro Integrated School | SAN MARIANO | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17277440.4821 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region II | Isabela | 103024 | Bannawag Primary School | ANGADANAN | 3 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21460349.4148 | 0 | Abandoned | 0.1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region II | Isabela | 103024 | Bannawag Primary School | ANGADANAN | 3 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM, AND RETAINING WALL | 6520 | 0 | Abandoned | 0.11 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11 | 0 |  |  | 0 | 0 | [6 empty] | 1
LMS 2021 | Region II | Quirino | 104240 | Rang-ayan PS | Aglipay | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17024914.59 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region II | Quirino | 104297 | Cupianan PS | Diffun | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16810212.3404 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | The workers arrived at the school last Feb. 5, 2023 but materials and equipment were not yet delivered onsite as of Feb. 15, 2023 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Aurora | 157509 | Dianao ES | DILASAG | 0 | 1 | 3 | CONSTRUCTION OF ONE(1) STOREY THREE(3) CLASSROOM SCHOOL BUILDING WITH (COMMON TOILET) WITH PROVISION OF PERIMETER FENCE, SCHOOL FURNITURE, SOLAR PANEL AND WATER SYSTEM | 17990219.996 |  | Ongoing | 0.46 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.46 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bataan | 104651 | Kanawan Integrated School | MORONG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18332263.58 |  | Abandoned | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bataan | 500119 | Biaan Aeta IS | MARIVELES | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17423919.51 |  | Ongoing | 0.2 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Bulacan | 158504 | Talamsi I ES (Talamsi PS) | DOÑA REMEDIOS TRINIDAD | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17999033.7429 |  | Abandoned | 0.3 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Nueva Ecija | 105274 | E. Abalos PS | CUYAPO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER) ANDSCHOOL FURNITURE | 4992620.94 |  | Abandoned | 0.4 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region III | Pampanga | 306913 | Camias High School | PORAC | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 5520405.3423 |  | Ongoing | 0.7 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.7 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region III | Tarlac | 106672 | Macaguing Primary School | SANTA IGNACIA | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 8884909.37 |  | Abandoned | 0.5 | [9 empty] | WERR Corporation International JV Bancal Construction and Supply | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region III | Zambales | 281504 | Belbel Elementary School | BOTOLAN | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18534442.11 |  | Ongoing | 0.3 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IV-A | Laguna | 108465 | Pulong Mindanao ES | SANTA MARIA | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CL SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15744764.7134 |  | Terminated | 0 | [10 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IV-A | Quezon | 108739 | Ligpit Bantayan ES | GUINAYANGAN | 4 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17714094.3688 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | based on the spot checking report made last November by LMS team (Audit); pls see narrative reports | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.34 | 0 |  |  | 1 | [7 empty] | 1
LMS 2021 | Region IV-A | Rizal | 109518 | Rawang ES | TANAY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM (for 4CL), AND WATER SYSTEM (for 4CL) | 15006078.5261 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IV-A | Rizal | 109518 | Rawang ES | TANAY | 2 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6267959.3241 | 0 | Terminated | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | [6 empty] | 0
LMS 2021 | Region IV-A | Tayabas City | 109241 | Pandakake ES | CITY OF TAYABAS | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18110071.5632 | 0 | Completed | 1 | 00:00:00 | December 7 2023 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | WERR | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2021 | Region IV-B | CALAPAN CITY | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 8578776.11 | 8479929.95 | Completed | 1 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2021-AdmS4(006)-BI-CB-013a-C200 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2022-01-25 | WERR COPR. INTL. JV. WITH BANCAL CONST, & SUPPLY | SCHOOL FURNITURE NOT YET DELIVERED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region IV-B | CALAPAN CITY | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 5719184.08 | 8479929.95 | Completed | 1 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2021-AdmS4(006)-BI-CB-013a-C200 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 2022-01-25 | WERR COPR. INTL. JV. WITH BANCAL CONST, & SUPPLY | SCHOOL FURNITURE NOT YET DELIVERED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2021 | Region IV-B | Marinduque | 109922 | Bacongbacong PS | Gasan | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), AND WATER SYSTEM | 12631518.4833 | 0 | Ongoing | 0.62 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.62 | 0 |  |  | 1 | [7 empty] | 0
LMS 2021 | Region IV-B | Occidental Mindoro | 110128 | EMOK ES | MAGSAYSAY | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18796598.3373 | 0 | Terminated | 0.1582 | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1582 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IV-B | Palawan | 305600 | Tabon National High School | Quezon | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18320194.7555 | 0 | Abandoned | 0.2 | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | terminated (implemented by C.O) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.2 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IX | Isabela City | 133031 | Caro ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF (1) ONE STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 10045807.572 | 0 | Ongoing | 0.18 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.18 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IX | Zamboanga City | 126129 | Sapa Dulian ES | ZAMBOANGA CITY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND OF DRILLING FOR DEEPWELL WATER SYSTEM & SOLAR PUMP | 21293479.9976 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.34 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IX | Zamboanga City | 126129 | Sapa Dulian ES | ZAMBOANGA CITY | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND OF DRILLING FOR DEEPWELL WATER SYSTEM & SOLAR PUMP | 6520 | 0 | Ongoing | 0.34 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34 |  |  | 0 | 0 | [6 empty] | 1
LMS 2021 | Region IX | Zamboanga del Norte | 195529 | Basak ES | SIAYAN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 10394988.9397 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IX | Zamboanga del Sur | 300000 | Digon National High School | MARGOSATUBIG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18679356.24 | 0 | ABANDONED | 0.25 | 2022-08-29 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2022-05-31 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.25 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region IX | Zamboanga Sibugay | 125639 | Datagan ES | Kabasalan | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16697503.52 | 0 | Ongoing | 0.38 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | PRISMOIDAL CONSRUCTION CORPORATION | CENTRAL OFFICE MANAGED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.38 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region V | Camarines Norte | 501259 | Malaya IS | LABO WEST | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SOLAR ENERGY AND WATER SYSTEMS AND SCHOOL FURNITURE AND FENCING AND SLOPE PROTECTION | 29291757.9847 | 0 | TERMINATED | 0.3 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CENTRAL OFFICE IMPLEMENTED | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region V | Camarines Sur | 113033 | Bagong Sirang Elementary School | SIRUMA | 4 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR,SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM | 10580022.8319 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.55 | 0.45 | 5.25 |  | 1 | [7 empty] | 0
LMS 2021 | Region V | Camarines Sur | 113107 | San Rafael ES | TIGAON | 4 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 10240762.8319 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.45 | 0.55 | 5.25 |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region V | Camarines Sur | 112358 | Santiago Elementary School | BALATAN | 5 | 1 | 4 | PROPOSED CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 14849440.7976 | 0 | Ongoing | 0.99 |  |  | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0.54 | 6.25 |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | CARAMORAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, PERIMETER FENCE (1 BAY = 3.0m) | 10114683.1467 | 0 | terminated | 0.0505 | [10 empty] | FOR TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.0505 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region V | Catanduanes | 113356 | Buenavista ES | VIRAC (Capital) | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, PERIMETER FENCE (1 BAY = 3.0m) | 10114683.1467 | 0 | terminated | 0.55 | [10 empty] | FOR TERMINATION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.55 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region V | Sorsogon | 114142 | Cristo Elementary School | DONSOL | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 7538498.756 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Inaugurated (November) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2021 | Region V | Sorsogon | 114296 | Malbog Elementary School | MAGALLANES | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SCHOOL FURNITURE,WATER SANITATION AND WATER SYSTEM | 10174305.4412 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 0
LMS 2021 | Region VI | Aklan | 500544 | Mambuquiao Integrated School | BATAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19683914.12 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2021 | Region VI | Aklan | 114804 | Bacyang PS | MADALAG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19567467.6 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2021 | Region VI | Antique | 178514 | Omlot PS (realigned from Tigunhao PS) | Laua-an | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20850221.18 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED. The school was re-aligned to Omlot PS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VI | Capiz | 115617 | Bantigue ES | PANAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20322685.02 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VI | Iloilo | 501248 | Adgao-Tagpuan-Ingay Integrated School | TUBUNGAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17764390.36 | 0 | Ongoing | 0.98 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED; Rectification of Punchlist | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0.03 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VI | Iloilo | 116180 | Caratagan PS | CALINOG | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20557581.5038 | 0 | Not Yet Started | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED. NPA threats | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VI | Kabankalan City | 117891 | Sagumayon PS | Kabankalan City | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 24548206.13 | 0 | Ongoing | 0.95 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VI | Negros Occidental | 302631 | Florentina C. Recto MHS - Caliling Ext | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12162474.45 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VI | Negros Occidental | 117008 | Patol Elementary School | CAUAYAN | 6 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17312723.74 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VI | Negros Occidental | 116982 | Talangnan ES | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19254393.25 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VII | Bogo City | 119105 | Anonang Norte ES | CITY OF BOGO | 4 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17588188.9435 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2021 | Region VII | Bohol | 117974 | Cansibuan PS | ANTEQUERA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 8051837.57 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Bohol | 118473 | Biasong ES | LOON | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9532846.1644 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Bohol | 118780 | Carmen Mellijor PS | TUBIGON | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6286948.88 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Site issues | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region VII | Bohol | 118349 | Biabas ES | GUINDULMAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9289481.37 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 0
LMS 2021 | Region VII | Carcar City | 119157 | Cara-atan Elementary School | CITY OF CARCAR | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17400878.67 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 |  | 1 | [7 empty] | 1
LMS 2021 | Region VII | Cebu | 118926 | Catang PS | ARGAO | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 9541017.1149 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Cebu | 118975 | Kaluangan I PS | ASTURIAS | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10414217.32 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Cebu | 119466 | Maharuhay ES | MEDELLIN | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, AND SCHOOL FURNITURE | 6563376.1669 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region VII | Cebu | 119448 | Palaypay PS | MALABUYOC | 7 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 8618124.5 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Danao City | 119352 | Melecio B. Tito ES | DANAO CITY | 5 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET), WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE AND WATER SYSTEM | 9616220.8261 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region VII | Negros Oriental | 120038 | Canlukduhan ES | AYUNGON | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17295671.81 | 17268197.24 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VII | Negros Oriental | 120303 | Mongpong Primary School | JIMALALUD | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16599217.8707 | 16572079.83 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VII | Negros Oriental | 120482 | Agan-an Elementary School | SIBULAN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16382034.5205 | 16354914.9 | completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VII | Negros Oriental | 120443 | Antulang Elementary School | SIATON | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16529232.17 | 16502080.2 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VII | Talisay City | 233505 | Campinsa Elementary School | CITY OF TALISAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10909009.1202 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0
LMS 2021 | Region VIII | Baybay City | 121093 | Sta. Cruz Elementary School | CITY OF BAYBAY | 5 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18363790.1292 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2021 | Region VIII | Borongan City | 122384 | San Andres Upper ES | CITY OF BORONGAN (Capital) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17844618.71 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NPA threats | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VIII | Calbayog City | 124082 | Cag-Anahaw Elementary School | CALBAYOG CITY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17574451.8 | CO IMPLEMENTED | Ongoing | 0.45 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VIII | Catbalogan City | 123393 | Cagudalo Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13637820.5287 | 0 | Ongoing | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NPA threats | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VIII | Leyte | 120947 | Canvertudes Primary School | ALANGALANG | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16755680.1115 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VIII | Leyte | 121044 | Balire Primary School | BARUGO | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16711986.9618 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2021 | Region VIII | Maasin City | 122153 | Bogo Multigrade School | CITY OF MAASIN (Capital) | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18370407.4436 | c/o CO | COMPLETED | 1 | c/o CO | 2024-05-02 | c/o CO | 2021-AdmS4(006)-BI-CB-013a-C204 | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | D.L Cervantes Construction Corporation JV 818 Dragon Construction | INAUGURATED (AUGUST 2023), CO IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2021 | Region VIII | Ormoc City | 124157 | Lake Danao Elementary School | ORMOC CITY | 4 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY THREE (3) CLASSROOMS (WITH COMMON TOILET) SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 9006106.97 | 8978795.07 | COMPLETED | 1 | c/o CO | 2023-07-14 | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | D.L Cervantes Corporation JV 818 Dragon Construction | inaugurated (August 2023) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2021 | Region VIII | Ormoc City | 124157 | Lake Danao Elementary School | ORMOC CITY | 4 |  | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOM (WITH COMMON TOILET) SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6004071.32 | 8978795.07 | COMPLETED | 1 | c/o CO | 2023-07-14 | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | c/o CO | D.L Cervantes Corporation JV 818 Dragon Construction | inaugurated (August 2023) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 4.25 |  | 0 | 0 | [6 empty] | 0
LMS 2021 | Region VIII | Samar (Western Samar) | 136923 | ARONG ES | GANDARA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19206793.96 | CO IMPLEMENTED | Ongoing | 0.95 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | Substantially Completed | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0.05 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region VIII | Southern Leyte | 122313 | Carnaga Elementary School | TOMAS OPPUS | 0 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9932687.594 | CO IMPLEMENTED | COMPLETED | 1 | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | CO IMPLEMENTED | COMPLETED - Central Office Implemented | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 0
LMS 2021 | Region X | Bukidnon | 113721 | Makabugwas Ta San Dionesio | TALAKAG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16205887.9248 | 0 | ABANDONED | 0.41 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Letter request for suspension was sent to the Central Office. No Response from CO. This is a CO Implemented project. We cannot fill in the details. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.41 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region X | Misamis Occidental | 127367 | Migubay PS | Concepcion | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13433577.8053 | 0 | Ongoing | 0.14 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Waiting for approved DAED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.14 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region X | Misamis Occidental | 127496 | Deboloc ES | Plaridel | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15202037.935 | 0 | Ongoing | 0.1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Waiting for approved DAED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.1 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region X | Misamis Oriental | 130200 | Aligodon Higaonon Tulogan Nauhanan | CLAVERIA | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19652994.9643 | 0 | Ongoing | 0.33 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | No Movement in Site (Abandoned); Building permit on Process, Contractor requested fot Time extension due to weather condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.33 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region X | Misamis Oriental | 130200 | Aligodon Higaonon Tulogan Nauhanan | CLAVERIA | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 6520 | 0 | Ongoing | 0.33 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | No Movement in Site (Abandoned); Building permit on Process, Contractor requested fot Time extension due to weather condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 |  |  | 0 | 0 | [6 empty] | 1
LMS 2021 | Region X | Ozamis City | 128190 | Balintawak Elementary School | OZAMIS CITY | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18244962.88 | 0 | Ongoing | 0.13 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Under Work Suspension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.13 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XI | Davao City | 108181 | Alon ES | DAVAO CITY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21434086.41 |  | Abandoned | 0.05 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.05 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XI | Davao City | 108181 | Alon ES | DAVAO CITY | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 6520 |  | Abandoned | 0.02 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 |  |  | 0 | 0 | [6 empty] | 1
LMS 2021 | Region XI | Davao De Oro |  | Amogad ES | LAAK (SAN VICENTE) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17426779.43 |  | Abandoned | 0.12 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.12 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XI | Davao del Norte | 204529 | Ngan PS | KAPALONG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, , AND WATER SYSTEM | 15998850.0145 |  | Abandoned | 0.09 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.09 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XI | Davao del Norte |  | Ibuyag Logsi KM 31 Ext | Talaingod | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS & ONE (1) STOREY - ONE (1) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, , AND WATER SYSTEM | 25796525.5025 |  | Abandoned | 0.1 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XI | Davao Oriental | 501608 | Modesto T. Veroy Sr. IS | CATEEL | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, TRANSMISSION LINE AND WATER SYSTEM | 14392154.4667 |  | Abandoned | 0.4 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 0
LMS 2021 | Region XI | Davao Oriental | 501608 | Modesto T. Veroy Sr. IS | CATEEL | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, TRANSMISSION LINE AND WATER SYSTEM | 6520 |  | Abandoned | 0.3 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 |  |  | 0 | 0 | [6 empty] | 0
LMS 2021 | Region XII | North Cotabato | 130084 | Balawan ES | MAKILALA | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19188630.3041 | 0 | Ongoing | 0.3 | CO Procured and subject for termination due to Prismoidal Contruction abandoned the project | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2021 | Region XII | Sarangani | 208019 | Nicomedes I. Sunio ES | MALUNGON | 0 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM and SCHOOL FENCE | 20549897.8317 | 0 | Ongoing | 0.25 | CO Procured and subject for termination due to Prismoidal Contruction abandoned the project | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0 |  |  | 0 | 1 | [6 empty] | 1
LMS 2022 | CAR | Abra | 135208 | Collago ES | LAGAYAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, AND WATER SYSTEM | 9300666.8908 | 9194846.22 | COMPLETED | 1 | 2024-04-05 | 2023-07-15 | OSEC-CAR-22-6291 | CAR-ABRA-2022-04-002 | 2022-03-25 | April 1, 2022 | April 13, 2022 | April 27, 2022 | September 22, 2022 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | CAR | Abra | 135186 | Lam-aoan PS | SALLAPADAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SLOPE PROTECTION, WATER SYSTEM AND REPAIR OF CLASSROOM | 20019229.9273 | 19802771.1823 | completed | 1 | 2023-12-22 | 2023-07-15 | OSEC-CAR-22-6778 | CAR-ABRA-2022-016 | October 12, 2022 | October 19, 2022 | November 2, 2022 | November 10, 2022 | November 24, 2022 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 0
LMS 2022 | CAR | Abra | 109752 | MANICBEL PRIMARY SCHOOL | SALLAPADAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SLOPE PROTECTION AND WATER SYSTEM | 19207305.1582 | 19001015.84 | COMPLETED | 1 | 2023-12-22 | 2023-07-15 | OSEC-CAR-22-6291 | CAR-ABRA-2022-04-001 | 2022-03-25 | April 1, 2022 | April 13, 2022 | sq | a1 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | CAR | Benguet | 135675 | Ebbes ES | SABLAN | 0 | 1 | 14 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM, REPAIR AND REHABILITATION OF CALSSROOMS AND IMPROVEMENT OF SCHOOLS FACILITIES | 25486535.9768 | 22001471.0172 | Completed | 1 | JULY 17, 2023 | 11/20/2023 | LMS-2022-01 | LMS-2022-01 | May 11, 2022 | May 18, 2022 | May 31, 2022 | 2022-09-09 | 0CTOBER 6, 2022 | JRF ANGOYNA GENERAL CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21324715.1738 | 18159900.5203 | Completed | 1 | 2023-08-21 | 2023-08-14 | LMS-2022-02 | LMS-2022-01 | May 11, 2022 | May 18, 2022 | May 31, 2022 | 2022-09-09 | 0CTOBER 6, 2022 | JRF ANGOYNA GENERAL CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CAR | Benguet | 135725 | Dorencio ES | TUBLAY | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18770107.0743 | 17086845.6 | COMPLETED | 1 | 2023-11-10 | 2023-11-30 | LMS-2022-01 | LMS-2022-01 | November 04, 2022 | November 11, 2022 | November 24, 2022 | 2023-01-20 | 2023-02-13 | KAT BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CAR | Ifugao | 135799 | Namal ES | ASIPULO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SLOPE PROTECTION, WATER SYSTEM AND PERIMETER FENCE (ONE BAY, 3.0M) WITH VEHICULAR AND PEDESTRIAN ENTRANCE/EXIT GATES | 23515376.9847 | 23275032.58 | Completed | 1 | 2024-10-31 | 2025-05-30 | LMS-2023-.02 | LMS-2023-.03 | 2023-11-29 | 2023-12-06 | 2023-12-19 | 2024-02-07 | 2024-03-05 | HAIGHTS CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.98 | 0.02 | 5.25 |  | 0 | 1 | [6 empty] | 0
LMS 2022 | CAR | Ifugao | 135800 | Nangkatengey ES | ASIPULO | 0 | 1 | 6 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE,SOLAR PV ENERGY SYSTEM AND WATER SYSTEM AND CONSTRUCTION OF ONE (1) STOREY -TWO(2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, PERIMETER FENCE (ONE BAY, 3.0M) WITH VEHICULAR AND PEDESTRIAN ENTRANCE/EXIT GATES AND SLOPE PROTECTION | 28545849.0892 | 28270735.81 | Completed | 1 | 2024-10-30 | 2025-03-25 |  | 2023-10 | 2022-12-27 | 2023-01-03 | 2023-01-17 | September 14,2023 | 2023-09-29 | Northern Communications Inc. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE,AND WATER SYSTEM | 11549894.5466 | 10323114.96 | Completed | 1 | 2023-06-05 | July 20, 2023 | LMS 2022-CAR-Kalinga-002 | LMS 2022-CAR-Kalinga-002 | August 12,2022 | August 19,2022 | August 31,2022 | October 14, 2022 | December 22, 2022 | Bangyan 3D Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 |  | 0 | 1 | [6 empty] | 0
LMS 2022 | CAR | Kalinga | 136019 | Cagaluan Elementary School | PASIL | 0 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH DETACHED TOILET) WITH SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE AND WATER SYSTEM | 12754502.0283 | 12625269.69 | Completed | 1 | 2024-02-21 | August 12, 2024, 2023 | LMS 2022-CAR-Kalinga-001 | LMS 2022-CAR-Kalinga-001 | August 12,2022 | August 19,2022 | August 31,2022 | October 14, 2022 | December 21, 2022 | Stellar JFS General Engineering and Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2022 | CAR | Kalinga | 136020 | Cagaluan ES Annex (Da-o PS) | PASIL | 0 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH DETACHED TOILET) WITH SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE AND WATER SYSTEM | 13755283.8632 | 9168628.55 | Completed | 1 | 2024-06-13 | 2024-09-12 | LMS 2022-CAR-Kalinga-002 | LMS 2022-CAR-Kalinga-002 | July 6, 2023 | July 13, 2023 | July 24, 2023 | September 19, 2023 | October 25, 2023 | NIHK Construction Services | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 |  | 1 | [7 empty] | 0
LMS 2022 | CAR | Mt. Province | 136188 | Latang Elementary School | BARLIG | 0 | 1 | 4 | CONSTRUCTION OF ELEVATED ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, PERIMETER FENCE AND REPAIR OF TWO (2) CLASSROOM SCHOOL BUILDING. | 32409555.9892 | 32000000 | Completed | 1 | 2023-11-10 | January 26, 2024 | INF-2022 LMS-003 | INF-2022 LMS-003 | 2022-11-13 | 2022-12-05 | 2022-12-05 | 2022-12-19 | 2023-01-04 | BAJE CONSTRUCTION | completed W/ time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CAR | Mt. Province | 136334 | Belwang Elementary School | SADANGA | 0 | 1 | 4 | CONSTRUCTION OF ELEVATED ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, PERIMETER FENCE AND REPAIR OF TWO (2) CLASSROOM SCHOOL BUILDING. | 32899132.2087 | 13427411.97 | Completed | 1 | 2024-02-15 | 2024-03-25 | INFRA2023-002 | INFRA2023-002 | 2023-05-02 | 2023-05-16 | 2023-05-25 | 2023-06-02 | 2023-07-20 | DANREV | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CAR | Mt. Province | 136348 | Kilong Elementary School | SAGADA | 0 | 1 | 4 | CONSTRUCTION OF ELEVATED ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, PERIMETER FENCE AND REPAIR OF TWO (2) CLASSROOM SCHOOL BUILDING. | 34321745.8749 | 16945355.98 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-018 | BEFF-INFRA2023-018 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CAR | Tabuk City | 137049 | Callagan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m) AND WATER SYSTEM | 17836389.9806 | 16943551 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-019 | BEFF-INFRA2023-019 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | CARAGA | Agusan del Norte | 131530 | Balangbalang ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR,SLOPE PROTECTION, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 22633517.1088 | 12091132.49 | Completed | 1 | 2023-11-22 | 2023-11-22 | 2023-001-LMS-CARAGA | 006-2023 | 2023-04-20 | 2023-04-27 | 2023-05-09 | 2023-05-24 | 2023-05-26 | AMALGO CONSTRUCTION | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 304823 | Cab-ilan National High School | DINAGAT | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25399321.6421 | 11736814.2 | Completed | 1 | 2024-05-25 | 2024-06-22 | LMS-001 | 44958 | 18/04/2022 | 29/04/2022 | 13/05/2022 | 2022-06-07 | 2022-07-26 | RJB CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23245664.4637 | 21098025.14 | COMPLETED | 1 | 2024-11-20 | 2025-05-22 | INFRA2023-004 | INFRA2023-004 | 2023-12-04 | 2023-12-11 | 2024-01-03 | 2024-01-31 | 2024-05-25 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21422137.7841 | 21036508.36 | Completed | 1 | 2022-12-28 | 2023-06-06 | INFRA22-003-02 | PB-05-2023 | 2023-07-03 | 2023-07-10 | 2023-07-24 | 2023-08-14 | 2023-08-25 | ARDRAW | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | CARAGA | Siargao | 132186 | Katipunan Elementary School | PILAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20882792.8856 | 17970756.58 | Completed | 1 | 2022-12-28 | 2022-12-05 | BEFF-INFRA2022-008 | BEFF-INFRA2022-008 | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-05-10 | 2022-05-19 | RELY CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Siargao | 132207 | Bailan Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20884952.7605 | 16246968.08 | Completed | 1 | 2022-12-28 | 2023-03-18 | BEFF-INFRA2022-009 | BEFF-INFRA2022-009 | 2022-03-31 | 2022-04-07 | 2022-04-21 | 2022-05-10 | 2022-05-19 | INNOVATI CONSTRUCTION CORP | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132349 | Little Baguio ES | BACUAG | 2 | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF 1 STY 1 CL DEPED STANDARD BUILDING | 17775494.1415 | 17586011.08 | COMPLETED | 1 | 2024-07-03 | 2023-11-06 | 2023LMSRO1-02 | SDOLU-LMS 2023-2 | 2023-11-20 | 2023-11-29 | 2023-12-13 | 2023-12-26 | 2024-01-05 | LAV CONSTRUCTION AND SUPPLY | DIVISION IMPLEMENTED ( SUSPENDED DUE TO NON PASSABLE SITE) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132463 | Sohoton ES | MALIMONO | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF 1STY 2 CL BLSB TYPE I BUILDING | 17220573.8108 | 10698569.48 | Completed | 1 | 2023-12-26 | 2024-04-29 | LMS 2022-RII-CAGAYAN-001 | INFRA2023 045 LOT 1 | 2023-05-08 | 2023-05-16 | 2023-05-29 | 2023-06-19 | 2023-06-22 | GANIE CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132528 | Gacepan ES | SISON | 2 | 1 | 5 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF TWO (2) 1STY 3 CL BLSB TYPE I BUILDING | 19503501.2023 | 15072295.7 | Completed | 1 | 2023-11-07 | February 13m 2024 | LMS 2022-RII-CAGAYAN-002 | INFRA2023 045 LOT 2 | 2023-05-08 | 2023-05-16 | 2023-05-29 | 2023-06-19 | 2023-06-22 | YZK CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Norte | 132547 | SALVACION ES | TAGANA-AN | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR/REHABILITATION OF TWO (2) UNITS 1STY 2 CL BLSB TYPE I BUILDING | 17808072.6712 | 14214688.77 | COMPLETED | 1 | 2023-07-18 | 2024-02-02 | 2022-004-LMS-CARAGA | 003-2023 | 2022-12-28 | 2023-01-05 | 2023-01-17 | 2023-02-01 | 2023-02-03 | DANREV CONSTRUCTION AND SUPPLY | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | CARAGA | Surigao del Sur | 214548 | Tabinas Indigenous Community Elementary School | CARMEN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, AND FLOOD MARKER | 21084577.8768 | 17818880.19 | Completed | 1 | 2024-05-15 | 2024-08-01 | CY2023 LMS | CY2023 LMS | 2023-06-26 | 2023-07-03 | 2023-07-17 | 2023-08-15 | 2023-09-13 | Rely Construction and Supply | with Time Extensions due to unworkable days due to bad weather condition and delays in the delivery of materials due to unpassable road | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region II | Batanes | 102319 | Yawran Barrio School | ITBAYAT | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 10213731.6964 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 2023-06-26 | 2023-07-10 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 0 | 1 | [6 empty] | 0
LMS 2022 | Region II | Batanes | 102327 | Nakanmuan Elementary School | SABTANG | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH SOLAR PV ENERGY AND WATER SYSTEM, SCHOOL FURNITURE, SLOPE PROTECTION, AND SANITATION FACILITIES IN THE LAST MILE SCHOOL CONSTRUCTION OF GROUP HANDWASHING FACILITIES, REPAIR OF EXISTING THREE (3) CLASSROOMS CONSTRUCTION OF POWERHOUSE (FOR FUTURE ELECTRIFICATION PROJECT) AND SERVICE ENTRANCE POST | 10379721.43 |  | COMPLETED | 1 | March 27, 2025 | March 26, 2025 | 2022-11-0196 | 2022-11-0196 | May 5, 2023 | April 13, 2023 | June 14, 2023 | August 11, 2023 | August 23, 2023 | Achanzar Construction | with realignment change in scope of work but same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | 1 | 2 | 10379721.43 |  |  |  | 1
LMS 2022 | Region II | Cagayan | 501587 | Bural Integrated School | RIZAL | 2 | 1 | 6 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING and ONE (1) STOREY FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER | 24792922.25 | 20313727.82 | COMPLETED | 1 | February 10, 2024 | July 30, 2024 | LMS 2022-RII-CAGAYAN-002 | INFRA 2023-044 | MAY 8, 2023 | MAY 15, 2023 | MAY 29, 2023 | JUNE 20, 2023 | JUNE 30, 2023 | FOREF CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 |  | 0 | 1 | 1 | 6 | 24792922.25 |  |  |  | 0
LMS 2022 | Region II | Cagayan | 501586 | San Juan ES | RIZAL | 2 | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 19396557.12 | 14311206.33 | COMPLETED | 1 | 2024-04-23 | November 29, 2023 | LMS 2022-RII-CAGAYAN-002 | INFRA2022-065 | 2023-10-20 | 2023-10-26 | 2023-11-06 | 2023-12-20 | 2023-12-29 | GCPK CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region II | Nueva Vizcaya | 281559 | Hukhukyung PS | AMBAGUIO | 0 | 1 | 6 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 31443712.89 | 21138448.62 | COMPLETED | 1 | 2024-02-04 | 03/18/2025 | PB11-CY2022-LMSP-INFRA-01-02 | PB12-013 S.2022 | 11/25/2022 | 2022-02-12 | 12/14/2022 | 12/19/2022 | 12/23/2022 | CAB Construction & Supply | With time extension due to bad weather condition and variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | Region II | Nueva Vizcaya | 103995 | Napo ES | AMBAGUIO | 0 | 1 | 8 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY -TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 31517947.89 | 22529216.03 | COMPLETED | 1 | 2024-02-04 | 03/18/2025 | PB11-CY2022-LMSP-INFRA-01-02 | PB12-014 S.2022 | 11/25/2022 | 2022-02-12 | 12/14/2022 | 12/19/2022 | 12/23/2022 | CAB Construction & Supply | with time extension due to road inaccessibilty, bad weather condition and extra work order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | Region II | Quirino | 156518 | La Paz ES Extension Annex | SAGUDAY | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 18060120.777 | 17930000 | Completed | 1 | 2024-02-04 | 00:00:00 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 00:00:00 | 00:00:00 | 00:00:00 | 2023-07-12 | Botey Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region IV-A | Batangas | 107208 | Coral na Munti ES | Agoncillo | 3 | 1 | 4 | CONSTRUCTION OF TWO UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23885332.0158 | 23500000 | COMPLETED | 1 | 2023-04-11 | 2023-06-16 | AGONCILLO LMS 2022 - RIVA - BATANGAS - 01 | CY 2022 BEFF | 2022-06-22 | 2022-06-29 | 2022-07-11 | 2022-08-02 | 2022-10-04 | Botey Construction | Certificate of Time Extension was granted to the contractor for 30days, with Liquidated damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2022 | Region IV-B | Palawan | 110744 | Maracañao Elementary School | AGUTAYA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20470791.2919 | 20622113.46 | Completed | 1 | 2023-12-26 | 00:00:00 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 05-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-19 | 2023-05-26 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region IV-B | Romblon | 111254 | Agbay-Ang ES | ALCANTARA | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND SLOPE PROTECTION | 19037682.2232 | 21050000 | Completed | 1 | 2024-01-25 | 00:00:00 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 04-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-18 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 1 | [7 empty] | 1
LMS 2022 | Region IX | Zamboanga del Norte | 124538 | Head Tipan ES | MUTIA | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15387438.1528 | 15899497.92 | Completed | 1 | 2023-04-10 | 2023-04-10 | 2022-055-CBZN | CB-2022-039 | 2022-10-28 | 2022-11-07 | 2022-11-18 | 2022-12-01 | 2022-12-07 | YSL BUILDERS | none | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region IX | Zamboanga del Norte | 124609 | Nilabo ES | RIZAL | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 21731277.2877 | 22131576 | COMPLETED | 1 | 2022-12-31 | 2023-02-20 | LMS2020-RIX-ZAMBOANGA DEL NORTE | LMS 2022-RIX-ZDN-01 | 2022-04-04 | 2022-04-13 | 2022-04-25 | 2022-05-04 | 2022-06-30 | YSL Builders | none | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region IX | Zamboanga del Sur | 125086 | INIGO G. MERCADO PS | JOSEFINA | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18280842.6521 | 17133688.9 | COMPLETED | 1 | 2022-12-26 | 2022-12-19 | ZDS-22-LMS-01 | ZDS-22-LMS-01 | 2023-04-05 | 2023-04-14 | 2023-04-27 | 2023-05-30 | 2023-06-07 | GENETIAN BUILDERS AND ENTERPRISES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2022 | Region IX | Zamboanga Sibugay | 125845 | Bualan ES | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7551146.3957 | 25295175.54 | COMPLETED | 1 | 2024-10-25 | 2025-01-10 | 2023-024-CBZN | CB2023-023 | Nov. 14, 2023 | Nov. 24, 2023 | Dec. 07, 2023 | Dec. 18, 2023 | Dec. 28, 2023 | YSL BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 0
LMS 2022 | Region IX | Zamboanga Sibugay | 303871 | Kasigpitan NHS | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7571189.8457 | 18787999.57 | Completed | 1 | 2024-10-25 | 2025-01-10 | ZDS-23-LMS-01 | ZDS-23-LMS-01 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | Genetian Builders & Enterprises Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 0
LMS 2022 | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11431953.6095 | 18086919.56 | Completed | 1 | 2023-11-04 | 2024-05-03 | ZDS-23-LMS-02 | ZDS-23-LMS-02 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | Genetian Builders & Enterprises Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2022 | Region IX | Zamboanga Sibugay | 125850 | Mahayahay ES | TALUSAN | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 7540541.3957 | 11154681.24 | Completed | 1 | 2024-10-25 | 2025-01-10 | ZS-2023-LMS-01 | ZS-2023-LMS-01 | 2023-04-04 | 2023-04-17 | 2023-04-28 | 2023-06-23 | 2023-07-07 | Shameem Construction | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 0
LMS 2022 | Region V | Catanduanes | 302074 | Bato RDHS | BATO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, AND WATER SYSTEM | 13040244.7845 | 17798245.81 | Completed | 1 | 2023-11-01 | 00:00:00 | 0 | 0 | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-16 | 2023-06-29 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, AND WATER SYSTEM | 23006293.5345 | 19137563.67 | Completed | 1 | 2023-02-23 | 00:00:00 | 0 | 44743 | 00:00:00 | 00:00:00 | 2022-05-26 | 00:00:00 | 2022-07-26 | Hi-Tone Construction & Devt. Corp. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 | [6 empty] | CY 2023 |  |  | 0
LMS 2022 | Region VI | Aklan | 114710 | TABUNGYAN ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 19158007.7445 | 18808160.79 | Completed | 1 | 2023-12-01 | 2023-12-05 | INFRA 2023-05-002 | 2023-07-001 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-10 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VI | Aklan | 501181 | Vivo Integrated School | Tangalan | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM, PERIMETER FENCE 200 Meters | 19740374.5242 | 19000879.05 | Completed | 1 | 2023-12-01 | November 24, 2023 | INFRA 2023-05-002 | 2023-07-002 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-06 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VI | Antique | 114975 | Buenavista ES | BELISON | 0 | 1 | 11 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, AND REPAIR/REHABILITATION OF 7 CLASSROOMS | 21786950.5096 | 16550995.27 | Completed | 1 | 2023-12-01 | 2024-07-08 | R6-D2-2022BEFF-37-NC | R6-D2-2022BEFF-37-NC | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-21 | 2022-12-21 | Nesmark Construction Enterprises | Completed as per approved plans and variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 1 | [7 empty] | 1
LMS 2022 | Region VI | Antique | 115129 | Igcagay PS | LIBERTAD | 0 | 1 | 2 | CONSTRUCTION OF ONE(1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR AND REHABILITATION OF 2 CLASSROOMS | 15795342.76 | 12901507.38 | Completed | 1 | 2023-12-01 | October 14, 2024 | R6-D2-BEFF2023-11-NC | R6-D2-BEFF2023-11-NC | 2023-06-19 | 2023-06-26 | 2023-07-03 | Augut 17, 2023 | 2023-08-29 | D' X-man Builders Corporation | Completed as per approved plans and variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | 1 | 4 | 15795342.76 |  |  |  | 1
LMS 2022 | Region VI | Guimaras | 115853 | Miagos Primary School | SAN LORENZO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 12611496.1788 | 12298193.75 | Completed | 1 | 2023-12-01 | 2023-09-23 | 03-2022-lot 1 | No. 03-A-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-09-26 | ARRIANNE MERCHANDISING AND CONSTRUCTION SERVICES, INC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | Region VI | Iloilo | 116117 | Tubod PS | BINGAWAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS 7x36 (MODIFIED STANDARD DPWH-DEPED) WITH TOILET EACH CLASSROOM, SOLAR PANEL @ WATER SUPPLY SYSTEM | 16950819.24 | 13831624.51 | Completed | 1 | 2024-04-06 | 2024-08-07 | BEFF2022-RVI-022-LMS-L1 | BEFF2022-RVI-022-LMS-L1 | 17/04/2023 | 24/04/2023 | 2023-08-05 | 29/06/2023 | 2023-03-08 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | 1 | 4 | 16950819.24 |  |  |  | 1
LMS 2022 | Region VII | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16249807.0207 | 16152092.89 | Completed | 1 | 2023-07-19 | 2023-07-19 | ITB 2022-10-136 | LMS202211017 | 2022-10-18 | ############# | ############# | ############# | 2022-12-09 | TRINITYCAD CORPORATION | With approved Time Extension & Variation order - extra work. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Biliran | 120765 | Palayan ES | ALMERIA | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16596356.1681 | 11728643.08 | Completed | 1 | 2024-05-01 | 2024-06-25 | 2022INFRA-LMS-04 | LMS 2023CONSTRUCTION-04 | 45089 | 45096 | 45110 | 45187 | 45258 | MKB Builders and Supply | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Eastern Samar | 501925 | San Roque Integrated School | JIPAPAD | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM, PERIMTER FENCE, REPAIR OF TWO (2) UNITS, TWO (2) CLASSROOMS | 16608334.2025 | 12209995.28 | Completed | 1 | 2024-01-19 | 2024-03-15 | 44986 | No. 03-2023 | 45028 | 45044 | 45057 | 45083 | 45093 | Early Riser Construction | Aprroved time Extension due to Bad weather condition , savings in procurement has request for approval for the repair of 5-Classroom LMS School in the municipality of Buenavista | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region VIII | Eastern Samar | 122471 | Tugas Elementary School | MASLOG | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15036383.787 | 12144077.99 | Completed | 1 | 2024-03-30 | 00:00:00 | BEFF2023-RVI-022-LMS-L1 | BEFF2023-RVI-022-LMS-L1 | 45033 | 45040 | 45054 | 45106 | 45141 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region VIII | Eastern Samar | 122729 | Putong Elementary School | SAN JULIAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13104079.1681 | 15174823.71 | COMPLETED | 1 | 2024-03-30 | 00:00:00 | BEFF2023-RVI-022-LMS-L2 | BEFF2023-RVI-022-LMS-L2 | 45033 | 45040 | 45054 | 45106 | 45141 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Eastern Samar | 122745 | Tanauan Elementary School | SAN POLICARPO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15933377.715 | 10644375.55 | Completed | 1 | 00:00:00 | FOR FINAL INSP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Leyte | 121878 | San Miguelay Elementary School | SANTA FE | 1 | 1 | 2 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 13098706.6964 | 13379302.42 | Completed | 1 | 2023-05-04 | 2023-05-01 | 2022 - LMS (RVIII) - LEYTE - Lot 3 | 2022 - LMS (RVIII) - LEYTE - Lot 3 | 44839 | 44848 | 44867 | 44888 | 44893 | RD COBACHA CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Leyte | 121948 | Cantariwis Elementary School | TOLOSA | 1 | 1 | 2 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13353072.2906 | 6133609.44 | Completed | 1 | 2023-05-04 | 2023-04-28 | 2022 - LMS (RVIII) - LEYTE - Lot 4 | 2022 - LMS (RVIII) - LEYTE - Lot 4 | 44839 | 44848 | 44867 | 44888 | 44893 | VHITS D.G. BUILDERS AND ENTERPRISES | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Leyte | 121521 | Caridad Primary School | JULITA | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18012019.0609 | 13314317.27 | Completed | 1 | 2023-06-30 | 2023-07-08 | 2022 - LMS (RVIII) - LEYTE - Lot 1 | 2022 - LMS (RVIII) - LEYTE - Lot 1 | 44839 | 44848 | 44867 | 44887 | 44890 | ROVINVAL ENGINEERING & CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region VIII | Leyte | 121734 | San Jose Elementary School | MERIDA | 4 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE, SOLAR PV ENERGY SYSTEM | 18232629.248 | 12604337.28 | Completed | 1 | 2023-06-30 | 2024-02-02 | 2022 - LMS (RVIII) - LEYTE - Lot 2 | 2022 - LMS (RVIII) - LEYTE - Lot 2 | 44839 | 44848 | 44867 | 44887 | 44890 | ROVINVAL ENGINEERING & CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Leyte | 121407 | Himokilan Elementary School | HINDANG | 5 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16283462.6909 | 16112917.3 | Completed | 1 | 2023-04-28 | 2023-04-28 | 2022 - LMS (RVIII) - LEYTE - Lot 1 | 2022 - LMS (RVIII) - LEYTE - Lot 1 | 44676 | 44693 | 44708 | 44827 | 44827 | V.JYN ENTERPRISES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Northern Samar | 122790 | Bagong Silang ES | BIRI | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18778633.5953 | 16732343.93 | Completed | 1 | 2024-02-10 | 2024-10-31 | CY 2022 LMS2022-RVIII-NS-Batch-2-L1 | CY 2022 LMS2022-RVIII-NS-Batch-2-L1 | 45056 | 45066 | 45076 | 45131 | 45142 | OPEN BUILDERS INC | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | Region VIII | Northern Samar | 122823 | Diraya ES | CAPUL | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND CONSTRUCTION OF FLOOD MARKER | 17825575.2844 | 19434689.34 | Completed | 1 | 2023-06-18 | 2023-06-18 | CY 2022 LMS2022-RVIII-NS-Batch-2-L2 | CY 2022 LMS2022-RVIII-NS-Batch-2-L2 | 44888 | 44896 | 44908 | 44928 | 44942 | ADB DYNAMIC BUILDER/JD PARTUZA CONSTRUCTION JV | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region VIII | Northern Samar | 193004 | R.F. Tobes Mem. School | ROSARIO | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND CONSTRUCTION OF FLOOD MARKER | 17471692.6459 |  | Completed | 1 | [10 empty] | Cancelled | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | Region VIII | Northern Samar | 123271 | Buenasuerte ES | VICTORIA | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15631093.1081 | 15310510.46 | Completed | 1 | 2023-06-07 | 2023-06-07 | CY 2022 LMS2022-RVIII-NS-B1 | CY 2022 LMS2022-RVIII-NS-B1 | 44888 | 44896 | 44908 | 44928 | 44942 | SAL CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Samar (Western Samar) | 123549 | Matuguinao CES | MATUGUINAO | 1 | 1 | 10 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, FLOOD MARKER AND REPAIR OF 6 CLASSROOMS | 22455102.9318 | 22842142.86 | Completed | 1 | 2023-05-03 | 2023-05-03 | CY2022LMSPB2L2 | 2022-00044 | 44841 | 44848 | 44860 | 44876 | 44887 | VHITS DG BUILDERS | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 | [6 empty] | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Samar (Western Samar) | 123583 | Bugho ES | JIABONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19752204.4305 | 19455461.72 | Completed | 1 | 2022-12-03 | 2022-12-12 | CY2022LMSPLOT1 | 2022-00018 | 44705 | 44714 | 44726 | 44764 | 44776 | SAMARINAN CONSTRUCTION INC | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2022 | Region VIII | Samar (Western Samar) | 501931 | Camayse Integrated School | ZUMARRAGA | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 20597729.1827 | 23519497.04 | Completed | 1 | 2023-07-16 | 2023-08-25 | CY2022LMSPB2L1 | 2022-00043 | 44841 | 44848 | 44860 | 44876 | 44887 | GPUY CONSTRUCTION AND SUPPLIES | WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Southern Leyte | 122062 | Amaga Elementary School | HINUNDAYAN | 0 | 1 | 4 | CONSTRUCTION OF TWO (2) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM AND REPAIR OF EXISTING CLASSROOM | 20946372.1533 | 20663270.39 | Completed | 1 | 2023-01-30 | 2023-03-24 | CY2022-LMS-L1 | CY2022-LMS-L1 | 44677 | 44685 | 44698 | 44739 | 44774 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Southern Leyte | 192031 | Cat-iwing MG Elem School | HINUNDAYAN | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4-SEATER), WATER SYSTEM, SOLAR POWER ENERGY SYSTEM, FLOOD MARKER AND REPAIR OF EXISTING CLASSROOMS | 13697447.694 | 13750750.19 | Completed | 1 | 2023-02-06 | 2023-01-26 | CY2022-LMS-B2-L1 | CY2022-LMS-B2-L1 | 44844 | 44851 | 44865 | 44916 | 44937 | BENCH CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Southern Leyte | 122233 | Bulawan Primary School | PINTUYAN | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER SYSTEM, SOLAR POWER ENERGY SYSTEM, FLOOD MARKER AND REPAIR OF EXISTING CLASSROOMS | 14948077.4973 | 13082478.98 | Completed | 1 | 2023-02-06 | 2023-11-30 | CY2022-LMS-B2-L2 | CY2022-LMS-B2-L2 | 44844 | 44851 | 44865 | 44916 | 44937 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region VIII | Southern Leyte | 122313 | Carnaga Elementary School | TOMAS OPPUS | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM AND REPAIR OF EXISTING CLASSROOM | 14814618.2991 | 14592604.89 | Completed | 1 | 2022-12-21 | 2023-03-09 | CY2022-LMS-L2 | CY2022-LMS-L2 | 44677 | 44685 | 44698 | 44739 | 44774 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 1
LMS 2022 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16459251.5365 | 11765349.85 | Completed | 1 | 2024-01-17 | 2023-08-18 | 2022-10-0228 | 2022-12-0327 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-07-11 | 2023-07-14 | ROVINVAL ENGINEERING AND CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16469856.5365 | 12076295.82 | Completed | 1 | 2023-12-31 | 2023-09-06 | 2022-04-0065 | 2022-09-0205 | 2023-04-25 | 2023-05-03 | 2023-05-15 | 2023-07-07 | 2023-07-27 | LJPM BUILDERS AND CONSTRUCTION SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region X | Lanao del Norte | 127171 | Sigayan Adil PS | PANTAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND REPAIR & REHABILITATION OF CLASSROOMS. | 17137950.7406 | 12954954.09 | Completed | 1 | 2023-06-09 | 2023-06-10 | 2023-02(Infra) | 44958 | 2022-11-23 | 2022-12-01 | 2022-12-19 | 2023-01-09 | 2023-02-09 | S& J BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0
LMS 2022 | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND REPAIR & REHABILITATION OF CLASSROOMS. | 15730677.8052 | 0 | COMPLETED | 1 | 2023-06-09 | 2023-05-05 | 2023-01(Infra) | 44927 | 2022-11-23 | 2022-12-01 | 2022-12-19 | 2023-01-09 | 2023-02-09 | AHM BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 0 | 1 |  |  |  | CY 2023 |  |  | 0
LMS 2022 | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 19938695.3452 | 0 | COMPLETED | 1 | 2023-01-05 | 2023-11-30 | 2022-05(infra) | 44682 | 2022-04-20 | 2022-04-29 | 2022-05-17 | 2022-08-25 | 2022-09-07 | N-ASIACOM | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1
LMS 2022 | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 1 | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND REPAIR AND REHABILITATION OF ONE STOREY THREE (3) - CLASSROOM SCHOOL BUILDING (BLSB - TYPE 1) - (6.40m x 8.00m) | 16494219.42 | 16279166.49 | Completed | 1 | 2023-08-09 | 2024-11-22 |  | 002-2023 | 2022-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-14 | 2023-01-30 | RRJ Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | [6 empty] | 1
LMS 2022 | Region X | Misamis Occidental | 127371 | Soso-on Elementary School | CONCEPCION | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17603739.1268 | 17030172.22 | Completed | 1 | 2023-03-06 | 2024-07-04 | LMS 2022-RX-Misamis Occidental-001 | 013-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-29 | RRJ Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 |  | 1 | [7 empty] | 1
LMS 2022 | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 16435255.6737 | 15385260.39 | Completed | 1 | 2023-07-08 | 2023-09-15 | LMS 2022-RX-Misamis Occidental-002 | 001-2023 | 2022-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-13 | 2023-01-27 | 3R's Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 |  | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2022 | Region X | Misamis Oriental | 201509 | Dahilig ES | BALINGOAN | 1 | 1 | 4 | CONSTRUCTION OF 2UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 14773677.2926 | 13824219.59 | Completed | 1 | 2023-04-12 | 2023-07-11 | PB-Infra 2022-001 |  | 2022-08-10 | 2022-08-10 | 2022-08-30 | 2022-09-22 | 2022-11-27 | Meterking Inc. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 |  |  | 1
LMS 2023 | CAR | Abra | 135187 | Lawigan PS | BOLINEY | 0 | 1 | 2 | CONSTRUCTION OF 1 STOREY 2 CLASSROOMS WITH COMMON TOILET, SCHOOL FURNITURES, WATER SYSTEM, RAINWATER COLLECTOR | 11110000 | 14152726.43 | Completed | 1 | 2024-06-04 | 2024-06-19 | SDO-ABRA-2023-06-043 | 2023-07-007 | June 28, 2023 | July 4, 2023 | July 17, 2023 | July 26, 2023 | August 9, 2023 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | CAR | Abra | 135047 | Bacag ES | LACUB | 0 | 1 | 2 | CONSTRUCTION OF 1 STOREY 2 CLASSROOMS WITH COMMON TOILET, SCHOOL FURNITURES, WATER SYSTEM, RAINWATER COLLECTOR | 12120000 | 17116471.79 | Completed | 1 | 2025-02-22 | 2024-04-06 | SDO-ABRA-2023-06-043 | 2023-07-007 | June 28, 2023 | July 4, 2023 | July 17, 2023 | July 26, 2023 | August 9, 2023 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | CAR | Abra | 135092 | Barit ES | LUBA | 0 | 1 | 2 | CONSTRUCTION OF 1 STOREY 2 CLASSROOMS WITH COMMON TOILET, SCHOOL FURNITURES, WATER SYSTEM, RAINWATER COLLECTOR | 10100000 | 17392036.74 | Completed | 1 | 2024-04-20 | 2023-12-30 | SDO-ABRA-2023-06-043 | 2023-07-007 | June 28, 2023 | July 4, 2023 | July 17, 2023 | July 26, 2023 | August 9, 2023 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | CAR | Abra | 135168 | Abas ES | SALLAPADAN | 0 | 1 | 2 | CONSTRUCTION OF 1 STOREY 2 CLASSROOMS WITH COMMON TOILET, SCHOOL FURNITURES, WATER SYSTEM, RAINWATER COLLECTOR | 9090000 | 16780281.43 | Completed | 1 | 2024-05-06 | 2023-12-17 | SDO-ABRA-2023-06-043 | 2023-07-007 | June 28, 2023 | July 4, 2023 | July 17, 2023 | July 26, 2023 | August 9, 2023 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 | - | 1 |  |  |  |  | CY 2023 | 1 |  | 0
LMS 2023 | CAR | Abra | 135184 | Gangal Elementary School | SALLAPADAN | 0 | 1 | 2 | CONSTRUCTION OF 1 STOREY 2 CLASSROOMS WITH COMMON TOILET, SCHOOL FURNITURES, WATER SYSTEM, RAINWATER COLLECTOR | 9090000 | 17364431.28 | Completed | 1 | 2024-01-14 | 2023-12-17 | SDO-ABRA-2023-06-043 | PB - Construction-2023-002 | June 28, 2023 | June 3,2023 | June 13,2023 | June 27,2023 | August 9, 2023 | SEMBRI CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 | - | 1 |  |  |  |  | CY 2023 | 1 |  | 0
LMS 2023 | CAR | Benguet | 135720 | Baayan ES | TUBLAY | 0 | 1 | 4 | CONSTRUCTION OF TWO(2) UNITS- ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND SLOPE PROTECTION | 23421679.46 | 22992313.95 | Completed | 1 | JULY 14, 2024 | JULY 4, 2024 | LMS-2023-01 | LMS-2023-01 | May 5, 2023 | May 12, 2023 | May 25, 2023 | 2023-09-08 | 2023-08-30 | MHIGS CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | CAR | Benguet | 502340 | Miguel Palispis Integrated School | TUBA | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM, SLOPE PROTECTION, REPAIR AND REHABILITATION OF CLASSROOMS | 27377352.57 | 27107027.98 | Completed | 1 | FEBRUARY 5, 2025 | MAY 29, 2025 | LMS-2023-306 | LMS-2023-306 | December 01, 2023 | December 11, 2023 | December 27, 2023 | 2024-02-12 | 2024-03-12 | HAIGHTS CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | CAR | Ifugao | 135786 | Ammoweg Elementary School | ASIPULO | 0 | 1 | 6 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) & TWO(2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM AND PERIMETER FENCE (ONE BAY, 3.0M) | 26101571.53 | 12980986.68 | Completed | 1 | 2024-06-09 | 2024-07-23 |  | 0 | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | CAR | Kalinga | 136022 | Colayo Elementary School | PASIL | 0 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM. | 24632636.5 | 12370674.27 | Completed | 1 | 2024-06-09 | 2024-07-23 | LMS 2023-CAR-Kalinga-001 | LMS 2023-CAR-Kalinga-001 | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CAR | Mt. Province | 136233 | Ambagiw Elementary School | BESAO | 0 | 1 | 4 | CONSTRUCTION OF ELEVATED TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, PERIMETER FENCE | 37084540.17 | 12174043.03 | Completed | 1 | 2024-06-09 | 2024-07-23 | INF-2023 LMS-001 | INF-2023 LMS-001 | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CAR | Tabuk City | 220523 | Cataw Primary School | CITY OF TABUK (Capital) | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, FLAG POLE, PERIMETER FENCE, GATE AND WATER SYSTEM | 23450515.55 | 23213776.25 | Completed | 1 | September 15, 2024 | May 17, 2024 | 1-2023-3 | 1-2023-3 | October 19- November 10, 2023 | October 27, 2023 @ 1:31pm | November 10, 2023 @ 1:31pm | November 30, 2023 | December 20, 2023 | Bangyan 3D Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | CARAGA | Agusan del Norte | 131531 | Humilog ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM COLLECTOR, | 17170000.1 | 14766095.03 | Ongoing | 0.99 | 00:00:00 | 00:00:00 | LMS 2023 - CARAGA - AGUSAN DEL NORTE - 001 | LMS 2023 - CARAGA - AGUSAN DEL NORTE - 001 | 00:00:00 | 00:00:00 | 00:00:00 | 2023-07-26 | 2023-08-07 | Jodels Construction Supplies & Merchandise | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.75 | 0.24 | 6.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET), with Provision of WATER SYSTEM-Deep Well Design with electric-powered Submersible water pump, School Furniture, Perimeter Solar Lighting System | 17166772.68 | 13427411.97 | Completed | 1 | 2024-02-15 | 2024-03-25 | INFRA2023-002 | INFRA2023-004 | 2023-05-02 | 2023-05-16 | 2023-05-25 | 2023-06-02 | 2023-07-20 | DANREV | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17169796.75 | 16945355.98 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-018 | BEFF-INFRA2023-018 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17169796.75 | 16943551 | Completed | 1 | 2024-04-08 | 2024-07-10 | BEFF-INFRA2023-019 | BEFF-INFRA2023-019 | 2024-01-26 | 2024-02-07 | 2024-02-20 | 2024-03-05 | 2024-03-08 | RBEP Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Surigao del Norte | 132543 | Laurel ES | TAGANA-AN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17165004.86 | 12091132.49 | Completed | 1 | 2023-11-22 | 2023-11-22 | 2023-001-LMS-CARAGA | 006-2023 | 2023-04-20 | 2023-04-27 | 2023-05-09 | 2023-05-24 | 2023-05-26 | AMALGO CONSTRUCTION | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | CARAGA | Surigao del Sur | 305747 | Gacub Atad S. Iligan Tribal National High School | CARMEN | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHTING SYSTEM, AND WATER SYSTEM | 14359089.13 | 11736814.2 | Completed | 1 | 2024-05-25 | 2024-06-22 | LMS-001 | 2023 - 002 | 2023-10-02 | 2023-10-16 | 2023-10-25 | 2023-11-02 | 2023-12-20 | RELY CONSTRUCTION AND SUPPLY | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | CARAGA | Tandag City | 136972 | Pag-asa Tribal Community Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22972431.7 | 22744896.06 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | CYL Construction and Supply | With Time Extension due to Extra Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5013 | 0.4987 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region I | Ilocos Norte | 100001 | Apaleng-Libtong ES | BACARRA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 16983806.6 | Completed | 1 | 2024-06-16 | 2024-10-15 | PB-05-2023 | PB-05-2023 | 2023-07-03 | 2023-07-10 | 2023-07-24 | 2023-08-14 | 2023-08-25 | ELOCIN CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.99 | 0.01 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region I | Ilocos Sur | 100477 | Lamagan PS | CERVANTES | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 13462349.99 | Completed | 1 | 2024-01-31 | 2024-04-24 | 2023-07-007-PB-Works |  | 2023-07-25 | 2023-08-01 | 2023-08-14 | 2023-08-23 | 2023-09-04 | WWW.Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region I | La Union | 151005 | Lacong ES-Annex | SAN GABRIEL | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 16946057.06 | Completed | 1 | 2024-01-06 | 2024-01-08 | 2023LMSRO1-01 | SDOLU-LMS 2023-1 | 2023-05-27 | 2023-06-05 | 2023-06-19 | 2023-07-10 | 2023-07-08 | HG LOPEZ CONSTRUCTION | DIVISION IMPLEMENTED COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region I | La Union | 101119 | Daeng ES | TUBAO | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17158043.98 | 16937084.62 | COMPLETED | 1 | 2024-11-28 | 2024-11-28 | 2023LMSRO1-02 | SDOLU-LMS 2023-2 | 2023-11-20 | 2023-11-29 | 2023-12-13 | 2023-12-26 | 2024-01-05 | LAV CONSTRUCTION AND SUPPLY | Completed DIVISION IMPLEMENTED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.86 | 0.14 | 5.25 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | Region II | Cagayan | 102834 | Dungan Elementary School | RIZAL | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15246726.74 | 10698569.48 | COMPLETED | 1 | December 26, 2023 | April 29, 2024 | LMS 2022-RII-CAGAYAN-001 | INFRA2023 045 | MAY 8, 2023 | MAY 16, 2023 | MAY 29, 2023 | JUNE 19, 2023 | JUNE 22, 2023 | GANIE CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region II | Cagayan | 102917 | Capacuan ES | SANTA PRAXEDES | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15246726.74 | 15072295.7 | COMPLETED | 1 | November 7, 2023 | February 13m 2024 | LMS 2022-RII-CAGAYAN-002 | INFRA2023 045 | MAY 8, 2023 | MAY 16, 2023 | MAY 29, 2023 | JUNE 19, 2023 | JUNE 22, 2023 | YZK CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region II | Nueva Vizcaya | 103988 | Daclig ES | AMBAGUIO | 0 | 1 | 2 | CONSTRUCTION OF 1STY2CL SCHOOL BUILDING WITH PROVISION OF SOLAR-POWERED ENERGY SYSTEM, SCHOOL FURNITURE, WATER SYSTEM AND EMBANKMENT | 17170000 | 13321708.11 | Ongoing | 0.882 | 2024-08-06 | - | PB10-002-SDONV-LMS2023 | PB10-002-SDONV-LMS2023 | 2023-07-10 | 10/13/2023 | 10/25/2023 | 2023-12-12 | 12/18/2023 | Zymx Construction & Pecdasen Builders (JVA) | with time extension due to road closure, bad weather condition and extra works | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.848 | 0.034 |  | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region II | Quirino | 156513 | DIODOL ES Annex | AGLIPAY | 0 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM (Option 2 - Water Source at a Higher Elevation) WITH SLOPE PROTECTION | 18077047.82 | 17818880.19 | COMPLETED | 1 | May 15, 2024 | August 01, 2024 | CY2023 LMS | CY2023 LMS | 2023-06-26 | 2023-07-03 | 2023-07-17 | 2023-08-15 | 2023-09-13 | Mak-Jay Construction | with Time Extensions due to unworkable days due to bad weather condition and delays in the delivery of materials due to unpassable road | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region III | Nueva Ecija | 105195 | Ariendo ES | BONGABON | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), PERIMETER FENCEA, SOLAR PV ENERGY SYSTEM AND SCHOOL FURNITURE | 17165672.76 | 16935358.6 | completed | 1 | 2023-12-06 | 2024-03-07 | DEPED-NE-INFRA-PB-01-2023 | INFRA-NE-01-2022 | 2023-06-19 | 2023-06-26 | 2023-07-10 | 2023-07-14 | 2023-08-08 | REBCOR CONST. AND TRADING CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region III | Tarlac | 106511 | Gayong-Gayong ES | MAYANTOC | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 11801006.92 |  | Completed | 1 |  | 2023-10-20 |  |  | 2023-05-03 | 2023-05-11 | 2023-05-24 | 2023-06-29 | 2023-07-05 | CAIXIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2023 | Region IV-A | Batangas | 107816 | San Pedro Elementary School | TINGLOY | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17638031.48 | 17402609.51 | Completed | 1 | 2024-04-23 | 2024-08-30 | LMS 2022 - IVA - BATANGAS - 001 | LMS 2023 - IVA - BATANGAS - 001 | 2023-10-20 | 2023-10-26 | 2023-11-06 | 2023-12-20 | 2023-12-29 | Marakesh Enterprise | Certificate of Time Extension was granted to the contractor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region IV-A | Batangas | 107663 | Hipit Elementary School | SAN NICOLAS | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16047281.48 | 15802341.11 | Completed | 1 | 2024-04-23 | 2024-08-30 | LMS 2023 - IVA - BATANGAS - 002 | LMS 2023 - IVA - BATANGAS - 002 | 2023-10-20 | 2023-10-26 | 2023-11-06 | 2023-12-20 | 2023-12-29 | Marakesh Enterprise | Certificate of Time Extension was granted to the contractor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25802288.87 | 25530000 | Completed | 1 | 2024-02-04 | 2024-05-04 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | C.G. Cabana Construction and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | - | 1 | [5 empty] | 1 |  | 1
LMS 2023 | Region IV-A | Quezon | 109052 | Del Pilar Elementary School | QUEZON | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16555387.23 | 16375912.86 | Completed | 1 | 2024-02-04 | 2024-02-28 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | Quezon Achievers | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4 | 1 | 2 | CONSTRUCTION OF ONE (1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL | 18146137.23 | 17930000 | Completed | 1 | 2024-02-04 | 2023-11-13 | 2023-048-INFRA | 2023-048-INFRA | 2023-07-19 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-12 | Botey Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 | - | 1 |  |  |  |  | CY 2023 | 1 |  | 0
LMS 2023 | Region IV-A | Tanauan City | 107764 | Mahabang Buhangin ES | CITY OF TANAUAN | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF, SCHOOL FURNITURE, PERIMETER FENCE 150.0m FRONTAGE (1 BAY = 3.0m), RAIN WATER COLLECTOR TWO (1) SETS AND PROVISION OF SOLAR PANEL | 17360252.16 | 17138185.47 | Ongoing | 0.65 | 2025-06-17 |  | LMS 2024 TANAUAN-001 | LMS 2024 TANAUAN-001 | 2024-08-30 | 2024-09-09 | 2024-09-23 | 2024-10-08 | 2024-10-21 | MARAKESH ENTERPRISES | delayed due to request for modification | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0.45 |  | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region IV-B | Oriental Mindoro | 130206 | Mungos Mangyan Elementary School | BONGABONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20880049.26 | 20622113.46 | Completed | 1 | 2023-12-26 | 2023-12-20 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 05-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-19 | 2023-05-26 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IV-B | Oriental Mindoro | 136953 | Naswak Hatubuan Bangon Elementary School | BONGABONG | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21303170.78 | 21050000 | Completed | 1 | 2024-01-25 | 2024-01-19 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 04-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-18 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IV-B | Oriental Mindoro | 137123 | Cambayang Elementary School | BULALACAO (SAN PEDRO) | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 14291013.26 | 14120000 | Completed | 1 | 2023-12-26 | 2024-12-02 | LMS 2023 - MIMAROPA - ORIENTAL MINDORO - 003 | LMS 06-2023 | 2023-04-19 | 2023-04-27 | 2023-05-10 | 2023-05-20 | 2023-05-26 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region IV-B | Puerto Princesa City | 171501 | Manggapin Elementary School | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM AT MANGGAPIN ELEMENTARY SCHOOL | 22354334.98 | 22131576 | Completed | 1 | July 25, 2024 Revised: August 23, 2024 | Aug. 26, 2024 | INFRA 2023-10-03 | INFRA 2023-10-03 | Oct. 25, 2023 | Oct. 31, 2023 | Nov. 13, 2023 | Nov. 16, 2023 | Nov. 21, 2023 | Maryknoll Builders and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.1 | 5.25 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | Region IX | Zamboanga del Norte | 303714 | Mutia NHS Annex - Tubak | MUTIA | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT AND SOLAR PV ENERGY SYSTEM | 17166895.91 | 16993668.9 | COMPLETED | 1 | 2023-11-15 | 2023-12-30 | 2023-8-CBZN | CB-2023-008 | 2023-04-05 | 2023-04-14 | 2023-04-27 | 2023-05-30 | 2023-06-07 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IX | Zamboanga del Norte | 124547 | Adante ES | PIÑAN (NEW PIÑAN) | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 25577846.13 | 25295175.54 | COMPLETED | 1 | 2024-06-30 | 2024-11-25 | 2023-024-CBZN | CB2023-023 | Nov. 14, 2023 | Nov. 24, 2023 | Dec. 07, 2023 | Dec. 18, 2023 | Dec. 28, 2023 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | Region IX | Zamboanga del Sur | 125307 | Bag-ong Opon Elementary School | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19077138.92 | 18787999.57 | COMPLETED | 1 | 2023-11-04 | 2023-12-14 | ZDS-23-LMS-01 | ZDS-23-LMS-01 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | GENETIAN BUILDERS AND ENTERPRISES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IX | Zamboanga del Sur | 124940 | Buburay ES | DIMATALING | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18381376.01 | 18086919.56 | COMPLETED | 1 | 2023-11-04 | 2023-11-30 | ZDS-23-LMS-02 | ZDS-23-LMS-02 | 2023-04-13 | 2023-04-26 | 2023-05-08 | 2023-05-22 | 2023-05-31 | GENETIAN BUILDERS AND ENTERPRISES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 13320323.48 | 11154681.24 | COMPLETED | 1 | 2023-11-04 | - | ZS-2023-LMS-01 | ZS-2023-LMS-01 | 2023-04-04 | 2023-04-17 | 2023-04-28 | 2023-06-23 | 2023-07-07 | Shameem Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Camarines Norte | 112269 | Resettlement ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF, SCHOOL FURNITURE, CONCRETE PATHWAY (WIDTH = 4.0m), PERIMETER FENCE 150.0m FRONTAGE (1 BAY = 3.0m) AND REPAIR OF 2CL BLSB TYPE 1 | 17976228.27 | 17729608.63 | COMPLETED | 1 | 2023-11-11 | 2024-02-26 | INFRA02-05 2023CN | INFRA02-05 2023CN | 2023-05-08 | 2023-05-15 | 2023-06-05 | 2023-06-16 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | CARAMORAN | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE WITH HAULING COST | 7587681.68 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 136922 | Arriesgado Elementary School | CLAVERIA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12631866.08 | Completed | 1 | 2023-12-07 | 2024-01-10 | INFRA 2023-05-002 | 2023-07-001 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-10 | NJNY Const. & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 113662 | Tabuk Elementary School | MANDAON | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12631638.76 | Completed | 1 | 2023-12-03 | 2024-01-16 | INFRA 2023-05-002 | 2023-07-002 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-06 | EJ Cantoria Const. & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 501528 | Tugbo Integrated School | MOBO | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 12784616.01 | 12632137.16 | Completed | 1 | 2023-12-10 | 2024-04-01 | INFRA 2023-05-002 | 2023-07-038 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 501545 | Madamba Integrated School | CATAINGAN | 3 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 14029531.76 | 13867265.99 | Completed | 1 | 2023-12-02 | 2024-01-15 | INFRA 2023-05-002 | 2023-07-039 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-05 | 3R3M Const & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 113531 | Calapayan Elementary School | CAWAYAN | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE WITH HAULING COST | 8597681.69 | 8496949.85 | Completed | 1 | 2023-12-10 | 2023-12-12 | INFRA 2023-05-002 | 2023-07-040 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region V | Masbate | 302123 | Buracan National High School | DIMASALANG | 3 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SANITATION AND WATER SYSTEM WITH HAULING COST | 13996557.55 | 13831624.51 | Completed | 1 | 2024-12-10 | 2024-01-15 | INFRA 2023-05-002 | 2023-07-041 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-13 | Square N Const & Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VI | Aklan | 114931 | Lanipga Napatag Primary School | TANGALAN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19969508.48 | 16152092.89 | Completed | 1 | 2023-12-31 | 2024-07-03 | DepED-RO6-D1-LMS2023-019-2023 | DepED-RO6-D1-LMS2023-019-2023 | 2023-04-26 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-27 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VI | Antique | 115139 | Tinindugan Primary School | LIBERTAD | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 12901507.38 | Completed | 1 | 2024-05-01 | 2024-06-25 | R6-D2-BEFF2023-11-NC | R6-D2-BEFF2023-11-NC | 2023-06-12 | 2023-06-19 | 2023-07-03 | 2023-09-18 | 2023-11-28 | MJSb Builders and Supply | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VI | Guimaras | 115859 | Tangaw Primary School | SAN LORENZO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) ROOFING, STEEL TRUSSES CONCRETE WORKS, MASONRY WORKS, ELECTRICAL WORKS, AND PLUMBINGWITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 17170000 | 12209995.28 | Completed | 1 | 2024-01-19 | 2024-03-15 | No. 03-2023 | No. 03-2023 | 2023-04-12 | 2023-04-28 | 2023-05-11 | 2023-06-06 | 2023-06-16 | Early Riser Construction | Completed with approved VO in the amount of 956,217.09 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VI | Iloilo | 116107 | Cairohan PS | BINGAWAN | 3 | 1 | 2 | ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY AND WATER SYSTEM | 18854193.63 | 12144077.99 | Completed | 1 | 2024-03-30 | 2024-08-07 | BEFF2023-RVI-022-LMS-L1 | BEFF2023-RVI-022-LMS-L1 | 2023-04-17 | 2023-04-24 | 2023-05-08 | 2023-06-29 | 2023-08-03 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region VI | Iloilo | 116099 | Malico PS | BATAD | 5 | 1 | 4 | ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY AND WATER SYSTEM | 23471443.86 | 15174823.71 | Completed | 1 | 2024-03-30 | 2024-08-08 | BEFF2023-RVI-022-LMS-L2 | BEFF2023-RVI-022-LMS-L2 | 2023-04-17 | 2023-04-24 | 2023-05-08 | 2023-06-29 | 2023-08-03 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region VII | Bohol | 117998 | Boyog ES | BALILIHAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 10766058.66 | 10644375.55 | Completed | 1 | 05/15/2024 | 2024-06-11 | PBI 2023-27 | PBI 2023-27 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-16 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VII | Bohol | 103611 | Cantumogcad ES | BUENAVISTA | 2 | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 12125725.66 | 11981920.24 | Completed | 1 | 05/15/2024 | 2024-05-13 | PBI 2023-28 | PBI 2023-28 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-16 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VII | Bohol | 117965 | Tanod ES | ANDA | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR AND SCHOOL FURNITURE | 6161022.46 | 6032357.5 | Completed | 1 | 4/16/2024 | 2024-06-25 | PBI 2023-29 | PBI 2023-29 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-17 | DMAM CONSTRUCTION SERVICES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2023 | Region VII | Bohol | 118859 | Pangian ES | VALENCIA | 3 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET)WITH PROVISION OF SCHOOL FURNITURE | 6014632.02 | 4452592.82 | Completed | 1 | 4/26/2024 | 2024-06-28 | PBI 2023-30 | PBI 2023-30 | 2023-07-10 | 2023-07-18 | 2023-08-03 | 2023-10-09 | 2023-11-28 | LTS BUILDERS AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2023 | Region VII | Cebu | 119061 | Balintawak ES | BANTAYAN | 4 | 1 | 4 | CONSTRUCTION OF 1STY-4CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11727969.19 | 11561367.39 | Completed | 1 | 2024-09-01 | 2024-09-01 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-03 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | Region VII | Cebu | 119063 | Guiwanon Elementary School | BANTAYAN | 4 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9943843.08 | 9794772.39 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-01 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2023 | Region VII | Cebu | 119071 | Vito ES | BANTAYAN | 4 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9896120.58 | 9745999.34 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-02 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ROVILLA CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 1 | [5 empty] | 1 |  | 0
LMS 2023 | Region VII | Cebu | 119192 | Francisco S. Villamor Sr.Elementary School | CARMEN | 5 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9745045.06 | 9618165.28 | Completed | 1 | 2024-03-01 | 2024-01-03 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-04 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 2023-12-09 | TRI-BAIRN CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VII | Cebu | 119230 | Magay ES | COMPOSTELA | 5 | 1 | 4 | PROPOSED CONSTRUCTION OF 1STY-4CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 11139089.16 | 10978920.9 | Completed | 1 | 2024-09-01 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-06 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | BARR STEEL CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VII | Cebu | 501350 | Tag-ubi Integrated School | COMPOSTELA | 5 | 1 | 3 | CONSTRUCTION OF 1STY-3CL SCHOOL BUILDING WITH COMMON TOILET WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9399879.76 | 7288932.45 | Completed | 1 | 25/12/2023 | 25/12/2023 | CY 2023 LMS-R7-CEBU | CY 2023 LMS-R7-CEBU-05 | 2023-07-19 | 2023-07-26 | 2023-08-07 | 2023-08-17 | 31/08/2023 | ANIELTHON CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 | - | 1 |  |  |  |  | CY 2024 | 1 |  | 0
LMS 2023 | Region VIII | Biliran | 120816 | Bacolod Elementary School | CULABA | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 14376421.62 | 14224004.88 | Completed | 1 | 2024-01-12 | 2024-03-22 | 2023INFRA-LMS-05 | LMS 2023CONSTRUCTION-05 | 45079 | 45078 | 45103 | 45127 | 45147 | MB ANG CONSTRUCTION & SUPPLY | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15484974.48 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Eastern Samar | 122696 | Lusod Elementary School | SALCEDO | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15745303.5 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 121561 | Caabangan Elementary School | LA PAZ | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 12995983.5 | 11450720.53 | Completed | 1 | 2023-12-14 | 2023-12-08 | 2023-(RVIII)-LEYTE-LOT-1 | 2023-(RVIII)-LEYTE-LOT-1 | 45041 | 45049 | 45061 | 45104 | 45117 | VHITS D.G. BUILDERS AND ENTERPRISES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 191564 | Kiling Elementary School | MACARTHUR | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12826208.38 | 9183502.01 | Completed | 1 | 2023-12-18 | 2024-02-27 | 2023-(RVIII)-LEYTE-LOT-2 | 2023-(RVIII)-LEYTE-LOT-2 | 45041 | 45049 | 45061 | 45118 | 45121 | ROVINVAL ENGINEERING AND CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 191565 | San Pedro Elementary School | MACARTHUR | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12844022.18 | 9192622.73 | Completed | 1 | 2023-12-18 | 2024-02-27 | 2023-(RVIII)-LEYTE-LOT-3 | 2023-(RVIII)-LEYTE-LOT-3 | 45041 | 45049 | 45061 | 45118 | 45121 | ROVINVAL ENGINEERING AND CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 121703 | Camansi Primary School | MAYORGA | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12803795.93 | 9403914.76 | Completed | 1 | 2023-12-18 | 2024-02-27 | 2023-(RVIII)-LEYTE-LOT-4 | 2023-(RVIII)-LEYTE-LOT-4 | 45041 | 45049 | 45061 | 45118 | 45121 | ROVINVAL ENGINEERING AND CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 121915 | Mohon Primary School | TABONTABON | 2 | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM, AND REPAIR AND REHABILITATION OF BUILDING NO. 1 - TWO (2) - CLASSROOM SCHOOL BUILDING (DPWH-BOD) - (7.00m x 8.00m) | 16014286.06 | 11765349.85 | Completed | 1 | 2024-01-17 | 2024-04-01 | 2023-(RVIII)-LEYTE-LOT-5 | 2023-(RVIII)-LEYTE-LOT-5 | 45041 | 45049 | 45061 | 45118 | 45121 | ROVINVAL ENGINEERING AND CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Leyte | 121399 | Baldoza Elementary School | HINDANG | 5 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 14893613.63 | 12076295.82 | Completed | 1 | 2023-12-31 | 2024-04-08 | 2023-(RVIII)-LEYTE-LOT-6 | 2023-(RVIII)-LEYTE-LOT-6 | 45041 | 45049 | 45061 | 45114 | 45134 | LJPM BUILDERS AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Northern Samar | 122800 | Tampipi Elementary School | BIRI | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16742342.16 | 13536456.34 | Completed | 1 | 2024-03-07 | 2024-10-31 | CY2023-RVIII-NS-L1 | CY2023-RVIII-NS-L1 | 45056 | 45064 | 45076 | 45120 | 45147 | OPEN BUILDERS INC | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.95 | 0.05 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region VIII | Northern Samar | 123246 | Maragat ES | SAN VICENTE | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17137208.72 | 16694048.17 | Completed | 1 | 2023-11-30 | 2024-05-10 | CY2023-RVIII-NS-L3 | CY2023-RVIII-NS-L3 | 45056 | 45064 | 45076 | 45120 | 45135 | SAL CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.6 | 0.4 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region VIII | Northern Samar | 123248 | Sangputan ES | SAN VICENTE | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16979262.11 | 16779231.77 | Completed | 1 | 2024-02-25 | 2024-04-18 | CY2024-RVIII-NS-L2 | CY2024-RVIII-NS-L2 | 45056 | 45064 | 45076 | 45120 | 45138 | CHRISTFER CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region VIII | Samar (Western Samar) | 123299 | Tonga-Tonga Elementary School | ALMAGRO | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE,RAINWATER COLLECTOR AND SOLAR PV ENERGY SYSTEM | 13792245.27 | 13635666.07 | Completed | 1 | 2024-01-25 | 2024-01-24 | CY2023-LMSP-LOT1 | 2023-019 | 45022 | 45030 | 45044 | 45065 | 45096 | SEGUA CONSTRUCTION | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Samar (Western Samar) | 123589 | Cristina Elementary School | JIABONG | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE,AND SOLAR PV ENERGY SYSTEM | 15199206.48 | 15033271.98 | Completed | 1 | 2023-12-26 | 2023-12-22 | CY2023-LMSP-LOT2 | 2023-020 | 45022 | 45030 | 45044 | 45065 | 45096 | TOM BUILDERS | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Southern Leyte | 122069 | Cabulisan Multi-Grade Elem.School | HINUNDAYAN | 2 | 1 | 4 | CONSTRUCTION OF TWO (2) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 20809347.25 | 11554829.22 | Completed | 1 | 2024-01-25 | 2024-04-14 | CY2023-LMS-L1 | CY2023-LMS-L1 | 45030 | 45041 | 45055 | 45124 | 45141 | VHITS D.G. BUILDERS & ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region VIII | Southern Leyte | 122254 | Sta. Filomena Elementary School | SAN JUAN (CABALIAN) | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 13874607.84 | 7704585.11 | Completed | 1 | 2023-12-16 | 2024-04-04 | CY2023-LMS-L2 | CY2023-LMS-L2 | 45030 | 45041 | 45055 | 45124 | 45141 | VHITS D.G. BUILDERS & ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1
LMS 2023 | Region X | Lanao del Norte | 127159 | Bowi PS | PANTAR | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17600258.64 | 14152726.43 | Completed | 1 | 2024-06-04 | 2024-05-30 | 2023 - 01(Infra) | 44927 | 2023-07-28 | 2023-08-07 | 2023-08-22 | 2023-09-01 | 2023-12-07 | SBM Builder's | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17609276.98 | 17116471.79 | Completed | 1 | 2025-03-20 | 2025-03-20 | 2024 - 09(Infra) | 45536 | 2024-06-06 | 2024-06-14 | 2024-07-05 | 2024-08-05 | 2024-08-26 | Lanao Genesis Construction Supply | 1st contract was terminated; 2nd contract NTP on Aug. 2024, looking for source of water for watersystem | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.98 | 0.02 | 5.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 1 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 17750076.13 | 17392036.74 | Ongoing | 0.95 | 2024-04-22 | 00:00:00 | LMS 2023 - RX - MISAMIS OCCIDENTAL - 001 - R | 016-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | Genetian Builders & Enterprises, Inc. | Schedule for Final Inspection on June 4, 2025. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 |  | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region X | Misamis Occidental | 127539 | Camanse ES | SINACABAN | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 17472250.06 | 16780281.43 | Completed | 1 | 2024-05-06 | 2024-06-13 | LMS 2023 - RX - MISAMIS OCCIDENTAL - 002 - R | 017-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-11-08 | Genetian Builders & Enterprises, Inc. | Completed with occupancy permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region X | Misamis Oriental | 130154 | Kinanao Pamalihi ES | BALINGASAG | 1 | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19632409.94 | 17364431.28 | Completed | 1 | 2024-05-04 | 2024-12-15 | PB - Construction-2023-002 | 4673305 | June 3,2023 | June 13,2023 | June 27,2023 | July 27,2023 | 2023-12-29 | Minkonstrak Engineering and Gen Services | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1
LMS 2023 | Region XI | Davao del Norte | 101973 | Kamingawan ES | TALAINGOD | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, RAIN WATER COLLECTOR AND WATER SYSTEM | 19766589.1 |  | Ongoing | 0.9 | [10 empty] | abandoned/ issued suspension due to unaccessable road | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 |  |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | Region XI | Davao del Norte | 501904 | Dulyan Integrated School | TALAINGOD | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, RAIN WATER COLLECTOR AND WATER SYSTEM | 16958383.69 |  | Completed | 1 | [10 empty] | abandoned/ issued suspension due to unaccessable road | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 |  | 0 | [5 empty] | 2 |  | 1
LMS 2023 | Region XI | Mati City | 102157 | Catmonan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 13168096.28 | 12980986.68 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | Region XI | Mati City | 129418 | Magum ES | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 12551905.33 | 12370674.27 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 12355882.59 | 12174043.03 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0
LMS 2023 | Region XI | Mati City | 102164 | Talucanga Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 14492041.68 | 11647469.14 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | BQPC Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0
LMS 2024 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9889180.89 | 9770516.9 | Completed | 1 | May 13, 2025 | May 17, 2025 | CAR-ABRA-2024-04-005 | 2024-07-011 | June15, 2024 | June 21, 2024 | July 03, 2024 | July 12, 2024 | September 3, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.82 | 0.18 | 5.25 | [8 empty] | 5th | 0
LMS 2024 | CAR | Abra | 305104 | Tineg National High School | TINEG | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9742716.24 | 9626000.22 | Ongoing | 0.796 | May 13, 2025 | 00:00:00 | CAR-ABRA-2024-04-005 | 2024-07-011 | June15, 2024 | June 21, 2024 | July 03, 2024 | July 12, 2024 | September 3, 2024 | SEMBRI CONSTRUCTION | suspended due to inaccesibility of roads | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0.646 | [9 empty] | 1st | 0
LMS 2024 | CAR | Apayao | 135242 | Namaltugan ES | CALANASAN (BAYAG) | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 12848533.6 | 11097515.65 | Completed | 1 | January 22,2025 | 00:00:00 | LMS-2024-002 |  | Dec 28,2023 | January 5,2024 | January 22,2024 | February 7,2024 | June 17,2024 | J.G. Yacas Construction,Supply and Equipment Rentals | ongoing correction of punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1
LMS 2024 | CAR | Apayao | 135257 | Caglayan ES | CONNER | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 11380362.07 | 12529250.6 | Completed | 1 | January 17,2025 | 00:00:00 | LMS-2024-001 |  | Dec 28,2023 | January 5,2024 | January 22,2024 | February 7,2024 | June 17,2024 | J.G. Yacas Construction,Supply and Equipment Rentals | ongoing correction of punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1
LMS 2024 | CAR | Benguet | 135684 | Yabyabuan MG School | SABLAN | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND SITE DEVELOPMENT | 18336389.21 | 17444882.84 | Completed | 1 | 2025-01-22 | 2025-01-15 | LMS-2024-02 | LMS-2024-02 | 2023-06-12 | 2023-12-13 | 2023-12-27 | 2024-02-07 | 2024-05-27 | MANIMELDS CONSTRUCTION AND IRON WORKS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 4th | 1
LMS 2024 | CAR | Benguet | 135685 | Andolor ES | TUBA | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND SITE DEVELOPMENT | 15677245.35 | 14458792.44 | Completed | 1 | 2025-01-16 | 2025-01-10 | LMS-2024-01 | LMS-2024-01 | 2023-06-12 | 2023-12-13 | 2023-12-27 | 2024-02-07 | 2024-05-21 | KAIT BUILDERS AND CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 5th | 1
LMS 2024 | CAR | Ifugao | 135753 | Halag E/S - Halag 3 (Riverside) | AGUINALDO | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, WATER SYSTEM, SLOPE PROTECTION AND PERIMETER FENCE (ONE BAY=3.0M) | 16279751.9 | 15802017.06 | Ongoing | 0.75 | 2025-06-06 | 2025-06-02 |  | 2024-03 | 2023-11-28 | 2023-12-05 | 2023-12-18 | 2024-01-02 | 2024-05-31 | MR-G Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.43 | 0.32 | [9 empty] | 5th | 0
LMS 2024 | CAR | Ifugao | 135912 | Pulaan PS | LAMUT | Lone | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY FOUR (4) (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, WATER SYSTEM,CONCRETE PAVEMENT AND PERIMETER FENCE (ONE BAY=3.0M) | 18781299.1 | 17620179.52 | Ongoing | 0.73 | 2025-06-06 | 00:00:00 |  | 2024-04 | 2023-11-28 | 2023-12-05 | 2023-12-18 | 2024-01-18 | 2024-05-31 | Al Muhandis Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.22 | 0.51 | [9 empty] | 2nd | 0
LMS 2024 | CAR | Kalinga | 136052 | Taggay Elementary School | PINUKPUK | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, WATER SYSTEM AND SITE LEVELING/IMPROVEMENT | 17317546.86 | 16893904.27 | Ongoing | 0.7 | March 19, 2025 | 00:00:00 | LMS 2024-CAR-KALINA-001 | LMS 2024-CAR-KALINA-001 | November 24, 2023 | December 5, 2023 | December 19, 2023 | February 5, 2024 | August 14, 2024 | Mighty Stellar Development Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.35 | 0.35 | [9 empty] | 4th | 0
LMS 2024 | CAR | Kalinga | 136064 | Liwan West Annex (Alibangbang PS) | RIZAL (LIWAN) | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH OUT TOILET) WITH PROVISION OF WATER AND SANITATION FACILITIES (4-SEATER), SCHOOL FURNITURE, SOLAR ENERGY SYSTEM AND PEREMETER FENCE | 19599915.89 | 19115517.14 | Ongoing | 0.7 | April 7, 2025 | 00:00:00 | LMS 2024-CAR-KALINA-002 | LMS 2024-CAR-KALINA-002 | November 24, 2023 | December 5, 2023 | December 19, 2023 | January 30, 2024 | August 18, 2024 | CNL Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.35 | 0.35 | [9 empty] | 3rd | 1
LMS 2024 | CAR | Mt. Province | 136308 | Natta'longan Elementary School | PARACELIS | Lone | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (ELEVATED) (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 50525998.85 | 49519489.88 | Ongoing | 0.76 | 2025-05-01 | 00:00:00 | INFRA-2023 -007 | INFRA-2023 -007 | November 25, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | 2024-07-05 | APO General Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.75 | 0.01 | [9 empty] | 1st | 1
LMS 2024 | CAR | Mt. Province | 136331 | Tambingan Elementary School | SABANGAN | Lone | 1 | 4 | CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 51045855.22 | 50030042.7 | Ongoing | 0.82 | 2025-05-31 | 00:00:00 | INFRA-2023 -008 | INFRA-2023 -008 | November 25, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | 2024-07-05 | FB Bantales Eng'g & Const'n | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.8 | 0.02 | [9 empty] | 1st | 1
LMS 2024 | CAR | Tabuk City | 220525 | BURAYUKAN ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE, SlOPE PROTECTION, SCHOOL GATE AND WATER SYSTEM | 26997429.04 | 26751878.94 | Completed | 1 | February 9 ,2025 | 2024-11-01 | I-2023-4 | I-2023-4 | December 2 - December 21, 2023 | December 8, 2023 @ 8:00pm | December 21, 2023 @ 10:00am | January 22, 2024 | May 15, 2024 | Bangyan 3D Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 | [8 empty] | 3rd | 0
LMS 2024 | CAR | Tabuk City | 136111 | SOTTO ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE, SlOPE PROTECTION, SCHOOL GATE AND WATER SYSTEM | 24327074.03 | 24078626.44 | Completed | 1 | February 9 ,2025 | 2024-11-01 | I-2024-I | I-2024-I | January 3 - January 22, 2024 | January 10, 2024 @ 10:00am | January 22, 2024 @ 1:00pm | January 26, 2024 | May 15, 2024 | Bangyan 3D Construction | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 | [8 empty] | 1st | 0
LMS 2024 | CARAGA | Agusan del Norte | 131588 | RAM Elementary School | TUBAY | 2nd | 1 | 4 | : CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 23088243.68 | 0 | Ongoing | 0.7 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.7 | [9 empty] | 5th | 1
LMS 2024 | CARAGA | Agusan del Sur | 212051 | Jose T. Cuyos, Sr. I PS | ROSARIO | 1st | 1 | 4 | CONSTRUCTION OF TWO(2) UNITS - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE and SOLAR PV ENERGY SYSTEM | 20300220.62 | 17777918.71 | Completed | 1 | 2025-01-07 | 2025-01-07 | 2024-06-028 | 2024-04-010 | 2024-05-01 | 2024-05-07 | 2024-05-20 | 2024-06-05 | 2024-08-07 | OBMB BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 4th | 1
LMS 2024 | CARAGA | Bayugan City | 131643 | Taglibas ES | CITY OF BAYUGAN | 1st | 1 | 4 | CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM COLLECTOR, | 22961884 | 0 | Ongoing | 0.85 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | Mt. Ararat realigned to Taglibas ES | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.85 |  |  |  |  | 1 | 4 | 22961884 |  |  | 4th | 1
LMS 2024 | CARAGA | Butuan City | 132072 | Doña Teodora ES | BUTUAN CITY (Capital) | 1st | 1 | 6 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 27272727.27 | 25950680.71 | Ongoing | 0.95 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | with suballotment already downloaded | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 | [9 empty] | 4th | 1
LMS 2024 | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22850951.92 | 2923591.71 | Ongoing | 0.9 | 2025-01-31 | 00:00:00 | 10312123 | 10312123 | 2023-11-13 | 2023-11-09 | 2023-12-06 | 2024-05-24 | 2024-05-24 | RELY CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 | [9 empty] | 5th | 1
LMS 2024 | CARAGA | Dinagat Island | 132558 | Sta Cruz Elementary School | TUBAJON | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SOLAR PV ENERGY SYSTEM, FURNITURES AND WATER SYSTEM | 22210093.61 | 21098025.14 | COMPLETED | 1 | 2024-11-20 | 2025-05-22 | INFRA2023-004 | INFRA2023-004 | 2023-12-04 | 2023-12-11 | 2024-01-03 | 2024-01-31 | 2024-05-25 | RJB CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 5th | 1
LMS 2024 | CARAGA | Siargao | 132223 | N.Sering Comm. Sch.ES | SOCORRO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16637813.31 | 16378679.01 | Ongoing | 0.18 | 2024-08-27 | 00:00:00 | BEFF-INFRA2024-001 | BEFF-INFRA2024-001 | 2024-01-27 | 2024-02-07 | 2024-04-02 | 2024-04-02 | 2024-05-29 | AN ESCALANTE CONSTRUCTION INC. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.18 | 0 | [9 empty] | 1st | 1
LMS 2024 | CARAGA | Surigao City | 132242 | Alegria ES | SURIGAO CITY (Capital) | 2nd | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22395355.38 | 18148693.46 | Completed | 1 | 2025-01-21 | 2025-01-20 | 2023-11-577 | FY-2023-INFRA-015 | 2023-12-10 | 2023-12-18 | 2024-01-05 | 2024-07-26 | 2024-08-09 | RELY CONSTRUCTION AND SUPPLY INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | CARAGA | Surigao del Norte | 132481 | Sani-Sani PS | PLACER | 2nd | 1 | 2 | CONSTRUCTION OF 1STY2CL (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18036516.81 | 17823108.98 | COMPLETED | 1 | 2024-10-20 | 2024-12-09 | 2024-001-LMS-CARAGA | INFRA003-2024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2024-05-09 | 2024-05-13 | RJB CONSTRUCTION AND SUPPLY | WITH TIME EXTENSION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 4th | 1
LMS 2024 | CARAGA | Surigao del Sur | 500571 | Pakwan Integrated School | LANUZA | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21869030.83 | 21626168.4137 | Ongoing | 0.9 | 2025-04-12 | 00:00:00 | LMS 2024 - R XIII - SURIGAO DEL SUR - 003 | 008 - 2024 | 2023-11-09 | 2023-11-15 | 2023-11-30 | 2024-02-19 | 2024-10-14 | RELY CONSTRUCTION AND SUPPLY | Contract time extension approved due to impassable roads caused by severe weather | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 | [9 empty] | 4th | 1
LMS 2024 | CARAGA | Tandag City | 132965 | Hitaob Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22162351.68 | 17311234.52 | Ongoing | 0.4 | 2025-01-07 | 00:00:00 | 2023-11-201 | 0 | 2023-11-29 | 2023-12-07 | 2023-12-27 | 2024-01-10 | 2024-07-09 | Grandstellar Builders Inc. | with time extension and suspension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 | [9 empty] | 4th | 1
LMS 2024 | Region I | La Union | 101087 | Sasaba PS | SANTOL | 1st | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17022941.1 | 16772636.16 | Completed | 1 | 2024-12-20 | 2024-12-10 | 2024LMS RO1-01 | SDOLU-2024 LMS-01 | 2024-08-04 | 2024-03-26 | 2024-04-11 | 2024-04-18 | 2024-06-24 | DPV BUILDERS AND CONSTRUCTION SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region I | La Union | 100821 | Bitag Elementary School | ARINGAY | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17910473.72 | 17679318.86 | Completed | 1 | 2025-04-28 | 2025-05-06 | 2024LMS RO1-02 | SDOLU-2024 LMS-02 | 2024-08-04 | 2024-03-26 | 2024-04-11 | 2024-04-18 | 2024-06-24 | LAV CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0.15 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region I | Pangasinan I, Lingayen | 500371 | Awag Integrated School | ANDA | 1st | 1 | 3 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 11559999.13 | Ongoing | 0.95 | 2025-05-05 | 2025-05-02 | 2024-06-003-INFRA |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-15 | 2024-10-08 | JFM Altitude Construction Corporation | for final inspection | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0.45 | [9 empty] | 1st | 1
LMS 2024 | Region II | Cagayan | 501171 | Taguing Integrated School | BAGGAO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS AND WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 13818238.93 | 8116162.4 | Ongoing | 0.95 | OCTOBER 26, 2024 | 00:00:00 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS AND WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | INFRA 2023-0125 LOT 1 | November 13, 2023 | NOVEMBER 5, 2023 | DECEMBER 5, 2023 | MAY 13, 2024 | MAY 29, 2024 | GCPK CONSTRUCTION AND SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.78 | 0.17 | [9 empty] | 1st | 0
LMS 2024 | Region II | Cagayan | 102578 | Tabbac ES | BUGUEY | 1st | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17029400.36 | 11646330.27 | Completed | 1 | OCTOBER 27, 2024 | 00:00:00 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | INFRA 2023-0125 LOT 3 | November 13, 2023 | NOVEMBER 5, 2023 | DECEMBER 5, 2023 | MAY 17, 2024 | MAY 30, 2024 | GANIE CONSTRUCTION | For final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.96 | 0.04 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Cagayan | 102736 | Tucalana Elementary School | LAL-LO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS AND WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 11886988.83 | 13638101.5 | Ongoing | 0.92 | November 20, 2024 | 00:00:00 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS AND WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | INFRA 2023-0125 LOT 2 | November 13, 2023 | NOVEMBER 5, 2023 | DECEMBER 5, 2023 | MAY 13, 2024 | may 24, 2024 | JIRK CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.07 | [9 empty] | 1st | 0
LMS 2024 | Region II | Cagayan | 155003 | Balagan Elementary School | SANTO NIÑO (FAIRE) | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM - 2CL | 14163603.2 | 10105949.45 | Ongoing | 0.89 | OCTOBER 25, 2024 | 00:00:00 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM - 2CL | INFRA 2023-0125 LOT 4 | November 13, 2023 | NOVEMBER 5, 2023 | DECEMBER 5, 2023 | MAY 13, 2024 | MAY 29, 2024 | BIFESA CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.04 | [9 empty] | 1st | 1
LMS 2024 | Region II | City of Ilagan | 103408 | San Rafael ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 16958663.8 | Completed | 1 | 2024-11-03 | february 03,2025 | 10315778 | INF-2024-02 | 2023-11-13 | NOVEMEBR 20, 2023 | DECEMBER 04,2023 | 2023-12-28 | 2024-06-24 | SMT CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 103273 | San Andres Elementary School | DELFIN ALBANO (MAGSAYSAY) | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS-ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22766285.57 | 22493466.3 | Completed | 1 | 00:00:00 | 2025-02-25 | Proj. No 2023-11-01 | 2024-0501 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 501150 | Daragutan West Integrated School | SAN MARIANO | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13962204.51 | 13788225.53 | Completed | 1 | 00:00:00 | 2024-12-10 | Proj. No 2023-11-01 | 2024-0501 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 501310 | Dibulo Integrated School | DINAPIGUE | 4th | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS-ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22800890.39 | 22463533.84 | Completed | 1 | 00:00:00 | 2025-05-14 | Proj. No 2023-11-02 | 2024-0502 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 103462 | Dalibubon Elementary School | JONES | 4th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13962204.51 | 13788225.53 | Completed | 1 | 00:00:00 | 2025-05-14 | Proj. No 2023-11-02 | 2024-0502 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 103498 | Manano Elementary School - Main | MALLIG | 5th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 13962204.51 | 13822582.46 | Completed | 1 | 00:00:00 | 2024-10-14 | Proj. No 2023-11-03 | 2024-0503 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Isabela | 103284 | Benguet Elementary School | ECHAGUE | 6th | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS-ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22800890.39 | 22572881.49 | Completed | 1 | 00:00:00 | 2025-05-14 | Proj. No 2023-11-03 | 2024-0503 | November 11,2023 | November 20,2023 | December 05,2023 | 2023-12-13 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Nueva Vizcaya | 156001 | Tidang Village ES | KAYAPA | Lone | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17157372.61 | 13430612.1 | COMPLETED | 1 | 11/27/2024 | March 6, 2025 | PB01-004-SDONV-CY2024LMS | PB01-004-SDONV-CY2024LMS | 01/21/2024 | 01/20/2024 | 2024-07-02 | 02/26/2024 | 2024-10-05 | MBW Construction | with time extension due to bad weather | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9455 | 0.0545 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region II | Quirino | 156510 | Didang PS | NAGTIPUNAN | Lone | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11267016.46 | 10547583.26 | Completed | 1 | 2024-09-18 | 00:00:00 | LMS 2024 - II - QUIRINO - 001 | 53-12-22-2023 | 2023-12-23 | 2023-12-29 | 2024-01-11 | 2024-02-15 | 2024-06-05 | NTL BUILDERS & DEVELOPER | with Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.95 | 0.05 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Bulacan | 158519 | Talamsi II ES | DOÑA REMEDIOS TRINIDAD | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18181818.18 | 17959590.65 | Completed | 1 | 2025-01-08 | 2024-12-20 | PB-24-005 | PB-24-05-011 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-06-05 | EMICA BUILDERS AND SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 105296 | Manuel Tiaoqui Elementary School (Formerly Tagtagumbao PS) | CUYAPO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 14568887.4 | 14370537.84 | completed | 1 | 2025-01-12 | 2025-03-11 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-001-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-15 | IJKMAE CONSTRUCTION INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 159020 | Tamale ES (Former Jaime L. Gamilla ES Annex) | BONGABON | 3rd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17167389.49 | 16942768.53 | completed | 1 | 2025-01-12 | 2025-03-11 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-002-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-15 | JOYUS CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Nueva Ecija | 105594 | Singgalat ES | PALAYAN CITY (Capital) | 3rd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17167389.49 | 16832451.48 | completed | 1 | 2025-01-05 | 2024-11-28 | DEPED-NE-INFRA-063-2024 | INFRA-NE-LMS-003-2024 | 2024-03-08 | 2024-03-20 | 2024-04-02 | 2024-05-22 | 2024-08-08 | V TRILLANA BUILDERS & TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 2nd | 1
LMS 2024 | Region III | Pampanga | 502153 | Sebitanan Integrated School | SASMUAN (SEXMOAN) | 2nd | 1 | 6 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - SIX (6) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET IN EACH CLASSROOM) WITH PROVISION OF SCHOOL FURNITURE | 17171717.17 | 16961394.45 | Completed | 1 | 2025-01-05 | 2025-01-03 | I-2024-002 | I-2024-002 | 2023-11-16 | 2023-11-24 | 2023-12-06 | 2024-05-24 | 2024-05-31 | V. TRILLANA BUILDERS AND TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 0
LMS 2024 | Region III | Pampanga | 300939 | Tagulod High School | CANDABA | 4th | 1 | 6 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - SIX (6) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET IN EACH CLASSROOM) WITH PROVISION OF SCHOOL FURNITURE & DETACHED HANDWASHING FACILITY | 17171717.17 | 16964878.39 | Completed | 1 | 2024-12-30 | 2024-12-09 | I-2024-003 | I-2024-003 | 2023-11-16 | 2023-11-24 | 2023-12-06 | 2024-05-24 | 2024-05-31 | TRACCOR BUILDERS | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 0
LMS 2024 | Region III | Tarlac | 106552 | Sapang ES | MONCADA | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 12791493.32 | 8769144.65 | Ongoing | 0.95 | 2025-05-01 | 00:00:00 | 0 | 0 | 00:00:00 | 2024-06-03 | 2024-06-17 | 2024-06-28 | 2024-09-18 | HOR-VERT ENTERPRISES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.1 | [9 empty] | 4th | 0
LMS 2024 | Region III | Zambales | 106945 | Buhawen Elementary School | SAN MARCELINO | 1st | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 16950000 | completed | 1 | 2025-01-02 | 2025-02-15 | Infra-2024-001 | Infra-2024-002 | 2023-11-23 | 2023-11-29 | 2023-12-11 | 2023-12-18 | 2024-06-06 | V. TRILLANA BUILDERS AND TRADING | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region III | Zambales | 106915 | Manggahan Elementary School | PALAUIG | 2nd | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 13378953.8 | completed | 1 | 2024-12-04 | 2025-05-06 | Infra-2024-001 | Infra-2024-004 | 2023-11-23 | 2023-11-29 | 2023-12-11 | 2023-12-18 | 2024-06-07 | THREE CM Builders | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1
LMS 2024 | Region IV-A | Batangas | 107828 | Gumapac Barangay School | TUY | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18412863.76 | 17900000 | Ongoing | 0.35 | 2025-08-04 |  | LMS 2024 - IVA - BATANGAS - 001 | LMS 2024 - IVA - BATANGAS - 001 | June 11,2024 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Botey Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.35 | [9 empty] | 1st | 1
LMS 2024 | Region IV-A | Batangas | 107583 | Tulos Elementary School | ROSARIO | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18151995.7 | 18150000 | Ongoing | 0.35 | 2025-08-04 |  | LMS 2024 - IVA - BATANGAS - 002 | LMS 2024 - IVA - BATANGAS - 002 | June 11,2024 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Botey Construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0.1 | [9 empty] | 1st | 1
LMS 2024 | Region IV-A | Cavite | 108119 | Guitasin Primary School | SILANG | 5th | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24907973.66 | Ongoing | 0.5 | 2025-07-13 | 00:00:00 | RIVACaviteBACInfra 005-2024 | RIVACaviteBACInfra 005-2024 | 2024-08-01 | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction | On-going masonry works and preparation of roofing works | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0.35 | [9 empty] | 1st | 1
LMS 2024 | Region IV-A | Laguna | 164519 | Sitio Pulot/Bay ES | KALAYAAN | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16454451.88 |  | Under Procurement | 0 | [10 empty] | For reversion due to the issue on School Site with NPC (under negotiation) / awaiting letter from SDO. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 3rd | 1
LMS 2024 | Region IV-A | Quezon | 108570 | SAN RAFAEL ELEMENTARY SCHOOL | BURDEOS | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19200611.34 | 18954730.71 | Completed | 1 | 2025-03-05 | 2025-03-04 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | N.T. Sotelo Contruction & Supply Corporation | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.87 | 0.13 | 5.25 | [8 empty] | 3rd | 1
LMS 2024 | Region IV-A | Quezon | 109096 | Segaras ES | SAN ANDRES | 3rd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16402689.46 | 13000000 | Completed | 1 | 2024-11-15 | 2024-10-18 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | Botey Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 | [8 empty] | 3rd | 1
LMS 2024 | Region IV-A | Quezon | 108735 | DUNGAWAN PAALYUNAN ES | GUINAYANGAN | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 16402689.46 | 14411651.63 | Completed | 1 | 2024-11-15 | 2025-01-30 | 2023-05-INFRAEPA | 2023-05-INFRAEPA | 2023-11-24 | 2023-12-01 | 2023-12-15 | 2023-12-29 | 2024-05-20 | M.G. Villamin Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region IV-A | Tayabas City | 109249 | Eugenio Francia Elementary School | CITY OF TAYABAS | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23636363.64 |  | Under Procurement | 0 | [10 empty] | Preparation of Plans / POW/DUPA Modified Design | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region IV-B | Oriental Mindoro | 137017 | Magdayaga Elementary School | Bongabong | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21109748.66 | 20837923.61 | Completed | 1 | 2025-01-25 | 2023-12-20 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 003 | LMS 15-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | CMSEL CONST. AND DEVELOPER | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1
LMS 2024 | Region IV-B | Oriental Mindoro | 306032 | Bailan Katutubong Mangyan High School | Bulalcao | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21994317.96 | 21725000 | Completed | 1 | 2025-05-27 | 2025-05-23 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 002 | LMS 14-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | A.D.L. CONSTRAK OPC | With contract time extensions due to frequent rains and armed conflict. Final payment on process. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.86 | 0.14 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region IV-B | Oriental Mindoro | 137102 | EM Fabella-Ansaldo Elementary School | Roxas | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20756365.76 | 20230000 | Completed | 1 | 2025-01-25 | 2024-12-03 | LMS 2024 - MIMAROPA - ORIENTAL MINDORO - 001 | LMS 13-2024 | Nov. 29, 2023 | Dec. 7, 2023 | Dec. 20, 2023 | Jan. 4, 2024 | May 20, 2024 | A.D.L. CONSTRAK OPC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1
LMS 2024 | Region IV-B | Palawan | 111056 | Batang-Batang Beach Elementary School | NARRA | 2nd | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 15827000 | Ongoing | 0.15 | 2025-10-22 | 00:00:00 | 2024-01-001_INFRA | 2025-03-001 | 2024-11-15 | 2024-11-26 | 2024-11-29 | 2025-12-16 | 2025-03-26 | Maryknoll Builders & Ssupply | NEGOTIATED PROCUREMENT | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region IV-B | Puerto Princesa City | 111511 | Cabayugan ES - Sugod Extension | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21248071.44 | 20966655 | Ongoing | 0.5 | May 18, 2025 | 00:00:00 | LMS 2024 - MIMAROPA - PUERTO PRINCESA CITY - 002 | INFRA 2024-07-005 | 2024-06-25 | 2024-07-01 | July 15, 2024 | July 23, 2024 | Sept. 19, 2024 | Maryknoll Builders & Ssupply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0 | [9 empty] | 4th | 1
LMS 2024 | Region IV-B | Puerto Princesa City | 111520 | Makirawa ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 20830359.96 | 20620761 | Completed | 1 | January 15, 2025 | 00:00:00 | LMS 2024 - MIMAROPA - PUERTO PRINCESA CITY - 001 | INFRA 2023-11-04 | Nov. 22, 2023 | Nov. 28, 2023 | Dec. 11, 2023 | Dec. 22, 2023 | May 13, 2024 | Joint Venture of Ian Jason Construction & Supply and RBM2 Construction | For Final Inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region IV-B | Romblon | 171008 | Palati PS | ODIONGAN | Lone | 1 | 3 | LMSP - PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 19645773.82 | 0 | Ongoing | 0.7977 | 00:00:00 | 00:00:00 | INF-LMS-2024-01 | INF-LMS-2024-01 | 2023-11-14 | 2023-11-21 | 2023-12-05 | 2024-01-29 | 2024-05-22 | RMR Construction and Trading | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.65 | 0.1477 | [9 empty] | 1st | 1
LMS 2024 | Region IV-B | Romblon | 111437 | Layag Cultural Minority School | SAN FERNANDO | Lone | 1 | 2 | LMSP - PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 15486264.53 | 0 | Ongoing | 0.4 | 00:00:00 | 00:00:00 | INF-LMS-2024-02 | INF-LMS-2024-02 | 2023-11-14 | 2023-11-21 | 2023-12-05 | 2024-01-29 | 2024-05-22 | RMR Construction and Trading | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.4 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region IX | Dapitan City | 125928 | Daro Elementary School | DAPITAN CITY | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITs ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 22816847.47 | 22512075.6 | Ongoing | 0.7 | November 14, 2024 | - | SDODAP-INFRA-2023-004 | SDODAP-INFRA-2023-004 | November 14, 2023 | November 21, 2023 | December 07, 2023 | May 06, 2024 | May 17, 2024 | MORTE CONSTRUCTION | - | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.7 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region IX | Isabela City | 502129 | Badjao Floating Integrated School | CITY OF ISABELA (Capital) | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19205159.17 | 17785991.82 | Ongoing | 0.58 | 2025-06-27 | - | INFRAEPA2024-01 | - | - | 2024-11-15 | 2023-12-04 | 2024-05-16 | 2024-09-02 | 2M CONSTRUCTION AND ENTERPRISES | NONE | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.58 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region IX | Pagadian City | 198503 | Bentud Pinukis Penintulan Nu Piksalabukan Subanen | PAGADIAN CITY (Capital) | 1st | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22198056.48 | 21927158.04 | COMPLETED | 1 | December 04, 2024 | December 04, 2024 | LMS-2024-RIX-PAG-01 | LMS-2024-RIX-PAG-01 | November 13, 2023 | November 21, 2023 | December 04, 2023 | December 11, 2023 | June 03, 2024 | GENETIAN BUILDERS & ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga City | 126168 | Pasilmanta ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24974606.93 | Completed | 1 | November 30, 2024 | 2025-02-13 | LMS 2024 -RIX- ZAMBO CITY - 02 | LMS 2024 -RIX- ZAMBO CITY - 02 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga City | 126133 | Simanta ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24988205.79 | Completed | 1 | November 30, 2024 | 2025-02-10 | LMS 2024 -RIX- ZAMBO CITY - 01 | LMS 2024 -RIX- ZAMBO CITY - 01 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga City | 126167 | Panganak ES | ZAMBOANGA CITY | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 25252525.25 | 24980749.43 | Completed | 1 | November 30, 2024 | 2025-05-28 | LMS 2024 -RIX- ZAMBO CITY - 03 | LMS 2024 -RIX- ZAMBO CITY - 03 | October 30,2023 | November 7, 2023 | November 20,2023 | May 13,2024 | June 03, 2024 | ZAMBOANGA 3VC CONSTRUCTION INC, | With Approved Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.95 | 0.05 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga del Norte | 124673 | Tinago ES | SERGIO OSMEÑA SR. | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 24985083.83 | 25698497.43 | COMPLETED | 1 | November 20, 2024 | 2024-10-30 | 2024-005-CBZN | CB-2024-018 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 20, 2024 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga del Norte | 303702 | SITOG NHS - SEROAN EXT. | KATIPUNAN | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER SOLAR LIGHT, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 24985434.88 | 24704050.49 | COMPLETED | 1 | November 20, 2024 | 2024-10-30 | 2024-006-CBZN | CB-2024-019 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 20, 2024 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 | [8 empty] | 4th | 1
LMS 2024 | Region IX | Zamboanga del Sur | 125481 | Sto. Rosario Elementary School | TUKURAN | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23519080.9 | 21703822.5 | COMPLETED | 1 | 2024-12-28 | 2025-03-06 | ZDS-24-LMS-01 | ZDS-24-LMS-01 | 2023-11-13 | 2023-11-21 | 2023-12-04 | 2024-01-03 | 2024-05-22 | R.R. GANDINGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 2nd | 1
LMS 2024 | Region IX | Zamboanga del Sur | 125350 | TAPIAN ES | SAN MIGUEL | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET), SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22127905.86 | 20576515 | COMPLETED | 1 | 2024-11-18 | 2024-11-15 | ZDS-24-LMS-02 | ZDS-24-LMS-02 | 2023-11-13 | 2023-11-21 | 2023-12-04 | 2024-01-03 | 2024-05-22 | R.R. GANDINGAN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 1st | 1
LMS 2024 | Region IX | Zamboanga Sibugay | 303858 | Bulawan NHS | Payao | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 13539348.82 | 12340386.36 | Completed | 1 | October 23, 2024 | March 19, 2025 | ZSY-2024LMS-01 | ZSY-2024LMS-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 26, 2024 | Long Island Builders and Construction | With Approved Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 0
LMS 2024 | Region IX | Zamboanga Sibugay | 125833 | Paruk ES | Siay | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND WATER SYSTEM | 9316708.43 | 8213612.07 | Completed | 1 | September 24, 2024 | March 19, 2025 | ZSY-2024LMS-02 | ZSY-2024LMS-02 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 26, 2024 | Long Island Builders and Construction | With Approved Time Extension due to manhauling of construction materials from barangay road to site area | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 1st | 0
LMS 2024 | Region V | Camarines Norte | 501259 | Malaya Integrated School | LABO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND RAIN WATER COLLECTOR TWO (2) SETS | 17467038.05 | 10339297.77 | COMPLETED | 1 | 2024-12-11 | 2025-02-09 | INFRA06-11-2023CN | INFRA06-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-06-14 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.67 | 0.33 | 5.25 | [8 empty] | 1st | 0
LMS 2024 | Region V | Camarines Norte | 112308 | Mangcawayan Island Elementary School | VINZONS | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND RAIN WATER COLLECTOR TWO (2) SETS - TRIPLE HAULING | 13898660.22 | 9599009.6 | COMPLETED | 1 | 2024-11-11 | 2025-01-10 | INFRA06-11-2023CN | INFRA06-11-2023CN | 2023-11-07 | 2023-11-15 | 2023-12-06 | 2024-01-16 | 2024-06-14 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION | WITH RETIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.57 | 0.43 | 5.25 | [8 empty] | 1st | 0
LMS 2024 | Region V | Camarines Sur | 300315 | Salvacion High School | SIPOCOT | 1st | 1 | 8 | PROPOSED CONSTRUCTION OF 2 UNITS, 1 STOREY, 4 CLASSROOM SCHOOL BUILDING W/ 2 UNITS, 4 SEATER WATER AND SANITATION FACILITIES, 2 UNITS RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 2 UNITS, 1 STOREY, 4 CLASSROOM SCHOOL BUILDING | 34039259.84 | 33361240.37 | COMPLETED | 1 | 2024-12-08 | 2025-03-11 | 2024-05-043 | 2024-05-043 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-10 | 2024-06-11 | Honeyville Construction | approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0.15 | 5.25 | [8 empty] | 1st | 0
LMS 2024 | Region V | Camarines Sur | 112696 | Tampuhan ES | LIBMANAN | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10803221.3 | 9474512.96 | Ongoing | 0.99 | 2024-10-26 |  | 2024-05-044 | 2024-05-044 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-22 | 2024-06-13 | TGME Construction and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.87 | 0.12 | 6.25 | [8 empty] | 4th | 0
LMS 2024 | Region V | Camarines Sur | 112757 | Barobaybay ES | MAGARAO | 3rd | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10728585.06 | 10342846.08 | Completed | 1 | 2024-10-09 |  | 2024-05-045 | 2024-05-045 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-18 | 2024-06-11 | TRDV Construction and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 4th | 0
LMS 2024 | Region V | Camarines Sur | 112556 | Oring ES | CARAMOAN | 4th | 1 | 4 | PROPOSED CONSTRUCTION OF 2 UNITS, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 2 UNITS, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 22399589.68 | 22130242.21 | Completed | 1 | 2024-10-11 |  | 2024-05-046 | 2024-05-046 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2023-12-29 | 2024-06-13 | TGME Construction and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [8 empty] | 4th | 0
LMS 2024 | Region V | Camarines Sur | 500468 | Harrison Integrated School | GARCHITORENA | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11795242.42 | 11526923.04 | Ongoing | 0.99 | 2024-10-19 |  | 2024-05-047 | 2024-05-047 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-18 | 2024-06-21 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0.09 | 6.25 | [8 empty] | 1st | 1
LMS 2024 | Region V | Camarines Sur | 112324 | Cristo Rey Elementary School | BAAO | 5th | 1 | 2 | PROPOSED CONSTRUCTION OF 1 UNIT, 1 STOREY, 2 CLASSROOM SCHOOL BUILDING W/ 1 UNIT, 4 SEATER WATER AND SANITATION FACILITIES, 1 UNIT RAINWATER COLLECTOR, AND SCHOOL FURNITURE FOR 1 UNIT, 1 STO - 2 CL (7m x 9m) SCHOOL BUILDING | 10792740.79 | 8646767.36 | Ongoing | 0.99 | 2024-10-08 |  | 2024-05-048 | 2024-05-048 | 2023-11-23 | 2023-12-01 | 2023-12-13 | 2024-01-22 | 2024-06-10 | RIDERS CORNER BUILDING AND REALTY DEVELOPMENT CORPORATION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0.09 | 6.25 | [8 empty] | 1st | 0
LMS 2024 | Region V | Catanduanes | 174016 | Pananaogan Elementary School | BATO | Lone | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17171717.17 | 16742770.61 | Completed | 1 | 2024-10-22 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2024-05-24 | STEVEN CONSTRUCTION& SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 11.24 | [8 empty] | 1st | 1
LMS 2024 | Region V | Catanduanes | 113296 | Siay Elementery School | SAN MIGUEL | Lone | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY THREE (3) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 17637171.72 | 17186395.36 | Ongoing | 0.95 | 2024-10-22 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 2024-05-24 | NGS CONSTRUCTION& SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region V | Masbate | 113866 | Daplian ES | SAN FERNANDO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12273116.16 | 12130990.29 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-026 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.9 | [9 empty] | 1st | 1
LMS 2024 | Region V | Masbate | 113893 | Jagna-an ES | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12273116.16 | 12131339.29 | Ongoing | 0.8 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-027 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.8 | [9 empty] | 1st | 1
LMS 2024 | Region V | Masbate | 113896 | Mabini Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11598060.61 | 11468418.82 | Ongoing | 0.85 | 2025-05-27 | 00:00:00 | INFRA 2024-09-003 | 2024-021 | 2024-09-10 | 2024-09-18 | 2024-09-30 | 2024-10-22 | 2024-12-28 | SMDF CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.85 | [9 empty] | 1st | 1
LMS 2024 | Region V | Masbate | 113898 | Roosevelt Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12015834.81 | 11839039.3 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-08-002 | 2024-028 | 2024-08-12 | 2024-08-20 | 2024-09-02 | 2024-09-20 | 2024-12-28 | JOHNCB CONSTRUCTION & SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.9 | [9 empty] | 1st | 1
LMS 2024 | Region V | Masbate | 113902 | Tutuban Elementary School | SAN JACINTO | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11598060.61 | 11469699.82 | Ongoing | 0.9 | 2025-05-27 | 00:00:00 | INFRA 2024-09-003 | 2024-022 | 2024-09-10 | 2024-09-18 | 2024-09-30 | 2024-10-22 | 2024-12-28 | SMDF CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.9 | [9 empty] | 2nd | 1
LMS 2024 | Region V | Masbate City | 500393 | Alejandro Delos Reyes Integrated School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 20202020.2 | 19798704.92 | COMPLETED | 1 | 2025-04-20 | 2025-04-18 | LMS 2024 - RV - MASBATE CITY - 001 | LMS 2024 - RV - MASBATE CITY - 001 | 2024-03-07 | 2024-03-15 | 2024-04-01 | 2024-07-01 | 2024-07-15 | GINA'S CONSTRUCTION SERVICES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.81 | 0.19 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region V | Sorsogon | 114136 | Sto. Nino Elementary School | CASTILLA | 1st | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, SOLAR PV ENERGY SYSTEM | 18030049.99 | 16059049.82 | Ongoing | 0.2 | 2025-08-10 | 00:00:00 | 24-04-004 | 24-04-004 | 2024-04-30 | 2024-05-08 | 2024-05-20 | 2024-12-06 | 2025-03-14 | 144 Cubits Builders and Supply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.2 | [9 empty] | 3rd | 1
LMS 2024 | Region V | Sorsogon | 302769 | Sablayan High School | JUBAN | 2nd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, SOLAR PV ENERGY SYSTEM, SLOPE PROTECTION PROTECTION | 20447749.05 | 18206941.63 | Ongoing | 0.1 | 2025-09-09 | 00:00:00 | 24-04-004 | 24-04-004 | 2024-04-30 | 2024-05-08 | 2024-05-20 | 2024-12-06 | 2025-03-14 | 144 Cubits Builders and Supply | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.1 | [9 empty] | 2nd | 1
LMS 2024 | Region VI | Aklan | 114860 | Cogon Elementary School | MALINAO | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21223289.1 | 20460400.84 | Completed | 1 | 2025-01-31 | 2025-02-14 | DepED-RO6-D1-2024-CY2024-LMS-056-2024 | DepED-RO6-D1-2024-CY2024-LMS-056-2024 | 2023-11-14 | 2023-11-21 | 2023-12-04 | 2024-01-19 | 2024-05-29 | GMO CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 3rd | 1
LMS 2024 | Region VI | Antique | 115268 | Panpanan I ES | SAN REMIGIO | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE(1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17377521.03 | 12162100.86 | Ongoing | 0.3 | 2025-09-19 | 00:00:00 | R6-D2-GAA2024-07-NC | R6-D2-GAA2024-07-NC | 2024-01-26 | 2024-02-02 | 2024-02-16 | 2024-04-05 | 2024-07-19 | MDG Const. & Supply | Already issued ressumption order last February 24, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0.15 | [9 empty] | 3rd | 1
LMS 2024 | Region VI | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2nd | 1 | 5 | CONSTRUCTION OF 1STY 5CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM with hauling cost | 16383838.38 | 15997903.42 | Ongoing | 0.75 | 2025-03-07 | 00:00:00 | 0 | 0 | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-08-06 | 2024-02-10 | Keanne construction services | With approved 150CD time extension due to unpassable road (landslide/manual hauling/unpassable road) Project ID and Contract ID to be confirmed from the BAC Secretariat | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.35 | 0.4 | [9 empty] | 4th | 1
LMS 2024 | Region VI | Capiz | 500796 | Duluan Integrated School | MA-AYON | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 24242424.24 | 14878415.3 | Ongoing | 0.85 | 2025-06-19 | 00:00:00 | R6-DepEd-Capiz-CY 2024-BEFF-DuluanIS-Lot1 | CB No. 2024 - 032 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-14 | AMD ENGINEERING AND CONSTRUCTION SUPPLY | REQUESTED FOR 60 CD TIME EXTENSION. APPROVED LAST APRIL 2, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0.4 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Capiz | 501439 | Sinamongan Integrated School | PILAR | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21919191.92 | 13454000 | Ongoing | 0.95 | 2025-05-03 | 00:00:00 | R6-DepEd-Capiz-CY 2024-BEFF-SinamonganIS-Lot2 | CB No. 2024 - 033 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-25 | TUNGALA CONSTRUCTION SERVICES | SUBSTANTIALLY COMPLETED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0.45 | [9 empty] | 5th | 1
LMS 2024 | Region VI | Guimaras | 115903 | Paaralan ng Buhay ng Taras | NUEVA VALENCIA | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 17188760.85 | 16914477.63 | Completed | 1 | 2024-10-26 | 2024-12-27 | No. 06-2024 | No. 06-2024 | 2023-10-16 | 2023-10-24 | 2023-11-05 | 2024-05-13 | 2024-05-24 | Early Riser Construction | With approved time extension due to unworkable weather conditions & change/increase of elevation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 5th | 0
LMS 2024 | Region VI | Himamaylan City | 117066 | Balatogan Elementary School | CITY OF HIMAMAYLAN | 5th | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17171717.17 | 16860289.87 | Ongoing | 0.75 | 2025-06-12 | 00:00:00 | 2024-10-0006 | 2024-10-0006 | 2024-06-29 | 2024-07-11 | 2024-07-23 | 2024-08-20 | 2024-10-08 | JCORD Construction | On going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0.45 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Iloilo | 116833 | Lubog Primary School | TIGBAUAN | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 12634605.87 | Ongoing | 0.5 | 2025-10-10 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L3 | BEFF2024-RVI-022-ILOILO-LMS-L3 | 2024-08-07 | 2024-08-14 | 2024-08-30 | 2024-09-13 | 2025-02-12 | EC Builders | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0.3 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Iloilo | 115973 | Aglay-ao Primary School | ANILAO | 4th | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 14058943.18 | Ongoing | 0.4 | 2025-04-04 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L2 | BEFF2024-RVI-022-ILOILO-LMS-L2 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-12-23 | 2025-02-27 | CDJ Builders Corporation | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0.15 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Iloilo | 116064 | California PS | BAROTAC VIEJO | 5th | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 13610045.75 | Ongoing | 0.3 | 2025-04-04 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L1 | BEFF2024-RVI-022-ILOILO-LMS-L1 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-12-23 | 2025-02-27 | CDJ Builders Corporation | with NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.15 | 0.15 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Negros Occidental | 117026 | Gahit ES | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11139555.27 | Ongoing | 0.85 | 2025-03-03 | 00:00:00 | 23-11-29 | 24-09-005 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-17 | KEANNE CONSTRUCTION SERVICES | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.7 | 0.15 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Negros Occidental | 117262 | E. Basa ES | MOISES PADILLA (MAGALLON) | 5th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 9895300.9 | Ongoing | 0.85 | 2025-02-15 | 00:00:00 | 23-11-29 | 24-09-003 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-04 | CGGFR Construction and Construction Supply | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.75 | 0.1 | [9 empty] | 1st | 1
LMS 2024 | Region VI | Negros Occidental | 180510 | Montelo ES | ILOG | 6th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11222892.59 | Ongoing | 0.85 | 2025-03-03 | 00:00:00 | 23-11-004 | 24-09-004 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-20 | Par Builders | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0.4 | [9 empty] | 1st | 1
LMS 2024 | Region VII | Cebu | 119637 | TUBOD ES | SAN FERNANDO | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF TWO (2) UNITS ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 14679322.67 | 10400000 | Ongoing | 0.8 | 28/04/2025 | 00:00:00 | CY 2024 BEFF LMS-DepED-R7-Cebu-01 | CY 2024 BEFF LMS-DepED-R7-Cebu-01 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | TRI-BAIRN CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.6 | 0.2 | [9 empty] | 1st | 0
LMS 2024 | Region VII | Cebu | 119699 | LIPTONG ES | SANTANDER | 2nd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 11508290.01 | 11393207.11 | COMPLETED | 1 | 28/04/2025 | 28/04/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-02 | CY 2024 BEFF LMS-DepED-R7-Cebu-02 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | RT CONSTRUCTION & ENTERPRISES | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.8 | 0.2 | 5.25 | [8 empty] | 6th | 0
LMS 2024 | Region VII | Cebu | 118976 | KALUANGAN II | ASTURIAS | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 11508290.01 | 11328208.14 | COMPLETED | 1 | 28/04/2025 | 28/04/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-03 | CY 2024 BEFF LMS-DepED-R7-Cebu-03 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | ANIELTHON CONSTRUCTION & SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.8 | 0.2 | 5.25 | [8 empty] | 6th | 0
LMS 2024 | Region VII | Cebu | 119435 | TARONG ES | MADRIDEJOS | 4th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 8027122.46 | 7907423.97 | Ongoing | 0.8 | 29/03/2025 | 00:00:00 | CY 2024 BEFF LMS-DepED-R7-Cebu-04 | CY 2024 BEFF LMS-DepED-R7-Cebu-04 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | ROVILLA CONSTRUCTION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0.3 | [9 empty] | 6th | 0
LMS 2024 | Region VII | Cebu | 119214 | CAN-IBUANG PS | CATMON | 5th | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE AND WATER SYSTEM (DEEP WELL) | 8027122.46 | 7900000 | COMPLETED | 1 | 29/03/2025 | 29/03/2025 | CY 2024 BEFF LMS-DepED-R7-Cebu-05 | CY 2024 BEFF LMS-DepED-R7-Cebu-05 | 2024-11-06 | 18/06/2024 | 2024-02-07 | 16/08/2024 | 22/10/2024 | TRI-BAIRN CONSTRUCTION | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.85 | 0.15 | 5.25 | [8 empty] | 2nd | 0
LMS 2024 | Region VII | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21640739.3 | 18676898.11 | Ongoing | 0.8 | 2025-07-29 | 00:00:00 | ITB 2023-11-145 | LMS202405023 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With approved time extension due to access road issue during rainy days, unworkable weather condition, with change order to cover other essential items(refer to Variation order). Double hauling | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.65 | 0.15 | [9 empty] | 1st | 1
LMS 2024 | Region VII | Negros Oriental | 120027 | PANUSUAN ELEMENTARY SCHOOL | AMLAN | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 15703660.79 | 12964000.46 | COMPLETED | 1 | 2025-02-14 | 2025-02-14 | ITB 2023-11-146 | LMS202405024 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension due to variation orders, cutting of trees permit and unworkable weather condition | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 4th | 1
LMS 2024 | Region VII | Negros Oriental | 120618 | Nasuji Elementary School | VALENCIA (LUZURRIAGA) | 3rd | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22517074.36 | 19373377.44 | COMPLETED | 1 | 2025-05-15 | 2025-05-13 | ITB 2023-11-147 | LMS202405025 | 2023-11-09 | 2023-11-16 | 2023-11-28 | 2023-12-04 | 2024-05-22 | TrinityCAD Corporation | With time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.94 | 0.06 | 5.25 | [8 empty] | 4th | 1
LMS 2024 | Region VII | Siquijor | 120662 | New Corregidor Elementary School | LARENA | Lone | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE | 8295101.98 | 7573374.84 | Ongoing | 0.95 | 2024-11-11 | 2025-05-30 | 10336667 | 2023-89 | 2023-11-22 | 2023-11-29 | 2023-12-11 | 2023-12-12 | 2024-05-16 | Nale Construction | with Time Extension. Revised completion date December 31, 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.91 | 0.04 | [9 empty] | 1st | 0
LMS 2024 | Region VII | Talisay City | 119804 | Tapul Elementary School | Talisay City | 1st | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 21184978.14 | 20952888 | COMPLETED | 1 | 2025-01-31 | 2025-01-31 | 2024-001 | 45436 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-18 | 2024-06-06 | Quirante Construction Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 3rd | 0
LMS 2024 | Region VII | Toledo City | 120736 | NEW BUCAO ELEMENTARY SCHOOL | TOLEDO | 3rd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 9772031.96 | 10376058.62 | Ongoing | 0.2 | 2025-07-27 | 00:00:00 | LMS 2023-R VII-TOLEDO CITY-001 | 2024-015 | Mar. 21, 2024 | Mar. 27, 2024 | Apr. 8, 2024 | Apr. 19, 2024 | Feb. 27, 2025 | Tribairn Construction | Late issuance of NTP due to road not passable | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.1 | 0.1 | [9 empty] | 3rd | 0
LMS 2024 | Region VIII | Baybay City | 121144 | Villa Mag-aso Elementary School | CITY OF BAYBAY | 5th | 1 | 4 | PROPOSED CONSTRUCTION OF TWO (2) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 19881874.33 | 19632499.38 | Completed | 1 | 2025-03-01 | 2025-03-19 | 2023-12-I003 | 2023-12-I003 | 45264 | 45271 | 45287 | 45435 | 45439 | JONI Construction | Completed w/ Time Extension & Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.1 | 5.25 | [8 empty] | 4th | 1
LMS 2024 | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 15202832.83 | 14042674.27 | Completed | 1 | 2025-02-07 | 2025-02-07 | 2023INFRA-LMS-08 | LMS 2023CONSTRUCTION-08 | 45253 | 45265 | 45279 | 45293 | 45450 | Infraserve Builders & Supplies | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region VIII | Biliran | 120876 | Libtong Gamay Elementary School | NAVAL (Capital) | Lone | 1 | 2 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 14180378.83 | 14031045.79 | Completed | 1 | 2024-11-06 | 2024-11-06 | 2023INFRA-LMS-07 | LMS 2023CONSTRUCTION-07 | 45253 | 45265 | 45279 | 45293 | 45446 | MKB Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1
LMS 2024 | Region VIII | Borongan City | 122392 | Bagong Barrio Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17066464.54 | 16865513.94 | Ongoing | 0.78 | 2025-01-12 | 00:00:00 | CY2024-LMS-BOR-01 | CY2024-LMS-BOR-01 | 45211 | 45222 | 45237 | 45257 | 45419 | YFL BUILDERS | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.36 | 0.42 | [9 empty] | 1st | 1
LMS 2024 | Region VIII | Borongan City | 122405 | Pinanag-an Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17066464.54 | 16865202.19 | COMPLETED | 1 | 2025-01-12 | 2025-01-10 | CY2024-LMS-BOR-02 | CY2024-LMS-BOR-02 | 45211 | 45222 | 45237 | 45257 | 45419 | YFL BUILDERS | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.39 | 0.61 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region VIII | Borongan City | 122363 | San Jose Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17066464.54 | 16885799.89 | COMPLETED | 1 | 2025-01-12 | 2024-11-19 | CY2024-LMS-BOR-03 | CY2024-LMS-BOR-03 | 45211 | 45222 | 45237 | 45257 | 45419 | LEXBUILD CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.78 | 0.22 | 5.25 | [8 empty] | 3rd | 1
LMS 2024 | Region VIII | Calbayog City | 124053 | Manuel Barral Sr. Elementary School | CALBAYOG CITY | 1st | 1 | 4 | CONSTRUCTION OF ONE(1) STOREY- FOUR(4) CLASSROOM SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 26212956.92 | 23229065.52 | Ongoing | 62%% | 2025-04-30 | 2025-06-29 | 2024-RVIII(Calbayog)-LMSP | 2024-021 | 45419 | 45427 | 45439 | 45461 | 45580 | JFR Construction Inc. | APPROVED TIME EXTENSION FOR 30 DAYS | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.62 | [10 empty] | 4th | 1
LMS 2024 | Region VIII | Eastern Samar | 122578 | Magsaysay Elementary School | JIPAPAD | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17333806.45 | 17135103.63 | Ongoing | 0.64 | 2025-01-19 | 00:00:00 | CY2024-LMS-ES-L1 | CY2024-LMS-ES-L1 | 45212 | 45223 | 45238 | 45414 | 45419 | TUBIGAN BUILDERS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.64 | 0 | [9 empty] | 5th | 1
LMS 2024 | Region VIII | Leyte | 121208 | Anislagan Elementary School | CALUBIAN | 3rd | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM | 17489186 | 17261863.56 | Ongoing | 0.4 | 00:00:00 |  | CY2024 BEFF_LAST MILE SCHOOLS PROGRAM_LOT No.1 | CY2024 BEFF_LAST MILE SCHOOLS PROGRAM_LOT No.1 | 45448 | 45456 | 45468 | 45492 | 45533 | QCC CONSTRUCTION & SUPPLY | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0.15 | [9 empty] | 4th | 1
LMS 2024 | Region VIII | Leyte | 133375 | Patong Elementary School | LEYTE | 3rd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM | 17325083.74 | 15179372.22 | Ongoing | 0.95 | 00:00:00 |  | CY 2024 LAST MILE SCHOOLS_Lot No.3 | CY 2024 LAST MILE SCHOOLS_Lot No.3 | 45239 | 45247 | 45264 | 45440 | 45454 | BENCH CONSTRUCTION AND SUPPLY | with approved realignment; change of target from 2 cl to 4 cl | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.1 |  |  |  |  | 1 | 2 | 17325083.74 |  |  | 3rd | 1
LMS 2024 | Region VIII | Leyte | 121660 | Cansoso Elementary School | MATAG-OB | 4th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITHOUT COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 12894514.92 | 10340542.52 | Completed | 1 | 2024-11-15 | 2024-12-11 | CY 2024 LAST MILE SCHOOLS_Lot No.1 | CY 2024 LAST MILE SCHOOLS_Lot No.1 | 45239 | 45247 | 45264 | 45345 | 45454 | CFV ARAR CONTRACTOR'S PHILS., INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 4th | 1
LMS 2024 | Region VIII | Leyte | 120922 | Burubud-an Elementary School | ABUYOG | 5th | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO(2) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4-SEATER), SCHOOL FURNITURE, AND SOLAR PV ENERGY SYSTEM | 12463277.09 | 9154186.73 | Completed | 1 | 2024-11-07 | 2024-12-10 | CY 2024 LAST MILE SCHOOLS_Lot No.2 | CY 2024 LAST MILE SCHOOLS_Lot No.2 | 45239 | 45247 | 45264 | 45327 | 45439 | MIGHTY A's CONSTRUCTION AND HARDWARE SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 3rd | 1
LMS 2024 | Region VIII | Maasin City | 122143 | Rizal MGS | CITY OF MAASIN (Capital) | 1st | 1 | 4 | CONSTRUCTION OF TWO (2) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 20363491.72 | 16705170.37 | Ongoing | 0.98 | 2025-02-10 |  | INFRA-2024-01 | INFRA-2024-01 | 45349 | 45363 | 45378 | 45439 | 45502 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.13 | [9 empty] | 1st | 1
LMS 2024 | Region VIII | Northern Samar | 122817 | SOMOROY ES | BOBON | 1st | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16684815.11 | 14031008.57 | Ongoing | 0.95 | 2025-03-30 | 00:00:00 | CY2024-RVIII-NS-L1 | CY2024-RVIII-NS-L1 | 45230 | 45237 | 45258 | 45523 | 45589 | PABLO S. LABASBAS CONSTRUCTION | Substantially Completed; With APPROVED TIME EXTENSION DUE TO WEATHER | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.95 | [9 empty] | 1st | 1
LMS 2024 | Region VIII | Northern Samar | 122890 | P. Rebadulla ES | CATUBIG | 2nd | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16959472.6 | 0 | not yet started | 0 | 00:00:00 | 00:00:00 | CY2024-RVIII-NS-L2 | CY2024-RVIII-NS-L2 | 45472 | 45481 | 45495 | 0 | 0 | 0 | already with RTA; awaiting downloading of subaro | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 4th | 1
LMS 2024 | Region VIII | Samar (Western Samar) | 123703 | Puhagan Elementary School | SAN JORGE | 1st | 1 | 4 | CONSTRUCTION OF 1STY4CL (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19679125.21 | 14042674.27 | Completed | 1 | 2025-02-22 | 2025-03-19 | CY2023-LMSP-LOT1 | 2024-004 | 45224 | 45238 | 45261 | 45420 | 45426 | JFR CONSTRUCTION INC. | COMPLETED BUT WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.95 | 0.05 | 5.25 | [8 empty] | 1st | 1
LMS 2024 | Region VIII | Samar (Western Samar) | 501929 | Minarog Integrated School | PARANAS (WRIGHT) | 2nd | 1 | 5 | CONSTRUCTION OF 1STY2CL & 1STY3CL (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 25049393.91 | 24746651.56 | Completed | 1 | 2024-11-17 | 2025-03-03 | CY2023-LMSP-LOT2 | 2024-005 | 45224 | 45238 | 45261 | 45420 | 45426 | J AND D CONSTRUCTION | WITH TIME EXTENSIONS AND LD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 3rd | 1
LMS 2024 | Region VIII | Southern Leyte | 121994 | Baugo Multi-grade Elementary School | Bontoc | 1st | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 13995289.43 | 9708987.74 | Completed | 1 | 2024-10-26 | 2025-01-15 | CY2024-LMS-L1 | CY2024-LMS-L1 | 45219 | 45226 | 45238 | 45309 | 45456 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region VIII | Southern Leyte | 122211 | Maningning Elementary School | MALITBOG | 1st | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 12789868.29 | 7657657.39 | Completed | 1 | 2024-11-23 | 2025-01-30 | CY2024-LMS-L2 | CY2024-LMS-L2 | 45219 | 45226 | 45238 | 45309 | 45456 | BELGES CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region VIII | Southern Leyte | 122281 | Sta. Maria Primary School | Sogod | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 14050064.96 | 9864549.29 | Completed | 1 | 2024-10-26 | 2025-01-15 | CY2024-LMS-L3 | CY2024-LMS-L3 | 45219 | 45226 | 45238 | 45309 | 45456 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 1st | 1
LMS 2024 | Region X | Bukidnon | 113847 | Basbasanan To Goynawa To Balakayo | SAN FERNANDO | 2nd | 1 | 3 | CONSTRUCTION OF BUILDING NO.1- 1 STOREY 3 CLASSROOM BUILDING with TOILET ATTACHED, wITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, WATER SYSTEM, PERIMETER GATE AND FENCE | 11198312.24 | 8493552.5 | Ongoing | 0.95 | Revised to June 10, 2025 | 00:00:00 | PB-02-11-2023-0026 | 012-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-20 | Vibranium Builders Corporation | Substantially Completed; with Approved Time extension no.'s 1&2, variation order no.'s 1&2 and due to unfavorable weather conditions. Request a extension awaits the delivery of furniture. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 | [9 empty] | 1st | 0
LMS 2024 | Region X | Bukidnon | 113847 | Basbasanan To Goynawa To Balakayo | SAN FERNANDO | 2nd |  | 2 | CONSTRUCTION BUILDING NO. 2- 1 STOREY 2 CLASSROOM BUILDING WITH TOILET ATTACHED WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND PERIMETER SOLAR LIGHTS | 14860395.24 | 8493552.5 | Ongoing | 0.95 | Revised to June 10, 2025 | 00:00:00 | PB-02-11-2023-0026 | 012-2024 | 2023-11-26 | 2023-12-04 | 2023-12-18 | 2023-12-27 | 2024-05-20 | Vibranium Builders Corporation | substantially completed; with Approved Time extension no.'s 1&2, variation order no.'s 1&2 and due to unfavorable weather conditions. Request a extension awaits the delivery of furniture. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0.1 | [9 empty] | 1st | 1
LMS 2024 | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2nd | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16488351.52 | 12568813.6 | Completed | 1 | 2024-10-15 | 2024-11-12 | 2024-01-0003 | 2024-02-0002 | 2024-01-04 | 2024-01-23 | 2024-02-07 | 2024-05-08 | 2024-05-21 | JDE Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region X | Gingoog City | 111092 | Sagu-Ilaw Ta Kabuka Elementary School | GINGOOG CITY | 1st | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 22120108.86 | 21858003.57 | Ongoing | 0.5 | 2025-05-25 | 00:00:00 | LMS 2023 - RX - GINGOOG CITY - 004 | BMB-F-24-0000862 | 2023-11-03 | 2023-11-10 | 2023-11-21 | 2024-05-21 | 2024-06-03 | Blaff Construction and Supplies | On-going Construction (under time suspension - due to actual site condition) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region X | Iligan City | 128131 | Panoroganan ES | ILIGAN CITY | Lone | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 15851835.73 | 12555775.14 | Completed | 1 | 2025-01-10 | 2025-02-12 | INFRA-2023-11-03 | INFRA-2023-11-03 | 2023-11-28 | 2023-12-06 | 2023-12-20 | 2024-01-26 | 2024-05-31 | Brima Construction and Enterprise | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region X | Malaybalay City | 501853 | Mapayag Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 |  | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 18241095.24 | 14778549.81 | Ongoing | 0.9 | 2025-04-07 | 00:00:00 | 003-INFRA-2023 | 003-INFRA-2023 | 2023-11-29 | 2023-12-07 | 2023-12-19 | 2023-12-19 | 2024-09-09 | Vimbranium Builder's Corporation | Approved Time Extension equivalent to 30 CDs. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.05 | [9 empty] | 1st | 1
LMS 2024 | Region X | Misamis Occidental | 127568 | Gala ES | TUDELA | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 16544911.02 | 16369981.76 | Ongoing | 0.95 | 2024-03-19 | 00:00:00 | LMS 2024 - RX - MISAMIS OCCIDENTAL - 002 | 011-2024 | 2024-01-16 | 2024-01-24 | 2024-02-05 | 2024-03-24 | 2024-07-22 | RJLG CONSTRUCTION AND SUPPLIES | For final inspection on June 11, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.85 | 0.1 | [9 empty] | 2nd | 1
LMS 2024 | Region X | Misamis Oriental | 201506 | Kalitian ES | KINOGUITAN | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 17917491.26 | 14458743.76 | Completed | 1 | 2024-11-17 | 2024-12-18 | PB-BAC1-Construction 2024-001 | 4919317 | 2024-01-17 | 2024-01-24 | 2024-02-05 | 2024-02-21 | 2024-06-13 | CLC Construction Services & Supply | Completed (Including Variation Order) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region X | Misamis Oriental | 201503 | Lonsi ES | ALUBIJID | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND WATER SYSTEM | 16902227.11 | 13216388.97 | Completed | 1 | 2024-11-17 | 2025-03-20 | PB-BAC1-Construction 2024-002 | 4919350 | 2024-01-17 | 2024-01-24 | 2024-02-05 | 2024-02-21 | 2024-06-13 | Trench | Completed (Including Variation Order ) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 4.25 | [8 empty] | 2nd | 1
LMS 2024 | Region X | Oroquieta City | 238501 | Kanowanan Tribal ES | OROQUIETA CITY (Capital) | 1st | 1 | 2 | CONSTRUCTION OF 1STY2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM AND FLOOD MARKER | 15701425.95 | 13445916.11 | Completed | 1 | 2024-10-10 | 2024-12-09 |  |  | 2024-11-23 | 2024-11-30 | 2023-12-14 | 2024-05-03 | 2024-05-10 | RSMA BUILDERS & GEN. MDSE | Processing for Occupancy Permit. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 2nd | 1
LMS 2024 | Region X | Ozamis City | 128188 | Pershing Tan Queto Sr. ES | OZAMIS CITY | 2nd | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 18361158.83 | 18151162.88 | completed | 1 | 2024-11-29 | 2024-12-29 | 092-CIVIL 2023-003 (EPA) | 092-CIVIL 2023-003 (EPA) | 2023-11-22 | 2023-11-29 | 2023-12-15 | 2024-01-02 | 2024-06-27 | Mitz and Nick Builders | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 3rd | 1
LMS 2024 | Region X | Tangub City | 128223 | Capalaran West ES | TANGUB CITY | 2nd | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 19993368.26 | 19397245.16 | Completed | 1 | 2024-12-26 | 2025-02-03 | LMS 2023-Region X-Tangub 001 |  | 2024-11-23 | 2024-11-30 | 2023-12-12 | 2023-12-20 | 2024-07-04 | RIC Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | [8 empty] | 5th | 1
LMS 2024 | Region X | Valencia City | 137043 | MAKAILAW ELEMENTARY SCHOOL | VALENCIA CITY | 4th | 1 | 4 | CONSTRUCTION OF 2 UNITS 1ST-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 18656357.05 | 14580621.09 | terminated | 0.24 | 2025-10-10 | 00:00:00 | 45352 | 009 s. 2024 | 2024-06-03 | 2024-02-02 | 2024-02-16 | 2024-03-11 | 2024-05-27 | ALRAF CONSTRUCTION | Contract Terminated/rescinded | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.24 | 0 | [9 empty] | 1st | 0
LMS 2024 | Region XI | Davao City | 137004 | Merol-O Elementary School | DAVAO CITY | 2nd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16861057.51 | 15858167.64 | Completed | 1 | Oct.25, 2024/Revised completion date: Dec. 24, 2024 |  | LMS-L001-2024 | #4 s. 2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Kiokong Construction | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 5th | 1
LMS 2024 | Region XI | Davao City | 306041 | Manaong National High School | DAVAO CITY | 3rd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16691097.64 | 15678874.9 | COMPLETED | 1 | Oct.25, 2024/Revised completion date: Dec. 24, 2024 |  | LMS-L001-2024 | #4 s. 2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Kiokong Construction | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 5th | 1
LMS 2024 | Region XI | Davao De Oro | 136925 | Puting Bato Elementary School | COMPOSTELA | 1st | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12681661.47 |  | Under Procurement | 0 | [10 empty] | as of April: postponed, submitted authority letter to CO allowing them to implement to other recipient NO RTA submitted to CO; as per DO this is for defferment; MGB Result; high susceptible to landslide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XI | Davao De Oro | 128336 | Mambatang ES | MABINI (DOÑA ALICIA) | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12458630.73 |  | Under Procurement | 0 | [10 empty] | as of April: postponed, submitted authority letter to CO allowing them to implement to other recipient NO RTA submitted to CO; as per DO this is for defferment; MGB Result; high susceptible to landslide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XI | Davao del Norte | 301773 | DUGAYAN NHS | KAPALONG | 1st | 1 | 6 | CONSTRUCTION OF 2 STOREY 6 CLASRROOM SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 31313131.31 | 25611457.03 | Ongoing | 0.6 |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Mark Anthony Construction & Supply | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.6 | 0 | [9 empty] | 5th | 1
LMS 2024 | Region XI | Davao del Sur | 128912 | Nodilla Elementary School | KIBLAWAN | 1st | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 21356418.04 |  | Ongoing | 0.27 | 2025-06-12 |  |  |  |  | May 28, 2024 | June 07, 2024 | August 09, 2024 |  | PHSMB CONSTRUCTION AND SUPPLY | for issuance NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.27 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XI | Davao Occidental | 205025 | Kangko ES | MALITA | Lone | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 17231437.46 | 17048325.13 | Completed | 1 | February 24, 2024 |  | ITB W-03-2024 | contract no. 2024-010 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | resolution no. 09,s. 2024 | August 08, 2024 | Digos Constrak Corporation | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1
LMS 2024 | Region XI | Davao Oriental | 501516 | Mc Arthur S. Madani Integrated School | CATEEL | 1st | 1 | 2 | CONSTRUCTION OF 1 UNIT 1STRY-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER - MC ARTHUR S. MADANI IS | 8496765.67 | 7108626.1 | COMPLETED | 1 | October 3, 2024 | November 29, 2024 |  | 2024-012 | December 8, 2023 | December 15, 2023 | December 27, 2023 | January 26, 2024 | June 4, 2024 | ELLE | w/ Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region XI | Davao Oriental | 129310 | Logdeck Elementary School | LUPON | 2nd | 1 | 2 | CONSTRUCTION OF 1 UNIT 1STRY-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER - LOGDECK ELEMENTARY SCHOOL | 8257545.94 | 6290078.09 | COMPLETED | 1 | September 26, 2024 | November 20, 2024 |  | 2024-011 | December 8, 2023 | December 15, 2023 | December 27, 2023 | January 26, 2024 | May 29, 2024 | Matt Glass | w/ Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1
LMS 2024 | Region XI | Panabo City | 129813 | Mabunao ES | CITY OF PANABO | 2nd | 1 | 2 | CONSTRUCTION OF 1STY2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 9748536.16 | 7000000 | Ongoing | 0.51 |  |  |  |  | JUNE 28, 2024 | JULY 3, 2024 | JULY 18, 2024 | AUGUST 8, 2024 |  | RUPLINO SEISMUNDO CONSTRUCTION CORPORATION | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.51 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XII | General Santos City | 281537 | Tanda Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 4 | CONSTRUCTION OF TWO(2) STOREY - FOUR(4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 22222222.22 | 0 | Under Procurement | 0 |  |  | 0 | 0 | [5 empty] | 0 | change of program; for reversion/ waive due to armed conflict | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1
LMS 2024 | Region XII | South Cotabato | 137086 | Tubak Elementary School | LAKE SEBU | 2nd | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS AND ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 22222222.22 | 21979700.2 | Ongoing | 0 | 2026-04-02 |  | DSC-24-08-131 | 2025-009 | 2024-08-06 | 2024-08-14 | 2024-08-27 | 2024-09-30 | 2025-03-07 | COFFEJOK CONSTRUCTION & SUPPLY CORPORATION | suspended; WITH TIME SUSPENSION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [9 empty] | 3rd | 1
LMS 2024 | Region XII | South Cotabato | 136941 | Kule Elementary School | T'BOLI | 2nd | 1 | 5 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS AND ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 22222222.22 | 21978971.76 | Ongoing | 0.0311 | 2026-02-01 |  | DSC-24-08-131 | 2025-008 | 2024-08-06 | 2024-08-14 | 2024-08-27 | 2024-09-30 | 2025-03-07 | COFFEJOK CONSTRUCTION & SUPPLY CORPORATION | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.0311 | [9 empty] | 3rd | 1
LMS 2024 | Region XII | Sultan Kudarat | 137132 | DATU SALAYAN ELEMENTARY SCHOOL | BAGUMBAYAN | 2nd | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 18079433.89 | 17635084.59 | Ongoing | 0.87 | 2025-06-24 | 00:00:00 | 24-01-005 | 24-01-005 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-07 | 2024-10-07 | Cofejok Construction and Supply Corporation | Time Extended due to road inaccessibility | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.84 | 0.03 | [9 empty] | 1st | 1