## REPAIR 2020-2024
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED
REPAIR 2020 | BARMM | Cotabato City | 131248 | L.R. Sebastian ES | COTABATO CITY | 1 | 1 | 6 | Repair of classrooms | 2001691 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2020 | BARMM | Cotabato City | 131243 | P.C. Hill ES | COTABATO CITY | 1 | 1 | 14 | Repair of classrooms | 4560581 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2020 | BARMM | Cotabato City | 131254 | Tamontaka Central School | COTABATO CITY | 1 | 1 | 8 | Repair of classrooms | 3169591 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2020 | CAR | Abra | 218506 | Lubong PS | Bangued | 0 | 1 | 3 | Repair of Classrooms | 2127169 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135180 | Danac ES | BOLINEY | 0 | 1 | 2 | Repair of Classrooms | 2010666 | 1 |  | COMPLETED | 100% | [10 empty] | Suspended | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135004 | Quimloong ES | Bucay | 0 | 1 | 5 | Repair of Classrooms | 3067940 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135026 | Abaquid ES | DANGLAS | 0 | 1 | 7 | Repair of Classrooms | 4351892 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135092 | Barit ES | DOLORES | 0 | 1 | 4 | Repair of Classrooms | 3228573 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135017 | Dolores CS | Dolores | 0 | 1 | 15 | Repair of Classrooms | 8219742 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | 0 | 1 | 10 | Repair of Classrooms | 6867519 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135094 | Botot ES | LUBA | 0 | 1 | 5 | Repair of Classrooms | 4900628 | 1 |  | COMPLETED | 100% | [10 empty] | Suspended | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 305088 | Lul-luno NHS | LUBA | 0 | 1 | 8 | Repair of Classrooms | 5926820 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | 0 | 1 | 9 | Repair of Classrooms | 5181879 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135194 | Sal-lapadan CS | Sallapadan | 0 | 1 | 12 | Repair of Classrooms | 5332406 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 218513 | Presentar PS | SAN QUINTIN | 0 | 1 | 2 | Repair of Classrooms | 1057033 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135147 | Tangadan ES | SAN QUINTIN | 0 | 1 | 15 | Repair of Classrooms | 9613341 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135025 | Velasco ES | Tayum | 0 | 1 | 8 | Repair of Classrooms | 5121658 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 | 8 | Repair of Classrooms | 5894653 | 1 |  | COMPLETED | 100% | [10 empty] | Suspended | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | 0 | 1 | 11 | Repair of Classrooms | 4779563 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135229 | Ayayao PS | CALANASAN (BAYAG) | 0 | 1 | 1 | Repair of Classroom | 539850 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135257 | Caglayan ES | CONNER | 0 | 1 | 10 | Repair of Classroom | 4048005 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135295 | MALUBIBIT NORTE ES | FLORA | 0 | 1 | 5 | Repair of Classrooms | 2309657 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135313 | Lenneng Elementary School | KABUGAO (Capital) | 0 | 1 | 5 | Repair of Classrooms | 2139722 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135300 | Mallag PS | KABUGAO (Capital) | 0 | 1 | 1 | Repair of Classroom | 495224 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135364 | IMELDA ES | STA. MARCELA | 0 | 1 | 4 | Repair of Classrooms | 1693306 | 1 |  | COMPLETED | 100% | [10 empty] | Mobilization | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136403 | Apolinario Mabini ES | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 4613665 | 1 | 10427010.49 | COMPLETED | 100% | 2020-10-14 |  | 007,s.2020 | 007,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | RHOB Construction and Eng'g Services | suspended | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7764059 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305269 | Baguio City High School - Main | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 2136319 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136393 | Bonifacio Elementary school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7827739 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136407 | Crystal Cave Elementary School | BAGUIO CITY | 0 | 1 | 8 | Repair of Classrooms | 3658159 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136410 | Happy Hollow Elementary School | BAGUIO CITY | 0 | 1 | 9 | Repair of Classrooms | 3366825 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | 8 | Repair of Classrooms | 3263073 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136413 | Loakan Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 1814359 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136394 | Lucban Elementary school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7118721 | 1 | 7786214.99 | COMPLETED | 100% | 2020-07-16 |  | 005,s.2020 | 005,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | RC Pulmano Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305283 | Magsaysay National High School | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1627041 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 10353735 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 6073211 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 1504706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136417 | SPED Center (FL) | BAGUIO CITY | 0 | 1 | 24 | Repair of Classrooms | 7112285 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1858089 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135372 | Adoyunan ES | ATOK | 0 | 1 | 8 | Repair of Classrooms | 3599230 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135373 | Beckes Pol-oc PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1375047 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135374 | Bilis Elementary School | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1241177 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135381 | Caliking ES | ATOK | 0 | 1 | 5 | Repair of Classroom | 2350065 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135383 | Celo Haight Elementary School | ATOK | 0 | 1 | 2 | Repair of Classrooms | 6430478 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135385 | Dalmacio Miguel PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 924293 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135387 | Englandad PS | ATOK | 0 | 1 | 3 | Repair of Classrooms | 2026193 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135391 | Ja'pa PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1256456 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135392 | Mauro P. Laruan ES | ATOK | 0 | 1 | 4 | Repair of Classrooms | 4048738 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135394 | Oyusan PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1402704 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135397 | Topdac ES | ATOK | 0 | 1 | 6 | Repair of Classrooms | 3411204 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 219528 | Batanes Primary School | BAKUN | 0 | 1 | 2 | Repair of Classrooms | 802607 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 219519 | Bakian Guiniawan PS | BOKOD | 0 | 1 | 1 | Repair of Classroom | 1489705 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135440 | Ekip ES | BOKOD | 0 | 1 | 3 | Repair of Classrooms | 1869872 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135467 | Bangsalan-Daganos PS | BUGUIAS | 0 | 1 | 2 | Repair of Classrooms | 1437022 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135479 | Cotcot-Talabis ES | BUGUIAS | 0 | 1 | 2 | Repair of Classrooms | 1381392 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135493 | Pugo James Mocate ES | BUGUIAS | 0 | 1 | 1 | Repair of Classroom | 568823 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135548 | Bashoy ES | KABAYAN | 0 | 1 | 6 | Repair of Classrooms | 2785352 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135557 | Tawangan ES | KABAYAN | 0 | 1 | 4 | Repair of Classrooms | 2618230 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135563 | Beleng-Belis Barrio School | KAPANGAN | 0 | 1 | 2 | Repair of Classrooms | 763854 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135570 | Gadang ES | KAPANGAN | 0 | 1 | 4 | Repair of Classrooms | 2216852 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135594 | Camilo Lucaben ES | KIBUNGAN | 0 | 1 | 9 | Repair of Classrooms | 4073883 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135607 | Polis Barrio School | KIBUNGAN | 0 | 1 | 2 | Repair of Classrooms | 1417025 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135608 | Saddle ES | KIBUNGAN | 0 | 1 | 3 | Repair of Classrooms | 1193559 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135618 | Balukas Elementary School | LA TRINIDAD (Capital) | 0 | 1 | 4 | Repair of Classrooms | 2303221 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135641 | Baguyos PS | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1344446 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135668 | Suyoc ES | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1089718 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135670 | Taneg PS | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1161572 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135673 | Bayabas MG School | SABLAN | 0 | 1 | 3 | Repair of Classrooms | 1931257 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135680 | Pappa MG School | SABLAN | 0 | 1 | 4 | Repair of Classrooms | 1705973 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135683 | Taya MG School | SABLAN | 0 | 1 | 2 | Repair of Classrooms | 2031157 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135698 | Lubas ES | TUBA | 0 | 1 | 5 | Repair of Classrooms | 3671290 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | 0 | 1 | 4 | Repair of Classrooms | 2276761 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135757 | Manaot ES | AGUINALDO | 0 | 1 | 2 | Repair of Classrooms | 1312773 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135773 | Laya ES | ALFONSO LISTA (POTIA) | 0 | 1 | 5 | Repair of Classrooms | 1594777 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135779 | Pinto ES | ALFONSO LISTA (POTIA) | 0 | 1 | 12 | Repair of Classrooms | 4739601 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 10 | Repair of Classrooms | 3459596 | 1 |  | COMPLETED | 100% | [10 empty] | - Contractor's Fault - (The Division Office Isued a demand letter for the Contarctor to finish all the remaining works before the opening of classes) | [12 empty] | 100% |  | 44621 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135793 | Haliap ES | ASIPULO | 0 | 1 | 8 | Repair of Classroom | 4780869 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135832 | Anao ES | HINGYON | 0 | 1 | 2 | Repair of Classrooms | 767767 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135843 | Piwong ES | HINGYON | 0 | 1 | 9 | Repair of Classrooms | 4452945 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135849 | Baang ES | HUNGDUAN | 0 | 1 | 3 | Repair of Classrooms | 1454283 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135858 | Nungulunan ES | HUNGDUAN | 0 | 1 | 5 | Repair of Classrooms | 2225337 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135869 | Hucab ES | KIANGAN | 0 | 1 | 9 | Repair of Classrooms | 4287534 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 | 1 | 10 | Repair of Classrooms | 4958595 | 1 |  | COMPLETED | 100% | [10 empty] | Contractor's Fault- Lack of manpower and Difficult accessibility to the project site during raing season | [12 empty] | 100% |  | 44621 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | 11 | Repair of Classrooms | 6018988 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | 6 | Repair of Classrooms | 4546582 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 319116 | Balbalan National High school | Balbalan | 0 | 1 | 4 | Repair of Classrooms | 1460102 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136026 | Magsilay Elementary School | Pasil | 0 | 1 | 3 | Repair of Classrooms | 1508008 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136031 | Aciga Elementary School | Pinukpuk | 0 | 1 | 8 | Repair of Classrooms | 3405448 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136034 | Asibanglan Elementary School | Pinukpuk | 0 | 1 | 2 | Repair of Classrooms | 443303 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136050 | Malagnat Elementary School | PINUKPUK | 0 | 1 | 10 | Repair of Classrooms | 5088889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 319103 | Tappo Vocational High School | Pinukpuk | 0 | 1 | 6 | Repair of Classrooms | 2662854 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136199 | Bagnen Elementary School | BAUKO | 0 | 1 | 9 | Repair of Classrooms | 5142350 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | 0 | 1 | 11 | Repair of Classrooms | 3919247 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136201 | Bansa Elementary School | BAUKO | 0 | 1 | 7 | Repair of Classrooms | 2716325 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136204 | Bila Elementary School | BAUKO | 0 | 1 | 8 | Repair of Classrooms | 4090415 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305245 | Tapapan National High School | BAUKO | 0 | 1 | 8 | Repair of Classrooms | 3476351 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305243 | Guinaang National High School | BONTOC (Capital) | 0 | 1 | 9 | Repair of Classrooms | 4351525 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 | 1 | 18 | Repair of Classrooms | 6638500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136313 | San Rafael Elementary School | PARACELIS | 0 | 1 | 3 | Repair of Classrooms | 1139865 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136357 | Banaao Elementary School | TADIAN | 0 | 1 | 9 | Repair of Classrooms | 4378194 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305240 | Cagubatan National High School | TADIAN | 0 | 1 | 11 | Repair of Classrooms | 3805972 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | 0 | 1 | 9 | Repair of Classrooms | 4118352 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136155 | Bado Dangwa ES | CITY OF TABUK (Capital) | 0 | 1 | 10 | Repair of Classrooms | 5146257 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3773138 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136158 | Balawag ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 2766453 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305198 | Balawag NHS | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 3940554 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136161 | Binongsay ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 3635102 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136162 | Bullagian ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1560899 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136091 | Bulo East ES | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 5260915 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136163 | Cabaritan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3094090 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3077094 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136164 | Calanan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3111037 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136099 | Camp Conrado M. Balweg Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1347970 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136004 | Casigayan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1120533 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220523 | Cataw Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2119557 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220522 | Dananao Primary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 749121 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136167 | Gaogao Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classroom | 2793115 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220502 | Gawidan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 712290 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136098 | Hilltop ES | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 9792355 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136100 | Lacnog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1068464 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136175 | Masablang Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 2248302 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136179 | Pinagan ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2240601 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136111 | Sotto ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1289762 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136180 | SUYANG ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1332063 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136181 | Toppan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3632233 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 4890035 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131470 | LINGAYAO ES | LAS NIEVES | 1 | 1 | 9 | Repair of Classrooms | 2903241 | 1 | 2903240.3576 | COMPLETED | 100% | [9 empty] | J-R3 CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131550 | F.S. OMAYANA ES | BUENAVISTA | 2 | 1 | 6 | Repair of Classrooms | 2730700 | 1 | 2730699.31 | COMPLETED | 100% | [9 empty] | BN BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131432 | CUYAGO ES | JABONGA | 2 | 1 | 11 | Repair of Classroom | 4005211 | 1 | 4005210.65 | COMPLETED | 100% | [9 empty] | J-R3 CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131491 | Amontay ES | NASIPIT | 2 | 1 | 7 | Repair of Classroom | 2572830 | 1 | 2572829.178 | COMPLETED | 100% | [9 empty] | BN BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131501 | Punta ES | NASIPIT | 2 | 1 | 14 | Repair of Classrooms | 5392357 | 1 | 5392356.429 | COMPLETED | 100% | [9 empty] | ETP BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Norte | 131504 | Talisay ES SPED Center | NASIPIT | 2 | 1 | 19 | Repair of Classrooms | 6812834 | 1 | 6812833.07 | COMPLETED | 100% | [9 empty] | RAMJEQUO CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131670 | Bunaguit ES | ESPERANZA | 1 | 1 | 7 | Repair of Classrooms | 4288273 | 1 | 907374.9027 | COMPLETED | 100% |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131685 | Jose Calo Agudo ES | ESPERANZA | 1 | 1 | 11 | Repair of Classrooms | 5471524 | 1 | 831400.6127 | COMPLETED | 100% |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131680 | Langag ES | ESPERANZA | 1 | 1 | 5 | Repair of Classrooms | 2981536 | 1 | 1295038.5106 | COMPLETED | 100% |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131687 | Salug ES | ESPERANZA | 1 | 1 | 7 | Repair of Classrooms | 4100539 | 1 | 462674.3557 | COMPLETED | 100% |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131690 | San Vicente PS | ESPERANZA | 1 | 1 | 4 | Repair of Classrooms | 2424897 | 1 | 1001764.8066 | COMPLETED | 100% |  |  | 2020-03-01 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131695 | Tagbalili ES | ESPERANZA | 1 | 1 | 2 | Repair of Classroom | 1182367 | 1 | 1182366.719 | COMPLETED | 100% |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131730 | Loreto CES | LORETO | 1 | 1 | 17 | Repair of Classrooms | 7663991 | 1 | 1178086.9053 | COMPLETED | 100% |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 304720 | Los Arcos NHS | PROSPERIDAD | 1 | 1 | 9 | Repair of Classrooms | 4495402 | 1 | 1456263.3134 | COMPLETED | 100% |  |  | 2020-03-02 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131775 | East Prosperidad Central Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 19 | Repair of Classrooms | 9432657 | 1 | 3852452.9854 | COMPLETED | 100% |  |  | 2020-03-03 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131776 | La Caridad ES | PROSPERIDAD (Capital) | 1 | 1 | 5 | Repair of Classrooms | 4060509 | 1 | 3716862.9869 | COMPLETED | 100% |  |  | 2020-03-04 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131796 | La Purisima Elementary Schhol | PROSPERIDAD (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1970778 | 1 | 5744341.7 | COMPLETED | 100% |  |  | 2020-03-08 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131803 | New Maug Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 10 | Repair of Classrooms | 5847856 | 1 | 5847855.9534 | COMPLETED | 100% |  |  | 2020-03-09 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131781 | New Visayas ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1817798 | 1 | 4495401.9091 | COMPLETED | 100% |  |  | 2020-03-05 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131782 | Pakwan ES | PROSPERIDAD (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3673954 | 1 | 5471523.1407 | COMPLETED | 100% |  |  | 2020-03-06 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131786 | SAN RAFAEL ES | PROSPERIDAD (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3852453 | 1 | 5635792.4023 | COMPLETED | 100% |  |  | 2020-03-07 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131936 | Anislagan ES | SAN LUIS | 1 | 1 | 11 | Repair of Classrooms | 5744342 | 1 | 6181298.8776 | COMPLETED | 100% |  |  | 2020-03-10 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LGC Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131940 | Cecilia Elementary School | SAN LUIS | 1 | 1 | 7 | Repair of Classrooms | 3946733 | 1 | 7663990.16 | COMPLETED | 100% |  |  | 2020-03-11 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131945 | Dimasalang ES | SAN LUIS | 1 | 1 | 6 | Repair of Classrooms | 3716863 | 1 | 8167662.9 | COMPLETED | 100% |  |  | 2020-03-12 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ROCK Diwata Builders Inc. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131947 | Dona Maxima ES | SAN LUIS | 1 | 1 | 11 | Repair of Classrooms | 6181299 | 1 | 4560096.22 | COMPLETED | 100% |  |  | 2020-03-13 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ALCT Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131966 | Sta. Ines ES | SAN LUIS | 1 | 1 | 10 | Repair of Classrooms | 5635793 | 1 | 4453513.48 | COMPLETED | 100% |  |  | 2020-03-14 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JM Lacorte Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131864 | Banag-banag ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3552946 | 1 | 4318652.22 | COMPLETED | 100% |  |  | 2020-03-15 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131865 | Causwagan ES | SIBAGAT | 1 | 1 | 4 | Repair of Classrooms | 2055354 | 1 | 4288272.53 | COMPLETED | 100% |  |  | 2020-03-16 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | JB Ciano Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131868 | El Rio ES | SIBAGAT | 1 | 1 | 9 | Repair of Classrooms | 4453514 | 1 | 4100538.81 | COMPLETED | 100% |  |  | 2020-03-17 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131872 | Kolambugan ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3208468 | 1 | 4060508.52 | COMPLETED | 100% |  |  | 2020-03-18 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131876 | Mahayahay ES | SIBAGAT | 1 | 1 | 3 | Repair of Classrooms | 1725552 | 1 | 3946732.94 | COMPLETED | 100% |  |  | 2020-03-19 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131879 | Padiay ES | SIBAGAT | 1 | 1 | 6 | Repair of Classrooms | 3487766 | 1 | 3673953.75 | COMPLETED | 100% |  |  | 2020-03-20 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131884 | San Roque ES | SIBAGAT | 1 | 1 | 2 | Repair of Classroom | 1178087 | 1 | 3552945.88 | COMPLETED | 100% |  |  | 2020-03-21 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | MJS Const. & Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131885 | San Vicente ES | SIBAGAT | 1 | 1 | 4 | Repair of Classrooms | 2060098 | 1 | 3487765.53 | COMPLETED | 100% |  |  | 2020-03-22 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131886 | Senai ES | SIBAGAT | 1 | 1 | 3 | Repair of Classrooms | 1456264 | 1 | 3208467.21 | COMPLETED | 100% |  |  | 2020-03-23 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 304740 | SIBAGAT NATIONAL HIGH SCHOOL OF HOME INDUSTRIES | SIBAGAT | 1 | 1 | 16 | Repair of Classrooms | 8167663 | 1 | 2270701.7098 | COMPLETED | 100% |  |  | 2020-03-24 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131890 | Tabontabon ES | SIBAGAT | 1 | 1 | 8 | Repair of Classrooms | 4560097 | 1 | 1750631.0447 | COMPLETED | 100% |  |  | 2020-03-24 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | DAVE Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131971 | Causwagan ES | TALACOGON | 1 | 1 | 9 | Repair of Classrooms | 4318653 | 1 | 1817797.7461 | COMPLETED | 100% |  |  | 2020-03-25 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131976 | Culi-Ram ES | TALACOGON | 1 | 1 | 4 | Repair of Classroom | 2035852 | 1 | 1970777.2701 | COMPLETED | 100% |  |  | 2020-03-25 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABZKO Construction Corp. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131648 | Antioquia ES | BUNAWAN | 2 | 1 | 2 | Repair of Classrooms | 907375 | 1 | 4318652.22 | COMPLETED | 100% |  |  | 2020-03-26 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131657 | Libertad ES | BUNAWAN | 2 | 1 | 19 | Repair of Classrooms | 8861401 | 1 | 1725551.4142 | COMPLETED | 100% |  |  | 2020-03-26 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | INNOVATI Const. | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 212013 | Singanan ES | BUNAWAN | 2 | 1 | 3 | Repair of Classrooms | 1815620 | 1 | 2035851.1157 | COMPLETED | 100% |  |  | 2020-03-27 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131752 | Halapitan Elementary School | LA PAZ | 2 | 1 | 5 | Repair of Classrooms | 2540328 | 1 | 1815619.0454 | COMPLETED | 100% |  |  | 2020-03-27 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | ABM1 Builders and Supply | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 212006 | Ferdinand-Sabud ES | LORETO | 2 | 1 | 3 | Repair of Classrooms | 2270702 | 1 | 2060097.3697 | COMPLETED | 100% |  |  | 2020-03-29 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 212047 | SIKAT PANLABUAN PS | LORETO | 2 | 1 | 2 | Repair of Classrooms | 831401 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131744 | Sto Nino ES | LORETO | 2 | 1 | 3 | Repair of Classrooms | 1750632 | 1 | 2424896.3867 | COMPLETED | 100% |  |  | 2020-03-29 |  | MARCH 25, 2020 | MARCH 23, 2020 | APRIL 15, 2020 |  |  | LM Const. & Gen. Mrkt | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | 9 | Repair of Classrooms | 4617364 | 1 |  | COMPLETED | 100% | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131850 | BY Tumulak ES | SAN FRANCISCO | 2 | 1 | 1 | Repair of Classroom | 462675 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131853 | Lapinigan CES with SPED Program | SAN FRANCISCO | 2 | 1 | 22 | Repair of Classrooms | 9485939 | 1 |  | COMPLETED | 100% | [10 empty] | with RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131929 | San Pascual ES | SANTA JOSEFA | 2 | 1 | 14 | Repair of Classrooms | 6598983 | 1 |  | COMPLETED | 100% | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 132008 | Pulanglupa ES | TRENTO | 2 | 1 | 2 | Repair of Classrooms | 1001765 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 132010 | Salvacion ES | TRENTO | 2 | 1 | 10 | Repair of Classrooms | 5466058 | 1 |  | COMPLETED | 100% | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 317438 | San Roque NHS | TRENTO | 2 | 1 | 2 | Repair of Classroom | 1295039 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | 11 | Repair of Classrooms | 6902023 | 1 |  | COMPLETED | 100% | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Agusan del Sur | 131922 | Veruela Central Elementary School | VERUELA | 2 | 1 | 14 | Repair of Classrooms | 6211205 | 1 |  | COMPLETED | 100% | [10 empty] | FOR FURTHER INVESTIGATION OF DOCUMENTS SUBMITTED DURING BIDDING | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Caraga | Bayugan City | 131600 | Katipunan ES | Bayugan City | 1 | 1 | 7 | Repair of Classrooms | 3279775 | 1 |  | COMPLETED | 100% |  |  | 2020-001 | 2020-001 | [5 empty] | ALCT Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Caraga | Bayugan City | 131601 | Kiawan ES | Bayugan City | 1 | 1 | 3 | Repair of Classrooms | 1533187 | 1 |  | COMPLETED | 100% |  |  | 2020-002 | 2020-002 | [5 empty] | ALCT Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Caraga | Bayugan City | 131636 | New Leyte ES | Bayugan City | 1 | 1 | 5 | Repair of Classrooms | 2208541 | 1 |  | COMPLETED | 100% |  |  | 2020-004 | 2020-004 | [5 empty] | MAIR Construction General Merchandise | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Caraga | Bayugan City | 131611 | San Isidro ES | Bayugan City | 1 | 1 | 6 | Repair of Classrooms | 3082265 | 1 |  | COMPLETED | 100% |  |  | 2020-003 | 2020-003 | [5 empty] | ETP Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 803075 | 1 | 803074.81 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 132613 | Coleto ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1142992 | 1 | 1142991.99 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 132615 | F. C. Pedraverde-Lindo ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1138775 | 1 | 1138774.04 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER1 | REPAIR2020_CLUSTER1 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 132617 | Gerardo D. Verano Jr. E.S | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1212729 | 1 | 1212728.01 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 132836 | Mangagoy North ES | CITY OF BISLIG | 2 | 1 | 4 | Repair of Classrooms | 1612102 | 1 | 1612101.25 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Bislig City | 132626 | Pamaypayan ES | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 803085 | 1 | 803084.8 | COMPLETED | 100% | December 22, 2020 | January 04, 2021 | REPAIR2020_CLUSTER2 | REPAIR2020_CLUSTER2 | Nov. 29, 2019 | Dec. - 06, 2019 | Dec. 18, 2019 | Jan. 06, 2020 | Sept. 17,2020 | MN Bayalas Construction | Waiting for the Sub-ARO to release | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Butuan City | 132074 | F.R. Sibayan Central Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 4634588 | 1 |  | COMPLETED | 100% | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Butuan City | 500317 | La Soledad ES | BUTUAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 4477443 | 1 |  | COMPLETED | 100% | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Butuan City | 212501 | West Central ES | BUTUAN CITY (Capital) | 1 | 1 | 19 | Repair of Classrooms | 5446943 | 1 |  | COMPLETED | 100% | 2021-04-01 | [8 empty] | Two J.E. Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Cabadbaran City | 131573 | Bay-ang ES | CITY OF CABADBARAN | 2 | 1 | 8 | Repair of Classrooms | 2253162 | 1 | 2253161.11 | COMPLETED | 100% |  |  |  |  | DECEMBER 10, 2019 | DECEMBER 17,2019 | JANUARY 6, 2020 | FEBRUARY 3, 2020 |  | 3C'SL CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Cabadbaran City | 131576 | La Union ES | CITY OF CABADBARAN | 2 | 1 | 21 | Repair of Classrooms | 6710617 | 1 | 6710616.93 | COMPLETED | 100% |  |  |  |  | DECEMBER 10, 2019 | DECEMBER 17,2019 | JANUARY 6, 2020 | FEBRUARY 3, 2020 |  | JY BONTILAO CONSTRUCTION & ENTERPRISE | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Dinagat Island | 132502 | Paniog ES | BASILISA (RIZAL) | 0 | 1 | 6 | Repair of Classrooms | 2498907 | 1 | 2498906.76 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Dinagat Island | 132508 | Sombrado ES | BASILISA (RIZAL) | 0 | 1 | 2 | Repair of Classrooms | 1161567 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Dinagat Island | 132511 | Taliman ES | BASILISA (RIZAL) | 0 | 1 | 2 | Repair of Classrooms | 1214000 | 1 | 1214000 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Dinagat Island | 132512 | Villa Ecleo ES | BASILISA (RIZAL) | 0 | 1 | 4 | Repair of Classrooms | 1609125 | 1 | 1609124.16 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Dinagat Island | 132552 | Imelda ES | TUBAJON | 0 | 1 | 3 | Repair of Classrooms | 1765000 | 1 | 1765000 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132143 | San Miguel Elementary School | Dapa | 1 | 1 | 2 | Repair of Classroom | 970000 | 1 | 970000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-007 | BEFF-INFRA2020-007 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132133 | Sta. Felomina Elementary School | Dapa | 1 | 1 | 2 | Repair of Classroom | 997000 | 1 | 997000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-011 | BEFF-INFRA2020-011 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132164 | Bitoon Elementary School | Del Carmen | 1 | 1 | 5 | Repair of Classroom | 1995000 | 1 | 1995000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-010 | BEFF-INFRA2020-010 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132167 | Dumoyog Elementary School | DEL CARMEN | 1 | 1 | 3 | Repair of Classrooms | 2223000 | 1 | 2223000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-001 | BEFF-INFRA2020-001 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132178 | San Fernando Elementary Schoo | Del Carmen | 1 | 1 | 3 | Repair of Classroom | 1497000 | 1 | 1497000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-006 | BEFF-INFRA2020-006 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GEN. LUNA | 1 | 1 | 3 | Repair of Classrooms | 1694000 | 1 | 1694000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-002 | BEFF-INFRA2020-002 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | Gen. Luna | 1 | 1 | 3 | Repair of Classroom | 1596000 | 1 | 1596000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-008 | BEFF-INFRA2020-008 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | San Benito | 1 | 1 | 3 | Repair of Classroom | 1397000 | 1 | 1397000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-013 | BEFF-INFRA2020-013 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | San Isidro | 1 | 1 | 3 | Repair of Classroom | 1197000 | 1 | 1197000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-014 | BEFF-INFRA2020-014 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132205 | Abad Santos Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 4 | Repair of Classrooms | 1066000 | 1 | 1066000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-003 | BEFF-INFRA2020-003 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 6 | Repair of Classroom | 2495000 | 1 | 2495000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-005 | BEFF-INFRA2020-005 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 213001 | Atoyay Elementary School | SOCORRO | 1 | 1 | 5 | Repair of Classroom | 2990000 | 1 | 2990000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-009 | BEFF-INFRA2020-009 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132222 | Lanit ag Elementary School | SOCORRO | 1 | 1 | 1 | Repair of Classroom | 509000 | 1 | 509000 | COMPLETED | 100% |  |  | C1-BEFF-INFRA2020-004 | C1-BEFF-INFRA2020-004 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132233 | Lawigan Primary School | SOCORRO | 1 | 1 | 1 | Repair of Classroom | 509000 | 1 | 509000 | COMPLETED | 100% |  |  | C1-BEFF-INFRA2020-004 | C1-BEFF-INFRA2020-004 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Siargao | 132223 | N. Sering Comm. Elementary School | SOCORRO | 1 | 1 | 5 | Repair of Classroom | 1995000 | 1 | 1995000 | COMPLETED | 100% |  |  | BEFF-INFRA2020-012 | BEFF-INFRA2020-012 | JAN-7-2020 | JAN-20-2020 | FEB-3-2020 | FEB-10-2020 |  | RADIAN CONSTRUCTION AND SUPPLY | RTA Issued, Awaiting SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao City | 304792 | Juan P. Cedro Sr. Memorial High Schoo | SURIGAO CITY (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2071556 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao City | 132259 | San Jose Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 1776000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao City | 304807 | San Jose NHS | SURIGAO CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1347653 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Norte | 304811 | Alegria NHS | Alegria | 2 | 1 | 24 | Repair of Classrooms | 5798611 | 1 | 5798610.29 | COMPLETED | 100% |  |  | 001-BEFF 2020 | 002-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Kent Marketing Group of Companies, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Norte | 132329 | San Pedro ES | Alegria | 2 | 1 | 13 | Repair of Classrooms | 3270493 | 1 | 3270492.73 | COMPLETED | 100% |  |  | 002-BEFF 2020 | 001-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Kent Marketing Group of Companies, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Norte | 132452 | Bunyasan ES | Malimono | 2 | 1 | 7 | Repair of Classrooms | 2019600 | 1 | 2019600 | COMPLETED | 100% |  |  | 003-BEFF 2020 | 003-2020 | 2020-01-27 | 2020-02-04 | 2020-02-21 | 2020-03-16 |  | Windfall Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132657 | Buntalid Elementary School | Cantilan | 1 | 1 | 5 | Repair of Classrooms | 3000472 | 1 | 2142064.8 | COMPLETED | 100% | 2021-05-13 | 2021-05-07 |  | 2020-008 | [5 empty] | Baicamar Const. and Supplies Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132662 | Consuelo Elementary School | Cantilan | 1 | 1 | 7 | Repair of Classrooms | 4710678 | 1 | 3042188.77 | COMPLETED | 100% | 2021-05-10 | 2021-04-20 |  | 2020-009 | [5 empty] | FP Alonto Construction Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132702 | Segunda R. Cuajao Memorial Elementary School | Carrascal | 1 | 1 | 8 | Repair of Classrooms | 5040089 | 1 | 5004887.78 | COMPLETED | 100% | 2021-05-13 | 2021-05-12 |  | 2020-010 | [5 empty] | LPO1 Group of Companies | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132734 | Hinatuan North Central Elementary School | Hinatuan | 2 | 1 | 19 | Repair of Classrooms | 10342438 | 1 | 7676915.81 | COMPLETED | 100% | 2021-05-10 |  |  | 2020-011 | [5 empty] | J-R3 Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132807 | Pedro Redondo Elementary School- (Island School Site) | Lingig | 2 | 1 | 5 | Repair of Classrooms | 3415232 | 1 | 2877023.17 | COMPLETED | 100% | 2021-05-10 | 2021-08-12 |  | 2020-012 | [5 empty] | J-R3 Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Surigao del Sur | 132814 | Tagpupuran Elementary School | Lingig | 2 | 1 | 6 | Repair of Classrooms | 3470586 | 1 | 2569826.08 | COMPLETED | 100% | 2021-05-10 | 2021-08-12 |  | 2020-013 | [5 empty] | Jimberns Builders and Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Tandag City | 132961 | Buenavista Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 8 | Repair of Classrooms | 1638886 | 1 | 1638885.99 | COMPLETED | 100% | January 20, 2020 | [8 empty] | JTA Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Tandag City | 500587 | Carmen IS | CITY OF TANDAG (Capital) | 1 | 1 | 7 | Repair of Classrooms | 1573690 | 1 | 1573689.49 | COMPLETED | 100% | January 20, 2020 | [7 empty] | August 15, 2019 | FP Alonto Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1676881 | 1 | 1676880.8 | COMPLETED | 100% | January 20, 2020 | December 18, 2020 | [7 empty] | MRS Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Tandag City | 132974 | San Agustin Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 7 | Repair of Classrooms | 1909931 | 1 | 1909930.28 | COMPLETED | 100% | January 20, 2020 | [8 empty] | CV Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CARAGA | Tandag City | 132977 | San Jose Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 2 | Repair of Classrooms | 588795 | 1 | 588794.84 | COMPLETED | 100% | January 20, 2020 | December 18, 2020 | [7 empty] | MRS Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY | 1 | 1 | 25 | Repair of Classrooms | 10000000 | 1 | 9991962.22 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Bagong Barrio SHS | KALOOKAN CITY | 1 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 100% | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136639 | Bagong Silang ES | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 5300000 | 1 | 5295739.98 | COMPLETED | 100% | 2021-08-24 | 2021-08-03 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1 | 1 | 4 | Repair of Classrooms | 5000000 | 1 | 4995981.11 | COMPLETED | 100% | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136633 | Camarin D ES | KALOOKAN CITY | 1 | 1 | 26 | Repair of Classrooms | 11000000 | 1 | 10991158.44 | COMPLETED | 100% | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319701 | Cielito Zamora Junior High School | KALOOKAN CITY | 1 | 1 | 4 | Repair of classrooms | 4000000 | 1 | 3996784.89 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136636 | Congress ES | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4735000 | 1 | 4731194.11 | COMPLETED | 100% | 2021-08-24 | 2021-08-23 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Don Antonio Uy Remington SHS | KALOOKAN CITY | 1 | 1 | 2 | Repair of Classrooms | 2000000 | 1 | 1998392.44 | COMPLETED | 100% | 2021-08-24 | 2021-08-19 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4785000 | 1 | 4781153.92 | COMPLETED | 100% | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 9000000 | 1 | 8992766 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 5937257 | 1 | 5937256.44 | COMPLETED | 100% | 2020-12-07 | 11/16/2020 |  | PCA-2020-INFRA-001 | 1/23/2020 | 11/25/2019 | 2/24/2020 | 2020-06-03 | 2020-09-08 | EV & E CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136646 | NHC ES | KALOOKAN CITY | 1 | 1 | 10 | Repair of Classrooms | 5000000 | 1 | 4995981.11 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305378 | NHC HS | KALOOKAN CITY | 1 | 1 | 12 | Repair of Classrooms | 4310000 | 1 | 4306535.72 | COMPLETED | 100% | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136655 | Sampaguita Elementary School | KALOOKAN CITY | 1 | 1 | 15 | Repair of Classrooms | 5900000 | 1 | 5895257.71 | COMPLETED | 100% | 2021-08-24 | 2021-06-29 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City |  | Vicente Malapitan North SHS | KALOOKAN CITY | 1 | 1 | 6 | Repair of Classrooms | 7000000 | 1 | 6994373.56 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305388 | Caloocan HS | KALOOKAN CITY | 2 | 1 | 40 | Repair of Classrooms | 10000000 | 1 | 9991962.22 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | KALOOKAN CITY | 2 | 1 | 9 | Repair of Classrooms | 2500000 | 1 | 2497990.56 | COMPLETED | 100% | 2021-08-24 |  |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | KALOOKAN CITY | 2 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 100% | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Caloocan City | 305391 | M. B. Asistio, Sr. HS | KALOOKAN CITY | 2 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 2997588.67 | COMPLETED | 100% | 2021-08-24 | 2021-08-18 |  | PCA-2020-INFRA-002 | September 11, 2020 | September 21, 2020 | October 5, 2020 | October 13, 2020 | November 27, 2020 | J. Simeon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | 0 | 1 | 18 | Repair of Classrooms | 5927946 | 1 | 4700481.32 | COMPLETED | 100% | April 23, 2021 |  | REPAIR2020-NCR-SANJUAN-001 | 2020-PB-001 | November 21, 2019 | December 6, 2019 | December 19, 2019 | February 18, 2020 | December 7, 2020 | GOLDEN SHOVEL BUILDERS EARTHMOVING AND DEVELOPMENT CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 136782 | Almanza Elementary School | CITY OF LAS PIÑAS | 0 | 1 | 18 | Repair of Classrooms | 2617692 | 1 | 2617691.75 | COMPLETED | 100% | 2021-01-21 | 2020-12-18 | [6 empty] | 2020-09-23 | Image Builders and General Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 | 12 | Repair of Classrooms | 2918934 | 1 | 2918993.98 | COMPLETED | 100% | 2021-01-21 | 2021-04-20 | [6 empty] | 2020-09-23 | RM Mangubat Realty and Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 320301 | Las Pinas East NHS - Equitable Annex | CITY OF LAS PIÑAS | 0 | 1 | 32 | Repair of Classrooms | 3295088 | 1 | 3295087.25 | COMPLETED | 100% | 2021-01-21 | 2020-12-18 | [6 empty] | 2020-09-23 | Image Builders and General Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Las Piñas City | 136786 | Moonwalk ES - Mikesell Annex | CITY OF LAS PIÑAS | 0 | 1 | 13 | Repair of Classrooms | 1312503 | 1 | 1312503 | COMPLETED | 100% | 2021-01-21 | 2021-01-20 | [6 empty] | 2020-09-23 | REDCAR Trading and Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136699 | Bangkal ES Main | CITY OF MAKATI | 1 | 1 | 36 | Repair of Classrooms | 2500000 | 1 | 1910420.43 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-007 | 2020-007 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Dreamworxs Builders & Trading, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 305409 | Gen. Pio del Pilar NHS | CITY OF MAKATI | 1 | 1 | 17 | Repair of Classrooms | 3926450 | 1 | 2653829.77 | COMPLETED | 100% | March 10, 2021 | March 10, 2021 | 2020-009 | 2020-009 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 3, 2020 | Zaneya Builders & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136706 | Jose Magsaysay ES | CITY OF MAKATI | 1 | 1 | 30 | Repair of Toilets | 4139315.84 | 1 | 4128981.28 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-006 | 2020-006 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | St. Gabriel Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136708 | Nicanor C. Garcia, Sr. ES | CITY OF MAKATI | 1 | 1 | 11 | Repair of Classrooms | 1917013 | 1 | 1906020.37 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-006 | 2020-006 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | St. Gabriel Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136715 | Palanan ES | CITY OF MAKATI | 1 | 1 | 40 | Repair of Classrooms | 4000000 | 1 | 2639426.63 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-007 | 2020-007 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Dreamworxs Builders & Trading, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136694 | Fort Bonifacio ES | CITY OF MAKATI | 2 | 1 | 15 | Repair of Classrooms | 1730417 | 1 | 1481252.95 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 305411 | Fort Bonifacio HS | CITY OF MAKATI | 2 | 1 | 52 | Repair of Classrooms | 2152386.5 | 1 | 1600572.72 | COMPLETED | 100% | March 10, 2021 | March 10, 2021 | 2020-009 | 2020-009 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 3, 2020 | Zaneya Builders & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2 | 1 | 36 | Repair of Classrooms | 3097855 | 1 | 3072264.56 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-010 | 2020-010 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | MCORR Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 320001 | Pitogo HS | CITY OF MAKATI | 2 | 1 | 38 | Repair of Classrooms | 2940794.54 | 1 | 2691571.12 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136696 | Rizal ES | CITY OF MAKATI | 2 | 1 | 54 | Repair of Classrooms | 2932017 | 1 | 2906048.66 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-010 | 2020-010 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | MCORR Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136712 | South Cembo ES | CITY OF MAKATI | 2 | 1 | 49 | Repair of Toilets | 6187099.88 | 1 | 6154750.12 | COMPLETED | 100% | March 22, 2021 | March 22, 2021 | 2020-008 | 2020-008 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 15, 2020 | TM Abad Construction | reverted due to previous project cityhall | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Makati City | 136698 | West Rembo ES | CITY OF MAKATI | 2 | 1 | 12 | Repair of Classrooms | 1406103 | 1 | 1156979.1 | COMPLETED | 100% | March 11, 2021 | March 11, 2021 | 2020-011 | 2020-011 | October 22, 2020 | October 30, 2020 | November 11, 2020 | November 25, 2020 | December 4, 2020 | Sherf Builders Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Malabon City | 340567 | SHS within Imelda ES | CITY OF MALABON | 0 | 1 | 9 | Repair of Classrooms | 2182877 | 1 | 2182876.16 | COMPLETED | 100% |  |  |  | 2020-INFRA-09-0006 |  |  | 01/31/2020 (120 CDs) |  | 2020-10-12 | Tapnio & Tan Construction & Development Corp. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 6 | Repair of Classrooms | 1677247 | 1 | 1677246.48 | COMPLETED | 100% |  | 2020-12-21 |  | 2020-INFRA-09-0005 |  |  | 01/31/2020 (120 CDs) |  | 2020-10-14 | Martian Builders & Supplies | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 6421055 | 1 | 6421054.08 | COMPLETED | 100% | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136665 | DONA PILAR ELEMENTARY SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9402013 | 1 | 9402012.41 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500333 | EULOGIO RODRIGUEZ INTEGRATED SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9944054 | 1 | 9844613 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 500331 | ISAAC LOPEZ INTEGRATED SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 10150751 | 1 | 10049242.84 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 107975 | Mandaluyong Addition Hills ES | CITY OF MANDALUYONG | 0 | 1 | 36 | Repair of Classrooms | 8500786 | 1 | 8500785.42 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136660 | MANDALUYONG ELEMENTARY SCHOOL | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 9474902 | 1 | 9380152.43 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 305393 | Mandaluyong High School | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of classrooms | 9230097 | 1 | 9,137,795,.22 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136669 | Nueve de Febrero Elementary School | CITY OF MANDALUYONG | 0 | 1 | 24 | Repair of Classrooms | 5180804 | 1 | 5180803.97 | COMPLETED | 100% | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City | 136670 | Pedro P. Cruz (Mauway) ES | CITY OF MANDALUYONG | 0 | 1 | 30 | Repair of Classrooms | 5470279 | 1 | 5470278.61 | COMPLETED | 100% | November 16, 2020 | November 16, 2020 | 2020-Mandaluyong-01 | No.1 | January 27 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | B.Valencerina Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Mandaluyong City |  | Senate President Neptali A. Gonzales IS | CITY OF MANDALUYONG | 0 | 1 | 24 | Refurbishment of Classrooms | 35976579 | 1 | 35640463.12 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-05 | No.05 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136434 | Gen. Vicente Lim Elementary School | TONDO | 1 | 1 | 21 | Repair of Classrooms | 6023971 | 1 | 6023970.46 | COMPLETED | 100% | April 20, 2021 | April 8, 2021 | [6 empty] | December 7, 2021 | Open Builders Incorporated | Bid-out/Waiting for the SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136441 | R. Almario Elementary School | TONDO | 1 | 1 | 42 | Repair of Classrooms | 14700000 | 1 | 14592990.89 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 222001 | R. Almario Elementary School - Parola Annex | TONDO | 1 | 1 | 8 | Repair of Classrooms | 5000000 | 1 | 4964096.43 | COMPLETED | 100% | August 7, 2021 | 2021-08-06 | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136419 | Barrio Obrero Elementary School | TONDO | 2 | 1 | 85 | Repair of Classrooms | 20635044 | 1 | 20484829.86 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | Under procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 3 | 1 | 33 | Repair of Classrooms | 11550000 | 1 | 11465921.42 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136463 | Trinidad Tecson Elementary School | SAMPALOC | 4 | 1 | 44 | Repair of Classrooms | 10000000 | 1 | 9927204.69 | COMPLETED | 100% | August 7, 2021 | 2021-06-29 | [6 empty] | November 26, 2020 | CB Tampengco Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136478 | H.J. Atienza Elementary School | MALATE | 5 | 1 | 53 | Repair of Classrooms | 15000000 | 1 | 14906250 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | Aylan Construction & Trading | Under procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136484 | Fernando Ma. Guerrero E.S. | SANTA ANA | 5 | 1 | 89 | Repair of Classrooms | 15000000 | 1 | 14906250 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | Aylan Construction & Trading | Work suspended due to overlapping of work with DPWH retrofitting project | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 305313 | I. Villamor High School | SANTA ANA | 6 | 1 | 70 | Repair of Classrooms | 15678069 | 1 | 15678068.61 | COMPLETED | 100% | June 18, 2021 | 2021-06-02 | [6 empty] | November 26, 2020 | Lourbel Consttuction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 60 | Repair of Classrooms | 25000000 | 1 | 24842526.77 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Manila | 136485 | Sta. Ana ES | SANTA ANA | 6 | 1 | 71 | Repair of Classrooms | 25000000 | 1 | 24843750.08 | COMPLETED | 100% | August 7, 2021 | N/A | [6 empty] | November 26, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 2928816.3 | COMPLETED | 100% | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 2928817 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319903 | Barangka NHS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 3421665.38 | COMPLETED | 100% | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 3421666 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 | February 6,2020 | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319907 | Jesus Dela Peña National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319904 | Kalumpang National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 995850.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 7310695.34 | COMPLETED | 100% | November 25,2020 | November 4,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | CRYSTAL DREAMS DEV. CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 7310696 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 995850.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 324347 | 1 | 323270.6 | COMPLETED | 100% | 2021-02-15 | February 4,2021 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 | 1 | 60 | Repair of classrooms | 7403981 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 279466.16 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 280834 | 1 | 3312296.07 | COMPLETED | 100% | November 25,2020 | November 4,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | METER KING INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1 |  | 1 | Repair of Toilets | 3312297 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305401 | Marikina Science HS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319905 | San Roque National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305405 | Sta. Elena HS | CITY OF MARIKINA | 1 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | November 3,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA | 1 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 7403980.83 | COMPLETED | 100% | February 25,2021 | October 23,2020 |  |  | December 22,2019 | January 6,2020 | January 20,2020 | January 21,2020 | August 25,2020 | MMEEN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA | 1 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | 2018-11-12 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 995851 | 1 | 995850.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 10786068 | 1 | 10786067.59 | COMPLETED | 100% | November 25,2020 | November 25,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | MMEEN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elem Level | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 | 2018-11-12 | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elem. Level | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 5914427 | 1 | 5914426.7 | COMPLETED | 100% | November 25,2020 | November 25,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 26,2020 | TRIX =ZION VENTURES CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elementary level | CITY OF MARIKINA | 2 |  | 42 | Repair of classrooms | 8570644 | 1 | 8570643.62 | COMPLETED | 100% | February 25,2021 | February 4,2021 |  |  | February 6,2020 | February 12,2020 | February 24,2020 | February 21,2020 | August 25,2020 | TRIX =ZION VENTURES CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Sec. Level | CITY OF MARIKINA | 2 |  | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 | 2018-11-12 | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Sec. Level | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | 2018-11-12 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 | 1 | 36 | Repair of classrooms | 7041978 | 1 | 7041977.54 | COMPLETED | 100% | March 2,2021 | October 27,2020 |  |  | December 22,2019 | January 6,2020 | January 20,2020 | January 21,2020 | September 2,2020 | SHERF bUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 | January 6,2020 | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 404781 | 1 | 400821.7 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 |  |  | 2020-10-23 | January 6,2020 | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4308481 | 1 | 4308480.44 | COMPLETED | 100% | November 25,2020 | November 3,2020 |  |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 314329 | 1 | 312243.75 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 5483788 | 1 | 5483787.55 | COMPLETED | 100% | November 25,2020 | November 3,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 7650423 | 1 | 7650422.56 | COMPLETED | 100% | November 25,2020 | November 4,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | M-TRI R CONSTRUCTION and TRADING CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136683 | Kapitan Moy ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305400 | Marikina Heights NHS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | November 3,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repair/Upgrading of Water System | 558843 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | NATIONAL BUILDERS & SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 280667 | 1 | 279466.16 | COMPLETED | 100% | 2021-02-15 | February 4,2021 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 7023649 | 1 | 7023648.16 | COMPLETED | 100% | November 25,2020 | November 25,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 26,2020 | TRIX =ZION VENTURES CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 318517 | 1 | 316107.25 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4438637 | 1 | 4438636.97 | COMPLETED | 100% | November 25,2020 | November 25,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 6521366 | 1 | 6521365.42 | COMPLETED | 100% | November 25,2020 | November 4,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | BIG BOY CONSTRUCTION SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 2383433 | 1 | 2383432.62 | COMPLETED | 100% | November 25,2020 | November 3,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | RUTHLAND TRADING and COSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 |  | 30 | Repair of Classrooms | 12645660 | 1 | 12645659.02 | COMPLETED | 100% | February 25,2021 | October 28,2020 | N/A |  | February 6,2020 | February 12,2020 | February 24,2020 | February 26,2020 | August 27,2020 | MARAKESH ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 32 | Provision of Make Shift Shower Rooms | 997132 | 1 | 997131.04 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 4551799 | 1 | 4551798.56 | COMPLETED | 100% | November 25,2020 | November 4,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | CRYSTAL DREAMS DEV. CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 |  | 1 | Repainting of Covered Court/Mini Gym Flooring Including Stage | 320105 | 1 | 318738.72 | COMPLETED | 100% | 2021-02-15 | 2021-01-15 | N/A |  | 2020-10-23 |  | 2020-10-27 | 2020-10-28 | 2020-12-15 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 9711211 | 1 | 9711210.4 | COMPLETED | 100% | November 25,2020 | November 25,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 25,2020 | B.C. CUERPO CONSTRUCTION CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 305630 | SSS Village NHS | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 | 1 | 17 | Provision of Make Shift Shower Rooms | 681835 | 1 | 681834.03 | COMPLETED | 100% | November 2,2020 | Oct. 30,2020 | N/A |  | February 13,2020 |  | February 17,2020 | February 21,2020 | September 1,2020 | GSMAXX CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 |  | 1 | Repair of Toilets | 1532844 | 1 | 1532843.09 | COMPLETED | 100% | November 25,2020 | November 11,2020 | N/A |  | January 31,2020 | February 6,2020 | February 17,2020 | February 21,2020 | August 28,2020 | GOLDEN SHOVEL BUILDERS EARTHMOVING and DEVT. CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Marikina City | 136686 | St. Mary ES | CITY OF MARIKINA | 2 |  | 28 | Repair of Classrooms | 5062768 | 1 | 5062767.88 | COMPLETED | 100% | March 2,2021 | October 27,2020 | N/A |  | February 6,2020 | February 12,2020 | February 24,2020 | February 26,2020 | September 2,2020 | SHERF bUILDERS CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | 56 | Repair of classrooms | 8102278 | 1 | 8040863.03 | COMPLETED | 100% | May 4, 2021 | 2021-05-01 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136912 | Cupang ES | CITY OF MUNTINLUPA | 0 | 1 | 47 | Repair of classrooms | 7910483 | 1 | 11033706.41 | COMPLETED | 100% | May 4, 2021 | 2021-04-30 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Dec. 23, 2021 | GMO Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 303450 | Cupang Senior High School | CITY OF MUNTINLUPA | 0 | 1 | 60 | Repair of classrooms | 3203233 | 1 |  | COMPLETED | 100% | May 4, 2021 | Feb. 19, 2021 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | GMO Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136900 | F. De Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 16 | Repair of Classrooms | 4145346 | 1 | 4145345.57 | COMPLETED | 100% | Jan.28, 2021 | Feb. 26, 2021 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Sept. 23, 2020 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classrooms | 11708081 | 1 | 11621306.42 | COMPLETED | 100% | May 4, 2021 | 2021-04-17 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 320702 | Muntinlupa Business High School - Sucat Annex | CITY OF MUNTINLUPA | 0 | 1 | 37 | Repair of Classrooms | 5000517 | 1 | 7006974.14 | COMPLETED | 100% | May 4, 2021 | 2021-04-03 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | Open Builders Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 305470 | PEDRO E. DIAZ HIGH SCHOOL | CITY OF MUNTINLUPA | 0 | 1 | 47 | Repair of classrooms | 7062357 | 1 | 4904526.76 | COMPLETED | 100% | May 4, 2021/June 18, 2021 |  |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Dec. 23, 2021 | Redcar Trading and Const | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | Repair of Classrooms | 2074091 | 1 | 2074090.26 | COMPLETED | 100% | Jan. 28, 2021 | Jan. 22, 2020 |  |  | 11/25/19-12/16/19 | Dec. 3, 2019 | Dec. 16, 2019 | Dec. 20, 2019 | Sept. 23, 2020 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Muntinlupa City | 136905 | Soldiers' Hills ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | Repair of Classrooms | 2857186 | 1 | 2857185.65 | COMPLETED | 100% | Jan.28, 2021 | 2020-12-19 |  |  | Oct. 6-27, 2020 | Oct. 15, 2020 | Oct. 28, 2020 | Oct. 29, 2020 | Sept. 23, 2020 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | Repair of Classrooms | 3550468 | 1 |  | COMPLETED | 100% | January 28, 2021 | January 28, 2021 |  | - |  |  |  | February 12, 2020 | September 11, 2020 | RHR Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 6 | Repair of Classrooms | 2541300 | 1 |  | COMPLETED | 100% | March 2, 2021 | March 2, 2021 |  | - |  |  |  | February 12, 2020 | September 11, 2020 | Tapnio & Tan Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 9 | Repair of Classrooms | 4469616 | 1 | 3376689.23 | COMPLETED | 100% | 2021-05-10 | May 7, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 11, 2020 | REDCAR TRADING & CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 32 | Renovation of School Building | 5989048 | 1 | 5414347.51 | COMPLETED | 100% | 2021-05-10 | May 6, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 | 21 | Repair of Classrooms | 6073842 | 1 | 4367703.07 | COMPLETED | 100% | May 14, 2021 | May 26, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 15, 2020 | OPEN BUILDERS, INCORPORATED | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 22 | Renovation Of School Building | 5033243 | 1 | 4524088.67 | COMPLETED | 100% | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305426 | PARANAQUE NHS-BACLARAN | CITY OF PARAÑAQUE | 1 | 1 | 8 | Renovation Of School Building | 2841268 | 1 | 2806060.77 | COMPLETED | 100% | April 24, 2021 | April 24, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Nov 25, 2020 | Sherf Builders Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136772 | R. GATCHALIAN ES | CITY OF PARAÑAQUE | 1 | 1 | 20 | Renovation Of School Building | 3819670 | 1 | 3429451.2 | COMPLETED | 100% | 2021-05-10 | May 7, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 226002 | SAN ISIDRO ELEMENTARY SCHOOL | CITY OF PARAÑAQUE | 1 | 1 | 1 | Renovation Of School Building | 3551273 | 1 | 3516255.47 | COMPLETED | 100% | 2021-05-10 | May 7, 2021 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 11, 2020 | OPEN BUILDERS, INCORPORATED | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136766 | Tambo ES | CITY OF PARAÑAQUE | 1 | 1 | 18 | Renovation Of School Building | 5654268 | 1 | 4975169.34 | COMPLETED | 100% | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | 15 | Repair of Classrooms | 5509082 | 1 | 5723613.23 | COMPLETED | 100% | May 14, 2021 | 2021-06-18 |  |  | February 25, 2020 | March 3, 2020 | September 24, 2020 | October 12, 2020 | Dec 15, 2020 | OPEN BUILDERS, INCORPORATED | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 305429 | Masville NHS | CITY OF PARAÑAQUE | 2 | 1 | 16 | Renovation Of School Building | 5091387 | 1 | 4580642.38 | COMPLETED | 100% | 2021-05-10 | May 10, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | Redcar Trading & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Paranaque City | 136759 | San Antonio ES | CITY OF PARAÑAQUE | 2 | 1 | 12 | Renovation Of School Building | 4788498 | 1 | 4772116.91 | COMPLETED | 100% | 2021-05-10 | May 7, 2021 |  |  | October 9, 2020 | October 16, 2020 | October 28, 2020 | October 29, 2020 | Dec 11, 2020 | RGDG Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 12 | Renovation Of School Building | 3008719 | 1 | 2975654.81 | COMPLETED | 100% | April 6, 2021 | March 26, 2021 |  |  | September 22, 2020 |  | October 15, 2020 | October 22, 2020 | December 1, 2020 | RGDG Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasay City | 136596 | Villamor Airbase ES | PASAY CITY | 0 | 1 | 43 | Repair of Classrooms | 13125997 | 1 | 13125996.07 | COMPLETED | 100% | July 17, 2021 | 2021-10-11 |  |  | November 19, 2019 |  | November 27, 2019 | January 8, 2020 | October 20, 2020 | Dreamworx Builder & Trdg. Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136726 | DR. SIXTO ANTONIO ELEMENTARY SCHOOL | CITY OF PASIG | 0 | 1 | 6 | Repair of Classrooms | 6753578 | 1 | 6484874.15 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305415 | Kapitolyo HS | CITY OF PASIG | 0 | 1 | 11 | Repair of Classrooms | 6503176 | 1 | 6453165.61 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136719 | Liberato Damian ES | CITY OF PASIG | 0 | 1 | 9 | Repair of Classrooms | 6165642 | 1 | 6065709.85 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 1 | Repair and Rehabilitation of Auditorium | 46757348 | 1 | 46657798.84 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136737 | Rosario ES | CITY OF PASIG | 0 | 1 | 79 | Repair of Classrooms | 18433162 | 1 | 18433162 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 136738 | San Lorenzo Ruiz ES | CITY OF PASIG | 0 | 1 | 38 | Repair of classrooms | 10889486 | 1 | 10383598.81 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 340655 | Ugong Pasig National High School | CITY OF PASIG | 0 | 1 | 17 | Repair of classrooms | 8825129 | 1 | 6888888.88 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Pasig City | 305414 | Sagad HS | CITY OF PASIG | 1 | 1 | 13 | Repair of Classrooms | 8009508 | 1 | 8009508 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136500 | BUNGAD Elementary School | QUEZON CITY | 1 | 1 | 17 | Repair of Classrooms | 10575472 | 1 | 10575471.73 | COMPLETED | 100% |  |  | SDO-2020-INFRA-006 | 008, s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 |  | 2020-12-22 | JRCF Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 18 | Repair of Classrooms | 12042455 | 1 | 7263320.67 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 40 | Repair of Classrooms | 20242021 | 1 | 20242020.15 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305324 | Sergio Osmena, Sr. HS | QUEZON CITY | 1 | 1 | 25 | Repair of Classrooms | 13465807 | 1 | 21642253.53 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136544 | Holy Spirit ES | QUEZON CITY | 2 | 1 | 80 | Repair of Classrooms | 35583393 | 1 | 35583392.99 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 319501 | Holy Spirit National High School | QUEZON CITY | 2 | 1 | 22 | Repair of Classrooms | 9549411 | 1 | 9549410.49 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136545 | Lupang Pangako ES | QUEZON CITY | 2 | 1 | 30 | Repair of Classrooms | 12165753 | 1 | 12165752.44 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136560 | Batino Elementary School (SPED Center) | QUEZON CITY | 3 | 1 | 20 | Repair of Classrooms | 16055060 | 1 | 16055059.89 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305346 | Camp Gen. E. Aguinaldo HS | QUEZON CITY | 3 | 1 | 43 | Repair of Classrooms | 18453991 | 1 | 15094086 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136579 | GEN. ROXAS Elementary School | QUEZON CITY | 4 | 1 | 28 | Repair of Classrooms | 13342976 | 1 | 13342975.81 | COMPLETED | 100% |  |  | SDO-2020-INFRA-006 | 008, s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 |  | 2020-12-14 | TM ABAD Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305356 | Ponciano A. Bernardo HS | QUEZON CITY | 4 | 1 | 31 | Repair of Classrooms | 15481044 | 1 | 21430000.61 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 009, s.2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | J. SIMEON Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 31 | Repair of Classrooms | 12377970 | 1 | 17121742.29 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 305339 | North Fairview HS | QUEZON CITY | 5 | 1 | 35 | Repair of Classrooms | 16581817 | 1 | 16581816.1 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City | 340690 | SHS in NOH-Sta Lucia | QUEZON CITY | 5 | 1 | 20 | Repair of Classrooms | 12889402 | 1 | 12798453.27 | COMPLETED | 100% |  |  | SDO-2020-INFRA-009 | 011, s.2020 | 2020-10-09 | 2020-10-16 | 2020-10-29 |  | 2020-12-28 | RHR Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Quezon City |  | West Fairview HS Annex | QUEZON CITY | 5 | 1 | 21 | Repair of classrooms | 8040798 | 1 | 8040797.38 | COMPLETED | 100% |  |  | SDO-2020-INFRA-007 | 010 s. 2020 | 2020-09-14 | 2020-09-22 | 2020-10-06 | 2020-10-14 | 2020-12-15 | IM Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1 | 1 | 2 | Repair of classrooms | 1132559 | 1 | 1130760.99 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | DAWING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 19 | Repair of Classrooms | 8500000 | 1 | 8452895.95 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305466 | Pateros National High School | PATEROS | 1 | 1 | 12 | Repair of Classrooms | 4006325 | 1 | 4004527.47 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | DAWING CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305466 | Pateros National High School | PATEROS | 1 |  | 20 | Repair of Classrooms | 4000000 | 1 | 3977865.72 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136895 | Paulina Manalo ES | PATEROS | 1 | 1 | 12 | Repair of Classrooms | 3000000 | 1 | 2983213.88 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136898 | Sto. Rosario Elementary School | PATEROS | 1 | 1 | 8 | Repair of Classrooms | 2000000 | 1 | 1988009.96 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 5000000 | 1 | 4972314.53 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 6500000 | 1 | 6466300.71 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136873 | Eusebio C. Santos Elementary School | TAGUIG CITY | 1 | 1 | 15 | Repair of Classrooms | 4120021 | 1 | 4096678.4 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305462 | Gen. Ricardo G. Papa, Sr. Memorial HS Annex | TAGUIG CITY | 1 | 1 | 12 | Repair of Classrooms | 2703631 | 1 | 2688403.33 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | CRESTA MANAGEMENT CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 21 | Repair of Classrooms | 7000000 | 1 | 6963557.53 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320604 | Sen. Renato "Compañero" Cayetano Memorial Science & Technology High School | TAGUIG CITY | 1 | 1 | 12 | Repair of Classrooms | 4000000 | 1 | 3979120.35 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 500565 | Taguig Integrated School | TAGUIG CITY | 1 | 1 | 9 | Repair of Classrooms | 3000000 | 1 | 2983085.6 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305460 | Taguig National High School | TAGUIG CITY | 1 | 1 | 9 | Repair of Classrooms | 2778695 | 1 | 2763713.99 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-005 |  | November 29, 2019 | December 2,2019 | December 20, 2019 | January 8, 2020 | October 26, 2020 | CRESTA MANAGEMENT CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136877 | Tipas Elementary School -Main | TAGUIG CITY | 1 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 1491711.41 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136879 | Ususan Elementary School | TAGUIG CITY | 1 | 1 | 20 | Repair of Classrooms | 5000000 | 1 | 4972244.95 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-007 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | C.B. TAMPENGCO CONSTRUCTION & SUPPY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 18 | Repair of Classrooms | 5400000 | 1 | 5371297.14 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320612 | Gat. Andres Bonifacio High School | TAGUIG CITY | 2 | 1 | 20 | Repair of Classrooms | 6000000 | 1 | 5969292.92 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136886 | Kapitan Jose Cardones Memorial ES | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 7000000 | 1 | 6964111.49 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136890 | Maharlika Elementary School | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6000000 | 1 | 5968583.62 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 500341 | Palar Integrated School | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6000000 | 1 | 5968973.68 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 18 | Repair of Classrooms | 4500000 | 1 | 4476962.88 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 136891 | Tenement Elementary School | TAGUIG CITY | 2 | 1 | 15 | Repair of Classrooms | 4500000 | 1 | 4476555.15 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Taguig City & Pateros | 320605 | Upper Bicutan National High School | TAGUIG CITY | 2 | 1 | 12 | Repair of Classrooms | 3000000 | 1 | 2984133.45 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | November 8-15 | November 16, 2020 | December 1, 2020 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136793 | Canumay West ES | CITY OF VALENZUELA | 1 | 1 | 58 | Repair of Classrooms | 14307871 | 1 | 14232465.7 | COMPLETED | 100% | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305439 | Canumay West National High School | CITY OF VALENZUELA | 1 | 1 | 42 | Repair of Classrooms | 6501204 | 1 | 6501204 | COMPLETED | 100% | May 29, 2021 | 2021-03-19 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | 10 | Repair of Classrooms | 2945973 | 1 | 2945973 | COMPLETED | 100% | May 29, 2021 | 2021-11-05 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | Used as quarantine/isolation facility of LGU | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 18 | Repair of Classrooms | 5182293 | 1 | 5182293 | COMPLETED | 100% | May 29, 2021 | 2021-09-21 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | Used as quarantine/isolation facility of LGU | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1 | 1 | 13 | Repair of Classrooms | 4787891 | 1 | 4769546.44 | COMPLETED | 100% | August 5, 2021 | 2021-07-07 |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2 | 1 | 44 | Repair of Classrooms | 10505698 | 1 | 10428168.99 | COMPLETED | 100% | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 | 1 | 6 | Repair of Classrooms | 2390922 | 1 | 2353303.86 | COMPLETED | 100% | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 20 | Repair of Classrooms | 4765006 | 1 | 4719604.96 | COMPLETED | 100% | August 5, 2021 | 2021-07-07 |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136814 | Gen. T. de Leon ES | CITY OF VALENZUELA | 2 | 1 | 62 | Repair of Classrooms | 15993182 | 1 | 15915164.5 | COMPLETED | 100% | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 305442 | Parada NHS | CITY OF VALENZUELA | 2 | 1 | 15 | Repair of Classrooms | 5836640 | 1 | 5804677.4 | COMPLETED | 100% | August 5, 2021 |  |  | INFRA-BEFF-2020-11-0003(LI) | Aug 25, 2020 | Sept 3, 2020 | Sept 15, 2020 | Sept 18, 2020 | Dec 8, 2020 | Aylan Construction & Trading | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | NCR | Valenzuela City | 136827 | Serrano ES | CITY OF VALENZUELA | 2 | 1 | 24 | Repair of Classrooms | 5885727 | 1 | 5885727 | COMPLETED | 100% | May 29, 2021 | 2021-01-25 |  | INFRA-EPA-BEFF-2020-09-0001(LI) | Nov 27, 2019 | Dec 5, 2019 | Dec 17, 2019 | Dec 27, 2019 | Oct 1, 2020 | Hawkstow Construction & Development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Alaminos City | 101168 | Amandiego ES | CITY OF ALAMINOS | 1 | 1 | 8 | Repair of Classrooms | 3366258 | 1 | 3366257.28 | COMPLETED | 100% |  |  | INFRA-2020-01-01 | WAITING for sUB- SARO | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | DPV BUILDERS & CONSTRUCTION SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Alaminos City | 101184 | Maliga ES | CITY OF ALAMINOS | 1 | 1 | 7 | Repair of Classrooms | 2736298 | 1 | 2736298 | COMPLETED | 100% |  |  | INFRA-2020-01-02 | WAITING for sUB- SARO | nov. 22-29, 2019 | nov. 28, 2019 | dec. 13, 2019 | jan. 20, 2020 | 2020-09-30 | CLP BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Batac City | 100091 | Baoa ES | CITY OF BATAC | 2 | 1 | 7 | Repair of Classrooms | 2571399 | 1 | 2551129.5 | COMPLETED | 100% |  |  |  |  | Nov 19,2019 | Nov 27,2019 | December 9,2019 |  |  | Abeian Construction | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Batac City | 320803 | City of Batac National high school Payao | CITY OF BATAC | 2 | 1 | 6 | Repair of Classrooms | 2498035 | 1 | 2073396.55 | COMPLETED | 100% |  |  | BEFF-2018-11-0264 | PB-2018-11-010 | Nov 19,2019 | Nov 27,2019 | December 9,2019 | March 01,2019 | September 5,2019 | M.A. Tejada Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Batac City | 100083 | Parangopong ES | CITY OF BATAC | 2 | 1 | 9 | Repair of Classrooms | 3163364 | 1 | 3033698.62 | COMPLETED | 100% |  |  |  |  | Nov 19,2019 | Nov 27,2019 | December 9,2019 |  |  | Abeian Construction | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Candon City | 100426 | Amguid Elementary School | CITY OF CANDON | 2 | 1 | 5 | Repair of Classrooms | 1587764 | 1 | 1587763.8499 | COMPLETED | 100% | 2020-12-30 | 2020-12-07 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | M.A. TEJADA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Candon City | 100447 | Salvador Elementary School | CITY OF CANDON | 2 | 1 | 9 | Repair of Classrooms | 3077748 | 1 | 3077747.1659 | COMPLETED | 100% | 2020-12-30 | 2020-12-29 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | MRK-SQUARE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Candon City | 100449 | Tablac Elementary School | CITY OF CANDON | 2 | 1 | 10 | Repair of Classrooms | 3486773 | 1 | 3486772.7136 | COMPLETED | 100% | 2020-12-30 | 2020-12-29 |  |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2019-12-23 |  | M.A. TEJADA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | 6 | Repair of Classrooms | 385994 | 1 | 385994 | COMPLETED | 100% | January 21, 2021 | December 18, 2020 |  |  |  | 2020-01-03 | 2020-01-17 | 2019-12-15 | 09/24/2020 | CHESTINAN CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Dagupan City | 102177 | Pantal ES | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 1368846 | 1 | 1368845.65 | COMPLETED | 100% | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | ELGRAM TRADING AND CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 1241291 | 1 | 1241290.83 | COMPLETED | 100% | January 21, 2021 | December 18, 2020 |  |  |  | 2020-01-03 | 2020-01-17 | 2019-12-15 | 09/24/2020 | CHESTINAN CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY | 4 | 1 | 2 | Repair of Classrooms | 231620 | 1 | 231619.77 | COMPLETED | 100% | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | ELGRAM TRADING AND CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Dagupan City | 102153 | West CES II | DAGUPAN CITY | 4 | 1 | 4 | Repair of Classrooms | 2561838 | 1 | 2561837.42 | COMPLETED | 100% | January 21, 2021 | December 18, 2020 |  |  | Nov 18-25, 2019 | 2019-11-25 | 2019-12-09 | 2019-12-15 | 09/24/2020 | VIKING III BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 5 | Repair of Classrooms | 1846630 | 1 | 1846629.4665 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-12-10 | Abeian Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100004 | Ganagan Elementary School | BACARRA | 1 | 1 | 11 | Repair of Classrooms | 3535101 | 1 | 3530900.25 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-12-10 | Elocin Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100220 | Carasi ES | CARASI | 1 | 1 | 10 | Repair of Classrooms | 3022516 | 1 | 3022515.9108 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100218 | Boyboy ES | PIDDIG | 1 | 1 | 6 | Repair of Classrooms | 1998104 | 1 | 1998103.7322 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100265 | Parang ES | SARRAT | 1 | 1 | 6 | Repair of Classrooms | 1994924 | 1 | 1994923.69 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 10 14 2020 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100295 | Dipilat ES | VINTAR | 1 | 1 | 3 | Repair of Classrooms | 981791 | 1 | 980829.4679 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100073 | Tabtabagan Elementary School | BANNA (ESPIRITU) | 2 | 1 | 9 | Repair of Classrooms | 3004849 | 1 | 3004207.94 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Norte | 100132 | Hilaria Salvatierra Mem. ES | DINGRAS | 2 | 1 | 11 | Repair of Classrooms | 3475934 | 1 | 3475933.45 | COMPLETED | 100% |  |  |  |  | 11 13 2019 | 11 21 2019 | 2019-03-12 | 12 13 2019 | 2020-09-10 | KRB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100504 | Maratudo ES | MAGSINGAL | 1 | 1 | 7 | Repair of Classrooms | 2619969 | 1 | 2619968.2 | COMPLETED | 100% | 2020-12-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100591 | Asilang PS | SAN JUAN (LAPOG) | 1 | 1 | 2 | Repair of Classrooms | 900467 | 1 | 900466.01 | COMPLETED | 100% | 2020-11-26 | 2020-11-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100732 | Nagtupacan ES | SANTO DOMINGO | 1 | 1 | 10 | Repair of Classrooms | 3256297 | 1 | 3256296.68 | COMPLETED | 100% | 2021-01-25 | 2020-12-16 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100649 | Masadag ES | SINAIT | 1 | 1 | 9 | Repair of Classrooms | 2873937 | 1 | 2873936.84 | COMPLETED | 100% | 2020-12-26 | 2020-12-16 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MA TEJADA CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100470 | Comillas North ES | CERVANTES | 2 | 1 | 9 | Repair of Classrooms | 3488144 | 1 | 3488143.73 | COMPLETED | 100% | 2021-01-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | JC Andulay Construction and Supply | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100578 | Mckinley PS | GALIMUYOD | 2 | 1 | 2 | Repair of Classrooms | 943222 | 1 |  | reverted | 0% |  |  | 6804205 | [7 empty] | Deferred | [12 empty] | 0% | [7 empty] | reverted
REPAIR 2020 | Region I | Ilocos Sur | 100565 | Butarag PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | Repair of Classrooms | 904445 | 1 | 900462.12 | COMPLETED | 100% | 2021-01-21 | 2021-01-20 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100577 | Matue PS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 3 | Repair of Classrooms | 1216449 | 1 | 1214939.32 | COMPLETED | 100% | 2021-01-21 | 2021-01-20 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100535 | Cadacad ES | NAGBUKEL | 2 | 1 | 7 | Repair of Classrooms | 2489286 | 1 | 2489285.06 | COMPLETED | 100% | 2020-12-26 | 2020-12-15 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100486 | Patungcaleo ES | QUIRINO (ANGKAKI) | 2 | 1 | 8 | Repair of Classrooms | 3478514 | 1 | 3478513.65 | COMPLETED | 100% | 2021-01-26 | 2021-01-18 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | JC Andulay Construction and Supply | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100556 | Arangin-Dinaratan ES | SALCEDO (BAUGEN) | 2 | 1 | 8 | Repair of Classrooms | 3137928 | 1 | 3137927.5 | COMPLETED | 100% | 2021-01-26 | 2021-01-25 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100675 | Padaoil Elementary School | SANTA CRUZ | 2 | 1 | 3 | Repair of Classrooms | 1320128 | 1 | 1252499.86 | COMPLETED | 100% | 2021-01-21 | 2021-01-04 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100679 | Quinsoriano PS | SANTA CRUZ | 2 | 1 | 2 | Repair of Classrooms | 1027520 | 1 | 959056.72 | COMPLETED | 100% | 2021-01-06 | 2021-01-04 | 7176296 |  | 2020-08-13 | 2020-08-20 | 2020-09-01 | 2020-09-08 | 2020-11-23 | CLEOFEL CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100704 | Butir Elementary School | SANTA MARIA | 2 | 1 | 4 | Repair of Classrooms | 1342677 | 1 | 1342676.31 | COMPLETED | 100% | 2020-11-26 | 2020-11-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100331 | Banga ES | SUGPON | 2 | 1 | 3 | Repair of Classrooms | 900466 | 1 | 900465.95 | COMPLETED | 100% | 2020-11-26 | 2021-01-04 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100333 | Calipayan ES | SUGPON | 2 | 1 | 2 | Repair of Classrooms | 683984 | 1 | 683983.23 | COMPLETED | 100% | 2020-11-12 | 2020-10-26 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100337 | DANAC ELEMENTARY SCHOOL | SUGPON | 2 | 1 | 7 | Repair of Classrooms | 2603072 | 1 | 2603071.82 | COMPLETED | 100% | 2021-01-26 | 2021-01-07 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-29 | MRK-SQUARE CONSTRUCTION AND SUPPLY | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Ilocos Sur | 100755 | Lubnac ES | SUYO | 2 | 1 | 4 | Repair of Classrooms | 1711721 | 1 | 1711720.75 | COMPLETED | 100% | 2020-12-26 | 2021-01-15 | 6804205 |  | 2020-01-17 | 2020-01-27 | 2020-02-06 | 2020-02-14 | 2020-09-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Bidded. Waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 10 | Repair of Classrooms | 3243011 | 1 | 3243010.91 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100873 | Apatut ES | BALAOAN | 1 | 1 | 9 | Repair of Classrooms | 3054363 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100878 | Butubut ES | BALAOAN | 1 | 1 | 15 | Repair of Classrooms | 4771100 | 1 | 4771099.33 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | M.O. DE GUZMAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 300106 | Castor Concepcion MNHS | BALAOAN | 1 | 1 | 2 | Repair of Classrooms | 634777 | 1 | 634776.91 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | M.O. DE GUZMAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101051 | Lacong Elementary School | SAN GABRIEL | 1 | 1 | 6 | Repair of Classrooms | 2059883 | 1 | 2059882.73 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONTRUCTION AND SUPPLY | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 151005 | Lacong ES-Annex | SAN GABRIEL | 1 | 1 | 3 | Repair of Classrooms | 1148808 | 1 | 1148807.34 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONTRUCTION AND SUPPLY | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101065 | Dasay ES | SAN JUAN | 1 | 1 | 11 | Repair of Classrooms | 3691340 | 1 | 3691339.82 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101072 | Sta. Rosa Elementary School | SAN JUAN | 1 | 1 | 12 | Repair of Classrooms | 3879143 | 1 | 3879142.31 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101080 | Liguay ES | SANTOL | 1 | 1 | 4 | Repair of Classrooms | 1575994 | 1 | 1575993.46 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | ARM ASIA ENGINEERING AND CONSTRUCTION | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 | 6 | Repair of Classrooms | 2410644 | 1 | 2410643.02 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | ARM ASIA ENGINEERING AND CONSTRUCTION | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101104 | Badang ES | SUDIPEN | 1 | 1 | 3 | Repair of Classrooms | 1133821 | 1 | 1133820.96 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101105 | Basig ES | SUDIPEN | 1 | 1 | 4 | Repair of Classrooms | 1691915 | 1 | 1691914.75 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101108 | Maliclico ES | SUDIPEN | 1 | 1 | 3 | Repair of Classrooms | 1133932 | 1 | 1133931.45 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100805 | Macalva ES | AGOO | 2 | 1 | 15 | Repair of Classrooms | 5287565 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100808 | San Vicente-San Agustin ES | AGOO | 2 | 1 | 9 | Repair of Classrooms | 3462718 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100819 | Aringay Central Elem.. School | ARINGAY | 2 | 1 | 15 | Repair of Classrooms | 5364289 | 1 | 5364288.66 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100826 | Immalog ES | ARINGAY | 2 | 1 | 5 | Repair of Classrooms | 1606932 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100838 | Sta. Lucia ES | ARINGAY | 2 | 1 | 8 | Repair of Classrooms | 3107956 | 1 | 3107955.3 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | LAV CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2 | 1 | 3 | Repair of Classrooms | 1279165 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100868 | Tagudtud ES | BAGULIN | 2 | 1 | 5 | Repair of Classrooms | 1733523 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100912 | Bawanta ES | BAUANG | 2 | 1 | 9 | Repair of Classrooms | 3427303 | 1 | 3427302.76 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100919 | Bucayab Elementary School | BAUANG | 2 | 1 | 6 | Repair of Classrooms | 2200874 | 1 | 2200873.2 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100934 | Burgos CS | BURGOS | 2 | 1 | 12 | Repair of Classrooms | 3989948 | 1 | 3989947.65 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY | Constructors Risk ( Ongoing) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100940 | Caba CES | CABA | 2 | 1 | 7 | Repair of Classrooms | 2985668 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 100989 | Mamat-ing Sur ES | NAGUILIAN | 2 | 1 | 11 | Repair of Classrooms | 3859499 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 300108 | Cuenca National High School | PUGO | 2 | 1 | 8 | Repair of Classrooms | 2867105 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101004 | Tavora ES | PUGO | 2 | 1 | 3 | Repair of Classrooms | 976327 | 1 | 976326.62 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-28 | 2019-12-12 | 2019-12-20 | 2020-06-15 | VILLAR GEN. CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101095 | Cupang ES | SANTO TOMAS | 2 | 1 | 9 | Repair of Classrooms | 2753850 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | La Union | 101103 | Ubagan Elementary School | SANTO TOMAS | 2 | 1 | 3 | Repair of Classrooms | 1216450 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Laoag City | 102193 | A. P. Santos ES (SPED Center) | LAOAG CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1434851 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Laoag City | 102206 | Barit Elementary School | LAOAG CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1321210 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Laoag City | 102197 | Cataban Elementary School | LAOAG CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2438380 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101142 | Macaboboni ES | AGNO | 1 | 1 | 4 | Repair of Classrooms | 1781046 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300250 | San Jose NHS | ANDA | 1 | 1 | 14 | Repair of Classrooms | 4633352 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 | 1 | 10 | Repair of Classrooms | 3706231 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101325 | BASING ES | BINMALEY | 1 | 1 | 1 | Repair of Classroom | 3021989 | 1 | 3011876.69 | COMPLETED | 100% | [9 empty] | Chestinan Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101346 | CATUNGI ES | BOLINAO | 1 | 1 | 1 | Repair of Classroom | 1746265 | 1 | 1735786.54 | COMPLETED | 100% | [9 empty] | ABC East Multi Builders and Traders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 500615 | Liwa-Liwa Integrated School | BOLINAO | 1 | 1 | 3 | Repair of Classrooms | 948931 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300249 | Sampaloc NHS | BOLINAO | 1 | 1 | 7 | Repair of Classrooms | 2069244 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300268 | Zaragoza NHS | BOLINAO | 1 | 1 | 6 | Repair of Classrooms | 2268927 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101382 | SAN FRANCISCO ES | BUGALLON | 1 | 1 | 1 | Repair of Classroom | 2047002 | 1 | 2016883.62 | COMPLETED | 100% | [9 empty] | Chestinan Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 6 | Repair of Classrooms and Construction of Fence | 3781378 | 1 | 3033987.04 | COMPLETED | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 7 | Repair of Classrooms and Construction of Fence | 3744940 | 1 | 3253738.61 | COMPLETED | 100% | [9 empty] | Manimeld's Construction and Iron Works | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 400000 | 1 | 395110.89 | COMPLETED | 100% | [9 empty] | Manimeld's Construction and Iron Works | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 480000 | 1 | 474974.86 | COMPLETED | 100% | [9 empty] | Manimeld's Construction and Iron Works | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 1 | Repair and Construction of Fence | 600000 | 1 | 594931 | COMPLETED | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101454 | MALACAPAS ES | DASOL | 1 | 1 | 1 | Repair of Classroom | 2163366 | 1 | 1557621.1 | COMPLETED | 100% | [9 empty] | ABC East Multi Builders and Traders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101455 | TAMBOBONG ES | DASOL | 1 | 1 | 1 | Repair of Classroom | 1728314 | 1 | 1716214.56 | COMPLETED | 100% | [9 empty] | ABC East Multi Builders and Traders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101460 | Bamban Sur ES | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 1850727 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101465 | Maringindingin ES | INFANTA | 1 | 1 | 3 | Repair of Classrooms | 1102421 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101485 | MATALAVA ES | LINGAYEN | 1 | 1 | 1 | Repair of Classroom | 2709003 | 1 | 2693876.94 | COMPLETED | 100% | [9 empty] | CWME Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101516 | CABANAETAN ES | MABINI | 1 | 1 | 1 | Repair of Classroom | 2063910 | 1 | 1762347.81 | COMPLETED | 100% | [9 empty] | WM Salayog Construction and General Merchandise | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101526 | San Pedro ES | MABINI | 1 | 1 | 7 | Repair of Classrooms | 2333356 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101530 | Villacorta ES | MABINI | 1 | 1 | 4 | Repair of Classrooms | 1630902 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101332 | MANAT ES | BINMALEY | 2 | 1 | 13 | Repair of Classrooms | 6026318 | 1 | 5975677.44 | COMPLETED | 100% | [9 empty] | Chestinan Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101334 | NAGUILAYAN ES | BINMALEY | 2 | 1 | 18 | Repair of Classrooms | 8344132 | 1 | 8293925.72 | COMPLETED | 100% | [9 empty] | Chestinan Construction Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101322 | SAN ISIDRO SUR ES | BINMALEY | 2 | 1 | 11 | Repair of Classrooms | 5099192 | 1 | 5054675.63 | COMPLETED | 100% | [9 empty] | Szcon Builders Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101336 | STA. ROSA ES | BINMALEY | 2 | 1 | 5 | Repair of Classrooms | 2172951 | 1 | 2160486.45 | COMPLETED | 100% | [9 empty] | Szcon Builders Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101613 | Tagac ES | MANGATAREM | 2 | 1 | 6 | Repair of Classrooms | 1930252 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101266 | Bani ES | BAYAMBANG | 3 | 1 | 3 | Repair of Classrooms | 550304 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101275 | Macayocayo ES | BAYAMBANG | 3 | 1 | 9 | Repair of Classrooms | 2906423 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101429 | Buenlag CS | CALASIAO | 3 | 1 | 3 | Repair of Classrooms | 812667 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101422 | Calasiao Central School | CALASIAO | 3 | 1 | 8 | Repair of Classrooms | 2264869 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101437 | Mancup ES | CALASIAO | 3 | 1 | 7 | Repair of Classrooms | 1968215 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101531 | Abonagan - Bobon Elementary School | MALASIQUI | 3 | 1 | 3 | Repair of Classrooms | 810225 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101544 | Lokeb Sur ES | MALASIQUI | 3 | 1 | 4 | Repair of Classrooms | 1277066 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan I, Lingayen | 101620 | Lambayan ES | MAPANDAN | 3 | 1 | 6 | Repair of Classrooms | 1632176 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101796 | Doña Consolacion Sta. Maria ES | MANAOAG | 4 | 1 | 6 | Repair of Classrooms | 2163904 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101806 | San Ramon-Mermer ES | MANAOAG | 4 | 1 | 2 | Repair of Classrooms | 734513 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102127 | Doña Felisa Navarro ES | MANGALDAN | 4 | 1 | 4 | Repair of Classrooms | 1497824 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101829 | Talogtog ES | MANGALDAN | 4 | 1 | 8 | Repair of Classrooms | 2329972 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101926 | Lekep ES | SAN FABIAN | 4 | 1 | 2 | Repair of Classrooms | 686038 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101937 | Macayug ES | SAN JACINTO | 4 | 1 | 6 | Repair of Classrooms | 2302996 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101755 | Villanueva ES | BAUTISTA | 5 | 1 | 4 | Repair of Classrooms | 1128326 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101760 | Casantiagoan ES | BINALONAN | 5 | 1 | 4 | Repair of Classrooms | 1483682 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101764 | Moreno ES | BINALONAN | 5 | 1 | 4 | Repair of Classrooms | 1299611 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101777 | Tabuyoc ES | BINALONAN | 5 | 1 | 2 | Repair of Classrooms | 469201 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101781 | Cabu-Cala ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1137460 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101789 | Limos-Turko ES | LAOAC | 5 | 1 | 5 | Repair of Classrooms | 1750659 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101778 | Quevedo-Anisca ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1145381 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101859 | Palguyod Elementary School | POZORRUBIO | 5 | 1 | 6 | Repair of Classrooms | 2019003 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102017 | Artacho ES | SISON | 5 | 1 | 5 | Repair of Classrooms | 1723302 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS | 5 | 1 | 5 | Repair of Classrooms | 1865153 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101713 | Carosucan Sur ES | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 1051679 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101724 | Don Teodorico Bauzon ES | ASINGAN | 6 | 1 | 6 | Repair of Classrooms | 2571721 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101725 | Palaris ES | ASINGAN | 6 | 1 | 6 | Repair of Classrooms | 2717755 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101717 | Sobol ES | ASINGAN | 6 | 1 | 3 | Repair of Classrooms | 1330034 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101728 | Toboy ES | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 874202 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101845 | San Miguel ES | NATIVIDAD | 6 | 1 | 4 | Repair of Classrooms | 1821560 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101898 | San Angel ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 851953 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101900 | San Luis ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 933671 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101953 | Juan C. Laya Central School SPED Center | SAN MANUEL | 6 | 1 | 7 | Repair of Classrooms | 2660607 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101956 | Lomboy Elementary School | SAN MANUEL | 6 | 1 | 2 | Repair of Classrooms | 848113 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101969 | Cabayawasan ES | SAN NICOLAS | 6 | 1 | 1 | Repair of Classroom | 599759 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101983 | Cabitnongan ES | SAN NICOLAS | 6 | 1 | 5 | Repair of Classrooms | 2216301 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101987 | East Central School | SAN NICOLAS | 6 | 1 | 4 | Repair of Classrooms | 1609999 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101995 | San Antonio West ES | SAN NICOLAS | 6 | 1 | 7 | Repair of Classrooms | 3056791 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 101997 | Sta. Maria ES | SAN NICOLAS | 6 | 1 | 3 | Repair of Classrooms | 1332636 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA | 6 | 1 | 3 | Repair of Classrooms | 1153139 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102048 | Pugot Elementary School | SANTA MARIA | 6 | 1 | 2 | Repair of Classrooms | 831671 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102073 | Panganiban CES | TAYUG | 6 | 1 | 2 | Repair of Classrooms | 935881 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102078 | Annam ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 957513 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102098 | Carosalesan ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 976842 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102100 | Concepcion ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 974826 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102084 | Evangelista ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 962203 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Pangasinan II, Binalonan | 102088 | Lubong Elementary School | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 967736 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Carlos City | 102243 | Gamata Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | Repair of Classrooms | 796101 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Saro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Carlos City | 102231 | Lilimasan Elementary School | SAN CARLOS CITY | 3 | 1 | 8 | Repair of Classrooms | 3035305 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Saro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 | 1 | 6 | Repair of Classrooms | 2230765 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Saro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Carlos City | 102265 | Turac Elementary School | SAN CARLOS CITY | 3 | 1 | 14 | Repair of Classrooms | 3352672 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Saro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 11 | Repair of Classrooms | 4801438 | 1 | 4801437.28 | COMPLETED | 100% |  | N/A | CSFLU-INFRA-015-2019 |  | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | N/A | JL DE GUZMAN ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | San Fernando City | 300126 | Pao National High School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3103862 | 1 | 3103861.06 | COMPLETED | 100% |  | N/A | CSFLU-INFRA-016-2019 |  | 2019-11-19 | 2019-11-26 | 2019-12-09 | 2019-12-16 | N/A | DPV BUILDERS AND CONSTRUCTION SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Urdaneta City | 102286 | Anonas East ES | CITY OF URDANETA | 5 | 1 | 1 | Repair of Classroom | 272477 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Urdaneta City | 102268 | Bactad ComS | CITY OF URDANETA | 5 | 1 | 2 | Repair of Classrooms | 660130 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Urdaneta City | 102295 | Don Amadeo Perez, Sr. MECS - West | CITY OF URDANETA | 5 | 1 | 7 | Repair of Classrooms | 1287396 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Urdaneta City | 102308 | Tabuyoc ES | CITY OF URDANETA | 5 | 1 | 4 | Repair of Classrooms | 999203 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Vigan City | 100790 | Gov. Evaristo Singson II MES | CITY OF VIGAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2009192 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Vigan City | 100791 | Jose Singson ES | CITY OF VIGAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2113088 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region I | Vigan City | 100794 | Pantay Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2015147 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Batanes | 102313 | Diptan Elementary School | BASCO (Capital) | 0 | 1 | 3 | Repair of Classrooms | 2100459 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Batanes | 102325 | Mahatao Elementary School | MAHATAO | 0 | 1 | 3 | Repair of Classrooms | 2014835 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102360 | Angkiray ES | ALCALA | 1 | 1 | 5 | Repair of Classrooms | 1409654 | 1 | 509555.55 | COMPLETED | 100% | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | [12 empty] | 100% |  | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102363 | Baybayog ES | ALCALA | 1 | 1 | 6 | Repair of Classrooms | 1477000 | 1 | 664079.14 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102367 | DALAOIG ELEMENTARY SCHOOL | ALCALA | 1 | 1 | 6 | Repair of Classrooms | 1427456 | 1 | 758275.68 | COMPLETED | 100% | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | [12 empty] | 100% |  | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102369 | Jurisdiccion ES | ALCALA | 1 | 1 | 5 | Repair of Classrooms | 1506286 | 1 | 603348.24 | COMPLETED | 100% | [10 empty] | COMPLETED WITH DEDUCTION;For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project sites are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time | [12 empty] | 100% |  | 44621 | 9.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102456 | Binalan Elementary School | APARRI | 1 | 1 | 7 | Repair of Classrooms | 1782270 | 1 | 2574796 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 4 | Repair of Classrooms | 782183 | 1 | 214852.42 | COMPLETED | 100% | [10 empty] | abandoned (for issuace of notice for termination) | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102476 | Agaman Proper ES | BAGGAO | 1 | 1 | 6 | Repair of Classrooms | 1181000 | 1 | 2548680 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102479 | Alba ES | BAGGAO | 1 | 1 | 5 | Repair of Classrooms | 1326203 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102528 | San Luis ES | BAGGAO | 1 | 1 | 7 | Repair of Classrooms | 1970162 | 1 | 904721 | COMPLETED | 100% | [10 empty] | For Issuance of Termination Order *Issued notice of termination and still ignored and failed to comply on the show cause order requested * Next step is to issued termination order due the continuous refusal to undertake the awarded contract. *All the Project site are substantially completed as stated in the Statement of Work accomplishments however failed to execute the issued variation orders to complete e the project) The classroom was fully rehabilitated and all functional as classroom as of this time. | [12 empty] | 100% |  | 44621 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 155015 | Centro West Elementary School | BUGUEY | 1 | 1 | 4 | Repair of Classrooms | 1490133 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102597 | Camalaniugan Central School | CAMALANIUGAN | 1 | 1 | 6 | Repair of Classrooms | 1210600 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102724 | Bagumbayan ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 370000 | 1 | 1139853 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102738 | Bangag ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 295000 | 1 | 1936890 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102739 | Bicud ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 825000 | 1 | 1157995 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102726 | Binag ES | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 675000 | 1 | 3585178 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102740 | Cabayabasan ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1825000 | 1 | 932388 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102741 | Catayauan ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 1500000 | 1 | 1305251 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1120000 | 1 | 3352574 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102728 | Cullit ES | LAL-LO | 1 | 1 | 5 | Repair of Classrooms | 475000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102744 | Dalaya ES | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 400000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102731 | Lallo North CS | LAL-LO | 1 | 1 | 15 | Repair of Classrooms | 2000000 | 1 | 1332046 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102747 | Logac ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 1680000 | 1 | 1221313 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1300000 | 1 | 3618098 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102732 | Maxingal ES | LAL-LO | 1 | 1 | 9 | Repair of Classrooms | 1800000 | 1 | 2689300 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102733 | Naguillan ES | LAL-LO | 1 | 1 | 7 | Repair of Classrooms | 900000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102734 | San Antonio ES | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 600000 | 1 | 2555566 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102751 | San Lorenzo ES | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 680000 | 1 | 1282703 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102754 | Sta.Maria CS | LAL-LO | 1 | 1 | 11 | Repair of Classrooms | 2400000 | 1 | 2700146 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102336 | Calog Sur ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 350000 | 1 | 1680443 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102347 | San Julian ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 800000 | 1 | 1282703 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102350 | Sirit ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 900000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102584 | Calayan CS | CALAYAN | 2 | 1 | 5 | Repair of Classrooms | 1040092 | 1 | 1175337 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 155035 | Kadinakan PS | CALAYAN | 2 | 1 | 2 | Repair of Classroom | 452536 | 1 | 1624679 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102592 | Minabel ES | CALAYAN | 2 | 1 | 8 | Repair of Classroom | 1834320 | 1 | 5975009 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2 | 1 | 7 | Repair of Classroom | 2595359 | 1 | 2251823 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102761 | Finugo Norte ES | LASAM | 2 | 1 | 2 | Repair of Classroom | 519420 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102764 | Lasam CS | LASAM | 2 | 1 | 10 | Repair of Classrooms | 1500000 | 1 | 1282703 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102767 | Minanga Norte ES | LASAM | 2 | 1 | 3 | Repair of Classroom | 342698 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102772 | Nicolas Agatep ES | LASAM | 2 | 1 | 3 | Repair of Classroom | 757021 | 1 | 6086958 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102777 | Tucalan Passing ES | LASAM | 2 | 1 | 6 | Repair of Classroom | 1473970 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102830 | Villa Rey ES | PIAT | 2 | 1 | 2 | Repair of Classrooms | 275000 | 1 | 5975009 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102834 | Dungan Elementary School | RIZAL | 2 | 1 | 6 | Repair of Classroom | 1070678 | 1 | 4274531 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 501172 | Dungao Integrated School | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 376770 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102949 | Niug ES | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | Repair of Classrooms | 500000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102950 | San Manuel ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | Repair of Classrooms | 350000 | 1 | 397800 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102953 | Sto. Nino Central Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 18 | Repair of Classrooms | 3200000 | 1 | 769629 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102954 | Tabang ES | SANTO NIÑO (FAIRE) | 2 | 1 | 2 | Repair of Classrooms | 280000 | 1 | 689089 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cagayan | 102956 | Virginia Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 | 1949077 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103191 | Doña Pacita C. Bautista ES | CITY OF CAUAYAN | 3 | 1 | 8 | Repair of Classrooms | 2020197 | 1 | 453800 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103224 | San Francisco ES - Annex | CITY OF CAUAYAN | 3 | 1 | 3 | Repair of Classrooms | 1025687 | 1 | 1583979 | COMPLETED | 100% | 2019-02-05 |  | CW-053 s. 2019 | CW-053 s. 2019 | 2019-07-30 | 2019-08-08 | 2019-08-20 | 2019-09-23 | 2019-11-05 | NEW AMSON CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103200 | San Luis ES | CITY OF CAUAYAN | 3 | 1 | 10 | Repair of Classrooms | 2604986 | 1 | 2248779 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 155504 | Sta. Luciana ES Annex | CITY OF CAUAYAN | 3 | 1 | 2 | Repair of Classrooms | 754871 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Cauayan City | 103207 | Villa Luna ES - Annex | CITY OF CAUAYAN | 3 | 1 | 5 | Repair of Classrooms | 1374066 | 1 | 1316449 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103416 | Bigao Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 5 | Repair of Classrooms | 1234174 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103386 | Cadu ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | Repair of Classrooms | 635625 | 1 | 1522505 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103402 | Ilagan South CS | ILAGAN CITY (CAPITAL) | 1 | 1 | 37 | Repair of Classrooms | 7596213 | 1 | 2888624 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103434 | Siffu Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | Repair of Classrooms | 1604725 | 1 | 1958177 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | City of Ilagan | 103380 | Sta. Victoria ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 4 | Repair of Classrooms | 1057440 | 1 | 1780840 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103098 | Andabuen Elementary School - Main | BENITO SOLIVEN | 2 | 1 | 6 | Repair of Classrooms | 2548680 | 1 | 1551493 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103118 | San Francisco Elementary School | BENITO SOLIVEN | 2 | 1 | 4 | Repair of Classrooms | 1522505 | 1 | 2943908 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103120 | Sevillana Elementary School | BENITO SOLIVEN | 2 | 1 | 1 | Repair of Classroom | 467054 | 1 | 467054 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103351 | Union Elementary School | GAMU | 2 | 1 | 9 | Repair of Classrooms | 3735752 | 1 | 406835 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 2 | 1 | 27 | Repair of Classrooms | 6086958 | 1 | 1895365 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103750 | Casala Elementary School | SAN MARIANO | 2 | 1 | 7 | Repair of Classrooms | 2555566 | 1 | 1282703 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103751 | Cataguing Elementary School | SAN MARIANO | 2 | 1 | 4 | Repair of Classrooms | 932388 | 1 | 1008538 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103733 | Caunayan Elementary School | SAN MARIANO | 2 | 1 | 3 | Repair of Classrooms | 1305251 | 1 | 461849 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300595 | Ueg National High School | SAN MARIANO | 2 | 1 | 4 | Repair of Classrooms | 366729 | 1 | 1845751 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103056 | Consular Elementary School | ANGADANAN | 3 | 1 | 9 | Repair of Classrooms | 3352574 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103058 | Dalakip Elementary School | ANGADANAN | 3 | 1 | 10 | Repair of Classrooms | 3618098 | 1 | 366729 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103068 | Sinabbaran Elementary School | ANGADANAN | 3 | 1 | 2 | Repair of Classrooms | 406835 | 1 | 3735752 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103165 | Cabatuan East Central School | CABATUAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3585178 | 1 | 643920 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103167 | Calaocan Elementary School | CABATUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1332046 | 1 | 6126341 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103171 | La Paz Elementary School | CABATUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2251823 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103783 | Dagupan Elementary School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1221313 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103787 | San Marcos Elementary School | SAN MATEO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1958177 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306143 | Cagasat HS-Magsaysay Annex | CORDON | 4 | 1 | 21 | Repair of Classrooms | 3167768 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103246 | Capirpiriwan Elementary School | CORDON | 4 | 1 | 6 | Repair of Classrooms | 2158715 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103251 | Kakilingan Elementary School | CORDON | 4 | 1 | 6 | Repair of Classrooms | 4386238 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500073 | Wigan Integrated School | CORDON | 4 | 1 | 15 | REPAIR OF CLASSROOMS | 6126341 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300498 | Addalam Region HS - Main | JONES | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2574796 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103465 | Disimpit Elementary School | JONES | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2700146 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103475 | Pungpongan PS | Jones | 4 | 1 | 1 | Repair of Classroom | 376770 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103482 | Tubar Elementary School | JONES | 4 | 1 | 5 | Repair of Classrooms | 1764251 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103650 | Bautista Elementary School - Annex | SAN AGUSTIN | 4 | 1 | 2 | Repair of classrooms | 904721 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103649 | Bautista Elementary School - Main | SAN AGUSTIN | 4 | 1 | 8 | Repair of Classrooms | 1740581 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103653 | Dabubu Elementary School | SAN AGUSTIN | 4 | 1 | 10 | Repair of Classrooms | 3520968 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103656 | Mapalad Elementary School | SAN AGUSTIN | 4 | 1 | 12 | REPAIR OF CLASSROOMS | 4274531 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103658 | Masaya Sur Elementary School | SAN AGUSTIN | 4 | 1 | 10 | Repair of Classrooms | 3368895 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103659 | Nemmatan Primary School | SAN AGUSTIN | 4 | 1 | 1 | Repair of Classroom | 397800 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103663 | Quimalabasa Sur Primary School | SAN AGUSTIN | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 453800 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103665 | San Agustin Central School | SAN AGUSTIN | 4 | 1 | 16 | Repair of Classrooms | 6243110 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103666 | San Antonio Elementary School | SAN AGUSTIN | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1780840 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103669 | Sinaoangan Sur Elementary School | SAN AGUSTIN | 4 | 1 | 1 | Repair of Classroom | 461849 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103670 | Sto. Nino Elementary School | SAN AGUSTIN | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1845751 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103129 | Catabban Elementary School | BURGOS | 5 | 1 | 5 | Repair of Classrooms | 1157995 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103137 | San Miguel Elementary School | BURGOS | 5 | 1 | 10 | Repair of Classrooms | 2943908 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103585 | San Mateo Elementary School | QUIRINO | 5 | 1 | 5 | Repair of Classrooms | 1551493 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103282 | Annafunan Elementary School | ECHAGUE | 6 | 1 | 8 | Repair of Classrooms | 5679661 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103328 | Buneg Elementary School | ECHAGUE | 6 | 1 | 2 | Repair of Classroom | 3472005 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103286 | Castillo Elementary School | ECHAGUE | 6 | 1 | 6 | REPAIR OF CLASSROOMS | 1936890 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103330 | Dammang Malitao Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103332 | Fugu Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103333 | Garit Elementary School | ECHAGUE | 6 | 1 | 10 | Repair of Classrooms | 3265082.02 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103334 | Gucab Elementary School | ECHAGUE | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 5975009 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300541 | Imelda R. Marcos High School | ECHAGUE | 6 | 1 | 11 | Repair of Classrooms | 5531986 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306120 | Imelda R. Marcos HS - Mabbayad Annex | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 4458685 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103336 | Malitao Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103315 | Pangal Sur Elementary School | ECHAGUE | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 689089 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300566 | Pangal Sur High School | ECHAGUE | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 1949077 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103301 | Sinabbaran Elementary School | ECHAGUE | 6 | 1 | 6 | REPAIR OF CLASSROOMS | 1895365 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103337 | Soyung Elementary School | ECHAGUE | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1282703 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103325 | Sta. Monica Elementary School | ECHAGUE | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1008538 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103675 | Burgos West Elementary School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1139853 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103683 | Guam Elementary School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1175337 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500083 | Palawan Integrated School | SAN GUILLERMO | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 769629 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 500022 | Rizal Integrated School | SAN GUILLERMO | 6 | 1 | 3 | REPAIR OF CLASSROOMS | 1583979 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103690 | San Guillermo Central School | SAN GUILLERMO | 6 | 1 | 11 | REPAIR OF CLASSROOMS | 2888624 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103698 | Villa Teresita Primary School | SAN GUILLERMO | 6 | 1 | 2 | REPAIR OF CLASSROOMS | 643920 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 155521 | Camarag Elementary School | SAN ISIDRO | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 2689300 | 1 | 7596212.3 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103708 | Dona Paulina Elementary School | SAN ISIDRO | 6 | 1 | 5 | REPAIR OF CLASSROOMS | 1680443 | 1 | 1234173.09 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6 | 1 | 5 | REPAIR OF CLASSROOMS | 1624679 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 6 | 1 | 10 | REPAIR OF CLASSROOMS | 5975009 | 1 | 1604724.29 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6 | 1 | 8 | REPAIR OF CLASSROOMS | 2248779 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 155510 | Ramos West Elementary School | SAN ISIDRO | 6 | 1 | 7 | REPAIR OF CLASSROOMS | 1316449 | 1 | 635624.46 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Isabela | 300591 | San Isidro National High School | SAN ISIDRO | 6 | 1 | 23 | Repair of Classroom | 4458685 | 1 | 1057439.69 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104187 | Abuyo ES | ALFONSO CASTAÑEDA | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104188 | Alfonso Castañeda Central School | ALFONSO CASTAÑEDA | 0 | 1 | 5 | Repair of Classrooms | 5000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104199 | Galintuja ES | ALFONSO CASTAÑEDA | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104204 | Lipuga ES | ALFONSO CASTAÑEDA | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103909 | Beti ES | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103910 | Bone North Elementary School | ARITAO | 0 | 1 | 8 | Repair of Classrooms | 6000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103914 | Canarem PS | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103922 | Nagcuartelan ES | ARITAO | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103923 | Sta. Clara ES | ARITAO | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103926 | Ukaw ES | ARITAO | 0 | 1 | 4 | Repair of Classrooms | 4000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103927 | Yaway ES | ARITAO | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103986 | Busilac ES | BAYOMBONG (Capital) | 0 | 1 | 10 | Repair of Classrooms | 3394851 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104010 | Labbu ES | BAYOMBONG (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1589487 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 103997 | Paitan ES | BAYOMBONG (Capital) | 0 | 1 | 10 | Repair of Classrooms | 2812660 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104037 | Belance Elementary School | DUPAX DEL NORTE | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104038 | Binuangan Elementary School | DUPAX DEL NORTE | 0 | 1 | 6 | Repair of Classrooms | 4000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 156007 | Naruron ES | DUPAX DEL NORTE | 0 | 1 | 3 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104052 | New Gumiad ES | DUPAX DEL NORTE | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104057 | Banila ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104060 | Carolotan ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104061 | Castro ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104063 | Ecameging ES | DUPAX DEL SUR | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104065 | Ganao Elementary School | DUPAX DEL SUR | 0 | 1 | 6 | Repair of classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104068 | Lukidnon ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104072 | Talbec ES | DUPAX DEL SUR | 0 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104082 | Catarawan ES | Kasibu | 0 | 1 | 3 | Repair of Classroom | 1580200 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104103 | Siguem ES | KASIBU | 0 | 1 | 2 | Repair of Classrooms | 3000000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Nueva Vizcaya | 104179 | Commonal ES | Solano | 0 | 1 | 2 | Repair of Classroom | 725641 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 300655 | BURGOS NHS | Cabarroguis | 0 | 1 | 14 | Repair of Classrooms | 6273122 | 1 | 6273121.05 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 500872 | Cabarroguis CS - Integrated SPED Center | Cabarroguis | 0 | 1 | 8 | Repair of Classrooms | 2790188 | 1 | 2790187.6 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104269 | UPPER DIBIBI ES | Cabarroguis | 0 | 1 | 3 | Repair of Classrooms | 999835 | 1 | 999834.16 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104284 | LOWER GABRIELA ES | Diffun | 0 | 1 | 8 | Repair of Classrooms | 2345432 | 1 | 2345431.41 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104312 | Pimentel ES | Diffun | 0 | 1 | 4 | Repair of Classrooms | 1129544 | 1 | 1129543.01 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104317 | ABBAG ES | Maddela | 0 | 1 | 5 | Repair of Classrooms | 1444003 | 1 | 1444002.8 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Quirino | 104321 | Dialanese ES | MADDELA | 0 | 1 | 3 | Repair of Classrooms | 1390578 | 1 | 1390577.71 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 | 1 | 1 | Repair of Classroom | 5300000 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103842 | Santiago West Central School-Special Science Elementary School | CITY OF SANTIAGO | 4 | 1 | 6 | Repair of Classrooms | 2936962 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Santiago City | 103817 | Nabbuan ES | Santiago City | 4 | 1 | 6 | Repair of Classrooms | 1427298 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Tuguegarao City | 157001 | Dadda ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 2 | Repair of Classrooms | 181932 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3 | 1 | 12 | Repair of Classrooms | 618079 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107022 | Abelardo G. Tinio ES | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 2639883 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 161001 | Air Force City Elementary School | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 773417 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | 16 | Repair of Classrooms | 5524899 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1 | 1 | 11 | Repair of Classrooms | 3594079 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | 12 | Repair of Classrooms | 3976260 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107025 | Cutud ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1451683 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107055 | Don Pepe Henson Memorial School | ANGELES CITY | 1 | 1 | 7 | Repair of Classrooms | 2271624 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 305554 | Dr Clemente N. Dayrit Sr. MHS | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 2932403 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107028 | Enrica Sandico ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1668594 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1977628 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500129 | Gov. Rafael L. Lazatin IS | ANGELES CITY | 1 | 1 | 20 | Repair of Classrooms | 3362242 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107041 | Gueco Balibago ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 1305815 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1 | 1 | 6 | Repair of Classrooms | 2461913 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1 | 1 | 30 | Repair of Classrooms | 8168153 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107059 | Pampang ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 703067 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107032 | Pineda-Gutierrez ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 706015 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107044 | Sapang Bato ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 1827826 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107048 | Sta. Teresita Elementary School | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1250538 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 500729 | Carmen T. Valenzuela IS | Baler | 0 | 1 | 3 | Repair of Classrooms | 1065612 | 1 | 1065611.28 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-12 | AMC CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104418 | Suklayin ES | Baler | 0 | 1 | 2 | Repair of Classrooms | 737268 | 1 | 737267.01 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104427 | F. BENITEZ ES | Casiguran | 0 | 1 | 4 | Repair of Classrooms | 1480002 | 1 | 1480001.71 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-24 | VB Donato Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104476 | Maligaya ES | Dilasag | 0 | 1 | 2 | Repair of Classrooms | 835626 | 1 | 835625.25 | COMPLETED | 100% |  |  |  |  | Dec 9, 2019-Jan 6, 2020 | 2019-12-17 | 2020-01-07 | 2020-01-07 | 2020-08-24 | MITZIE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104470 | DIPACULAO CS | Dipaculao | 0 | 1 | 9 | Repair of Classrooms | 2529568 | 1 | 2529567.57 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-12 | FNR BUILDERS AND SONS SUPPLY INC | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 300676 | Puangi NHS | Dipaculao | 0 | 1 | 6 | Repair of Classrooms | 1782880 | 1 | 1782879.53 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104497 | DIMOTOL ES | Ma. Aurora | 0 | 1 | 2 | Repair of Classrooms | 622332 | 1 | 622331.56 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104501 | GALINTUJA ES | Ma. Aurora | 0 | 1 | 4 | Repair of Classrooms | 1234817 | 1 | 1234816.66 | COMPLETED | 100% |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-10-07 | ES Pua Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Balanga City | 104567 | Tenejero Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2172873 | 1 | 2169279.43 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Balanga City | 104568 | Tortugas Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 4 | Repair of Classrooms | 719500 | 1 | 723093.14 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104572 | Colo ES | DINALUPIHAN | 1 | 1 | 7 | Repair of Classroom | 4327176 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104575 | Dinalupihan ES | DINALUPIHAN | 1 | 1 | 3 | Repair of Classrooms | 1848889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104580 | Luakan ES | DINALUPIHAN | 1 | 1 | 8 | Repair of Classrooms | 3408889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104583 | New San Jose ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 3610955 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104584 | OLD SAN JOSE ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 10 | Repair of Classrooms | 6024316 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104594 | SAN PABLO ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 9 | Repair of Classrooms | 3147026 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104597 | SAN SIMON ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 4 | Repair of Classrooms | 2280209 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104609 | Culis ES | HERMOSA | 1 | 1 | 14 | Repair of Classrooms | 4521976 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104665 | PAG ASA ELEMENTARY SCHOOL | ORANI | 1 | 1 | 2 | Repair of Classrooms | 1260486 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104667 | PANTALAN LUMA ELEMENTARY SCHOOL | ORANI | 1 | 1 | 3 | Repair of Classrooms | 1920785 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104668 | Paraiso ES | ORANI | 1 | 1 | 8 | Repair of Classrooms | 2878889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104694 | Nagwaling ES | PILAR | 1 | 1 | 3 | Repair of Classrooms | 968889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104541 | Bagac ES | BAGAC | 2 | 1 | 6 | Repair of Classrooms | 2756222 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104550 | Saysain ES | BAGAC | 2 | 1 | 8 | Repair of Classrooms | 2790375 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104638 | BASECO ELEMENTARY SCHOOL | MARIVELES | 2 | 1 | 6 | Repair of Classrooms | 2104991 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104644 | LUCANIN ELEMENTARY SCHOOL | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 1312724 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104646 | Old Alion ES | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 1538889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104679 | DAAN PARE ELEMENTARY SCHOOL | ORION | 2 | 1 | 6 | Repair of Classrooms | 2308003 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104683 | PABLO ROMAN ELEMENTARY SCHOOL | ORION | 2 | 1 | 6 | Repair of Classrooms | 2305690 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104691 | DIWA ELEMENTARY SCHOOL | PILAR | 2 | 1 | 4 | Repair of Classrooms | 2491600 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104802 | Caniogan ES | CALUMPIT | 1 | 1 | 7 | Repair of Classrooms | 2925443 | 1 | 2880704.02 | COMPLETED | 100% |  |  | 20-10-008 | 20-11-029 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-25 | THREE PAUL BUILDERS & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300769 | Caniogan High school | CALUMPIT | 1 | 1 | 15 | Repair of Classrooms | 3192303 | 1 | 3192302.08 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-012 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | KPS CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104839 | Iba Ibayo ES | HAGONOY | 1 | 1 | 10 | Repair of Classrooms | 5394296 | 1 | 4088696.37 | COMPLETED | 100% |  |  | 20-10-009 | 20-11-030 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | G.M. Caparas Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104758 | Tarcan Elementary School | BALIUAG | 2 | 1 | 14 | Repair of Classrooms | 6417780 | 1 | 4608181.89 | COMPLETED | 100% |  |  | 20-10-010 | 20-11-031 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104784 | Bonga Mayor ES | BUSTOS | 2 | 1 | 7 | Repair of Classrooms | 2500000 | 1 | 2500000 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-013 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | T.G. OCAMPO CONSTRUCTION & SURVEYING SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104794 | San Pedro ES | BUSTOS | 2 | 1 | 7 | Repair of Classrooms | 4003285 | 1 | 4003284.26 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-014 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | SAMENARA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105000 | Banga ES | PLARIDEL | 2 | 1 | 13 | Repair of Classrooms | 5420938 | 1 | 4413564.28 | COMPLETED | 100% |  |  | 20-10-011 | 20-11-032 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | G.M. Caparas Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105001 | Bintog ES | PLARIDEL | 2 | 1 | 11 | Repair of Classrooms | 5830315 | 1 | 5420937.28 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-015 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | THREE POLL BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105003 | Dampol ES | PLARIDEL | 2 | 1 | 8 | Repair of Classrooms | 3883370 | 1 | 3883369.25 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-016 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | ELMUEL JAY TRADING & CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300722 | Binagbag NHS | ANGAT | 3 | 1 | 19 | Repair of Classrooms | 5742000 | 1 | 5742000 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-017 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | V. TRILLANA BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104723 | O. M. Esteban ES (Pulong Yantok ES) | ANGAT | 3 | 1 | 14 | Repair of Classrooms | 6280662 | 1 | 6180661.37 | COMPLETED | 100% |  |  | 20-10-012 | 20-11-033 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-02 | Emica Builders & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105071 | Calumpit Elementary School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 3 | Repair of Classrooms | 1613540 | 1 | 1613539.03 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-018 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EMICA BUILDERS & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104940 | Banahaw ES | NORZAGARAY | 3 | 1 | 5 | Repair of Classrooms | 2522787 | 1 | 2497433.24 | COMPLETED | 100% |  |  | 20-10-013 | 20-11-034 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-07 | C.B. Tampengco Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 158532 | Bigte Elementary School | NORZAGARAY | 3 | 1 | 7 | Repair of Classrooms | 3470513 | 1 | 2599888.93 | COMPLETED | 100% |  |  | 20-10-018 | 20-11-039 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104947 | FVR Phase 3 Elementary School | NORZAGARAY | 3 | 1 | 14 | Repair of Classrooms | 3977275 | 1 | 2882869.97 | COMPLETED | 100% |  |  | 20-10-014 | 20-11-035 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104954 | Padling Elementary School | NORZAGARAY | 3 | 1 | 9 | Repair of Classrooms | 4909526 | 1 | 3528761.5 | COMPLETED | 100% |  |  | 20-10-015 | 20-11-036 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104957 | San Mateo Elementary School | NORZAGARAY | 3 | 1 | 8 | Repair of Classrooms | 4115647 | 1 | 2955033.88 | COMPLETED | 100% |  |  | 20-10-016 | 20-11-037 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | Altitude Engineering & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104958 | Sapang Kawayan Elementary School | NORZAGARAY | 3 | 1 | 14 | Repair of Classrooms | 6968622 | 1 | 5212528.88 | COMPLETED | 100% |  |  | 20-10-017 | 20-11-038 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | Altitude Engineering & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105058 | Palapala Elementary School | SAN ILDEFONSO | 3 | 1 | 13 | Repair of Classrooms | 5348766 | 1 | 5348765.86 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-019 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | ELDICO BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105095 | Batasan ES | SAN MIGUEL | 3 | 1 | 10 | Repair of Classrooms | 5889704 | 1 | 4233011.45 | COMPLETED | 100% |  |  | 20-10-020 | 20-11-041 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105079 | Malibay ES | SAN MIGUEL | 3 | 1 | 11 | Repair of Classrooms | 6179255 | 1 | 4437455.13 | COMPLETED | 100% |  |  | 20-10-019 | 20-11-040 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3 | 1 | 64 | Repair of Classrooms | 17217307 | 1 | 17217306.74 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-020 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306708 | Maronquillo National High School | SAN RAFAEL | 3 | 1 | 8 | Repair of Classrooms | 3119632 | 1 | 3119631.36 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-023 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105125 | Pasong Callos ES | SAN RAFAEL | 3 | 1 | 7 | Repair of Classrooms | 2491408 | 1 | 2491407.11 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-021 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | E.B. MATIAS TRADING & CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105135 | Sapang Pahalang Elementary School | SAN RAFAEL | 3 | 1 | 5 | Repair of Classrooms | 1978304 | 1 | 1978303.78 | COMPLETED | 100% |  |  | 19-11-009 | 20-10-022 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104967 | San Pascual ES | OBANDO | 4 | 1 | 4 | Repair of Classrooms | 2677553 | 1 | 2628643.52 | COMPLETED | 100% |  |  | 20-10-021 | 20-11-042 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-25 | ADIMRE Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306714 | Catmon HS | SANTA MARIA | 4 | 1 | 18 | Repair of Classrooms | 5530674 | 1 | 4431643.39 | COMPLETED | 100% |  |  | 20-10-027 | 20-11-048 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-26 | OPEN BUILDERS INCORPORATED | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105144 | CORNELIA M. DE JESUS MEMORIAL CENTRAL SCHOOL | SANTA MARIA | 4 | 1 | 19 | Repair of Classrooms | 8359304 | 1 | 5966907.42 | COMPLETED | 100% |  |  | 20-10-022 | 20-11-043 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 24 | Repair of Classrooms | 10348898 | 1 | 7230931.98 | COMPLETED | 100% |  |  | 20-10-026 | 20-11-047 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-01 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105162 | San Jose Patag Elementary School | SANTA MARIA | 4 | 1 | 10 | Repair of Classrooms | 4610059 | 1 | 3835980.47 | COMPLETED | 100% |  |  | 20-10-023 | 20-11-044 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-25 | THREE PAUL BUILDERS & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105165 | Silangan ES | SANTA MARIA | 4 | 1 | 4 | Repair of Classrooms | 1874751 | 1 | 1452009.69 | COMPLETED | 100% |  |  | 20-10-024 | 20-11-045 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-03 | GELROCK BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105168 | Sta. Maria Elementary School | SANTA MARIA | 4 | 1 | 12 | Repair of Classrooms | 6233930 | 1 | 4357109.28 | COMPLETED | 100% |  |  | 20-10-025 | 20-11-046 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-01 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Cabanatuan City | 307301 | Cesar E. Vergara Memorial High School | CABANATUAN CITY | 3 | 1 | 2 | Repair of Classrooms | 860041 | 1 | 860040.4 | COMPLETED | 100% |  |  |  |  | 2019-12-02 | 2019-12-06 | 2019-12-17 | 2019-12-18 |  | MARVELOUS QUEJADA CONSTRUCTION INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Cabanatuan City | 107105 | Macatbong ES | CABANATUAN CITY | 3 | 1 | 10 | Repair of Classrooms | 2808809 | 1 | 2808808.88 | COMPLETED | 100% |  |  |  |  | 2019-12-02 | 2019-12-06 | 2019-12-17 | 2019-12-18 |  | MARVELOUS QUEJADA CONSTRUCTION INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105314 | Bagong Silang ES | CITY OF GAPAN | 4 | 1 | 4 | Repair of Classrooms | 2006325 | 1 | 2006324.27 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 300815 | Kapalangan NHS | CITY OF GAPAN | 4 | 1 | 8 | Repair of Classrooms | 2229905 | 1 | 2229904.97 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105326 | Mangino ES | CITY OF GAPAN | 4 | 1 | 3 | Repair of Classrooms | 1519230 | 1 | 1519229.71 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105345 | Sto. Nino ES | CITY OF GAPAN | 4 | 1 | 6 | Repair of Classrooms | 2779927 | 1 | 2779926.12 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 306922 | Duquit High School | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 738904 | 1 | 738903.37 | COMPLETED | 100% |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | E.B. MATIAS CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106068 | Madapdap Resettlement ES | MABALACAT CITY | 1 | 1 | 8 | Repair of Classrooms | 2691160 | 1 | 1893668.64 | COMPLETED | 100% | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106084 | Mawake ES | MABALACAT CITY | 1 | 1 | 9 | Repair of Classrooms | 3898654 | 1 | 2675191.75 | COMPLETED | 100% | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 159535 | Northville 16 ES | MABALACAT CITY | 1 | 1 | 16 | Repair of Classrooms | 2865659 | 1 | 700247.19 | COMPLETED | 100% |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | E.B. MATIAS CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106085 | Paralayunan ES | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 473895 | 1 | 331892.45 | COMPLETED | 100% | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106088 | Talimundok Elementary School | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 700248 | 1 | 2456430.31 | COMPLETED | 100% |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | N.M.D CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106089 | Villa Teodora ES | MABALACAT CITY | 1 | 1 | 8 | Repair of Classrooms | 2456431 | 1 | 2005928.25 | COMPLETED | 100% | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Malolos City | 300751 | Marcelo H. del Pilar National HS | CITY OF MALOLOS (Capital) | 1 | 1 | 17 | Repair of Classrooms | 4403562 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Malolos City | 104882 | Tikay ES | CITY OF MALOLOS (Capital) | 1 | 1 | 17 | Repair of Classrooms | 3576371 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 104923 | Libtong Elementary School | CITY OF MEYCAUAYAN | 4 | 1 | 11 | Repair of Classrooms | 3782072 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 104934 | Longos ES | CITY OF MEYCAUAYAN | 4 | 1 | 5 | Repair of Classrooms | 2164658 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 500965 | Saluysoy Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 3 | Repair of Classrooms | 1804578 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Munoz Science City | 105538 | CABISUCULAN ELEMENTARY SCHOOL | Science City of Muñoz | 2 | 1 | 5 | Repair of Classrooms | 1509126 | 1 |  | COMPLETED | 100% |  |  |  |  | 2019-11-19 | 2019-11-26 | 2019-12-11 | 2019-12-27 |  | Front Nine Konstuct (Builders & Reality Dev. Corporation) | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Munoz Science City | 105542 | MAGTANGGOL INTEGRATED SCHOOL (SECONDARY) | Science City of Muñoz | 2 | 1 | 3 | Repair of Classrooms | 701923 | 1 |  | COMPLETED | 100% |  |  |  |  | 2019-11-19 | 2019-11-26 | 2019-12-11 | 2019-12-27 |  | Front Nine Konstuct (Builders & Reality Dev. Corporation) | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105171 | Aliaga CS | ALIAGA | 1 | 1 | 8 | Repair of Classrooms | 2836041 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105172 | Betes Es | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2015049 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105183 | San Eustacio ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2104971 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105185 | San Juan ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2150580 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105187 | San Pablo (M) ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2137812 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105188 | Santiago ES | ALIAGA | 1 | 1 | 3 | Repair of Classrooms | 1143583 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105192 | Sunson Es | ALIAGA | 1 | 1 | 4 | Repair of Classrooms | 1408383 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105255 | Baloy Elementary School | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105256 | Bambanaba ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3222059 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105257 | Bentigan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105259 | Bonifacio ES | CUYAPO | 1 | 1 | 3 | Repair of Classrooms | 1669931 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105261 | Burgos ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3362740 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105263 | Cabileo ES | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1133420 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105269 | Cuyapo CS | CUYAPO | 1 | 1 | 12 | Repair of Classrooms | 6179721 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105270 | Democrito M. Jose ES | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105271 | Dona Consuelo ES | CUYAPO | 1 | 1 | 7 | Repair of Classrooms | 3719598 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105276 | Luna ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105281 | Nagcuralan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105283 | Paitan Norte ES | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105285 | Piglisan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105287 | Rizal Elementary School | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2231377 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105289 | Salagusog ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3362740 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105290 | San Antonio ES | CUYAPO | 1 | 1 | 12 | Repair of Classrooms | 5885655 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105295 | Sta. Cruz ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105389 | Manacsac ES | GUIMBA | 1 | 1 | 15 | Repair of Classrooms | 4816240 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105420 | Manggang Marikit ES | GUIMBA | 1 | 1 | 14 | Repair of Classrooms | 4144424 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105390 | Maturanoc ES | GUIMBA | 1 | 1 | 16 | Repair of Classrooms | 5256456 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105391 | Naglabrahan ES | GUIMBA | 1 | 1 | 2 | Repair of Classrooms | 710878 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105392 | Nagpandayan Es | GUIMBA | 1 | 1 | 16 | Repair of Classrooms | 4661475 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105427 | Pasong-Inchik ES | GUIMBA | 1 | 1 | 12 | Repair of Classrooms | 3556216 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105393 | San Andres ES | GUIMBA | 1 | 1 | 10 | Repair of Classrooms | 2595629 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105398 | Sta Ana ES | GUIMBA | 1 | 1 | 7 | Repair of Classrooms | 1941275 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306804 | BURGOS NATIONAL HIGH SCHOOL | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 1658020 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105240 | Camanggahan ES | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 977665 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 | 1 | 10 | Repair of Classrooms | 5265044 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN | 2 | 1 | 5 | Repair of Classrooms | 1564738 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300799 | Digdig HS | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 1652547 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105248 | Minuli ES | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 977470 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159013 | Nagcancionan ES | CARRANGLAN | 2 | 1 | 4 | Repair of Classrooms | 2195436 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105250 | Piut ES | CARRANGLAN | 2 | 1 | 4 | Repair of Classrooms | 1300512 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105494 | Caridad Sur ES | LLANERA | 2 | 1 | 9 | Repair of Classrooms | 3035645 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105512 | Agupalo Este ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1189702 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306806 | AGUPALO WESTE HIGH SCHOOL | LUPAO | 2 | 1 | 8 | Repair of Classrooms | 2780247 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105517 | Bagong Flores ES | LUPAO | 2 | 1 | 4 | Repair of Classrooms | 1278237 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105519 | Burgos ES | LUPAO | 2 | 1 | 2 | Repair of Classrooms | 706048 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105522 | Mapangpang ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1154327 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105527 | San Antonio Este ES | LUPAO | 2 | 1 | 10 | Repair of Classrooms | 3222719 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105528 | San Antonio Weste ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1147160 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105529 | San Isidro ES | LUPAO | 2 | 1 | 10 | Repair of Classrooms | 3376702 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105532 | Sto. Domingo ES | LUPAO | 2 | 1 | 5 | Repair of Classrooms | 1291854 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306832 | Conversion IS | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1453871 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105637 | Ballesteros ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 978384 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105645 | Estrella ES | RIZAL | 2 | 1 | 7 | Repair of Classrooms | 2060493 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105651 | Pag-Asa ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1631339 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105657 | Sta. Monica ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1772208 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 6 | Repair of Classrooms | 1999768 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105196 | Bantug Elem. School | BONGABON | 3 | 1 | 4 | Repair of Classrooms | 1410620 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105197 | Bongabon CS | BONGABON | 3 | 1 | 6 | Repair of Classrooms | 2022807 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105200 | Calaanan ES | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1101363 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105201 | Camp Martyr ES | BONGABON | 3 | 1 | 4 | Repair of Classrooms | 1417666 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105202 | Cruz ES | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1121598 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105211 | R. VIJANDRE ELEMENTARY SCHOOL | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1205140 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105199 | Rosa A. Ilagan ES (Bongabon North ES) | BONGABON | 3 | 1 | 17 | Repair of Classrooms | 5314706 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105298 | Bagong Sikat ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 2119838 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105301 | Bateria ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 7 | Repair of Classrooms | 3857236 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105302 | Bugnan ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | Repair of Classrooms | 1292516 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105306 | F. Buencamino Sr. Integrated School (F. Buencamino Sr. ES) | GABALDON (BITULOK & SABANI) | 3 | 1 | 8 | Repair of Classrooms | 4129219 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105307 | Gabaldon CS | GABALDON (BITULOK & SABANI) | 3 | 1 | 8 | Repair of Classrooms | 2668145 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300805 | Gabaldon Voc'l. Agric. HS | GABALDON (BITULOK & SABANI) | 3 | 1 | 18 | Repair of Classrooms | 9421526 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105309 | Ligaya ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 9 | Repair of Classrooms | 5052082 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306814 | Ligaya National High School | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 3126062 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105311 | Pantoc ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | Repair of Classrooms | 1651240 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105312 | Pinamalisan ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | Repair of Classrooms | 2200467 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105313 | Tagumpay ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 1995274 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105346 | Azarcon ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 5 | Repair of Classrooms | 1906771 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105348 | Belen ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2088305 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105349 | Bravo ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2000947 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105350 | Burol ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2196276 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105355 | Manarog ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2062401 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105356 | Mataas Na Kahoy ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 8 | Repair of Classrooms | 2720969 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105363 | Talabutab Norte ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 8 | Repair of Classrooms | 2674755 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105364 | Talabutab Sur Elementary School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2042532 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105362 | Virginia D. Dulay Elementary School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 2 | Repair of Classroom | 927002 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105577 | Bagong Buhay ES | PALAYAN CITY (Capital) | 3 | 1 | 10 | Repair of Classrooms | 2917986 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300787 | Fort Magsaysay NHS (formerly Barangay Militar HS) | PALAYAN CITY (Capital) | 3 | 1 | 7 | Repair of Classrooms | 2134529 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105584 | Maligaya ES | PALAYAN CITY (Capital) | 3 | 1 | 10 | Repair of Classrooms | 3101159 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105587 | Marcos Village ES | PALAYAN CITY (Capital) | 3 | 1 | 5 | Repair of Classrooms | 2174495 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105592 | Sandelain ES | PALAYAN CITY (Capital) | 3 | 1 | 6 | Repair of Classrooms | 1924722 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105593 | Sapang Buho ES | PALAYAN CITY (Capital) | 3 | 1 | 8 | Repair of Classrooms | 2581288 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105747 | Berang Elementary School | SANTA ROSA | 3 | 1 | 2 | Repair of Classrooms | 801412 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159026 | Casimiro Pagsanjan Mem. Sch. | SANTA ROSA | 3 | 1 | 5 | Repair of Classrooms | 1500797 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105749 | Dr. A. Oliveros Mem. ES | SANTA ROSA | 3 | 1 | 17 | Repair of Classrooms | 4040713 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105748 | Dr. Sancho T. Manubay ES | SANTA ROSA | 3 | 1 | 8 | Repair of Classrooms | 1942623 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105750 | E. Saulo Mem. ES | SANTA ROSA | 3 | 1 | 15 | Repair of Classrooms | 4468661 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105764 | Esing T. Angeles E/S | SANTA ROSA | 3 | 1 | 3 | Repair of Classrooms | 1142500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105746 | Eulalio N. Adriano Elementary School | SANTA ROSA | 3 | 1 | 10 | Repair of Classrooms | 2839845 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105752 | La Fuente ES | SANTA ROSA | 3 | 1 | 12 | Repair of Classrooms | 3685271 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105755 | Mapalad North ES | SANTA ROSA | 3 | 1 | 9 | Repair of Classrooms | 2869216 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105756 | Mapalad Sur ES | SANTA ROSA | 3 | 1 | 7 | Repair of Classrooms | 2152139 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105758 | Pilang ES | SANTA ROSA | 3 | 1 | 3 | Repair of Classrooms | 1130434 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105760 | San Gregorio ES | SANTA ROSA | 3 | 1 | 23 | Repair of Classrooms | 6690512 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105761 | San Pedro ES | SANTA ROSA | 3 | 1 | 9 | Repair of Classrooms | 2859540 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105765 | SANTA ROSA CENTRAL SCHOOL | SANTA ROSA | 3 | 1 | 25 | Repair of Classrooms | 7017038 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105762 | Sapsap ES | SANTA ROSA | 3 | 1 | 2 | Repair of Classrooms | 801412 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105766 | Sto. Rosario ES | SANTA ROSA | 3 | 1 | 21 | Repair of Classrooms | 4801331 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4 | 1 | 20 | Repair of Classrooms | 10191999 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4 | 1 | 16 | Repair of Classrooms | 5163618 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105217 | Concepcion ES | CABIAO | 4 | 1 | 18 | Repair of Classrooms | 9488597 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105218 | Entablado ES | CABIAO | 4 | 1 | 16 | Repair of Classrooms | 8159361 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105231 | Jose Rico Cruz ES (Sta. Ines ES) | CABIAO | 4 | 1 | 4 | Repair of Classrooms | 2196301 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105219 | Maligaya ES | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3610248 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105220 | Palasinan ES | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3853712 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105221 | POLILIO ELEMENTARY SCHOOL | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3604061 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105222 | San Antonio-Bagong Buhay Elementary School | CABIAO | 4 | 1 | 12 | Repair of Classrooms | 6481726 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105224 | San Fernando Norte ES | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3221517 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105226 | San Gregorio ES | CABIAO | 4 | 1 | 3 | Repair of Classrooms | 1666450 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105227 | San Roque ES | CABIAO | 4 | 1 | 1 | Repair of Classrooms | 600667 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105228 | San Vicente Elementary School | CABIAO | 4 | 1 | 8 | Repair of Classrooms | 4081283 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105230 | St. Joseph ES | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3343879 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306823 | Sta. Isabel High School | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3179853 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105233 | Sta. Rita ES | CABIAO | 4 | 1 | 10 | Repair of Classrooms | 5255570 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105365 | Bago ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 8 | Repair of Classrooms | 2822327 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159014 | Gawad Kalinga Comm. ES (Pahalang ES) | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 714957 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105367 | Gen. Tinio East CS | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 1988904 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105368 | Gen. Tinio West Central School | GENERAL TINIO (PAPAYA) | 4 | 1 | 10 | Repair of Classrooms | 3202694 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159019 | Minalungao Elementary School | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 708056 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105370 | Padolina ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 1988486 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105588 | Palale ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 5 | Repair of Classrooms | 1689174 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105371 | Patindig-Araw ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 704885 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105372 | Pias ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 2039777 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105373 | Rio Chico ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms | 1094044 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300840 | Rio Chico National High School | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 2115010 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105439 | Lambakin ES | JAEN | 4 | 1 | 4 | Repair of Classrooms | 1220558 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105442 | Magsalisi East Elementary School | JAEN | 4 | 1 | 7 | Repair of Classrooms | 2659199 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105443 | Malabon Kaingin ES | JAEN | 4 | 1 | 3 | Repair of Classrooms | 963934 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105455 | Sapang ES | JAEN | 4 | 1 | 6 | Repair of Classrooms | 2002776 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105456 | Sta. Rita ES | JAEN | 4 | 1 | 10 | Repair of Classrooms | 2831361 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105458 | Sto. Tomas South ES | JAEN | 4 | 1 | 4 | Repair of Classrooms | 1763007 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105616 | San Josef ES | PEÑARANDA | 4 | 1 | 9 | Repair of Classrooms | 3046722 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105617 | San Mariano ES | PEÑARANDA | 4 | 1 | 3 | Repair of Classrooms | 1475181 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105667 | Maugat ES | SAN ANTONIO | 4 | 1 | 7 | Repair of Classrooms | 2589321 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105670 | San Antonio CS | SAN ANTONIO | 4 | 1 | 15 | Repair of Classrooms | 4721514 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105678 | Tikiw ES | SAN ANTONIO | 4 | 1 | 6 | Repair of Classrooms | 1858770 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105679 | Alua Elementary School | SAN ISIDRO | 4 | 1 | 18 | Repair of Classrooms | 5890306 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105680 | Barangka ES | SAN ISIDRO | 4 | 1 | 6 | Repair of Classrooms | 2453118 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105684 | Malapit West ES | SAN ISIDRO | 4 | 1 | 12 | Repair of Classrooms | 3307954 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO | 4 | 1 | 7 | Repair of Classrooms | 3167589 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105689 | Sto. Cristo ES | SAN ISIDRO | 4 | 1 | 5 | Repair of Classrooms | 1535138 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 | 1 | 14 | Repair of Classrooms | 2234453 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105737 | Mallorca ES | SAN LEONARDO | 4 | 1 | 6 | Repair of Classrooms | 2056871 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105740 | San Anton ES | SAN LEONARDO | 4 | 1 | 11 | Repair of Classrooms | 5145314 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4 | 1 | 6 | Repair of Classrooms | 1926099 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105742 | San Roque ES | SAN LEONARDO | 4 | 1 | 13 | Repair of Classrooms | 3935074 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105743 | Tagumpay Elementary School | SAN LEONARDO | 4 | 1 | 2 | Repair of Classrooms | 706072 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105744 | Tambo North E/S | SAN LEONARDO | 4 | 1 | 13 | Repair of Classrooms | 2996022 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 162002 | Amelia Heights ES | OLONGAPO CITY | 1 | 1 | 6 | Repair of Classrooms | 2253614 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 107118 | Bangal ES | OLONGAPO CITY | 1 | 1 | 6 | Repair of Classrooms | 2030302 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 301055 | Iram High School | OLONGAPO CITY | 1 | 1 | 4 | Repair of Classrooms | 1258235 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106117 | Ayala ES | MAGALANG | 1 | 1 | 8 | Repair of Classrooms | 2911636 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106118 | Balitucan ES | MAGALANG | 1 | 1 | 9 | Repair of Classrooms | 4168331 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106123 | Magalang ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1336078 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159515 | Orchard Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1178349 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106126 | Pitabacan ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 2092366 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106127 | San Agustin ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1303006 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159546 | San Isidro Resettlement ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 3376673 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106132 | San Pablo ES | MAGALANG | 1 | 1 | 5 | Repair of Classrooms | 2065701 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106134 | San Roque Es | MAGALANG | 1 | 1 | 12 | Repair of Classrooms | 5585730 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106138 | Sta Maria ES | MAGALANG | 1 | 1 | 10 | Repair of Classrooms | 5296195 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106137 | Sta. Lucia ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 2982501 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106139 | Sto Nino ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1606878 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106140 | Sto Rosario ES | MAGALANG | 1 | 1 | 5 | Repair of Classrooms | 2342476 | 1 | 1065977.99 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106142 | Turu ES | MAGALANG | 1 | 1 | 4 | Repair of Classrooms | 1821595 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105969 | Paguiruan ES | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 1820395 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105992 | Pandaguirig ES | Floridablanca | 2 | 1 | 2 | Repair of Classrooms | 725858 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106006 | Lambac ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2962178 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106008 | Maquiapo Elementary School | GUAGUA | 2 | 1 | 10 | Repair of Classrooms | 3842905 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106009 | Mauli ES | GUAGUA | 2 | 1 | 3 | Repair of Classrooms | 1349993 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2841606 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106012 | Rizal ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2599844 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106015 | San Juan ES | Guagua | 2 | 1 | 6 | Repair of Classrooms | 3021207 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106017 | San Vicente ES | GUAGUA | 2 | 1 | 9 | Repair of Classrooms | 4793869 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106022 | Graciano Paule ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2667050 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106047 | Lauc Pao ES | LUBAO | 2 | 1 | 4 | Repair of Classrooms | 1951368 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106023 | Lubao ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1105624 | 1 |  | COMPLETED | 100% | [10 empty] | Classroom to be repared use as Quarantine Facilities by DOH and LGU | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106048 | Prado Saba | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1152135 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106030 | San Miguel ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2878277 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106052 | San Pablo 1st ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1573751 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 300925 | San Pablo II NHS | LUBAO | 2 | 1 | 11 | Repair of Classrooms | 4186351 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106054 | San Pedro Palcarangan ES | LUBAO | 2 | 1 | 6 | Repair of Classrooms | 3148829 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106058 | Sta Cruz Es | LUBAO | 2 | 1 | 4 | Repair of Classrooms | 2640845 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106034 | Sta Lucia ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1086265 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106035 | Sta Maria ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2557899 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106036 | Sta. Monica Elementary School | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2509562 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159538 | Mancantian ES (Balik Barangay) | PORAC | 2 | 1 | 3 | Repair of Classrooms | 1018519 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106291 | San Basilio ES | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 2841343 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106292 | San Isidro ES | SANTA RITA | 2 | 1 | 5 | Repair of Classrooms | 2698001 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106295 | Sta. Rita CS | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 3138516 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106272 | Sasmuan ES | SASMUAN (SEXMOAN) | 2 | 1 | 6 | Repair of Classrooms | 3034203 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105884 | Cupang ES | ARAYAT | 3 | 1 | 4 | Repair of Classrooms | 2083940 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105893 | San Nicolas ES | ARAYAT | 3 | 1 | 10 | Repair of Classrooms | 5168395 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105900 | Baliti ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 3985843 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105901 | Bitas ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 3915955 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105902 | Buensuseso ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 2145280 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105903 | Cacutud ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 1135532 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105904 | Gatiawin ES | Arayat | 3 | 1 | 11 | Repair of Classrooms | 5900428 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105907 | Palinlang ES | Arayat | 3 | 1 | 2 | Repair of Classrooms | 901560 | 1 | 891625.54 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105908 | Plaza Luma ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 2182601 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105909 | San Antonio ES | Arayat | 3 | 1 | 5 | Repair of Classrooms | 2588432 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105891 | San Juan Baño ES | Arayat | 3 | 1 | 6 | Repair of Classrooms | 2812490 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105910 | Telapayong ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 1797984 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105913 | Cabalantian ES | BACOLOR | 3 | 1 | 8 | Repair of Classrooms | 3171315 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105920 | Maliwalo ES | Bacolor | 3 | 1 | 8 | Repair of Classrooms | 3171450 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105925 | San Isidro ES | Bacolor | 3 | 1 | 5 | Repair of Classrooms | 2608525 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105927 | Talba ES | Bacolor | 3 | 1 | 8 | Repair of Classrooms | 3181963 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159507 | Tinajero ES (Madapdap Resettlement ) | Bacolor | 3 | 1 | 5 | Repair of Classrooms | 2695016 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106162 | Acli ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1415064 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106165 | Buenavista ES | MEXICO | 3 | 1 | 4 | Repair of Classrooms | 2078208 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106166 | Camuning ES | MEXICO | 3 | 1 | 7 | Repair of Classrooms | 3256300 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106168 | Concepcion ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1471122 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106184 | Lagundi ES | MEXICO | 3 | 1 | 5 | Repair of Classrooms | 2107747 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106171 | Laput ES | MEXICO | 3 | 1 | 2 | Repair of Classrooms | 1045346 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106187 | Mexico CS | MEXICO | 3 | 1 | 9 | Repair of Classrooms | 5382071 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106197 | Nueva Victoria ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1582569 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106174 | Panipuan ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1540775 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106193 | San Lorenzo ES | MEXICO | 3 | 1 | 8 | Repair of Classrooms | 3512794 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106194 | San Miguel ES | MEXICO | 3 | 1 | 2 | Repair of Classrooms | 1015309 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106176 | San Patricio ES | MEXICO | 3 | 1 | 6 | Repair of Classrooms | 3044581 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106179 | Sto Rosario ES | MEXICO | 3 | 1 | 7 | Repair of Classrooms | 3449278 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106181 | Tangle ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1367609 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106278 | Fulgencio Matias ES | SANTA ANA | 3 | 1 | 3 | Repair of Classrooms | 1314340 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106276 | San Agustin ES | SANTA ANA | 3 | 1 | 3 | Repair of Classrooms | 1354876 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106277 | San Isidro ES | SANTA ANA | 3 | 1 | 10 | Repair of Classrooms | 4599156 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106281 | San Pablo ES | SANTA ANA | 3 | 1 | 8 | Repair of Classrooms | 3747918 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106279 | San Pedro - San Juan ES | SANTA ANA | 3 | 1 | 2 | Repair of Classrooms | 879693 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106284 | Sta Ana ES | SANTA ANA | 3 | 1 | 11 | Repair of Classrooms | 5131866 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106285 | Sta Lucia ES | SANTA ANA | 3 | 1 | 11 | Repair of Classrooms | 5932524 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106286 | Sta. Maria ES | STA. ANA | 3 | 1 | 3 | Repair of Classrooms | 1603918 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105867 | Balucuc ES | APALIT | 4 | 1 | 6 | Repair of Classrooms | 2808354 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105873 | Macario Arnedo ES | APALIT | 4 | 1 | 3 | Repair of Classrooms | 1524777 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105872 | Jose Escaler MES | Apalit | 4 | 1 | 5 | Repair of Classrooms | 2685200 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105944 | Pulong Palazan ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1567249 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105945 | Salapungan ES | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 2815282 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105947 | Talang ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2122329 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105950 | Vizal San Pablo I ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1588743 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105952 | Vizal San Sto Niño ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1644889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105946 | Tagulod ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1563776 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106104 | Consuelo Elementary | MACABEBE | 4 | 1 | 9 | Repair of Classrooms | 3713215 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159514 | Bebe PS | SAN LUIS | 4 | 1 | 3 | Repair of Classrooms | 1638737 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106240 | San Carlos ES | SAN LUIS | 4 | 1 | 11 | Repair of Classrooms | 5467399 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106244 | San Juan ES | SAN LUIS | 4 | 1 | 9 | Repair of Classrooms | 4459480 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106247 | San Roque Es | San Luis | 4 | 1 | 5 | Repair of Classrooms | 2570934 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106251 | Sta Rita ES | San Luis | 4 | 1 | 6 | Repair of Classrooms | 2794104 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159503 | San Juan ES | SAN SIMON | 4 | 1 | 2 | Repair of Classrooms | 1077029 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106260 | San Nicolas ES | SAN SIMON | 4 | 1 | 3 | Repair of Classrooms | 1439986 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 300938 | Sto Tomas NHS | SANTO TOMAS | 4 | 1 | 10 | Repair of Classrooms | 4420170 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 871551 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 |  | 4 | Repair of Classrooms | 1809288 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500981 | Arch. Emilio Cinense Memorial Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 986563 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500140 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2182804 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500146 | Calulut IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1659518 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500138 | City of San Fernando West IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1676821 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500147 | Del Carmen Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1595162 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107181 | Dela Paz Norte ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1551658 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107182 | Dolores ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1649456 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500136 | Lara Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1283183 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500148 | Magliman Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1476251 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500145 | Maimpis Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1457905 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 501141 | Malino Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500137 | Nuestra Senora Del Pilar IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | Repair of Classrooms | 2990792 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 301064 | Pampanga HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2102513 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107186 | Panipuan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2454314 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 307603 | Panipuan High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 873859 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500143 | Saguin Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 869145 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 163004 | San Agustin ES (Annex) | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2303703 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500149 | San Agustin IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1417557 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1574612 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107197 | San Juan South ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 5 | Repair of Classrooms | 2051615 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500142 | San Nicolas IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1475461 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107198 | San Pedro ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1584297 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107190 | Sindalan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573960 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500144 | Telebastagan Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105724 | Parang Mangga ES | San Jose City | 2 | 1 | 2 | Repair of Classrooms | 812533 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105731 | Sto. Tomas ES | San Jose City | 2 | 1 | 6 | Repair of Classrooms | 2233299 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105714 | Villa Floresta Es | San Jose City | 2 | 1 | 4 | Repair of Classrooms | 1511037 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107153 | Dulong Bayan ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 2 | Repair of Classroom | 651166 | 1 | 651165.13 | COMPLETED | 100% | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107155 | Gaya-Gaya ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | Repair of Classrooms | 5681659 | 1 | 5681658.84 | COMPLETED | 100% | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 162506 | Goldenville ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 21 | Repair of Classrooms | 5048646 | 1 | 5048645.88 | COMPLETED | 100% | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107160 | S. Palay Proper ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 11 | Repair of Classrooms | 4330492 | 1 | 4330492 | COMPLETED | 100% | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107161 | San Jose Del Monte Central School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 19 | Repair of Classrooms | 5189604 | 1 | 5189603.88 | COMPLETED | 100% | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 160004 | Dagundon ES | ANAO | 1 | 1 | 4 | Repair of Classrooms | 1962060 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106339 | Bilad ES | CAMILING | 1 | 1 | 7 | Repair of Classrooms | 2988914 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106347 | Marawi ES | Camiling | 1 | 1 | 4 | Repair of Classrooms | 1847777 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106524 | San Jose ES | MAYANTOC | 1 | 1 | 4 | Repair of Classrooms | 2032268 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106535 | San Pedro ES | MONCADA | 1 | 1 | 5 | Repair of Classrooms | 2004224 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106582 | Mabilang ES | PANIQUI | 1 | 1 | 3 | Repair of Classrooms | 1145606 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106585 | Paniqui South Central Elementary School | PANIQUI | 1 | 1 | 1 | Repair of Classroom | 707901 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106672 | Macaguing Primary School | SANTA IGNACIA | 1 | 1 | 2 | Repair of Classrooms | 912404 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300979 | Pilpila NHS | Sta. Ignacia | 1 | 1 | 2 | Repair of Classrooms | 905247 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4393346 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106463 | Ayson ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 970716 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106464 | Bawa ES | GERONA | 2 | 1 | 7 | Repair of Classrooms | 2926749 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106446 | Carbonel ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 1085370 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106447 | Caturay ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 1916555 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106450 | Gabaldon ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4363042 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | 9 | Repair of Classrooms | 3696798 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106452 | Magaspac ES | GERONA | 2 | 1 | 5 | Repair of Classrooms | 2625334 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106472 | Matapitap ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 836651 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106474 | New Salem ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 954870 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106477 | Pinasling ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 1601166 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106455 | Quezon ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4621090 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | 9 | Repair of Classrooms | 4189987 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106480 | San Agustin ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 2177557 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106482 | San Bartolome ES | GERONA | 2 | 1 | 3 | Repair of Classrooms | 1351848 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300986 | San Jose NHS | GERONA | 2 | 1 | 8 | Repair of Classrooms | 2905787 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106641 | Pao ES | SAN JOSE | 2 | 1 | 8 | Repair of Classrooms | 3882486 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106776 | Bantog ES | VICTORIA | 2 | 1 | 3 | Repair of Classrooms | 1480642 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106367 | Angelina Dizon Jimenez ES (Sto. Domingo ES) | CAPAS | 3 | 1 | 3 | Repair of Classrooms | 1478216 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106393 | Cafe ES | CONCEPCION | 3 | 1 | 6 | Repair of Classrooms | 2621875 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106539 | Demetrio F. Nagtalon ES | Moncada | 1 | 1 | 3 | Repair of Classrooms | 1290975 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106540 | Villa PS | Moncada | 1 | 1 | 2 | Repair of Classrooms | 837845 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106570 | San Isidro ES | Paniqui | 1 | 1 | 10 | Repair of Classrooms | 4147472 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106592 | Buenavista ES | PURA | 1 | 1 | 10 | Repair of Classrooms | 4275159 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106613 | Serrano PS | RAMOS | 1 | 1 | 1 | Repair of Classroom | 494268 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1 | 1 | 8 | Repair of Classrooms | 3526330 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106616 | Bamban ES | San Clemente | 1 | 1 | 1 | Repair of Classroom | 558252 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106619 | Doclong 1st ES | San Clemente | 1 | 1 | 3 | Repair of Classrooms | 1658198 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300985 | San Felipe HS | San Manuel | 1 | 1 | 9 | Repair of Classrooms | 4185564 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106661 | San Manuel | San Manuel | 1 | 1 | 2 | Repair of Classrooms | 795279 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106686 | Taguiporo-Cabaruan ES | Sta. Ignacia | 1 | 1 | 3 | Repair of Classrooms | 1412459 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac City | 106694 | San Nicolas ES | CITY OF TARLAC (Capital) | 2 | 1 | 24 | Repair of Classrooms | 1687448 | 1 | 1687447.61 | COMPLETED | 100% |  |  |  |  | Nov. 26, 2019 | Dec. 2,2019 | Dec. 10, 2019 | Dec. 17, 2019 |  | Boycing Construction Services | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac City | 106721 | Sepung Calzada Panampunan ES | CITY OF TARLAC (Capital) | 2 | 1 | 13 | Repair of Classrooms | 2726781 | 1 | 2726780.78 | COMPLETED | 100% |  |  |  |  | Nov. 26, 2019 | Dec. 2,2019 | Dec. 10, 2019 | Dec. 17, 2019 |  | J.P Aquino Construction | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106864 | San Isidro Elementary School | CASTILLEJOS | 1 | 1 | 9 | Repair of Classrooms | 3518889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106837 | Sta. Rita Elementary School | CABANGAN | 2 | 1 | 6 | Repair of Classrooms | 2748889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106849 | San Roque Elementary School | CANDELARIA | 2 | 1 | 8 | Repair of Classrooms | 2938889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106881 | Sta. Barbara Elementary School | IBA (Capital) | 2 | 1 | 8 | Repair of Classrooms | 3668889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 301005 | Bani National High School | MASINLOC | 2 | 1 | 10 | Repair of Classrooms | 5388889 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106920 | Angel C. Manglicmot Mem. Elementary School | SAN ANTONIO | 2 | 1 | 8 | Repair of Classrooms | 2924426 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Antipolo City | 109339 | San Isidro ES |  | 1 | 1 | 17 | Repair of Classrooms | 3736502 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Antipolo City | 109347 | Binayoyo ES | CITY OF ANTIPOLO | 2 | 1 | 12 | Repair of Classrooms | 2281358 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2 | 1 | 33 | Repair of Classrooms | 7994549.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Antipolo City | 109338 | Peñafrancia ES Annex | CITY OF ANTIPOLO | 2 | 1 | 6 | Repair of Classrooms | 1859001 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Antipolo City | 109357 | Rizza ES | CITY OF ANTIPOLO | 2 | 1 | 8 | Repair of Classrooms | 1205668 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107403 | Dayapan ES | LEMERY | 1 | 1 | 4 | Repair of Classrooms | 813141 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107392 | Talaga Elementary School | LEMERY | 1 | 1 | 15 | Repair of Classrooms | 6362453 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107825 | Gregorio Agoncillo Elementary School | TUY | 1 | 1 | 13 | Repair of Classrooms | 5441535 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107202 | Agoncillo Central School | AGONCILLO | 3 | 1 | 3 | Repair of Classrooms | 882972 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 307705 | Agoncillo National High School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1549056 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107205 | Banyaga Elementary School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1206729 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 301076 | Banyaga National High School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1226698 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107207 | Bilibinwang Elementary School | AGONCILLO | 3 | 1 | 2 | Repair of Classrooms | 616467 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107212 | Pook Elementary School | AGONCILLO | 3 | 1 | 9 | Repair of Classrooms | 616467 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107213 | Subic Elementary School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 959460 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107338 | Col. Pedro Pasia Memorial School | CUENCA | 3 | 1 | 19 | Repair of Classrooms | 5539065 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 301100 | Fermin La Rosa National High School | CUENCA | 3 | 1 | 12 | Repair of Classrooms | 2074812 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107367 | As-Is Elementary School | LAUREL | 3 | 1 | 4 | Repair of Classrooms | 1557093 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107370 | Bignay Primary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 603365 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107371 | Bugaan Integrated School | LAUREL | 3 | 1 | 7 | Repair of Classrooms | 2089701 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107372 | Buso-Buso Elementary School | LAUREL | 3 | 1 | 9 | Repair of Classrooms | 2648916 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107374 | Laurel Central School | LAUREL | 3 | 1 | 11 | Repair of Classrooms | 5112153 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 163517 | Martin Esperanza Elementary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 591592 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107377 | Niyugan Elementary School | LAUREL | 3 | 1 | 5 | Repair of Classrooms | 2432662 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107378 | Paliparan Elementary School | LAUREL | 3 | 1 | 3 | Repair of Classrooms | 1204785 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107380 | San Gabriel Elementary School | LAUREL | 3 | 1 | 5 | Repair of Classrooms | 2360701 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107383 | Sta. Maria Elementary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 1234099 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas | 107572 | Rosario West Central School | ROSARIO | 4 | 1 | 13 | Repair of Classrooms | 6376574 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109587 | Banaba South ES | BATANGAS CITY (Capital) | 5 | 1 | 8 | Repair of Classrooms | 2560001 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109546 | Bilogo ES | BATANGAS CITY (Capital) | 5 | 1 | 5 | Repair of Classrooms | 1600000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109564 | Dela Paz Itaas ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1000335 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109603 | Dumuclay ES | BATANGAS CITY (Capital) | 5 | 1 | 7 | Repair of Classrooms | 2147232 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109617 | Lilinggiwan ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | Repair of Classrooms | 652643 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109579 | Talahib Payapa ES | BATANGAS CITY (Capital) | 5 | 1 | 4 | Repair of Classrooms | 1342702 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109557 | Talumpok Proper ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 998072 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Batangas City | 109580 | Tibig ES | BATANGAS CITY (Capital) | 5 | 1 | 6 | Repair of Classrooms | 1972311 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Binan City | 164511 | Dr. Jose Tamayo MES | CITY OF BIÑAN | 5 | 1 | 8 | Repair of Classrooms | 507252 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Binan City | 108227 | Platero ES | CITY OF BIÑAN | 5 | 1 | 22 | Repair of Classrooms | 3106003 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Binan City | 108229 | San Vicente ES | CITY OF BIÑAN | 5 | 1 | 27 | Repair of Classrooms | 3583812 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Binan City | 108215 | Tomas A. Turalba Memorial Elementary | CITY OF BIÑAN | 5 | 1 | 8 | Repair of Classrooms | 1006701 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Binan City | 164512 | Zapote ES | CITY OF BIÑAN | 5 | 1 | 10 | Repair of Classrooms | 1443118 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cabuyao City | 108234 | Baclaran Elementary School | CABUYAO | 2 | 1 | 8 | Repair of Classrooms | 3796819 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cabuyao City | 108238 | Butong Elementary School | CABUYAO | 2 | 1 | 4 | Repair of Classrooms | 1936897 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cabuyao City | 108243 | Gulod Elementary School | CABUYAO | 2 | 1 | 4 | Repair of classrooms/toilets | 1714134 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Calamba City | 109816 | Jose Platon MS | CITY OF CALAMBA | 2 | 1 | 15 | Repair of Classrooms | 3025658 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Calamba City | 109833 | Looc ES | CITY OF CALAMBA | 2 | 1 | 21 | Repair of Classrooms | 2606952 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Calamba City | 109858 | Punta Elementary School | CITY OF CALAMBA | 2 | 1 | 12 | Repair of Classrooms | 2340802 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Calamba City | 109838 | San Juan Elementary School | CITY OF CALAMBA | 2 | 1 | 7 | Repair of Classrooms | 1114794 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Calamba City | 109863 | Ulango Elementary School | CITY OF CALAMBA | 2 | 1 | 4 | Repair of Classrooms | 1329429 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107937 | Bulihan ES | GMA | 5 | 1 | 8 | Repair of Classrooms | 3518909 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107939 | Family Village Resources ES | GMA | 5 | 1 | 4 | Repair of Classrooms | 2080029 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301202 | Lumil NHS | Silang | 5 | 1 | 8 | Repair of Classrooms | 4328589 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108116 | Mataas na Burol ES | Silang | 5 | 1 | 2 | Repair of Classrooms | 1065511 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301199 | Lucsuhin NHS | Alfonso | 7 | 1 | 4 | Repair of Classrooms | 1762538 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107860 | Loma ES | Amadeo | 7 | 1 | 6 | Repair of Classrooms | 3244084 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301217 | Talon National High School | Amadeo | 7 | 1 | 12 | Repair of Classrooms | 5659631 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108003 | Agus-Os ES | Indang | 7 | 1 | 6 | Repair of Classrooms | 2730777 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301167 | Amaya Sch. of Home Industries | Tanza | 7 | 1 | 16 | Repair of Classrooms | 6753518 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301219 | Tanza National Trade School | Tanza | 7 | 1 | 12 | Repair of Classrooms | 6782126 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108179 | Bagong Pook ES | Trece Martires City | 7 | 1 | 8 | Repair of Classrooms | 3528386 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108180 | Conchu ES | Trece Martires City | 7 | 1 | 10 | Repair of Classrooms | 4943386 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108184 | Lapidario ES | Trece Martires City | 7 | 1 | 13 | Repair of Classrooms | 5864012 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108185 | Osorio ES | Trece Martires City | 7 | 1 | 18 | Repair of Classrooms | 8564806 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 164014 | Southville ES | Trece Martires City | 7 | 1 | 10 | Repair of Classrooms | 4355169 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301165 | Alfonso National High School | Alfonso | 8 | 1 | 8 | Repair of Classrooms | 5018720 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107841 | Bilog ES | Alfonso | 8 | 1 | 6 | Repair of Classrooms | 3261082 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107843 | Esperanza ES | Alfonso | 8 | 1 | 6 | Repair of Classrooms | 3360912 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107934 | Narvaez ES | GEA | 8 | 1 | 2 | Repair of Classrooms | 1181930 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 107935 | Tabora ES | GEA | 8 | 1 | 2 | Repair of Classrooms | 1178657 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108041 | Layong Mabilog ES | Maragondon | 8 | 1 | 2 | Repair of Classrooms | 1106870 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108043 | Maragondon ES | Maragondon | 8 | 1 | 12 | Repair of Classrooms | 5957416 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301204 | Maragondon NHS | Maragondon | 8 | 1 | 15 | Repair of Classrooms | 7685021 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 108040 | Marcelo D. Samaniego ES (former Bucal IV ES) | Maragondon | 8 | 1 | 3 | Repair of Classrooms | 1674148 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite | 301169 | Constancio E. Aure Sr. NHS (Asis NHS) | Mendez | 8 | 1 | 12 | Repair of Classrooms | 6098488 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite City | 109635 | Dalahican Elem. School | CAVITE CITY | 1 | 1 | 4 | Repair of Classrooms | 2150367 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Cavite City | 109633 | Ovidio S. Dela Rosa ES | CAVITE CITY | 1 | 1 | 4 | Repair of Classrooms | 1039842 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Dasmarinas City | 301187 | Pag-asa NHS (Dasmarinas NHS - Pag-asa Annex) | CITY OF DASMARIÑAS | 4 | 1 | 6 | Repair of Classrooms | 1815112 | 1 | 1815111.48 | COMPLETED | 100% | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Dasmarinas City | 107912 | Salawag ES | CITY OF DASMARIÑAS | 4 | 1 | 14 | Repair of Classrooms | 4599517 | 1 | 4599516.34 | COMPLETED | 100% | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Dasmarinas City | 107914 | Z. H. Gana Mem. Sch. (San Jose) | CITY OF DASMARIÑAS | 4 | 1 | 4 | Repair of Classrooms | 1278118 | 1 | 1278117.33 | COMPLETED | 100% | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Gen. Trias City | 107944 | Angel L. Bawalan ES (Alingaro ES) | CITY OF GENERAL TRIAS | 6 | 1 | 5 | Repair of Classrooms | 2718895 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Gen. Trias City | 107959 | Diego Mojica MS | CITY OF GENERAL TRIAS | 6 | 1 | 15 | Repair of Classrooms | 7358248 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Gen. Trias City | 107947 | Gen. Trias MES | CITY OF GENERAL TRIAS | 6 | 1 | 11 | Repair of Classrooms | 4946085 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Gen. Trias City | 107950 | Luis Ferrer III MES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 2522689 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Gen. Trias City | 107951 | Manggahan ES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 3400058 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Imus City | 107969 | Anabu II Elementary School | IMUS | 3 | 1 | 14 | Repair of Classrooms | 4926134 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Imus City | 107974 | Imus Pilot Elementary School | IMUS | 3 | 1 | 4 | Repair of Classrooms | 1748352 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108429 | Sampaguita Village ES | SAN PEDRO | 1 | 1 | 8 | Repair of Classrooms | 3458474 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 307907 | San Pedro Relocation Center NHS, Main (Langgam) Campus | SAN PEDRO | 1 | 1 | 21 | Repair of Classrooms | 8878108 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108201 | Bitin ES | BAY | 2 | 1 | 7 | Repair of Classrooms | 2852805 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108203 | Maitim ES | BAY | 2 | 1 | 3 | Repair of Classrooms | 1296378 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108210 | Sto. Domingo ES | BAY | 2 | 1 | 10 | Repair of Classrooms | 3948040 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3 | 1 | 10 | Repair of Classrooms | 3861753 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108253 | Balayhangin ES | CALAUAN | 3 | 1 | 8 | Repair of Classrooms | 3024363 | 1 |  | COMPLETED | 100% |  |  |  |  | 2018-11-23 | 2018-12-14 | 2019-12-27 | 2019-08-02 | 2019-08-09 | MICLOVER GEN. CONSTRUCTION & IRON WORKS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108351 | Abo- Bukal ES | NAGCARLAN | 3 | 1 | 10 | Repair of Classrooms | 3780806 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108359 | Labangan ES | NAGCARLAN | 3 | 1 | 4 | Repair of Classrooms | 1457353 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108373 | Yukos ES Annex | NAGCARLAN | 3 | 1 | 6 | Repair of Classrooms | 2707348 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 301248 | Lumot NHS | CAVINTI | 4 | 1 | 13 | Repair of Classrooms | 5333167 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108282 | Talaongan West ES | CAVINTI | 4 | 1 | 2 | Repair of Classrooms | 792989 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108296 | F.S. Brosas MES | LILIW | 4 | 1 | 5 | Repair of Classrooms | 1832132 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108323 | Balubad ES | LUMBAN | 4 | 1 | 2 | Repair of Classrooms | 822837 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108324 | Caliraya ES | LUMBAN | 4 | 1 | 3 | Repair of Classrooms | 1076827 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108293 | E.G. Olarte ES | MABITAC | 4 | 1 | 3 | Repair of Classrooms | 1222658 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 164504 | San Miguel ES | MABITAC | 4 | 1 | 4 | Repair of Classrooms | 730364 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 164531 | Munting Kawayan ES | MAJAYJAY | 4 | 1 | 1 | Repair of Classroom | 376471 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 301268 | Sta. Catalina NHS | MAJAYJAY | 4 | 1 | 5 | Repair of Classrooms | 2654182 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108350 | Suba ES | MAJAYJAY | 4 | 1 | 3 | Repair of Classrooms | 1194039 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108375 | Paete CES | PAETE | 4 | 1 | 16 | Repair of Classrooms | 5833108 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108382 | M. Z. Lanuza ES | PAGSANJAN | 4 | 1 | 2 | Repair of Classrooms | 841515 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108387 | San Isidro ES | PAGSANJAN | 4 | 1 | 6 | Repair of Classrooms | 2376771 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108388 | Unson ES | PAGSANJAN | 4 | 1 | 4 | Repair of Classrooms | 1444867 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108397 | J.Z. Fernandez MES | PAKIL | 4 | 1 | 3 | Repair of Classrooms | 1179649 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108406 | Concepcion-Mojon E/S | PILA | 4 | 1 | 7 | Repair of Classrooms | 2475101 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108420 | Cuyab ES | SAN PEDRO | 4 | 1 | 7 | Repair of Classrooms | 2872892 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 342346 | Laguna SHS | SANTA CRUZ | 4 | 1 | 1 | Repair of Classroom | 612269 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108443 | Palasan ES | SANTA CRUZ | 4 | 1 | 8 | Repair of Classrooms | 3395768 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 164507 | New Little Baguio ES | SANTA MARIA | 4 | 1 | 2 | Repair of Classrooms | 761982 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108464 | PARANG NG BUHO ELEM. SCHOOL | SANTA MARIA | 4 | 1 | 4 | Repair of Classrooms | 1521878 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Laguna | 108493 | Palanas ES | SINILOAN | 4 | 1 | 4 | Repair of Classrooms | 1540458 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109658 | Abundio Torre Memorial Elementary School | LIPA CITY | 4 | 1 | 8 | Repair of Classrooms | 1397581 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 4 | 1 | 6 | Repair of Classrooms | 3643773 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109660 | Bulacnin ES | Lipa City | 4 | 1 | 5 | Repair of Classrooms | 1273544 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 301489 | Bulacnin NHS | Lipa City | 4 | 1 | 23 | Repair of Classrooms | 4986899 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 4 | 1 | 17 | Repair of Classrooms | 4955247 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 4 | 1 | 2 | Repair of Classrooms | 936336 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109695 | Paninsingin ES | LIPA CITY | 4 | 1 | 7 | Repair of Classrooms | 2933558 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109687 | San Sebastian ES | LIPA CITY | 4 | 1 | 3 | Repair of Classrooms | 1703412 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109705 | Tangway Loob ES | LIPA CITY | 4 | 1 | 8 | Repair of Classrooms | 3772262 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 301488 | Bugtongnapulo NHS | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6101653 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109674 | Cumba-Quezon ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2420000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109681 | Malagonlong ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1024241 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109654 | Sto. Niño ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 1498468 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109655 | Sto. Toribio ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2574861 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lipa City | 109704 | Tangway ES | LIPA CITY | 6 | 1 | 17 | Repair of Classrooms | 2010303 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 109730 | Dalahican Elementary School | LUCENA CITY (Capital) | 2 | 1 | 10 | Repair of Classrooms | 4097038 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 167503 | Dalahican ES Annex | LUCENA CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1319563 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 109741 | Domoit Elementary School | LUCENA CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 2457753 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 308503 | Gulang-Gulang NHS | LUCENA CITY (Capital) | 2 | 1 | 22 | Repair of Classrooms | 8145631 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 109737 | Ibabang Iyam ES | LUCENA CITY (Capital) | 2 | 1 | 11 | Repair of Classrooms | 3858173 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 | 1 | 16 | Repair of Classrooms | 5279994 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 109714 | Lucena East VII Elementary School | LUCENA CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 2319110 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Lucena City | 109732 | Lucena South II Elementary School | LUCENA CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 4647094 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108562 | Cabugao ES | BURDEOS | 1 | 1 | 5 | Repair of Classrooms | 3416495 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108786 | Gumian ES | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 894813 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108789 | Libjo Elementary School | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 1164616 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108983 | Gango ES | JOMALIG | 1 | 1 | 4 | Repair of Classrooms | 2797662 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108891 | Concepcion ES | MAUBAN | 1 | 1 | 5 | Repair of Classrooms | 1376750 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108636 | Candelaria Elementary School 1 & 2 | CANDELARIA | 2 | 1 | 12 | Repair of Classrooms | 3539600 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108618 | KINATIHAN II ES | CANDELARIA | 2 | 1 | 7 | Repair of Classrooms | 2592006 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108678 | Don Eulogio Capino ES | DOLORES | 2 | 1 | 6 | Repair of Classrooms | 2216058 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108679 | Don Eulogio Capino ES Annex (Putol) | DOLORES | 2 | 1 | 5 | Repair of Clas+R357+N355 | 2026980 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108682 | Pedro Bombane ES | DOLORES | 2 | 1 | 3 | Repair of classrooms/toilets | 926963 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 109112 | San Antonio CS | SAN ANTONIO | 2 | 1 | 7 | Repair of Classrooms | 2929484 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 165001 | Bagong Silang ES | BUENAVISTA | 3 | 1 | 6 | Repair of Classrooms | 3214035 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108536 | Batabat ES | BUENAVISTA | 3 | 1 | 4 | Repair of classrooms/toilets | 1883276 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108555 | Villa Veronica ES | BUENAVISTA | 3 | 1 | 1 | Repair of Classroom | 564648 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS - Tagabas Ibaba Ext) | CATANAUAN | 3 | 1 | 3 | Repair of Classrooms | 1225610 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 301282 | Ajos National High School | MULANAY | 3 | 1 | 8 | Repair of Classrooms | 3681693 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108924 | Burgos ES | MULANAY | 3 | 1 | 7 | Repair of Classrooms | 2904311 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 301394 | San Isidro NHS, Padre Burgos | PADRE BURGOS | 3 | 1 | 8 | Repair of Classrooms | 3419402 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 109125 | Look Awasan ES | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | Repair of Classrooms | 3443009 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 109141 | Busokbusokan Elementary School | SAN NARCISO | 3 | 1 | 1 | Repair of Classroom | 605617 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 8 | Repair of Classrooms | 2516266 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108521 | Malusak ES | ATIMONAN | 4 | 1 | 10 | Repair of Classrooms | 5296233 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108597 | Cunalum ES | CALAUAG | 4 | 1 | 2 | Repair of Classrooms | 1334835 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108606 | Pinagkamaligan ES | CALAUAG | 4 | 1 | 3 | Repair of Classrooms | 1402288 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108752 | Bamban ES | GUMACA | 4 | 1 | 3 | Repair of Classrooms | 1759020 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Quezon | 108815 | Rosario ES | LOPEZ | 4 | 1 | 1 | Repair of Classroom | 459795 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109311 | Dona Nieves Songco MES | Angono | 1 | 1 | 4 | Repair of Classrooms | 1158203 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109374 | Bangad ES | Binangonan | 1 | 1 | 9 | Repair of Classrooms | 3293120 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 301445 | Janosa NHS | Binangonan | 1 | 1 | 6 | Repair of Classrooms | 2689105 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109369 | Macamot ES | BINANGONAN | 1 | 1 | 6 | Repair of Classrooms | 1997198 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109371 | Pilapila ES | Binangonan | 1 | 1 | 8 | Repair of Classrooms | 3000675 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109399 | Francisco P. Felix ES Unit 1 | CAINTA | 1 | 1 | 12 | Repair of classrooms | 3456558 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109406 | Saint Anthony ES | CAINTA | 1 | 1 | 19 | Repair of classrooms | 5015368 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109409 | San Juan Elementary School | CAINTA | 1 | 1 | 6 | Repair of classrooms | 902993 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109411 | St. Joseph ES | CAINTA | 1 | 1 | 6 | Repair of classrooms | 772619 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109542 | San Francisco ES | Taytay | 1 | 1 | 4 | Repair of Classrooms | 989591 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109533 | Sta. Ana ES | Taytay | 1 | 1 | 8 | Repair of Classrooms | 2147633 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109427 | Malalim ES | Baras | 2 | 1 | 9 | Repair of Classrooms | 1938313 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109421 | Subay ES | Cardona | 2 | 1 | 5 | Repair of Classrooms | 2157759 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 308120 | Jalajala NHS | Jalajala | 2 | 1 | 8 | Repair of Classrooms | 2197501 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 165503 | Hulo ES | Pililla | 2 | 1 | 8 | Repair of Classrooms | 2549915 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109452 | Matagbak ES | Pililla | 2 | 1 | 2 | Repair of Classrooms | 777922 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109470 | Macabud ES | Rodriguez | 2 | 1 | 8 | Repair of Classrooms | 1485871 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 301449 | Mascap NHS | Rodriguez | 2 | 1 | 4 | Repair of Classrooms | 1786744 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 301451 | Montalban Heights NHS | Rodriguez | 2 | 1 | 14 | Repair of Classrooms | 4147244 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 301460 | Jose F. Diaz MNHS | San Mateo | 2 | 1 | 3 | Repair of Classrooms | 1154908 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 109502 | Cayabu ES | Tanay | 2 | 1 | 1 | Repair of Classroom | 348116 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 308138 | Tanay West NHS | TANAY | 2 | 1 | 12 | Repair of Classrooms | 2565674 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Rizal | 308123 | Pantay NHS | Teresa | 2 | 1 | 10 | Repair of Classrooms | 2403242 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109788 | C.M. Azcarate Elementary School | SAN PABLO CITY | 3 | 1 | 10 | Repair of Classrooms | 4280501 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109781 | Fule Almeda Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms & Covered Pathway | 2407838 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109782 | Major Juan Eseo Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms | 3961119 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | SAN PABLO CITY | 3 | 1 | 3 | Repair of Classrooms & Covered Pathway | 3046850 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109769 | San Crispin Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms | 3489626 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 301503 | San Cristobal National High School | SAN PABLO CITY | 3 | 1 | 6 | Repair of Classrooms & Covered Pathway | 3487254 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109808 | San Diego Elementary School | SAN PABLO CITY | 3 | 1 | 1 | Repair of Classrooms & Covered Pathway | 1579633 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | San Pablo City | 109754 | San Gabriel Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms & Covered Pathway | 4071014 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 6 | Repair of Classrooms | 2836803 | 1 | 628546.8 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-002 | R4A-STA.ROSA-2019-01 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108484 | Sinalhan Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 584002 | 1 | 555634.92 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Sta. Rosa City | 251501 | Southville 4 Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 770721 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108485 | Tagapo Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 830666 | 1 | 555634.92 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 321602 | BALELE HIS | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 2702927 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107769 | NATATAS ES | CITY OF TANAUAN | 3 | 1 | 5 | Repair of Classrooms | 1838936 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107746 | Ambulong ES | CITY OF TANAUAN | 3 | 1 | 13 | Repair of Classrooms | 6592443 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107750 | Banadero ES | CITY OF TANAUAN | 3 | 1 | 7 | Repair of Classrooms | 4180287 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107755 | BOOT ES | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 3547896 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107758 | GONZALES ES | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 4727664 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107759 | Hidalgo Elementary School | CITY OF TANAUAN | 3 | 1 | 6 | Repair of Classrooms | 1015976 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107761 | JANOPOL ORIENTAL ES | CITY OF TANAUAN | 3 | 1 | 10 | Repair of Classrooms | 4731762 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107766 | MARIA PAZ ES | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 5934108 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107767 | MAUGAT ELEMENTARY SCHOOL | CITY OF TANAUAN | 3 | 1 | 1 | Repair of Classroom | 669396 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 301128 | NATATAS NATIONAL HIGH SCHOOL | CITY OF TANAUAN | 3 | 1 | 6 | Repair of Classrooms | 2345842 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107780 | Paaralang Sentral ng Talaga | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 3195329 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107780 | Paaralang Sentral ng Talaga | CITY OF TANAUAN | 3 |  | 6 | Repair of Classrooms | 394703 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107773 | Sala ES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 2817668 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 301154 | TANAUAN SCHOOL OF FISHERIES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 4411730 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 107787 | WAWA ES | CITY OF TANAUAN | 3 | 1 | 3 | Repair of Classrooms | 1763211 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tanauan City | 301163 | Wawa NHS | CITY OF TANAUAN | 3 | 1 | 4 | Repair of Classrooms | 1922021 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1 | 1 | 4 | Repair of Classrooms | 1571379 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1 | 1 | 4 | Repair of Classrooms | 1760000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-A | Tayabas City | 301381 | Rosario Quesada Mem. NHS | CITY OF TAYABAS | 1 | 1 | 8 | Repair of Classrooms | 2931720 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Calapan City | 111535 | Bulusan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1415523 | 1 | 1415523 | COMPLETED | 100% | 2021-02-11 | 2021-02-15 | N/A | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Calapan City | 111545 | Salong Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | Repair of Classroom | 475673 | 1 | 475673 | COMPLETED | 100% | 2021-02-11 | 2021-02-15 | N/A | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Calapan City | 111547 | Silonay ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2685813 | 1 | 2685813 | COMPLETED | 100% | 2021-02-11 | 2021-02-15 | N/A | 2020-019 | 2019-11-07 | 2019-11-29 | 2019-12-11 | 2019-12-19 | 2020-09-28 | KARANGYAN BUILDERS AND TRADERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109865 | Agot ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 297000 | 1 | 291967.5 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109884 | Amoingon ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 675000 | 1 | 665245.78 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109885 | Balagasan ES | BOAC (Capital) | 0 | 1 | 5 | Repair of Classrooms | 773000 | 1 | 764237.51 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109886 | Balaring-Caganhao ES | BOAC (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1933000 | 1 | 1885073.89 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109867 | Balimbing ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 432000 | 1 | 426212.23 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109888 | Bangbangalon ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 508000 | 1 | 500584.7 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109868 | Bantauyan PS | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 632000 | 1 | 622068.79 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109889 | Bantay ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 539000 | 1 | 533019.43 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109892 | Boi ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 404000 | 1 | 394368.57 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109869 | Buliasnin ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 699000 | 1 | 688711.73 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109893 | Canat ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 699000 | 1 | 690931.48 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109871 | Hinapulan ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 787000 | 1 | 776584.3 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109872 | Lupac-Tabigue ES | BOAC (Capital) | 0 | 1 | 12 | Repair of Classrooms | 1760000 | 1 | 1703521.64 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109874 | Maligaya ES | BOAC (Capital) | 0 | 1 | 2 | Repair of Classrooms | 329000 | 1 | 325103.61 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109875 | Pawa ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 421000 | 1 | 416841.96 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109878 | Poras ES | BOAC (Capital) | 0 | 1 | 15 | Repair of Classrooms | 8714094 | 1 | 8531773.04 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109880 | Puyog ES | BOAC (Capital) | 0 | 1 | 3 | Repair of Classrooms | 829000 | 1 | 809404.96 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109881 | Sawi ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 172000 | 1 | 170057.74 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109882 | Tanza ES | BOAC (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1425000 | 1 | 1381910.99 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109883 | Tumagabok ES | BOAC (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1359000 | 1 | 1318907.69 | COMPLETED | 100% | 2021-09-09 | [7 empty] | 2021-01-12 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 301561 | Sayao NHS | MOGPOG | 0 | 1 | 6 | Repair of Classrooms | 1702423 | 1 | 1675251.92 | COMPLETED | 100% | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 110002 | Makulapnit ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 3877194 | 1 | 3815939.26 | COMPLETED | 100% | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 109968 | Masalukot ES | SANTA CRUZ | 0 | 1 | 2 | Repair of Classrooms | 2059805 | 1 | 2013292.22 | COMPLETED | 100% | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Marinduque | 301563 | Tagum NHS | SANTA CRUZ | 0 | 1 | 8 | Repair of Classrooms | 4659654 | 1 | 4393285.75 | COMPLETED | 100% | 2021-08-31 | [7 empty] | 2021-01-04 | GS MOTAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110080 | Bulangcog ES | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1883062 | 1 | 1881767.04 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110091 | New Dagupan ES | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1903503 | 1 | 1902146.31 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110090 | Poypoy Elementary School | CALINTAAN | 0 | 1 | 6 | Repair of Classrooms | 1897071 | 1 | 1877504.53 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110131 | Guballa ES | MAGSAYSAY | 0 | 1 | 6 | Repair of Classrooms | 1999086 | 1 | 1997544.35 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110258 | Curanta ES | SAN JOSE | 0 | 1 | 4 | Repair of Classrooms | 1283416 | 1 | 1281441.72 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Occidental Mindoro | 110263 | La Curva ES | SAN JOSE | 0 | 1 | 6 | Repair of Classrooms | 1929434 | 1 | 1927130.12 | COMPLETED | 100% | 2021-01-25 | 2021-01-15 | N/A |  | Sept.20,2020 | Sept.27,2020 | Oct.11,2020 | Oct.18,2020 | Oct.25,2020 | hawkstow construction and development | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110330 | Felix Hernandez MS | BACO | 1 | 1 | 7 | Repair of Classrooms | 2481425 | 1 | 2481424.93 | COMPLETED | 100% | 2020-03-16 | 2021-02-09 | REPAIR 2020 - R IVB - Oriental Mindoro-030 | 009-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | Kasanga Const. and Supplies | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110516 | Karumangit ES | NAUJAN | 1 | 1 | 7 | Repair of Classrooms | 1753519 | 1 | 1753518.05 | COMPLETED | 100% | 2020-03-17 | 2021-03-11 | REPAIR 2020 - R IVB - Oriental Mindoro-034 | 010-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | CMSEL Const. & Developer | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110521 | Masagana ES | NAUJAN | 1 | 1 | 5 | Repair of Classrooms | 1818210 | 1 | 1818209.57 | COMPLETED | 100% | 2020-03-17 | 2021-03-11 | REPAIR 2020 - R IVB - Oriental Mindoro-035 | 010-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | CMSEL Const. & Developer | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110594 | CASILIGAN ELEMENTARY SCHOOL | POLA | 1 | 1 | 11 | Repair of Classrooms | 3410706 | 1 | 3410705.24 | COMPLETED | 100% | 2020-03-16 | 2021-02-24 | REPAIR 2020 - R IVB - Oriental Mindoro-042 | 011-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | ETVR Trading & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110697 | LOYAL ELEMENTARY SCHOOL | VICTORIA | 1 | 1 | 8 | Repair of Classrooms | 2966591 | 1 | 2966590.5641 | COMPLETED | 100% | 2020-03-17 | 2021-02-17 | REPAIR 2020 - R IVB - Oriental Mindoro-039 | 012-2020 | 2019-11-20 | 2019-11-27 | 2020-03-12 | 2020-05-28 | 2020-11-09 | DK Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110432 | Agsalin ES | GLORIA | 2 | 1 | 5 | Repair of Classrooms | 2020000 | 1 | 2020000 | COMPLETED | 100% | 2020-03-17 | 2021-01-22 | REPAIR 2020 - R IVB - Oriental Mindoro-012 | 013-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 170040 | BULAKLAKAN ELEMENTARY SCHOOL | GLORIA | 2 | 1 | 1 | Repair of Classroom | 555000 | 1 | 555000 | COMPLETED | 100% | 2020-03-17 | 2021-01-22 | REPAIR 2020 - R IVB - Oriental Mindoro-038 | 013-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110444 | Langgang ES | GLORIA | 2 | 1 | 6 | Repair of Classrooms | 2088323 | 1 | 2088322.0363 | COMPLETED | 100% | 2020-03-16 | 2021-01-20 | REPAIR 2020 - R IVB - Oriental Mindoro-009 | 014-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ETVR Trading & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110460 | Bait ES | MANSALAY | 2 | 1 | 9 | Repair of Classrooms | 3345001 | 1 | 3345000.0049 | COMPLETED | 100% | 2020-03-17 | 2021-03-01 | REPAIR 2020 - R IVB - Oriental Mindoro-013 | 015-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Oriental Mindoro | 110477 | Sta. Brigida ES | MANSALAY | 2 | 1 | 7 | Repair of Classrooms | 2810001 | 1 | 2810000.0047 | COMPLETED | 100% | 2020-03-17 | 2021-03-01 | REPAIR 2020 - R IVB - Oriental Mindoro-019 | 016-2020 | 2019-11-20 | 2019-11-27 | 2019-12-12 | 2020-03-04 | 2020-11-09 | ADL Constrak | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110750 | Araceli North Central School | ARACELI | 1 | 1 | 3 | Repair of Classrooms | 1134132 | 1 | 1134131.66 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110999 | BALADING ES | CUYO | 1 | 1 | 5 | Repair of Classrooms | 1430836 | 1 | 1233608.77 | COMPLETED | 100% | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111008 | BISUCAY ES | CUYO | 1 | 1 | 3 | Repair of Classrooms | 1312119 | 1 | 1149086.13 | COMPLETED | 100% | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110754 | Bohol Elementary School | DUMARAN | 1 | 1 | 4 | Repair of Classrooms | 1271997 | 1 | 1271996.8 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110767 | Dumaran Central School | DUMARAN | 1 | 1 | 7 | Repair of Classrooms | 1406107 | 1 | 1406106.04 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111022 | Diapila Elementary School | EL NIDO (BACUIT) | 1 | 1 | 2 | Repair of Classrooms | 982614 | 1 | 982613.11 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110952 | New Colaylayan Elementary School | LINAPACAN | 1 | 1 | 3 | Repair of Classrooms | 1236637 | 1 | 1236636.94 | COMPLETED | 100% | 2021-02-28 | 2021-01-08 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111040 | ALCOBA ES | MAGSAYSAY | 1 | 1 | 4 | Repair of Classrooms | 1730748 | 1 | 1494874.25 | COMPLETED | 100% | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111047 | LOS ANGELES ES | MAGSAYSAY | 1 | 1 | 4 | Repair of Classrooms | 1666717 | 1 | 1439253 | COMPLETED | 100% | 2021-03-30 | 2021-02-28 | 2020-09-002 | 2020-09-002 | 2020-02-08 | 2020-02-21 | 2020-03-04 | 2020-11-10 | 2020-11-20 | Futuristic Trdg. And Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111150 | Jolo Elementary School | ROXAS | 1 | 1 | 5 | Repair of Classrooms | 1920534 | 1 | 1920533.09 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1 | 1 | 6 | Repair of Classrooms | 2270817 | 1 | 2270816.65 | COMPLETED | 100% | 2021-02-28 | 2020-12-18 | 2020-09-003 | 2020-09-003 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Ian Jason Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 301712 | New Guinlo National High School | TAYTAY | 1 | 1 | 9 | Repair of Classrooms | 3029810 | 1 | 3029809.84 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-001 | 2020-09-001 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110803 | Look Dahu ES | BALABAC | 2 | 1 | 2 | Repair of Classrooms | 933961 | 1 | 933960.83 | COMPLETED | 100% | 2021-03-13 | 2021-03-13 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110810 | Marabon ES | BALABAC | 2 | 1 | 4 | Repair of Classrooms | 1579290 | 1 | 1579289.24 | COMPLETED | 100% | 2021-03-13 | 2021-03-10 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110809 | Matangule ES | BALABAC | 2 | 1 | 3 | Repair of Classrooms | 1204568 | 1 | 1204567.45 | COMPLETED | 100% | 2021-03-13 | 2021-03-10 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110840 | Ocayan ES | BATARAZA | 2 | 1 | 2 | Repair of Classrooms | 874843 | 1 | 874842.86 | COMPLETED | 100% | 2021-03-13 | 2021-02-12 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110852 | Sayab II ES | BATARAZA | 2 | 1 | 2 | Repair of Classrooms | 776021 | 1 | 776020.08 | COMPLETED | 100% | 2021-03-13 | 2021-02-11 | 2020-09-004 | 2020-09-004 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | Maryknol Builders and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111057 | Batang-Batang Proper ES | NARRA | 2 | 1 | 1 | Repair of Classroom | 339300 | 1 | 339299.96 | COMPLETED | 100% | 2021-02-28 | Dec.31,2020 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111065 | Elvita ES | NARRA | 2 | 1 | 8 | Repair of Classrooms | 2361371 | 1 | 2361370.5 | COMPLETED | 100% | 2021-02-28 | Dec.31,2020 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111070 | Maranan Elementary School | NARRA | 2 | 1 | 2 | Repair of Classrooms | 625732 | 1 | 625731.56 | COMPLETED | 100% | 2021-02-28 | 2021-02-25 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111071 | Mariwara ES | NARRA | 2 | 1 | 2 | Repair of Classrooms | 724068 | 1 | 724067.53 | COMPLETED | 100% | 2021-02-28 | 2021-02-25 | 2020-09-005 | 2020-09-005 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | A.A. Padua Design & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 111090 | Alfonzo XIII ES | Quezon | 2 | 1 | 6 | Repair of Classrooms | 1944224 | 1 | 1944223.5995 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 304876 | Labog National High School | SOFRONIO ESPAÑOLA | 2 | 1 | 3 | Repair of Classrooms | 1287265 | 1 | 1287264.797 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110725 | Isaub ES | ABORLAN | 3 | 1 | 4 | Repair of Classrooms | 1109401 | 1 | 1109400.383 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Palawan | 110731 | Plaridel ES | ABORLAN | 3 | 1 | 5 | Repair of Classrooms | 1527056 | 1 | 1527055.0386 | COMPLETED | 100% | 2021-02-28 | 2021-02-12 | 2020-09-006 | 2020-09-006 | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2020-09-25 | 2020-10-05 | E.M. Abin Trdg. & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Puerto Princesa City | 111506 | Bacungan Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1815720 | 1 | 1815719.8 | COMPLETED | 100% | 2021-03-08 | 2020-12-22 | N/A |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Puerto Princesa City | 301783 | Irawan NHS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 12 | Repair of Classrooms | 5658033 | 1 | 5658032.14 | COMPLETED | 100% | 2021-03-08 | 2021-01-07 | N/A |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Puerto Princesa City | 111502 | Valentin Macasaet MES | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 11 | Repair of Classrooms | 4926275 | 1 | 4926274.03 | COMPLETED | 100% | 2021-03-08 | 2020-12-10 | N/A |  | 2019-11-26 | 2020-12-03 | 2019-12-16 | 2020-03-02 | 2020-09-28 | Don Virgilio Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111267 | Balogo Elementary School | BANTON | 0 | 1 | 1 | Repair of Classroom | 551971 | 1 | 551970.96 | COMPLETED | 100% | 2021-04-08 | 2022-08-04 | N/A | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | 10 | Repair of Classrooms | 1822330 | 1 | 1822329.84 | COMPLETED | 100% | 2021-04-08 | 2022-08-04 | N/A | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111288 | Haguimit Cult. Min. Sch. | CAJIDIOCAN | 0 | 1 | 4 | Repair of Classrooms | 2338840 | 1 | 2338839.42 | COMPLETED | 100% | 2021-04-08 | 2022-08-04 | N/A | SBP-2020-001 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111298 | Agbatang ES | CONCEPCION | 0 | 1 | 4 | Repair of Classrooms | 617419 | 1 | 617418.47 | COMPLETED | 100% | 2021-04-08 | 2022-04-26 | N/A | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 301756 | Concepcion NHS (Main) | CONCEPCION | 0 | 1 | 19 | Repair of Classrooms | 6559615 | 1 | 6559614.3 | COMPLETED | 100% | 2021-04-08 | 2022-04-26 | N/A | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 309206 | Concepcion NHS Annex (Bakhawan) | CONCEPCION | 0 | 1 | 6 | Repair of Classrooms | 1945800 | 1 | 1945799.38 | COMPLETED | 100% | 2021-04-08 | 2022-04-26 | N/A | SBP-2020-002 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-11-03 | NMDC CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111352 | FERROL CES | FERROL | 0 | 1 | 15 | Repair of Classrooms | 5343473 | 1 | 5343472.9 | COMPLETED | 100% | 2021-04-04 | 2021-08-05 | N/A | SBP-2020-004 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111339 | LIBERTAD ES | ODIONGAN | 0 | 1 | 15 | Repair of Classrooms | 3448533 | 1 | 3448532.75 | COMPLETED | 100% | 2021-04-04 | 2021-08-05 | N/A | SBP-2020-003 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111355 | MAYHA ES | ODIONGAN | 0 | 1 | 10 | Repair of Classrooms | 3019280 | 1 | 3019279.02 | COMPLETED | 100% | 2021-04-04 | 2021-08-05 | N/A | SBP-2020-003 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | RG FLORENTINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111381 | Li-O ES | ROMBLON (Capital) | 0 | 1 | 11 | Repair of Classrooms | 2620341 | 1 | 2620340.11 | COMPLETED | 100% | 2021-04-03 | 2021-05-04 | N/A | SBP-2020-005 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-29 | CSR CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111389 | San Jose ES | ROMBLON (Capital) | 0 | 1 | 11 | Repair of Classrooms | 2605071 | 1 | 2605070.54 | COMPLETED | 100% | 2021-04-03 | 2021-05-04 | N/A | SBP-2020-005 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-29 | CSR CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IV-B | Romblon | 111428 | Ben G. Talamisan ES | SAN ANDRES | 0 | 1 | 7 | Repair of Classrooms | 2804039 | 1 | 2804038.45 | COMPLETED | 100% | 2021-04-04 | 2021-08-05 | N/A | SBP-2020-004 | 2019-11-20 | 2020-11-26 | 2019-12-10 | 2020-01-23 | 2020-10-30 | [14 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dapitan City | 125913 | Burgos ES | DAPITAN CITY | 1 | 1 | 6 | Repair of Classrooms | 2555853 | 1 | 2555852.44 | COMPLETED | 100% | 2021-03-05 | 2021-09-30 | 2020-09-003 | 2020-09-003 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dapitan City | 125927 | Carang ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3242668 | 1 | 3242667.68 | COMPLETED | 100% | 2021-03-05 | 2021-09-30 | 2020-09-003 | 2020-09-003 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dapitan City | 125929 | Guimputlan ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3209366 | 1 | 3209365.01 | COMPLETED | 100% | 2021-03-05 | 2021-09-16 | 2020-09-004 | 2020-09-004 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dapitan City | 125932 | Oro ES | DAPITAN CITY | 1 | 1 | 6 | Repair of Classrooms | 2363194 | 1 | 2363193.49 | COMPLETED | 100% | 2021-03-05 | 2021-06-28 | 2020-09-004 | 2020-09-004 | 2019-12-02 | 2019-12-02 | 2019-12-16 | 2020-09-29 | 2020-10-06 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dipolog City | 125982 | Dipolog Pilot Demonstration School | DIPOLOG CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 4164359 | 1 | 4164358.89 | COMPLETED | 100% | 2021-04-30 | 2022-02-08 | Repair/Rehab of 14-Classroom at Dipolog Pilot Demonstration School | DepED-Repair-20-IX-Dip-DPDS | 2019-12-16 | 2019-12-23 | 2020-01-10 | 2020-09-16 | 2020-10-01 | Stars and Stripes Construction | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Dipolog City | 125970 | Turno Elementary School | DIPOLOG CITY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 997384 | 1 | 997383.03 | COMPLETED | 100% | 2020-12-31 | 2020-12-28 | Repair/Rehab of 3-Classroom at Turno ES | DepED-Repair-20-IX-Dip-TES | 2019-12-16 | 2019-12-23 | 2020-01-10 | 2020-09-16 | 2020-10-01 | RGS Construction | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | 0 | 1 | 13 | Repair of Classrooms | 5493434 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Isabela City | 126009 | Kauman Ekka E/S | CITY OF ISABELA (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1035623 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Isabela City | 126013 | Palasanan Primary School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1826545 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Isabela City | 126006 | Simeon & Josefa Obsequio ES | CITY OF ISABELA (Capital) | 0 | 1 | 5 | Repair of Classrooms | 2090131 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126086 | Banale ES | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2405483 | 1 | 2405482.2 | COMPLETED | 100% | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126041 | Deborok ES | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2761439 | 1 | 2761438.08 | COMPLETED | 100% | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126088 | Dumalian ES | PAGADIAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2131551 | 1 | 2131550.1 | COMPLETED | 100% | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126063 | Kalasan ES | PAGADIAN CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1346933 | 1 | 1346932.62 | COMPLETED | 100% | 2021-03-03 | 2021-02-10 | Depep-Repair-2020-IX-PAG-2 | Depep-Repair-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ARADEL CONST. & SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126072 | La Suerte ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | Repair of Classrooms | 846400 | 1 | 846400 | COMPLETED | 100% | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 303903 | Lison Valley NHS | PAGADIAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 3591001 | 1 | 3591000.3 | COMPLETED | 100% | 2021-03-03 | 2021-02-09 | Depep-Repair-2020-IX-PAG-1 | Depep-Repair-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | JZ MAGO CONST. & ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Pagadian City | 126048 | Tomas Sagun ES | PAGADIAN CITY (Capital) | 1 | 1 | 17 | Repair of Classrooms | 6789638 | 1 | 6789637.66 | COMPLETED | 100% | 2021-03-03 | 2021-03-03 | Depep-Repair-2020-IX-PAG-3 | Depep-Repair-2020-IX-PAG-3 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-16 | 2020-09-28 | ALIÑAB CONST. & SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126135 | ANULING ES | ZAMBOANGA CITY | 1 | 1 | 10 | Repair of Classrooms | 4029799 | 1 | 4029799 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-02 | ZC-REPAIR-2020-02 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | JM2K CONSTUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126105 | STO NINO ES | ZAMBOANGA CITY | 1 | 1 | 8 | Repair of Classrooms | 3601775 | 1 | 3601775 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-01 | ZC-REPAIR-2020-01 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | MMP CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126197 | BOALAN ES | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2127334 | 1 | 2127334 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-09 | ZC-REPAIR-2020-09 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126157 | DULIAN ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3634752 | 1 | 3634752 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-03 | ZC-REPAIR-2020-03 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | IYADA BUILDERS AND ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126158 | ELIGNA ES | ZAMBOANGA CITY | 2 | 1 | 4 | Repair of Classrooms | 1697978 | 1 | 1697978 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-04 | ZC-REPAIR-2020-04 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | IYADA BUILDERS AND ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126188 | LUMBAYAO ES | ZAMBOANGA CITY | 2 | 1 | 5 | Repair of Classrooms | 2047334 | 1 | 2047334 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-07 | ZC-REPAIR-2020-07 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126161 | MAGSAYSAY ES | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2144572 | 1 | 2144572 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-05 | ZC-REPAIR-2020-05 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | HIGH RISER CONSTRUCTION AND TRADING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126189 | MERCEDES CS | ZAMBOANGA CITY | 2 | 1 | 6 | Repair of Classrooms | 2247334 | 1 | 2247334 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-08 | ZC-REPAIR-2020-08 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | ZAMBOANGA 3VC CONSTRUCTION, INC. | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 303930 | SANGALI NHS | ZAMBOANGA CITY | 2 | 1 | 12 | Repair of Classrooms | 4236657 | 1 | 4236657 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-10 | ZC-REPAIR-2020-10 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | HIGH RISER CONSTRUCTION AND TRADING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga City | 126175 | TUMALUTAB ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3787925 | 1 | 3787925 | COMPLETED | 100% | 2021-01-21 | January 13,2021 | ZC-REPAIR-2020-06 | ZC-REPAIR-2020-06 | AUG 1,2022 | AUG 15,2020 | AUG 29,2020 | SEPT 14,2020 | SEPT 21,2020 | SK PATH CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 303679 | Dilawa NHS | PIÑAN (NEW PIÑAN) | 1 | 1 | 6 | Repair of Classrooms | 2319430 | 1 | 2319429.89 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-007 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124590 | Macleodes ES | POLANCO | 1 | 1 | 2 | Repair of Classrooms | 785342 | 1 | 785341.55 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-015 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124639 | Biayon ES | SERGIO OSMEÑA SR. | 1 | 1 | 6 | Repair of Classrooms | 2347360 | 1 | 2347359.89 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-021 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | 10 | Repair of Classrooms | 4182786 | 1 | 4182785.64 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-031 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124339 | Tamarok ES | JOSE DALMAN (PONOT) | 2 | 1 | 8 | Repair of Classrooms | 3212723 | 1 | 3212722.36 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-057 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 303702 | Katipunan NHS Annex - Sitog | KATIPUNAN | 2 | 1 | 6 | Repair of Classrooms | 2360667 | 1 | 2360667 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-040 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124386 | San Vicente ES | KATIPUNAN | 2 | 1 | 6 | Repair of Classrooms | 2350813 | 1 | 2350812.28 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-036 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124510 | Manukan East Central School | MANUKAN | 2 | 1 | 9 | Repair of Classrooms | 3522691 | 1 | 3522690.49 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-048 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 303712 | Marupay NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 6 | Repair of Classrooms | 2385342 | 1 | 2385341.73 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-044 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124483 | Nabilid ES | PRES. MANUEL A. ROXAS | 2 | 1 | 7 | Repair of Classrooms | 2774496 | 1 | 2774495.08 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-041 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 | 9 | Repair of Classrooms | 3673150 | 1 | 3673149.18 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-072 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 7 | Repair of Classrooms | 2884501 | 1 | 2884500.15 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-074 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124346 | Daniel Maing ES | KALAWIT | 3 | 1 | 9 | Repair of Classrooms | 3743519 | 1 | 3743518.69 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-097 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124463 | Baybay Central School | LILOY | 3 | 1 | 14 | Repair of Classrooms | 5790685 | 1 | 5790684.5 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-081 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124447 | Causwagan ES | LILOY | 3 | 1 | 6 | Repair of Classrooms | 2510306 | 1 | 2510305.77 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-079 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124457 | Patawag ES | LILOY | 3 | 1 | 6 | Repair of Classrooms | 2507263 | 1 | 2507262.28 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-080 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124461 | Silucap ES | LILOY | 3 | 1 | 9 | Repair of Classrooms | 3740761 | 1 | 3740760.71 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-092 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | 8 | Repair of Classrooms | 3334613 | 1 | 3334612.22 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-086 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124623 | Salug CS | SALUG | 3 | 1 | 7 | Repair of Classrooms | 2920936 | 1 | 2920935.08 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-083 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 6 Oct. 2020 | YSL BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124733 | Sibuco CS | SIBUCO | 3 | 1 | 10 | Repair of Classrooms | 4304337 | 1 | 4304336.88 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-103 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124835 | Dacon Learning Center | SIRAWAI | 3 | 1 | 12 | Repair of Classrooms | 5253380 | 1 | 5253379.43 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-106 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124843 | Piacan ES | SIRAWAI | 3 | 1 | 5 | Repair of Classrooms | 2154703 | 1 | 2154702.05 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-107 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Norte | 124844 | Sirawai CS | SIRAWAI | 3 | 1 | 6 | Repair of Classrooms | 2582851 | 1 | 2582850.18 | COMPLETED | 100% |  |  | Repair2020-RIX-Zamboanga Del Norte-108 |  | 20 Nov. 2019 | 28 Nov. 2019 | 11 Dec. 2019 | 16 Dec. 2019 | 9 Oct. 2020 | CPAN ENGINEERING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124867 | ANONANG ES | AURORA | 1 | 1 | 5 | Repair of Classrooms | 1762209 | 1 | 1762208.02 | COMPLETED | 100% | 2021-01-21 | 2021-01-21 | ZDS-20-RR-01 | ZDS-20-RR-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AC DEMONI CONSTRUCTION | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124889 | BALINTAWAK ES | AURORA | 1 | 1 | 3 | Repair of Classrooms | 1086798 | 1 | 3033931.32 | COMPLETED | 100% | 2021-01-21 | 2022-12-10 | ZDS-20-RR-04 | ZDS-20-RR-04 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CPIN BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124873 | CAMPO UNO ES | AURORA | 1 | 1 | 8 | Repair of Classrooms | 2956766 | 1 | 2956765.74 | COMPLETED | 100% | 2021-01-21 | 2020-12-15 | ZDS-20-RR-02 | ZDS-20-RR-02 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CHIOCO BUILDERS AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 303779 | JUAN LUMOSAD MEMORIAL NHS | AURORA | 1 | 1 | 7 | Repair of Classrooms | 3033932 | 1 | 1086797.52 | COMPLETED | 100% | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124899 | MONTE ALEGRE ES | AURORA | 1 | 1 | 2 | Repair of Classrooms | 830503 | 1 | 830502.99 | COMPLETED | 100% | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124879 | PABLO DONGALLO ES | AURORA | 1 | 1 | 9 | Repair of Classrooms | 3895978 | 1 | 3895977.93 | COMPLETED | 100% | 2021-02-20 | 2022-12-10 | ZDS-20-RR-03 | ZDS-20-RR-03 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CPIN BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125113 | COMBO ES | LABANGAN | 1 | 1 | 4 | Repair of Classrooms | 1402138 | 1 | 1126630.55 | COMPLETED | 100% | 2021-01-21 | 2020-12-15 | ZDS-20-RR-05 | ZDS-20-RR-05 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | JOCODZ CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125122 | OLD LABANGAN ES | LABANGAN | 1 | 1 | 7 | Repair of Classrooms | 2558050 | 1 | 2558049.76 | COMPLETED | 100% | 2021-02-20 | 2020-12-14 | ZDS-20-RR-06 | ZDS-20-RR-06 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AYUS BUILDERS AND ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125275 | ALICIA ES | MOLAVE | 1 | 1 | 5 | Repair of Classrooms | 1639671 | 1 | 1402137.5 | COMPLETED | 100% | 2021-02-20 | 2020-12-14 | ZDS-20-RR-06 | ZDS-20-RR-06 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | AYUS BUILDERS AND ENTERPRISES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125281 | LOWER DIMOROK ES | MOLAVE | 1 | 1 | 4 | Repair of Classrooms | 1859068 | 1 | 1639670.78 | COMPLETED | 100% | 2021-02-20 | 2020-12-15 | ZDS-20-RR-07 | ZDS-20-RR-07 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | ARADEL CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125283 | MALILI ES | MOLAVE | 1 | 1 | 2 | Repair of Classrooms | 789265 | 1 | 1859067.22 | COMPLETED | 100% | 2021-02-20 | 2020-12-15 | ZDS-20-RR-07 | ZDS-20-RR-07 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | ARADEL CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125290 | UPPER DIMOROK ES | MOLAVE | 1 | 1 | 6 | Repair of Classrooms | 2455074 | 1 | 789264.59 | COMPLETED | 100% | 2021-01-21 | 2020-01-21 | ZDS-20-RR-08 | ZDS-20-RR-08 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CDTECH BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125317 | GAPASAN ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | Repair of Classrooms | 1126631 | 1 | 2455073.24 | COMPLETED | 100% | 2021-01-21 | 2020-01-21 | ZDS-20-RR-08 | ZDS-20-RR-08 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | CDTECH BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124972 | LUDIONG ES | DINAS | 2 | 1 | 5 | Repair of Classrooms | 2171443 | 1 | 2171442.18 | COMPLETED | 100% | 2021-01-21 | 2021-05-20 | ZDS-20-RR-09 | ZDS-20-RR-09 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | A.M. TABAYAG BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 124981 | SAN ISIDRO ES | DINAS | 2 | 1 | 1 | Repair of Classroom | 476098 | 1 | 476097.2 | COMPLETED | 100% | 2021-01-21 | 2021-05-20 | ZDS-20-RR-09 | ZDS-20-RR-09 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | A.M. TABAYAG BUILDERS | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 314237 | Mecolong National High School | DUMALINAO | 2 | 1 | 1 | Repair of Classroom | 491647 | 1 | 491646.92 | COMPLETED | 100% | 2021-01-21 | 2020-12-10 | ZDS-20-RR-010 | ZDS-20-RR-010 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | KAYRO CONSTRUCTION AND SUPPLY | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 303756 | Balongating National High School | GUIPOS | 2 | 1 | 5 | Repair of Classrooms | 2245689 | 1 | 2245688.45 | COMPLETED | 100% | 2021-01-21 | 2020-12-10 | ZDS-20-RR-010 | ZDS-20-RR-010 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | KAYRO CONSTRUCTION AND SUPPLY | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125340 | Langilan Elementary School | SAN MIGUEL | 2 | 1 | 3 | Repair of Classrooms | 1398474 | 1 | 1398473.45 | COMPLETED | 100% | 2021-01-21 | 2020-12-11 | ZDS-20-RR-011 | ZDS-20-RR-011 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | DASSAN CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125348 | San Miguel CES | SAN MIGUEL | 2 | 1 | 3 | Repair of Classrooms | 1353966 | 1 | 1353965.2 | COMPLETED | 100% | 2021-01-21 | 2020-12-11 | ZDS-20-RR-011 | ZDS-20-RR-011 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | DASSAN CONSTRUCTION AND SUPPLIES | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125455 | LACUPAYAN ES | TIGBAO | 2 | 1 | 1 | Repair of Classroom | 160490 | 1 | 160489.01 | COMPLETED | 100% | 2021-01-21 | 2020-12-11 | ZDS-20-RR-012 | ZDS-20-RR-012 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | MS CONSTRUCTION AND MARKETING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga del Sur | 125466 | Upper Nilo Elementary School | TIGBAO | 2 | 1 | 4 | Repair of Classrooms | 1797518 | 1 | 1797517.75 | COMPLETED | 100% | 2021-01-21 | 2020-12-11 | ZDS-20-RR-012 | ZDS-20-RR-012 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-03 | 2020-09-16 | MS CONSTRUCTION AND MARKETING | None | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125522 | Lambuyogan ES | ALICIA | 1 | 1 | 2 | Repair of Classrooms | 822717 | 1 | 822716.78 | COMPLETED | 100% | March 05, 2021 | March 05, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 05, 2020 | Oct. 23, 2020 | Lyra Mae Construction | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125703 | Payag ES | MALANGAS | 1 | 1 | 8 | Repair of Classrooms | 3534348 | 1 | 3534347.95 | COMPLETED | 100% | March 13, 2020 | March 04, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 05, 2020 | Nov. 03, 2020 | Lucky Saver Construction | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125626 | Makilas ES | IPIL | 2 | 1 | 8 | Repair of Classrooms | 2445052 | 1 | 2445051.1 | COMPLETED | 100% | March 05, 2021 | March 05, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 23, 2020 | CPAN Engineering & Enterprises | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga Sibugay | 125713 | Bulansing ES | NAGA | 2 | 1 | 4 | Repair of Classrooms | 1316588 | 1 | 1316587.05 | COMPLETED | 100% | Feb. 19, 2021 | Feb. 19, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 09, 2020 | StoneThrow Construction & Enterprises | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region IX | Zamboanga Sibugay | 303848 | Minsulao NHS | SIAY | 2 | 1 | 7 | Repair of Classrooms | 2658182 | 1 | 2658181.7 | COMPLETED | 100% | Feb. 19, 2021 | Feb. 19, 2021 |  |  | Jan. 08, 2020 | Jan. 16, 2020 | Jan. 29, 2020 | March 04, 2020 | Oct. 09, 2020 | StoneThrow Construction & Enterprises | WAITING FOR SARO RELEASE | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111601 | Banao Elementary School | BACACAY | 1 | 1 | 4 | Repair of Classrooms | 1139697 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111588 | Busdac Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 941288 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111591 | Igang Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 767667 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111617 | Pigcobuhan Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 963121 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111618 | Pili Elementary School | BACACAY | 1 | 1 | 8 | Repair of Classrooms | 1627797 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 301878 | Sogod National High school | BACACAY | 1 | 1 | 9 | Repair of Classrooms | 1579316 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111621 | Tambilagao Elementary School | BACACAY | 1 | 1 | 3 | Repair of Classrooms | 897469 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 172511 | Malolos Elementary School | MALINAO | 1 | 1 | 3 | Repair of Classrooms | 665481 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111885 | Tanawan Elementary School | MALINAO | 1 | 1 | 2 | Repair of Classrooms | 543386 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 112058 | San Andres Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 627361 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 112059 | San Fernando Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 773030 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 172513 | Bagumbayan Elementary School | TIWI | 1 | 1 | 3 | Repair of Classrooms | 783440 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111642 | Comun Elementary School | CAMALIG | 2 | 1 | 6 | Repair of Classrooms | 2337085 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111643 | COTMON ES | CAMALIG | 2 | 1 | 10 | Repair of Classrooms | 4939038 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111634 | Manawan Elementary School | CAMALIG | 2 | 1 | 6 | Repair of Classrooms | 2348936 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111638 | TUMPA ES | CAMALIG | 2 | 1 | 3 | Repair of Classrooms | 1785483 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111679 | ALOBO ES | DARAGA | 2 | 1 | 2 | Repair of Classrooms | 1163892 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111680 | ANISLAG ES | DARAGA | 2 | 1 | 17 | Repair of Classrooms | 8419062 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111660 | BANADERO ES | DARAGA | 2 | 1 | 12 | Repair of Classrooms | 5361485 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111682 | BIGAO ES | DARAGA | 2 | 1 | 6 | Repair of Classrooms | 3155884 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111683 | BURGOS ES | DARAGA | 2 | 1 | 1 | Repair of Classroom | 646158 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111681 | Bascaran Elementary School | DARAGA (LOCSIN) | 2 | 1 | 9 | Repair of Classrooms | 3374262 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111714 | Manases Olaybal Mem. ES (Sinungtan) | GUINOBATAN | 3 | 1 | 2 | Repair of classrooms | 809352 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 112004 | Kinale Elementary School | POLANGUI | 3 | 1 | 3 | Repair of classrooms | 1241578 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 112010 | Matacon Elementary School | POLANGUI | 3 | 1 | 8 | Repair of classrooms | 3230494 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111989 | Maynaga Elementary School | POLANGUI | 3 | 1 | 2 | Repair of classrooms | 390991 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111994 | Pintor Elementary School | POLANGUI | 3 | 1 | 6 | Repair of classrooms | 2118154 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Albay | 111994 | Pintor Elementary School | POLANGUI | 3 |  | 3 | Repair of classrooms | 831759 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112201 | Bayabas ES | LABO | 1 | 1 | 5 | Repair of classrooms | 2202654 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112191 | Marcos Pimentel ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1109596 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112243 | Calaburnay ES | PARACALE | 1 | 1 | 6 | Repair of classrooms | 2276041 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112083 | Balce ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1298106 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 | 1 | 5 | Repair of classrooms | 3221415 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte |  | Basud NHS (ANNEX) | BASUD | 2 | 1 | 16 | Repair of classrooms | 3998179 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112131 | Alawihao ES | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2251264 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 8 | Repair of 8 Toilets | 1581659 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112134 | Daet ES | DAET (Capital) | 2 | 1 | 9 | Repair of classrooms | 3358442 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112145 | F. Baldovino ES | DAET (Capital) | 2 | 1 | 1 | Repair of Classroom | 681885 | 1 | 2896889.8 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112147 | Gregorio Pimentel Memorial School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2301225 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112136 | Mantagbac Elem School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2172702 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 500030 | Moreno Integ. Sch. | DAET (Capital) | 2 | 1 | 3 | Repair of classrooms | 1209225 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 6 | Repair of classrooms | 2248959 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2 | 1 | 3 | Repair of classrooms | 1403213 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 8 | Repair of classrooms | 3618510 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112296 | Talisay ES | TALISAY | 2 | 1 | 8 | Repair of classrooms | 3053386 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Norte | 112316 | Vinzons Pilot Elementary School | VINZONS | 2 | 1 | 12 | Repair of classrooms | 3381245 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112457 | Biong ES | Cabusao | 1 | 1 | 5 | Repair of classrooms | 2269484 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112461 | Pandan ES | Cabusao | 1 | 1 | 2 | Repair of classrooms | 888400 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112462 | San Pedro ES | Cabusao | 1 | 1 | 4 | Repair of classrooms | 1810771 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112463 | Sta. Cruz ES | Cabusao | 1 | 1 | 5 | Repair of classrooms | 2274700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | Cabusao | 1 | 1 | 10 | Repair of classrooms | 5047271 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112576 | Cabasag Elementary School | Del Gallego | 1 | 1 | 3 | Repair of classrooms | 1371400 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112686 | MAMBULO VIEJO ES | LIBMANAN | 2 | 1 | 2 | Repair of classrooms | 777645 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112687 | Mancawayan Elementary School | LIBMANAN | 2 | 1 | 3 | Repair of classrooms | 1217756 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 173538 | Mandacanan PS | LIBMANAN | 2 | 1 | 2 | Repair of classrooms | 854235 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112697 | Tarum Elementary School | LIBMANAN | 2 | 1 | 7 | Repair of classrooms | 2869984 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112699 | USON ES | LIBMANAN | 2 | 1 | 1 | Repair of classroom | 529447 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 309748 | Milaor NHS - Dalipay Annex HS | MILAOR | 2 | 1 | 2 | Repair of classrooms | 898871 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112794 | Bingcay ES | MINALABAC | 2 | 1 | 2 | Repair of classrooms | 795816 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112798 | HOBO ES | MINALABAC | 2 | 1 | 5 | Repair of classrooms | 2056807 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112802 | MANAPAO ES | MINALABAC | 2 | 1 | 4 | Repair of classrooms | 1683820 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112803 | MATAOROC ES | MINALABAC | 2 | 1 | 4 | Repair of classrooms | 1533446 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112804 | MINALABAC CS | MINALABAC | 2 | 1 | 3 | Repair of classrooms | 1203855 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 302067 | Villamayor HS - Bagolatao Annex HS | MINALABAC | 2 | 1 | 1 | Repair of classroom | 393374 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112866 | BATANG ES | PAMPLONA | 2 | 1 | 6 | Repair of classrooms | 469288 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 113007 | Pipian ES | SAN FERNANDO | 2 | 1 | 2 | Repair of classrooms | 1020849 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112497 | Union Elementary School | CALABANGA | 3 | 1 | 20 | Repair of classrooms | 5756737 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112521 | Tacolod Elementary School - Main | CANAMAN | 3 | 1 | 6 | Repair of classrooms | 874095 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112770 | Sta. Lucia ES | MAGARAO | 3 | 1 | 3 | Repair of classrooms | 677704 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 301962 | Altamarino-Clasio High School (formerly Curry High School) | PILI (Capital) | 3 | 1 | 14 | Repair of classrooms | 4109500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112937 | San Jose South ES | PILI (Capital) | 3 | 1 | 5 | Repair of classrooms | 2571940 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 301943 | Bikal Fisheries School | CARAMOAN | 4 | 1 | 2 | Repair of classrooms | 1187378 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 301949 | BURABOD NHS | GARCHITORENA | 4 | 1 | 2 | Repair of classrooms | 1149756 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112598 | Del Pilar ES | GARCHITORENA | 4 | 1 | 6 | Repair of classrooms | 2919492 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112628 | MAYSALAY ES | GOA | 4 | 1 | 9 | Repair of classrooms | 4246896 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 173516 | Kinahulogan CS | LAGONOY | 4 | 1 | 3 | Repair of classrooms | 1790500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112668 | SAN ROQUE ES | LAGONOY | 4 | 1 | 4 | Repair of classrooms | 2110700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112888 | Bulalacao Elementary School | PRESENTACION (PARUBCAN) | 4 | 1 | 7 | Repair of classrooms | 3840300 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112330 | Nababarera ES | BAAO | 5 | 1 | 1 | Repair of classroom | 455700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112348 | Caroche ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 663100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112350 | Coguit ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 900800 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112352 | Maguiron ES | BALATAN | 5 | 1 | 2 | Repair of classrooms | 963100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112357 | San Francisco ES | BALATAN | 5 | 1 | 5 | Repair of classrooms | 2345300 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112368 | CRISTO REY ELEMENTARY SCHOOL | BATO | 5 | 1 | 2 | Repair of classrooms | 371100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 330563 | Divine Shepherd High School | BATO | 5 | 1 | 2 | Repair of classrooms | 737600 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112371 | Lobong Elementary School | BATO | 5 | 1 | 2 | Repair of classrooms | 937600 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112376 | Neighborhood ES | BATO | 5 | 1 | 3 | Repair of classrooms | 1510700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112377 | Nino Jesus ES | BATO | 5 | 1 | 2 | Repair of classrooms | 1070700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112380 | Sagrada ES | BATO | 5 | 1 | 3 | Repair of classrooms | 1170500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112385 | San Vicente ES | BATO | 5 | 1 | 1 | Repair of classroom | 455700 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112387 | Tagpolo ES | BATO | 5 | 1 | 1 | Repair of classroom | 540100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112404 | Lourdes Elementary School | BUHI | 5 | 1 | 2 | Repair of classrooms | 821100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Camarines Sur | 112844 | Sto. Domingo Elementary School | NABUA | 5 | 1 | 2 | Repair of classrooms | 887100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113157 | Mavil ES | Bagamanoc | 0 | 1 | 8 | Repair of classrooms | 1511768 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113159 | San Vicente ES | Bagamanoc | 0 | 1 | 10 | Repair of classrooms | 1797634 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113165 | Suchan ES | Bagamanoc | 0 | 1 | 9 | Repair of classrooms | 2252853 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113196 | Buenavista Elementary School | Caramoran | 0 | 1 | 3 | Repair of classrooms | 2030585 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113197 | Camburo ES | Caramoran | 0 | 1 | 3 | Repair of classrooms | 1894021 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113202 | Panique ES | Caramoran | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113214 | Sabloyon Elementary School | Caramoran | 0 | 1 | 6 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113203 | San Jose ES | Caramoran | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113235 | Catamban ES | Pandan | 0 | 1 | 3 | Repair of classrooms | 1759996 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113240 | Panuto ES | Pandan | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113244 | Alinawan ES | Panganiban (Payo) | 0 | 1 | 6 | Repair of classrooms | 1304299 | 1 |  | COMPLETED | 100% | [10 empty] | For Termination | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113268 | Agojo ES | SAN ANDRES (CALOLBON) | 0 | 1 | 9 | Repair of classrooms | 2415912 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113270 | Barihay ES | SAN ANDRES (CALOLBON) | 0 | 1 | 3 | Repair of classrooms | 906101 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113317 | Almojuela ES | Viga | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113311 | Magsaysay ES | Viga | 0 | 1 | 6 | Repair of classrooms | 1802746 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113340 | Dugui Too Elementary School | Virac (Capital) | 0 | 1 | 9 | Repair of classrooms | 2435394 | 1 |  | COMPLETED | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113342 | Gogon Elementary School | Virac (Capital) | 0 | 1 | 9 | Repair of classrooms | 1700000 | 1 |  | COMPLETED | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113365 | Pajo Baguio ES | Virac (Capital) | 0 | 1 | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113366 | Pajo San Isidro ES | Virac (Capital) | 0 | 1 | 3 | Repair of classrooms | 1173746 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Catanduanes | 113351 | Taytay ES | Virac (Capital) | 0 | 1 | 6 | Repair of classrooms | 1274178 | 1 |  | COMPLETED | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  |  |  | bid valuation | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 114430 | CAWAYAN ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 7 | Repair of Classrooms | 3956619 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 114448 | LA PURISIMA ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 9 | Repair of Classrooms | 5889144 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 114450 | SAN ANTONIO ES | Iriga City | 5 | 1 | 15 | Repair of classrooms | 5207367 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 114428 | STA. CRUZ SUR ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 13 | Repair of Classrooms | 6585458 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 114454 | STA. ELENA ES | Iriga City | 5 | 1 | 8 | Repair of classrooms | 2768499 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 302250 | STA. MARIA HIGH SCHOOL | IRIGA CITY | 5 | 1 | 11 | Repair of Classrooms | 6951082 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Iriga City | 302256 | STO. NIÑO NHS | Iriga City | 5 | 1 | 16 | Repair of classrooms | 6020363 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 302257 | Banquerohan NHS | LEGAZPI CITY (Capital) | 2 | 1 | 8 | Repair of classrooms | 1280830 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 114471 | Ems Barrio PS | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Repair of classrooms | 1605708 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | 7 | Repair of classrooms | 2007013 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | Repair of classrooms | 534530 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 310205 | Maslog National High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | Repair of classrooms | 1026825 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 | 7 | Repair of classrooms | 1813256 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Legazpi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | Repair of classrooms | 1255355 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 111835 | Allang ES | CITY OF LIGAO | 3 | 1 | 1 | Repair of classrooms | 489730 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 111810 | Baligang ES | CITY OF LIGAO | 3 | 1 | 10 | Repair of classrooms | 2912081 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 111817 | Busac ES | CITY OF LIGAO | 3 | 1 | 5 | Repair of classrooms | 2511247 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 321702 | Maonon HS | CITY OF LIGAO | 3 | 1 | 7 | Repair of classrooms | 2204548 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 231007 | Pandan ES, Macael Ext. | CITY OF LIGAO | 3 | 1 | 5 | Repair of Classroom | 1607571 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Ligao City | 111831 | Tinago ES | CITY OF LIGAO | 3 | 1 | 9 | Repair of classrooms | 3071712 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113574 | Calpi ELementary school | CLAVERIA | 1 | 1 | 2 | Repair of classrooms | 725543 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 309905 | Osmeña NHS | Claveria | 1 | 1 | 4 | Repair of classrooms | 1367871 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113588 | Pasig ES | Claveria | 1 | 1 | 8 | Repair of classrooms | 2512195 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 302173 | Tiburcio A. Berdida, Sr. NHS | Claveria | 1 | 1 | 13 | Repair of classrooms | 4875583 | 1 | 1632669.02 | COMPLETED | 100% | 2019-11-18 |  | 2018-12-016 | 2019-02-007 | 2018-12-04 | 2018-12-12 | 2018-12-24 | 2019-08-05 | 2019-08-20 | Camsur Bicol Trading INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 302144 | Magdalena NHS | BALENO | 2 | 1 | 4 | Repair of classrooms | 1216913 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113442 | Tinapian ES | BALENO | 2 | 1 | 2 | Repair of classrooms | 684789 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113644 | Centro Elementary School | MANDAON | 2 | 1 | 2 | Repair of classrooms | 581833 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2 | 1 | 2 | Repair of classrooms | 1185607 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 309907 | San Pablo National High School | MANDAON | 2 | 1 | 6 | Repair of classrooms | 1706161 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113753 | Polot Elementary School | MOBO | 2 | 1 | 2 | Repair of classrooms | 616278 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113513 | Emilio S. Boro Sr. CS | CATAINGAN | 3 | 1 | 10 | Repair of classrooms | 3164310 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113521 | Nadawisan ES | CATAINGAN | 3 | 1 | 2 | Repair of classrooms | 809623 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113498 | Pawican Elementary School | CATAINGAN | 3 | 1 | 8 | Repair of classrooms | 2935001 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | 1 | Repair of Classroom | 446532 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate | 113945 | Candelaria ES | USON | 3 | 1 | 2 | Repair of classrooms | 990845 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate City | 321801 | Bolo National High School | CITY OF MASBATE | 2 | 1 | 9 | Repair of classrooms | 2567003 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Masbate City | 231501 | Gutusan Elementary School | CITY OF MASBATE | 2 | 1 | 2 | Repair of classrooms | 815796 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3 | 1 | 8 | Repair of Classrooms | 2478286 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 15 | Repair of Classrooms | 6956530 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 114514 | Jose Rizal Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 114508 | Julian B. Meliton Elementary School | NAGA CITY | 3 | 1 | 13 | Repair of classrooms | 9056339 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 302268 | Naga City Science HighSchool | NAGA CITY | 3 | 1 | 2 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 | 7 | Repair of Classrooms | 2579955 | 1 | 773478 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | MRP MERCHANDISING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of Classrooms | 4237520 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Naga City | 114513 | Villa Grande Homes Elementary School | NAGA CITY | 3 | 1 | 10 | Repair of classrooms | 7158588 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114117 | Amomonting ES | Castilla | 1 | 1 | 5 | Repair of classrooms | 1587337 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114124 | Loreto ES | CASTILLA | 1 | 1 | 6 | Repair of classrooms | 1336557 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 302226 | Mayon National High School | CASTILLA | 1 | 1 | 9 | Repair of classrooms | 1925443 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114135 | Sogoy ES | CASTILLA | 1 | 1 | 5 | Repair of classrooms | 1133279 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114276 | Cagbolo ES | Magallanes | 1 | 1 | 2 | Repair of classrooms | 721239 | 1 | 350390.39 | COMPLETED | 100% | [9 empty] | 0405 Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114283 | Sta. Elena Elementary School | Magallanes | 1 | 1 | 3 | Repair of classrooms | 889056 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114336 | Abas ES | Pilar | 1 | 1 | 4 | Repair of classrooms | 938327 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114365 | Bayasong Elementary School | Pilar | 1 | 1 | 7 | Repair of classrooms | 1809964 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 113991 | Putiao Elementary School | Barcelona | 2 | 1 | 4 | Repair of classrooms | 1569711 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114009 | Cocok-Cabitan E.S. | Bulan | 2 | 1 | 4 | Repair of classrooms | 1580311 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114010 | Daganas ES | Bulan | 2 | 1 | 1 | Repair of classrooms | 445198 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114051 | San Ramon ES | Bulan | 2 | 1 | 3 | Repair of classrooms | 1350766 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114065 | Sabang ES | Bulusan | 2 | 1 | 5 | Repair of classrooms | 1791896 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114075 | STA. BARBARA ES | BULUSAN | 2 | 1 | 6 | Repair of Classroom | 2156524 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114077 | TINAMPO ES | BULUSAN | 2 | 1 | 4 | Repair of classrooms | 1207989 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114184 | Aguinaldo ES | Gubat | 2 | 1 | 2 | Repair of classrooms | 544985 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114187 | Bonifacio ES | Gubat | 2 | 1 | 7 | Repair of classrooms | 1265041 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114220 | TOGAWE ES | GUBAT | 2 | 1 | 5 | Repair of classrooms | 1207330 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114228 | Carriedo ES | Irosin | 2 | 1 | 6 | Repair of classrooms | 2061337 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114268 | SANGKAYON ELEMENTARY SCHOOL | Juban | 2 | 1 | 4 | Repair of classrooms | 1464639 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114302 | Banogao Elementary School | Matnog | 2 | 1 | 4 | Repair of classrooms | 1426718 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon | 114317 | Laboy ES | Matnog | 2 | 1 | 6 | Repair of classrooms | 2180201 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 1675949 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114537 | Gajo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 1125556 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114547 | San Vicente Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | Repair of classrooms | 803478 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114583 | Tublijon Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of classrooms | 888888 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador ES | Sorsogon East | 1 |  | 3 | Repair of classrooms |  | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Sorsogon City | 114562 | San Lorenzo ES | Sorsogon East | 1 | 1 | 7 | Repair of classrooms | 2877167 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Tabaco City | 114607 | Baranghawon ES | CITY OF TABACO | 1 | 1 | 8 | Repair of classrooms | 2670101 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Tabaco City | 114614 | Fatima ES | CITY OF TABACO | 1 | 1 | 7 | Repair of classrooms | 2936931 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Tabaco City | 114593 | Oras ES | CITY OF TABACO | 1 | 1 | 6 | Repair of classrooms | 2572112 | 1 | 1091142.38 | COMPLETED | 100% | 2020-01-20 | [22 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Tabaco City | 114602 | Sua-Igot Elementary School | CITY OF TABACO | 1 | 1 | 9 | Repair of classrooms | 3282210 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region V | Tabaco City | 114624 | Tabaco South Central School | CITY OF TABACO | 1 | 1 | 6 | Repair of classrooms | 2680876 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500543 | Balete Integrated School | BALETE | 0 | 1 | 16 | Repair of Classrooms | 8100000 | 1 | 8100000 | COMPLETED | 100% | 2021-04-20 | 2021-05-27 | DepED-RO6-D1-2020BEFFREPAIR-C5-119-2019 | DepED-RO6-D1-2020BEFFREPAIR-C5-119-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | FIRST MAKEEN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114682 | Bay-ang Elementary School | BATAN | 0 | 1 | 2 | Repair of Classrooms | 1100000 | 1 | 1100000 | COMPLETED | 100% | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302300 | Camaligan NHS | BATAN | 0 | 1 | 14 | Repair of Classroom | 5548400 | 1 | 5544942.25 | COMPLETED | 100% | 2021-04-25 | 2021-07-30 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 0 | 1 | 3 | Repair of Classrooms | 1380283 | 1 | 1380282.63 | COMPLETED | 100% | 2021-03-26 | 2021-03-19 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114732 | Buenavista PS | IBAJAY | 0 | 1 | 2 | Repair of Classrooms | 1124398 | 1 | 1124397.6 | COMPLETED | 100% | 2021-03-26 | 2021-03-19 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114720 | Laguinbanwa ES | IBAJAY | 0 | 1 | 1 | Repair of Classroom | 867600 | 1 | 867057.75 | COMPLETED | 100% | 2021-04-25 | 2021-10-05 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | DepED-RO6-D1-2020BEFFREPAIR-C4-118-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 0 | 1 | 10 | Repair of Classrooms | 4138369 | 1 | 4138369 | COMPLETED | 100% | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114768 | Tayhawan Elementary School | LEZO | 0 | 1 | 2 | Repair of Classrooms | 1277929 | 1 | 1277928.98 | COMPLETED | 100% | 2021-03-26 | 2021-03-30 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114791 | Maytaraw PS | LIBACAO | 0 | 1 | 3 | Repair of Classrooms | 4307099 | 1 | 4307098.55 | COMPLETED | 100% | 2021-06-09 |  | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | BENZEN CONSTRUCTION | Last Mile School; The project is on-going but with slow accomplishment | [12 empty] | 100% |  | 44621 | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114792 | Ogsip PS | LIBACAO | 0 | 1 | 1 | Repair of Classroom | 605000 | 1 | 605000 | COMPLETED | 100% | 2021-02-09 | 2021-02-05 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | DepED-RO6-D1-2020BEFFREPAIR-C8-122-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | SOLID MERCHNDISING | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114800 | Taroytoy Primary School | LIBACAO | 0 | 1 | 4 | Repair of Classrooms | 2890128 | 1 | 2890127.37 | COMPLETED | 100% | 2021-11-25 | 2022-06-22 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114816 | Madalag ES | MADALAG | 0 | 1 | 4 | Repair of Classrooms | 2043391 | 1 | 2043390.79 | COMPLETED | 100% | 2021-03-26 | 2021-05-28 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | DepED-RO6-D1-2020BEFFREPAIR-C6-120-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302315 | Madalag NHS | MADALAG | 0 | 1 | 16 | Repair of Classrooms | 7561873 | 1 | 7561872.63 | COMPLETED | 100% | 2021-11-25 | 2022-06-22 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | DepED-RO6-D1-2020BEFFREPAIR-C2-116-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114864 | Lilo-an Elementary School | MALINAO | 0 | 1 | 5 | Repair of Classrooms | 2521003 | 1 | 2129225.57 | COMPLETED | 100% | 2021-04-08 | 2021-09-20 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | CULASI GENERAL MERCHANDISING AND COSNTRUCTION SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114936 | Tangalan ES | TANGALAN | 0 | 1 | 13 | Repair of Classrooms | 6365102 | 1 | 6365101.45 | COMPLETED | 100% | 2021-06-09 | 2022-01-10 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | DepED-RO6-D1-2020BEFFREPAIR-C1-115-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | BENZEN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302336 | Tangalan National High School | TANGALAN | 0 | 1 | 8 | Repair of Classrooms | 3571719 | 1 | 3018495.53 | COMPLETED | 100% | 2021-04-08 | 2021-03-08 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | DepED-RO6-D1-2020BEFFREPAIR-C7-121-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-05 | CULASI GENERAL MERCHANDISING AND COSNTRUCTION SERVICES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114658 | Bacan Elementary School | BANGA | 1 | 1 | 11 | Repair of Classrooms | 4912801 | 1 | 3479184.25 | COMPLETED | 100% | 2021-06-04 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C1-086-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C1-086-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302289 | Bacan National High School | BANGA | 1 | 1 | 11 | Repair of Classrooms | 4127044 | 1 | 2883553.52 | COMPLETED | 100% | 2021-06-04 | 2021-08-06 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C2-087-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C2-087-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114660 | Banga ES | BANGA | 1 | 1 | 3 | Repair of Classrooms | 1456427 | 1 | 1063569.91 | COMPLETED | 100% | 2021-05-11 | 2021-07-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302324 | Aklan NHS for Arts & Trades | KALIBO (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1958234 | 1 | 1936838.36 | COMPLETED | 100% | 2021-05-11 | 2021-10-26 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114755 | Estancia ES | KALIBO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2712717 | 1 | 2684061.64 | COMPLETED | 100% | 2021-05-11 | 2021-08-24 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C7-092-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114756 | Kalibo I ES | KALIBO (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1440784 | 1 | 755708.14 | COMPLETED | 100% | 2021-06-04 | 2021-09-09 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114750 | Kalibo Pilot Elementary School | KALIBO (Capital) | 1 | 1 | 13 | Repair of Classrooms | 5935839 | 1 | 4501000 | COMPLETED | 100% | 2021-05-11 | 2021-08-06 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C3-088-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C3-088-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302332 | Regional Science High School for Region VI | KALIBO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2208673 | 1 | 1935844.79 | COMPLETED | 100% | 2021-06-04 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114761 | Tigayon Elementary School | KALIBO (Capital) | 1 | 1 | 2 | Repair of Classrooms | 867016 | 1 | 1262252.98 | COMPLETED | 100% | 2021-06-05 | 2021-06-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C6-091-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500172 | Makato Integrated School | MAKATO | 2 | 1 | 17 | Repair of Classrooms | 8142047 | 1 | 5283061.61 | COMPLETED | 100% | 2021-05-11 | 2021-05-10 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C5-090-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C5-090-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114866 | Malinao ES | MALINAO | 2 | 1 | 11 | Repair of Classrooms | 4509313 | 1 | 3479184.25 | COMPLETED | 100% | 2021-05-11 | 2021-04-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C9-094-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C9-094-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 302319 | Malinao Sch. For Phil. Craftsmen | MALINAO | 2 | 1 | 16 | Repair of Classrooms | 6322220 | 1 | 3479184.25 | COMPLETED | 100% | 2021-05-11 |  | DepED-RO6-D1-2020BEFFREPAIRBATCH2-C1-089-2020 | DepED-RO6-D1-2020BEFFREPAIRBATCH2-C1-089-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  | 44621 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114917 | Bulwang ES | NUMANCIA | 2 | 1 | 3 | Repair of Classrooms | 1735369 | 1 | 1267439.44 | COMPLETED | 100% | 2021-05-11 | 2021-07-29 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114920 | Dongon ES | NUMANCIA | 2 | 1 | 11 | Repair of Classrooms | 4499768 | 1 | 3143162.58 | COMPLETED | 100% | 2021-05-11 | 2021-04-30 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C10-095-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C10-095-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 114921 | Laguinbanua ES | NUMANCIA | 2 | 1 | 4 | Repair of Classrooms | 2403401 | 1 | 1755990.65 | COMPLETED | 100% | 2021-05-11 | 2021-07-29 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C11-096-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 12 | Repair of Classrooms | 3571719 | 1 | 3065772.11 | COMPLETED | 100% | 2021-05-11 | 2021-06-11 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C8-093-2020 | DepED-RO6-D1-2020BEFF(REPAIR)BATCH2-C8-093-2020 | 2020-12-02 | 2020-12-09 | 2020-12-21 | 2021-12-23 | 2021-01-04 | GMO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 |  | 11 | Repair of Classrooms | 4386775 | 1 | 897505.98 | COMPLETED | 100% | 2020-12-29 | 2020-11-23 | DepED-RO6-D1-2020QRF(REPAIR)-C21-038-2020 | DepED-RO6-D1-2020QRF(REPAIR)-C21-038-2020 | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-07-22 | 2020-08-24 | EARLY RISER CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Aklan | 500035 | Numancia Integrated Sch | NUMANCIA | 2 | 1 | 12 | Repair of Classrooms |  | 1 | 5850000 | COMPLETED | 100% | 2021-05-23 | 2021-12-10 | DepED-RO6-D1-2020BEFFREPAIR-C3-117-2019 | DepED-RO6-D1-2020BEFFREPAIR-C3-117-2019 | 2019-11-20 | 2019-11-27 | 2019-12-09 | 2019-12-27 | 2020-10-28 | FIRST MAKEEN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115001 | Yapu ES | BUGASONG | 0 | 1 | 7 | Repair of Classrooms | 2384806 | 1 | 2384805.52 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115056 | San Vicente ES | CULASI | 0 | 1 | 5 | Repair of Classrooms | 1184099 | 1 | 1184098.51 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115058 | Tomao PS | CULASI | 0 | 1 | 2 | Repair of Classrooms | 707955 | 1 | 707954.51 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115120 | Paningayan Primary School | LAUA-AN | 0 | 1 | 2 | Repair of Classrooms | 541383 | 1 | 541382.91 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115127 | Bulanao ES | LIBERTAD | 0 | 1 | 4 | Repair of Classrooms | 1167416 | 1 | 1167415.76 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115162 | Patria ES | PANDAN | 0 | 1 | 12 | Repair of Classrooms | 3123406 | 1 | 3123405.87 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 302380 | Sta. Ana NHS | PANDAN | 0 | 1 | 3 | Repair of Classrooms | 893091 | 1 | 893090.82 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115182 | Magsaysay ES | PATNONGON | 0 | 1 | 3 | Repair of Classrooms | 922585 | 1 | 922584.33 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115190 | Villa Flores Elementary School | PATNONGON | 0 | 1 | 3 | Repair of Classrooms | 910960 | 1 | 910959.29 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115247 | Nagbangi I ES | SAN REMIGIO | 0 | 1 | 9 | Repair of Classrooms | 3312934 | 1 | 3312933.07 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115248 | Nagbangi II ES | SAN REMIGIO | 0 | 1 | 4 | Repair of Classrooms | 1171022 | 1 | 1171021.58 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115274 | Trinidad ES | SAN REMIGIO | 0 | 1 | 6 | Repair of Classrooms | 1758732 | 1 | 1758731.19 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115278 | Alegre ES | SEBASTE | 0 | 1 | 5 | Repair of Classrooms | 909620 | 1 | 909619.12 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115284 | P. Javier PS | SEBASTE | 0 | 1 | 1 | Repair of Classroom | 342209 | 1 | 342208.45 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115303 | MAASIN ELEMENTARY SCHOOL | SIBALOM | 0 | 1 | 4 | Repair of Classrooms | 652157 | 1 | 652156.8 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115340 | Bandoja PS | TIBIAO | 0 | 1 | 3 | Repair of Classrooms | 1168380 | 1 | 1168379.23 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Antique | 115375 | Igtugas ES | TOBIAS FORNIER (DAO) | 0 | 1 | 4 | Repair of Classrooms | 1147844 | 1 | 1147843.2 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Bacolod City | 117480 | BACOLOD CITY SPED CENTER | BACOLOD CITY (Capital) | 0 | 1 | 10 | Repair of Classrooms | 3101751 | 1 |  | COMPLETED | 100% | [10 empty] | RTA isuued, waiting for issuance of SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Bacolod City | 117454 | Mandalagan ES | BACOLOD CITY (Capital) | 0 | 1 | 17 | Repair of Classrooms | 5231763 | 1 |  | COMPLETED | 100% | [10 empty] | RTA isuued, waiting for issuance of SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 2161682 | 1 |  | COMPLETED | 100% | [10 empty] | RTA isuued, waiting for issuance of SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Bago City | 117522 | Louisiana Elementary School | BAGO CITY | 4 | 1 | 6 | Repair of Classrooms | 2303740 | 1 | 1448262.47 | COMPLETED | 100% |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Bago City | 117500 | Newton Jison ES | BAGO CITY | 4 | 1 | 9 | Repair of Classrooms | 3509767 | 1 | 2216066.59 | COMPLETED | 100% |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 24 | Repair of Classrooms | 9493231 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Cadiz City | 117564 | Luis Uy Chiat Elementary School | CADIZ CITY | 2 | 1 | 7 | Repair of Classrooms | 3333723 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115553 | Cabungahan Elementary School | MA-AYON | 1 | 1 | 8 | Repair of Classrooms | 2329273 | 1 | 2329272.6417 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115566 | New Guia ES | MA-AYON | 1 | 1 | 9 | Repair of Classrooms | 2490000 | 1 | 2490000 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115573 | Quinat-uyan ES | MA-AYON | 1 | 1 | 4 | Repair of Classrooms | 1054041 | 1 | 1054040.3583 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115618 | Bato PS | PANAY | 1 | 1 | 1 | Repair of classroom | 330991 | 1 | 330990.7 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115625 | Daga ES | PANAY | 1 | 1 | 3 | Repair of Classrooms | 1042856 | 1 | 1042855.0883 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115643 | Agustin A. Almalbis MS | PANITAN | 1 | 1 | 4 | Repair of Classrooms | 1401985 | 1 | 1401984.7416 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115644 | Ambilay ES | PANITAN | 1 | 1 | 6 | Repair of Classrooms | 1869605 | 1 | 1869604.9884 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115681 | San Ramon ES | PILAR | 1 | 1 | 5 | Repair of Classrooms | 1539024 | 1 | 1539023.8911 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115683 | Sinamongan ES | PILAR | 1 | 1 | 6 | Repair of Classrooms | 1829503 | 1 | 1829502.0089 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115694 | Maximo Dais ES | PONTEVEDRA | 1 | 1 | 7 | Repair of Classrooms | 1620241 | 1 | 1620240.6971 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115776 | Joaquin Artuz ES | TAPAZ | 1 | 1 | 9 | Repair of Classrooms | 3740151 | 1 | 2880000 | COMPLETED | 100% | [9 empty] | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115409 | Agcabugao Elementary School | CUARTERO | 2 | 1 | 5 | Repair of Classrooms | 1960908 | 1 | 1441137.1718 | COMPLETED | 100% | [9 empty] | MARIZALOI CONST | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115410 | Agdahon ES | CUARTERO | 2 | 1 | 10 | Repair of Classrooms | 4227569 | 1 | 3140790.49 | COMPLETED | 100% | [9 empty] | MARIZALOI CONST | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115411 | Agnaga ES | CUARTERO | 2 | 1 | 3 | Repair of Classrooms | 820418 | 1 | 699736.1582 | COMPLETED | 100% | [9 empty] | MARIZALOI CONST | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115415 | Vicente F. Fabuna ES (Bito-on Ilaya) | CUARTERO | 2 | 1 | 4 | Repair of Classrooms | 952108 | 1 | 820417.0046 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115429 | Agtambi PS | DAO | 2 | 1 | 2 | Repair of Classrooms | 559891 | 1 | 559890.5596 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115430 | Agtanguay ES | DAO | 2 | 1 | 2 | Repair of Classrooms | 812715 | 1 | 812714.0019 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2 | 1 | 12 | Repair of Classrooms | 3430391 | 1 | 3430390.57 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115451 | Consolacion ES | DUMALAG | 2 | 1 | 5 | Repair of Classrooms | 1652334 | 1 | 1504024.2016 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115452 | Dolores ES | DUMALAG | 2 | 1 | 5 | Repair of Classrooms | 1716193 | 1 | 1562151.7984 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115494 | SIBARIWAN ELEMENTARY SCHOOL | DUMARAO | 2 | 1 | 2 | Repair of Classrooms | 706078 | 1 | 706077.4034 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115499 | Agustin P. Navarra Elemenatary School | IVISAN | 2 | 1 | 7 | Repair of Classrooms | 2004443 | 1 | 2004442.1166 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115534 | Linambasan ES | JAMINDAN | 2 | 1 | 5 | Repair of Classrooms | 1539109 | 1 | 1539108.1154 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115591 | Malogo ES | MAMBUSAO | 2 | 1 | 3 | Repair of Classrooms | 1027966 | 1 | 1027965.9756 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115609 | Tongatong ES | MAMBUSAO | 2 | 1 | 5 | Repair of Classrooms | 1558188 | 1 | 1558187.0944 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115728 | Agtatacay Sur Elementary School | SAPI-AN | 2 | 1 | 5 | Repair of Classrooms | 1553419 | 1 | 1553418.7751 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115732 | Benlit ES | SAPI-AN | 2 | 1 | 6 | Repair of Classrooms | 1458094 | 1 | 1458093.1649 | COMPLETED | 100% | [9 empty] | MBM CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115754 | Fructousa A. de Romero PS | SIGMA | 2 | 1 | 2 | Repair of Classrooms | 1395735 | 1 | 1395734.4385 | COMPLETED | 100% | [9 empty] | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115777 | Leopoldo Gialogo ES | TAPAZ | 2 | 1 | 6 | Repair of Classroom | 2098538 | 1 | 1738089.8534 | COMPLETED | 100% | [9 empty] | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115785 | Malitbog ES | TAPAZ | 2 | 1 | 4 | Repair of Classrooms | 1186124 | 1 | 355264.4993 | COMPLETED | 100% | [9 empty] | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115790 | San Antonio ES (tapaz east) | TAPAZ | 2 | 1 | 3 | Repair of Classrooms | 1358583 | 1 | 2098537.87 | COMPLETED | 100% | [9 empty] | FIRST R+J | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115794 | San Miguel Ilaya ES | TAPAZ | 2 | 1 | 6 | Repair of Classrooms | 2433015 | 1 | 1186123.46 | COMPLETED | 100% | [9 empty] | FIRST R+J | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 115816 | San Nicolas ES | TAPAZ | 2 | 1 | 5 | Repair of Classrooms | 2256671 | 1 | 1044735.5007 | COMPLETED | 100% | [9 empty] | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Capiz | 179003 | Sinonod PS | TAPAZ | 2 | 1 | 1 | Repair of Classroom | 461989 | 1 | 1873910.1466 | COMPLETED | 100% | [9 empty] | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Escalante City | 325605 | Escalante NHS - Libertad Ext. | CITY OF ESCALANTE | 1 | 1 | 5 | Repair of Classrooms | 1147308 | 1 | 1147307.33 | COMPLETED | 100% |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Escalante City | 117059 | Libertad Elementary School | CITY OF ESCALANTE | 1 | 1 | 12 | Repair of Classrooms | 2955791 | 1 | 2955791 | COMPLETED | 100% |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Escalante City | 117060 | Mabini Central Elementary School | CITY OF ESCALANTE | 1 | 1 | 18 | Repair of Classrooms | 2527000 | 1 | 2526999.01 | COMPLETED | 100% |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region VI | Guimaras | 115905 | Cabalagnan Elementary School | NUEVA VALENCIA | 0 | 1 | 13 | Repair of Classrooms | 4617921 | 1 |  | COMPLETED | 100% |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 6-Oct. 2020 | Quadtech Builders Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Guimaras | 179501 | Unisan Multigrade School | NUEVA VALENCIA | 0 | 1 | 5 | Repair of Classrooms | 1235832 | 1 |  | COMPLETED | 100% |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 6-Oct. 2020 | Quadtech Builders Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Guimaras | 115855 | Sapal Elementary School | SAN LORENZO | 0 | 1 | 10 | Repair of Classrooms | 2535000 | 1 |  | COMPLETED | 100% |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 30-Sept. 2020 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Guimaras | 115879 | Liningwan Central School | SIBUNAG | 0 | 1 | 15 | Repair of Classrooms | 4793000 | 1 |  | COMPLETED | 100% |  |  |  |  | 25-Nov. 2019 | 19-Dec. 2019 | 19-Dec. 2019 | 26-Dec. 2019 | 30-Sept. 2020 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Himamaylan City | 117071 | Catingib ES | CITY OF HIMAMAYLAN | 5 | 1 | 6 | Repair of Classrooms | 1291397 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Himamaylan City | 117103 | Mambagaton ES | CITY OF HIMAMAYLAN | 5 | 1 | 13 | Repair of Classrooms | 4174262 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Himamaylan City | 117108 | Manuel Yulo ES | CITY OF HIMAMAYLAN | 5 | 1 | 7 | Repair of Classrooms | 2452596 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116385 | Tano-ong PS | IGBARAS | 1 | 1 | 4 | Repair of Classrooms | 1048632 | 1 | 1048631.37 | COMPLETED | 100% | 2021-02-19 | 2021-05-21 | REPAIR2020-RVI-ILOILO-B1L1 | REPAIR2020-RVI-ILOILO-B1L1 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Anjush Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116631 | Sta. Clara ES | OTON | 1 | 1 | 7 | Repair of Classrooms | 1968930 | 1 | 1968929.53 | COMPLETED | 100% | 2021-02-16 | 2021-05-31 | REPAIR2020-RVI-ILOILO-B1L2 | REPAIR2020-RVI-ILOILO-B1L2 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | SKY Builders Constrcution & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116840 | Adgao-Tagpuan-Ingay ES | TUBUNGAN | 1 | 1 | 12 | Repair of Classrooms | 4831686 | 1 | 4831685.7 | COMPLETED | 100% | 2021-02-11 | 2021-02-05 | REPAIR2020-RVI-ILOILO-B1L3 | REPAIR2020-RVI-ILOILO-B1L3 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | October 5, 0200 | Early Riser Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116849 | Lanag Norte ES | TUBUNGAN | 1 | 1 | 10 | Repair of Classrooms | 3605887 | 1 | 3605886.45 | COMPLETED | 100% | 2021-02-24 | 2021-01-26 | REPAIR2020-RVI-ILOILO-B1L4 | REPAIR2020-RVI-ILOILO-B1L4 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 115953 | Cagay ES | ALIMODIAN | 2 | 1 | 5 | Repair of Classrooms | 2192144 | 1 | 2192143.8 | COMPLETED | 100% | 2021-02-11 | 2021-01-18 | REPAIR2020-RVI-ILOILO-B1L5 | REPAIR2020-RVI-ILOILO-B1L5 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-05 | Early Riser Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116515 | Tacuyong Sur ELementary School | LEON | 2 | 1 | 14 | Repair of Classrooms | 5774000 | 1 | 5774000 | COMPLETED | 100% | 2021-02-11 | 2021-02-08 | REPAIR2020-RVI-ILOILO-B1L6 | REPAIR2020-RVI-ILOILO-B1L6 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | RISM BUILDERS & CONST. SERVICES INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116611 | Cagban ES | NEW LUCENA | 2 | 1 | 8 | Repair of Classrooms | 2595137 | 1 | 2595136.29 | COMPLETED | 100% | 2021-02-04 | 2021-09-30 | REPAIR2020-RVI-ILOILO-B1L7 | REPAIR2020-RVI-ILOILO-B1L7 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-06 | SLW8 Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 115998 | Calansanan ES | BADIANGAN | 3 | 1 | 6 | Repair of Classrooms | 2197355 | 1 | 2197354.33 | COMPLETED | 100% | 2021-02-24 | 2021-01-26 | REPAIR2020-RVI-ILOILO-B1L8 | REPAIR2020-RVI-ILOILO-B1L8 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116103 | Agba-o ES | BINGAWAN | 3 | 1 | 13 | Repair of Classrooms | 4161861 | 1 | 4161860.12 | COMPLETED | 100% | 2021-02-11 | 2021-02-10 | REPAIR2020-RVI-ILOILO-B1L9 | REPAIR2020-RVI-ILOILO-B1L9 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | RISM BUILDERS & CONST. SERVICES INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116663 | Danao ES | POTOTAN | 3 | 1 | 7 | Repair of Classrooms | 2915334 | 1 | 2915333.56 | COMPLETED | 100% | 2021-02-03 | 2021-05-25 | REPAIR2020-RVI-ILOILO-B1L10 | REPAIR2020-RVI-ILOILO-B1L10 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-06 | Q.M. Florete Cosntruction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116276 | Libo-o ES | DINGLE | 4 | 1 | 10 | Repair of Classrooms | 3482400 | 1 | 3448463.39 | COMPLETED | 100% | 2021-02-11 | 2021-02-09 | REPAIR2020-RVI-ILOILO-B1L11 | REPAIR2020-RVI-ILOILO-B1L11 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-07 | GMO Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116283 | SAN MATIAS ELEMENTARY SCHOOL | DINGLE | 4 | 1 | 10 | Repair of Classrooms | 4156798 | 1 | 4156797.5 | COMPLETED | 100% | 2021-02-13 | 2021-02-05 | REPAIR2020-RVI-ILOILO-B1L12 | REPAIR2020-RVI-ILOILO-B1L12 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Micro-Asia Builders Corp. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo | 116762 | Calaigang ES | SAN RAFAEL | 5 | 1 | 11 | Repair of Classrooms | 4541350 | 1 | 4541349.37 | COMPLETED | 100% | 2021-02-19 | 2021-02-11 | REPAIR2020-RVI-ILOILO-B1L13 | REPAIR2020-RVI-ILOILO-B1L13 | 2019-12-21 | 2019-12-27 | 2020-01-10 | 2020-02-27 | 2020-10-13 | Anjush Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo City | 117580 | Arevalo ES | ILOILO CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 1785842 | 1 | 1785842 | COMPLETED | 100% | 2020-02-09 | 2019-12-16 | 20-10-004 | 14-08-054 | 2018-11-14 | 2018-11-20 | 2018-12-07 | 2018-12-11 | 2019-09-05 | RISM BUILDERS & CONST. SERVICES INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Iloilo City | 117584 | Sto. Domingo ES | ILOILO CITY (Capital) | 0 | 1 | 8 | Repair of Classrooms | 1562190 | 1 | 1562190 | COMPLETED | 100% | 2020-02-09 | 2019-12-16 | 20-10-005 | 14-08-054 | 2018-11-14 | 2018-11-20 | 2018-12-07 | 2018-12-11 | 2019-09-05 | RISM BUILDERS & CONST. SERVICES INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 312102 | Bantayan NHS - Baras Diutay Ext. | CITY OF KABANKALAN | 6 | 1 | 5 | Repair of Classrooms | 2229775 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 4316400 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 117863 | Magtongtong ES | CITY OF KABANKALAN | 6 | 1 | 8 | Repair of Classrooms | 2943394 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 117844 | Mansumbil Elementary School | CITY OF KABANKALAN | 6 | 1 | 7 | Repair of Classrooms | 1382874 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 117865 | Pangyasan PS | CITY OF KABANKALAN | 6 | 1 | 2 | Repair of Classrooms | 592725 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Kabankalan City | 117850 | Pres. Osmena ES | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 3207618 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | La Carlota City | 117631 | Balabag ES | LA CARLOTA CITY | 4 | 1 | 15 | Repair of Classrooms | 3606012 | 1 |  | COMPLETED | 100% | [10 empty] | Already Submit the RTA/waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 16 | Repair of Classrooms | 3822948 | 1 |  | COMPLETED | 100% | [10 empty] | Already Submit the RTA/waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | La Carlota City | 500192 | La Carlota City SPED Integrated School | LA CARLOTA CITY | 4 | 1 | 12 | Repair of Classrooms | 2089503 | 1 |  | COMPLETED | 100% | [10 empty] | Already Submit the RTA/waiting for SARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116896 | Bagacay ES | CALATRAVA | 1 | 1 | 5 | Repair of Classrooms | 1570015 | 1 | 1570014.19 | COMPLETED | 100% | 2021-01-07 |  | 6777947 | 20-09-009 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116901 | Calatrava I Central School | CALATRAVA | 1 | 1 | 15 | Repair of Classrooms | 3604009 | 1 | 3604008.76 | COMPLETED | 100% | 2021-01-07 |  | 6777956 | 20-09-010 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116920 | Ecogan ES | CALATRAVA | 1 | 1 | 6 | Repair of Classrooms | 2042200 | 1 | 2042200 | COMPLETED | 100% | 2021-04-30 |  | 6778114 | 20-09-021 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-10-22 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116909 | R. Magsaysay MES | CALATRAVA | 1 | 1 | 13 | Repair of Classrooms | 3465960 | 1 | 3465959.26 | COMPLETED | 100% | 2021-01-07 |  | 6777970 | 20-09-011 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117394 | Concepcion ES | CITY OF TALISAY | 3 | 1 | 8 | Repair of Classrooms | 1851001 | 1 | 1851000.14 | COMPLETED | 100% | 2021-01-07 |  | 6777983 | 20-09-012 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 302623 | Enrique B. Magalona NHS - San Isidro Ext. | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 7 | Repair of Classrooms | 1477000 | 1 | 1477000 | COMPLETED | 100% | 2021-01-07 |  | 6777998 | 20-09-013 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117276 | B.R. Dela Rama ES | MURCIA | 3 | 1 | 22 | Repair of Classrooms | 5208404 | 1 | 5208403.98 | COMPLETED | 100% | 2021-01-07 |  | 6778008 | 20-09-014 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117293 | Lopez Jaena ES | MURCIA | 3 | 1 | 16 | Repair of Classrooms | 4399449 | 1 | 4399448.83 | COMPLETED | 100% | 2021-02-06 |  | 6778119 | 20-09-022 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-23 | 2020-09-29 | SUNSHINE SAPPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | 17 | Repair of Classrooms | 3462730 | 1 | 3462729.72 | COMPLETED | 100% | 2021-01-07 |  | 6778028 | 20-09-016 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117316 | Pontevedra North ES | PONTEVEDRA | 4 | 1 | 30 | Repair of Classrooms | 9087058 | 1 | 9087057.12 | COMPLETED | 100% | 2021-01-07 |  | 6778018 | 20-09-015 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116867 | Binalbagan South ES | BINALBAGAN | 5 | 1 | 1 | Repair of Classroom | 983374 | 1 | 983373.92 | COMPLETED | 100% | 2021-01-07 |  | 6778124 | 19-12-025 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 116869 | Doña Concepcion Y. Yusay Memorial School | BINALBAGAN | 5 | 1 | 10 | Repair of Classrooms | 2154887 | 1 | 2154886.46 | COMPLETED | 100% | 2021-01-07 |  | 6778075 | 20-04-017 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117011 | Si-alay ES | CAUAYAN | 6 | 1 | 10 | Repair of Classrooms | 2355031 | 1 | 2355030.15 | COMPLETED | 100% | 2021-01-07 |  | 6778091 | 20-04-018 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6 | 1 | 8 | Repair of Classrooms | 2405400 | 1 | 2405400 | COMPLETED | 100% | 2021-01-07 |  | 6778097 | 20-09-019 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-10-21 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Negros Occidental | 117162 | Bocana ES | ILOG | 6 | 1 | 17 | Repair of Classrooms | 3537884 | 1 | 3537883.01 | COMPLETED | 100% | 2021-01-07 |  | 6778106 | 20-09-020 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Passi City | 186002 | AGLALANA ELEMENTARY SCHOOL - ANNEX | CITY OF PASSI | 4 | 1 | 7 | Repair of Classrooms | 1838647 | 1 | 1838646.33 | COMPLETED | 100% |  |  |  | RO6-D14-CY2020-REPAIR-CLASSROOMS-L2 |  |  |  |  | November 6, 2020 | Early Riser Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Passi City | 186003 | Pagaypay Elementary School | CITY OF PASSI | 4 | 1 | 3 | Repair of Classrooms | 769662 | 1 | 769661.03 | COMPLETED | 100% |  |  |  | R06-D14-CY2020-REPAIR-CLASSROOMS-L1 |  |  |  |  | November 6, 2020 | Early Riser Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Passi City | 117928 | Talongonan Elementary School | CITY OF PASSI | 4 | 1 | 5 | Repair of Classrooms | 1289230 | 1 | 1289229.27 | COMPLETED | 100% |  |  |  | R06-D14-CY2020-REPAIR-CLASSROOMS-L1 |  |  |  |  | November 6, 2020 | Early Riser Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Sagay City | 117729 | Campo Santiago ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2352066 | 1 | 2352065.09 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Sagay City | 117717 | Hautea ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2225599 | 1 | 2225598.13 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Sagay City | 302770 | Sewahon National High School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 2972911 | 1 | 2972910.93 | COMPLETED | 100% |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | San Carlos City | 117796 | Malindog ES | SAN CARLOS CITY | 1 | 1 | 10 | Repair of Classrooms | 3494847 | 1 | 3491000 | COMPLETED | 100% | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | San Carlos City | 117764 | Punod ES | SAN CARLOS CITY | 1 | 1 | 9 | Repair of Classrooms | 3663014 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | 2 | Repair of Classrooms | 716540 | 1 | 715000 | COMPLETED | 100% | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Silay City | 500199 | Don Albino & Doña Dolores Jison IS | SILAY CITY | 3 | 1 | 13 | Repair of Classrooms | 3869000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VI | Sipalay City | 117360 | Maricalum ES | CITY OF SIPALAY | 6 | 1 | 6 | Repair of Classrooms | 2144197 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bais City | 120094 | Lowason ES | BAIS CITY | 2 | 1 | 7 | Repair of Classrooms | 2503300 | 1 |  | COMPLETED | 100% | [9 empty] | PAR | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bais City | 120100 | Palaypay ES | BAIS CITY | 2 | 1 | 12 | Repair of Classrooms | 3944563 | 1 |  | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bayawan City | 120116 | Maglinao Elementary School | BASAY | 3 | 1 | 13 | Repair of Classrooms | 5188394 | 1 |  | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bayawan City | 120156 | Kalumboyan ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 27 | Repair of Classrooms | 9371995 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bayawan City | 120137 | San Jose Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 8 | Repair of Classrooms | 1787212 | 1 |  | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bogo City | 119110 | Marangog ES | CITY OF BOGO | 4 | 1 | 8 | Repair of Classrooms | 1931819 | 1 | 2964721.57 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | Septptember 25, 2020 | Inabanga Drilling | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 117987 | Laya ES | BACLAYON | 1 | 1 | 10 | Repair of Classrooms | 2964722 | 1 | 4518423.55 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118101 | Pangangan ES | CALAPE | 1 | 1 | 19 | Repair of Classrooms | 4518424 | 1 | 2953032.13 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118728 | Sto. Niño ES | TALIBON | 2 | 1 | 16 | Repair of Classrooms | 2953033 | 1 | 2269568.23 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118767 | Tagum Sur ES | TRINIDAD | 2 | 1 | 12 | Repair of Classrooms | 2269569 | 1 | 1747575.57 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 25, 2020 | Inabanga Drilling | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118806 | Bood Elementary School | UBAY | 2 | 1 | 13 | Repair of Classrooms | 1747576 | 1 | 3004320.21 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | October 18, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118041 | Bilar Central ES | BILAR | 3 | 1 | 12 | Repair of Classrooms | 3004321 | 1 | 6183313.36 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 21, 2020 | LTS Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118411 | Balili ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2382324 | 1 | 2094612.22 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118412 | Boctol ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2796022 | 1 | 1022109.47 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LTS Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118414 | Bunga Mar ES | JAGNA | 3 | 1 | 15 | Repair of Classrooms | 5707971 | 1 | 953437.6 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118413 | Bunga Ylaya ES | JAGNA | 3 | 1 | 5 | Repair of Classrooms | 1243259 | 1 | 4078883.97 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | JF Estapia construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118415 | Buyog ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1231828 | 1 | 1597582.98 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118416 | Cabungaan ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 2261795 | 1 | 1489323.25 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | Sombrio Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118417 | Calabacita ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2097273 | 1 | 1444881.41 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LTS Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118418 | Cambugason ES | JAGNA | 3 | 1 | 9 | Repair of Classrooms | 1678898 | 1 | 1131798.98 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 10, 2020 | Algamon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118419 | Can-ipol ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1374469 | 1 | 2052105.72 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118420 | Canjulao ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2784402 | 1 | 1165667.99 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | MABB Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118421 | Cantagay ES | JAGNA | 3 | 1 | 5 | Repair of Classrooms | 1581749 | 1 | 1425644.73 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | A.D. Daniel construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118422 | Cantuyoc ES | JAGNA | 3 | 1 | 6 | Repair of Classrooms | 1427826 | 1 | 2664613.1 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118423 | Can-uba ES | JAGNA | 3 | 1 | 10 | Repair of Classrooms | 3798578 | 1 | 596892.48 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 10, 2020 | Algamon Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118424 | Jagna Central ES | JAGNA | 3 | 1 | 27 | Repair of Classrooms | 6183314 | 1 | 5738027.78 | COMPLETED | 100% |  |  |  |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-02-13 | September 23, 2020 | Clavite Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118425 | Kinagbaan ES | JAGNA | 3 | 1 | 2 | Repair of Classrooms | 727415 | 1 | 1572397.99 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118426 | Larapan ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2240723 | 1 | 1724597.4 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118427 | Lonoy ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2301511 | 1 | 2071243.72 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | 3N Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118428 | Malbog ES | JAGNA | 3 | 1 | 8 | Repair of Classrooms | 2920486 | 1 | 1190280.86 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | LM Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118431 | Odiong ES | JAGNA | 3 | 1 | 4 | Repair of Classrooms | 1678249 | 1 | 1329453.55 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 4, 2020 | C Jansen Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 500208 | Tubod ES | JAGNA | 3 | 1 | 6 | Repair of Classrooms | 1774442 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Bohol | 118864 | Valencia Central Elementary School | VALENCIA | 3 | 1 | 24 | Repair of Classrooms | 5738028 | 1 | 1652345.79 | COMPLETED | 100% |  |  |  |  | August 19, 2020 | August 27, 2020 | Sept 8, 2020 | October 28, 2020 | December 7, 2020 | Sombrio Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Carcar City | 119180 | Napo Elementary School | CITY OF CARCAR | 1 | 1 | 4 | Repair of Classrooms | 1648918 | 1 |  | COMPLETED | 100% | 2021-02-05 | 2020-12-11 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119633 | Tañañas Elementary School | SAN FERNANDO | 1 | 1 | 2 | Repair of Classrooms | 445693 | 1 |  | COMPLETED | 100% | 2021-02-05 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119722 | Sibonga Central ES | SIBONGA | 1 | 1 | 16 | Repair of Classrooms | 5377393 | 1 |  | COMPLETED | 100% | 2021-02-05 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2 | 1 | 17 | Repair of Classrooms | 4467735 | 1 |  | COMPLETED | 100% | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119298 | Dalaguete Central ES | DALAGUETE | 2 | 1 | 9 | Repair of Classrooms | 3014494 | 1 |  | COMPLETED | 100% | 2021-01-06 | 2020-10-30 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119327 | Panaguikan ES | DALAGUETE | 2 | 1 | 11 | Repair of Classrooms | 3808351 | 1 |  | COMPLETED | 100% | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119329 | Sacsac ES | DALAGUETE | 2 | 1 | 10 | Repair of Classrooms | 2544596 | 1 |  | COMPLETED | 100% | 2021-03-07 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | 33 | Repair of Classrooms | 10084805 | 1 |  | COMPLETED | 100% | 2021-01-06 | 2020-12-28 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119190 | Dawis Sur ES | CARMEN | 5 | 1 | 10 | Repair of Classrooms | 3100579 | 1 |  | COMPLETED | 100% | 2021-01-06 | 2020-10-19 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119198 | Puente ES | CARMEN | 5 | 1 | 9 | Repair of Classrooms | 4092882 | 1 |  | COMPLETED | 100% | 2021-02-05 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119742 | Sogod Central ES | SOGOD | 5 | 1 | 22 | Repair of Classrooms | 5389977 | 1 |  | COMPLETED | 100% | 2021-01-06 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119250 | Tugbongan ES | CONSOLACION | 6 | 1 | 11 | Repair of Classroom | 3442625 | 1 |  | COMPLETED | 100% | 2021-01-06 |  |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119251 | Alegria ES | CORDOVA | 6 | 1 | 7 | Repair of Classrooms | 2531381 | 1 |  | COMPLETED | 100% | 2021-02-05 | 2020-10-19 |  |  | 2020-01-29 | 2020-02-05 | 2020-02-17 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu | 119255 | Cordova Central ES | CORDOVA | 6 | 1 | 19 | Repair of Classrooms | 7913474 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 303138 | Camp Lapu-Lapu NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 1941128.16 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 119919 | Carreta ES (Bagong Buhay ES) | CEBU CITY (Capital) | 1 | 1 | 37 | Repair of Classrooms | 2839457.83 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1195235 | 1 |  | COMPLETED | 100% | [10 empty] | FOR ISSUANCE OF NTP | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 303154 | Regino Mercado NHS (Night) | CEBU CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 1179167 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 119903 | San Jose Elementary School | CEBU CITY (Capital) | 1 | 1 | 8 | Repair of Classrooms | 1339994 | 1 |  | COMPLETED | 100% | [10 empty] | FOR ISSUANCE OF NTP | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 32 | Repair of Classrooms | 2936384.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 119905 | Bulacao Community ES | CEBU CITY (Capital) | 2 | 1 | 7 | Repair of Classrooms | 1581930.28 | 1 |  | COMPLETED | 100% | [10 empty] | Suspended due to fire evacuees in-house in school | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 119866 | Don Vicente Rama MES (Basak ES) | CEBU CITY (Capital) | 2 | 1 | 18 | Repair of Classrooms | 3422466.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 119910 | PARDO EXTENSION ELEMENTARY SCHOOL | CEBU CITY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 553319 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 1176673 | 1 | 2542106.2 | COMPLETED | 100% |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION | FOR ISSUANCE OF NTP | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | City of Naga, Cebu | 325304 | Cogon National High School | CITY OF NAGA | 1 | 1 | 4 | Repair of Classrooms | 564747 | 1 | 543284.65 | COMPLETED | 100% |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | City of Naga, Cebu | 325308 | Tagjaguimit National High School | CITY OF NAGA | 1 | 1 | 2 | Repair of Classrooms | 543285 | 1 | 1000000 | COMPLETED | 100% |  |  |  |  | January 7, 2020 | January 13, 2020 | January 27, 2020 | January 29, 2020 | September 23, 2020 | F E & A Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | City of Naga, Cebu | 303120 | Tuyan National High School | CITY OF NAGA | 1 | 1 | 8 | Repair of Classrooms | 2542107 | 1 | 564746.27 | COMPLETED | 100% |  |  | cityofnaga 2019-004 |  | 2019-11-19 | 2019-11-26 | 2019-12-12 | Dec.23, 2019 |  | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Danao City | 119355 | Portland ES | DANAO CITY | 5 | 1 | 4 | Repair of Classrooms | 1000000 | 1 | 1405616.36 | COMPLETED | 100% | 2021-04-27 |  |  |  |  | 2019-11-20 | 2019-12-09 | 2019-12-19 | 2020-12-21 | PAR Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Dumaguete City | 119945 | Cantil-e ES | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1181000 | 1 | 2729546.51 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | with variation order | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Dumaguete City | 119940 | West City Exceptional Child Learning Center | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1405617 | 1 | 1181000 | COMPLETED | 100% | 2021-04-28 |  |  |  | 2020-01-22 | 2020-01-29 | 2020-02-10 | 2020-02-26 | 2020-12-22 | RISM Builders and Construction Services, Inc. | with variation order | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120260 | Agulang PS | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 691810 | 1 | 990614 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120241 | Calabaclabacan ES | CITY OF GUIHULNGAN | 1 | 1 | 8 | Repair of Classrooms | 2729547 | 1 | 1100736.86 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120250 | Lip-o ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1400423 | 1 | 1131560 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120252 | Magkanaway PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1131560 | 1 | 1922984 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120278 | Nagsaha ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 990614 | 1 | 1574195.47 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120281 | Plagatasanon ES | CITY OF GUIHULNGAN | 1 | 1 | 5 | Repair of Classrooms | 1574196 | 1 |  | COMPLETED | 100% |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | FROY J BUILDERS AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120286 | Tominhao PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1100737 | 1 | 1400423 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Guihulngan City | 120641 | Ulay Elementary School | VALLEHERMOSO | 1 | 1 | 7 | Repair of Classrooms | 1922984 | 1 | 691810 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Lapu-Lapu City | 119977 | Gun-ob ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 4 | Repair of Classrooms | 1848839.29 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Lapu-Lapu City | 119972 | Abuno ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 6 | Repair of Classrooms | 2307557 | 1 |  | COMPLETED | 100% |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Lapu-Lapu City | 303183 | Marigondon NHS - Science Tech. Educ. Center (STEC) Ext. | LAPU-LAPU CITY (OPON) | 6 | 1 | 13 | Repair of Classrooms | 2128918 | 1 | 2984674.27 | COMPLETED | 100% |  |  | RE2020-001 | 2020-09-046 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Tri Bairn Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Lapu-Lapu City | 119958 | Sta. Rosa ES | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | Repair of Classrooms | 4899367 | 1 |  | COMPLETED | 100% |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | GOLDEN HAMMER CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Mandaue City | 120008 | Bakilid ES | MANDAUE CITY | 6 | 1 | 9 | Repair of Classrooms | 2984675 | 1 | 717399.7 | COMPLETED | 100% |  |  | RE2020-002 | 2020-09 -047 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Golden Hammer Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Mandaue City | 312801 | Canduman NHS - Tabok NHS | MANDAUE CITY | 6 | 1 | 2 | Repair of Classroom | 672833 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | 2 | Repair of Classrooms | 717400 | 1 | 672832.91 | COMPLETED | 100% |  |  | RE2020-003 | 2020-0 9 -048 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-01-06 |  | Jelay Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120043 | Iniban Elementary School | AYUNGON | 1 | 1 | 9 | Repair of Classrooms | 1921000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120206 | Linothangan Elementary School | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3292082 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120208 | Malaiba Elementary School | CANLAON CITY | 1 | 1 | 3 | Repair of Classrooms | 843690 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120211 | Masulog ES | CANLAON CITY | 1 | 1 | 20 | Repair of Classrooms | 8310000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120213 | Panubigan Elementary School | CANLAON CITY | 1 | 1 | 16 | Repair of Classrooms | 6951280 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120216 | Tabalogo ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3435981 | 1 |  | COMPLETED | 100% |  |  | 2019 - 48 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | ALOJA BUILDERS AND REALTY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120384 | Campuyo Elementary School | MANJUYOD | 1 | 1 | 9 | Repair of Classrooms | 4400000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 303207 | Amlan National High School | AMLAN (AYUQUITAN) | 2 | 1 | 17 | Repair of Classrooms | 6183000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120025 | Aurelio Ibero MES (Jugno ES) | AMLAN (AYUQUITAN) | 2 | 1 | 7 | Repair of Classroom | 1941000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120364 | Lumbangan Elementary School | MABINAY | 2 | 1 | 26 | Repair of Classrooms | 6532000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120488 | Escaguit Elementary School | SIBULAN | 2 | 1 | 4 | Repair of Classrooms | 1443000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120445 | Bantolinao Elementary School | SIATON | 3 | 1 | 6 | Repair of Classrooms | 1720574 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120462 | Lico-Lico Elementary School | SIATON | 3 | 1 | 9 | Repair of Classrooms | 2693714 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120474 | Palayuhan ES | SIATON | 3 | 1 | 8 | Repair of Classrooms | 1836000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Negros Oriental | 120647 | Kaladias ES | ZAMBOANGUITA | 3 | 1 | 14 | Repair of Classrooms | 3411000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Siquijor | 120670 | Cangomantong Elementary School | LAZI | 0 | 1 | 8 | Repair of Classrooms | 2908041 | 1 |  | COMPLETED | 100% |  |  | 2019 - 49 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Siquijor | 120682 | Minalulan Elementary School | MARIA | 0 | 1 | 10 | Repair of Classrooms | 2207997 | 1 |  | COMPLETED | 100% |  |  | 2019 - 50 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | VVER Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Siquijor | 120709 | Tambisan Elementary School | SAN JUAN | 0 | 1 | 7 | Repair of Classrooms | 2317963 | 1 |  | COMPLETED | 100% |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Siquijor | 120696 | Cang-atuyom Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | Repair of Classrooms | 645206 | 1 |  | COMPLETED | 100% |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Siquijor | 120704 | San Antonio Elementary School | SIQUIJOR (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1388364 | 1 | 5613375.27 | COMPLETED | 100% |  |  |  | 2020-001-Infra |  |  | December 18, 2019 | December 26, 2019 | September 28, 2020 | ESP Design, Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tagbilaran City | 322102 | San Isidro National High School | TAGBILARAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1829395 | 1 |  | COMPLETED | 100% |  |  | talisaycity2020-001 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | SB & T Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tagbilaran City | 118715 | Tiptip Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 16 | Repair of Classrooms | 5613376 | 1 | 1829394.44 | COMPLETED | 100% |  |  |  | 2020-002-Infra |  |  | December 18, 2019 | December 26, 2019 | September 28, 2020 | ESP Design, Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Talisay City | 119798 | Iba Elementary School | CITY OF TALISAY | 1 | 1 | 3 | Repair of Classrooms | 1181811 | 1 |  | COMPLETED | 100% |  |  | talisaycity2020-002 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | JY Bontilao Construction & Enterprises | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Talisay City | 303019 | Jaclupan National High School | CITY OF TALISAY | 1 | 1 | 6 | Repair of Classrooms | 2247523 | 1 |  | COMPLETED | 100% | [9 empty] | RISM | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Talisay City | 119787 | Lawaan Elementary School | CITY OF TALISAY | 1 | 1 | 6 | Repair of Classrooms | 2379951 | 1 |  | COMPLETED | 100% |  |  | talisaycity2020-003 |  | 2020-01-07 | 2020-01-13 | 2020-01-27 | 2020-01-30 | waiting for SARO | QCC Construction & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 120546 | Canghatap Elementary School | CITY OF TANJAY | 2 | 1 | 5 | Repair of Classrooms | 2178500 | 1 |  | COMPLETED | 100% | [9 empty] | RISM | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 100% | [9 empty] | RISM | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 100% | [9 empty] | RISM | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 234002 | Rosario V. Moras Memorial School | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms |  | 1 |  | COMPLETED | 100% | [9 empty] | VVER | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 120411 | Caningay Elementary School | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1968302 | 1 |  | COMPLETED | 100% | [9 empty] | VVER | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Tanjay City | 120428 | Tigbao Elementary School | PAMPLONA | 2 | 1 | 5 | Repair of Classrooms |  | 1 | 3803586.63 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VII | Toledo City | 120715 | Cantabaco ES | TOLEDO CITY | 3 | 1 | 16 | Repair of Classrooms | 3803587 | 1 | 3803586.63 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121084 | Hibunawan Elementary School | CITY OF BAYBAY | 5 | 1 | 6 | Repair of Classrooms | 2116610 | 1 | 2116609.83 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I014 | 2019-11-I014 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MELGAZO CONSTRUCTION AND SUPPLY | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121142 | Kantagnos Elementary School | CITY OF BAYBAY | 5 | 1 | 2 | Repair of Classrooms | 780000 | 1 | 780000 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I019 | 2019-11-I019 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | J CUSTORIO CONSTRUCTION | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121123 | Maslug Elementary School | CITY OF BAYBAY | 5 | 1 | 3 | Repair of Classrooms | 905670 | 1 | 905669.71 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I017 | 2019-11-I017 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | AAVB CONSTRUCTION AND SUPPLY | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121124 | Maypatag Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1771880 | 1 | 1771879.65 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I018 | 2019-11-I018 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MELGAZO CONSTRUCTION AND SUPPLY | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121110 | Pansagan Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1505631 | 1 | 1505630.15 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I015 | 2019-11-I015 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | JFR CONSTRUCTION | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121149 | San Agustin Elementary School | CITY OF BAYBAY | 5 | 1 | 5 | Repair of Classrooms | 1596320 | 1 | 1596319.19 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I020 | 2019-11-I020 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | RAQ J BUILDERS | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Baybay City | 121111 | San Juan Elementary School | CITY OF BAYBAY | 5 | 1 | 3 | Repair of Classrooms | 904047 | 1 | 904046.26 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | 2019-11-I016 | 2019-11-I016 | 2019-11-21 | 2019-11-29 | 2019-12-11 | 2019-12-18 | January 0, 1900 | MAGA CONSTRUCTION AND SUPPLIES | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120789 | CAPAYAS ES | CABUCGAYAN | 0 | 1 | 2 | Repair of Classrooms | 742261 | 1 | 742260.66 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120794 | PAWIKAN ES | CABUCGAYAN | 0 | 1 | 1 | Repair of Classroom | 363074 | 1 | 361130.34 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120807 | LOOC ES | CAIBIRAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 361500 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120812 | TOMALISTIS ES | CAIBIRAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 361500 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120834 | KAWAYAN CS | KAWAYAN | 0 | 1 | 2 | Repair of Classrooms | 715583 | 1 | 362918.37 | COMPLETED | 100% | [9 empty] | INFRASERVE CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 500411 | INASUYAN ES | KAWAYAN | 0 | 1 | 1 | Repair of Classroom | 361500 | 1 | 715582.37 | COMPLETED | 100% | [9 empty] | INFRASERVE CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120840 | SAN LORENZO ES | KAWAYAN | 0 | 1 | 1 | Repair of Classroom | 362919 | 1 | 361500 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120847 | BATO BANLAS ES | MARIPIPI | 0 | 1 | 1 | Repair of Classroom | 386852 | 1 | 749483.85 | COMPLETED | 100% | [9 empty] | SEGUA CONST | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120846 | AGUTAY ES | MARIPIPI | 0 | 1 | 2 | Repair of Classrooms | 749484 | 1 | 386851.28 | COMPLETED | 100% | [9 empty] | SEGUA CONST | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120848 | BINALAYAN ES | MARIPIPI | 0 | 1 | 2 | Repair of Classrooms | 838646 | 1 | 838645.37 | COMPLETED | 100% | [9 empty] | BCG DESIGN AND CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120849 | CALBANI ES | MARIPIPI | 0 | 1 | 1 | Repair of Classroom | 389617 | 1 | 389617.2 | COMPLETED | 100% | [9 empty] | BCG DESIGN AND CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Biliran | 120850 | CANDUHAO ES | MARIPIPI | 0 | 1 | 3 | Repair of Classrooms | 1159960 | 1 | 1159959.18 | COMPLETED | 100% | [9 empty] | MB ANG CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Borongan City | 122358 | Calingatngan ES | BORONGAN CITY(Capital) | 0 | 1 | 9 | Repair of Classrooms | 2808676 | 1 | 2808675.05 | COMPLETED | 100% | [9 empty] | J.A DEVELOPERS AND ENGINEERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Borongan City | 122404 | Locso-on ES | BORONGAN CITY(Capital) | 0 | 1 | 9 | Repair of Classrooms | 2810086 | 1 | 2810085.84 | COMPLETED | 100% | [9 empty] | J.A DEVELOPERS AND ENGINEERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | Repair of Classrooms | 681346 | 1 | 681345.91 | COMPLETED | 100% | [9 empty] | STONE BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124076 | Alang-Alang Elementary School | CALBAYOG CITY | 1 | 1 | 3 | Repair of Classrooms | 1172229 | 1 | 1160700.88 | COMPLETED | 100% | [10 empty] | MORI Builders | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124054 | Bayo Elementary School | CALBAYOG CITY | 1 | 1 | 1 | Repair of classroom | 390525 | 1 | 384884.2 | COMPLETED | 100% | [10 empty] | GBV Construction | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124083 | Cagbayang Elementary School | CALBAYOG CITY | 1 | 1 | 5 | Repair of Classrooms | 1952754 | 1 | 1947085.41 | COMPLETED | 100% | [10 empty] | PEDAD Construction & Supply | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124035 | Cahumpan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 763213 | 1 | 710954.46 | COMPLETED | 100% | [10 empty] | ND Caranzo | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1 | 1 | 8 | Repair of Classrooms | 3059713 | 1 | 2076954.8 | COMPLETED | 100% | [10 empty] | HD Golden Builders | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124087 | Capacuhan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 780025 | 1 | 737498.68 | COMPLETED | 100% | [10 empty] | ND Caranzo | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124088 | Caybago Elementary School | CALBAYOG CITY | 1 | 1 | 4 | Repair of Classrooms | 1600837 | 1 | 1085071.3 | COMPLETED | 100% | [10 empty] | HD Golden Builders | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124064 | Longsob Elementary School | CALBAYOG CITY | 1 | 1 | 1 | Repair of Classroom | 389792 | 1 | 347226.6 | COMPLETED | 100% | [10 empty] | ND Caranzo | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Calbayog City | 124023 | Pagbalican Elementary School | CALBAYOG CITY | 1 | 1 | 2 | Repair of Classrooms | 774944 | 1 | 769467.49 | COMPLETED | 100% | [10 empty] | GBV Construction | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Catbalogan | 123420 | Buluan Elementary School | Catbalogan City | 2 | 1 | 3 | Repair of Classrooms | 1043049 | 1 | 1043048.84 | COMPLETED | 100% | [10 empty] | QCC Construction and Supply | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Catbalogan | 123397 | Catbalogan I Central Elementary School | Catbalogan City | 2 | 1 | 10 | Repair of Classrooms | 3506054 | 1 | 3506053.14 | COMPLETED | 100% | [10 empty] | NV & C CONSTRUCTION AND GENERAL SUPPLY | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Catbalogan | 123425 | Lagundi Elementary School | Catbalogan City | 2 | 1 | 2 | Repair of Classrooms | 699872 | 1 | 699871.6 | COMPLETED | 100% | [10 empty] | AGB CONSTRUCTION AND SUPPLY | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | 0 | 1 | 6 | Repair of Classrooms | 2046940 | 1 | 2031518.8385 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122415 | Cansangaya Elementary School | CAN-AVID | 0 | 1 | 5 | Repair of Classrooms | 1994195 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | 0 | 1 | 14 | Repair of Classrooms | 4360911 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122453 | Hapitan Elementary School | DOLORES | 0 | 1 | 1 | Repair of Classroom | 353104 | 1 | 350428.9355 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122455 | Jicontol Elementary School | DOLORES | 0 | 1 | 6 | Repair of Classrooms | 2202201 | 1 | 2185518.9932 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122484 | Gen. MacArthur Central Elementary School | GENERAL MACARTHUR | 0 | 1 | 21 | Repair of Classrooms | 6402167 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122518 | Banaag Elementary School | GUIUAN | 0 | 1 | 3 | Repair of Classrooms | 1069944 | 1 | 1061883.0115 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122579 | Maylimon Elementary School | JIPAPAD | 0 | 1 | 1 | Repair of Classroom | 372407 | 1 | 369585.0013 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | 4 | Repair of Classrooms | 1510232 | 1 | 1505451.556 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122693 | College Elementary School | SALCEDO | 0 | 1 | 1 | Repair of Classroom | 339709 | 1 | 338633.6771 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122716 | Jagnaya Elementary School | SALCEDO | 0 | 1 | 3 | Repair of Classrooms | 1055580 | 1 | 1052238.1504 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122697 | Malbog Elementary School | SALCEDO | 0 | 1 | 3 | Repair of Classrooms | 1267689 | 1 | 1263676.6166 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Eastern Samar | 122698 | Naparaan Elementary School | SALCEDO | 0 | 1 | 9 | Repair of Classrooms | 3314403 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 303421 | San Agustin National High School | BABATNGON | 1 | 1 | 3 | Repair of Classrooms | 1021071 | 1 | 1021070.85 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121863 | Pinarigusan Primary School | SAN MIGUEL | 1 | 1 | 1 | Repair of Classroom | 423232 | 1 | 423231.17 | COMPLETED | 100% | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1 | 1 | 2 | Repair of Classrooms | 885311 | 1 | 885310.1433 | COMPLETED | 100% | [9 empty] | 4ANGLE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121947 | Canmogsay Elementary School | TOLOSA | 1 | 1 | 3 | Repair of Classrooms | 839984 | 1 | 839983.91 | COMPLETED | 100% | [9 empty] | 4ANGLE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121952 | Olot Elementary School | TOLOSA | 1 | 1 | 3 | Repair of Classrooms | 991438 | 1 | 991437.33 | COMPLETED | 100% | [9 empty] | 4ANGLE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 12 | Repair of Classrooms | 3326367 | 1 | 3326366.83 | COMPLETED | 100% | [9 empty] | C N E CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121042 | Abango Elementary School | BARUGO | 2 | 1 | 3 | Repair of Classrooms | 1018677 | 1 | 1018676.87 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121293 | Dagami North Central School | DAGAMI | 2 | 1 | 3 | Repair of Classrooms | 623315 | 1 | 623314.11 | COMPLETED | 100% | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121314 | Guinarona Elementary School | DAGAMI | 2 | 1 | 8 | Repair of Classrooms | 2056575 | 1 | 2056574.43 | COMPLETED | 100% |  |  |  |  | 2018-07-22 | 2018-08-05 | 2018-08-19 |  |  | JJ PALACIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121316 | Maliwaliw Elementary School | DAGAMI | 2 | 1 | 3 | Repair of Classrooms | 624970 | 1 | 624969.89 | COMPLETED | 100% | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121334 | San Jose Central School | DULAG | 2 | 1 | 5 | Repair of Classrooms | 1541090 | 1 | 1541089.94 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121617 | Casuntingan Elementary School | MACARTHUR | 2 | 1 | 1 | Repair of Classroom | 541219 | 1 | 541218.55 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121814 | Colawen Elementary School | PASTRANA | 2 | 1 | 4 | Repair of Classrooms | 1051632 | 1 | 1051631.79 | COMPLETED | 100% | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121958 | Astorga Elementary School | TUNGA | 2 | 1 | 3 | Repair of Classrooms | 1025655 | 1 | 1025654.45 | COMPLETED | 100% | [9 empty] | KAMARI CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 191556 | Burabod PS | McARTHUR | 3 | 1 | 1 | Repair of Classroom | 387305 | 1 | 387304.76 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121717 | Calunasan Elementary School | MERIDA | 4 | 1 | 9 | Repair of Classrooms | 2076549 | 1 | 2076548.42 | COMPLETED | 100% | [9 empty] | SAMARINAN CONSTRUCTION AND DEVELOPMENT CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121724 | Libjo Elementary School | MERIDA | 4 | 1 | 2 | Repair of Classrooms | 494631 | 1 | 494631 | COMPLETED | 100% | [9 empty] | CERILLES ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121730 | Merida Central School | MERIDA | 4 | 1 | 4 | Repair of Classroom | 771294 | 1 | 771293.2 | COMPLETED | 100% | [9 empty] | CERILLES ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121800 | Parrilla Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 1156231 | 1 | 1156230.15 | COMPLETED | 100% | [9 empty] | QCC CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121808 | Tabunok Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 930301 | 1 | 930300.6 | COMPLETED | 100% | [9 empty] | QCC CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 120904 | Bernardo V. Closa Central School | ABUYOG | 5 | 1 | 7 | Repair of Classrooms | 1267288 | 1 | 1297441.71 | COMPLETED | 100% | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 120900 | Tib-o Elementary School | ABUYOG | 5 | 1 | 3 | Repair of Classrooms | 513525 | 1 | 792280.74 | COMPLETED | 100% | [9 empty] | HD GOLDEN BUILDERS AND SUPPLY INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 303347 | Bato School of Fisheries | BATO | 5 | 1 | 1 | Repair of Classroom | 1534343 | 1 | 1534342.17 | COMPLETED | 100% | [9 empty] | BCG DESIGN AND CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Leyte | 121646 | Paril Elementary School | MAHAPLAG | 5 | 1 | 3 | Repair of Classrooms | 1225422 | 1 | 1225421.53 | COMPLETED | 100% | [9 empty] | BCG DESIGN AND CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 303457 | Guadalupe NHS | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1383064 | 1 | 1383063.87 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-006 | REPAIR-20-006 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 122160 | Hinapu Gamay ES | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1666719 | 1 | 1666718.92 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-003 | REPAIR-20-003 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 303468 | Malapoc Sur NHS | CITY OF MAASIN (Capital) | 0 | 1 | 6 | Repair of Classrooms | 1451962 | 1 | 1451961.18 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-007 | REPAIR-20-007 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 122140 | Matin-Aw ES | CITY OF MAASIN (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1382512 | 1 | 1382511.09 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-001 | REPAIR-20-001 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 122144 | San Isidro MGS | CITY OF MAASIN (Capital) | 0 | 1 | 4 | Repair of Classrooms | 901739 | 1 | 901738.86 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-002 | REPAIR-20-002 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 122175 | Sta. Cruz ES | CITY OF MAASIN (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1675367 | 1 | 1675366.97 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-004 | REPAIR-20-004 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Maasin City | 238001 | Tomoy-Tomoy MGS | CITY OF MAASIN (Capital) | 0 | 1 | 3 | Repair of Classrooms | 685413 | 1 | 685412.48 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 | REPAIR-20-005 | REPAIR-20-005 | 2019-11-21 | 2019-11-29 | 2019-11-12 | 2020-02-13 |  | VHITS D. G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 122812 | Manuel L. Quezon ES | Bobon | 1 | 1 | 4 | Repair of Classrooms | 1317473 | 1 | 809721.4 | COMPLETED | 100% | [9 empty] | J. Custorio Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 122826 | Oson ES | Capul | 1 | 1 | 5 | Repair of Classrooms | 1292094 | 1 | 1006550 | COMPLETED | 100% | [9 empty] | Grinder Civil Eng'g & Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 123084 | Curry ES | Lope de Vega | 1 | 1 | 4 | Repair of Classrooms | 1567753 | 1 | 954140.27 | COMPLETED | 100% | [9 empty] | JCAD Engineering & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 303577 | San Isidro AIHS | San Isidro | 1 | 1 | 14 | Repair of Classrooms | 3471838 | 1 | 2214649.01 | COMPLETED | 100% | [9 empty] | ACHROCONS Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 123275 | Gonzaga ES | Victoria | 1 | 1 | 2 | Repair of Classrooms | 769310 | 1 | 769218.57 | COMPLETED | 100% |  |  | BEFF2019-NS-B2-REPAIR-LOT6 | BEFF2019-NS-B2-REPAIR-LOT6 | 2019-08-01 | 2019-08-08 | 2019-08-20 |  |  | ACF Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 123278 | Lungib ES | Victoria | 1 | 1 | 7 | Repair of Classrooms | 1399544 | 1 | 1398625.31 | COMPLETED | 100% | [9 empty] | ACF Const. & Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 122898 | Hibubullao ES | Catubig | 2 | 1 | 12 | Repair of Classrooms | 4050183 | 1 | 2545200 | COMPLETED | 100% | [9 empty] | J. Custorio Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 123108 | Mapanas CS | Mapanas | 2 | 1 | 10 | Repair of Classrooms | 2836215 | 1 | 1899450 | COMPLETED | 100% | [9 empty] | J. Custorio Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Northern Samar | 303584 | Sumoroy AIHS | Palapag | 2 | 1 | 47 | Repair of Classrooms | 16132693 | 1 | 10305280 | COMPLETED | 100% | [9 empty] | J. Custorio Const. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124143 | Alta Vista Elementary School | ORMOC CITY | 4 | 1 | 1 | Repair of Classroom | 385187 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124144 | Bagong ES | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1954500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124174 | Cabato-an Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 944555 | 1 |  | COMPLETED | 100% | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L4 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 |  | rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124175 | Cagbuhangin Elementary School | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1806239 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124148 | Can-adieng ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 760000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124149 | Can-untog Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 955206 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124177 | Concepcion ES | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 1213000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124150 | Dolores ES | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 845000 | 1 | 221248.6542 | COMPLETED | 100% |  |  |  | 2019-BEFF-R-B1-C1 | January 31, 2019 | January 30, 2019 | February 11, 2019 | February 18, 2019 | August 27, 2019 | J. CUSTORIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124152 | Donghol Elementary School | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1659807 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124153 | Gaas ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 825000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124180 | Inaad Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 1120229 | 1 | 1120228.6 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L2 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | Melgazo Construction and Supply | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124181 | Juaton Elementary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 763431 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124158 | Liberty ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 810000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124159 | Luna ES | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 465000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124162 | Magaswe Primary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 777275 | 1 |  | COMPLETED | 100% | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L4 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 |  | rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124163 | Maglahug ES | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 900000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124164 | Mahayag Elementary School | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 1860468 | 1 | 1860467.34 | COMPLETED | 100% | January 0, 1900 | January 0, 1900 |  | BEFF-2020-REPAIR-B1-L3 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | Melgazo Construction and Supply | RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124166 | Milagro ES | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 465000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124217 | Nasunogan Elementary School | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 1331276 | 1 | 1331275.59 | COMPLETED | 100% |  |  |  | BEFF-2020-REPAIR-B1-L1 | 2019-11-20 | 2019-11-29 | 2019-12-11 | 2019-01-06 | January 0, 1900 | QCC Construction and Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124187 | Nueva Vista ES | ORMOC CITY | 4 | 1 | 6 | Repair of Classrooms | 1512000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124167 | Patag Elementary School | ORMOC CITY | 4 | 1 | 5 | Repair of Classrooms | 2279928 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124191 | T. Aviles Elementary School | ORMOC CITY | 4 | 1 | 9 | Repair of Classrooms | 3229803 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Ormoc City | 124193 | Valencia Central School | ORMOC CITY | 4 | 1 | 15 | Repair of Classrooms | 2351774 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123285 | ALMAGRO CS | ALMAGRO | 1 | 1 | 8 | Repair of Classrooms | 3377152 | 1 | 3377151.28 | COMPLETED | 100% | [8 empty] | 2020-09-23 | VHITS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123288 | COSTA RICA ELEM.SCHOOL | ALMAGRO | 1 | 1 | 4 | Repair of Classrooms | 1718248 | 1 | 1718247.44 | COMPLETED | 100% | [8 empty] | 2020-09-23 | MAGA CONSTRUCTION AND SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123292 | LUNANG I CS | ALMAGRO | 1 | 1 | 4 | Repair of Classrooms | 1544706 | 1 | 1544705.86 | COMPLETED | 100% | [8 empty] | 2020-09-23 | REVCON | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123537 | CANHUMAWID ES | GANDARA | 1 | 1 | 2 | Repair of Classrooms | 909886 | 1 | 909885.62 | COMPLETED | 100% | [8 empty] | 2020-09-23 | SLHAV | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123553 | PIZARRO ES | GANDARA | 1 | 1 | 5 | Repair of Classrooms | 1912618 | 1 | 1912617.36 | COMPLETED | 100% | [8 empty] | 2020-09-23 | TUBIGAN BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123816 | BAQUIW ES | TAGAPUL-AN | 1 | 1 | 3 | Repair of Classrooms | 1158604 | 1 | 1158603.81 | COMPLETED | 100% | [8 empty] | 2020-09-23 | GG | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123308 | BASIAO ES | BASEY | 2 | 1 | 9 | Repair of Classrooms | 3980962 | 1 | 3980961.4 | COMPLETED | 100% | [8 empty] | 2020-09-23 | EMT | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123313 | CATADMAN ES | BASEY | 2 | 1 | 2 | Repair of Classrooms | 954532 | 1 | 949436.02 | COMPLETED | 100% | [8 empty] | 2020-09-23 | G BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123317 | LOOG ES | BASEY | 2 | 1 | 4 | Repair of Classrooms | 1575134 | 1 | 1575133.23 | COMPLETED | 100% | [8 empty] | 2020-09-23 | TRIPLE Z- MC | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123322 | RAWIS ES | BASEY | 2 | 1 | 12 | Repair of Classrooms | 4903375 | 1 | 4903374.25 | COMPLETED | 100% | [8 empty] | 2020-09-23 | MAGA | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123325 | SERUM ES | BASEY | 2 | 1 | 3 | Repair of Classrooms | 1143309 | 1 | 1143308.36 | COMPLETED | 100% | [8 empty] | 2020-09-23 | GPUY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123354 | Tinaogan ES | BASEY | 2 | 1 | 2 | Repair of Classrooms | 602388 | 1 | 597314.94 | COMPLETED | 100% | [8 empty] | 2020-09-23 | G BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123580 | TABAY ES | hinabangan | 2 | 1 | 2 | Repair of Classrooms | 771789 | 1 | 771788.76 | COMPLETED | 100% | [8 empty] | 2020-09-23 | PLGL | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123604 | SAN FERNANDO ES | JIABONG | 2 | 1 | 1 | Repair of Classroom | 365779 | 1 | 365778.92 | COMPLETED | 100% | [8 empty] | 2020-09-23 | PLGL | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123642 | Motiong Central Elem. School | MOTIONG | 2 | 1 | 8 | Repair of Classrooms | 3077837 | 1 | 3077836.5 | COMPLETED | 100% | [8 empty] | 2020-09-23 | JC | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Samar (Western Samar) | 123659 | Bangon ES | PINABACDAO | 2 | 1 | 8 | Repair of Classrooms | 3226729 | 1 | 3226728.53 | COMPLETED | 100% | [8 empty] | 2020-09-23 | EMT | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122074 | Mahalo Elementary School | ANAHAWAN | 0 | 1 | 4 | Repair of Classroom | 1280614 | 1 | 1280613.96 | COMPLETED | 100% | 2021-01-13 | January 0, 1900 | BEFF-CY2020- REPAIR-L1 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 121993 | Banahao Multi-Grade Elementary School | BONTOC | 0 | 1 | 2 | Repair of Classrooms | 663664 | 1 | 663663.17 | COMPLETED | 100% | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L6 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | J'NER CEPADA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122085 | Tigbao Elementary School | LIBAGON | 0 | 1 | 9 | Repair of Classrooms | 3075638 | 1 | 3075637.02 | COMPLETED | 100% | 2021-02-12 | January 0, 1900 | BEFF-CY2020- REPAIR-L3 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 0 | 1 | 22 | Repair of Classrooms | 7217394 | 1 | 7217393.56 | COMPLETED | 100% | 2021-03-14 | January 0, 1900 | BEFF-CY2020- REPAIR-L4 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122300 | Panian Elementary School | SAINT BERNARD | 0 | 1 | 3 | Repair of Classrooms | 997824 | 1 | 997823.57 | COMPLETED | 100% | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L2 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 0 | 1 | 16 | Repair of Classrooms | 5806035 | 1 | 5806034.2 | COMPLETED | 100% | 2021-03-14 | January 0, 1900 | BEFF-CY2020- REPAIR-L5 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Southern Leyte | 122266 | Kanangkaan Elementary School | SOGOD | 0 | 1 | 4 | Repair of Classrooms | 1440270 | 1 | 1440269.29 | COMPLETED | 100% | 2021-01-06 | January 0, 1900 | BEFF-CY2020- REPAIR-L6 |  | 2019-11-24 | 2019-12-09 | 2020-01-07 | 2020-03-02 | 2020-10-08 | J'NER CEPADA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 195001 | Manlurip Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 652167 | 1 | 652166.89 | COMPLETED | 100% | [9 empty] | RD COBACHA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 303664 | Marasbaras NHS | TACLOBAN CITY (Capital) | 1 | 1 | 19 | Repair of Classrooms | 2061155 | 1 | 2061154.36 | COMPLETED | 100% | [9 empty] | ARCHO CONS CORP. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 124237 | Old Kawayan Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 513031 | 1 | 513030.49 | COMPLETED | 100% | [9 empty] | PYUKIE CONSTRUCTION INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 124238 | Palanog ES | TACLOBAN CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 1233854 | 1 | 870269.84 | COMPLETED | 100% | [9 empty] | PYUKIE CONSTRUCTION INC. | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 124249 | San Fernando Central School | TACLOBAN CITY (Capital) | 1 | 1 | 18 | Repair of Classrooms | 2389725 | 1 | 2389724.01 | COMPLETED | 100% | [9 empty] | UNITRON CONSTRUCTION & DEV'T CORPORATION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 124251 | San Roque ES | TACLOBAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 677216 | 1 | 677215.32 | COMPLETED | 100% | [9 empty] | RD COBACHA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region VIII | Tacloban City | 124241 | Sto. Nino Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 9 | Repair of Classrooms | 870270 | 1 | 870269.84 | COMPLETED | 100% | [9 empty] | VHITS D. G BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126818 | Sagaran ES | TALAKAG | 1 | 1 | 4 | Repair of Classrooms | 1006621 | 1 |  | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126779 | Intavas Elementary School | IMPASUG-ONG | 2 | 1 | 6 | Repair of Classrooms | 1725348 | 1 |  | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126497 | Babahagon ES | LANTAPAN | 2 | 1 | 5 | Repair of Classrooms | 2035461 | 1 |  | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | Rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126354 | Maraymaray ES | DON CARLOS | 3 | 1 | 11 | Repair of Classrooms | 4066050 | 1 | 4066049.62 | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126365 | San Nicolas ES | DON CARLOS | 3 | 1 | 19 | Repair of Classrooms | 5090229 | 1 | 5090228.1 | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126395 | Balaoro ES | KADINGILAN | 3 | 1 | 2 | Repair of Classrooms | 913873 | 1 | 913872.63 | COMPLETED | 100% |  |  | PB-02-01-2020-0003 |  | January 23, 2020 | January 31, 2020 | February 12, 2020 |  |  |  | AWAITING FOR SUB-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126414 | Barorawon Elementary School | KALILANGAN | 4 | 1 | 7 | Repair of Classrooms | 2222638 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126423 | Kibaritan ES | KALILANGAN | 4 | 1 | 2 | Repair of Classrooms | 935495.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126678 | BALMAR ELEMENTARY SCHOOL | PANGANTUCAN | 4 | 1 | 5 | Repair of Classrooms | 1690252.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126685 | Kimanait ES | PANGANTUCAN | 4 | 1 | 2 | Repair of Classrooms | 1071961.79 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Bukidnon | 126693 | New Iloilo ES | PANGANTUCAN | 4 | 1 | 4 | Repair of Classrooms | 1900000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Cagayan de Oro City | 127957 | North City Central School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1708745 | 1 | 1708744.56 | COMPLETED | 100% |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | Brima Const. | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Cagayan de Oro City | 304124 | Puntod National High School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 16 | Repair of Classrooms | 2744803 | 1 | 2744802.27 | COMPLETED | 100% |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | JARM Const. | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Cagayan de Oro City | 127958 | St. John Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 5 | Repair of Classrooms | 1025981 | 1 | 1025980.57 | COMPLETED | 100% |  |  |  |  | 2020-01-13 | 2020-01-20 | 2020-02-03 |  |  | Brima Const. | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Camiguin | 126887 | Compol ES | CATARMAN | 0 | 1 | 5 | Repair of Classrooms | 2555182 | 1 | 2555181.99 | COMPLETED | 100% | [10 empty] | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Camiguin | 126922 | Volcan ES | MAMBAJAO (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1356240 | 1 | 1356239.24 | COMPLETED | 100% | [10 empty] | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Camiguin | 126934 | MANUYOG ES | SAGAY | 0 | 1 | 1 | Repair of Classroom | 610453 | 1 | 610452.81 | COMPLETED | 100% | [10 empty] | Waiting for Sub-ARO | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | El Salvador | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | 11 | Repair of Classrooms | 5475269 | 1 |  | COMPLETED | 100% | [10 empty] | Under-procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Gingoog City | 128007 | Anakan Central School | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1848904 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Gingoog City | 128016 | Elpidio Galarion Ampatin PS (Mangilit PS) | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1838607 | 1 |  | COMPLETED | 100% | [10 empty] | with issue on peace and order | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Gingoog City | 128044 | Tagdaging Elementary School | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 1839227 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Iligan City | 128153 | Bernardo E. Ramos Memorial School | ILIGAN CITY | 0 | 1 | 3 | Repair of Classrooms | 553054 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Iligan City | 128090 | Iligan City SPED Center | ILIGAN CITY | 0 | 1 | 18 | Repair of Classrooms | 2171114 | 1 |  | COMPLETED | 100% | [10 empty] | WITH LD | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Iligan City | 128103 | Mandulog ES | ILIGAN CITY | 0 | 1 | 10 | Repair of Classrooms | 1469000 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Iligan City | 128087 | Servillano G. Reuyan Memorial Elementary School | ILIGAN CITY | 0 | 1 | 4 | Repair of Classrooms | 721717 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Iligan City | 128144 | Villaverde ES | ILIGAN CITY | 0 | 1 | 12 | Repair of Classrooms | 1601250 | 1 |  | COMPLETED | 100% | [10 empty] | WITH LD | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 126945 | Minaulon Elementary School | BACOLOD | 1 | 1 | 4 | Repair of Classrooms | 1126939 | 1 | 1126938.04 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Yamar Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 126947 | Rufino Santos Sr MES | BACOLOD | 1 | 1 | 5 | Repair of Classrooms | 1662788 | 1 | 1662787.66 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Yamar Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 126948 | Rupagan ES | BACOLOD | 1 | 1 | 7 | Repair of Classrooms | 1695571 | 1 | 1695570.93 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 126983 | Pendulonan PS | BAROY | 1 | 1 | 2 | Repair of Classrooms | 788032 | 1 | 788031.04 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127056 | Libertad ES | KOLAMBUGAN | 1 | 1 | 2 | Repair of Classrooms | 740972 | 1 | 740971.71 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127110 | Atanacia Logronio ES (Segapod ES) | MAIGO | 1 | 1 | 6 | Repair of Classrooms | 1804270 | 1 | 1804269.16 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127115 | Liangan West ES | MAIGO | 1 | 1 | 5 | Repair of Classrooms | 1399695 | 1 | 1399694.96 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Lanao Genesis Construction Supply | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127237 | Kakai-Renabor ES | TUBOD (Capital) | 1 | 1 | 5 | Repair of Classrooms | 1416436 | 1 | 1416435.36 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Millenium Builders & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 315102 | Lanao del Norte Provincial Science and Technology HS (former Malingao NHS (Annex New Pualas NHS) | TUBOD (Capital) | 1 | 1 | 14 | Repair of Classrooms | 3759554 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127228 | Malingao Central School | TUBOD (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2771299 | 1 | 2771298.55 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Millenium Builders & Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Lanao del Norte | 127086 | Maranding CES | LALA | 2 | 1 | 1 | Repair of Multi-Purpose Bldg. | 2655805 | 1 | 2655804.75 | COMPLETED | 100% |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-02-24 |  | Inmar Builders | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Malaybalay City | 126550 | Miglamin ES | CITY MALAYBALAY (Capital) | 2 | 1 | 15 | Repair of Classrooms | 4054554 | 1 | 4054553.38 | COMPLETED | 100% |  |  | 002-INFRA -2020-001 | 002-INFRA -2020-001 | 2020-01-30 | 2020-02-07 | 2020-02-19 |  |  |  | Under-procurement | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127326 | Pestanas ES | CALAMBA | 1 | 1 | 3 | Repair of Classrooms | 1006093 | 1 | 1006092.03 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127419 | Lopez Jaena CS | LOPEZ JAENA | 1 | 1 | 22 | Repair of Classrooms | 7286935 | 1 | 7286934.67 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127483 | Panaon CES | PANAON | 1 | 1 | 23 | Repair of Classrooms | 6066929 | 1 | 6066928.88 | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127286 | Bagong Anonang Diut ES | BONIFACIO | 2 | 1 | 1 | Repair of Classroom | 404547 | 1 | 404546.21 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127342 | Lupagan Elementary School | CLARIN | 2 | 1 | 3 | Repair of Classrooms | 924746 | 1 | 924745.55 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127357 | Sebasi ES | CLARIN | 2 | 1 | 1 | Repair of Classroom | 370302 | 1 | 370301.95 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2 | 1 | 7 | Repair of Classrooms | 2430598 | 1 | 1797255.26 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 127826 | Portulin ES | MEDINA | 1 | 1 | 3 | Repair of Classrooms | 1149685 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 127585 | Baybay ES | ALUBIJID | 2 | 1 | 4 | Repair of Classrooms | 1573035 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 127588 | Lagtang ES | ALUBIJID | 2 | 1 | 3 | Repair of Classrooms | 1176407 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 127695 | Sinalac ES | INITAO | 2 | 1 | 3 | Repair of Classrooms | 1480061 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 127920 | Tubajon ES | LAGUINDINGAN | 2 | 1 | 6 | Repair of Classrooms | 2233191 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Misamis Oriental | 501158 | Tuod ES | MANTICAO | 2 | 1 | 9 | Repair of Classrooms | 3256655 | 1 |  | COMPLETED | 100% | [10 empty] | For RTA | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Oroquieta City | 127448 | Malindang ES | OROQUIETA CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2377623 | 1 | 2377622.68 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Oroquieta City | 127467 | Rizal ES | OROQUIETA CITY (Capital) | 1 | 1 | 10 | Repair of Classrooms | 3496604 | 1 | 3496603.59 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Oroquieta City | 127461 | Tuyabang Proper ES | OROQUIETA CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 689469 | 1 | 689468.57 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Ozamis City | 128173 | Antero D. Hinagdanan Elementary School | OZAMIS CITY | 2 | 1 | 4 | Repair of Classrooms | 1426384 | 1 | 1426383.73 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Ozamis City | 304163 | Labo National High School | OZAMIS CITY | 2 | 1 | 7 | Repair of Classrooms | 2804615 | 1 | 2804614.34 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2 | 1 | 10 | Repair of Classrooms | 3046802 | 1 | 3046801.1 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Tangub City | 128247 | Matugnao ES | TANGUB CITY | 2 | 1 | 3 | Repair of Classrooms | 930033 | 1 |  | COMPLETED | 100% |  |  | Repair2020-RX-Tangub City-004 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Tangub City | 128250 | Panalsalan ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1786304 | 1 |  | COMPLETED | 100% |  |  | Repair2020-RX-Tangub City-011 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Tangub City | 128214 | San Apolinario ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1786304 | 1 |  | COMPLETED | 100% |  |  | Repair2020-RX-Tangub City-008 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Tangub City | 128235 | Tituron ES | TANGUB CITY | 2 | 1 | 6 | Repair of Classrooms | 1781946 | 1 |  | COMPLETED | 100% |  |  | Repair2020-RX-Tangub City-002 |  | 2020-01-14 | 2020-01-24 | 2020-02-05 |  |  |  | for contract signing | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region X | Valencia City | 126844 | Liloan ES | CITY OF VALENCIA | 4 | 1 | 4 | Repair of Classrooms | 1298766 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128386 | Mahayahay ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | Repair of Classrooms | 1570356 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128395 | New Panay ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 3 | Repair of Classrooms | 1708204 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128399 | Saranga ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 2 | Repair of Classrooms | 1347567 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128437 | Mamonga ES | MONKAYO | 1 | 1 | 5 | Repair of Classrooms | 2615886 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2 | 1 | 10 | Repair of Classrooms | 3150185 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128338 | Masicareg ES | MABINI (DOÑA ALICIA) | 2 | 1 | 2 | Repair of Classrooms | 1096959 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128363 | Anislagan ES | MACO | 2 | 1 | 8 | Repair of Classrooms | 3829945 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128348 | Gayab ES | MACO | 2 | 1 | 9 | Repair of Classrooms | 4621970 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Compostela Valley | 128536 | Biasong ES | PANTUKAN | 2 | 1 | 3 | Repair of Classrooms | 963259 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 206005 | Pamantawan PS | DAVAO CITY | 2 | 1 | 10 | Repair of Classrooms | 3457811 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Sub-aro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 129568 | Kanacan ES | DAVAO CITY | 3 | 1 | 9 | Repair of Classrooms | 3526407 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Sub-aro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 11 | Repair of Classrooms | 3718419 | 1 |  | COMPLETED | 100% | [10 empty] | Waiting for Sub-aro | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128651 | Domingo B. Hain Elementary School | KAPALONG | 1 | 1 | 12 | Repair of Classrooms | 6617873 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 500849 | Macgum Integrated School | NEW CORELLA | 1 | 1 | 6 | Repair of Classrooms | 3083628 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128615 | Balisong ES | BRAULIO E. DUJALI | 2 | 1 | 9 | Repair of Classrooms | 4050000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128624 | Alejal Elementary School | CARMEN | 2 | 1 | 11 | Repair of Classrooms | 5500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128627 | Carmen CES SPED CENTER | CARMEN | 2 | 1 | 20 | Repair of Classrooms | 14058726.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 315904 | La Paz National High School | CARMEN | 2 | 1 | 9 | Repair of Classrooms | 4950000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128640 | Sto Niño ES | CARMEN | 2 | 1 | 5 | Repair of Classrooms | 2900000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Norte | 128750 | La Libertad ES | SANTO TOMAS | 2 | 1 | 6 | Repair of Classrooms | 3015641 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128829 | Eman ES | BANSALAN | 0 | 1 | 9 | Repair of Classrooms | 3261000 | 1 |  | reverted | 0% | [10 empty] | The Project was not implement because the buildings to be repair is beyond repair due to a series of earthquake on year 2019 | [12 empty] | 0% | [7 empty] | reverted
REPAIR 2020 | Region XI | Davao del Sur | 128908 | Latian ES | KIBLAWAN | 0 | 1 | 8 | Repair of Classrooms | 2715310 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128909 | Manual ES | KIBLAWAN | 0 | 1 | 10 | Repair of Classrooms | 3722304 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128931 | Bacungan ES | MAGSAYSAY | 0 | 1 | 12 | Repair of Classrooms | 5044913 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 128948 | Bulacan ES | MALALAG | 0 | 1 | 22 | Repair of Classrooms | 6927965 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao del Sur | 129047 | Malinao ES | PADADA | 0 | 1 | 13 | Repair of Classrooms | 4787067 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128961 | Aglaungan Elementary School | MALITA | 0 | 1 | 3 | Repair of Classrooms | 1263922 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128962 | Procopio Mejellano Sr. Elementary School | MALITA | 0 | 1 | 5 | Repair of Classrooms | 2569431 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 128985 | Talogoy Elementary School | MALITA | 0 | 1 | 11 | Repair of Classrooms | 4556287 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Occidental | 129011 | Upper Ticulon ES | MALITA | 0 | 1 | 8 | Repair of Classrooms | 3756459 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 129242 | Pantuyan ES | CARAGA | 1 | 1 | 19 | Repair of Classrooms | 5743782 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 304309 | Cateel Nat'l. Agri. HS | CATEEL | 1 | 1 | 11 | Repair of Classrooms | 4105851 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 129270 | San Alfonso ES | CATEEL | 1 | 1 | 18 | Repair of Classrooms | 5124985 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Davao Oriental | 500417 | Jose Antop, Sr. San Isidro Integrated School | MANAY | 1 | 1 | 11 | Repair of Classrooms | 3495256 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Digos City | 206501 | Bagumbuhay ES | CITY OF DIGOS (Capital) | 1 | 1 | 3 | Repair of Classrooms | 765925 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Digos City | 129759 | Ruparan ES | CITY OF DIGOS (Capital) | 1 | 1 | 5 | Repair of Classrooms | 1956676 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Island Garden City of Samal | 128599 | Balet Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 14 | Repair of Classrooms | 6907504 | 1 |  | COMPLETED | 100% | [10 empty] | Rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Island Garden City of Samal | 128688 | Don Esteban Dasalla Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 7 | Repair of Classrooms | 2274970 | 1 |  | COMPLETED | 100% | [10 empty] | Rebid | [12 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2 | 1 | 13 | Repair of Classrooms | 5704593 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Mati City | 304326 | Mati SAT | CITY OF MATI (Capital) | 2 | 1 | 39 | Repair of Classrooms | 32082132 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Panabo City | 129807 | Katipunan ES | CITY OF PANABO | 2 | 1 | 3 | Repair of Classrooms | 1698435 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Panabo City | 207002 | San Francisco ES | CITY OF PANABO | 2 | 1 | 12 | Repair of Classrooms | 4516674 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XI | Tagum City | 128774 | FLORENTINO CATALAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 19 | Repair of Classrooms | 6211673 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | City of Tacurong | 131219 | AMADO FERNANDEZ SR. CES | CITY OF TACURONG | 1 | 1 | 12 | Repair of Classrooms | 5213289 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | City of Tacurong | 131227 | SAN ANTONIO ES | CITY OF TACURONG | 1 | 1 | 6 | Repair of Classrooms | 2402967 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | General Santos City | 317004 | Elias Buscano Sr. High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 5 | Repair of Classrooms | 1574730 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | General Santos City | 131291 | Sarif Mucsin Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 13 | Repair of Classrooms | 4444243 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Kidapawan City | 131349 | Sibawan Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2890817 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Koronadal City | 131404 | Engkong ES | CITY OF KORONADAL (Capital) | 2 | 1 | 8 | Repair of classrooms | 2911633 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 129847 | Polayagan ES | Alamada | 1 | 1 | 8 | Repair of Classrooms | 3033956 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130195 | Central Bulanan ES | Midsayap | 1 | 1 | 5 | Repair of Classrooms | 1762770 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 316515 | Malibatuan HS - Ganatan Annex | Arakan | 2 | 1 | 5 | Repair of Classrooms | 1951383 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 316534 | Meocan High School | Arakan | 2 | 1 | 2 | Repair of Classrooms | 762404 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130151 | Kibia CES | Matalam | 2 | 1 | 16 | Repair of Classrooms | 5640974 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130016 | Malabuaya ES | Kabacan | 3 | 1 | 6 | Repair of Classrooms | 2299825 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130255 | Bagontapay CES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 954546 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130408 | Lampagang ES | Tulunan | 3 | 1 | 4 | Repair of classrooms | 1412060 | 1 |  | COMPLETED | 100% |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130439 | Tokawal ES | Alabel | 0 | 1 | 10 | Repair of classrooms | 3556420 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500297 | Spring IS | ALABEL (Capital) | 0 | 1 | 3 | Repair of classrooms | 2230024 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500795 | Glan Central Integrated SPED Center | Glan | 0 | 1 | 2 | Repair of classrooms | 735805 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500281 | Wali Integrated School | Maitum | 0 | 1 | 10 | Repair of classrooms | 7611720 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500711 | Francisco A. Cagang Sr. Integrated School | Malapatan | 0 | 1 | 6 | Repair of classrooms | 5236787 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130577 | Malalag Cogon ES | Malungon | 0 | 1 | 10 | Repair of classrooms | 4189694 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130621 | San Roque ES | Malungon | 0 | 1 | 10 | Repair of classrooms | 6883419 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130904 | Ricardo O. Avila Memorial Elementary School | TUPI | 1 | 1 | 8 | Repair of Classrooms | 2512269 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130908 | Simbo ES | TUPI | 1 | 1 | 5 | Repair of Classrooms | 1997101 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130635 | Matlong Elementary School | BANGA | 2 | 1 | 9 | Repair of Classrooms | 3078617 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130642 | Rizal ES | Banga | 2 | 1 | 21 | Repair of Classrooms | 6346541 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131089 | Kapingkong Central Elementary School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 12 | Repair of Classrooms | 4817960 | 1 |  | COMPLETED | 100% | Mar. 15, 2021 |  |  | 2020-008 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Palmares Gen. Merchandise | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131001 | Magsaysay Elementary School | Esperanza | 2 | 1 | 5 | Repair of Classrooms | 1511627 | 1 |  | COMPLETED | 100% | Apr. 14, 2021 | Feb. 15, 2021 |  | 2020-007 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Cofejok Construction & Supply Corporation | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131115 | Celeste Central Elementary School | Lebak | 2 | 1 | 3 | Repair of Classrooms | 1357010 | 1 |  | COMPLETED | 100% | Mar. 15, 2021 | Feb. 15, 2021 |  | 2020010 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | KLD Engineering Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131127 | F. Parohinog Sr. Memorial Elementary School | Lebak | 2 | 1 | 8 | Repair of Classrooms | 2698003 | 1 |  | COMPLETED | 100% | Apr. 14, 2021 | Jun. 10, 2021 |  | 2020-011 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Bamec Developer | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131113 | Nuling Elementary School | Lebak | 2 | 1 | 6 | Repair of Classrooms | 2222211 | 1 |  | COMPLETED | 100% | Mar. 15, 2021 | Jun. 10, 2021 |  | 2020-009 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Bamec Developer | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | BARMM | Basilan | 133137 | Bato-Bato ES | AKBAR | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133186 | Caddayan ES | AKBAR | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133196 | Languyan ES | HADJI MOHAMMAD AJUL | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133062 | Landungan ES | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133072 | Lukbaldaya PS | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133046 | Tairan ES | LANTAWAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 304934 | Bubuan NHS-Saluping Annex | TABUAN-LASA | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 304954 | Tipo-Tipo NHS | TIPO-TIPO | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Basilan | 133152 | Pipil ES | UNGKAYA PUKAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Cotabato City | 131260 | Datu Usman Elementary School | COTABATO CITY | 1 | 1 | 6 | Repair of classrooms | 3000000 | 1 |  | under procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | under procurement
REPAIR 2021 | BARMM | Lamitan City | 132998 | Colony Central Elementary School | CITY OF LAMITAN | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133224 | Nusa ES | BALINDONG (WATU) | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304960 | Buadiposo-Buntong NHS | BUADIPOSO-BUNTONG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 324601 | Datu Mamintal Adiong Sr. Mem. NHS | BUBONG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133270 | Buaya-an Elementary School | DITSAAN-RAMAIN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304968 | Mangurun Memorial NHS | KAPAI | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 304971 | Mulondo NHS | MULONDO | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133451 | Saguiaran CES | SAGUIARAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 133293 | Mimbaguiang ES | TAGOLOAN II | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - I | 318118 | Johayver Maulana NHS | TARAKA | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133784 | Ngingir Elementary School | CALANOGAS | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133586 | Don Pablo Hofer ES | KAPATAGAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133678 | Beta Elementary School | LUMBACA-UNAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133846 | Tangcal Central Elementary School | TUBARAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Lanao del Sur - II | 133858 | Tugaya Central Elementary School | TUGAYA | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134200 | Macasampen ES | GUINDULUNGAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134132 | Libutan ES | MAMASAPANO | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 318310 | Sapakan NHS | RAJAH BUAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao I | 134197 | Kalantungan ES | TALAYAN | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 133930 | Raranaon ES | BULDON | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 134275 | Datu Sa Biwang ES | DATU BLAH T. SINSUAT | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 133990 | Capiton PS | DATU ODIN SINSUAT (DINAIG) | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Maguindanao II | 318325 | Datu Alamanza Dilangalen NHS | NORTHERN KABUNTALAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Marawi City | 318607 | Bacarat Memorial National H/S | MARAWI CITY | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134299 | Bwansa Elementary School | INDANAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134454 | Lapa ES | MAIMBUNG | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134488 | Bowal Bowal ES | PANGUTARAN | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134555 | Kadday Mampalam ES | PATIKUL | 1 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Sulu | 134478 | Panglima Agga Central School | OLD PANAMAO | 2 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134686 | Batu-Batu Central School | PANGLIMA SUGALA (BALIMBING) (Capital) | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134810 | Lawm Sikubong ES | SAPA-SAPA | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134832 | Talisay ES | SIBUTU | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 305057 | Manuk Mangkaw NHS | SIMUNUL | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | BARMM | Tawi-Tawi | 134774 | Taganak ES | TURTLE ISLANDS | 0 | 1 | 3 | Repair of Classrooms | 500000 | 1 |  | Under Procurement | 0% | [23 empty] | 0% |  | 0 | [5 empty] | Under Procurement
REPAIR 2021 | CAR | Abra | 134974 | Sappaac ES | BANGUED (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3174289.69 | 1 | 3164484.93 | COMPLETED | 100% | 2022-04-13 | 2021-12-20 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135188 | Lingey Elementary School | BUCLOC | 0 | 1 | 7 | Repair of Classrooms | 4460075.37 | 1 | 4452189.68 | COMPLETED | 100% | 2022-04-13 | 2021-12-20 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | 0 | 1 | 9 | Repair of Classrooms | 6491846.5 | 1 | 6481279.72 | COMPLETED | 100% | 2022-04-13 | 2021-12-20 | CAR-ABRA-2019-010 |  | 2018-05-12 | 2018-12-10 | 2018-12-22 | 2018-12-28 | 2019-08-09 | LONNIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135027 | Benben PS | LA PAZ | 0 | 1 | 1 | Repair of Classroom | 648764.09 | 1 | 638826.36 | COMPLETED | 100% | 2022-05-23 | 2021-12-20 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135034 | Liguis ES | LA PAZ | 0 | 1 | 9 | Repair of Classrooms | 6821548.24 | 1 | 6806714.7 | COMPLETED | 100% | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135037 | Mudeng ES | LA PAZ | 0 | 1 | 10 | Repair of Classrooms | 7984480.95 | 1 | 7971266.95 | COMPLETED | 100% | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135041 | San Gregorio ES | LA PAZ | 0 | 1 | 11 | Repair of Classrooms | 5732676.73 | 1 | 5721407.05 | COMPLETED | 100% | 2021-04-13 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 218514 | Taping Primary School | LAGANGILANG | 0 | 1 | 2 | Repair of Classrooms | 1178716.27 | 1 | 1173557.22 | COMPLETED | 100% | 2022-04-13 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135060 | Diangay PS | LICUAN-BAAY (LICUAN) | 0 | 1 | 3 | Repair of Classrooms | 2682252.16 | 1 | 2668754.31 | COMPLETED | 100% | 2022-04-13 | 2021-11-12 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135086 | Agumanay ES | LUBA | 0 | 1 | 3 | Repair of Classrooms | 4635039.19 | 1 | 4626110.79 | COMPLETED | 100% | 2022-06-06 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135108 | Pega PS | LUBA | 0 | 1 | 2 | Repair of Classrooms | 1850476.27 | 1 | 1839361.97 | COMPLETED | 100% | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 134996 | Liagan PS | MANABO | 0 | 1 | 2 | Repair of Classrooms | 1570561.53 | 1 | 1555567.3 | COMPLETED | 100% | 2022-04-13 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135146 | Suyo Pilot ES | PIDIGAN | 0 | 1 | 7 | Repair of Classrooms | 4388345.16 | 1 | 4375458.03 | COMPLETED | 100% | 2022-06-06 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305077 | Bolbolo NHS | PILAR | 0 | 1 | 4 | Repair of Classrooms | 1344048.55 | 1 | 1339014.87 | COMPLETED | 100% | 2022-04-13 | 2021-11-12 | CAR-ABRA-2019-019 |  | 2019-07-02 | 2019-07-08 | 2019-07-22 | 2019-07-25 | 2019-09-09 | LONNIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 | 1 | 9 | Repair of Classrooms | 5567452.93 | 1 | 5558175.15 | COMPLETED | 100% | 2022-06-06 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | 0 | 1 | 5 | Repair of Classrooms | 4718508.77 | 1 | 4710435.02 | COMPLETED | 100% | 2022-06-06 | 2021-12-20 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 109752 | Manicbel PS | Sallapadan | 0 | 1 | 2 | Repair of Classrooms | 2041138.48 | 1 | 2051020.63 | COMPLETED | 100% | 2022-05-23 | 2021-12-20 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 12 | Repair of Classrooms | 7414928.15 | 1 | 7409546.13 | COMPLETED | 100% | 2022-04-13 | 2021-12-20 | CAR-ABRA-2019-017 |  | 2019-07-02 | 2019-07-08 | 2019-07-22 | 2019-07-25 | 2019-09-09 | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135096 | Dacuag PS | TUBO | 0 | 1 | 2 | Repair of Classrooms | 2393325.74 | 1 | 2389794.93 | COMPLETED | 100% | 2021-04-13 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135279 | Sacpil ES | CONNER | 0 | 1 | 6 | Repair of Classrooms | 3768428.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135319 | Madatag ES | KABUGAO (Capital) | 0 | 1 | 6 | Repair of Classrooms | 3795597.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135334 | Catammoyoan ES | LUNA | 0 | 1 | 2 | Repair of Classrooms | 1269199.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | 4 | Repair of Classrooms | 2407152.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 319304 | BCNHS, Hillside Ext. | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1179180.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 305273 | Happy Hollow National High School | BAGUIO CITY | 0 | 1 | 6 | Repair of Classrooms | 3847478.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 221505 | Irisan Elementary School | BAGUIO CITY | 0 | 1 | 3 | Repair of Classrooms | 2081257.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 221501 | Kias Elementary School | BAGUIO CITY | 0 | 1 | 6 | Repair of Classrooms | 3838325.19 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135401 | Bagtangan ES | BAKUN | 0 | 1 | 8 | Repair and Improvement of School Facilities | 4543047.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135406 | Ketagan-Cabatan ES | BAKUN | 0 | 1 | 4 | Repair and Improvement of School Facilities | 3029589.92 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135444 | Kiweng PS | BOKOD | 0 | 1 | 2 | Repair of Classrooms | 1713052.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135464 | Bad-ayan ES | BUGUIAS | 0 | 1 | 13 | Repair and Improvement of School Facilities | 7991798.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135511 | Pacalso ES | ITOGON | 0 | 1 | 7 | Repair of Classrooms | 4000100 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135554 | Kabayan CS | KABAYAN | 0 | 1 | 10 | Repair of Classrooms | 5329056.09 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 501203 | Datakan Integrated School | KAPANGAN | 0 | 1 | 11 | Repair and Improvement of School Facilities | 4437835.42 | 1 |  | COMPLETED | 100% | 2022-10-30 | [9 empty] | The contractor lacks manpower and financial capability, resulting to the delay of the project. | [12 empty] | 100% |  | 44927 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | CAR | Benguet | 135606 | Palina ES | KIBUNGAN | 0 | 1 | 6 | Repair and Improvement of School Facilities | 3281489.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135627 | Longlong ES | LA TRINIDAD (Capital) | 0 | 1 | 11 | Repair of Classrooms | 6345300.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135681 | Sablan CS | SABLAN | 0 | 1 | 14 | Repair of Classrooms | 8117741.37 | 1 | 7724770.89 | COMPLETED | 100% | 2022-10-30 | [9 empty] | The contractor lacks manpower and financial capability, resulting to the delay of the project. | [12 empty] | 100% |  | 44927 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | CAR | Benguet | 135729 | Mamuyod ES | TUBLAY | 0 | 1 | 3 | Repair of Classrooms | 1849635.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135732 | Pangablan PS | TUBLAY | 0 | 1 | 2 | Repair of Classrooms | 1265000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 305190 | Sta. Maria National High School | ALFONSO LISTA (POTIA) | 0 | 1 | 23 | Repair of Classrooms | 12354057.65 | 1 | 11184969.32 | COMPLETED | 100% | 2022-11-30 | [9 empty] | post qualification | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135788 | Asipulo CS | ASIPULO | 0 | 1 | 1 | Repair of Classroom | 577266.8 | 1 | 567981.06 | COMPLETED | 100% | 2021-10-14 | 2021-11-03 | [21 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135791 | Cawayan ES | ASIPULO | 0 | 1 | 8 | Repair of Classrooms | 4504565.68 | 1 | 4500558.68 | COMPLETED | 100% | 2022-11-30 | [9 empty] | hard accessibility,contractors fault/negligence, lack of skilled workers causing repitition of works, hardship in delivery of lumbers. | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135844 | Ubuag PS | HINGYON | 0 | 1 | 4 | Repair of Classrooms | 2129242.21 | 1 | 1844364.55 | COMPLETED | 100% | 2022-02-03 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135881 | Burnay ES | LAGAWE (Capital) | 0 | 1 | 7 | Repair of Classrooms | 2806042.72 | 1 | 2537620.27 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135915 | Sanafe ES | LAMUT | 0 | 1 | 7 | Repair of Classrooms | 3263849.61 | 1 | 2895974.33 | COMPLETED | 100% | February 9,2022 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 305197 | Allaguia National High School | PINUKPUK | 0 | 1 | 6 | Repair of Classrooms | 3311300.45 | 1 |  | COMPLETED | 100% | 2022-09-30 | [9 empty] | Contractor's Fault | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Kalinga | 136048 | Magaogao Elementary School | PINUKPUK | 0 | 1 | 6 | Repair of Classrooms | 2784538.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 319113 | Mananig National High School | PINUKPUK | 0 | 1 | 2 | Repair of Classrooms | 808723.55 | 1 |  | COMPLETED | 100% | [10 empty] | for final inspection | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 136117 | Ammaboy Elementary School | TANUDAN | 0 | 1 | 3 | Repair of Classrooms | 1158191.47 | 1 |  | COMPLETED | 100% | [10 empty] | for final inspection | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | 0 | 1 | 6 | Repair of Classrooms | 4533161.71 | 1 | 4135213.55 | COMPLETED | 100% | 2022-04-28 | 2022-04-22 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-06 | Precious Gold Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136198 | Bagnen Oriente Elementary School | BAUKO | 0 | 1 | 5 | Repair of Classrooms | 5800703.93 | 1 | 5299471.51 | COMPLETED | 100% | 2021-12-11 | 2022-12-22 |  | INF-2021 R-005 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | EMNAR Const'n & Eng'g Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136214 | Letang Elementary School | BAUKO | 0 | 1 | 5 | Repair of Classrooms | 4021436.78 | 1 | 3739882 | COMPLETED | 100% | 2022-01-29 | 2022-01-25 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-01 | DMYA Construire Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 305228 | Albago National High School | BONTOC (Capital) | 0 | 1 | 6 | Repair of Classrooms | 5458857.12 | 1 | 4569212.27 | COMPLETED | 100% | 2022-03-08 | 2022-03-23 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-09-29 | JBA Construction & Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136302 | Labay Elementary School | PARACELIS | 0 | 1 | 5 | Repair of Classrooms | 6254664.25 | 1 | 6187398.67 | COMPLETED | 100% | 2022-04-28 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-12-14 | SEMBRI | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136312 | San Emilio Elementary School | PARACELIS | 0 | 1 | 4 | Repair of Classrooms | 5754631.61 | 1 | 2580004.66 | COMPLETED | 100% | 2021-12-11 |  |  | INF-2021 R-009 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | Boyet Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136323 | Madepdeppas Elementary School | SABANGAN | 0 | 1 | 5 | Repair of Classrooms | 3530376.87 | 1 | 3217304.63 | COMPLETED | 100% | 2021-12-28 | 2022-05-24 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-09-29 | Graceron Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136359 | Batayan Elementary School | TADIAN | 0 | 1 | 4 | Repair of Classrooms | 5939992.98 | 1 | 5679281.53 | COMPLETED | 100% | 2022-01-02 | 2022-02-18 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-04 | [14 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136373 | Pandayan Elementary School | TADIAN | 0 | 1 | 5 | Repair of Classrooms | 5301291.4 | 1 | 5200341.68 | COMPLETED | 100% | 2021-12-11 | 2021-12-23 |  | INF-2021 R-012 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | EMNAR Const'n & Eng'g Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 3999350.83 | 1 | 3113115.58 | COMPLETED | 100% | November 23,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 220515 | Basao Isla Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2007716.09 | 1 | 1561598.63 | COMPLETED | 100% | November 08,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 3791847.94 | 1 | 2831026.37 | COMPLETED | 100% | November 23,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1840687.18 | 1 | 1434700.16 | COMPLETED | 100% | November 23,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136166 | Dupag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 4206607.19 | 1 | 3968655.08 | COMPLETED | 100% | December 08,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136007 | Laya Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 1038803.86 | 1 | 809999.18 | COMPLETED | 100% | October 24,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 319117 | Naneng NHS - Mosimos Extension | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1802145 | 1 | 1802145 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136181 | Toppan ES | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 3326116.1 | 1 | 2645981.11 | COMPLETED | 100% | November 23,2021 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131467 | Balungagan ES | LAS NIEVES | 1 | 1 | 2 | Repair of Classrooms | 1437536.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131477 | Sagbuco ES | LAS NIEVES | 1 | 1 | 2 | Repair of Classrooms | 1519571.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131513 | Sacol ES | BUENAVISTA | 2 | 1 | 3 | Repair of Classrooms | 2040652.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131570 | Tanutao ES | BUENAVISTA | 2 | 1 | 3 | Repair of Classrooms | 2040652.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 304677 | Carmen NHS | CARMEN | 2 | 1 | 1 | Repair of Classroom | 1024721.06 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131418 | Cervantina ES | CARMEN | 2 | 1 | 2 | Repair of Classrooms | 1441782.04 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131436 | Magsaysay ES | JABONGA | 2 | 1 | 3 | Repair of Classrooms | 2102730.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131454 | San Roque Elementary School | KITCHARAO | 2 | 1 | 2 | Repair of Classrooms | 1473669.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131482 | Caloc-an ES | MAGALLANES | 2 | 1 | 2 | Repair of Classrooms | 1472619.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131490 | Aclan Elementary School | NASIPIT | 2 | 1 | 1 | Repair of Classroom | 819021.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131497 | Jaguimitan ES | NASIPIT | 2 | 1 | 1 | Repair of Classroom | 867506.27 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131531 | Humilog ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | Repair of Classroom | 919116.77 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131541 | La Paz ES | SANTIAGO | 2 | 1 | 2 | Repair of Classrooms | 1486092.91 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Norte | 131593 | Tubay Central Elementary School | TUBAY | 2 | 1 | 2 | Repair of Classrooms | 1473669.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131688 | San Isidro ES | ESPERANZA | 1 | 1 | 3 | Repair of Classrooms | 1986030.2 | 1 | 1942914.76 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ABADA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131713 | Tahina ES | ESPERANZA | 1 | 1 | 4 | Repair of Classrooms | 2562627.1 | 1 | 2517614.52 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ABADA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 317444 | Aurora Nhs | PROSPERIDAD (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2593266.16 | 1 | 2550087.95 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | JB CIANO CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131981 | Kabakahan ES | TALACOGON | 1 | 1 | 5 | Repair of Classrooms | 3114802.86 | 1 | 3072470.23 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ROCK DIWATA BUILDERS INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 | 9 | Repair of Classrooms | 5855797.46 | 1 | 5812436.97 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | ROCK DIWATA BUILDERS INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131754 | Kimondo ES | LA PAZ | 2 | 1 | 2 | Repair of Classrooms | 1450807.05 | 1 | 1406715.08 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | LM CONSTRUCTION & GENERAL MARKETING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131715 | Binucayan CES | LORETO | 2 | 1 | 9 | Repair of Classrooms | 5079981.07 | 1 | 5035764.92 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DAVE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131742 | San Miguel ES | LORETO | 2 | 1 | 2 | Repair of Classrooms | 1481702.74 | 1 | 1439329.37 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DAVE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131924 | Aurora ES | SANTA JOSEFA | 2 | 1 | 10 | Repair of Classrooms | 5598627.97 | 1 | 5553052.81 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | DDS BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 500798 | Patrocinio Integrated School | SANTA JOSEFA | 2 | 1 | 4 | Repair of Classrooms | 2324851.04 | 1 | 2280159.05 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 131932 | Simeon S. Castor ES | SANTA JOSEFA | 2 | 1 | 4 | Repair of Classrooms | 2760647.69 | 1 | 2719383.58 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | LM CONSTRUCTION & GENERAL MARKETING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 132000 | Gasa ES | TRENTO | 2 | 1 | 4 | Repair of Classrooms | 2461155.56 | 1 | 2418246.72 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 132001 | Isdaon Elementary School | TRENTO | 2 | 1 | 6 | Repair of Classrooms | 3640183.73 | 1 | 3595513.58 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | JB CIANO CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 317409 | Kapatungan National High School | TRENTO | 2 | 1 | 5 | Repair of Classrooms | 3623329.29 | 1 | 3579842.32 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Agusan del Sur | 132013 | San Juan ES | TRENTO | 2 | 1 | 7 | Repair of Classrooms | 4501788.25 | 1 | 4459039.69 | COMPLETED | 100% |  |  |  |  | AUGUST 02, 2021 | AUGUST 02, 2021 | AUGUST 16, 2021 |  |  | MRS BUILDERS & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Bayugan City | 131599 | Hamogaway ES | CITY OF BAYUGAN | 1 | 1 | 3 | Repair of Classrooms | 1451174.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Bayugan City | 131612 | Sinadyap ES | CITY OF BAYUGAN | 1 | 1 | 9 | Repair of Classrooms | 3784290.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Bislig City | 132611 | Burboanan ES | CITY OF BISLIG | 2 | 1 | 3 | Repair of Classrooms | 1235124.95 | 1 | 986217.78 | COMPLETED | 100% | November 17, 2021 | November 10, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Bislig City | 132623 | SER-FEL MONE ES | CITY OF BISLIG | 2 | 1 | 4 | Repair of Classrooms | 1494568.14 | 1 | 1193277.63 | COMPLETED | 100% | November 17, 2021 | November 12, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Bislig City | 132638 | SIMON EDGAR A. GARAY ES | CITY OF BISLIG | 2 | 1 | 2 | Repair of Classrooms | 742005.43 | 1 | 590580.9 | COMPLETED | 100% | November 17, 2021 | November 10, 2021 | BEFF_REPAIR2021_001 | BEFF_REPAIR2021_001 | June 09, 2021 | June 17, 2021 | June 30, 2021 | July 06, 2021 | July 14, 2021 | MN Bayalas Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Butuan City | 132073 | Datu Santiago B. Ecleo, Sr. Mem'l. Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 5296975.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Butuan City | 132035 | Mahayahay ES | BUTUAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2670112.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Cabadbaran City | 131577 | Alfonso B. Dagani ES | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 1353061.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Cabadbaran City | 131518 | Comagascas Elementary Schools | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 1608455.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Cabadbaran City | 317312 | La Union NHS (Calamba NHS Annex) | CITY OF CABADBARAN | 2 | 1 | 2 | Repair of Classrooms | 986339.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Cabadbaran City | 131528 | Puting Bato Elementary School | CITY OF CABADBARAN | 2 | 1 | 1 | Repair of Classroom | 575692.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Cabadbaran City | 131578 | Sanghan ES | CITY OF CABADBARAN | 2 | 1 | 3 | Repair of Classrooms | 2395603.08 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | 0 | 1 | 5 | Repair of Classrooms | 1931052.9 | 1 | 1929067.29 | COMPLETED | 100% | 2021-11-17 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Dinagat Island | 132319 | Rosita ES | LIBJO (ALBOR) | 0 | 1 | 3 | Repair of Classrooms | 1938513.44 | 1 | 1929999.98 | COMPLETED | 100% | 2021-11-14 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132125 | Can-uyan Primary School | DAPA | 1 | 1 | 1 | Repair of Classroom | 497000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132142 | San Carlos Elementary School | DAPA | 1 | 1 | 2 | Repair of Classrooms | 1010000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132173 | Lobogon Elementary School | DEL CARMEN | 1 | 1 | 2 | Repair of Classrooms | 943000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 486000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 485000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132185 | Jaboy Elementary School | PILAR | 1 | 1 | 2 | Repair of Classrooms | 958000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 948000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1 | 1 | 1 | Repair of Classroom | 517000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 990000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132195 | Macapagal Primary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 489426.04 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132197 | Pelaez Elementary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 468000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 2 | Repair of Classrooms | 975000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Siargao | 132231 | Del Pilar Community School | SOCORRO | 1 | 1 | 2 | Repair of Classrooms | 993000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao City | 132256 | Orok Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1940038.57 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao City | 132295 | Serna Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1591384.77 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Norte | 132474 | Macalaya ES | PLACER | 2 | 1 | 8 | Repair of Classrooms | 5245388.45 | 1 | 5235000 | COMPLETED | 100% | 2021-11-02 |  | 001-BEFF-2021-CARAGA | 001-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | Windfall Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 1 | Repair of Classroom | 414081.85 | 1 | 397585.25 | COMPLETED | 100% | 2021-09-06 |  | 003-BEFF-2021-CARAGA | 003-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | R.F. Varquez Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Norte | 132477 | Panhutongan ES | PLACER | 2 | 1 | 3 | Repair of Classrooms | 2133444.29 | 1 | 2123401.73 | COMPLETED | 100% | 2021-10-06 |  | 002-BEFF-2021-CARAGA | 002-2021 | 2021-06-09 | 2021-06-16 | 2021-06-28 | 2021-07-01 | 2021-07-04 | Chives Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 500321 | Matho Integrated School | CORTES | 1 | 1 | 4 | Repair of Classrooms | 3208327.87 | 1 | 2045494.59 | COMPLETED | 100% | 2021-12-13 | November 24, 2021 |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | LPO1 GROUP OF COMPANIES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132780 | R. Moreno Elementary School | LIANGA | 1 | 1 | 5 | Repair of Classrooms | 4108268.49 | 1 | 2663874.03 | COMPLETED | 100% | 2021-12-13 | November 11, 2021 |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | TRIDENT ENGINEERING SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132947 | Layog Elementary School | TAGO | 1 | 1 | 4 | Repair of Classrooms | 3342302.63 | 1 | 2163079.08 | COMPLETED | 100% | 2021-12-12 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-06 | FP ALONTO CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132948 | Lindoy Elementary School | TAGO | 1 | 1 | 1 | Repair of Classroom | 571915.5 | 1 | 361782.94 | COMPLETED | 100% | 2021-12-12 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-06 | FP ALONTO CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132575 | Campbagang Elementary School | BAROBO | 2 | 1 | 5 | Repair of Classrooms | 4201512.17 | 1 | 2843751.17 | reverted | 65% | 2022-11-30 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-10 | TWO J.E. CONSTRUCTION AND SUPPLY | terminated; reverted | [12 empty] | 65% |  | 44986 | [5 empty] | reverted
REPAIR 2021 | CARAGA | Surigao del Sur | 132724 | Bigaan Elementary School | HINATUAN | 2 | 1 | 2 | Repair of Classrooms | 1563818.75 | 1 | 1110868.58 | COMPLETED | 100% | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132729 | Cambatong Elementary School | HINATUAN | 2 | 1 | 1 | Repair of Classroom | 963943.23 | 1 | 677562.54 | COMPLETED | 100% | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Surigao del Sur | 132747 | San Juan Elementary School | HINATUAN | 2 | 1 | 1 | Repair of Classroom | 956087.39 | 1 | 674806.95 | COMPLETED | 100% | 2021-12-13 |  |  |  | 2021-07-12 | 2021-07-21 | 2021-08-04 | 2021-08-24 | 2021-09-07 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Tandag City | 132978 | Tandag Central Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1048250.65 | 1 | 721850.3 | COMPLETED | 100% | 2019-11-28 | [7 empty] | August 15, 2019 | AMA Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2052079.62 | 1 | 1414320.21 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | Repair of Classrooms | 3054188.64 | 1 | 1985098.07 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136643 | A. Mabini Elementary School | KALOOKAN CITY | 1 | 1 | 1 | Repair of Perimeter Fence | 35000000 | 1 | 34850000 | COMPLETED | 100% | 2022-04-25 |  | 2021-Infra-002 | 2021-Infra-Cal-002 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2019-09-06 | IM Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1 | 1 | 28 | Repair of Classrooms | 14100000 | 1 | 14044594.8 | COMPLETED | 100% | 2022-02-27 | 2021-08-18 | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 305374 | Camarin High School | KALOOKAN CITY | 1 | 1 | 36 | Repair of Classrooms | 16200000 | 1 | 16174537.387 | COMPLETED | 100% | 2022-02-27 |  | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136645 | Marcelo H. del Pilar ES (MLQ ES Unit I) | KALOOKAN CITY | 1 | 1 | 9 | Repair of Classrooms | 5032830.79 | 1 | 5000698.61 | COMPLETED | 100% | 2022-02-27 |  | 2021-Infra-002 | 2021-Infra-Cal-003 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Solenko Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136629 | Morning Breeze Elementary School | KALOOKAN CITY | 1 | 1 | 33 | Repair of Classrooms | 16000000 | 1 | 15945000 | COMPLETED | 100% | 2022-09-30 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | KALOOKAN CITY | 2 | 1 | 18 | Repair of Classrooms | 10600000 | 1 | 10560000 | COMPLETED | 100% | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | KALOOKAN CITY | 2 | 1 | 18 | Repair of Classrooms | 10600000 | 1 | 10560000 | COMPLETED | 100% | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Caloocan City | 305390 | Maria Clara HS | KALOOKAN CITY | 2 | 1 | 20 | Repair of Classrooms | 9000000 | 1 | 8965000 | COMPLETED | 100% | 2022-05-13 |  | 2021-Infra-002 | 2021-Infra-Cal-004 | 2021-06-29 | 2021-07-07 | 2021-07-19 | 2021-08-02 | 2021-08-31 | Aylan Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | 0 | 1 | 6 | Repair of Classrooms | 3000000 | 1 | 2388888.88 | COMPLETED | 100% | 2021-12-20 |  | REPAIR2021-NCR-SANJUAN-001 | INFRA2021-08-01 | 2021-07-06 | 2021-07-13 | 2021-07-26 | 2021-07-28 | 2021-08-04 | ZEAL POWER CONSTRUCTION AND DEV'T CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Las Piñas City | 320302 | CAA NHS Annex | CITY OF LAS PIÑAS | 0 | 1 | 27 | Repair of Classrooms | 4945261.49 | 1 | 3417765.61 | COMPLETED | 100% | 2021-12-22 | 2021-11-10 | REPAIR2021-NCR-LAS PIÑAS CITY-001 |  | 2021-06-30 | 2021-07-07 | 2021-07-21 | 2021-07-19 | 2021-08-24 | Open Builders Incorporated | Turn-over | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Makati City | 305412 | Benigno "Ninoy" S. Aquino HS | CITY OF MAKATI | 2 | 1 | 59 | Repair of Toilets | 7200222.96 | 1 | 4680401.6 | COMPLETED | 100% | 2022-01-31 |  | SDO-MKT-021-008 | SDO-MKT-021-008 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-06 | 2021-09-08 | DREAMWORX BUILDER & TRADING, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 500337 | Catmon IS | CITY OF MALABON | 0 | 1 | 59 | Repair of Classrooms | 4500000 | 1 | 4469655.11 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0003 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | MRRM TRADING & CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 501208 | Dampalit IS | CITY OF MALABON | 0 | 1 | 12 | Repair of Classrooms | 547476.62 | 1 | 542461 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136835 | Longos ES | CITY OF MALABON | 0 | 1 | 8 | Repair of Classrooms | 387857.31 | 1 | 386779.49 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 10 | Repair of Classrooms | 2791834.53 | 1 | 2786822.55 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305447 | Malabon National High School | CITY OF MALABON | 0 | 1 | 9 | Repair of Classrooms | 3124712.65 | 1 | 3114428.54 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0005 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | DREAMWORX BUILDER & TRADING, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | 67 | Repair of Classrooms | 4500000 | 1 | 4468956.55 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-004 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | TAPNIO & TAN CONSTRUCTION & DEVT. CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | 21 | Repair of Classrooms | 861201.95 | 1 | 859671.83 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | 0 | 1 | 16 | Repair of Classrooms | 500000 | 1 | 498127.47 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 500339 | Tañong IS | CITY OF MALABON | 0 | 1 | 15 | Repair of Classrooms | 555637.65 | 1 | 554096.37 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305448 | Tañong NHS | CITY OF MALABON | 0 | 1 | 1 | Repair of Classroom | 270614.12 | 1 | 269678.35 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0007 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | Martian Builders and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Malabon City | 305452 | Tinajeros NHS | CITY OF MALABON | 0 | 1 | 8 | Repair of Classrooms | 355402.21 | 1 | 350382.11 | COMPLETED | 100% |  |  |  | 2021-INFRA-10-0006 |  | SEPT 8, 2021 | 2021-09-28 | 2021-10-07 | 2021-10-14 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 500500 | Hulo Integrated School | CITY OF MANDALUYONG | 0 | 1 | 64 | Repair of Classrooms | 15791089.99 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School (Isaac Lopez ES) | CITY OF MANDALUYONG | 0 | 1 | 40 | Repair of Classrooms | 8303301.94 | 1 | 10049242.84 | COMPLETED | 100% | January 11, 2021 | January 11, 2021 | 2020-Mandaluyong-04 | No.04 | August 10, 2020 - August 28, 2020 | August 18, 2020 | September 1, 2020 | September 4, 2020 | October 15, 2020 | Tracsom Builders, Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 68 | Repair of Classrooms | 11622728.4 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Manila | 305288 | Dr. Juan G. Nolasco High School | TONDO | 1 | 1 | 102 | Repair of Classrooms | 33000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2 | 1 | 60 | Repair of Classrooms | 23200000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136426 | Francisco Benitez Elementary School | TONDO | 2 | 1 | 68 | Repair of Classrooms | 27800000 | 1 |  | COMPLETED | 100% | 2022-09-30 | [9 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136428 | Gregoria de Jesus ES | TONDO | 2 | 1 | 46 | Repair of Classrooms | 21900000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3 | 1 | 57 | Repair of Classrooms | 20200000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 33 | Repair of Classrooms | 13800000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 500568 | Antonio A. Maceda Integrated School | SAMPALOC | 4 | 1 | 48 | Repair of Classrooms | 17500000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136462 | Gen. L. Geronimo Elementary School | SAMPALOC | 4 | 1 | 51 | Repair of Classrooms | 17700000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136465 | Juan Luna Elementary School | SAMPALOC | 4 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305310 | Carlos P. Garcia High School | PACO | 6 | 1 | 76 | Repair of Classrooms | 31700000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6 | 1 | 69 | Repair of Classrooms | 30800000 | 1 |  | COMPLETED | 100% | [10 empty] | Ongoing; Requested for time extension | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Manila | 305315 | Victoriano Mapa High School | SAN MIGUEL | 6 | 1 | 34 | Repair of Classrooms | 16150000 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Marikina City | 319903 | Barangka NHS | CITY OF MARIKINA | 1 | 1 | 20 | Repair of Classrooms | 5880043.6 | 1 | 5810762.74 | COMPLETED | 100% | 2021-12-05 | 2021-10-22 | REPAIR-2021-NCR-MARIKINA CITY-005 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | OPEN BUILDERS INCORPORATED | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136672 | Industrial Valley ES | CITY OF MARIKINA | 1 | 1 | 30 | Repair of Classrooms | 7289241.42 | 1 | 7192530.47 | COMPLETED | 100% | 2021-12-05 | November 4,2020 | REPAIR-2021-NCR-MARIKINA CITY-004 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-16 | TRIX-ZION VENTURES CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 71 | Repair of Classrooms | 26904567.33 | 1 | 26788608.22 | COMPLETED | 100% | 2022-01-05 | 2021-01-15 | REPAIR-2021-NCR-MARIKINA CITY-003 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 83 | Repair of Classrooms | 20342356.74 | 1 | 20231961.91 | COMPLETED | 100% | 2022-01-04 | Oct. 30,2020 | REPAIR-2021-NCR-MARIKINA CITY-006 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | MT. GUITING-GUITING CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2 | 1 | 20 | Repair of Classrooms | 3779778.12 | 1 | 3673457.09 | COMPLETED | 100% | 2021-11-05 | 2021-10-22 | REPAIR-2021-NCR-MARIKINA CITY-0001 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | SHERF BUILDERS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Marikina City | 305630 | SSS National High School | CITY OF MARIKINA | 2 | 1 | 20 | Repair of Classrooms | 3903308.21 | 1 | 3853308.21 | COMPLETED | 100% | 2021-11-05 | 2021-11-15 | REPAIR-2021-NCR-MARIKINA CITY-002 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | ST. GABRIEL BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classsroom | 7883989.97 | 1 | 7874528.38 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 32 | Repair of Classsroom | 2956597.21 | 1 | 2929909.9 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 228502 | Filinvest Alabang Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 18 | Repair of Classrooms | 2251992.82 | 1 | 2215811.55 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 21 | Repair of Classrooms | 465900.65 | 1 | 423054.55 | COMPLETED | 100% | 2022-02-12 | 2021-04-17 |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 500438 | Lakeview Integrated School | CITY OF MUNTINLUPA | 0 | 1 | 32 | Repair of Classsroom | 8161304.02 | 1 | 8092879.8 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | 0 | 1 | 28 | Repair of Classrooms | 9385103.5 | 1 | 9377379.45 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 21 | Repair of Classsroom | 2068928.09 | 1 | 2062619.37 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 72 | Repair of Classsroom | 11212593.59 | 1 | 11188729.42 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 79 | Repair of Classsroom | 8092765.95 | 1 | 8058590.7 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 70 | Repair of Classsroom | 11100443.04 | 1 | 11068283.06 | COMPLETED | 100% | 2022-02-12 | Jan. 22, 2020 |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 320701 | Poblacion National High School | CITY OF MUNTINLUPA | 0 | 1 | 44 | Repair of Classrooms | 3518631.25 | 1 | 3476011.78 | COMPLETED | 100% | 2022-02-01 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 6 | Repair of Classrooms | 1171377.26 | 1 | 1133816.25 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 58 | Repair of Classrooms | 7592098.05 | 1 | 7585902.63 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136906 | Tunasan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 22 | Repair of Classsroom | 5787317.34 | 1 | 5775710.85 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | RGDG CONST | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Muntinlupa City | 136907 | Victoria Homes ES | CITY OF MUNTINLUPA | 0 | 1 | 43 | Repair of Classsroom | 2745612.97 | 1 | 2679216.17 | COMPLETED | 100% | 2022-02-12 |  |  |  | 8/2-22/21 | 2021-08-10 | 2021-08-23 | 2021-08-25 | 2021-09-10 | REDCAR TRADING AND CONST. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 340628 | Filemon Lizan Senior High School | CITY OF NAVOTAS | 0 | 1 | 16 | Repair of Classrooms | 4146099.62 | 1 | 4091619.52 | COMPLETED | 100% | 2021-11-22 |  | BAC-PB-2021-05 | BAC-PB-2021-05 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | St. Gabriel Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | Repair of Classrooms | 3586590.03 | 1 | 3558762.46 | COMPLETED | 100% | 2021-11-19 |  | BAC-PB-2021-03 | BAC-PB-2021-03 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | RHR Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | 0 | 1 | 15 | Repair of Classrooms | 6281344.86 | 1 | 6246516.52 | COMPLETED | 100% | 2021-11-21 |  | BAC-PB-2021-04 | BAC-PB-2021-04 | 2021-05-27 | 2021-06-07 | 2021-06-21 | 2021-07-05 | 2021-07-19 | MRRM Trading & Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136767 | Baclaran ES Central | CITY OF PARAÑAQUE | 1 | 1 | 27 | Renovation of School Building | 3401859.28 | 1 | ₱2,449,068.77 | COMPLETED | 100% | 2020-01-05 |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | august 8, 2019 | AGH Construction Corp | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 12 | Renovation of School Building | 4469756.83 | 1 | ₱2,932,759.67 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 |  |  | Open Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 320205 | Don Bosco High School Parañaque | CITY OF PARAÑAQUE | 1 | 1 | 40 | Renovation of School Building | 6376607.77 | 1 | ₱5,602,990.20 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 44 | Renovation of School Building | 3828482.48 | 1 | ₱3,367,611.91 | COMPLETED | 100% | 2021-05-10 | May 6, 2021 |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | October 29, 2020 | Dec 11, 2020 | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136757 | Paranaque Elementary School Unit II | CITY OF PARAÑAQUE | 1 | 1 | 28 | Renovation of School Building | 6371447.85 | 1 | ₱4,200,155.58 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Dreamworx Builder & Trading Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 15 | Repair of Classrooms | 3880768.29 | 1 | ₱2,834,346.28 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | November 6, 2019 | Open Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305427 | Paranaque NHS - Don Galo Annex | CITY OF PARAÑAQUE | 1 | 1 | 39 | Renovation of School Building | 3574901.7 | 1 | ₱2,478,753.31 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 | 2019-08-28 | November 6, 2019 | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 28 | Renovation of School Building | 4220750.09 | 1 | ₱2,987,924.09 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 340635 | Sto. Niño Senior High School | CITY OF PARAÑAQUE | 1 | 1 | 12 | Renovation of School Building | 4382325.75 | 1 | ₱2,907,126.06 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | Open Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136766 | Tambo ES | CITY OF PARAÑAQUE | 1 | 1 | 53 | Renovation of School Building | 3482039.2 | 1 | ₱2,548,301.47 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-23 | 2019-08-28 | November 6, 2019 | R2A Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 305428 | Dr. Arcadio Santos NHS - Main | CITY OF PARAÑAQUE | 2 | 1 | 36 | Renovation of School Building | 6374901.7 | 1 | ₱4,074,142.04 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Trix-Zion Ventures Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Paranaque City |  | Marcelo Green ES | CITY OF PARAÑAQUE | 2 | 1 | 40 | Renovation of School Building | 6376607.77 | 1 | ₱4,153,528.85 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-25 |  |  | Rakmir Trading & Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Paranaque City | 136755 | Masville ES | CITY OF PARAÑAQUE | 2 | 1 | 28 | Renovation of School Building | 2751762.77 | 1 | ₱2,739,675.82 | COMPLETED | 100% |  |  |  |  | 2021-06-03 | 2021-06-11 | 2021-06-24 |  |  | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 | 1 | 23 | Repair of Classrooms & Gymnasium | 10175124.74 | 1 | 10122201.82 | COMPLETED | 100% | 2022-07-01 |  |  | SDOPC- CA-2021-12-008 | 2021-10-23 |  | 2021-11-12 | 2021-12-01 | 2021-12-06 | Dreamworx Builder & Trading Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 11 | Repair of Classrooms | 3000000 | 1 | 2898085.88 | COMPLETED | 100% | 1/1/2022 (1/16/2022 revised) |  | SDOPC 2021-07-004 | SDOPC 2021-07-005 |  | 2021-07-22 | 2021-08-03 | 2021-08-19 | 8/26/2021 (9/3/2021 recieved) | RAKMIR TRADING & CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 36 | Repair of classsroom | 13027391.68 | 1 | 12959052.4 | COMPLETED | 100% | 2022-07-15 | March 26, 2021 | SDOPC 2021-07-003 | SDOPC- CA-2021-12-007 | 2021-07-15 | 2021-07-22 | 2021-08-04 | 2021-12-01 | 2021-12-06 | REDCAR TRADING & CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasay City | 136601 | Timoteo Paez ES | PASAY CITY | 0 | 1 | 9 | Repair of Classrooms & Gymnasium | 10478004.8 | 1 | 10408120.51 | COMPLETED | 100% | 2022-07-04 |  |  | SDOPC- CA-2021-12-009 | 2021-10-23 |  | 2021-11-12 | 2021-12-01 | 2021-12-06 | RGDG Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Pasig City | 136736 | Napico Elementary School | CITY OF PASIG | 0 | 1 | 54 | Repair of Classrooms | 10617899 | 1 | 6925414.89 | COMPLETED | 100% |  |  | PB No. 2021-Infra-004 | PCA-2021-Infra-002-a | July 1, 2023 | July 9, 2023 | July 21, 2023 | August 11, 2023 |  | OPEN BUILDERS INCORPORATED | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 136720 | Palatiw ES | CITY OF PASIG | 0 | 1 | 12 | Repair of Classrooms | 3966835.32 | 1 | 2776777.56 | COMPLETED | 100% |  |  | PB No. 2021-Infra-005 | PCA-2021-Infra-002-a | July 1, 2024 | July 9, 2024 | July 21, 2024 | August 11, 2024 |  | ZANEYA BUILDERS AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 305419 | Santolan HS | CITY OF PASIG | 0 | 1 | 24 | Repair of Classrooms | 9024884.16 | 1 | 6669390 | COMPLETED | 100% |  |  | PB No. 2021-Infra-003 | PCA-2021-Infra-002-a | July 1, 2022 | July 9, 2022 | July 21, 2022 | August 11, 2022 |  | GMO CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Pasig City | 305420 | Sta. Lucia HS | CITY OF PASIG | 0 | 1 | 12 | Repair of Classrooms | 3144024.36 | 1 | 2569335.6 | COMPLETED | 100% |  |  | PB No. 2021-Infra-002 | PCA-2021-Infra-002-a | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 11, 2021 |  | OPEN BUILDERS INCORPORATED | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136497 | Masambong Elementary School | QUEZON CITY | 1 | 1 | 41 | Repair of Classrooms | 16400000 | 1 | 16341506.12 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 10 | Repair of Classrooms | 2995854.13 | 1 | 2995854.13 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305332 | Bagong Silangan HS | QUEZON CITY | 2 | 1 | 51 | Repair of Classrooms | 20400000 | 1 | 20327239.32 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136559 | Quirino ES | QUEZON CITY | 3 | 1 | 43 | Repair of Classrooms | 19350000 | 1 | 19280984.36 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 38 | Repair of Classrooms | 15200000 | 1 | 15145786.16 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305358 | Ramon Magsaysay (Cubao) HS | QUEZON CITY | 4 | 1 | 55 | Repair of Classrooms | 22000000 | 1 | 21921532.6 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 305336 | Lagro HS | QUEZON CITY | 5 | 1 | 24 | Repair of Classrooms | 9600000 | 1 | 9565759.68 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136511 | Culiat Elementary School | QUEZON CITY | 6 | 1 | 39 | Repair of Classrooms | 15600000 | 1 | 15544359.48 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Quezon City | 136514 | Pasong Tamo ES | QUEZON CITY | 6 | 1 | 48 | Repair of Classrooms | 19200000 | 1 | 19131519.36 | COMPLETED | 100% |  |  |  |  | 2021-08-05 | 2021-08-17 | 2021-08-31 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Taguig | 500342 | Napindan Integrated School | TAGUIG CITY | 1 | 1 | 33 | Repair of Classrooms | 9900000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 18 | Repair of Classrooms | 6300000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500565 | Taguig Integrated School | TAGUIG CITY | 1 | 1 | 24 | Repair of Classrooms | 7200000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | TM ABAD CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305460 | Taguig National High School | TAGUIG CITY | 1 | 1 | 41 | Repair of Classrooms | 12300000 | 1 | 2763713.99 | COMPLETED | 100% |  |  | DTP-CY20-INFRA-005 |  | 2021-08-11 | 2021-08-13 | 2021-08-30 | January 8, 2020 | October 26, 2020 | TM ABAD CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 16 | Repair of Classrooms | 4800000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500340 | Kapitan Eddie T. Reyes Integrated School | TAGUIG CITY | 2 | 1 | 27 | Repair of Classrooms | 8100000 | 1 |  | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 500340 | Kapitan Eddie T. Reyes Integrated School | TAGUIG CITY | 2 |  | 6 | Repair of Classrooms | 3000683.71 | 1 |  | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 320606 | President Diosdado Macapagal HS - Signal VNHS Annex | TAGUIG CITY | 2 | 1 | 20 | Repair of Classrooms | 7000000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | TM ABAD CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 29 | Repair of Classrooms | 10150000 | 1 | 4476962.88 | COMPLETED | 100% | 2021-09-16 |  | DTP-CY20-INFRA-008 |  | 2021-08-11 | 2021-08-13 | 2021-08-30 | December 9, 2020 | December 16, 2020 | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 136887 | Upper Bicutan ES | TAGUIG CITY | 2 | 1 | 21 | Repair of Classrooms | 6300000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Taguig | 305465 | Western Bicutan NHS | TAGUIG CITY | 2 | 1 | 23 | Repair of Classrooms | 6900000 | 1 |  | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-08-11 | 2021-08-13 | 2021-08-30 |  |  | AYLAN CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 22 | Repair of Classrooms | 7615969.12 | 1 | 7567366.19 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 136805 | Paltok ES | CITY OF VALENZUELA | 1 | 1 | 18 | Repair of Classrooms | 7864249.43 | 1 | 7814204.44 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320402 | Vicente Trinidad National High School (Punturin NHS) | CITY OF VALENZUELA | 1 | 1 | 24 | Repair of Classrooms | 10847548.51 | 1 | 10785600.14 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 320408 | Bagbaguin National High School | CITY OF VALENZUELA | 2 | 1 | 20 | Repair of Classrooms | 8941874.4 | 1 | 8890203.41 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | Other buildings for repair used as isolation by LGU | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 305444 | Maysan National High School | CITY OF VALENZUELA | 2 | 1 | 23 | Repair of Classrooms | 10395960.78 | 1 | 10337387.28 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2 | 1 | 47 | Repair of Classrooms | 14680783.55 | 1 | 14606341.82 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | NCR | Valenzuela City | 305441 | Valenzuela NHS | CITY OF VALENZUELA | 2 | 1 | 47 | Repair of Classrooms | 10082592.16 | 1 | 10027879.63 | COMPLETED | 100% | 2022-05-28 |  |  | INFRA-BEFF-PB-2021-08-0002(LI) | 2021-06-30 | 2021-07-12 | 2021-07-23 |  | 2021-09-30 | Aylan Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Alaminos City | 101195 | San Roque ES | CITY OF ALAMINOS | 1 | 1 | 7 | Repair of Classrooms | 2930407.7 | 1 | 2917415.1 | COMPLETED | 100% | 2021-11-12 | 2021-10-25 | INFRA-BEFF-CY-2021-08-02 | INFRA-BEFF-CY-2021-08-02 | JULY 9-16, 2021 | 2021-07-15 | 2021-07-29 | 2021-08-04 | 2021-08-16 | DPV BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Batac City | 100082 | P. Q. Pimentel ES | CITY OF BATAC | 2 | 1 | 6 | Repair of Classrooms | 2930501.36 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Candon City | 100432 | Bugnay Elementary School | CITY OF CANDON | 2 | 1 | 7 | Repair of Classrooms | 2893673.92 | 1 | 2873551.02 | COMPLETED | 100% | [6 empty] | 2021-06-28 |  | 2021-07-28 | MA TEJADA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Dagupan City | 102162 | BLISS ES | DAGUPAN CITY | 4 | 1 | 3 | Repair of classrooms | 2053774.07 | 1 | 2049096.68 | COMPLETED | 100% |  |  |  |  | July 15-Aug 4, 2021 | July 23, 2021 | Aug 4, 2021 |  |  | VIKING III BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Dagupan City | 102158 | Lasip Grande ES | DAGUPAN CITY | 4 | 1 | 3 | Repair of classrooms | 2053774.07 | 1 | 2048566.46 | COMPLETED | 100% |  |  |  |  | July 15-Aug 4, 2021 | July 23, 2021 | Aug 4, 2021 |  |  | ASS CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Norte | 100228 | Piddig South CES | PIDDIG | 1 | 1 | 6 | Repair of Classrooms | 2599235.92 | 1 | 2589397.4039 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Norte | 100306 | Visaya ES | VINTAR | 1 | 1 | 6 | Repair of Classrooms | 3418730.85 | 1 | 2796516.9313 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Norte | 100071 | Quiaoit Memorial ES | BANNA (ESPIRITU) | 2 | 1 | 5 | Repair of Classrooms | 2475545.66 | 1 | 2018708.2516 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Norte | 100144 | Elizabeth ES | MARCOS | 2 | 1 | 9 | Repair of Classrooms | 5107009.86 | 1 | 5086958.2927 | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region I | Ilocos Sur | 100725 | Calay-ab ES | SANTO DOMINGO | 1 | 1 | 10 | Repair of Classrooms | 4840360.43 | 1 | 3953523.63 | COMPLETED | 100% | 2021-12-10 | 2021-12-10 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-13 | MA TEJADA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Sur | 100329 | Apang ES | ALILEM | 2 | 1 | 5 | Repair of Classrooms | 2616874.49 | 1 | 2190525.61 | COMPLETED | 100% | 2021-11-17 | 2021-11-17 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-20 | MRK-SQUARE CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Ilocos Sur | 100334 | Caoayan Elementary School | SUGPON | 2 | 1 | 4 | Repair of Classrooms | 2080224.67 | 1 | 1738402.32 | COMPLETED | 100% | 2021-11-17 | 2021-11-17 | 7807196 |  | 2021-06-30 | 2021-07-07 | 2021-07-22 | 2021-08-02 | 2021-08-20 | MRK-SQUARE CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100885 | Pantar ES | BALAOAN | 1 | 1 | 12 | Repair of Classrooms | 5079914.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100964 | Oaqui ES | LUNA | 1 | 1 | 12 | Repair of Classrooms | 4555595.06 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 101074 | Taboc ES | SAN JUAN | 1 | 1 | 13 | Repair of Classrooms | 6034970.66 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 101106 | Castro ES | SUDIPEN | 1 | 1 | 7 | Repair of Classrooms | 2760188.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100837 | Sta. Cecilia ES | ARINGAY | 2 | 1 | 9 | Repair of Classrooms | 4341954.42 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100861 | Cambaly Elementary School | BAGULIN | 2 | 1 | 6 | Repair of Classrooms | 2392239.02 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100915 | PUGO ELEMENTARY SCHOOL | BAUANG | 2 | 1 | 9 | Repair of Classrooms | 3589404.06 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100933 | Bilis ES | BURGOS | 2 | 1 | 4 | Repair of Classrooms | 1742137.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 100945 | San Cornelio ES | CABA | 2 | 1 | 5 | Repair of Classrooms | 2235770.77 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 101007 | Cadumanian ES | ROSARIO | 2 | 1 | 7 | Repair of Classrooms | 2845560.02 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | La Union | 101014 | Marcos Elementary School | ROSARIO | 2 | 1 | 8 | Repair of Classrooms | 2482537.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Laoag City | 102200 | Navotas Elementary School | LAOAG CITY (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1090679.4 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Laoag City | 102201 | Pila Elementary School | LAOAG CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1955641.96 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101135 | Aroas ES | AGNO | 1 | 1 | 8 | Repair of Classrooms | 2808060.82 | 1 | 2162080.59 | COMPLETED | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500608 | BANI EAST INTEGRATED SCHOOL | BANI | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2967912.84 | COMPLETED | 100% | [9 empty] | CLP Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101363 | Samang Elementary School | BOLINAO | 1 | 1 | 5 | Repair of Classrooms | 2216027.06 | 1 | 2211235.22 | COMPLETED | 100% | [9 empty] | Elgram Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 1 | Repair of Classrooms & Fence | 2254424.72 | 1 | 2244516.1 | COMPLETED | 100% | [9 empty] | ILS Power Engineering and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 1 | Repair of Classrooms & Fence | 1174242.24 | 1 | 1156860.08 | COMPLETED | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2995097.98 | COMPLETED | 100% | [9 empty] | Elgram Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 500609 | Barlo Integrated School | MABINI | 1 | 1 | 8 | Repair of Classrooms | 3500000 | 1 | 3483630.7 | COMPLETED | 100% | [9 empty] | Angelina T. Dizon Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan NHS | MABINI | 1 | 1 | 11 | Repair of classrooms | 5108210.04 | 1 | 5100197.102 | COMPLETED | 100% | [9 empty] | DPV BUILDERS AND CONSTRUCTION SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101523 | Mabini CS | MABINI | 1 | 1 | 10 | Repair of Classrooms | 3566269.42 | 1 | 3555928.78 | COMPLETED | 100% | [9 empty] | Casipit Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101327 | Camaley CS | BINMALEY | 2 | 1 | 3 | Repair of Classrooms | 1273542.02 | 1 | 1243526.82 | COMPLETED | 100% | [9 empty] | Rockwell Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101584 | Linmansangan ES | MANGATAREM | 2 | 1 | 8 | Repair of Classrooms | 2676608.6 | 1 | 2140420 | COMPLETED | 100% | 2022-11-30 | [8 empty] | CLP Builders | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101682 | Duplac ES | URBIZTONDO | 2 | 1 | 5 | Repair of Classrooms | 1995473.57 | 1 | 1992410.41 | COMPLETED | 100% | [9 empty] | RC Gabriel Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300247 | Real National High School | URBIZTONDO | 2 | 1 | 10 | Repair of Classrooms | 3442214.96 | 1 | 3392183.9 | COMPLETED | 100% | [9 empty] | Rockwell Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101278 | Nalsian ES | BAYAMBANG | 3 | 1 | 10 | Repair of Classrooms | 3484782.67 | 1 | 2508542.4 | COMPLETED | 100% | [9 empty] | MN Coloma Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101556 | Bakitiw ES | MALASIQUI | 3 | 1 | 3 | Repair of Classrooms | 1153088.69 | 1 | 808171.17 | COMPLETED | 100% | [9 empty] | MN Coloma Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3 | 1 | 5 | Repair of Classrooms | 2444057.58 | 1 | 2032424.25 | COMPLETED | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101639 | Banaoang Central School | SANTA BARBARA | 3 | 1 | 29 | Repair of Classrooms | 3489897.45 | 1 | 2556231.41 | COMPLETED | 100% | [9 empty] | MN Coloma Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan I, Lingayen | 101647 | Maticmatic ES | SANTA BARBARA | 3 | 1 | 16 | Repair of Classrooms | 3155828.82 | 1 | 2208832.24 | COMPLETED | 100% | [9 empty] | MN Coloma Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101943 | Sta. Maria ES | SAN JACINTO | 4 | 1 | 15 | Repair of Classrooms | 8578901.99 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101696 | Atainan ES | ALCALA | 5 | 1 | 11 | Repair of Classrooms | 7839599.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101698 | Gualsic ES | ALCALA | 5 | 1 | 13 | Repair of Classrooms | 8267640.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101708 | South Central School | ALCALA | 5 | 1 | 6 | Repair of Classrooms | 3589345.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101770 | Balisa ES | BINALONAN | 5 | 1 | 6 | Repair of Classrooms | 3488516.86 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101772 | Bued ES | BINALONAN | 5 | 1 | 9 | Repair of Classrooms | 5326521.83 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101773 | Linmansangan ES | BINALONAN | 5 | 1 | 14 | Repair of Classrooms | 9820165.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101779 | Botigue ES | LAOAC | 5 | 1 | 3 | Repair of Classrooms | 1919125.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101784 | Don Rufino Tabayoyong CS | LAOAC | 5 | 1 | 7 | Repair of Classrooms | 1860998.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | 55 | Repair of Classrooms | 25000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102057 | Doña Aurea ES | SANTO TOMAS | 5 | 1 | 19 | Repair of Classrooms | 15000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101722 | Bobonan Elementary School | ASINGAN | 6 | 1 | 2 | Repair of Classrooms | 1873121.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101728 | Toboy ES | ASINGAN | 6 | 1 | 4 | Repair of Classrooms | 4000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101745 | Don Francisco D. Toliao ES | BALUNGAO | 6 | 1 | 2 | Repair of Classrooms | 1873121.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101742 | San Leon ES | BALUNGAO | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101832 | Batchelor Elementary School | NATIVIDAD | 6 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | 3 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101846 | San Narciso Norte ES | NATIVIDAD | 6 | 1 | 2 | Repair of Classrooms | 1328655.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101878 | Carmen Elementary School | ROSALES | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101899 | San Antonio ES | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 1330763.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101886 | Tomana Elementary School SPED Center | ROSALES | 6 | 1 | 2 | Repair of Classrooms | 1891736.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101950 | Cabacaraan ES | SAN MANUEL | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101991 | Nining ES | SAN NICOLAS | 6 | 1 | 1 | Repair of Classroom | 694127.88 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 101997 | Sta. Maria ES | SAN NICOLAS | 6 | 1 | 6 | Repair of Classrooms | 6057408.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102004 | Don Luis Domingo Sr. ES | SAN QUINTIN | 6 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102049 | Samon Elementary School | SANTA MARIA | 6 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102055 | West Central School | SANTA MARIA | 6 | 1 | 2 | Repair of Classrooms | 1884545.91 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102061 | Agno Elementary School | TAYUG | 6 | 1 | 6 | Repair of Classrooms | 4000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102076 | Toketec ES | TAYUG | 6 | 1 | 2 | Repair of Classrooms | 1878557.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102079 | Barat ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1328655.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102099 | Casilan ES | UMINGAN | 6 | 1 | 3 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102100 | Concepcion ES | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1330763.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102088 | Lubong Elementary School | UMINGAN | 6 | 1 | 2 | Repair of Classrooms | 1324272.75 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Pangasinan II, Binalonan | 102093 | Umingan CES | UMINGAN | 6 | 1 | 7 | Repair of Classrooms | 6295323.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | San Carlos City | 102224 | Quintong Elementary School | SAN CARLOS CITY | 3 | 1 | 5 | Repair of classrooms | 2755453.72 | 1 | 2,218,140.24. | COMPLETED | 100% | DEC. 21,2021 |  |  |  |  | AUGUST 12,2021 | AUGUST 31,2021 | SEPT. 8,2021 | SEPT.22,2021 | RGP SUCCESS VENTURES INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | San Fernando City | 101035 | Sevilla Elementary School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 13 | Repair of classrooms | 6472844.79 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Urdaneta City | 300403 | Mariano Q. Umipig NHS | CITY OF URDANETA | 5 | 1 | 5 | Repair of Classrooms | 2973693.33 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region I | Vigan City | 100789 | Capangpangan ES | CITY OF VIGAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2852635.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | 0 | 1 | 6 | Repair of Classrooms | 3032100.24 | 1 | 2609212.82 | COMPLETED | 100% | 2023-01-23 | [22 empty] | 100% |  | 44927 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300422 | BAYBAYOG NATIONAL HIGH SCHOOL | ALCALA | 1 | 1 | 25 | Repair of Classrooms | 4540622.6 | 1 | 3520000 | COMPLETED | 100% | 2022-01-23 | [8 empty] | Achanzar Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102368 | Damurog Elementary School | ALCALA | 1 | 1 | 3 | Repair of Classrooms | 1161744.71 | 1 | 1146214.5 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102513 | Bitag Grande ES | BAGGAO | 1 | 1 | 8 | Repair of Classrooms | 1652432.55 | 1 | 1575479.9 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102570 | Buguey South CS (Pattao ES) | BUGUEY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2209809.65 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102564 | Maddalero ES | BUGUEY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2664606.59 | COMPLETED | 100% | 2022-01-23 | [8 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102580 | Villa Gracia ES | BUGUEY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1334816.05 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102595 | Alilinu ES | CAMALANIUGAN | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 | 2469478.83 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102599 | Catotoran ES | CAMALANIUGAN | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 1979874.28 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102696 | Gonzaga South CS | GONZAGA | 1 | 1 | 4 | Repair of Classrooms | 3500000 | 1 | 2554772.63 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102698 | Isca ES | GONZAGA | 1 | 1 | 5 | Repair of Classrooms | 3500000 | 1 | 3492180.47 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155054 | CAMBONG ELEMENTARY SCHOOL | LALLO | 1 | 1 | 5 | Repair of Classrooms | 990181.08 | 1 | 989887.78 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102738 | Bangag ES | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 450000 | 1 | 439812.38 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102725 | Bical ES | LAL-LO | 1 | 1 | 6 | Repair of Classrooms | 1500000 | 1 | 1474223.2 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102739 | Bicud ES | LAL-LO | 1 | 1 | 10 | Repair of Classrooms | 1200000 | 1 | 1184936.93 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102727 | Cagoran Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 500000 | 1 | 489987.63 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102741 | Catayauan Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 650000 | 1 | 639888.95 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102742 | Catugan ES | LAL-LO | 1 | 1 | 9 | Repair of Classrooms | 1000000 | 1 | 989940.92 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300469 | LAL-LO NATIONAL HIGH SCHOOL | LAL-LO | 1 | 1 | 23 | Repair of Classrooms | 4100000 | 1 | 4039791.71 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1 | 1 | 14 | Repair of Classrooms | 3450000 | 1 | 3448460.86 | COMPLETED | 100% | 2022-01-22 | [8 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102748 | Magapit ES | LAL-LO | 1 | 1 | 8 | Repair of Classrooms | 700000 | 1 | 689895.1 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102732 | Maxingal Elementary School | LAL-LO | 1 | 1 | 4 | Repair of Classrooms | 2500000 | 1 | 2496276.85 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102750 | Paranum Elementary School | LAL-LO | 1 | 1 | 2 | Repair of Classrooms | 600000 | 1 | 589571.52 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155030 | San Mariano Elementary School | LAL-LO | 1 | 1 | 10 | Repair of Classrooms | 1250000 | 1 | 1234279.66 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102754 | Sta. Maria CS | LAL-LO | 1 | 1 | 1 | Repair of Classroom | 400000 | 1 | 389954.61 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102735 | Sta. Teresa Elementary School | LAL-LO | 1 | 1 | 8 | Repair of Classrooms | 1200000 | 1 | 1179629.91 | COMPLETED | 100% | [9 empty] | JIRK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102902 | Kapanikian ES | SANTA ANA | 1 | 1 | 3 | Repair of Classrooms | 908534.57 | 1 | 904857.14 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155018 | Visitacion Elementary School | SANTA ANA | 1 | 1 | 6 | Repair of Classrooms | 1654807.23 | 1 | 1207924.37 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102924 | Alucao Elementary School | SANTA TERESITA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1497118.65 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102933 | Simpatuyo ES | SANTA TERESITA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1497549.79 | COMPLETED | 100% | [9 empty] | RPF Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102342 | Lucban ES | ABULUG | 2 | 1 | 5 | Repair of Classrooms | 1200000 | 1 | 1192013.97 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102536 | Ballesteros CS | BALLESTEROS | 2 | 1 | 6 | Repair of Classrooms | 1900000 | 1 | 1899001.31 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102550 | Sta. Cruz ES | BALLESTEROS | 2 | 1 | 3 | Repair of Classrooms | 950000 | 1 | 949739.88 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 300442 | Calayan HS - Camiguin Annex | CALAYAN | 2 | 1 | 4 | Repair of Classrooms | 1370984.22 | 1 | 1355701.19 | COMPLETED | 100% | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 306427 | Calayan HS- Dilam Extension | CALAYAN | 2 | 1 | 7 | Repair of Classrooms | 2119294.92 | 1 | 2116992.67 | COMPLETED | 100% | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102585 | Camiguin ES | CALAYAN | 2 | 1 | 8 | Repair of Classrooms | 1926243.69 | 1 | 1910651.04 | COMPLETED | 100% | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102587 | Dadao ES | CALAYAN | 2 | 1 | 5 | Repair of Classrooms | 1318985.64 | 1 | 1303023.61 | COMPLETED | 100% | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155012 | Dilam East PS | CALAYAN | 2 | 1 | 4 | Repair of Classrooms | 1260892.67 | 1 | 1245218.95 | COMPLETED | 100% | 2023-12-22 | [8 empty] | JIRK Construction | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102590 | Dilam ES | CALAYAN | 2 | 1 | 6 | Repair of Classrooms | 1207379.16 | 1 | 1205543.66 | COMPLETED | 100% | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102591 | Magsidel ES | CALAYAN | 2 | 1 | 8 | Repair of Classrooms | 2182236.64 | 1 | 2180899.08 | COMPLETED | 100% | 2023-12-22 | [8 empty] | BA Lagazo Builders | isolated island | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102618 | Pata Elementary School | CLAVERIA | 2 | 1 | 5 | Repair of Classrooms | 1200000 | 1 | 1199027.61 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102760 | Callao ES | LASAM | 2 | 1 | 6 | Repair of Classrooms | 1800000 | 1 | 1798582.71 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102765 | Magsaysay ES | LASAM | 2 | 1 | 3 | Repair of Classrooms | 800000 | 1 | 796141.97 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102784 | Bidduang ES | PAMPLONA | 2 | 1 | 11 | Repair of Classrooms | 2300000 | 1 | 2297947.79 | COMPLETED | 100% | [9 empty] | BA Lagazo Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102820 | Apayao ES | PIAT | 2 | 1 | 5 | Repair of Classrooms | 1450000 | 1 | 1448831.65 | COMPLETED | 100% | [9 empty] | Bifesa Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102821 | Catarauan ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 194600 | 1 | 190311.7 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102822 | Dugayung ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 630000 | 1 | 596791.95 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102823 | Gumarueng ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 508985 | 1 | 485701.6 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102824 | Macapil ES | PIAT | 2 | 1 | 3 | Repair of Classrooms | 300000 | 1 | 284216.77 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102826 | Minanga ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 1310000 | 1 | 1309799.21 | COMPLETED | 100% | [9 empty] | 4MD JSL Construction Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102827 | Piat CS | PIAT | 2 | 1 | 1 | Repair of Classroom | 1340000 | 1 | 1339004.96 | COMPLETED | 100% | [9 empty] | 4MD JSL Construction Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102828 | Sicatna ES | PIAT | 2 | 1 | 4 | Repair of Classrooms | 2000000 | 1 | 1889026.82 | COMPLETED | 100% | 2022-01-18 | [8 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102825 | Sta. Barbara-Maguilling E/S | PIAT | 2 | 1 | 1 | Repair of Classroom | 1300000 | 1 | 1296445.52 | COMPLETED | 100% | [9 empty] | Bifesa Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102829 | Sto. Domingo ES | PIAT | 2 | 1 | 3 | Repair of Classrooms | 900000 | 1 | 858524.11 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102831 | Warat ES | PIAT | 2 | 1 | 1 | Repair of Classroom | 471985 | 1 | 443710.09 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102833 | Cambabangan ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1084632.51 | 1 | 1080367.75 | COMPLETED | 100% | [9 empty] | 4MD JSL Construction Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102835 | Duyun ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1112471.11 | 1 | 1059525.94 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1209499.3 | 1 | 1144430.34 | COMPLETED | 100% | 2022-01-18 | [8 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 155003 | Balagan Elementary School | SANTO NIÑO (FAIRE) | 2 | 1 | 6 | Repair of Classrooms | 1900000 | 1 | 1781062.5 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102955 | Tamucco ES | SANTO NIÑO (FAIRE) | 2 | 1 | 7 | Repair of Classrooms | 2000000 | 1 | 1999184.05 | COMPLETED | 100% | 2022-01-18 | [8 empty] | Bifesa Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102800 | Lagum ES | PEÑABLANCA | 3 | 1 | 2 | Repair of Classrooms | 850000 | 1 | 812269.08 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cagayan | 102803 | Minanga ES | PEÑABLANCA | 3 | 1 | 5 | Repair of Classrooms | 2100000 | 1 | 1991245.35 | COMPLETED | 100% | [9 empty] | GCPK Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 6 | 1 | 1 | Repair of Classroom | 479698.73 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103218 | Labinab Angeles ES | CITY OF CAUAYAN | 6 | 1 | 6 | Repair of Classrooms | 4021985.88 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Cauayan City | 103219 | Rizal ES | CITY OF CAUAYAN | 6 | 1 | 3 | Repair of Classrooms | 1969460.51 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 500018 | San Lorenzo Integrated School (San Lorenzo ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | 15 | Repair of Classrooms | 4819746.79 | 1 | 3362233.71 | COMPLETED | 100% | 2021-11-01 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 103408 | San Rafael ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 1 | Repair of Classroom | 541590.21 | 1 | 438190.87 | COMPLETED | 100% | 2021-11-01 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | City of Ilagan | 103436 | Sta. Isabel Sur ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 9 | Repair of Classrooms | 2630096.89 | 1 | 1838477.86 | COMPLETED | 100% | 2021-11-01 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103242 | Aguinaldo Elementary School | CORDON | 4 | 1 | 5 | Repair of Classrooms | 2059183.1 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103258 | Cordon North Central School | CORDON | 4 | 1 | 5 | Repair of Classrooms | 2059183.11 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103249 | Dallao Elementary School | CORDON | 4 | 1 | 4 | Repair of Classrooms | 1609558.49 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103250 | Gayong Elementary School | CORDON | 4 | 1 | 3 | Repair of Classrooms | 1379043.13 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103252 | Malapat Elementary School | CORDON | 4 | 1 | 3 | Repair of Classrooms | 1372227.51 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103255 | San Juan Elementary School | CORDON | 4 | 1 | 4 | Repair of Classrooms | 1826976 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103440 | Bannawag Elementary School | JONES | 4 | 1 | 4 | Repair of Classrooms | 1878025.6 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 306134 | Sgt. Prospero G. Bello HS - Dumawing Annex | JONES | 4 | 1 | 3 | Repair of Classrooms | 1466253.52 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103636 | Roxas Central School | ROXAS | 5 | 1 | 18 | Repair of Classrooms | 8000734.08 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103645 | San Francisco Elementary School | ROXAS | 5 | 1 | 5 | Repair of Classrooms | 2089258.59 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103285 | Carulay Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1768069.09 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103287 | Diasan Elementary School | ECHAGUE | 6 | 1 | 3 | Repair of Classrooms | 1561016.93 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103288 | Dicaraoyan Elementary School | ECHAGUE | 6 | 1 | 6 | Repair of Classrooms | 2502953.17 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103312 | Libertad Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1997013.28 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103292 | Mabbayad Elementary School | ECHAGUE | 6 | 1 | 4 | Repair of Classrooms | 1838784.3 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 6 | 1 | 5 | Repair of Classrooms | 2081569.06 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 103981 | Ammococan ES | BAYOMBONG (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1930797.18 | 1 | 1905726.67 | COMPLETED | 100% | 70 CD | [5 empty] | 2021-09-29 |  |  | IA castaneda Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104000 | Villa Adriano PS | BAYOMBONG (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1922979.53 | 1 | 1898185.46 | COMPLETED | 100% | 60 CD | [5 empty] | 2021-09-29 |  |  | South East Horizon 818 Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104103 | Siguem ES | KASIBU | 0 | 1 | 2 | Repair of Classrooms | 1219022.13 | 1 | 1149434.19 | COMPLETED | 100% | 37 CD | [5 empty] | 2021-09-29 |  |  | Zyronne Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104109 | Acacia PS | KAYAPA | 0 | 1 | 5 | Repair of Classrooms | 3102941.72 | 1 | 3093258.46 | COMPLETED | 100% | 80 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104141 | Baan Elementary School | KAYAPA | 0 | 1 | 8 | Repair of Classrooms | 2780775.44 | 1 | 2754509.38 | COMPLETED | 100% | 71 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104123 | Dempeg Elementary school | KAYAPA | 0 | 1 | 5 | Repair of Classrooms | 4752582.53 | 1 | 4635888.72 | COMPLETED | 100% | 82 CD | [5 empty] | 2021-09-29 |  |  | Mighty Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104138 | Pangawan ES | KAYAPA | 0 | 1 | 6 | Repair of Classrooms | 3750000 | 1 | 3732418.23 | COMPLETED | 100% | 65 CD | [5 empty] | 2021-09-29 |  |  | Boyet Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104149 | Bonifacio Elementary School | QUEZON | 0 | 1 | 6 | Repair of Classrooms | 1572452.24 | 1 | 1331486.9 | COMPLETED | 100% | 70 CD | [5 empty] | 2021-09-29 |  |  | Ambaguio Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104163 | Tutong Elementary School | QUEZON | 0 | 1 | 4 | Repair of Classrooms | 1205008.96 | 1 | 1115423.5 | COMPLETED | 100% | 66 CD | [5 empty] | 2021-09-29 |  |  | Rosa Mystica | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Nueva Vizcaya | 104201 | Genato ES | SANTA FE | 0 | 1 | 6 | Repair of Classrooms | 2311886.4 | 1 | 2246747.23 | COMPLETED | 100% | 65 CD | [5 empty] | 2021-09-29 |  |  | Zyronne Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 500108 | Dumabel IS | AGLIPAY | 0 | 1 | 8 | Repair of Classrooms | 2301846.22 | 1 | 0 | COMPLETED | 100% |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  |  |  | for Contract Signing | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104234 | Osmena P/S Annex | AGLIPAY | 0 | 1 | 2 | Repair of Classrooms | 514962.77 | 1 | 505601.99 | COMPLETED | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-27 | Atlantic Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104294 | Bikibik ES | DIFFUN | 0 | 1 | 3 | Repair of Classrooms | 872126.15 | 1 | 868139.78 | COMPLETED | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104308 | Macate ES | DIFFUN | 0 | 1 | 6 | Repair of Classrooms | 1906391.03 | 1 | 1860661.77 | COMPLETED | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 300661 | Magsaysay National High School | DIFFUN | 0 | 1 | 9 | Repair of Classrooms | 4438598.02 | 1 | 0 | COMPLETED | 100% |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  |  |  | for Contract Signing | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Quirino | 104356 | La Conwap ES | NAGTIPUNAN | 0 | 1 | 4 | Repair of Classrooms | 1716600.17 | 1 | 1706378.11 | COMPLETED | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-27 | Atlantic Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Santiago City | 500938 | Sinili Integrated School | CITY OF SANTIAGO | 4 | 1 | 8 | Repair of Classrooms | 2789132.95 | 1 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Tuguegarao City | 104384 | Balzain East ES | TUGUEGARAO CITY(Capital) | 3 | 1 | 12 | Repair of classrooms | 1046550.08 | 1 | 0 | COMPLETED | 100% | [10 empty] | procured | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | TUGUEGARAO CITY(Capital) | 3 | 1 | 48 | Repair of classrooms | 1953449.9 | 1 | 0 | COMPLETED | 100% | [10 empty] | procured | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 161001 | Air Force City Elementary School | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344973.74 | COMPLETED | 100% | 2021-10-30 | 2021-10-07 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301038 | Angeles City Nat'l. Trade School | ANGELES CITY | 1 | 1 | 16 | Repair of Classrooms | 3116479.76 | 1 | 3111464.79 | COMPLETED | 100% | 2021-11-29 | 2021-10-13 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1 | 1 | 32 | Repair of Classrooms | 7096381.72 | 1 | 7086139.77 | COMPLETED | 100% | 2021-11-29 |  | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | GMO Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 3600000 | 1 | 3593489.6 | COMPLETED | 100% | 2021-11-29 |  | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Eldico Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107052 | Apung Guidang Nepomuceno Elementary School | ANGELES CITY | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 | 494888.88 | COMPLETED | 100% | 2021-10-21 | 2021-10-21 | N/A |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107024 | Belen Homesite ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344960.94 | COMPLETED | 100% | 2021-10-30 | 2021-10-07 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107025 | Cutud ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344133.09 | COMPLETED | 100% | 2021-10-30 | 2021-09-30 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Mam Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1800000 | 1 | 1794988.33 | COMPLETED | 100% | 2021-10-30 | 2021-10-20 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Nulas Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301040 | Francisco G. Nepomuceno Mem. HS | ANGELES CITY | 1 | 1 | 24 | Repair of Classrooms | 2923827.98 | 1 | 2916984.81 | COMPLETED | 100% | 2021-10-30 | 2021-09-20 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | EB Matias COnstruction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107041 | Gueco Balibago ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2244540.91 | COMPLETED | 100% | 2021-10-30 | 2021-10-18 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Marveric Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 100% | 2021-10-21 | 2021-10-21 | N/A |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107059 | Pampang ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2245474.37 | COMPLETED | 100% | 2021-10-30 | 2021-10-19 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | GMO Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107033 | Pulung Cacutud ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 100% | 2021-10-21 | 2021-10-21 | N/A |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107034 | Pulungbulo ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 100% | 2021-10-21 | 2021-10-21 | N/A |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 | 1 | 12 | Repair of Classrooms | 2515459.64 | 1 | 2509960.73 | COMPLETED | 100% | 2021-10-30 | 2021-09-20 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | TG Ocampo Construction and Surveying Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107035 | Salapungan ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1345777.5 | COMPLETED | 100% | 2021-10-30 | 2021-09-09 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Altitude Engineering and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107036 | San Ignacio ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1800000 | 1 | 1794767.82 | COMPLETED | 100% | 2021-10-30 | 2021-09-08 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | V.Trillana Builders and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107037 | Sapalibutad ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344568.33 | COMPLETED | 100% | 2021-10-30 | 2021-09-30 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Apu Construction, Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107048 | Sta. Teresita Elementary School | ANGELES CITY | 1 | 1 | 11 | Repair of Classrooms | 4950000 | 1 | 4938888.88 | COMPLETED | 100% | 2021-11-29 |  | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Traccor Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 500133 | Sto. Domingo IS | ANGELES CITY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2689371.37 | COMPLETED | 100% | 2021-10-30 | 2021-10-07 | N/A |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | PVB Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104423 | Casiguran CS | CASIGURAN | 0 | 1 | 15 | Repair of Classrooms | 6219097.83 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | 15 | Repair of Classrooms | 6300933.24 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104424 | Dibacong ES | CASIGURAN | 0 | 1 | 8 | Repair of Classrooms | 3472876.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 306502 | Dibacong NHS | CASIGURAN | 0 | 1 | 12 | Repair of Classrooms | 5932859.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104432 | Diagyan ES | DILASAG | 0 | 1 | 6 | Repair of Classrooms | 2540300.52 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104433 | Dicabasan ES | DILASAG | 0 | 1 | 4 | Repair of Classrooms | 1751483.75 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104434 | Dilaguidi ES | DILASAG | 0 | 1 | 7 | Repair of Classrooms | 3089493.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104437 | Diniog ES | DILASAG | 0 | 1 | 8 | Repair of Classrooms | 2782588.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104463 | BAYABAS ES | DIPACULAO | 0 | 1 | 12 | Repair of Classrooms | 7497102.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300693 | DIPACULAO NHS | DIPACULAO | 0 | 1 | 19 | Repair of Classrooms | 12775492.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104483 | TOYTOYAN ES | DIPACULAO | 0 | 1 | 2 | Repair of Classrooms | 1363370.02 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104488 | Cabituculan East ES | MARIA AURORA | 0 | 1 | 11 | Repair of Classrooms | 4813419.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300679 | Canili Area NHS | MARIA AURORA | 0 | 1 | 10 | Repair of Classrooms | 5771155.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104502 | Kadayakan ES | MARIA AURORA | 0 | 1 | 7 | Repair of Classrooms | 3089493.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104485 | Marcos R. Necesito Sr. Memorial ES | MARIA AURORA | 0 | 1 | 5 | Repair of Classrooms | 2183562.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 157506 | Ramada ES | MARIA AURORA | 0 | 1 | 6 | Repair of Classrooms | 1778650.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104518 | Diotorin ES | SAN LUIS | 0 | 1 | 2 | Repair of Classrooms | 909958.59 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300686 | DITUMABO NHS | San Luis | 0 | 1 | 18 | Repair of Classrooms | 9558789.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1964739.03 | 1 | 1947613.51 | COMPLETED | 100% | 2021-11-09 | 2021-09-17 | 2021-06-01-3R | 2021-06-01-3R | 2021-06-30 | 2021-07-08 | 2021-07-30 | 2021-08-03 | 2021-08-11 | YELLOW CIRCLES CONS. AND TRADING CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 104557 | Cupang Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 6 | Repair of Classrooms | 3485178.13 | 1 | 3470385 | COMPLETED | 100% | 2021-11-02 |  | 2021-06-01-01 | 2021-06-01-01 | 2021-06-30 | 2021-07-08 | 2021-07-21 | 2021-07-23 | 2021-08-04 | RAVH construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 104562 | Puerto Rivas Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1415596.91 | 1 | 1400000 | COMPLETED | 100% | 2021-11-02 | 2021-09-17 | 2021-06-01-02 | 2021-06-01-02 | 2021-06-30 | 2021-07-08 | 2021-07-21 | 2021-07-23 | 2021-08-04 | L. A. GONIDO BUILDERS INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 300708 | Luakan NHS | DINALUPIHAN | 1 | 1 | 11 | Repair of Classrooms | 7716237.91 | 1 | 7695356.71 | COMPLETED | 100% | 2021-12-19 |  | BEEF CY2021 -REPAIR-0001 | 2021-CON-00017 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-23 | AMP Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104590 | Pita ES | DINALUPIHAN | 1 | 1 | 12 | Repair of Classrooms | 3122076.98 | 1 | 3091400.95 | COMPLETED | 100% | 2021-10-12 | 2021-09-28 | BEEF CY2021 -REPAIR-0002 | 2021-CON-00018 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | Rodmac Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104595 | San Ramon ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 3443226.79 | 1 | 3432803.2 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0003 | 2021-CON-00019 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RZ Tigas Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104597 | San Simon ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 5051050.39 | 1 | 5039000 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0004 | 2021-CON-00020 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | De Jesus Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306603 | Sta. Lucia HS | DINALUPIHAN | 1 | 1 | 5 | Repair of Classrooms | 3224558.77 | 1 | 3214492.95 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0005 | 2021-CON-00021 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | MJ Camacho Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104663 | Orani North ES | ORANI | 1 | 1 | 12 | Repair of Classrooms | 5728355.99 | 1 | 5677892.94 | COMPLETED | 100% | 2021-12-10 |  | BEEF CY2021 -REPAIR-0006 | 2021-CON-00022 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | AJN Construction INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104672 | Talimundoc ES | ORANI | 1 | 1 | 5 | Repair of Classrooms | 4452753.42 | 1 | 4421845.34 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0007 | 2021-CON-00023 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RWD Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104702 | F.C. Del Rosario ES | SAMAL | 1 | 1 | 6 | Repair of Classrooms | 3450193.48 | 1 | 3440178.44 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0008 | 2021-CON-00024 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | Bonibal Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104708 | Samal South ES | SAMAL | 1 | 1 | 4 | Repair of Classrooms | 2855061.48 | 1 | 2841340.27 | COMPLETED | 100% | 2021-10-12 | 2021-10-08 | BEEF CY2021 -REPAIR-0009 | 2021-CON-00025 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RCS Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104709 | Sapa ES | SAMAL | 1 | 1 | 6 | Repair of Classrooms | 4845801.52 | 1 | 4835618.09 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0010 | 2021-CON-00026 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Mecon Systems | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104541 | Bagac ES | BAGAC | 2 | 1 | 14 | Repair of Classrooms | 7196707.49 | 1 | 7160574.49 | COMPLETED | 100% | 2021-12-10 |  | BEEF CY2021 -REPAIR-0011 | 2021-CON-00027 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | BQA Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104640 | Bayview ES | MARIVELES | 2 | 1 | 5 | Repair of Classrooms | 2003696.12 | 1 | 1993634.94 | COMPLETED | 100% | 2021-10-10 | 2021-10-08 | BEEF CY2021 -REPAIR-0012 | 2021-CON-00028 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Macco Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306607 | Mariveles NHS Cab. Annex- New Alion | MARIVELES | 2 | 1 | 16 | Repair of Classrooms | 7719964.38 | 1 | 7669082.06 | COMPLETED | 100% | 2021-12-10 |  | BEEF CY2021 -REPAIR-0014 | 2021-CON-00030 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | V Trillana Builders and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306610 | Mariveles NHS Cab.-Annex-Batangas II | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 3505504.87 | 1 | 3500165.91 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0015 | 2021-CON-00031 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Five A Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 300710 | Mariveles NHS Cabcaben | MARIVELES | 2 | 1 | 15 | Repair of Classrooms | 6715056.17 | 1 | 6614285.57 | COMPLETED | 100% | 2021-12-10 |  | BEEF CY2021 -REPAIR-0013 | 2021-CON-00029 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Turquoise Construction & Realty Development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104678 | Capunitan ES | ORION | 2 | 1 | 6 | Repair of Classrooms | 5364413.31 | 1 | 5354192.45 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0016 | 2021-CON-00032 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | RTDJR Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104683 | Pablo R. Roman ES | ORION | 2 | 1 | 6 | Repair of Classrooms | 5753642.58 | 1 | 5732990.17 | COMPLETED | 100% | 2021-12-10 |  | BEEF CY2021 -REPAIR-0017 | 2021-CON-00033 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Polymer Vic Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104695 | Panilao ES | PILAR | 2 | 1 | 8 | Repair of Classrooms | 4518178.57 | 1 | 4505663.68 | COMPLETED | 100% | 2021-11-11 |  | BEEF CY2021 -REPAIR-0018 | 2021-CON-00034 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | NBZ Engineering & Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104797 | Buguion ES | CALUMPIT | 1 | 1 | 8 | Repair of Classrooms | 5539435.93 | 1 | 3700000 | COMPLETED | 100% | 2022-02-11 | 2021-12-28 | PB-21-016 | PB-21-027 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104729 | Borol I ES | BALAGTAS | 2 | 1 | 6 | Repair of Classrooms | 3094968.93 | 1 | 2341888.88 | COMPLETED | 100% | 2022-01-12 | 2022-01-10 | PB-21-017 | PB-21-028 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104740 | Dr. N.V. Rustia MS | BALIUAG | 2 | 1 | 5 | Repair of classrooms | 2973898 | 1 | 2221888.88 | COMPLETED | 100% | 2022-01-12 | 2022-01-10 | PB-21-018 | PB-21-029 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 306717 | Teodoro Evangelista Mem. HS | BALIUAG | 2 | 1 | 2 | Repair of Classrooms | 1084238.79 | 1 | 878179.43 | COMPLETED | 100% | 2021-12-13 | 2022-02-10 | PB-21-020 | PB-21-031 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | G.M. CAPARAS CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104759 | Tiaong ES | BALIUAG | 2 | 1 | 10 | Repair of Classrooms | 6046645.27 | 1 | 4383888.88 | COMPLETED | 100% | 2022-02-11 | 2021-12-03 | PB-21-019 | PB-21-030 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300720 | Alexis G. Santos National High School | BUSTOS | 2 | 1 | 12 | Repair of Classrooms | 4467440.6 | 1 | 3000000 | COMPLETED | 100% | 2022-02-11 | 2021-11-18 | PB-21-021 | PB-21-032 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104721 | Paltok Elementary School | ANGAT | 3 | 1 | 9 | Repair of Classrooms | 5149218.55 | 1 | 4089389.39 | COMPLETED | 100% | 2022-02-11 | 2022-01-21 | PB-21-022 | PB-21-033 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | D' JARED VIEW CONSTRUCTION CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105074 | Kalawakan Elementary School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 4 | Repair of Classrooms | 2086281.89 | 1 | 1519879.67 | COMPLETED | 100% | 2022-02-23 | 2022-02-11 | PB-21-023 | PB-21-061 | 2021-09-17 | 2021-09-24 | 2021-10-06 | 2021-10-12 | 2021-10-19 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105076 | Kalayakan E/S | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 3 | Repair of Classrooms | 2242268.01 | 1 | 1634818.96 | COMPLETED | 100% | 2022-02-23 | 2022-01-20 | PB-21-024 | PB-21-062 | 2021-09-17 | 2021-09-24 | 2021-10-06 | 2021-10-12 | 2021-10-19 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300758 | MINUYAN NATIONAL HIGH SCHOOL | NORZAGARAY | 3 | 1 | 16 | Repair of Classrooms | 6246511.56 | 1 | 4398425.46 | COMPLETED | 100% | 2022-02-11 | 2022-02-11 | PB-21-025 | PB-21-034 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | T.G. OCAMPO CONSTRUCTION AND SURVEYING SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105050 | Bagong Baryo Elementary School | SAN ILDEFONSO | 3 | 1 | 9 | Repair of Classrooms | 6095001.86 | 1 | 5554601.96 | COMPLETED | 100% | 2022-02-18 | 2021-12-20 | PB-21-027 | PB-21-048 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-09-01 | 2021-09-14 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105034 | Calawitan Elementary School | SAN ILDEFONSO | 3 | 1 | 12 | Repair of Classrooms | 4524468.72 | 1 | 3244044.07 | COMPLETED | 100% | 2022-02-11 | 2022-01-20 | PB-21-026 | PB-21-035 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | GMO CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300730 | Calawitan NHS | SAN ILDEFONSO | 3 | 1 | 17 | Repair of Classrooms | 5945745.09 | 1 | 4263099.23 | COMPLETED | 100% | 2022-02-11 | 2022-02-11 | PB-21-028 | PB-21-036 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | GMO CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300772 | Partida HS (San Miguel NHS - Partida HS) | SAN MIGUEL | 3 | 1 | 13 | Repair of Classrooms | 3728391.26 | 1 | 3105283.35 | COMPLETED | 100% | 2022-01-19 | 2021-11-29 | PB-21-030 | PB-21-049 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-09-01 | 2021-09-14 | R.G. ROQUE CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 158502 | San Vicente ES | SAN MIGUEL | 3 | 1 | 3 | Repair of Classrooms | 1733486.25 | 1 | 1609677.73 | COMPLETED | 100% | 2022-01-12 | 2022-01-17 | PB-21-029 | PB-21-037 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105126 | Pasong Inchik ES | SAN RAFAEL | 3 | 1 | 7 | Repair of Classrooms | 3691870.19 | 1 | 2944713.7 | COMPLETED | 100% | 2022-01-12 | 2022-01-10 | PB-21-031 | PB-21-038 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | R.G. ROQUE CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300740 | ASSEMBLYWOMAN FELICITA G. BERNARDINO MEMORIAL TRADE SCHOOL | MARILAO | 4 | 1 | 12 | Repair of Classrooms | 3261889.39 | 1 | 2480102.24 | COMPLETED | 100% | 2022-01-12 | 2022-01-10 | PB-21-032 | PB-21-039 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | RHR CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Cabanatuan City | 107081 | Ibabao Bana ES | CABANATUAN CITY | 3 | 1 | 2 | Repair of Classrooms | 811379.13 | 1 |  | COMPLETED | 100% | 2021-09-03 | 2021-08-31 | [7 empty] | RC Pallarca Contruction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Cabanatuan City | 107114 | Pagas Elementary School | CABANATUAN CITY | 3 | 1 | 4 | Repair of Classrooms | 2167148.36 | 1 |  | COMPLETED | 100% | 2021-11-02 | 2021-09-03 | [7 empty] | Marvelous Quejada Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Gapan City | 105322 | Mabuga ES | CITY OF GAPAN | 4 | 1 | 4 | Repair of Classrooms | 2788898.31 | 1 | 2779344.7 | COMPLETED | 100% | 2021-10-03 | 2021-09-08 | 2021-05-31-001-CL-Repair | 2021-05-31-001-CL-Repair | 2021-06-01 | 2021-06-08 | 2021-06-21 | 2021-06-28 | 2021-07-05 | Joynieltin Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106073 | Bical ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1200000 | 1 | 1188888.88 | COMPLETED | 100% | 2021-10-17 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | F.A ASPRER CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106064 | Calumpang ES | MABALACAT CITY | 1 | 1 | 7 | Repair of Classrooms | 4000000 | 1 | 3970038.52 | COMPLETED | 100% | 2021-12-09 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106075 | Dapdap ES | MABALACAT CITY | 1 | 1 | 7 | Repair of Classrooms | 3000000 | 1 | 2989121.21 | COMPLETED | 100% | 2021-10-25 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106078 | Duquit ES | MABALACAT CITY | 1 | 1 | 4 | Repair of Classrooms | 1304023.09 | 1 | 1288888.88 | COMPLETED | 100% | 2021-10-17 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106080 | Lakandula ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1363525.22 | COMPLETED | 100% | 2021-10-17 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1 | 1 | 12 | Repair of Classrooms | 3200000 | 1 | 2896823.85 | COMPLETED | 100% | 2021-11-26 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT CITY | 1 | 1 | 26 | Repair of Classrooms | 10000000 | 1 | 7188888.88 | COMPLETED | 100% | 2021-12-12 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | NULAS BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106069 | Mauaque Resetlement ES | MABALACAT CITY | 1 | 1 | 18 | Repair of Classrooms | 7000000 | 1 | 6989813.25 | COMPLETED | 100% | 2021-12-09 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | TRACCOR BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106070 | San Joaquin ES | MABALACAT CITY | 1 | 1 | 18 | Repair of Classrooms | 9000000 | 1 | 6210013.85 | COMPLETED | 100% | 2021-12-16 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 306942 | Santos Ventura National High School | MABALACAT CITY | 1 | 1 | 24 | Repair of Classrooms | 6000000 | 1 | 4664104.47 | COMPLETED | 100% | 2021-12-12 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106071 | Sapang Biabas Resettlement ES | MABALACAT CITY | 1 | 1 | 12 | Repair of Classrooms | 6000000 | 1 | 4799865.66 | COMPLETED | 100% | 2021-12-16 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 345342 | SHS within Sapang Biabas Resettlement ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1686102.39 | 1 | 1306846.51 | COMPLETED | 100% | 2021-10-17 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106072 | Sta. Ines ES | MABALACAT CITY | 1 | 1 | 24 | Repair of Classrooms | 7000000 | 1 | 5247520.08 | COMPLETED | 100% | 2021-12-09 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | 17 | Repair of Classrooms | 7200000 | 1 | 7169996.42 | COMPLETED | 100% | 2021-12-16 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 104887 | Balayong ES | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1514093.45 | 1 | 1029265.01 | COMPLETED | 100% | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-01 | RADIANCE TRADERS & BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 323604 | Cong. Teodulo Natividad High School | CITY OF MALOLOS (Capital) | 1 | 1 | 12 | Repair of Classrooms | 2071171.7 | 1 | 1659737.13 | COMPLETED | 100% | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-01 | R. G. DIAZ BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 104869 | Dakila ES | CITY OF MALOLOS (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1364038.83 | 1 | 1049168.41 | COMPLETED | 100% | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-02 | ELMUEL JAY TRADING & CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 4 | Repair of Classrooms | 1735446.03 | 1 | 1215979.68 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 500967 | Malhacan Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 2 | Repair of Classrooms | 1039502.43 | 1 | 828529.23 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 104936 | Tugatog ES | CITY OF MEYCAUAYAN | 4 | 1 | 4 | Repair of Classrooms | 1627673.53 | 1 | 1160149.17 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105537 | Licaong ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 1 | Repair of Classroom | 189079 | 1 |  | COMPLETED | 100% | 2021-10-04 | 2021-08-16 | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500396 | Magtanggol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2436219.35 | 1 |  | COMPLETED | 100% | 2021-10-29 |  | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | AMC CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500396 | Magtanggol IS | SCIENCE CITY OF MUÑOZ | 2 |  | 4 | Repair of Classrooms | 1998270.36 | 1 |  | COMPLETED | 100% | 2021-10-29 |  | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | GR ERCILLA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105549 | Mangandingay Elementary School | SCIENCE CITY OF MUÑOZ | 2 | 1 | 7 | Repair of Classrooms | 3643972.5 | 1 |  | COMPLETED | 100% | 2021-11-28 |  | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | FC MARTINEZ CONSTRUCTION DEVELOPMENT AND SUPPLY CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500398 | Palusapis IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2239646.39 | 1 |  | COMPLETED | 100% | 2021-10-29 |  | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | D.B. BARAQUEL CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105563 | Villa Isla ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2075870.16 | 1 |  | COMPLETED | 100% | 2021-10-29 |  | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | MN COLOMA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105564 | Villa Nati ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | Repair of Classrooms | 436159.58 | 1 |  | COMPLETED | 100% | 2021-10-04 | 2021-08-16 | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 22 | Repair of Classrooms | 10000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105280 | C.B. Tejero E/S | CUYAPO | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105267 | Columbitin Elementry School | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 306824 | Cuyapo National High School Annex | CUYAPO | 1 | 1 | 7 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105273 | Dr. A. Ongsiako Sr. ES | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105279 | Matindeg ES | CUYAPO | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105296 | Tagtagumbao PS | CUYAPO | 1 | 1 | 3 | Repair of Classrooms | 1703864.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105405 | Bagong Barrio ES | GUIMBA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105407 | Balingog West ES | GUIMBA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105380 | Cavite ES | GUIMBA | 1 | 1 | 10 | Repair of Classrooms | 4312500 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105382 | Consuelo ES | GUIMBA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105388 | Guiset ES | GUIMBA | 1 | 1 | 8 | Repair of Classrooms | 3812500 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105419 | Macamias ES | GUIMBA | 1 | 1 | 4 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 501658 | Maybubon Integrated School | GUIMBA | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105399 | Sta. Cruz ES | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105430 | STA. VERONICA ELEMENTARY SCHOOL | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105433 | Yuson ES | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105480 | Licab CS | LICAB | 1 | 1 | 18 | Repair of Classrooms | 8062500 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105481 | Linao ES | LICAB | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105483 | San Casimiro ES | LICAB | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105619 | Bertese ES | QUEZON | 1 | 1 | 5 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105622 | Labong ES | QUEZON | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105623 | Pulong Bahay Elementary School | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105624 | Quezon CS | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3358788.77 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105627 | San Andres I ES | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105629 | San Manuel ES | QUEZON | 1 | 1 | 10 | Repair of Classrooms | 4312500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105631 | Sta. Rita ES | QUEZON | 1 | 1 | 11 | Repair of Classrooms | 4562500 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105769 | Buasao ES | SANTO DOMINGO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105775 | Dolores ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105785 | Sta. Rita ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105781 | Villa Juan ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 2812500 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105789 | Bagong Silang ES | TALAVERA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105790 | Bakal I ES | TALAVERA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105791 | Bakal II ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 1976215.59 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105794 | Bulac ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105798 | Casulucan Este ES | TALAVERA | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105817 | Dimasalang Sur ES | TALAVERA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 | 1 | 10 | Repair of Classrooms | 5000000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105831 | Sibul ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 1976215.59 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105855 | Concepcion East ES | ZARAGOZA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105856 | Concepcion West ES | ZARAGOZA | 1 | 1 | 8 | Repair of Classrooms | 3812500 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159016 | Felicidad V. Buendia ES | ZARAGOZA | 1 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159010 | Manaol ES | ZARAGOZA | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105860 | Mayamot ES | ZARAGOZA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105861 | San Isidro Elementary School | ZARAGOZA | 1 | 1 | 15 | Repair of Classrooms | 6562500 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105864 | Sta. Lucia (Y) ES | ZARAGOZA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105595 | Cambitala ES | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1710328.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105600 | Liberty ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1968182.78 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105601 | Marikit ES | PANTABANGAN | 2 | 1 | 2 | Repair of Classrooms | 1122245.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159007 | Masiway ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1918731.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105604 | Pantabangan East CS | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1494082.21 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105606 | Salvacion Elementary School | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1951540.35 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105608 | San Juan ES | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105638 | Bicos ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1147507.92 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105639 | Cabucbucan ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105648 | Macapsing ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105299 | Bagting ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1123672.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105300 | Bantug ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1135127.05 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105303 | Calabasa ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1123672.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105304 | Camatchile Elementay School | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105310 | Malinao Elementary School | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105347 | Balangkare ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 2 | Repair of Classrooms | 1154027.53 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105462 | Casa Real Elementary School | LAUR | 3 | 1 | 3 | Repair of Classrooms | 1746398.03 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105578 | Langka ES | PALAYAN CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1230314.78 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105590 | Pinaltakan ES(Red Cross Village PS) | PALAYAN CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1230314.78 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300856 | Sta. Rita NHS | CABIAO | 4 | 1 | 3 | Repair of Classrooms | 1746398.03 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105369 | Nazareth Elementary School | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms | 975216.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300848 | San Mariano National High School | SAN ANTONIO | 4 | 1 | 12 | Repair of Classrooms | 5500000 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105688 | San Roque ES | SAN ISIDRO | 4 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 301050 | Baretto National HIgh School | OLONGAPO CITY | 1 | 1 | 8 | Repair of Classrooms | 4400000 | 1 | 4389769.38 | COMPLETED | 100% | 2021-11-23 |  | 2021-07-194 lot 4 | 2021-07-194 lot 4 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | J.I. Viacrusis Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107119 | Boton ES | OLONGAPO CITY | 1 | 1 | 11 | Repair of Classrooms | 6000000 | 1 | 5957131.73 | COMPLETED | 100% | 2021-12-23 |  | 2021-07-194 lot 3 | 2021-07-194 lot 3 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | V. Trillana Builders and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107126 | Gordon Heights I Elementary School | OLONGAPO CITY | 1 | 1 | 30 | Repair of Classrooms | 12000000 | 1 | 11969997.92 | COMPLETED | 100% | 2022-01-21 |  | 2021-07-194 lot 1 | 2021-07-194 lot 1 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | Mitzie Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 301056 | Kalalake NHS | OLONGAPO CITY | 1 | 1 | 14 | Repair of Classrooms | 7600000 | 1 | 7569619.71 | COMPLETED | 100% | 2021-12-23 |  | 2021-07-194 lot 2 | 2021-07-194 lot 2 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | AMP Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107130 | Tabacuhan ES | OLONGAPO CITY | 1 | 1 | 7 | Repair of Classrooms | 3593934.69 | 1 | 3542319.53 | COMPLETED | 100% | 2021-11-23 |  | 2021-07-194 lot 5 | 2021-07-194 lot 5 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | Bancal Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106119 | Bucanan Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1538159.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 159527 | Mariano D. Baron ES | MAGALANG | 1 | 1 | 4 | Repair of Classrooms | 1529504.96 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106131 | San Miguel ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1016684.6 | 1 | 1182095.53 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106141 | Talimundoc Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1376840.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105966 | FLORIDABLANCA ELEMENTARY SCHOOL | FLORIDABLANCA | 2 | 1 | 6 | Repair of Classrooms | 3711312.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 159528 | Sitio Culubasa ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 2419352.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105975 | Sta. Monica ES | FLORIDABLANCA | 2 | 1 | 6 | Repair of Classrooms | 3490321.48 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105976 | Sto. Rosario ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 2437094.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 2 | Repair of Classrooms | 1016684.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106013 | San Antonio ES | GUAGUA | 2 | 1 | 5 | Repair of Classrooms | 2449530.1 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106057 | Santiago ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2667607.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106216 | Camias ES | PORAC | 2 | 1 | 8 | Repair of Classrooms | 3736512.16 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106296 | V. De Castro ES | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 3045421.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106267 | Batang II ES | SASMUAN (SEXMOAN) | 2 | 1 | 2 | Repair of Classrooms | 1486465.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106271 | San Pedro ES | SASMUAN (SEXMOAN) | 2 | 1 | 4 | Repair of Classrooms | 2508155.57 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105898 | Arayat CS | ARAYAT | 3 | 1 | 8 | Repair of Classrooms | 3705737.72 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105881 | Batasan ES | ARAYAT | 3 | 1 | 8 | Repair of Classrooms | 3900024.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105883 | Candating ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3739085.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105885 | Guemasan ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3981381.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105886 | Lacquios ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3503855.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105887 | Mapalad ES | ARAYAT | 3 | 1 | 5 | Repair of Classrooms | 2766819.95 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 305740 | San Juan Baño High School | ARAYAT | 3 | 1 | 10 | Repair of Classrooms | 2454028.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105893 | San Nicolas ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3503855.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106172 | Malino ES | MEXICO | 3 | 1 | 6 | Repair of Classrooms | 3117879 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106189 | Pandacaqui Resettlement Elementary School | MEXICO | 3 | 1 | 8 | Repair of Classrooms | 3189141.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105869 | Cansinala Elementary School | APALIT | 4 | 1 | 6 | Repair of Classrooms | 3703073.13 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105870 | Fausto Gonzales Sioco Memorial School | APALIT | 4 | 1 | 5 | Repair of Classrooms | 2900097.13 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105871 | Galang Memo. ES (Calantipe ES) | APALIT | 4 | 1 | 5 | Repair of Classrooms | 3063958.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105875 | Sampaga ES | APALIT | 4 | 1 | 4 | Repair of Classrooms | 2749163.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105878 | Sto. Rosario ES | APALIT | 4 | 1 | 8 | Repair of Classrooms | 4849474.59 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105879 | Sucad ES | APALIT | 4 | 1 | 10 | Repair of Classrooms | 5935952.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105880 | Sulipan ES | APALIT | 4 | 1 | 6 | Repair of Classrooms | 3115052.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105929 | Bahay Pare ES | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105955 | Gulap ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2648153.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105956 | Lanang ES | CANDABA | 4 | 1 | 2 | Repair of Classrooms | 1434384.43 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105936 | Magumbali Elementary School | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105957 | Mandasig ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2733276.36 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106097 | San Vicente Ferrer ES | MACABEBE | 4 | 1 | 3 | Repair of Classrooms | 1651357.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106241 | San Isidro ES | SAN LUIS | 4 | 1 | 7 | Repair of Classrooms | 3506001.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106242 | San Jose ES | SAN LUIS | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106245 | San Luis CS | SAN LUIS | 4 | 1 | 2 | Repair of Classrooms | 1107135.94 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106253 | Sto. Rosario ES | SAN LUIS | 4 | 1 | 5 | Repair of Classrooms | 3034613.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500981 | Arch. E. Cinense Memorial Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107167 | Bulaon ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1906166.55 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500146 | Calulut IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107180 | Del Rosario ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1821749.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500136 | Lara IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500145 | Maimpis IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500980 | Malpitic Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 307611 | Northville High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1799902.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 12 | Repair of Classrooms | 5220000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500979 | Pandaras Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 5 | Repair of Classrooms | 3500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500978 | Pulung Bulu Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500143 | Saguin IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107195 | San Fernando ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 5916427 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107175 | San Jose-Juliana ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500150 | Sta. Lucia Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose City | 105709 | San Jose East Central School | SAN JOSE CITY | 2 | 1 | 13 | Repair of Classrooms | 3497407.03 | 1 | 3497407.03 | COMPLETED | 100% | 2021-12-19 |  | REPAIR 2021 - RIII - SAN JOSE CITY - 001 | [6 empty] | JGR DESIGN AND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose City | 105727 | Saranay Elementary School | SAN JOSE CITY | 2 | 1 | 3 | Repair of Classrooms | 1213958.94 | 1 |  | COMPLETED | 100% | 2021-09-19 | 2021-09-19 | REPAIR 2021 - RIII - SAN JOSE CITY - 002 | [6 empty] | ADROIT CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107144 | Bagong Buhay E ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | Repair of Classrooms | 3610367.54 | 1 | 3564888.88 | COMPLETED | 100% | 2021-12-07 |  | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 001 | PB-ER-CW-2021-07-01 lot 1 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | Altitude Engineering and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107149 | Minuyan ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | Repair of Classrooms | 4851098.41 | 1 | 4831093.18 | COMPLETED | 100% | 2021-12-07 | 2021-10-19 | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 002 | PB-ER-CW-2021-07-01 lot 2 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | RKEA Builders and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107163 | SAN RAFAEL (BBH) ELEMENTARY SCHOOL | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | Repair of Classrooms | 2006901.5 | 1 | 1993656.57 | COMPLETED | 100% | 2021-12-07 | 2021-10-19 | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 003 | PB-ER-CW-2021-07-01 lot 3 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | Che-Riss Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106309 | San Jose ES | ANAO | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106338 | Bancay I ES | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 846601.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106342 | Caniag ES | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 1078788.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106361 | Cayasan PS | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 846676.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106362 | Libueg ES | CAMILING | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106346 | Malacampa ES - Main | CAMILING | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2005912.29 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106332 | Pindangan 2nd ES | CAMILING | 1 | 1 | 5 | Repair of Classrooms & Toilets | 2747329.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106335 | Surgui ES | CAMILING | 1 | 1 | 5 | Repair of Classrooms & Toilets | 2516279.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106522 | Rotrottooc-Calabtangan ES | MAYANTOC | 1 | 1 | 1 | Repair of Classrooms & Toilets | 491854 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106523 | San Bartolome ES | MAYANTOC | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2317898.59 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106525 | Taldiapan PS | MAYANTOC | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1605328.99 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106541 | Banaoang East Elementary School | MONCADA | 1 | 1 | 1 | Repair of Classrooms & Toilets | 490723.35 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106528 | Calamay ES | MONCADA | 1 | 1 | 2 | Repair of Classrooms & Toilets | 857532.76 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106547 | Camangaan PS | MONCADA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106529 | Lapsing ES | MONCADA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106532 | Moncada North CS | MONCADA | 1 | 1 | 4 | Repair of Classrooms | 2546329.18 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106577 | Carino ES | PANIQUI | 1 | 1 | 3 | Repair of Classrooms | 1482402.1 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106595 | Doña Felisa Y. Sawit ES | PURA | 1 | 1 | 6 | Repair of Classrooms & Toilets | 3395792.52 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106596 | Estipona ES | PURA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1899462.94 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106599 | Matindeg ES | PURA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1632680.09 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106603 | Poroc PS | PURA | 1 | 1 | 2 | Repair of Classrooms & Toilets | 1261201.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1 | 1 | 4 | Repair of Classrooms | 1928035.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106612 | San Raymundo ES | RAMOS | 1 | 1 | 3 | Repair of Classrooms | 1792612.4 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106615 | Balloc ES | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 1702097.21 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106622 | Maasin Elementary School | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 2768946.07 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106653 | Legaspi ES | SAN MANUEL | 1 | 1 | 8 | Repair of Classrooms | 4839624.09 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106657 | Salcedo ES | SAN MANUEL | 1 | 1 | 3 | Repair of Classrooms | 1779579.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106673 | Nambalan ES | SANTA IGNACIA | 1 | 1 | 10 | Repair of Classrooms | 4954809.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106674 | Pilpila ES | SANTA IGNACIA | 1 | 1 | 3 | Repair of Classrooms | 1752756.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106629 | David Elementary School | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 2406468.52 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 307001 | Moriones High School | SAN JOSE | 2 | 1 | 2 | Repair of Classrooms | 1173034.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 160015 | Quimmardero Elementary School | SAN JOSE | 2 | 1 | 5 | Repair of Classrooms | 2480562.82 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106646 | Sta. Cruz ES | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 1694032.09 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 307021 | Balayang HS | VICTORIA | 2 | 1 | 9 | Repair of Classrooms | 3292984.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106787 | Bulo ES | VICTORIA | 2 | 1 | 7 | Repair of Classrooms | 3922672.67 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106780 | Mangolago Elementary School | VICTORIA | 2 | 1 | 3 | Repair of Classrooms | 1544896.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106782 | San Agustin ES | VICTORIA | 2 | 1 | 5 | Repair of Classrooms | 2728771.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106314 | Banaba ES | BAMBAN | 3 | 1 | 6 | Repair of Classrooms | 3288427.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106311 | Pag-asa Elementary School | BAMBAN | 3 | 1 | 6 | Repair of Classrooms | 2740683 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106373 | Dolores ES | CAPAS | 3 | 1 | 4 | Repair of Classrooms | 2393193.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106372 | Juan Navarro ES | CAPAS | 3 | 1 | 2 | Repair of Classrooms | 1276692.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106374 | Kawili-Wili ES | CAPAS | 3 | 1 | 3 | Repair of Classrooms | 1753488.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 300968 | Lawy NHS | CAPAS | 3 | 1 | 6 | Repair of Classrooms | 3178167.26 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106404 | Concepcion North CES | CONCEPCION | 3 | 1 | 11 | Repair of Classrooms | 4377888.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106428 | Concepcion West Central ES | CONCEPCION | 3 | 1 | 9 | Repair of Classrooms | 4045549.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106399 | Magunting ES | CONCEPCION | 3 | 1 | 5 | Repair of Classrooms | 2912652.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106496 | Bantog ES | LA PAZ | 3 | 1 | 6 | Repair of Classrooms | 3477686.04 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106493 | Matayumtayum ES | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1619336.1 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106494 | Mayang ES | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1772645.66 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106504 | Rizal Multigrade | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1628242.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac City | 106740 | Lourdes ES | CITY OF TARLAC (Capital) | 2 | 1 | 5 | Repair of Classrooms | 1649234.99 | 1 | 1393961.94 | COMPLETED | 100% | 2021-10-30 | [8 empty] | MRRM Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac City | 106772 | Tarlac West Central ES | CITY OF TARLAC (Capital) | 2 | 1 | 17 | Repair of Classrooms | 6822915.62 | 1 | 6455834.24 | COMPLETED | 100% | 2021-10-30 | [8 empty] | AR. ESBI Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 160507 | Buenavista Elementary School | CASTILLEJOS | 1 | 1 | 4 | Repair of classrooms | 1811036.46 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106950 | Linusungan Elementary School | SAN MARCELINO | 1 | 1 | 12 | Repair of classrooms | 5299956.09 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 107021 | Tibag Elementary School | SUBIC | 1 | 1 | 4 | Repair of classrooms | 1581329.3 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | 8 | Repair of classrooms | 3268711.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106818 | Bucao Elementary School | BOTOLAN | 2 | 1 | 7 | Repair of classrooms | 2589175.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106830 | Laoag Elementary School | CABANGAN | 2 | 1 | 7 | Repair of classrooms | 3464002.24 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Zambales | 106838 | Sto. Nino Primary School | CABANGAN | 2 | 1 | 3 | Repair of classrooms | 1273198.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106843 | Dampay Elementary School | CANDELARIA | 2 | 1 | 7 | Repair of classrooms | 1943439.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106915 | Manggahan Elementary Scchool | PALAUIG | 2 | 1 | 5 | Repair of classrooms | 2188736.27 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region IV-A | Antipolo City | 342175 | Antipolo City SHS | CITY OF ANTIPOLO | 1 | 1 | 20 | Repair of Classrooms | 2060510.67 | 1 |  | COMPLETED | 100% |  | 2021-12-23 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Antipolo City | 109330 | Mambugan I ES | CITY OF ANTIPOLO | 1 | 1 | 9 | Repair of Classrooms | 2330000 | 1 |  | COMPLETED | 100% |  |  |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | N.Q. Villapando Const. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Antipolo City | 109331 | Mayamot ES | CITY OF ANTIPOLO | 1 | 1 | 12 | Repair of Classrooms | 3485696.99 | 1 | 4923244.483 | COMPLETED | 100% |  |  |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | N.Q. Villapando Const. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Antipolo City | 109350 | Isaias S. Tapales ES | CITY OF ANTIPOLO | 2 | 1 | 7 | Repair of Classrooms | 1660265.55 | 1 |  | COMPLETED | 100% |  | 2021-12-29 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Antipolo City | 109336 | Peace Village ES | CITY OF ANTIPOLO | 2 | 1 | 10 | Repair of Classrooms | 2278722.59 | 1 |  | COMPLETED | 100% |  | 2021-12-23 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 107878 | Bayanan ES | BACOOR | 2 | 1 | 4 | Repair of Classrooms | 205499.66 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 305685 | City of Bacoor National High School - Georgetown | BACOOR | 2 | 1 | 2 | Repair of Classrooms | 814525.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 301188 | Eastern Bacoor NHS | BACOOR | 2 | 1 | 10 | Repair of Classrooms | 1169325.48 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 107870 | Habay ES | BACOOR | 2 | 1 | 1 | Repair of Classroom | 272944.35 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 164009 | Poblacion ES (Bacoor ES (Annex)) | BACOOR | 2 | 1 | 4 | Repair of Classrooms | 107278.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Bacoor City | 305689 | Responsible Village Leaders Learning Academy (REVILLA) High School | BACOOR | 2 | 1 | 6 | Repair of Classrooms | 191032.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas | 107670 | Bayanan Elementary School | SAN PASCUAL | 2 | 1 | 5 | Repair of Classrooms | 2823484.28 | 1 | 2798484 | COMPLETED | 100% | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 004 | REPAIR 2021 - R IV-A - Batangas Province - 004 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | Supplicon Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas | 107675 | Malakimpook Elementary School | SAN PASCUAL | 2 | 1 | 6 | Repair of Classrooms | 2404006.82 | 1 | 2394766.84 | COMPLETED | 100% | 2021-11-24 | 2021-11-24 | REPAIR 2021 - R IV-A - Batangas Province - 003 | REPAIR 2021 - R IV-A - Batangas Province - 003 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | RRE Erectors Construction and Trading Specialist | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas | 107548 | Calantas Elementary School | ROSARIO | 4 | 1 | 5 | Repair of Classrooms | 3065032.18 | 1 | 3046773.49 | COMPLETED | 100% | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 001 | REPAIR 2021 - R IV-A - Batangas Province - 001 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | VRV Cosntruction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas | 301161 | Tulos National High School | ROSARIO | 4 | 1 | 7 | Repair of Classrooms | 4431241.78 | 1 | 4420000 | COMPLETED | 100% | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 002 | REPAIR 2021 - R IV-A - Batangas Province - 002 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | Botey Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas | 107620 | Paaralang Elementarya ng Muzon | SAN JUAN | 4 | 1 | 5 | Repair of Classrooms | 1526816.02 | 1 | 1507138.14 | COMPLETED | 100% | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 005 | REPAIR 2021 - R IV-A - Batangas Province - 005 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | GS Motar Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 109544 | Bagong Silang ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | Repair of Classrooms | 820765.96 | 1 | 640187.3 | COMPLETED | 100% | 10/29/2021 | 11/19/2021 | R4A-DI-BEFF- 2021-06-01 | INFRA- 2021-001 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Marakesh Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 109607 | Eulalia Talban Ebora MES (Malalim ES) | BATANGAS CITY (Capital) | 5 | 1 | 1 | Repair of Classroom | 569506.79 | 1 | 562449.74 | COMPLETED | 100% | 10/15/2021 | 10/15/2021 | R4A-DI-BEFF- 2021-06-05 | INFRA- 2021-005 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | VRV Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 109615 | Jose C. Pastor ES (Pallocan ES) | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1247915.18 | 1 | 1120000 | COMPLETED | 100% | 10/29/2021 | 2021-08-10 | R4A-DI-BEFF- 2021-06-02 | INFRA- 2021-002 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Botey Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 301483 | Talumpok NHS | BATANGAS CITY (Capital) | 5 | 1 | 6 | Repair of Classrooms | 2467827.74 | 1 | 2337742.39 | COMPLETED | 100% | 11/29/2021 | 11/29/2021 | R4A-DI-BEFF- 2021-06-06 | INFRA- 2021-006 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | VRV Construction and Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 109562 | Tulo 1 ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1255251.59 | 1 | 978989.46 | COMPLETED | 100% | 10/29/2021 | 11/19/2021 | R4A-DI-BEFF- 2021-06-03 | INFRA- 2021-003 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Marakesh Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Batangas City | 109559 | Tulo II ES | BATANGAS CITY (Capital) | 5 | 1 | 4 | Repair of Classrooms | 1663537.15 | 1 | 1445893.05 | COMPLETED | 100% | 11/13/2021 | 10/20/2021 | R4A-DI-BEFF- 2021-06-04 | INFRA- 2021-004 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | EUGE Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Binan City | 108225 | Pagkakaisa ES | CITY OF BIÑAN | 0 | 1 | 8 | Repair of Classrooms | 3010686.91 | 1 | 2220628.1 | COMPLETED | 100% | 12/25/2021 |  | R4A-BNN-2021-01 |  | 2021-07-19 | 2021-07-29 | 2021-08-10 | 2021-08-24 | 2021-09-16 | GS Motar Builders Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cabuyao City | 108251 | San Isidro ES | CABUYAO | 2 | 1 | 8 | Repair of Classrooms | 3799177.85 | 1 | 3143580.78 | COMPLETED | 100% | 2022-02-01 | [8 empty] | GS Motar Builders Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Calamba City | 301517 | Canlubang Integrated School | CITY OF CALAMBA | 0 | 1 | 10 | Repair of Classrooms | 1936281.06 | 1 | 1388822.15 | COMPLETED | 100% | 01/27/2022 |  | 7736402 | Contract no. 4 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-08-17 | JB Alarcon Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Calamba City | 109846 | Laguerta ES | CITY OF CALAMBA | 0 | 1 | 4 | Repair of Classrooms | 833288.86 | 1 | 666050.88 | COMPLETED | 100% | 01/27/2022 |  | 7736417 | Contract no. 2 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-08-17 | Aaron Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108018 | Binakayan Elementary School | KAWIT | 1 | 1 | 15 | Repair of classrooms | 10177851.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 301174 | Binakayan National High School | KAWIT | 1 | 1 | 14 | Repair of classrooms | 7648351.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108102 | Bulihan Sites & Services Project Elementary School | SILANG | 5 | 1 | 12 | Repair of classrooms | 8157208.21 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108123 | Kaong Elementary School | SILANG | 5 | 1 | 4 | Repair of classrooms | 2631294.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108110 | Silang Central School | SILANG | 5 | 1 | 4 | Repair of classrooms | 2628381.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108162 | Halayhay Elementary School | TANZA | 7 | 1 | 6 | Repair of classrooms | 4022060.16 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108164 | Julugan Elementary School | TANZA | 7 | 1 | 4 | Repair of classrooms | 2629178.24 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108077 | Petronilo L. Torres Memorial Elementary School | NAIC | 8 | 1 | 8 | Repair of classrooms | 5611258.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite | 108154 | Tagaytay City Central School | TAGAYTAY CITY | 8 | 1 | 9 | Repair of classrooms | 5607232.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2103930.08 | COMPLETED | 100% | 2022-01-16 |  |  |  | 2021-07-06 | 2021-07-13 | 2021-07-25 | 2021-08-06 | 2021-08-19 | RA del Rosario | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Dasmarinas City | 107924 | Salitran Elementary | CITY OF DASMARIÑAS | 4 | 1 | 8 | Repair of Classrooms | 2842498.24 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | General Trias City | 107961 | Mary Cris ES | CITY OF GENERAL TRIAS | 6 | 1 | 8 | Repair of Classrooms | 3643612.19 | 1 |  | COMPLETED | 100% | [7 empty] | 2021-07-15 | 2021-10-15 | R.A. Yolangco Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | General Trias City | 107963 | Parklane ES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 2595334.03 | 1 |  | COMPLETED | 100% | [7 empty] | 2021-07-15 | 2021-10-15 | R.A. Yolangco Construction & Trading | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Imus City | 107972 | Buhay na Tubig ES | IMUS | 3 | 1 | 12 | Repair of Classrooms | 1696167.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Imus City | 164002 | Palico Elementary School | IMUS | 3 | 1 | 8 | Repair of Classrooms | 1302935.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Laguna | 108272 | Burol Elementary School | CAVINTI | 4 | 1 | 8 | Repair of Classrooms | 3694494.47 | 1 |  | COMPLETED | 100% |  |  |  |  | 2018-11-23 | 2018-12-14 | 2001-06-21 | 2019-08-02 | 2019-08-09 | N.T. Sotelo Construction & Supply Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Laguna | 164517 | Layasin Elementary School | CAVINTI | 4 | 1 | 3 | Repair of Classrooms | 1301264.28 | 1 |  | COMPLETED | 100% | [6 empty] | 2001-06-21 |  |  | N.T. Sotelo Construction & Supply Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109640 | Anangi ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1106822.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109671 | Anilao ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 1642536.71 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 301486 | Anilao National High School | LIPA CITY | 6 | 1 | 10 | Repair of Classrooms | 5706481.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 6 | 1 | 11 | Repair of Classrooms | 6185163.7 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109642 | Brion- Silva ES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2284424.96 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109692 | Cipriano Andal MES (Halang ES) | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 1324432.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 501184 | Cumba-Quezon Integrated School | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1186688.79 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109661 | Dagatan ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109690 | Duhatan ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2064541.58 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109645 | Edilberto L. Mendoza MES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2089854.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 | 4606330.1 | COMPLETED | 100% |  |  |  | R4A-LC-2019-11 | JULY 15-22, 2019 | 2019-07-24 | 2019-08-05 | 2019-08-27 | 2019-10-18 | MARAKESH ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109662 | Inosloban-Marawoy ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy Integrated National High School | LIPA CITY | 6 | 1 | 18 | Repair of Classrooms | 9484206.54 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109676 | Labac Elementary School | LIPA CITY | 6 | 1 | 11 | Repair of Classrooms | 6236230.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 303491 | Lipa City Senior High School | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2284424.96 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109682 | Pagolingin Bata ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 2428660.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 301497 | Pinagtongulan Integrated National High School | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 1921678.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109664 | Plaridel ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109684 | Rizal Elementary School | LIPA CITY | 6 | 1 | 14 | Repair of Classrooms | 3366304.02 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109685 | Sampaguita ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2642639.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109652 | San Isidro ES | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6761943.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 301500 | San Isidro Integrated National High School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 | 2098281.46 | COMPLETED | 100% | [9 empty] | EUGE CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109666 | Santo Toribio ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School ( | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6490636.92 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3396854.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109655 | Sto. Toribio ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1130408.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109702 | Tagbakin Elementary School | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1120702.21 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109703 | Tambo ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2867464.75 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lucena City | 109729 | BLISS Elementary School | LUCENA CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 9138166.33 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Lucena City | 109724 | Reymar Compound Elementary School | LUCENA CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 5313624.1 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108790 | Lual Elementary School | INFANTA | 1 | 1 | 8 | Repair of Classrooms | 2200040.47 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108791 | Magsaysay ES | INFANTA | 1 | 1 | 6 | Repair of Classrooms | 2050705.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108890 | Balaybalay ES | MAUBAN | 1 | 1 | 2 | Repair of Classrooms | 1116692.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 301301 | Cagbalete Island National High School | MAUBAN | 1 | 1 | 7 | Repair of Classrooms | 4598852.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 | 1 | 2 | Repair of Classrooms | 1627177.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108970 | Pagbilao CES (Pagbilao CES & Pabilao East CES) | PAGBILAO | 1 | 1 | 10 | Repair of Classrooms | 3451870.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109085 | Sampaloc Elementary School (Main) | SAMPALOC | 1 | 1 | 19 | Repair of Classrooms | 7673789.08 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108681 | Kinabuhayan ES | DOLORES | 2 | 1 | 2 | Repair of Classrooms | 973956.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108673 | Rosendo Algenio ES | DOLORES | 2 | 1 | 4 | Repair of Classrooms | 1860393.3 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109159 | Balubal ES | SARIAYA | 2 | 1 | 2 | Repair of Classrooms | 850184.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109174 | BIGNAY II ES | SARIAYA | 2 | 1 | 2 | Repair of Classrooms | 1417683.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109183 | Janagdong II ES | SARIAYA | 2 | 1 | 1 | Repair of Classroom | 659568.15 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109167 | Pantoc Elementary School | SARIAYA | 2 | 1 | 3 | Repair of Classrooms | 1496369.93 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109172 | Tumbaga II ES | SARIAYA | 2 | 1 | 3 | Repair of Classrooms | 1470422.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 109266 | BEHIA ES | TIAONG | 2 | 1 | 3 | Repair of Classrooms | 1925971.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108543 | Hagonghong ES | BUENAVISTA | 3 | 1 | 7 | Repair of Classrooms | 3780814.07 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 7 | Repair of Classrooms | 1229887.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108548 | San Isidro Ibaba ES | BUENAVISTA | 3 | 1 | 2 | Repair of Classrooms | 1324966.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108549 | San Isidro Ilaya ES | BUENAVISTA | 3 | 1 | 2 | Repair of Classrooms | 1233004.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108645 | Bolo Elementary School | CATANAUAN | 3 | 1 | 3 | Repair of Classrooms | 2134049.76 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108888 | Tubigan ES | MACALELON | 3 | 1 | 3 | Repair of Classrooms | 1182153.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108942 | Santa Rosa ES | MULANAY | 3 | 1 | 3 | Repair of Classrooms | 1255904.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108607 | Sabang ES | CALAUAG | 4 | 1 | 8 | Repair of Classrooms | 3914874.7 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108586 | Tabansak ES | CALAUAG | 4 | 1 | 5 | Repair of Classrooms | 3328109.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108736 | GAPAS ES | GUINYANGAN | 4 | 1 | 3 | Repair of Classrooms | 2134776.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108762 | Panikihan Elementary school | GUMACA | 4 | 1 | 5 | Repair of Classrooms | 3609988.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108812 | Magallanes Elementary School | LOPEZ | 4 | 1 | 2 | Repair of Classrooms | 493289.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Quezon | 108813 | Pamampangin ES | LOPEZ | 4 | 1 | 2 | Repair of Classrooms | 1119102.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 109372 | Tatala ES | BINANGONAN | 1 | 1 | 2 | Repair of Classrooms | 994592.59 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 109318 | Tayuman ES | BINANGONAN | 1 | 1 | 5 | Repair of Classrooms | 1663582.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 165506 | Cresdaville Elementary School | TAYTAY | 1 | 1 | 2 | Repair of Classrooms | 495604.18 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 301429 | Baras NHS | BARAS | 2 | 1 | 18 | Repair of Classrooms | 9359836.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 109461 | Amityville ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | Repair of Classrooms | 466449.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 109499 | Balimbing ES | TANAY | 2 | 1 | 4 | Repair of Classrooms | 1360728.49 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Rizal | 109524 | Tablon ES | TANAY | 2 | 1 | 3 | Repair of Classrooms | 1081677.35 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | San Pablo City | 109782 | Major Juan Eseo Elementary School to Fernando A. Quisumbing ES | SAN PABLO CITY | 3 | 1 | 8 | Repair of Classrooms Covered Court & Pathways | 5025125.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | San Pablo City | 109800 | San Joaquin Elementary School | SAN PABLO CITY | 3 | 1 | 5 | Repair of Classrooms Covered Court & Pathways | 3015075.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | SAN PABLO CITY | 3 | 1 | 11 | Repair of Classrooms | 4495601.76 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 | 1 | 3 | Repair of Classrooms | 1067606.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 |  | 6 | Repair of Classrooms | 2135212.19 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4255980.96 | 1 | 628546.8 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-002 | R4A-STA.ROSA-2019-01 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301239 | Don Jose National High School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4185000.94 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108478 | Malitlit Elementary School | CITY OF SANTA ROSA | 1 | 1 | 4 | Repair of Classrooms | 1702001.76 | 1 | 1156018.52 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-004 | R4A-STA.ROSA-2019-04 | 11/27/2018 | 2018-03-12 | 12/14/2018 | 2018-12-19 | 2019-08-30 | GS MOTAR BUILDERS CONSTRUCTION & TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301260 | Pulong Sta. Cruz NHS | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4072781.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108481 | Santa Rosa Elementary School Central II | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4342980.16 | 1 | 628546.8 | COMPLETED | 100% | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301272 | Sto. Domingo National High School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 2999999.56 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tanauan City | 107747 | Bagbag ES | CITY OF TANAUAN | 3 | 1 | 12 | Repair of Classrooms | 5283395.07 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tanauan City | 107752 | Banjo Laurel ES | CITY OF TANAUAN | 3 | 1 | 5 | Repair of Classrooms | 2822777.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tanauan City | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 5546991.93 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tanauan City | 107770 | Pagaspas ES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 5979808.48 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tanauan City | 107782 | Tanauan South Central School | CITY OF TANAUAN | 3 | 1 | 1 | Repair of Classroom | 1811750.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tayabas City | 109252 | Gibanga ES | CITY OF TAYABAS | 1 | 1 | 3 | Repair of Classrooms | 502214.46 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-A | Tayabas City | 109233 | EAST PALALE ES | TAYABAS | 1 | 1 | 7 | Repair of Classrooms | 2997134.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111551 | Balingayan Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2474624.27 | 1 | 2444928.78 | COMPLETED | 100% | 2022-02-17 | 2022-02-03 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111554 | Bayanan II Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classroom | 2877595.37 | 1 | 2843064.23 | COMPLETED | 100% | 2022-02-17 | 2022-02-03 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111538 | Ibaba Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 3439014.07 | 1 | 3397745.9 | COMPLETED | 100% | 2022-02-17 | 2022-02-03 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION & DEVELOPER | CLUSTER 2 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111541 | Maidlang Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3640206.39 | 1 | 3626200 | COMPLETED | 100% | 2022-01-18 | 2022-01-18 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 3 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 33 | Repair of Classrooms | 13728793.6 | 1 | 13600795.33 | COMPLETED | 100% | 2022-08-22 | 2022-08-23 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111544 | Parang Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3019943.63 | 1 | 3003900 | COMPLETED | 100% | 2022-01-18 | 2022-01-18 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 3 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Calapan City | 111580 | Teresa C. Montellano Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | Repair of Classrooms | 2359103.61 | 1 | 2328069.67 | COMPLETED | 100% | 2022-08-22 | 2021-12-01 | N/A |  | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 109889 | Bantay ES | BOAC (Capital) | 0 | 1 | 1 | Repair of Classroom | 623119.83 | 1 | 618201.17 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 109925 | Banot-Mahunig ES | GASAN | 0 | 1 | 5 | Repair of Classrooms | 2246556.4 | 1 | 2198750.75 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 308804 | Paciano A. Sena Mem. HS (Tabionan NHS) | GASAN | 0 | 1 | 6 | Repair of Classrooms | 1178249.53 | 1 | 1152608.32 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 301567 | Tiguion National High School | GASAN | 0 | 1 | 3 | Repair of Classrooms | 1608932.66 | 1 | 1400998.39 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-015 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 301530 | Balanacan NHS | MOGPOG | 0 | 1 | 10 | Repair of Classrooms | 3044390.9 | 1 | 2949869.21 | COMPLETED | 100% | 2021-12-28 |  | N/A | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 109941 | Bocboc ES | MOGPOG | 0 | 1 | 4 | Repair of Classrooms | 1776895.7 | 1 | 1753309.11 | COMPLETED | 100% | 2021-12-28 |  | N/A | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG | 0 | 1 | 4 | Repair of Classrooms | 1883818.07 | 1 | 1858671.03 | COMPLETED | 100% | 2021-12-28 |  | N/A | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 308803 | Puting Buhangin NHS | MOGPOG | 0 | 1 | 1 | Repair of Classroom | 682937.11 | 1 | 677356.29 | COMPLETED | 100% | 2021-12-28 |  | N/A | 2021-09-016 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-23 | 2021-10-13 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 110006 | Mongpong Elementary School | SANTA CRUZ | 0 | 1 | 4 | Repair of Classrooms | 1969331.88 | 1 | 1926298.51 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 301551 | Malibago National High School | TORRIJOS | 0 | 1 | 2 | Repair of Classrooms | 998885.26 | 1 | 998885.26 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Marinduque | 110032 | Sibuyao ES | TORRIJOS | 0 | 1 | 1 | Repair of Classroom | 672976.6 | 1 | 663668.29 | COMPLETED | 100% | 2022-01-18 |  | N/A | 2021-09-013 | 2021-07-10 | 2021-07-19 | 2021-08-02 | 2021-09-06 | 2021-09-23 | GS MOTAR COSTRUCTION BUILDERS AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110056 | Lumangbayan ES (Abra) | ABRA DE ILOG | 0 | 1 | 4 | Repair of Classrooms | 1977857 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110070 | San Vicente ES | ABRA DE ILOG | 0 | 1 | 6 | Repair of Classrooms | 2928582.16 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 301574 | CALINTAAN NATIONAL HIGH SCHOOL | CALINTAAN | 0 | 1 | 10 | Repair of Classrooms | 4849583.8 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 301590 | Magsaysay NHS - Purnaga Annex | MAGSAYSAY | 0 | 1 | 12 | Repair of Classrooms | 5805954.86 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110169 | Mamburao CS | MAMBURAO (Capital) | 0 | 1 | 7 | Repair of Classrooms | 3417380.11 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110301 | Mabini I ES | SAN JOSE | 0 | 1 | 4 | Repair of Classrooms | 1985850.92 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110272 | San Isidro ES | SAN JOSE | 0 | 1 | 8 | Repair of Classrooms | 3895006.17 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110162 | Cuarenta ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 2940428.55 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Occidental Mindoro | 110171 | Mulawin ES | SANTA CRUZ | 0 | 1 | 5 | Repair of Classrooms | 2453219.58 | 1 |  | COMPLETED | 100% | 2021-11-10 | December 17.2021 | N/A |  | 2021-07-07 | 2021-07-15 | july 28.2021 | 2021-08-04 | 2021-08-10 | hawkstow construction and development | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Oriental Mindoro | 110325 | Burbuli ES | BACO | 1 | 1 | 4 | Repair of Classrooms | 1556187.91 | 1 | 1541042.35 | COMPLETED | 100% | 2021-11-02 | 2021-10-26 | REPAIR 2021-R IVB-Oriental Mindoro-003 | 004-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | ETVR Trading and Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Oriental Mindoro | 110328 | Dulangan II ES | BACO | 1 | 1 | 15 | Repair of Classroom | 5627150.71 | 1 | 5581256.7 | COMPLETED | 100% | 2021-12-30 | 2021-12-13 | REPAIR 2021-R IVB-Oriental Mindoro-008 | 006-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | CMSEL Constuction and Developer | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Oriental Mindoro | 110517 | Mabini ES | NAUJAN | 1 | 1 | 5 | Repair of Classrooms | 1846256.38 | 1 | 1833888 | COMPLETED | 100% | 2022-03-29 | 2022-03-11 | REPAIR 2021-R IVB-Oriental Mindoro-005 | 005-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-12-06 | 2021-12-22 | DK Construction | For termination | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Oriental Mindoro | 110665 | Batong Dalig ES | SOCORRO | 1 | 1 | 6 | Repair of Classrooms | 2257389.82 | 1 | 2198888.88 | COMPLETED | 100% | 2021-12-12 | 2021-11-14 | REPAIR 2021-R IVB-Oriental Mindoro-006 | 016-2021 | 2021-07-06 | 2021-07-14 | 2021-07-27 | 2021-08-11 | Sept. 03, 2021 | GDB Masterbuilders Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Oriental Mindoro | 110688 | Antonino ES | VICTORIA | 1 | 1 | 7 | Repair of Classrooms | 2291994.35 | 1 | 2273301.57 | COMPLETED | 100% | 2021-10-30 | 2021-10-26 | REPAIR 2021-R IVB-Oriental Mindoro-001 | 003-2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-06 | 2021-07-22 | DK Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Palawan | 301720 | Panlaitan National High School | BUSUANGA | 1 | 1 | 4 | Repair of Classrooms | 2859559.56 | 1 | 2076383.88 | COMPLETED | 100% | 2022-02-01 | 2022-02-02 | 2021-08-001 | 2021-08-001 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Palawan | 111190 | IRAWAN ELEMENTARY SCHOOL | SAN VICENTE | 1 | 1 | 4 | Repair of Classrooms | 2861892.98 | 1 | 2027037.8 | COMPLETED | 100% | 2022-02-01 | 2022-01-31 | 2021-09-002 | 2021-09-002 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Palawan | 111123 | Salongsong Elementary School | RIZAL (MARCOS) | 2 | 1 | 4 | Repair of Classrooms | 2747499.38 | 1 | 2018792.85 | COMPLETED | 100% | 2022-02-01 | 2022-01-25 | 2021-09-003 | 2021-09-003 | 2021-07-13 | 2021-07-21 | 2021-08-02 | 2021-09-17 | 2021-09-27 | Maryknol Builders and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Puerto Princesa City | 301791 | Pto. Princesa City Nat. Sci. HS | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 6 | Repair of Classrooms | 3192370.19 | 1 | 2155813.35 | COMPLETED | 100% | 2021-12-15 | 2021-11-09 | N/A | Infra 2021-02 | 2021-06-03 | 2021-06-22 | 2021-07-05 | August 5, 2021 | 2021-08-09 | Ian Jason Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Puerto Princesa City | 111494 | Sta. Lourdes Elementary School | PUERTO PRINCESA CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1098015.32 | 1 | 877783.49 | COMPLETED | 100% | 2021-12-15 | 2021-11-09 | N/A | Infra 2021-02 | 2021-06-03 | 2021-06-22 | 2021-07-05 | August 5, 2021 | 2021-08-09 | Ian Jason Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IV-B | Romblon | 111353 | Hinag-oman ES | FERROL | 0 | 1 | 14 | Repair of Classrooms | 6181753.01 | 1 | 5431177.85 | COMPLETED | 100% | 2022-03-21 | 2022-06-15 | N/A | INF-SBR-2021-01 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region IV-B | Romblon | 111345 | Tumingad ES | ODIONGAN | 0 | 1 | 12 | Repair of Classrooms | 5533793.95 | 1 | 4299005.83 | COMPLETED | 100% | 2022-03-26 | 2022-04-16 | N/A | INF-SBR-2021-02 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region IV-B | Romblon | 301749 | Esteban Madrona National High School | SAN AGUSTIN | 0 | 1 | 19 | Repair of Classrooms | 5106874 | 1 | 4582963.83 | COMPLETED | 100% | 2022-10-31 |  | N/A | INF-SBR-2021-03 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-11-09 | 2021-12-14 | RG FLORENTINO CONSTRUCTION AND TRADING INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region IX | Dapitan City | 125945 | Aseniero ES | DAPITAN CITY | 1 | 1 | 8 | Repair of Classrooms | 3961640.58 | 1 | 3880225.64 | COMPLETED | 100% | 2022-01-22 | 2022-01-25 | 2021-01 | 2021-01 | 2021-06-12 | 2021-06-21 | 2021-07-05 | 2021-08-04 | 2021-08-25 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Dapitan City | 125918 | Maria Uray ES | DAPITAN CITY | 1 | 1 | 7 | Repair of Classrooms | 3455539.32 | 1 | 3441508.43 | COMPLETED | 100% | 2022-01-22 | 2021-12-27 | 2021-02 | 2021-02 | 2021-06-12 | 2021-06-21 | 2021-07-05 | 2021-08-04 | 2021-08-25 | MORTE CONSTRUCTION | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Dipolog City | 125988 | Guinsangaan ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 2993905.08 | 1 | 2543898.23 | COMPLETED | 100% | 2022-01-11 | 2022-01-17 | Repair and Rehabilitation of 4-CL School Building in Guinsangaan ES | DepED-Repair-21-IX-Dip-GES |  | 2021-07-30 | 2021-08-09 | Auguts 23, 2021 | 2021-09-13 | NGP Construction | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Isabela City | 126029 | Calvario Es | CITY OF ISABELA (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1391945.67 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Isabela City | 126007 | Calvario Peak ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1584545.91 | 1 |  | COMPLETED | 100% | [10 empty] | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Pagadian City | 126058 | Alegria ES | PAGADIAN CITY (Capital) | 1 | 1 | 5 | Repair of Classrooms | 3637816.48 | 1 | 3287314.07 | COMPLETED | 100% | 2022-01-22 | 2022-01-21 | PAG-21-RR-2 | PAG-21-RR-2 | 2021-06-04 | 2021-06-11 | 2021-06-24 | 2021-08-26 | 2021-09-10 | JZ MAGO CONST. & ENTERPRISES | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Pagadian City | 126038 | Bulawan Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 4101827.24 | 1 | 4450466.88 | COMPLETED | 100% | 2022-01-21 | 2022-01-21 | PAG-21-RR-1 | PAG-21-RR-1 | 2021-06-04 | 2021-06-11 | 2021-06-24 | 2021-07-26 | 2021-08-23 | JZ MAGO CONST. & ENTERPRISES | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga City | 126111 | Malagutay ES | ZAMBOANGA CITY | 1 | 1 | 5 | Repair of Classrooms | 2382246 | 1 | 2074307.48 | COMPLETED | 100% | December 6,2021 | December 16,2021 | ZC-REPAIR-2021-LOT-1 | ZC-REPAIR-2021-LOT-1 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | PM CONSTRUCTION AND TRADING | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga City | 126144 | Mt. View ES | ZAMBOANGA CITY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2375613.29 | COMPLETED | 100% | December 6,2021 | December 4,2021 | ZC-REPAIR-2021-LOT-2 | ZC-REPAIR-2021-LOT-2 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | JM2K CONSTRUCTION | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga City | 126115 | Bagacay ES | ZAMBOANGA CITY | 2 | 1 | 5 | Repair of Classrooms | 2218170.5 | 1 | 2113666 | COMPLETED | 100% | December 6,2021 | January 5,2022 | ZC-REPAIR-2021-LOT-3 | ZC-REPAIR-2021-LOT-3 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | ZAMBOPEN CONSTRUCTION | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga City | 126171 | Sapa Seco ES | ZAMBOANGA CITY | 2 | 1 | 9 | Repair of Classrooms | 3700000 | 1 | 3694930.02 | COMPLETED | 100% | December 6,2021 | January 26,2022 | ZC-REPAIR-2021-LOT-4 | ZC-REPAIR-2021-LOT-4 | June 18,2021 | July 2,2021 | July 16,2021 | July 30, 2021 | August 6,2021 | LONG ISLAND BUILDERS AND CONST. | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124564 | Silano ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 3 | Repair of Classrooms | 1929641.73 | 1 | 1921060.67 | COMPLETED | 100% | 2021-11-12 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 12, 2021 | STARS & STRIPES CONST | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124583 | Villahermosa ES | POLANCO | 1 | 1 | 4 | Repair of Classrooms | 2581516.35 | 1 | 2565006 | COMPLETED | 100% | 2021-11-12 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 12, 2021 | STARS & STRIPES CONST | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124608 | New Dapitan PS | RIZAL | 1 | 1 | 3 | Repair of Classrooms | 1932791.73 | 1 | 1929840.95 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124337 | Siparok ES | JOSE DALMAN (PONOT) | 2 | 1 | 5 | Repair of Classrooms | 3170127.77 | 1 | 3165367.93 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124377 | New Tambo ES | KATIPUNAN | 2 | 1 | 4 | Repair of Classrooms | 2521371.67 | 1 | 2517486.3 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124497 | Gov. Jose Aseniero ES | PRES. MANUEL A. ROXAS | 2 | 1 | 5 | Repair of Classrooms | 3137582.45 | 1 | 3132056.76 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124757 | Binuangan ES | SINDANGAN | 2 | 1 | 3 | Repair of Classrooms | 1945391.73 | 1 | 1942595.3 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124347 | Fatima ES | KALAWIT | 3 | 1 | 5 | Repair of Classrooms | 3245500.71 | 1 | 3240239.26 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Norte | 124468 | Lamao ES | LILOY | 3 | 1 | 4 | Repair of Classrooms | 2611149.17 | 1 | 2607123.85 | COMPLETED | 100% | 2021-11-06 |  |  |  |  | 2021-05-31 | 2021-06-11 | 2021-06-15 | July 6, 2021 | YSL BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 125080 | Josefina CES | JOSEFINA | 1 | 1 | 8 | Repair of Classrooms | 4373000 | 1 | 4146201.87 | COMPLETED | 100% | 2021-11-26 | 2021-11-25 | ZDS-21-RR-01 | ZDS-21-RR-01 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 125123 | San Isidro ES | LABANGAN | 1 | 1 | 1 | Repair of Classroom | 475000 | 1 | 450007.52 | COMPLETED | 100% | 2021-11-26 | 2021-11-24 | ZDS-21-RR-02 | ZDS-21-RR-02 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 125205 | San Isidro Central & SPED School (Special Science Education Program) | MAHAYAG | 1 | 1 | 6 | Repair of Classrooms | 2693000 | 1 | 2557383.82 | COMPLETED | 100% | 2021-11-26 | 2021-11-24 | ZDS-21-RR-02 | ZDS-21-RR-02 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 124935 | Bacayawan ES | DIMATALING | 2 | 1 | 3 | Repair of Classrooms | 1657000 | 1 | 1611890.1984 | COMPLETED | 100% | 2021-11-26 | 2021-11-24 | ZDS-21-RR-04 | ZDS-21-RR-04 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 124949 | Saloagan ES | DIMATALING | 2 | 1 | 3 | Repair of Classrooms | 1420000 | 1 | 1419614.9359 | COMPLETED | 100% | 2021-11-26 | 2021-11-24 | ZDS-21-RR-04 | ZDS-21-RR-04 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 314205 | Ignacio Garrata NHS | DINAS | 2 | 1 | 1 | Repair of Classroom | 552000 | 1 | 550906.44 | COMPLETED | 100% | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 124980 | Sambulawan ES | DINAS | 2 | 1 | 2 | Repair of Classrooms | 1098000 | 1 | 1063409.03 | COMPLETED | 100% | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga del Sur | 314238 | Tina NHS | DUMALINAO | 2 | 1 | 2 | Repair of Classrooms | 1062000 | 1 | 1058354.55 | COMPLETED | 100% | 2021-11-26 | 2021-11-23 | ZDS-21-RR-03 | ZDS-21-RR-03 | 2021-05-24 | 2021-06-03 | 2021-07-02 | 2021-07-05 | 2021-07-22 | CPIN BUILDERS | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125573 | Lobing Paaralan ng Buhay PS | Diplahan | 1 | 1 | 2 | Repair of Classrooms | 1137855.16 | 1 | 1137855.16 | COMPLETED | 100% | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125603 | Lumpanac ES | Imelda | 1 | 1 | 1 | Repair of Classroom | 629442.31 | 1 | 629442.31 | COMPLETED | 100% | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga Sibugay | 314301 | Dalama NHS | Payao | 1 | 1 | 2 | Repair of Classroom | 1277945.79 | 1 | 1277945.79 | COMPLETED | 100% | 2021-11-27 |  | ZSY-2021R-01 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Diplahan Commercial | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga Sibugay | 125787 | Habib Ibrahim Mem.ES | R.T. Lim | 2 | 1 | 4 | Repair of Classrooms | 2163800.31 | 1 | 2163800.31 | COMPLETED | 100% | 2021-11-27 | Nov. 27, 2021 | ZSY-2021R-02 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Stone Throw Construction and Enterprise | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region IX | Zamboanga Sibugay | 314318 | Salip T. Hasim NHS | Titay | 2 | 1 | 4 | Repair of Classrooms | 1585855.86 | 1 | 1585855.86 | COMPLETED | 100% | 2021-11-27 | Nov. 27, 2021 | ZSY-2021R-02 |  | April 31, 2021 | June 08, 2021 | June 21, 2021 | July 07, 2021 | July 22, 2021 | Stone Throw Construction and Enterprise | None | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111592 | Langaton Elementary School | BACACAY | 1 | 1 | 1 | Repair of Classroom | 416664.67 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111611 | Mapulang Daga Elementary School | BACACAY | 1 | 1 | 6 | Repair of Classrooms | 1859093.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111859 | Salvacion Elementary School | MALILIPOT | 1 | 1 | 14 | Repair of Classrooms | 4392296.95 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111869 | Bariw Elementary School | MALINAO | 1 | 1 | 7 | Repair of Classrooms | 2286837.43 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 301831 | Labnig National High School | MALINAO | 1 | 1 | 25 | Repair of Classrooms | 6842657.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111877 | Malinao Central School | MALINAO | 1 | 1 | 4 | Repair of Classrooms | 1506935.82 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 112054 | Fidel Surtida Elementary School | SANTO DOMINGO (LIBOG) | 1 | 1 | 3 | Repair of Classrooms | 634387.76 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1 | 1 | 15 | Repair of Classrooms | 3138408.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 112063 | Bariis Elementary School | TIWI | 1 | 1 | 5 | Repair of Classrooms | 1434930.14 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111702 | Tabontabon Elementary School | DARAGA (LOCSIN) | 2 | 1 | 12 | Repair of Classrooms | 5731232.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111890 | Buyo Elementary School | MANITO | 2 | 1 | 6 | Repair of Classrooms | 2049393.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111745 | Jovellar Central School | JOVELLAR | 3 | 1 | 29 | Repair of Classrooms | 11791022.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111762 | Libon East Central School | LIBON | 3 | 1 | 16 | Repair of Classrooms | 7192788.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111773 | Sampongan Elementary School | LIBON | 3 | 1 | 1 | Repair of Classrooms & Toilets | 982617.04 | 1 |  | COMPLETED | 100% | [10 empty] | School site is in far-flung area .Slow or no movement is due to difficulty in hauling construction materials. | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111960 | Macasitas Elementary School | PIO DURAN | 3 | 1 | 4 | Repair of Classrooms | 2107146.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 111968 | Panganiran Elementary School | PIO DURAN | 3 | 1 | 6 | Repair of Classrooms | 3210804.85 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Albay | 112003 | Cotnogan Elementary School | POLANGUI | 3 | 1 | 5 | Repair of Classrooms | 2458453.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112109 | Camacho Aler ES | CAPALONGA | 1 | 1 | 3 | Repair of classrooms | 1842011.13 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112115 | Esturas-Nabata ES | CAPALONGA | 1 | 1 | 5 | Repair of classrooms | 3478344.3 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112122 | Peter Sawmill ES | CAPALONGA | 1 | 1 | 6 | Repair of classrooms | 3648819.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112125 | San Roque ES | CAPALONGA | 1 | 1 | 5 | Repair of classrooms | 3655891.48 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112198 | G. Zabala-B. Placido ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1859948.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112218 | Malibago ES | LABO | 1 | 1 | 3 | Repair of classrooms | 1875698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112279 | Bulala ES | SANTA ELENA | 1 | 1 | 6 | Repair of classrooms | 3799856 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 173011 | Maulawin ES | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 2077497.4 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 301913 | Rizal NHS-Annex | SANTA ELENA | 1 | 1 | 5 | Repair of classrooms | 1943210.9 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 500634 | Sta. Elena IS | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 1854698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 173012 | Tabugon ES | SANTA ELENA | 1 | 1 | 3 | Repair of classrooms | 1982435.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112085 | Brinas ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112087 | Don Juan Pimentel ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112091 | Langa ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1833698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112094 | Mangcamagong ES | BASUD | 2 | 1 | 3 | Repair of classrooms | 1854698.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112141 | Calasgasan ES | DAET | 2 | 1 | 6 | Repair of classrooms | 3812860.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112226 | Hamoraon ES | MERCEDES | 2 | 1 | 5 | Repair of classrooms | 3363700.46 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112240 | Tarum ES | MERCEDES | 2 | 1 | 4 | Repair of classrooms | 2827875.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112307 | Juanita Balon ES | VINZONS | 2 | 1 | 3 | Repair of classrooms | 2059594.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Norte | 112315 | Trino P. Zenarosa ES | VINZONS | 2 | 1 | 5 | Repair of classrooms | 3467856.8 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112576 | Cabasag Elementary School | DEL GALLEGO | 1 | 1 | 2 | Repair of classrooms | 1138745.11 | 1 | 1082212.58 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112582 | Pasay ES | DEL GALLEGO | 1 | 1 | 5 | Repair of classrooms | 2983889.01 | 1 | 2835755.08 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112588 | Tabion Munti ES | DEL GALLEGO | 1 | 1 | 4 | Repair of classrooms | 2210619.62 | 1 | 2100874.33 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112741 | Cristo Rey ES | LUPI | 1 | 1 | 3 | Repair of classrooms | 1724019.79 | 1 | 1638431.54 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-026 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 301968 | Don Mariano C. Veneracion NHS | PAMPLONA | 2 | 1 | 14 | Repair of classrooms | 6501971.64 | 1 | 6194804.38 | COMPLETED | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-027 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112996 | BICAL ELEMENTARY SCHOOL | SAN FERNANDO | 2 | 1 | 8 | Repair of classrooms | 4728231.14 | 1 | 4505460.97 | COMPLETED | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-027 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 301953 | Quipayo National High School | CALABANGA | 3 | 1 | 33 | Repair of Classrooms | 5626843.69 | 1 | 5601003.79 | COMPLETED | 100% | 3/25/2022 | 2022-12-03 |  | 2021-10-028 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | RD DAYAO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3 | 1 | 17 | Repair of Classrooms | 5840966.01 | 1 | 5761221.88 | COMPLETED | 100% | 3/25/2022 | 2022-05-10 |  | 2021-10-028 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | RD DAYAO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112932 | Pili Central School | PILI (Capital) | 3 | 1 | 23 | Repair of Classrooms | 11082687.77 | 1 | 10754162.29 | COMPLETED | 100% | 3/25/2022 | 2022-05-10 |  | 2021-10-029 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | EA AC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112534 | Caramoan CS | CARAMOAN | 4 | 1 | 7 | Repair of classrooms | 5045606.91 | 1 | 3885107.07 | COMPLETED | 100% | 3/17/2022 | 2022-05-10 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112600 | Garchitorena Central School | GARCHITORENA | 4 | 1 | 9 | Repair of classrooms | 6289238 | 1 | 6283024.12 | COMPLETED | 100% | 3/21/2022 | 2022-05-06 |  | 2021-10-030 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112882 | Bagong Sirang ES | PRESENTACION (PARUBCAN) | 4 | 1 | 5 | Repair of classrooms | 3313631.24 | 1 | 2776444.75 | COMPLETED | 100% | 3/17/2022 | 2022-05-10 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 113024 | Obias (Pugay) ES | SAN JOSE | 4 | 1 | 11 | Repair of classrooms | 5426381.93 | 1 | 4362593.59 | COMPLETED | 100% | 3/17/2022 | 2022-03-25 |  | 2021-10-031 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/17/2021 | 2 BROTHERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 113104 | Salvacion ES | TIGAON | 4 | 1 | 8 | Repair of classrooms | 5739569.29 | 1 | 5735517.55 | COMPLETED | 100% | 3/21/2022 | 2/25/2022 |  | 2021-10-030 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | 12 | Repair of Classrooms & 1 Ext. Office | 6201087.3 | 1 | 6193300 | COMPLETED | 100% | 3/19/2022 | 2022-12-03 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112319 | Baao Central School | BAAO | 5 | 1 | 20 | Repair of Classrooms | 10484131.24 | 1 | 10471270.65 | COMPLETED | 100% | 3/24/2022 | 3/28/2022 |  | 2021-10-032 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | BOTEY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112351 | Duran ES | BALATAN | 5 | 1 | 19 | Repair of Classrooms | 8163121.09 | 1 | 8155759.49 | COMPLETED | 100% | 3/29/2022 | 2/25/2022 |  | 2021-10-033 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112377 | Nino Jesus ES | BATO | 5 | 1 | 4 | Repair of Classrooms | 1853498.7 | 1 | 1850473.51 | COMPLETED | 100% | 3/29/2022 | 2/25/2022 |  | 2021-10-033 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 500869 | Sto. Nino Integrated School (ES) | BULA | 5 | 1 | 8 | Repair of Classrooms | 5106314 | 1 | 4335550 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112832 | Dolorosa ES | NABUA | 5 | 1 | 4 | Repair of Classrooms | 2453290 | 1 | 2392382.49 | COMPLETED | 100% | 3/25/2022 | 2/25/2022 |  | 2021-10-035 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | GMO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 | 1 | 5 | Repair of Classrooms & 1 Ext. Office | 2907137.62 | 1 | 2903036.4 | COMPLETED | 100% | 3/25/2022 | 2/25/2022 |  | 2021-10-035 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/25/2021 | GMO | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Camarines Sur | 112823 | Paloyon Oriental ES | NABUA | 5 | 1 | 7 | Repair of Classrooms | 4347199.71 | 1 | 4335550 | COMPLETED | 100% | 3/19/2022 | 2/25/2022 |  | 2021-10-2021 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113174 | Caragumihan ES | BARAS | 0 | 1 | 3 | Repair of classrooms | 1647659.71 | 1 | 1631142.19 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113170 | Puraran Elementary School | BARAS | 0 | 1 | 3 | Repair of classrooms | 2062944.49 | 1 | 2042276.29 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113179 | Salvacion ES | BARAS | 0 | 1 | 3 | Repair of classrooms | 2202449.89 | 1 | 2180377.1 | COMPLETED | 100% | 2022-04-22 |  |  |  | November 6, 2018 | November 13, 2018 | Nov. 26 -29, 2018 | April 3, 2019 | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 0 | 1 | 30 | Repair of classrooms | 16554217.62 | 1 | 16388615.76 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113194 | Sibacungan ES | BATO | 0 | 1 | 9 | Repair of classrooms | 5320459.13 | 1 | 5304497.75 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | 0 | 1 | 25 | Repair of classrooms | 9813743.54 | 1 | 9715584.05 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 500033 | Sicmil Integrated School | GIGMOTO | 0 | 1 | 5 | Repair of classrooms | 1402770.83 | 1 | 1388659.72 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113223 | Sioron ES | GIGMOTO | 0 | 1 | 10 | Repair of classrooms | 6111612.74 | 1 | 6050490.96 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113272 | Cabcab CES | SAN ANDRES (CALOLBON) | 0 | 1 | 28 | Repair of classrooms | 10321056.81 | 1 | 10318329.02 | COMPLETED | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Virac NRC Construction | bid valuation | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 500160 | Lictin IS | SAN ANDRES (CALOLBON) | 0 | 1 | 29 | Repair of classrooms | 11144886.66 | 1 | 10954879.63 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113290 | Mabato CES | SAN MIGUEL | 0 | 1 | 14 | Repair of classrooms | 7849938.34 | 1 | 7762166.3 | COMPLETED | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Virac NRC Construction | bid valuation | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 174007 | Pangilao ES | SAN MIGUEL | 0 | 1 | 3 | Repair of classrooms | 1992852.49 | 1 | 1960272.09 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113359 | Cavinitan ES | VIRAC (Capital) | 0 | 1 | 13 | Repair of classrooms | 6045212.55 | 1 | 6026827.06 | COMPLETED | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | 0 | 1 | 2 | Repair of classrooms | 1230729.78 | 1 | 1227154.54 | COMPLETED | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113349 | Sto. Domingo ES | VIRAC (Capital) | 0 | 1 | 9 | Repair of classrooms | 5426556.31 | 1 | 5410324.31 | COMPLETED | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Catanduanes | 113373 | Virac CES | VIRAC (Capital) | 0 | 1 | 29 | Repair of classrooms | 14905904.15 | 1 | 14861547.1 | COMPLETED | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 |  | 2021-08-06 | Lourbel Construction and Supply | bid valuation | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114449 | La Trinidad ES | IRIGA CITY | 5 | 1 | 8 | Repair of classrooms | 5606159.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114433 | Niño Jesus ES | IRIGA CITY | 5 | 1 | 1 | Repair of Classroom | 795079.58 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114422 | San Agustin ES | IRIGA CITY | 5 | 1 | 7 | Repair of classrooms | 5431280.07 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114424 | San Isidro ES | IRIGA CITY | 5 | 1 | 7 | Repair of classrooms | 5639456.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114438 | San Ramon ES | IRIGA CITY | 5 | 1 | 3 | Repair of classrooms | 3216846.91 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Iriga City | 114428 | Sta. Cruz Sur ES | IRIGA CITY | 5 | 1 | 3 | Repair of classrooms | 3063118.93 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Legazpi City | 114488 | Buyoan ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | Repair of classrooms | 1699111.23 | 1 | 1647560.51 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Legazpi City | 114460 | Homapon ES | LEGAZPI CITY (Capital) | 2 | 1 | 5 | Repair of classrooms | 2925315.74 | 1 | 2837168.77 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Legazpi City | 114461 | Imalnod ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | Repair of classrooms | 2863464.4 | 1 | 2776820.9 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Ligao City | 111843 | Ligao West CES (P) Dunao | CITY OF LIGAO | 3 | 1 | 32 | Repair of classrooms | 2738691.42 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Ligao City | 111851 | Tinampo ES | CITY OF LIGAO | 3 | 1 | 5 | Repair of classrooms | 2137426.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113771 | Morocborocan ES | MONREAL | 1 | 1 | 5 | Repair of classrooms | 3565020.8 | 1 | 3486715.49 | COMPLETED | 100% | 2022-03-13 |  | INFRA 2021-08-025 | 2021-062 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-13 | JOHNCB CONSTRUCTION & SUPPLIES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113939 | Tuburan ES | SAN PASCUAL | 1 | 1 | 2 | Repair of classrooms | 1535139.52 | 1 | 1495115.15 | COMPLETED | 100% | 2022-03-10 |  | INFRA 2021-08-026 | 2021-063 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-10 | RPN CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113399 | Bugui PS | AROROY | 2 | 1 | 3 | Repair of classrooms | 1854249.25 | 1 | 1805090.5 | COMPLETED | 100% | 2022-03-10 |  | INFRA 2021-08-027 | 2021-063 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-10 | RPN CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113652 | Mabato-bato ES | MANDAON | 2 | 1 | 6 | Repair of classrooms | 3765802.97 | 1 | 3730000.07 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-025 | 2021-048 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SQUARE N CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113507 | Cadulawan Elementary School | CATAINGAN | 3 | 1 | 4 | Repair of classrooms | 2577339.8 | 1 | 2571218.54 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-026 | 2021-049 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3 | 1 | 4 | Repair of classrooms | 2453675.42 | 1 | 2446192.53 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-036 | 2021-055 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113555 | Pin-as ES | CAWAYAN | 3 | 1 | 4 | Repair of classrooms | 2931978.81 | 1 | 2927114.09 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-039 | 2021-057 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113564 | Tubog ES | CAWAYAN | 3 | 1 | 2 | Repair of classrooms | 1371910.31 | 1 | 1368480.54 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-028 | 2021-050 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SIR HENRIK'S CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113615 | San Vicente ES | DIMASALANG | 3 | 1 | 1 | Repair of Classroom | 718335.9 | 1 | 717865.81 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-027 | 2021-049 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113625 | Libertad Primary School | ESPERANZA | 3 | 1 | 2 | Repair of classrooms | 1386613.31 | 1 | 1377662.966 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-031 | 2021-051 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | JOHNCB CONSTUCTION & SUPPLIES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113619 | Trangia-Mahusay ES | ESPERANZA | 3 | 1 | 4 | Repair of classrooms | 2858561.11 | 1 | 2842223.034 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-030 | 2021-051 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | JOHNCB CONSTUCTION & SUPPLIES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113798 | Apolinario Etang ES | PALANAS | 3 | 1 | 6 | Repair of classrooms | 3974465.26 | 1 | 3964529.09 | COMPLETED | 100% | 2022-02-21 |  | INFRA 2021-08-033 | 2021-053 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-23 | JIMWELL BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113789 | Biga-a Elem. School | PALANAS | 3 | 1 | 7 | Repair of classrooms | 4804236.42 | 1 | 4774456.1 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-032 | 2021-052 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | MARABE GEN. CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113780 | Malibas ES | PALANAS | 3 | 1 | 5 | Repair of classrooms | 3369788.83 | 1 | 3354319.46 | COMPLETED | 100% | 2022-03-06 |  | INFRA 2021-08-028 | 2021-060 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-12-06 | 2021-12-06 | RPN CONSTRUCTION SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113806 | Bunducan ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | Repair of classrooms | 4098985.95 | 1 | 4095642.7 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-034 | 2021-054 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | MME CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113812 | Lampuyang ES | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 3 | Repair of classrooms | 2025697.13 | 1 | 2017865.54 | COMPLETED | 100% | 2022-02-28 |  | INFRA 2021-08-035 | 2021-055 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-30 | RED DIAMOND CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113822 | Burabod ES | PLACER | 3 | 1 | 3 | Repair of classrooms | 2110703.13 | 1 | 2095600 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-037 | 2021-056 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113842 | Celera-Inocencio CS | PLACER | 3 | 1 | 4 | Repair of classrooms | 2664431.02 | 1 | 2657769.94 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-029 | 2021-050 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SIR HENRIK'S CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate | 113956 | Eugenio C. Clores Sr. ES | USON | 3 | 1 | 3 | Repair of classrooms | 2054951.35 | 1 | 2051733.57 | COMPLETED | 100% | 2022-02-24 |  | INFRA 2021-08-038 | 2021-056 | 2021-09-14 | 2021-09-22 | 2021-10-05 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate City | 113701 | N. De Los Santos Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 7 | Repair of classrooms | 2124106.61 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Masbate City | 113671 | Nicolas Danao ES | CITY OF MASBATE (Capital) | 2 | 1 | 6 | Repair of classrooms | 2050955.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 302266 | Carolina National High School | NAGA CITY | 3 | 1 | 6 | Repair of Classrooms | 3474232.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 114506 | Del Rosario Elementary School | NAGA CITY | 3 | 1 | 4 | Repair of Classrooms | 3063718.78 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 176502 | Grand View Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 1927041.59 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 114509 | Mac Mariano Elementary School | NAGA CITY | 3 | 1 | 5 | Repair of Classrooms | 2522665.69 | 1 | 1307633.45 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 176503 | Naga City SPED Center | NAGA CITY | 3 | 1 | 7 | Repair of Classrooms | 3310973.55 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 2566432.99 | 1 | 773478 | COMPLETED | 100% |  |  |  |  | 2018-11-07 | 2018-11-12 | 2018-11-27 | 2019-08-16 | 2019-09-12 | MRP MERCHANDISING | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 3 | Repair of Classrooms | 2029853.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Naga City | 114512 | Villa Corazon Elementary School | NAGA CITY | 3 | 1 | 11 | Repair of Classrooms | 5589846.56 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114150 | Rawis Elementary School | DONSOL | 1 | 1 | 2 | Repair of classrooms | 1016947.45 | 1 | 752447.44 | COMPLETED | 100% | 2021-11-04 | December 14, 2021 |  | 21-07-007-01 | July 14, 2021 | July 22, 2021 | August 3, 2021 | August 26, 2021 | 2021-09-06 | Alhadrax Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114338 | Banuyo ES | PILAR | 1 | 1 | 4 | Repair of classrooms | 1895945.38 | 1 | 1336895.1594 | COMPLETED | 100% | 2021-12-07 | December 7, 2021 |  | 21-07-007-02 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114356 | Pilar I Central School | PILAR | 1 | 1 | 4 | Repair of classrooms | 655461.49 | 1 | 450502.2506 | COMPLETED | 100% | 2021-12-07 | December 21, 2021 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 |  | Alhadrax Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114383 | Pilar II CS | PILAR | 1 | 1 | 5 | Repair of classrooms | 3502026.47 | 1 | 2267011.04 | COMPLETED | 100% | 2021-12-22 | November 19, 2021 |  | 21-07-007-03 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | Camsur Bicol Trading Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114017 | Lahong ES | BULAN | 2 | 1 | 5 | Repair of classrooms | 3754283.32 | 1 | 2530681.1665 | COMPLETED | 100% | 2021-12-22 | December 22, 2021 |  | 21-07-007-04 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114053 | Sigad Elementary School | BULAN | 2 | 1 | 1 | Repair of Classroom | 786814.36 | 1 | 503378.8135 | COMPLETED | 100% | 2021-12-22 | January 26, 2022 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | [15 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114265 | Mario G. Guarina ES | JUBAN | 2 | 1 | 2 | Repair of classrooms | 1680982.43 | 1 | 1107599.034 | COMPLETED | 100% | 2021-12-07 | December 2, 2021 |  | 21-07-007-05 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | NJNY Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114268 | Sangkayon ES | JUBAN | 2 | 1 | 2 | Repair of classrooms | 1205298.9 | 1 | 784569.626 | COMPLETED | 100% | 2021-12-07 | December 2, 2021 |  |  | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | [15 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon | 114410 | Manangkas ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of classrooms | 1543178.47 | 1 | 1178153.45 | COMPLETED | 100% | November 7, 2021 Revised to November 19, 2021 | November 19, 2021 |  | 21-07-007-06 | July 14, 2021 | July 22, 2021 | August 4, 2021 | August 26, 2021 | 2021-09-09 | Araphil Construction and Development Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 114534 | Bacon West Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 850247.3 | 1 | 821298.56 | COMPLETED | 100% | February 14, 2022 |  |  | 21-10-001-01 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 114536 | Del Rosario Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1778811.38 | 1 | 1728769.6 | COMPLETED | 100% | 2022-09-30 |  |  | 21-10-001-02 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Araphil Const & Dev. Corp | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 114538 | Gayong Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1353567.57 | 1 | 1302877.15 | COMPLETED | 100% | March 3, 2022 Revised to March 23, 2022 |  |  | 21-11-002 | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Araphil Const & Dev. Corp | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 114575 | Pangpang Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 22 | Repair of Classrooms | 7653614.43 | 1 | 4974858.82 | COMPLETED | 100% |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Alhadrax Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1002552.14 | 1 | 977105.91 | COMPLETED | 100% |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 500466 | Rizal Integrated National School (HS) | CITY OF SORSOGON (Capital) | 1 | 1 | 15 | Repair of Classrooms | 6321935.3 | 1 | 4109729.12 | COMPLETED | 100% |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | NJNY Construction & Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Sorsogon City | 114551 | Tiris Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | Repair of Classrooms | 933138.94 | 1 | 882436.69 | COMPLETED | 100% |  |  |  |  | September 6-27, 2021 | September 2, 2021 | September 27, 2021 | September 30, 2021 | October 4, 2021 | Kobe Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Tabaco City | 114608 | Basud ES | CITY OF TABACO | 1 | 1 | 9 | Repair of classrooms | 6828271.58 | 1 |  | COMPLETED | 100% | 2022-10-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Tabaco City | 114617 | Malictay ES | CITY OF TABACO | 1 | 1 | 15 | Repair of classrooms | 10749457.85 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region V | Tabaco City | 114620 | San Lorenzo ES | CITY OF TABACO | 1 | 1 | 24 | Repair of classrooms | 10877451.49 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Aklan | 178009 | Taba-ao Primary School | BANGA | 1 | 1 | 1 | Repair of Classroom | 406986.56 | 1 | 275895.72 | COMPLETED | 100% | 2022-01-07 | 2019-12-02 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-22 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114689 | Lalab Elementary School | BATAN | 1 | 1 | 6 | Repair of Classrooms | 2858987.64 | 1 | 2166767.77 | COMPLETED | 100% | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114790 | Marapayao PS | LIBACAO | 1 | 1 | 1 | Repair of Classroom | 772571.99 | 1 | 593232.23 | COMPLETED | 100% | 2021-12-17 | 2021-10-08 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-02-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114817 | Mamba ES | MADALAG | 1 | 1 | 3 | Repair of Classroom | 1674615.23 | 1 | 1269807.42 | COMPLETED | 100% | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114903 | Jalas ES | NEW WASHINGTON | 1 | 1 | 7 | Repair of Classrooms | 3323793.38 | 1 | 2334655.01 | COMPLETED | 100% | 2022-01-07 |  | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | completed | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114844 | Tugas-Dumga ES | MAKATO | 2 | 1 | 4 | Repair of Classrooms | 2167538.09 | 1 | 1557587.79 | COMPLETED | 100% | 2022-01-22 |  | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | completed | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114886 | Matabana ES | NABAS | 2 | 1 | 4 | Repair of Classrooms | 1988334.71 | 1 | 1513192.58 | COMPLETED | 100% | 2021-12-17 | 2021-12-03 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | DepED-RO6-D1-2021BEFF-REPAIR-014-017-03-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Aklan | 114937 | Tondog Elementary School | TANGALAN | 2 | 1 | 6 | Repair of Classrooms | 1581722.29 | 1 | 993077.27 | COMPLETED | 100% | 2022-01-22 |  | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | DepED-RO6-D1-2021BEFF-REPAIR-017-2021 | 2021-05-31 | 2021-06-10 | 2021-06-21 | 2021-07-22 | 2021-09-02 | LEGACY CONSTRUCTION CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 114940 | Bayo-Crispin V. Unica MS | ANINI-Y | 0 | 1 | 4 | Repair of Classrooms | 1653433.37 | 1 |  | COMPLETED | 100% | 2022-09-30 | [9 empty] | Roof and Roof Framing already Installed. Ceiling installed Painting and Electricakl Works partially completed. Remaining Works installed Painting, Blackboard, Hand Washing Facilities completion | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 114998 | Talisay Elementary School | BUGASONG | 0 | 1 | 13 | Repair of Classrooms | 6081093.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Antique | 115122 | Santiago ES | LAUA-AN | 0 | 1 | 11 | Repair of Classrooms | 4395339.39 | 1 |  | COMPLETED | 100% | [10 empty] | All completed except for 1 buidling which previously occupied by the teachers. Remaining works to 1 builing included Ramp, Flood Marker, Roofing and Painting Wqorks | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 115165 | San Joaquin ES | PANDAN | 0 | 1 | 5 | Repair of Classrooms | 2495960.52 | 1 |  | COMPLETED | 100% | [10 empty] | All completed except for 1 buidling. Remaining works to 1 builing included Ramp, Flood Marker, Roofing and Painting Wqorks | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 115234 | Aningalan ES | SAN REMIGIO | 0 | 1 | 17 | Repair of Classrooms | 3640593.42 | 1 |  | COMPLETED | 100% | [10 empty] | Nearing Completion. Remaining works includes Ceiling Works and Painting Works | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 115246 | Maragubdub ES | SAN REMIGIO | 0 | 1 | 9 | Repair of Classrooms | 4666788.52 | 1 |  | COMPLETED | 100% | 2022-09-30 | [9 empty] | Nearing Completion. Remaining works includes Ceiling Works and Painting Works | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Antique | 115326 | Mabini Elementary School | SIBALOM | 0 | 1 | 5 | Repair of Classrooms | 2643875.67 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Antique | 302352 | Concepcion L. Cazeñas MS | TOBIAS FORNIER (DAO) | 0 | 1 | 6 | Repair of Classrooms | 2977199.24 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Antique | 115378 | Manaling PS | TOBIAS FORNIER (DAO) | 0 | 1 | 1 | Repair of Classroom | 702351.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Antique | 115399 | Cansilayan PS | VALDERRAMA | 0 | 1 | 2 | Repair of Classrooms | 1990597.56 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Bacolod City | 302699 | ABKASA National High School | Bacolod City | 0 | 1 | 8 | Repair of Classrooms | 3844978.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Bago City | 117514 | Bagroy ES | BAGO CITY | 4 | 1 | 5 | Repair of Classrooms | 2681518.72 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Cadiz City | 311405 | Banquerohan NHS | Cadiz City | 2 | 1 | 14 | Repair of Classrooms | 6452598.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Cadiz City | 117538 | San Andres ES | Cadiz City | 2 | 1 | 3 | Repair of Classrooms | 1307681.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Cadiz City | 117540 | SPED Training Center | Cadiz City | 2 | 1 | 18 | Repair of Classrooms | 6854463.18 | 1 |  | reverted | 85% | 2023-01-31 | [9 empty] | Under suspension due to issue on building permit | [12 empty] | 85% |  | 44927 | [5 empty] | reverted
REPAIR 2021 | Region VI | Capiz |  | CANAPI-AN INTEGRATED SCHOOL | MAAYON | 1 | 1 | 6 | Repair of Classrooms | 2896550.15 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115638 | Tanza Norte ES | PANAY | 1 | 1 | 5 | Repair of Classrooms | 2061164.82 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115652 | Cogon ES (Panitan) | PANITAN | 1 | 1 | 4 | Repair of Classrooms | 951085.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115656 | Jesus Gonzalo Albana ES | PANITAN | 1 | 1 | 2 | Repair of Classroom | 644920.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | 7 | Repair of Classrooms | 2165497.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115716 | Manoling ES | PRESIDENT ROXAS | 1 | 1 | 8 | Repair of Classroom | 2784400.98 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115493 | San Juan ES (dumarao) | DUMARAO | 2 | 1 | 6 | Repair of Classrooms | 2248964.16 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 501092 | Bula Integrated School | MAMBUSAO | 2 | 1 | 12 | Repair of Classrooms | 4798702.92 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115600 | Burias ES | MAMBUSAO | 2 | 1 | 9 | Repair of Classrooms | 3235894.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Capiz | 115731 | Bangkal ES | SAPI-AN | 2 | 1 | 4 | Repair of Classrooms | 1285716.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Escalante City | 117042 | Don Esteban dela Rama Elementary School | CITY OF ESCALANTE | 1 | 1 | 11 | Repair of Classrooms | 4511858.06 | 1 |  | COMPLETED | 100% | 2022-09-30 | [9 empty] | Punclisted items are not yet addressed by the contractor | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Guimaras | 115826 | Old Poblacion Elementary School | BUENAVISTA | 0 | 1 | 14 | Repair of Classrooms | 6571845.67 | 1 | 4475425.9695 | COMPLETED | 100% | 2021-12-23 |  | 04-2021-lot 1 | 04-2021-lot 1 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | GMO Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Guimaras | 115873 | San Miguel Central School | JORDAN (Capital) | 0 | 1 | 8 | Repair of Classrooms | 3759977.03 | 1 | 2557000.0002 | COMPLETED | 100% | 2021-12-23 |  | 04-2021-lot 2 | 04-2021-lot 2 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Guimaras | 115893 | Concordia Elementary School | NUEVA VALENCIA | 0 | 1 | 10 | Repair of Classrooms | 4818602.53 | 1 | 4777492.2348 | COMPLETED | 100% | 2021-12-23 | 2021-10-11 | 04-2021-lot 3 | 04-2021-lot 3 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | Early Riser Constructio | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Guimaras | 115901 | Paaralan ng Buhay ng La Orca | NUEVA VALENCIA | 0 | 1 | 6 | Repair of Classrooms | 2305588.33 | 1 | 2287314.6769 | COMPLETED | 100% | 2021-12-23 | 2021-10-11 | 04-2021-lot 3 | 04-2021-lot 3 | 2021-05-26 | 2021-06-08 | 2021-06-22 | 2021-07-09 | 2021-07-20 | Early Riser Constructio | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Himamaylan City | 117072 | Cong. Eliseo P. Limsiaco Sr. MES | CITY OF HIMAMAYLAN | 5 | 1 | 10 | Repair of Classrooms | 3443803.28 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116724 | Dacdacanan ES | SAN JOAQUIN | 1 | 1 | 3 | Repair of Classrooms | 1555209.99 | 1 | 1058517.66 | COMPLETED | 100% | 2022-01-11 | 2022-01-05 | R-06--BEFF Repair -2021-B1-01 | R-06--BEFF Repair -2021-B1-01 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116748 | Toog-Tiglawa ES | SAN JOAQUIN | 1 | 1 | 8 | Repair of Classrooms | 2533607.93 | 1 | 1720662.98 | COMPLETED | 100% | 2022-01-11 | 2022-01-05 | R-06--BEFF Repair -2021-B1-01 | R-06--BEFF Repair -2021-B1-01 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 115948 | Bagsakan PS | ALIMODIAN | 2 | 1 | 2 | Repair of Classrooms | 945620.53 | 1 | 658561.72 | COMPLETED | 100% | 2021-12-16 | 2021-09-17 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116502 | Apian Elementary School | LEON | 2 | 1 | 5 | Repair of Classrooms | 1961689.47 | 1 | 1366626.93 | COMPLETED | 100% | 2021-12-16 | 2021-09-12 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116810 | Mambuyo ES | SANTA BARBARA | 2 | 1 | 5 | Repair of Classrooms | 2059368.98 | 1 | 1435111.64 | COMPLETED | 100% | 2021-12-16 | 2021-09-17 | R-06--BEFF Repair -2021-B1-02 | R-06--BEFF Repair -2021-B1-02 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Early Riser Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116646 | Barasan ES | POTOTAN | 3 | 1 | 11 | Repair of Classrooms | 3901045.83 | 1 | 2539424.22 | COMPLETED | 100% | 2022-01-11 | 2022-12-23 | R-06--BEFF Repair -2021-B1-03 | R-06--BEFF Repair -2021-B1-03 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Wilkinson Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116296 | Bugtongan ES | DUEÑAS | 4 | 1 | 8 | Repair of Classrooms | 2968679.52 | 1 | 2055495.78 | COMPLETED | 100% | 2021-12-16 | 2022-03-10 | R-06--BEFF Repair -2021-B1-04 | R-06--BEFF Repair -2021-B1-04 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Edison Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 116308 | Ponong Grande ES | DUEÑAS | 4 | 1 | 10 | Repair of Classrooms | 2483701.85 | 1 | 1691009.02 | COMPLETED | 100% | 2021-12-16 | 2022-03-10 | R-06--BEFF Repair -2021-B1-04 | R-06--BEFF Repair -2021-B1-04 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Edison Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5 | 1 | 35 | Repair of Classrooms | 6826100.75 | 1 | 4629459.85 | COMPLETED | 100% | 2021-12-16 | 2022-02-10 | R-06--BEFF Repair -2021-B1-05 | R-06--BEFF Repair -2021-B1-05 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Anjush Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo | 501491 | Batuanan IS | Carles | 5 | 1 | 5 | Repair of Classrooms | 1505955.39 | 1 | 1002969.95 | COMPLETED | 100% | 2021-12-16 | 2022-02-10 | R-06--BEFF Repair -2021-B1-05 | R-06--BEFF Repair -2021-B1-05 | 2021-06-04 |  | 2021-06-25 | 2021-07-14 | 2021-08-18 | Anjush Builders | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Iloilo City | 117622 | Molo I ES | ILOILO CITY (Capital) | 0 | 1 | 13 | Repair of Classrooms | 2417742.86 | 1 |  | reverted | 88% | 2023-03-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | [12 empty] | 88% |  | 44986 | [5 empty] | reverted
REPAIR 2021 | Region VI | Iloilo City | 302746 | R. G. Hechanova Memorial NHS | ILOILO CITY (Capital) | 0 | 1 | 4 | Repair of Classrooms | 1181220.57 | 1 |  | reverted | 10% | 2023-06-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | [12 empty] | 10% |  | 44986 | [5 empty] | reverted
REPAIR 2021 | Region VI | Iloilo City | 500551 | SPED - Integrated School for Exceptional Children | ILOILO CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 1283571.73 | 1 |  | reverted | 10% | 2023-06-01 | [9 empty] | Terminated October 2022; Contractor (E.M. Sinai Construction Services blacklisted) | [12 empty] | 10% |  | 44986 | [5 empty] | reverted
REPAIR 2021 | Region VI | Iloilo City | 117604 | Tacas ES | ILOILO CITY (Capital) | 0 | 1 | 7 | Repair of Classrooms | 1474559.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 15 | Repair of Classrooms | 5784190.44 | 1 | 5769246.44 | COMPLETED | 100% | [9 empty] | Rism Builers and Construction services Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | 22 | Repair of Classrooms | 4194461.43 | 1 | 4181072.72 | COMPLETED | 100% | [9 empty] | Rism Builers and Construction services Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 26 | Repair of Classrooms | 8719945.91 | 1 | 8705000 | COMPLETED | 100% | [9 empty] | Rism Builers and Construction services Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 18 | Repair of Classrooms | 6184935.25 | 1 | 6171000 | COMPLETED | 100% | [9 empty] | Rism Builers and Construction services Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | La Carlota City | 117638 | Cubay ES | LA CARLOTA CITY | 4 | 1 | 11 | Repair of Classrooms | 5314284.33 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 302669 | Negros Occidental High Schol | CITY OF BACOLOD | 0 | 1 | 8 | Repair of Classrooms | 3427235.39 | 1 | 1984312.59 | COMPLETED | 100% | 2021-12-10 |  |  | 21-07-004 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 116932 | Pesons ES | CALATRAVA | 1 | 1 | 2 | Repair of Classrooms | 981349.73 | 1 | 980319.48 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-006 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS - Bagong Silang Annex | SALVADOR BENEDICTO | 1 | 1 | 2 | Repair of Classrooms | 1428391.93 | 1 | 1363109.35 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-006 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117415 | Stop Aguinaldo ES | TOBOSO | 1 | 1 | 8 | Repair of Classrooms | 3107175.09 | 1 | 2941988.44 | COMPLETED | 100% | 2021-12-10 |  |  | 21-07-005 | [5 empty] | VALKYRIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 302663 | Manapla NHS - Purisima Extension | MANAPLA | 2 | 1 | 6 | Repair of Classrooms | 1523296.18 | 1 | 1439878.35 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-007 | [5 empty] | VALKYRIE CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117020 | Batea PS | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 4 | Repair of Classrooms | 2005139.74 | 1 | 1981661.1 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-008 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117345 | Nayon ES | SAN ENRIQUE | 4 | 1 | 9 | Repair of Classrooms | 3169104.53 | 1 | 3132417.47 | COMPLETED | 100% | 2021-11-22 |  |  | 21-008-01 | [5 empty] | SUNSHINE SAPPHIRE CONST. AND SUPPLY INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117186 | Bungahin ES | ISABELA | 5 | 1 | 7 | Repair of Classrooms | 2887809.11 | 1 | 2820315.97 | COMPLETED | 100% | 2021-11-22 |  |  | 21-08-002 | [5 empty] | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117190 | Don Beneito Lpez ES | ISABELA | 5 | 1 | 4 | Repair of Classrooms | 1578283.16 | 1 | 1553000 | COMPLETED | 100% | 2021-11-11 |  |  | 21-07-009 | [5 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117205 | Limalima Es | ISABELA | 5 | 1 | 7 | Repair of Classrooms | 2556323.37 | 1 | 2533323 | COMPLETED | 100% | 2021-11-11 |  |  | 21-07-010 | [5 empty] | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117241 | Talaptap ES | LA CASTELLANA | 5 | 1 | 10 | Repair of Classrooms | 3772314.67 | 1 | 3731000 | COMPLETED | 100% | 2021-11-11 |  |  | 21-07-011 | [5 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117262 | E. Basa ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 3 | Repair of Classrooms | 1505897.25 | 1 | 1481100.38 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-012 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 116944 | Calamunding ES | CANDONI | 6 | 1 | 3 | Repair of Classrooms | 1721546.58 | 1 | 1691000 | COMPLETED | 100% | 2021-11-11 |  |  | 21-07-013 | [5 empty] | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 116947 | Cantacson ES | CANDONI | 6 | 1 | 4 | Repair of Classrooms | 1915351.62 | 1 | 1749022.05 | COMPLETED | 100% | 2021-11-13 |  |  | 21-07-014 | [5 empty] | GOLDEN PACE CONSTRUCTIONS CORPORATION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Negros Occidental | 117184 | Vista Alegre ES | ILOG | 6 | 1 | 3 | Repair of Classrooms | 1680615.54 | 1 | 1654750.3 | COMPLETED | 100% | 2021-11-10 |  |  | 21-07-015 | [5 empty] | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Passi City | 117916 | Bacuranan Elementary School | CITY OF PASSI | 4 | 1 | 8 | Repair of Classrooms | 2985441.51 | 1 | 2447000 | COMPLETED | 100% | December 24, 2021 | N/A | RO6-D14-CY2021-REPAIR-CLASSROOMS-L1 | RO6-D14-CY2021-REPAIR-CLASSROOMS-L1 | June 08, 2021 | June 16, 2021 | August 16, 2021 | August 19, 2021 | August 24, 2021 | Rism Builders & Construction Services Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Roxas City | 117669 | Don Manuel Arnaldo MS | ROXAS CITY (Capital) | 1 | 1 | 12 | Repair of Classrooms | 2999777.59 | 1 | 2069000 | COMPLETED | 100% | 2021-11-14 |  |  | CON-2021-019 | June 9, 2021 | June 16, 2021 | June 29, 2021 | June 30, 2021 | August 9, 2021 | RISM Builders & Const. Svs., Inc. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Sagay City | 117703 | Plaridel Elementary School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 3004680.22 | 1 | 1832165.88 | COMPLETED | 100% | November 16, 2021 |  | 07-2021 | 07-2021 | June 7, 2021 | June 15, 2021 | June 30, 2021 | July 21, 2021 | August 16, 2021 | SANS CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | San Carlos City | 117742 | Ansulag ES | SAN CARLOS CITY | 1 | 1 | 6 | Repair of Classrooms | 2783150.74 | 1 | 2748000 | COMPLETED | 100% | 2021-06-25 | 2021-06-21 | 7773810-2021beff-ANSULAG ES | 7773810-2021beff-ANSULAG ES | 2021-06-17 | 2021-06-16 | 2021-07-07 | 2021-07-29 | 2021-08-20 | Rism Builders & Construction Services Inc. | 100% Completed | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 6 | Repair of Classrooms | 2442021.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VI | Sipalay City | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | 5 | Repair of Classrooms | 2673447.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bais City | 120088 | Cambagahan ES | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 550447.95 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bais City | 323005 | Manuel L. Teves Memorial HS | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 505199.54 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bais City | 120101 | Panalaan ES | BAIS CITY | 2 | 1 | 4 | Repair of Classrooms | 2031532.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bayawan City | 120114 | Don Pablo Carmen Blanco Utzurrum Memorial Elementary School | BASAY | 3 | 1 | 8 | Repair of Classrooms | 4820489.9 | 1 | 3424000 | COMPLETED | 100% |  |  |  | 2021-BEFF-001 | 6/18/2021 | 6/28/2021 | 2021-07-12 | 7/16/2021 | 6/27/2021 | RISM BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bogo City | 119118 | Bogo II Central ES | CITY OF BOGO | 4 | 1 | 4 | Repair of Classrooms | 2472943.1 | 1 |  | COMPLETED | 100% | Nov. 14, 2021 | [5 empty] | July 12, 2021 | July 14, 2021 | Aug. 16, 2021 | SB & T CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bogo City | 119119 | Bung-aw Elementary School | CITY OF BOGO | 4 | 1 | 2 | Repair of Classrooms | 1022507.69 | 1 |  | COMPLETED | 100% | Nov. 10, 2021 | [5 empty] | July 12, 2021 | July 14, 2021 | Aug. 12, 2021 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bohol | 117935 | Toril ES | ALBURQUERQUE | 1 | 1 | 9 | Repair of Classrooms | 2894130.84 | 1 | 1950492.7 | COMPLETED | 100% | 2022-10-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia | For Punchlisting | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118564 | Tawala ES | PANGLAO | 1 | 1 | 11 | Repair of Classrooms | 3584468.21 | 1 | 2407509.72 | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia | For Punchlisting | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118407 | Sto. Rosario Elementary School | INABANGA | 2 | 1 | 8 | Repair of Classrooms | 2726461.35 | 1 | 2028570.53 | COMPLETED | 100% |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | Inabanga Drilling | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118589 | Bogo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 8 | Repair of Classrooms | 2037504.14 | 1 | 1333892.23 | COMPLETED | 100% | 2022-11-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | LM Construction | For Punchlisting | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118613 | Kabasacan ES | SAGBAYAN (BORJA) | 2 | 1 | 4 | Repair of Classrooms | 1180348.83 | 1 | 884810.81 | COMPLETED | 100% |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | Inabanga Drilling | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bohol | 117940 | Cayacay ES | ALICIA | 3 | 1 | 11 | Repair of Classrooms | 3372561.8 | 1 | 2343280.96 | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | EFB Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN | 3 | 1 | 3 | Repair of Classrooms | 1088648.66 | 1 | 848900.62 | COMPLETED | 100% |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | C Jansen construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Bohol | 118863 | Ticum ES | VALENCIA | 3 | 1 | 7 | Repair of Classrooms | 2348214.64 | 1 | 1585072.11 | COMPLETED | 100% |  |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-22 | 2021-08-18 | Sept 28, 2021 | JF Estafia | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Carcar City | 119154 | Buenavista Elementary School | CITY OF CARCAR | 1 | 1 | 3 | Repair of Classrooms | 2221764.39 | 1 |  | COMPLETED | 100% | [6 empty] | July 7, 2021 | [16 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Carcar City | 119178 | MAINIT ELEMENTARY SCHOOL | CITY OF CARCAR | 1 | 1 | 1 | Repair of Classroom | 779719.39 | 1 | 697452.29 | COMPLETED | 100% |  |  |  | Repair2019-01carcar |  |  | July 7, 2021 |  |  | PJA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119618 | Balungag ES | SAN FERNANDO | 1 | 1 | 6 | Repair of Classrooms | 2245599.16 | 1 | 2196844.85 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-01 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | SB & T CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 118875 | Guiwang ES | ALCOY | 2 | 1 | 6 | Repair of Classrooms | 1905019.22 | 1 | 1886306.1 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-02 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | LA PRUEBA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 118933 | Tabayag ES | ARGAO | 2 | 1 | 6 | Repair of Classrooms | 2006667.47 | 1 | 1991113.58 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-03 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | MARLJAVIS CONSTRUCTION, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119324 | Manangal ES | DALAGUETE | 2 | 1 | 4 | Repair of Classrooms | 1227850.89 | 1 | 1215822.71 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-04 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | JY BONTILAO & ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 118913 | Sto. Rosario ES | ALOGUINSAN | 3 | 1 | 3 | Repair of Classrooms | 1274310.97 | 1 | 1008724.53 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-05 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | ANIELTHON CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119570 | Sambagon ES | PINAMUNGAHAN | 3 | 1 | 8 | Repair of Classrooms | 2622329 | 1 | 2607273.15 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-06 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119821 | Sandayong ES | TUBURAN | 3 | 1 | 6 | Repair of Classrooms | 2082851.88 | 1 | 1857235.25 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-07 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | GELA CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119216 | Catmondaan ES | CATMON | 5 | 1 | 7 | Repair of Classrooms | 2986666.58 | 1 | 2958650.33 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-08 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | BARR STEEL | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119218 | Ginabukan ES | CATMON | 5 | 1 | 1 | Repair of Classroom | 426692.23 | 1 | 424334.83 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-08 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | BARR STEEL | SUSPENDED (ROAD NOT PASSABLE DUE TO ROAD CONCRETING) | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119221 | Tabili Elem. | CATMON | 5 | 1 | 7 | Repair of Classrooms | 2613056.54 | 1 | 2592621.31 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-09 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | Golden Hammer Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu | 119254 | Cogon ES | CORDOVA | 6 | 1 | 6 | Repair of Classrooms | 2518645.47 | 1 | 2498421.71 | COMPLETED | 100% |  |  |  | CY 2021 BEFF REPAIR-DEPED-R7-10 | JUNE 24, 2021 | JULY 05, 2021 | JULY 19, 2021 | AUGUST 16, 2021 | SEPTEMBER 20, 2021 | JY BONTILAO & ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Cebu City | 119886 | Labangon Elementary School | CEBU CITY (Capital) | 2 | 1 | 18 | Repair of Classrooms | 3752209.21 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | City of Naga, Cebu | 119514 | Bairan Elementary School | CITY OF NAGA | 1 | 1 | 1 | Repair of Classroom | 524662.6 | 1 | 522369.86 | COMPLETED | 100% | 2021-11-15 | 2021-08-31 | cityofnaga2021-001 |  | 2021-07-08 | 2021-07-15 | 2021-07-27 | 2021-08-03 | 2021-08-09 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | City of Naga, Cebu | 119506 | Inayagan Elementary School | CITY OF NAGA | 1 | 1 | 3 | Repair of Classrooms | 1649255.52 | 1 | 1643039.14 | COMPLETED | 100% | 2021-11-15 | 2021-09-20 | cityofnaga2021-001 |  | 2021-07-08 | 2021-07-15 | 2021-07-27 | 2021-08-03 | 2021-08-09 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Danao City | 119349 | Guinsay ES | DANAO CITY | 5 | 1 | 2 | Repair of Classrooms | 1602429.37 | 1 | 1265800.85 | COMPLETED | 100% | [9 empty] | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Danao City | 322002 | Guinsay National High School | DANAO CITY | 5 | 1 | 2 | Repair of Classrooms | 1397522.32 | 1 | 1002959.84 | COMPLETED | 100% | [9 empty] | HERO Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Dumaguete City | 303166 | Camanjac National High School | Dumaguete City | 2 | 1 | 13 | Repair of Classrooms | 2999999.73 | 1 | 2979000 | COMPLETED | 100% | 2022-01-02 | [5 empty] | 2021-06-15 |  | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Guihulngan City | 120264 | Banwague ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 756256.04 | 1 | 622167.9 | COMPLETED | 100% | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Guihulngan City | 120251 | Maculos ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1773747.19 | 1 | 1230581.49 | COMPLETED | 100% | 2021-12-29 |  |  | ITB 2021-06 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Guihulngan City | 120283 | Taloto ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 1081239.33 | 1 | 775994.89 | COMPLETED | 100% | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Lapu-Lapu City | 303187 | Pusok NHS | LAPU-LAPU CITY (OPON) | 0 | 1 | 22 | Repair of Classrooms | 1556726.92 | 1 | 1523197.92 | COMPLETED | 100% | December 10, 2021 | Sept. 20, 2021 |  |  | June 03, 2021 | June 10, 2021 | June 22, 2021 | July 08, 2021 | August 12, 2021 | ANIELTHON CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Lapu-Lapu City | 119984 | Sudtonggan ES | LAPU-LAPU CITY (OPON) | 0 | 1 | 5 | Repair of Classrooms | 2413014.34 | 1 | 1785629.05 | COMPLETED | 100% | December 10, 2021 | November 10, 2021 |  |  | June 03, 2021 | June 10, 2021 | June 22, 2021 | July 08, 2021 | August 12, 2021 | TRAIBARN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | 13 | Repair of Classrooms | 2999986.07 | 1 | 2942434.03 | COMPLETED | 100% | 11-15-21 |  | RE2021-01 | 2021 - 07 | 2021-03-06 | 2021-09-06 | 06/21/21 | 06/30/21 | 07/21/21 | Golden Hammer Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120053 | So-ok Elementary School | AYUNGON | 1 | 1 | 8 | Repair of Classrooms | 3721317.42 | 1 | 3003000 | COMPLETED | 100% | 2021-12-04 | 2021-12-03 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120199 | Binalbagan Elementary School | CANLAON CITY | 1 | 1 | 10 | Repair of Classrooms | 4706070.84 | 1 | 3522000 | COMPLETED | 100% | 2021-12-04 | 2022-07-11 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120217 | Tigbahi ES | CANLAON CITY | 1 | 1 | 6 | Repair of Classrooms | 4246688.66 | 1 | 3177000 | COMPLETED | 100% | 2021-12-04 | 2022-07-11 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120219 | Villa Iowa ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 5165453.02 | 1 | 3874000 | COMPLETED | 100% | 2021-12-02 | 2022-03-08 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120374 | Pedro Gobuyan, Sr. MES (Mayaposi ES) | MABINAY | 2 | 1 | 6 | Repair of Classrooms | 1965466.89 | 1 | 1475000 | COMPLETED | 100% | 2021-12-02 | 2021-11-19 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 120437 | San Roque Primary School | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 1966423.02 | 1 | 1624000 | COMPLETED | 100% | 2021-12-04 | 2021-11-26 | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | 20 | Repair of Classrooms | 8901004.3 | 1 | 6664000 | COMPLETED | 100% | 2022-03-04 |  | n/a |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | processing of fire safety inspection certificate | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Siquijor | 120675 | Kimba Elementary School | Lazi | 1 | 1 | 5 | Repair of Classrooms | 2999578.32 | 1 | 2458560.33 | COMPLETED | 100% | 2021-11-15 |  |  |  | 2021-05-25 | 2021-06-02 | 2021-06-23 | 2021-06-30 | 2021-07-16 | NALE Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Tagbilaran City | 118716 | Ubujan Elementary School | Tagbilaran City | 1 | 1 | 14 | Repair of Classrooms | 6594981.05 | 1 | 5011996.46 | COMPLETED | 100% | February 4, 2022 | September 8, 2021 |  | 2021-01-Infra | June 14, 2021 | June 23, 2021 | July 5, 2021 | July 7, 2021 | August 2, 2021 | C. Jansen Construction and General Merchandise | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Talisay City | 233504 | Hawanay Elementary School | CITY OF TALISAY | 1 | 1 | 2 | Repair of Classrooms | 1502153 | 1 |  | COMPLETED | 100% | 2019-11-22 | August 23,2019 |  |  | 2019-01-08 | 2019-01-15 | 2019-01-28 | 2019-04-08 | 2019-08-22 | Maqueserg Construction & Gen. Mdse. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Talisay City | 119801 | Manguilamon Elementary School | CITY OF TALISAY | 1 | 1 | 2 | Repair of Classrooms | 1497351.18 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Tanjay City | 234006 | Canggabi Elementary School | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 484821.83 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Tanjay City | 234001 | George Pilas MS (Aseotes PS) | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 338983.18 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Tanjay City | 120542 | Pelagio Jabel MS (Bahian ES) | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms | 1086834.18 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Tanjay City | 120426 | Simborio ES | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1185395.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3 | 1 | 5 | Repair of Classrooms | 2842658.2 | 1 |  | COMPLETED | 100% | [9 empty] | ANIELTHON CONSTRUCTION AND SUPPLY | 2814944.5 | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Baybay City | 121109 | Palhi Elementary School | CITY OF BAYBAY | 5 | 1 | 4 | Repair of Classrooms | 2930798.51 | 1 | 2841049.98 | COMPLETED | 100% |  |  | 2021-06-I001 | 2021-06-I001 | 2021-06-07 | 2021-06-17 | 2021-07-13 | 2021-07-30 | 2021-08-10 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | 2 | Repair of Classrooms | 1085661.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Biliran | 120788 | Cabucgayan Central School | CABUCGAYAN | 0 | 1 | 13 | Repair of Classrooms | 4923979.52 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | 0 | 1 | 2 | Repair of Classrooms | 768493.11 | 1 | 361130.34 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Borongan City | 122407 | Suribao ES | CITY OF BORONGAN (Capital) | 0 | 1 | 8 | Repair of Classrooms | 2740661.46 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Borongan City | 122367 | Taboc ES | CITY OF BORONGAN (Capital) | 0 | 1 | 2 | Repair of Classrooms | 925079.86 | 1 | 1356342 | COMPLETED | 100% | 2019-11-13 |  | CY 2019 REPAIR/REHABILITATION-Batch 1-BORCITY | Repair/rehabilitation-Lot 2 | 2018-10-18 | 2018-10-26 | 2018-11-07 | 2018-11-16 | 2019-08-08 | YFL BUILDERS | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Calbayog City | 124121 | Binaliw Elementary School | CALBAYOG CITY | 1 | 1 | 8 | Repair of Classrooms | 3498263.94 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Catbalogan City | 123429 | Buri Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1385471.67 | 1 |  | COMPLETED | 100% | 2021-11-26 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Catbalogan City | 123427 | Rama Elementary School | CITY OF CATBALOGAN (Capital) | 2 | 1 | 3 | Repair of Classrooms | 1883358.94 | 1 |  | COMPLETED | 100% | 2021-11-26 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Catbalogan City | 123437 | San Roque ES | CITY OF CATBALOGAN (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1443033.65 | 1 |  | COMPLETED | 100% | 2021-11-26 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 122328 | Bigo Elementary School | ARTECHE | 0 | 1 | 1 | Repair of Classroom | 333601.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 122413 | Can-avid Central Elementary School | CAN-AVID | 0 | 1 | 9 | Repair of Classrooms | 2883439.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | 0 | 1 | 10 | Repair of Classrooms | 2364888.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 500235 | Dao Integrated School | ORAS | 0 | 1 | 5 | Repair of Classrooms | 1758934.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 303520 | Oras National High School | ORAS | 0 | 1 | 16 | Repair of Classrooms | 3287104.68 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | 0 | 1 | 1 | Repair of Classroom | 385124.95 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Eastern Samar | 303493 | Alugan National School of Craftsmanship and Home Industries | SAN POLICARPO | 0 | 1 | 14 | Repair of Classrooms | 4276384.84 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 120962 | Astorga Elementary School | ALANGALANG | 1 | 1 | 4 | Repair of Classrooms | 1786594.94 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121926 | Limbuhan Elementary School | TANAUAN | 1 | 1 | 5 | Repair of Classrooms | 1863222.03 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121928 | San Roque Elementary School | TANAUAN | 1 | 1 | 2 | Repair of Classrooms | 508738.47 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121933 | Tugop Elementary School | TANAUAN | 1 | 1 | 2 | Repair of Classrooms | 469762.42 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 191530 | Lanauan Elementary School | MACARTHUR | 2 | 1 | 3 | Repair of Classrooms | 1756698.03 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121809 | Aringit Primary School | PASTRANA | 2 | 1 | 2 | Repair of Classrooms | 1133412.54 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121967 | Capinahan Elementary School | VILLABA | 3 | 1 | 6 | Repair of Classrooms | 1798923.7 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121666 | Matag-ob Central School | MATAG-OB | 4 | 1 | 3 | Repair of Classrooms | 1814456.19 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 121802 | Rizal Elementary School | PALOMPON | 4 | 1 | 3 | Repair of Classrooms | 1170515.75 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 120921 | Anibongon Primary School | ABUYOG | 5 | 1 | 1 | Repair of Classroom | 518183.02 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 120931 | Matagnao Primary School | ABUYOG | 5 | 1 | 1 | Repair of Classroom | 520107.54 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5 | 1 | 19 | Repair of Classrooms | 11031710 | 1 |  | COMPLETED | 100% | [10 empty] | Under Procurement | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Leyte | 303439 | Tinago National High School | INOPACAN | 5 | 1 | 9 | Repair of Classrooms | 2737263.59 | 1 |  | COMPLETED | 100% | [10 empty] | For Award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Maasin City | 122132 | Libhu ES | CITY OF MAASIN (Capital) | 0 | 1 | 7 | Repair of Classrooms | 2900220.89 | 1 | 2025871.07 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 193007 | Balud Elementary School | CATARMAN (Capital) | 1 | 1 | 5 | Repair of Classrooms | 2280897.58 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 123131 | San Agustin PS | MONDRAGON | 1 | 1 | 2 | Repair of Classrooms | 785296.39 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 123205 | Vinisitahan ES | SAN ANTONIO | 1 | 1 | 7 | Repair of Classrooms | 3073891.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1 | 1 | 10 | Repair of Classrooms | 3774528.47 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 123277 | Luisita ES | VICTORIA | 1 | 1 | 3 | Repair of Classrooms | 1348487.09 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 122980 | Gibatangan Elementary School | LAOANG | 2 | 1 | 5 | Repair of Classrooms | 1874684.16 | 1 |  | COMPLETED | 100% | 2022-12-31 | [9 empty] | ongoing termination | [12 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 122998 | Mabini ES | LAPINIG | 2 | 1 | 3 | Repair of Classrooms | 1445464.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Northern Samar | 123156 | Matambag ES | PALAPAG | 2 | 1 | 4 | Repair of Classrooms | 1864201.8 | 1 |  | reverted | 50% | 2022-12-31 | [9 empty] | ongoing termination | [12 empty] | 50% |  | 44986 | [5 empty] | reverted
REPAIR 2021 | Region VIII | Ormoc City | 303654 | Dolores National High School | ORMOC CITY | 4 | 1 | 10 | Repair of Classrooms | 1957929.53 | 1 | 1369755.19 | COMPLETED | 100% | 2021-12-22 |  |  | 2019-BEFF-R-BQ-C4 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Ormoc City | 124207 | Doña Feliza Z. Mejia Elementary School | ORMOC CITY | 4 | 1 | 2 | Repair of Classrooms | 1268277.58 | 1 | 1024497.43 | COMPLETED | 100% | 2021-11-08 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-02 | Vhits DG Builders & Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Ormoc City | 124210 | Lao Elementary School | ORMOC CITY | 4 | 1 | 3 | Repair of Classrooms | 1624971.26 | 1 | 2065089.22 | COMPLETED | 100% | 2021-12-02 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Ormoc City | 124184 | Manlilinao Elementary School | ORMOC CITY | 4 | 1 | 1 | Repair of Classroom | 525654.72 | 1 | 770604.11 | COMPLETED | 100% | 2021-12-02 |  |  | 2019-BEFF-R-B1-C4 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-16 | QCC Construction and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Ormoc City | 124199 | Tambulilid Elementary School | ORMOC CITY | 4 | 1 | 4 | Repair of Classrooms | 2008847.4 | 1 | 1632682.48 | COMPLETED | 100% | 2021-11-18 |  |  |  | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-07-23 | 2021-08-02 | Vhits DG Builders & Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123542 | Gandara II CS | GANDARA | 1 | 1 | 6 | Repair of Classrooms | 2607347.76 | 1 | 2590089.36 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123808 | Lobe-Lobe Elementary School | SANTO NIÑO | 1 | 1 | 2 | Repair of Classrooms | 1305624.03 | 1 | 1296549.76 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123812 | Sto. Nino CS | SANTO NIÑO | 1 | 1 | 12 | Repair of Classrooms | 6909467.96 | 1 | 6894084.25 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123331 | Basey II CS | BASEY | 2 | 1 | 2 | Repair of Classrooms | 1266393.89 | 1 | 1246371.6 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123365 | Calbiga Central Elem. School | CALBIGA | 2 | 1 | 17 | Repair of Classrooms | 8303027.49 | 1 | 8267595.86 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123680 | Pinabacdao Central Elementary School | PINABACDAO | 2 | 1 | 3 | Repair of Classrooms | 1827517.73 | 1 | 1813092.65 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123760 | Cabungaan ES | SANTA RITA | 2 | 1 | 1 | Repair of Classroom | 596427.63 | 1 | 591427.63 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Samar (Western Samar) | 123772 | Sta. Rita I CS | SANTA RITA | 2 | 1 | 1 | Repair of Classroom | 1275269.66 | 1 | 1267269.66 | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Southern Leyte | 501531 | Beniton Integrated School | BONTOC | 0 | 1 | 2 | Repair of Classrooms | 920118.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Southern Leyte | 122005 | Hilaan Elementary School | BONTOC | 0 | 1 | 11 | Repair of Classrooms | 4917615.65 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 0 | 1 | 11 | Repair of Classrooms | 4797318.42 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Southern Leyte | 122059 | Silago Central School | SILAGO | 0 | 1 | 17 | Repair of Classrooms | 6962763.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Southern Leyte | 122272 | Milagroso Elementary School | SOGOD | 0 | 1 | 3 | Repair of Classrooms | 1320983.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Tacloban City | 124236 | Mercyville Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 10 | Repair of Classrooms | 3374635.4 | 1 |  | COMPLETED | 100% |  | 2021-11-04 | [7 empty] | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region VIII | Tacloban City | 314001 | San Jose Night High School | TACLOBAN CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 2360315.14 | 1 |  | COMPLETED | 100% |  | 2021-12-04 | [7 empty] | VHITS D.G. BUILDERS & ENTERPRISES | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Bukidnon | 126278 | Salimbalan ES | BAUNGON | 1 | 1 | 3 | Repair of Classrooms | 2253180.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Bukidnon | 126385 | Kubayan ES | IMPASUG-ONG | 2 | 1 | 4 | Repair of Classrooms | 2371397.18 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Bukidnon | 126404 | Mabuhay ES | KADINGILAN | 3 | 1 | 3 | Repair of Classrooms | 1806904.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1904895.89 | 1 |  | COMPLETED | 100% | 2021-12-12 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 001 | 2021-005 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Cagayan de Oro City | 127982 | Pagalungan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1017217.93 | 1 |  | COMPLETED | 100% | 2021-12-12 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 003 | 2021-005 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Cagayan de Oro City | 315408 | Gusa National High School - FS Catanico Annex | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 2684852.97 | 1 |  | COMPLETED | 100% | 2022-01-11 |  | REPAIR 2021 - RX - CAGAYAN DE ORO CITY - 002 | 2021-006 | 2021-06-28 | 2021-07-05 | 2021-08-20 | 2021-09-06 | September 13,2021 | JARM Construction Services and Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Camiguin | 126929 | Cabuan ES | GUINSILIBAN | 0 | 1 | 7 | Repair of Classrooms | 2579270.93 | 1 |  | COMPLETED | 100% | 2022-02-05 | [7 empty] | 2021-08-09 | VINLABZ CONSTRUCTION | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region X | Camiguin | 126934 | Manuyog ES | SAGAY | 0 | 1 | 1 | Rehabilitation of H.E. Bldg. | 420729.07 | 1 | 610452.81 | COMPLETED | 100% | 2022-02-05 | [7 empty] | 2021-08-09 | VINLABZ CONSTRUCTION | Waiting for Sub-ARO | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | El Salvador | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | 4 | Repair of Classrooms | 3003709.82 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Gingoog City | 501379 | Alfonso Ang Militante Integrated School - Elem | GINGOOG CITY | 1 | 1 | 2 | Repair of Classrooms | 934544.54 | 1 |  | COMPLETED | 100% | [10 empty] | for issuance of NTP | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Gingoog City | 128026 | DULAG ELEMENTARY SCHOOL | GINGOOG CITY | 1 | 1 | 4 | Repair of Classrooms | 2075040.34 | 1 |  | COMPLETED | 100% | [10 empty] | for issuance of NTP | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Iligan City | 128106 | Bulalang Elementary School | ILIGAN CITY | 0 | 1 | 4 | Repair of Classrooms | 1095118.2 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Iligan City | 128140 | Doña Juana A. Lluch MCS | ILIGAN CITY | 0 | 1 | 2 | Repair of Classrooms | 756841.2 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Iligan City | 128102 | Lanipao ES | ILIGAN CITY | 0 | 1 | 7 | Repair of Classrooms | 3188086.04 | 1 |  | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Lanao del Norte | 126978 | Fausto Alvia MES | BAROY | 1 | 1 | 10 | Repair of Classrooms | 4552901.44 | 1 |  | COMPLETED | 100% |  |  | 2021-02- INFRA- Lot No. 1 |  |  |  | 2021-08-05 |  |  | AMMAR Construcrion & Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Lanao del Norte | 200511 | San Juan PS | BAROY | 1 | 1 | 1 | Repair of Classroom | 574294.78 | 1 |  | COMPLETED | 100% | 2022-01-26 |  | 2021-02- INFRA-Lot No. 2 |  |  |  | 2021-08-05 |  | 2021-10-20 | INMAR Builder & Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Lanao del Norte | 127005 | CONCEPCION ELEMENTARY SCHOOL | KAPATAGAN | 2 | 1 | 2 | Repair of Classrooms | 942043.8 | 1 |  | COMPLETED | 100% | 2022-01-26 |  | 2021-02- INFRA-Lot No. 2 |  |  |  | 2021-08-05 |  | 2021-10-20 | INMAR Builder & Enterprises | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Lanao del Norte | 501240 | Calube Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2 | 1 | 2 | Repair of Classrooms | 1601151 | 1 |  | COMPLETED | 100% | 2022-01-26 |  | 2021-02- INFRA-Lot No. 3 |  |  |  | 2021-08-05 |  | 2021-10-20 | Lanao Genesis Construction Supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Malaybalay City | 126575 | Baganao ES | CITY MALAYBALAY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1279959.15 | 1 |  | COMPLETED | 100% | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-19 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | For Punchlist Inspection | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Malaybalay City | 126535 | Balangbang ES | CITY MALAYBALAY (Capital) | 2 | 1 | 2 | Repair of Classrooms | 827616.47 | 1 |  | COMPLETED | 100% | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-18 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | Issued Punchlist Inspection Report for Final Inspection | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Malaybalay City | 126588 | Natid-asan ES | CITY MALAYBALAY (Capital) | 2 | 1 | 3 | Repair of Classrooms | 892424.38 | 1 |  | COMPLETED | 100% | 2022-09-30 |  | 002-INFRA-2021 | 002-INFRA-2021 | 2021-06-10 | 2021-06-20 | 2021-06-30 | 2021-07-26 | 2021-08-30 | X & C Building Construction | Issued Punchlist Inspection Report for Final Inspection | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Misamis Occidental | 127392 | Guintomoyan ES | JIMENEZ | 1 | 1 | 2 | Repair of Classrooms | 1164418.06 | 1 |  | COMPLETED | 100% |  |  | REPAIR 2021-RX-Misamis Occidental-001 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | KAYRO CONSTRUCTION & SUPPLY | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Misamis Occidental | 127356 | San Roque ES | CLARIN | 2 | 1 | 9 | Repair of Classrooms | 4449102.42 | 1 |  | COMPLETED | 100% |  |  | REPAIR 2021-RX-Misamis Occidental-002 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | ESL MILESTONE BUILDERS & SUPPLY, INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Misamis Occidental | 304046 | Nueva Vista National High School | DON VICTORIANO CHIONGBIAN | 2 | 1 | 4 | Repair of Classrooms | 2282577.48 | 1 |  | COMPLETED | 100% |  |  | REPAIR 2021-RX-Misamis Occidental-003 |  | July 1, 2021 | July 9, 2021 | July 21, 2021 | August 13, 2021 |  | ESL MILESTONE BUILDERS & SUPPLY, INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Misamis Oriental | 127764 | Quezon ES | GITAGUM | 2 | 1 | 3 | Repair of Classrooms | 1875615.35 | 1 |  | COMPLETED | 100% | [5 empty] | Aug 19,2021 | Aug 31,2021 | Sept 6,2021 | Sept 8,2021 | TriFB | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Misamis Oriental | 127711 | San Isidro ES | JASAAN | 2 | 1 | 4 | Repair of Classrooms | 2253427.64 | 1 |  | COMPLETED | 100% | [5 empty] | Aug 19,2021 | Aug 31,2021 | Sept 6,2021 | Sept 8,2021 | TriFB | [13 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region X | Oroquieta City | 127444 | Cosme Cagas Memorial School | OROQUIETA CITY (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1873870.36 | 1 |  | COMPLETED | 100% | 2021-11-07 |  | n/a |  | 2021-05-27 | June 16,2021 | 2021-06-28 | 2021-07-12 | 2021-08-09 | Kayro Construction & Supply | Variance is subject for Variation order & Additional Works | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Oroquieta City | 304052 | Senote NHS | OROQUIETA CITY (Capital) | 1 | 1 | 3 | Repair of Classrooms | 1200968.32 | 1 |  | COMPLETED | 100% | 2021-11-07 |  | n/a |  | 2021-05-27 | June 16,2021 | 2021-06-28 | 2021-07-12 | 2021-08-09 | Kayro Construction & Supply | Variance is subject for Variation order & Additional Works | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Ozamis City | 128197 | Juan A. Acapulco Elementary School | OZAMIS CITY | 2 | 1 | 7 | Repair of Classrooms | 3380610.6 | 1 |  | COMPLETED | 100% | 2021-11-27 |  | REPAIR2021-RX-OZAMIZCITY-001 | 092-INFRA2021-002 | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-23 | 2021-08-18 | JJFY Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Ozamis City | 304168 | Ozamiz City School of Arts and Trades | OZAMIS CITY | 2 | 1 | 1 | Rehabilitation of Library Hub Bldg. | 2616798.77 | 1 |  | COMPLETED | 100% | 2021-11-17 |  | REPAIR2021-RX-OZAMIZCITY-002 | 092-INFRA2021-003 | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-23 | 2021-08-18 | JJFY Construction Services | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Tangub City | 128231 | Salimpuno Elementary School | TANGUB CITY | 2 | 1 | 5 | Repair of Classrooms | 2542915.98 | 1 |  | COMPLETED | 100% | 2021-11-02 |  | REPAIR2021-RX-TANGUB CITY-001 |  | 2021-06-02 | 2021-06-10 | 2021-06-22 | 2021-07-04 | 2021-07-12 | ESL MILESTONE BUILDERS & SUPPLY, INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Tangub City | 128257 | Sumirap Central School | TANGUB CITY | 2 | 1 | 5 | Repair of Classrooms | 2536138.58 | 1 |  | COMPLETED | 100% | 2021-11-02 |  | REPAIR2021-RX-TANGUB CITY-002 |  | 2021-06-02 | 2021-06-10 | 2021-06-22 | 2021-07-04 | 2021-07-12 | ESL MILESTONE BUILDERS & SUPPLY, INC | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region X | Valencia City | 126850 | MAILAG CENTRAL SCHOOL | CITY OF VALENCIA | 4 | 1 | 8 | Repair of Classrooms | 5203482.82 | 1 |  | COMPLETED | 100% | 2021-11-25 |  |  |  | 2021-05-31 | 2021-06-08 | 2021-06-21 | 2021-06-23 | 2021-06-28 | White Beard Construction | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Compostela Valley | 128432 | Haguimitan ES | MONKAYO | 1 | 1 | 4 | Repair of Classrooms | 2397445.19 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Compostela Valley | 128358 | Pangi ES | MACO | 2 | 1 | 10 | Repair of Classrooms | 5102251.9 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129711 | A. Mabini Elementary School | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 495768.19 | 1 | 3872051.47 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms kitchen, handwashing facility and gym | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129707 | M. Roxas ES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 475510.91 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129645 | Maa CES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 805542.56 | 1 | 1703807.3 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms, handwashinf facility and gym | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129558 | Magallanes Elementary School | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 475510.91 | 1 | 2472841.95 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129701 | San Roque CES | DAVAO CITY | 1 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 374518.99 | 1 | 5602823.14 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classroom and Gym | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129652 | Alejandra L. Navarro Central Elementary School | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 738689.89 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129523 | Daniel M. Perez Central Elem. School SPED Center | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 875966.74 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129479 | Dona Asuncion Hizon ES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 615740.75 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129481 | F. Bustamante CES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 629174.66 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129592 | Malabog CES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 933530.71 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129513 | Teofilo Fernandez ES | DAVAO CITY | 2 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 614724.37 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129679 | Artemio Loyola Elementary School | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 490808.78 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129464 | Baguio Central Elementary School | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 499936.64 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129562 | Cabagbahangan Elementary School | DAVAO CITY | 3 | 1 | 6 | Repair of Classrooms | 5942117.4 | 1 |  | COMPLETED | 100% | Dec. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | MAG Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129548 | Don Juan Dela Cruz CES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 622078.65 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129566 | General Roxas CES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 995558.09 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129538 | Lt. C. Villafuerte, Sr. ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 470893.94 | 1 | 1584162.33 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | Repair of Classrooms | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129620 | Marilog Central ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 624178.98 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 615990.67 | 1 |  | COMPLETED | 100% | Nov. 26, 2021 | [5 empty] | June 30, 2021 |  | Sept. 27, 2021 | R. Fabale Construction Corporation | Waiting for Sub-aro | [12 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao City | 129743 | Tugbok Central ES SPED Center | DAVAO CITY | 3 | 1 | 1 | Repair of Classrooms/Conversion of Classroom to Dental Clinics | 339806.72 | 1 | 1735633.46 | COMPLETED | 100% | Nov. 26, 2021 |  |  |  | November 29- December 18, 2018 | December 6, 2018 | June 30, 2021 | February 18, 2019 | Sept. 27, 2021 | R. Fabale Construction Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 128593 | San Vicente ES | ASUNCION (SAUG) | 1 | 1 | 5 | Repair of Classrooms | 3476488.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 305508 | Ramon S. Segundo Sr. NHS | KAPALONG | 1 | 1 | 3 | Repair of Classrooms | 2001811.05 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128616 | Cabayangan ES | BRAULIO E. DUJALI | 2 | 1 | 8 | Repair of Classrooms | 6873708.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128625 | Anibongan Elementary School | CARMEN | 2 | 1 | 11 | Repair of Classrooms | 7908251.72 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Norte | 128642 | Tibulao ES | CARMEN | 2 | 1 | 9 | Repair of Classrooms | 6465576.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Norte | 128748 | Kimamon ES | SANTO TOMAS | 2 | 1 | 12 | Repair of Classrooms | 8145121.93 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Sur | 129020 | New Visayas ES | MATANAO | 0 | 1 | 15 | Repair of Classrooms | 6736564 | 1 |  | COMPLETED | 100% | April 03, 2022 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Del Sur | 129048 | Mariano Sarona ES | PADADA | 0 | 1 | 11 | Repair of Classrooms | 4940752 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao del Sur | 129095 | Melilla ES | SANTA CRUZ | 0 | 1 | 6 | Repair of Classrooms | 3027305.38 | 1 |  | COMPLETED | 100% | March 18, 2022 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128989 | Bito ES | MALITA | 0 | 1 | 7 | Repair of Classrooms | 3854247.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128996 | Lagumit ES | MALITA | 0 | 1 | 4 | Repair of Classrooms | 2126569.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 128964 | Mariano Calungsod Regis ES (Bolila ES) | MALITA | 0 | 1 | 6 | Repair of Classrooms | 3001616.31 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Occidental | 129124 | San Agustin ES | SANTA MARIA | 0 | 1 | 3 | Repair of Classrooms | 1174733.57 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129221 | Manorigao ES | CARAGA | 1 | 1 | 4 | Repair of Classrooms | 1993784.29 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129347 | Cudada Elementary School | MANAY | 1 | 1 | 4 | Repair of Classrooms | 2255626.86 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129457 | Ompao ES | TARRAGONA | 1 | 1 | 8 | Repair of Classrooms | 3422416.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129193 | T Patricio Elementary School | BANAYBANAY | 2 | 1 | 6 | Repair of Classrooms | 2745688.58 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Davao Oriental | 129282 | Crispin Dela Cruz ES | GOVERNOR GENEROSO | 2 | 1 | 6 | Repair of Classrooms | 2888898.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Digos City | 129762 | Aplaya ES | CITY OF DIGOS (Capital) | 1 | 1 | 10 | Repair of Classrooms | 2589770.65 | 1 |  | COMPLETED | 100% | 1/16/2022 |  |  |  | 6/3-23/2021 | 2021-11-06 | 6-23-2021 |  |  | Johnray Developer and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Digos City | 129773 | Apolandia ES | CITY OF DIGOS (Capital) | 1 | 1 | 4 | Repair of Classrooms | 1497687.25 | 1 |  | COMPLETED | 100% | 1/16/2022 |  |  |  | 6/3-23/2021 | 2021-11-06 | 6-23-2021 |  |  | Johnray Developer and supply | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128600 | Caliclic Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | Repair of Classrooms | 1201006.09 | 1 |  | COMPLETED | 100% | 11/14/2021 | [7 empty] | 08/25/2021 | R.Fabale Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128740 | Tagdaliao Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 6 | Repair of Classrooms | 3854976.55 | 1 |  | COMPLETED | 100% | 01/26/2022 | [7 empty] | 08/23/2021 | VGG Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128741 | Tagluno Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 4 | Repair of Classrooms | 3811228.62 | 1 |  | COMPLETED | 100% | 01/28/2022 | [7 empty] | 08/25/2021 | R.Fabale Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Island Garden City of Samal | 128742 | Tayapoc Elementary School | ISLAND GARDEN CITY OF SAMAL | 2 | 1 | 2 | Repair of Classrooms | 1242926.34 | 1 |  | COMPLETED | 100% | 2021-11-12 | [7 empty] | 08/23/2021 | VGG Const. Corp. | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Mati City | 129392 | Cabubuanan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 5 | Repair of Classrooms | 3143567.79 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129802 | Consolacion ES | CITY OF PANABO | 2 | 1 | 8 | Repair of Classrooms | 5181337.4 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 304407 | Manay National High School | CITY OF PANABO | 2 | 1 | 10 | Repair of Classrooms | 6191526.15 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129784 | Panabo Central Elementary School SPED Center | CITY OF PANABO | 2 | 1 | 21 | Repair of Classrooms | 12733272.03 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Panabo City | 129788 | San Vicente ES | CITY OF PANABO | 2 | 1 | 8 | Repair of Classrooms | 4464790.83 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XI | Tagum City | 128789 | CABUGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1 | 1 | 8 | Repair of Classrooms | 3648846 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | General Santos City | 131301 | Daan Banwang Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | Repair of classrooms | 2953865.29 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | General Santos City | 210002 | Ignacio D. Solis Sr. Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 7 | Repair of classrooms | 3737537.94 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | Kidapawan City | 131345 | Luvimin Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 5 | Repair of classrooms | 3825479.86 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Koronadal City | 131386 | Supon ES | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | Repair of classrooms | 3000000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130040 | Cabpangi ES | LIBUNGAN | 1 | 1 | 4 | Repair of classrooms | 1890510.44 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130034 | Sinapangan ES | LIBUNGAN | 1 | 1 | 2 | Repair of classrooms | 1257607.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130042 | Wendelin Eduarte ES (Gumaga ES) | LIBUNGAN | 1 | 1 | 2 | Repair of classrooms | 912542.29 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130177 | Patindeguen ES | MIDSAYAP | 1 | 1 | 2 | Repair of classrooms | 912405.23 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130047 | AMABIL ELEMENTARY SCHOOL | MAGPET | 2 | 1 | 2 | Repair of classrooms | 1597235.09 | 1 |  | COMPLETED | 100% | 2022-12-31 | [22 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2 | 1 | 4 | Repair of classrooms | 1735541.5 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130124 | Sinkatulan ES | MAKILALA | 2 | 1 | 4 | Repair of classrooms | 1996026.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130370 | Dona Concordia B. Jayme CES | PRESIDENT ROXAS | 2 | 1 | 7 | Repair of classrooms | 2714581.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130371 | Egmedio Fernando ES (Jose Tuburan Sr.) | PRESIDENT ROXAS | 2 | 1 | 4 | Repair of classrooms | 2308535.18 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 129970 | New Bentangan PS | CARMEN | 3 | 1 | 2 | Repair of classrooms | 1333787.66 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130000 | Katidtuan Central Elementary School | KABACAN | 3 | 1 | 2 | Repair of classrooms | 912542.29 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130126 | Bangbang ES | MATALAM | 3 | 1 | 3 | Repair of classrooms | 1905715.99 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130241 | Langkong ES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 1948106.67 | 1 |  | COMPLETED | 100% | 2022-11-30 | [22 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130225 | Luz Village ES | M'LANG | 3 | 1 | 2 | Repair of classrooms | 1240283.71 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130233 | Pulanglupa ES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 1757826.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130404 | Damawato ES | TULUNAN | 3 | 1 | 2 | Repair of classrooms | 1258441.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130414 | New Culasi ES | TULUNAN | 3 | 1 | 2 | Repair of classrooms | 1221407.11 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 500283 | Hadji Musa IS | GLAN | 0 | 1 | 8 | Repair of classrooms | 7449381.88 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 304523 | Colon NHS | MAASIM | 0 | 1 | 36 | Repair of classrooms | 5797443.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 130586 | Balacayo ES | MALUNGON | 0 | 1 | 7 | Repair of classrooms | 6090886.77 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON | 0 | 1 | 10 | Repair of classrooms | 6806323.35 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 316603 | Malungon Gamay National High School | MALUNGON | 0 | 1 | 14 | Repair of classrooms | 1591195.09 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 500825 | Panamin IS | MALUNGON | 0 | 1 | 6 | Repair of classrooms | 5615613.46 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | South Cotabato | 130700 | Esperanza ES | NORALA | 2 | 1 | 10 | Repair of classrooms | 4346436.44 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | South Cotabato | 130782 | Shri- Visaya ES | SURALLAH | 2 | 1 | 7 | Repair of classrooms | 2964223.54 | 1 |  | COMPLETED | 100% | 2022-09-30 | [22 empty] | 100% |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | Sultan Kudarat | 131206 | Bannawag Elementary School | Pres. Quirino | 1 | 1 | 12 | Repair of classrooms | 6930227.21 | 1 | 4771656.5 | COMPLETED | 100% | Mar. 17, 2022 | Mar. 14, 2022 | 2021-05-008-Lot 1 | 2021-05-008 | Jul. 23, 2021 | Jul. 30, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Oct. 05, 2021 | John Ray Developer & Supplies | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sultan Kudarat | 130913 | Dorin Elementary School | Bagumbayan | 2 | 1 | 5 | Repair of classrooms | 3103050.23 | 1 | 2271179.12 | COMPLETED | 100% | Feb. 22, 2022 | Jan. 20, 2022 | 2021-05-008-Lot 2 | 2021-05-009 | Jul. 23, 2021 | Jul. 30, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Oct. 05, 2021 | Cofejok Construction & Supply Corporation | [13 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Tacurong City | 131221 | Abang Suizo ES | CITY OF TACURONG | 1 | 1 | 9 | Repair of Classrooms | 4372530.33 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | CAR | Abra | 134997 | Lublubnac PS | BUCAY | 0 | 1 | 3 | Repair of Classrooms | 2376540.7 | 1 | 1237086.8 | COMPLETED | 100% | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135176 | Cabaruyan ES | DAGUIOMAN | 0 | 1 | 5 | Repair of Classrooms | 3218586.75 | 1 | 2372519.51 | COMPLETED | 100% | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135021 | Mudiit ES | DOLORES | 0 | 1 | 8 | Repair of Classrooms | 4691995.62 | 1 | 3213851.29 | COMPLETED | 100% | 2023-01-07 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135040 | Pidipid ES | LA PAZ | 0 | 1 | 8 | Repair of Classrooms | 6190268.74 | 1 | 2585702.69 | COMPLETED | 100% | 2022-10-29 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | 13 | Repair of Classrooms | 10200503.12 | 1 | 4687393.27 | COMPLETED | 100% | 2022-11-28 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135104 | Lul-luno ES | LUBA | 0 | 1 | 4 | Repair of Classrooms | 3883217.7 | 1 | 6182717.4 | COMPLETED | 100% | 2022-12-28 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135009 | Sto. Tomas Barrio School | MANABO | 0 | 1 | 3 | Repair of Classrooms | 2589323.21 | 1 | 10195730.6 | COMPLETED | 100% | 2023-03-08 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 218517 | Banay PS | PIDIGAN | 0 | 1 | 3 | Repair of Classrooms | 2613153.97 | 1 | 3876538.09 | COMPLETED | 100% | 2022-12-08 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135177 | Callaban PS | SALLAPADAN | 0 | 1 | 1 | Repair of Classroom | 1240563.12 | 1 | 2606198.18 | COMPLETED | 100% | 2022-12-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 218511 | Pantoc ES | SAN QUINTIN | 0 | 1 | 4 | Repair of Classrooms | 3514287.7 | 1 | 3508272.06 | COMPLETED | 100% | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135014 | Bumagcat ES | TAYUM | 0 | 1 | 9 | Repair of Classrooms | 6211798.89 | 1 | 6205959.86 | COMPLETED | 100% | 2023-02-06 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135259 | Conner Central School | CONNER | 0 | 1 | 11 | Repair of Classrooms | 6662077.48 | 2 | 6328972.67 | COMPLETED | 100% | 2023-05-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | Bangyan 3D construction | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135266 | Karikitan ES | CONNER | 0 | 1 | 9 | Repair of Classrooms | 5846627.59 | 2 | 5554217.88 | COMPLETED | 100% | 2023-05-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | Bangyan 3D construction | [13 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | 10 | Repair of Classrooms | 3617786.15 | 2 | 3613888.57 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | For Punchlist | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 | 1 | 9 | Repair of Classrooms | 965067.74 | 2 | 963942.97 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | For Punchlist | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305107 | Apayao Science High Shool | LUNA | 0 | 1 | 18 | Repair of Classrooms | 4643093.95 | 2 | 4367761.94 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  | 45017 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135333 | Capagaypayan Primary School | LUNA | 0 | 1 | 2 | Repair of Classrooms | 1643773.83 | 2 | 1641935.01 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | 3 | Repair of Classrooms | 2120307.68 | 2 | 1944680.34 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135351 | Cacalaggan Elementary School | PUDTOL | 0 | 1 | 5 | Repair of Classrooms | 1516808.92 | 2 | 1514879.48 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 319009 | Tawit National High School | PUDTOL | 0 | 1 | 4 | Repair of Classrooms | 753644.59 | 2 | 751772.39 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305120 | MAYOR GUILLERMO BARSATAN MEMORIAL SCHOOL OF ARTS AND TRADE | SANTA MARCELA | 0 | 1 | 9 | Repair of Classrooms | 949317.74 | 2 | 947405.47 | COMPLETED | 100% | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Benguet | 135679 | Palali ES | SABLAN | 0 | 1 | 5 | Repair of Classrooms | 1672223.81 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Benguet | 135719 | Ambongdolan ES | TUBLAY | 0 | 1 | 6 | Repair of Classrooms | 4024447.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Ifugao | 135804 | Panubtuban ES | ASIPULO | 0 | 1 | 5 | Repair of Classrooms | 3263177 | 1 |  | COMPLETED | 100% | 2023-04-09 | [22 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Ifugao | 135834 | Bitu ES | HINGYON | 0 | 1 | 2 | Repair of Classrooms | 1672223.05 | 1 | 1667139.14 | COMPLETED | 100% | 2022-11-21 | Sept.29, 2022 | [21 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Kalinga | 220513 | Balinciagao ES - Limood Annex | PASIL | 0 | 1 | 3 | Repair of Classrooms | 1831297.95 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Kalinga | 136025 | Galdang Elementary School | PASIL | 0 | 1 | 2 | Repair of Classrooms | 1350608.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | BARLIG | 0 | 1 | 4 | Repair of Classrooms | 2651588.44 | 1 | 2572040.79 | COMPLETED | 100% | 2022-10-02 |  | INF-2022 R-001 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136247 | Suquib Primary School | BESAO | 0 | 1 | 2 | Repair of Classrooms | 1590953 | 1 | 1590953 | COMPLETED | 100% | 2022-09-19 | 2022-09-15 | INF-2022 R-002 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | 0 | 1 | 2 | Repair of Classrooms | 2121270.75 | 1 | 1824355.38 | COMPLETED | 100% | 2022-10-02 |  | INF-2022 R-003 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | ZYMX CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136332 | Anabel Elementary School | SADANGA | 0 | 1 | 1 | Repair of Classroom | 1060635 | 1 | 1049964.94 | COMPLETED | 100% | 2022-09-24 | 2022-09-20 | INF-2022 R-004 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136341 | Aguid Elementary School | SAGADA | 0 | 1 | 4 | Repair of Classrooms | 2651588 | 1 | 2598556.24 | COMPLETED | 100% | 2022-10-02 | 2022-09-15 | INF-2022 R-005 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Tabuk City | 136100 | Lacnog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 1615715.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 3 | Repair of Classrooms | 2221709.46 | 1 |  | COMPLETED | 100% |  |  | REPAIR 2022 - R XIII - AGUSAN DEL NORTE - 009 | REPAIR 2022 - R XIII - AGUSAN DEL NORTE - 009 | April 13, 2022 | April 22, 2022 | May 4, 2022 | June 11, 2022 | June 27, 2022 | BN Builders and Construction Supplies | [13 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Dinagat Island | 132395 | Cayetano Elementary School | DINAGAT | 0 | 1 | 3 | Repair of Classrooms | 2339173.98 | 2 |  | COMPLETED | 100% |  |  |  |  | 2022-08-16 | [18 empty] | 100% |  | 45017 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Dinagat Island | 132400 | New Mabuhay Elementary School | DINAGAT | 0 | 1 | 2 | Repair of Classrooms | 806296.12 | 2 |  | COMPLETED | 100% |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE) | [12 empty] | 100% |  | 45017 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Dinagat Island | 132312 | Llamera Elementary School | LIBJO (ALBOR) | 0 | 1 | 3 | Repair of Classrooms | 2251076.69 | 2 |  | COMPLETED | 100% |  |  |  |  | 2022-08-16 | [18 empty] | 100% |  | 45017 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 2 | Repair of Classrooms | 1000431.64 | 2 |  | COMPLETED | 100% |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE) | [12 empty] | 100% |  | 45017 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Dinagat Island | 132557 | Roxas Elementary School | TUBAJON | 0 | 1 | 2 | Repair of Classrooms | 1574058.26 | 2 |  | COMPLETED | 100% |  |  |  |  | 2022-08-16 | [5 empty] | DUE TO BAD WEATHER (ROUGH SEA AND SHEAR LINE) | [12 empty] | 100% |  | 45017 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1 | 1 | 5 | Repair of Classrooms | 2668177 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132163 | Bagacay Elementary School | DEL CARMEN | 1 | 1 | 1 | Repair of Classroom | 595000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132155 | Magsaysay Elementary School | GENERAL LUNA | 1 | 1 | 2 | Repair of Classrooms | 1385177 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132157 | Mam-on Primary school | GENERAL LUNA | 1 | 1 | 1 | Repair of Classroom | 630000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 1 | 1 | 2 | Repair of Classrooms | 1248000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132186 | Katipunan Elementary School | PILAR | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR | 1 | 1 | 6 | Repair of Classrooms | 1987906 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 2 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132200 | San Miguel Primary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 597000 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132202 | Sto. Nino Elementary School | SAN ISIDRO | 1 | 1 | 1 | Repair of Classroom | 2677422.17 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132206 | Alegria Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 5 | Repair of Classrooms | 2586906 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Siargao | 132212 | Rizal Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | Repair of Classroom | 595000.01 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2 | 1 | 3 | Repair of Classrooms | 2206679.8 | 1 |  | COMPLETED | 100% | 2022-09-30 |  | 001-BEFF 2022-Caraga | 004-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | DRANLIVE CONSTRUCTION | [13 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132344 | Cabugao ES | BACUAG | 2 | 1 | 5 | Repair of Classrooms | 3188794.34 | 1 |  | COMPLETED | 100% | 2022-09-23 |  | 002-BEFF 2022-Caraga | 007-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | RADIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2 | 1 | 6 | Repair of Classrooms | 3801772.6 | 1 |  | COMPLETED | 100% | 2022-10-13 | 2022-07-25 | 003-BEFF 2022-Caraga | 003-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | BAMBOE CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132339 | Macopa ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | Repair of Classrooms | 1063102.26 | 1 |  | COMPLETED | 100% | 2022-08-10 | 2022-06-14 | 004-BEFF 2022-Caraga | 002-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132527 | DE CASTRO ELEMENTARY SCHOOL | SISON | 2 | 1 | 4 | Repair of Classrooms | 2852624.19 | 1 |  | COMPLETED | 100% | 2022-10-24 |  | 005-BEFF 2022-Caraga | 014-2022 | 2022-04-06 | 2022-04-13 | 2022-04-25 | 2022-05-02 | 2022-06-16 | PAROPA CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 4 | Repair of Classrooms | 2738357.76 | 1 |  | COMPLETED | 100% | 2022-09-23 |  | 006-BEFF 2022-Caraga | 005-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | RADIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2 | 1 | 3 | Repair of Classrooms | 2125409.8 | 1 |  | COMPLETED | 100% | 2022-08-24 | 2022-07-25 | 007-BEFF 2022-Caraga | 006-2022 | 2022-02-15 | 2022-02-22 | 2022-03-08 | 2022-03-16 | 2022-05-26 | WINDFALL CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS | 1 | 1 | 3 | Repair of Classrooms | 2562384.81 | 1 |  | COMPLETED | 100% |  |  | Repair 2022 - Surigao del Sur 001 |  | March 03, 2022 | March 11, 2022 | March 23, 2022 | April 18, 2022 | N/A | Trident Engineering Services | Received Sub ARO last August 08, 2022 | [12 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 3 | Repair of Classrooms | 1060794.6 | 1 | 972916.7355 | COMPLETED | 100% | October 2022 |  | PB-002-2022-1 |  | 11 13 2019 | 11 21 2019 | 2022-09-03 | 12 13 2019 | 2020-12-10 | ELOCIN CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1 | 1 | 2 | Repair of Classrooms | 1319836.02 | 1 | 917631.5568 | COMPLETED | 100% | October 2022 |  | PB-002-2022-3 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Norte | 100233 | Virbira-Angset ES | CARASI | 1 | 1 | 2 | Repair of Classrooms | 1147833.65 | 1 | 1121874.05 | COMPLETED | 100% | October 2022 |  | PB-002-2022-4 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Norte | 100055 | San Isidro Elementary School | DUMALNEG | 1 | 1 | 3 | Repair of Classrooms | 1090731.29 | 1 | 1020136.54 | COMPLETED | 100% | October 2022 |  | PB-002-2022-2 |  |  |  | 2022-09-03 |  |  | ELOCIN CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 100616 | San Sebastian Elementary School | SAN VICENTE | 1 | 1 | 6 | Repair of Classrooms | 2202603.9 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 100659 | Cabuloan ES | SANTA CATALINA | 1 | 1 | 6 | Repair of Classrooms | 2732823.02 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 100345 | Tangilig ES | SUGPON | 1 | 1 | 3 | Repair of Classrooms | 1749456.98 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MRK-Square Construction & Supply | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 300054 | Lidlidda National High School | LIDLIDDA | 2 | 1 | 4 | Repair of Classrooms | 1936258.06 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 100539 | Lapting ES | NAGBUKEL | 2 | 1 | 5 | Repair of Classrooms | 1610201.01 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | MA Tejada Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 100386 | Ansad ES | SAN ESTEBAN | 2 | 1 | 2 | Repair of Classrooms | 1181156.93 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | Cleofel Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Ilocos Sur | 300079 | Sigay National High School | SIGAY | 2 | 1 | 3 | Repair of Classrooms | 1324194.15 | 1 |  | COMPLETED | 100% |  |  | 8656850 |  | 2022-05-11 | 2022-05-18 | 2022-05-31 | 2022-06-08 |  | Maple Leaf Engineering & Construction | For award. Waiting for release of Sub-ARO | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | La Union | 100858 | Alibangsay ES | BAGULIN | 2 | 1 | 5 | Repair of Classrooms | 1932199.32 | 1 | 1562163.94 | COMPLETED | 100% | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | LAV CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | La Union | 100938 | Tumapoc ES | BURGOS | 2 | 1 | 4 | Repair of Classrooms | 2110104.53 | 1 | 1809225.65 | COMPLETED | 100% | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | LAV CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | La Union | 500601 | Saytan Integrated School | PUGO | 2 | 1 | 11 | Repair of Classrooms | 5923501.12 | 1 | 5880521.45 | COMPLETED | 100% | 2022-09-08 |  |  |  | 2022-03-15 | 2022-03-23 | 2022-04-04 | 2022-04-12 | 2022-06-10 | EE MADAYAG CONSTRUCTION | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101400 | Anapao ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 394061.1 | 2 | 362840.2972 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Chestinan Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | previous yrs | 1 | 3 | 1990825.78 | CY 2022 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 1198077.02 | 2 | 1108514.0994 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Chestinan Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 10 | 6425000 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 1055914.95 | 2 | 532489.6849 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 13 | 8532813.69 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101402 | Cabaruan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 469196.065 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 4 | 2536000 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 405792.7316 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 3 | 2272014.38 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101404 | Concordia ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 582072.66 | 2 | 274245.6633 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 4 | 2773000 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101405 | Don Antonio Bonilla ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 394061.1 | 2 | 309879.845 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 2 | 1556295.47 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 319291.31 | 2 | 767911.13 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 2 | 1351977.28 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 931312.42 | 2 | 661243.7004 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 3 | 2273420.08 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101408 | Ilio-Ilio ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 960761.74 | 2 | 469196.065 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 5 | 3219840.17 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 469196.065 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | MCB Construction and Supply | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 8 | 5328631.81 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 535606.41 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 11.23 | 1 | 6 | 4061840.17 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101410 | Poguruac ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 673465.52 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 10.23 | 1 | 6 | 4043416.72 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 582072.66 | 2 | 610730.25 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 10.23 | 1 | 3 | 2225356.1 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 771100.79 | 2 | 1052773.81 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 10.23 | 1 | 6 | 3889245.87 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101413 | Sapa Pequeña ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 676606.66 | 2 | 767959.65 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 10.23 | 1 | 4 | 2683075.01 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101414 | Tambacan ES | BURGOS | 1 | 1 | 0 | Repair of Classrooms & Fence | 613871.39 | 2 | 767959.65 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | JFM Altitude Construction Corporation | with approved project modification change amount and scope of works | [12 empty] | 100% |  | 45017 | 10.23 | 1 | 3 | 1724000 | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101224 | Ambabaay ES | BANI | 1st | 1 | 3 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1390688.55 | 2 | 2808327.51 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Chestinan Construction Corporation | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101243 | Ranao ES | BANI | 1st | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 2828502.8 | 2 | 1358135.87 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | CLP Builders | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | 1 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1055914.95 | 2 | 1050888.88 | COMPLETED | 100% | 2023-12-14 |  | 2023-04-011-INFRA |  |  | 2023-07-12 | 2023-07-24 | 2023-08-15 | 2023-08-17 | JFM Altitude Construction Corporation | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101326 | Calit ES | BINMALEY | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 3964910.11 | COMPLETED | 100% | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-07-05 | 2023-07-07 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 11 | Repair of Classrooms & Fence (Additional fromProject Modification) | 5099191.35 | 2 | 3136173.02 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101503 | BALOCOC ELEMENTARY SCHOOL | LINGAYEN (Capital) | 2nd | 1 | 5 | Repair of Classrooms & Fence (Additional fromProject Modification) | 2317814.24 | 2 | 1868152.4779 | COMPLETED | 100% | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-26 | 2023-07-07 | ABC East Multi Builders and Traders | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 300211 | Lasip NHS | LINGAYEN (Capital) | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 2744062.88 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Mitzie Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101484 | Magsaysay ES | LINGAYEN (Capital) | 2nd | 1 | 2 | Repair of Classrooms & Fence (Additional fromProject Modification) | 301821.02 | 2 | 243266.2968 | COMPLETED | 100% | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-26 | 2023-07-07 | ABC East Multi Builders and Traders | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4635628.5 | 2 | 3697907.44 | COMPLETED | 100% | 2023-11-03 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101689 | Don Pio B. Palisoc ES | URBIZTONDO | 2nd | 1 | 5 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1767814.25 | 2 | 1752722.49 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Elmuel Jay Trading and Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101284 | Amancosiling Elementary School | BAYAMBANG | 3rd | 1 | 4 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1854251.4 | 2 | 3025618.07 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | TG Ocampo Construction and Surveying Services | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101263 | Ataynan ES | BAYAMBANG | 3rd | 1 | 10 | Repair of Classrooms & Fence (Additional fromProject Modification) | 4035628.5 | 2 | 1427693.78 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | Macco Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101288 | Carungay ES | BAYAMBANG | 3rd | 1 | 4 | Repair of Classrooms & Fence (Additional fromProject Modification) | 1854251.4 | 2 | 1848082.31 | COMPLETED | 100% | 2023-12-13 |  | 2023-04-011-INFRA |  |  | 2023-07-12 | 2023-07-24 | 2023-08-14 | 2023-08-16 | Szcon Builders Inc. | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101542 | Lokeb Este ES | MALASIQUI | 3rd | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3228502.8 | 2 | 3144928.81 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-22 | 2023-06-26 | ASS Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101549 | Payar-Gomez ES | MALASIQUI | 3rd | 1 | 9 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3165757.61 | 2 | 2420668.29 | COMPLETED | 100% | 2023-10-18 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | TG Ocampo Construction and Surveying Services | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan I, Lingayen | 101625 | Primicias Elementary School | MAPANDAN | 3rd | 1 | 8 | Repair of Classrooms & Fence (Additional fromProject Modification) | 3228502.8 | 2 | 2220224.26 | COMPLETED | 100% | 2023-10-23 |  | 2023-04-011-INFRA |  | 2023-04-20 | 2023-04-28 | 2023-05-15 | 2023-06-19 | 2023-06-21 | Mitzie Construction | additional; with approved project modification change amount and scope of works | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5 | 1 | 2 | Repair of Classrooms | 1060635.37 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 15 | Repair of Classrooms | 10000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 101735 | Mauban ES | BALUNGAO | 6 | 1 | 5 | Repair of Classrooms | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 101879 | Guiling-Coliling ES | ROSALES | 6 | 1 | 5 | Repair of Classrooms | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | Pangasinan II, Binalonan | 102139 | Severo L. Castulo Elementary School | SAN QUINTIN | 6 | 1 | 6 | Repair of Classrooms | 4000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region I | San Fernando City | 101035 | Sevilla Elementary School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 6 | Repair of Classrooms | 3201867.35 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | 0 | 1 | 6 | Repair of Classrooms | 3487110.41 | 1 | 2950000 | COMPLETED | 100% | [10 empty] | SARO received last August 8, 2022 | [12 empty] | 100% |  | 44986 | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Batanes | 102328 | Sabtang Central School | SABTANG | 0 | 1 | 7 | Repair of Classrooms | 2539099.16 | 1 | 2100000 | COMPLETED | 100% | [9 empty] | KNB Construction | SARO received last August 8, 2022. Waiting for the Variation Order. | [12 empty] | 100% |  | 44986 | 5.24 |  |  |  |  | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102838 | Illuru ES | RIZAL | 2 | 1 | 3 | Repair of Classrooms | 1001370.08 | 1 | 0 | COMPLETED | 100% | 2023-01-20 | 2022-11-18 | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1277209.13 | 1 | 0 | COMPLETED | 100% | 2023-01-20 | 2023-01-27 | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2 | 1 | 7 | Repair of Classrooms | 1433625.6 | 1 | 0 | COMPLETED | 100% | 2023-01-20 |  | REPAIR 2022-RII-CAGAYAN-001 | INFRA 2022-068 LOT 1 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103344 | Guibang Elementary School | GAMU | 2 | 1 | 12 | Repair of Classrooms | 4911086.63 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300565 | Palayan Region High School | ALICIA | 3 | 1 | 17 | Repair of Classrooms | 6381474.7 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103052 | Angadanan Central School | ANGADANAN | 3 | 1 | 6 | Repair of Classrooms | 3073731.89 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103067 | San Ambrocio Elementary School | ANGADANAN | 3 | 1 | 2 | Repair of Classrooms | 1611819.42 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300502 | Villa Domingo National High School | ANGADANAN | 3 | 1 | 9 | Repair of Classrooms | 2242253.51 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5 | 1 | 2 | Repair of Classrooms | 700749.68 | 1 | 0 | COMPLETED | 100% |  |  |  | 44715 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 500970 | Sto. Domingo-San Isidro Integrated School | LUNA | 5 | 1 | 6 | Repair of Classrooms | 3224814.73 | 1 | 0 | COMPLETED | 100% |  |  |  | 44715 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103719 | San Manuel Central School | SAN MANUEL | 5 | 1 | 14 | Repair of Classrooms | 8222849.33 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 5.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103334 | Gucab Elementary School | ECHAGUE | 6 | 1 | 10 | Repair of Classrooms | 2957750.54 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 300590 | San Guillermo Vocational & Industrial High School | SAN GUILLERMO | 6 | 1 | 14 | Repair of Classrooms | 5899546.51 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6 | 1 | 5 | Repair of Classrooms | 1676883.48 | 1 | 0 | COMPLETED | 100% |  |  |  | 44714 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103708 | Dona Paulina Elementary School | SAN ISIDRO | 6 | 1 | 1 | Repair of Classroom | 856701.71 | 2 | 1234173.09 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 6 | 1 | 12 | Repair of Classrooms | 3015522.35 | 2 | 1604724.29 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6 | 1 | 4 | Repair of Classrooms | 1544709.37 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6 | 1 | 14 | Repair of Classrooms | 2854123.08 | 2 | 0 | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6 | 1 | 4 | Repair of Classrooms | 1076711.08 | 1 | 0 | COMPLETED | 100% |  |  |  | 44714 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | Arevalo Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Nueva Vizcaya | 281559 | Hukhukyung Primary School | AMBAGUIO | 0 | 1 | 2 | Repair of Classrooms | 1590953 | 1 | 1351108.85 | COMPLETED | 100% | 2023-02-21 |  | PB10-01-CY2022 BEFF-RoC-Infra-Lot 1 |  | 2020-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-19 | 2022-12-19 | Mighty Construction | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Nueva Vizcaya | 104221 | Turod Elementary School | VILLAVERDE | 0 | 1 | 3 | Repair of Classrooms | 1672224 | 1 | 1412362.55 | COMPLETED | 100% | 2023-03-30 |  | PB10-01-CY2022 BEFF-RoC-Infra-Lot 2 |  | 2020-10-26 | 2022-11-03 | 2022-11-15 | 2022-12-01 | 2022-12-16 | I.A. Castaneda Construction & Supply | [13 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104373 | Dibul ES | SAGUDAY | 0 | 1 | 2 | Repair of Classrooms | 186296.13 | 2 | 186296.13 | COMPLETED | 100% | [7 empty] | 2022-09-09 | 2022-10-17 | FNS Builders & Enterprise | Completed | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104381 | Lumagui ES | SAGUDAY | 0 | 1 | 4 | Repair of Classrooms & Toilets | 974789.14 | 1 | 842413.23 | COMPLETED | 100% |  |  |  |  | 2022-04-28 | 2022-05-05 | 2022-05-23 | 2022-06-15 | 2022-08-26 | FNS Builders & Enterprise | Completed | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region II | Quirino | 104376 | Magsaysay ES | SAGUDAY | 0 | 1 | 12 | Repair of Classrooms | 1226272.55 | 1 | 1155941.97 | COMPLETED | 100% |  |  |  |  | 2022-04-28 | 2022-05-05 | 2022-05-23 | 2022-06-15 | 2022-08-26 | FNS Builders & Enterprise | Completed | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 501022 | Don Ambrocio Mendiola ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1650000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107027 | Dr. Clemente N. Dayrit Sr. Elem. School | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 1500000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2750000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107051 | Virgen Delos Remedios Elementary School | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 2100000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104610 | Hermosa ES | HERMOSA | 1 | 1 | 7 | Repair of Classrooms & Toilet | 3587274.66 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104661 | Kaparangan ES | ORANI | 1 | 1 | 3 | Repair of Classrooms & Toilet | 1888335.16 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104700 | Adamson ES | SAMAL | 1 | 1 | 5 | Repair of Classrooms & Toilet | 3597965.23 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104573 | Daang Bago ES | DINALUPIHAN | 3 | 1 | 5 | Repair of Classrooms & Toilet | 3788120.23 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107095 | Bakero Elementary School | CABANATUAN CITY | 3 | 1 | 3 | Repair of Classrooms | 1435845.59 | 2 | 1435845.59 | COMPLETED | 100% | 2022-12-20 | 2022-12-06 | N/A | 08-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | RC Pallarca Construction | N/A | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107109 | Cabanatuan North ES | CABANATUAN CITY | 3 | 1 | 8 | Repair of Classrooms | 3246291.99 | 2 | 3246291.99 | COMPLETED | 100% | 2023-01-19 | 2023-01-04 | N/A | 09-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | R.B. Valera Construction | N/A | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107116 | Sumacab ES | CABANATUAN CITY | 3 | 1 | 12 | Repair of Classrooms | 8318700.46 | 2 | 8318700.46 | COMPLETED | 100% | 2023-01-19 | 2022-12-19 | N/A | 10-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | Marvelous Quejada Construction | with approved project modification; change of number of classrooms from 14 to 12 | [12 empty] | 100% |  | 45017 | 3.23 | 1 | 14 | 8318700.46 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105337 | Parcutela ES | CITY OF GAPAN | 4 | 1 | 3 | Repair of Classrooms | 1475367.24 | 2 | 2779344.7 | COMPLETED | 100% | 2021-10-03 | 2021-09-13 | 2021-05-31-001-CL-Repair | 2021-05-31-001-CL-Repair | 2021-06-01 | 2021-06-08 | 2021-06-21 | 2021-06-28 | 2021-07-05 | Joynieltin Construction and Trading | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105328 | Puting Tubig ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 2696212.29 | 2 | 1474689.14 | COMPLETED | 100% | 2023-01-08 | 2022-11-24 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 229001 | Sapang Kawayan ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 3085558.94 | 2 | 2691143.44 | COMPLETED | 100% | 2023-01-08 | 2022-12-01 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105331 | Velcar ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 2742861.53 | 2 | 3082063.66 | COMPLETED | 100% | 2023-01-08 | 2022-12-01 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Mabalacat City | 106089 | Villa Teodora ES | MABALACAT CITY | 1 | 1 | 5 | Repair of Classrooms | 2111541.18 | 2 | 2101009.15 | COMPLETED | 100% | 2023-01-08 | 2022-12-07 |  |  | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | RAS2 Construction | [13 empty] | 100% |  | 45017 | 8.23 | 1 | 18 | 2111541.18 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 105537 | Licaong ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 9 | Repair of Classrooms | 1583079.96 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 500397 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 1998270.3 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 300824 | Munoz National HS-Main | SCIENCE CITY OF MUÑOZ | 2 | 1 | 8 | Repair of Classrooms | 4085861.56 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 9.23 | 2 | 8 | 4085861.56 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 105565 | Villa Santos Elementary School | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2054270.2 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA | 1 | 1 | 28 | Repair of Classrooms & Toilet | 14000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105571 | Monic ES | NAMPICUAN | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2120339.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105509 | San Vicente ES | LLANERA | 2 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105521 | Lupao Central School | LUPAO | 2 | 1 | 10 | Repair of Classrooms & Toilet | 5000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105599 | Kalayaan ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms & Toilet | 2000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105207 | E. Gotangco ES (Larcon ES) | BONGABON | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105308 | Gabaldon South ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 7 | Repair of Classrooms & Toilet | 3500000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105357 | Panacsac ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 5 | Repair of Classrooms & Toilet | 2500000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105470 | San Felipe ES | LAUR | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105753 | Malacanang Centro ES | SANTA ROSA | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105223 | San Carlos ES | CABIAO | 4 | 1 | 4 | Repair of Classrooms & Toilet | 2000000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105374 | Sibug ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms & Toilet | 1500000 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105448 | Pinanggaan ES | JAEN | 4 | 1 | 3 | Repair of Classrooms & Toilet | 1500000 | 2 | 5494658.89 | COMPLETED | 100% | 2023-02-28 | 2023-02-28 | 2022-10-275 Lot 3 | 2022-10-275 Lot 3 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | Kevin Paul Construction | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105612 | Kapt. Pedro Villanueva Elementary School | PEÑARANDA | 4 | 1 | 11 | Repair of Classrooms & Toilet | 5500000 | 2 | 1644967.35 | COMPLETED | 100% | 2023-02-28 | 2023-01-12 | 2022-10-275 Lot 1 | 2022-10-275 Lot 1 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | Mitzie Construction | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105686 | Pulo Elementary School | SAN ISIDRO | 4 | 1 | 7 | Repair of Classrooms & Toilet | 3500000 | 2 | 2739018.17 | COMPLETED | 100% | 2023-02-28 | 2023-02-03 | 2022-10-275 Lot 2 | 2022-10-275 Lot 2 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | J.I. Viacrusis Construction | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105738 | Mambangnan ES | SAN LEONARDO | 4 | 1 | 10 | Repair of Classrooms & Toilet | 5000000 | 2 | 1532289.94 | COMPLETED | 100% | 2022-12-22 | 2022-11-11 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | M.P. LINGAT CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 107138 | Ilalim ES | OLONGAPO CITY | 1 | 1 | 10 | Repair of Classrooms | 5500000 | 2 | 2267286.46 | COMPLETED | 100% | 2023-01-06 | 2022-11-21 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | P.V.B. CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 107128 | Mabayuan Elementary School | OLONGAPO CITY | 1 | 1 | 3 | Repair of Classrooms | 1650000 | 2 | 2371346.34 | COMPLETED | 100% | 2023-01-06 | 2022-11-17 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 500756 | Old Cabalan Integrated School | OLONGAPO CITY | 1 | 1 | 5 | Repair of Classrooms | 2750000 | 2 | 1459363.16 | COMPLETED | 100% | 2022-12-22 | 2022-11-04 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | RAS2 CONSTRUCTION | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106125 | Navaling ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1540552.88 | 2 | 2477090.29 | COMPLETED | 100% | 2023-01-06 | 2022-11-11 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | E.B. MATIAS CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106127 | San Agustin ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2277786.41 | 2 | 1174757.49 | COMPLETED | 100% | 2022-12-22 | 2022-11-11 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | J.V. BUAN CONSTRUCTION *T | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106128 | San Francisco ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2384119.08 | 2 | 2474932.77 | COMPLETED | 100% | 2023-01-06 | 2022-11-28 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106131 | San Miguel ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1472467.1 | 2 | 2008727.8 | COMPLETED | 100% | 2023-01-06 | 2022-11-10 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | ELDICO BUILDERS | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106136 | Sta. Cruz ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2485869.52 | 2 | 3511866.37 | COMPLETED | 100% | 2023-01-06 | 2022-11-22 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | BFF CONSTRUCTION | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106141 | Talimundoc Elementary School | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1223726.72 | 2 | 3172196.24 | COMPLETED | 100% | 2023-01-06 | 2022-11-24 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | CHARIOTS CONSTRUCTION INC. | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106142 | Turu ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2487954.94 | 2 | 2949000 | COMPLETED | 100% | 2023-01-06 | 2022-01-06 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105981 | Calantas ES | FLORIDABLANCA | 2 | 1 | 3 | Repair of Classrooms | 2025398.15 | 2 | 3106866.26 | COMPLETED | 100% | 2023-01-06 | 2022-01-06 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | R.G. ROQUE CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105982 | Camachile es | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 3659843.37 | 2 | 3158377.72 | COMPLETED | 100% | 2023-01-06 | 2022-11-08 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | I.B. MUSNGI CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 501827 | Nabuclod Integrated School | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 3182047.28 | 2 | 2932731.42 | COMPLETED | 100% | 2023-01-06 | 2022-11-02 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | TRACCOR BUILDERS | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 305365 | Pasay City North High School | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 2969082.06 | 2 | 2386859.4 | COMPLETED | 100% | 2023-01-06 | 2022-11-21 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | S.M. SEVERINO CONSTRUCTION & TRADING | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105971 | San Isidro ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 3116158 | 2 | 1452348.41 | COMPLETED | 100% | 2022-12-22 | 2022-11-04 | N/A | N/A | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | TRACCOR BUILDERS | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106219 | Katutubo Village ES | PORAC | 2 | 1 | 4 | Repair of Classrooms | 3182047.28 | 2 |  | COMPLETED | 100% | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 306935 | Bacolor HS | BACOLOR | 3 | 1 | 6 | Repair of Classrooms | 3055397.99 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105954 | Candaba ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 2397165.31 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106209 | Sta. Maria Elementary School | MINALIN | 4 | 1 | 2 | Repair of Classrooms | 1512902.81 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 100% | 2021-10-04 | 2021-08-16 | N/A |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 500140 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 100% | [10 empty] | completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 501137 | San Jose Panlumacan Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 100% | [10 empty] | completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 500142 | San Nicolas IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 100% | [10 empty] | completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106307 | Casili ES | ANAO | 1 | 1 | 3 | Repair of Classrooms | 1225710.58 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106607 | Coral ES | RAMOS | 1 | 1 | 6 | Repair of Classrooms | 3961082.42 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 2095026.05 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Batangas | 107807 | Banalo Elementary School | TINGLOY | 2 | 1 | 2 | Repair of Classrooms | 2831199.38 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Batangas | 107811 | Marikaban Elementary School | TINGLOY | 2 | 1 | 5 | Repair of Classrooms | 724950.42 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Batangas | 301073 | Balete National High School | BALETE | 3 | 1 | 5 | Repair of Classrooms | 2705209.33 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Batangas | 107658 | Abelo Elementary School | SAN NICOLAS | 3 | 1 | 3 | Repair of Classrooms | 844486.32 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Batangas | 301149 | Sta. Teresita National High School | SANTA TERESITA | 3 | 1 | 4 | Repair of Classrooms | 1456771.03 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Cavite | 107926 | Bailen Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 4 | Repair of Classrooms | 2548374.42 | 1 | 628586.93 | COMPLETED | 100% | 2022-10-27 | 2022-10-27 | REPAIR 2022-IVA-BATANGAS-03 | REPAIR 2022-IVA-BATANGAS-03 | 2022-06-14 | 2022-06-21 | 2022-07-04 | 2022-07-12 | 2022-07-29 | Rogelio F. Cruz Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Memorial National High School | RIZAL | 3 | 1 | 5 | Repair of Classrooms | 3232835.39 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Laguna | 108293 | Eugenia Games Olarte Reyes Elem. Sch. | MABITAC | 4 | 1 | 5 | Repair of Classrooms | 1272055.97 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Laguna | 108393 | Casinsin ES | PAKIL | 4 | 1 | 5 | Repair of Classrooms | 1664779.55 | 1 |  | COMPLETED | 100% |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 | [16 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 301487 | BOLBOK INTEGRATED NATIONAL HIGH SCHOOL | LIPA CITY | 6 | 1 | 16 | Repair of Classrooms | 8948954.48 | 2 | 2700000 | COMPLETED | 100% |  |  |  | R4A-LC-2019-7 | JULY 15-22, 2019 | 2019-07-24 | 2019-08-05 | 2019-08-27 | 2019-10-15 | BOTEY CONSTRUCTION | [13 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109690 | Duhatan ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2037231.5 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy Integrated National High School | LIPA CITY | 6 | 1 | 8 | Repair of Classrooms | 4504429.69 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 301494 | Lodlod Integrated National High School | LIPA CITY | 6 | 1 | 8 | Repair of Classrooms | 5358892.3 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 301495 | Lumbang Integrated NHS | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2719356.92 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109683 | Pagolingin ES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2730004.58 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 6 | 1 | 10 | Repair of Classrooms | 6581221.69 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109697 | Rafael M. Lojo MS | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 7445722.2 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109666 | Santo Toribio ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 3292261.64 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 6 | 1 | 9 | Repair of Classrooms | 7442046.68 | 2 |  | COMPLETED | 100% | [10 empty] | BID OUT, FOR POST QUALIFICATION | [12 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 2 | Repair of Classrooms | 1407120.6 | 1 |  | COMPLETED | 100% |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 | [16 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 109084 | Caldong Resettlement ES | SAMPALOC | 1 | 1 | 1 | Repair of Classroom | 1760999.14 | 1 |  | COMPLETED | 100% |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 | [16 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 108948 | Dayap ES | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 527643.68 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 301321 | Elias A. Salvador NHS | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 2203957.52 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 534417.42 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | CATANAUAN | 3 | 1 | 12 | Repair of Classrooms | 8377828.7 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 301354 | Malaya NHS | GENERAL LUNA | 3 | 1 | 6 | Repair of Classrooms | 4393375.16 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 301360 | Olongtao National High School | MACALELON | 3 | 1 | 16 | Repair of Classrooms | 15546791.97 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 301376 | Pitogo Community High School | PITOGO | 3 | 1 | 16 | Repair of Classrooms | 11159543.31 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 301414 | Unisan Integrated High School (Formerly Unisan NHS) | UNISAN | 3 | 1 | 6 | Repair of Classrooms | 2969709.9 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 109052 | Del Pilar Elementary School | QUEZON | 4 | 1 | 1 | Repair of Classroom | 1689722.45 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 109054 | Gumubat ES | QUEZON | 4 | 1 | 1 | Repair of Classroom | 1182116.92 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 109057 | Quezon ES | QUEZON | 4 | 1 | 1 | Repair of Classroom | 2219256.16 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3rd | 1 | 14 | Repair of Classrooms | 13925839.47 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-A | Tayabas City | 109251 | Domoit ES | CITY OF TAYABAS | 1 | 1 | 2 | Repair of Classrooms | 962073.64 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Tayabas City | 109253 | Ipilan-Alitao ES | CITY OF TAYABAS | 1 | 1 | 2 | Repair of Classrooms | 993543.89 | 1 |  | COMPLETED | 100% | [10 empty] | For release of NTP | [12 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-A | Tayabas City | 109247 | Wakas ES | CITY OF TAYABAS | 1 | 1 | 5 | Repair of Classrooms | 2050225.03 | 1 |  | COMPLETED | 100% |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 | [15 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Occidental Mindoro | 110094 | Agkawayan ES | LOOC | 0 | 1 | 5 | Repair of Classrooms | 2576920.34 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-B | Occidental Mindoro | 110123 | Caguray ES | MAGSAYSAY | 0 | 1 | 6 | Repair of Classrooms | 2942555.87 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1 | 1 | 4 | Repair of Classrooms | 2642335.47 | 1 | 2638211.6921 | COMPLETED | 100% | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1 | 1 | 2 | Repair of Classrooms | 1590148.61 | 1 | 1587192.7184 | COMPLETED | 100% | October 2022 | 2022-08-31 | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 2 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-B | Palawan | 110931 | Cabunlawan Elementary School | LINAPACAN | 1 | 1 | 3 | Repair of Classrooms | 2108116.42 | 1 | 2104826.3811 | COMPLETED | 100% | October 2022 | 2022-06-16 | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region IV-B | Palawan | 111051 | Rizal North Elementary School | MAGSAYSAY | 1 | 1 | 2 | Repair of Classrooms | 1657115 | 1 | 1654528.8146 | COMPLETED | 100% | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 1 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1 | 1 | 8 | Repair of Classrooms | 3789443.32 | 1 | 3682524.8033 | COMPLETED | 100% | October 2022 |  | 2022-02-002_INFRA | 2022-02-002_INFRA-LOT 2 | 2022-02-16 | 2022-02-23 | 2022-03-08 | 2022-03-14 | 2022-06-09 | MARYKNOLL BUILDERS AMD SUPPLY | [13 empty] | 100% |  | 44986 | 5.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111262 | Gui-ob Elementary School | ALCANTARA | 0 | 1 | 3 | Repair of Classrooms | 1521993.82 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-01 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111270 | Libtong ES | BANTON | 0 | 1 | 2 | Repair of Classrooms | 1059276.74 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-02 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 171003 | Cabibihan ES | CALATRAVA | 0 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-07 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY | Tawid dagat through maliit lang na bangka, hindi pa matawid, parati masama ang panahon, contractor had requested letter for time suspension. we attempted twice to reach the school but unfortunately palaging failure | [12 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111308 | Ambulong ES | CORCUERA | 0 | 1 | 2 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-06 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | RMR CONSTRUCTION AND TRADING | [13 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111351 | Claro M. Recto ES | FERROL | 0 | 1 | 3 | Repair of Classrooms | 1060635 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-03 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111290 | Jao-Asan ES | MAGDIWANG | 0 | 1 | 4 | Repair of Classrooms | 2120799.3 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-04 | 2022-07-29 | 2022-08-10 | 2022-08-23 |  |  |  | 2ND FAILURE OF BIDDING - FOR NEGOTIATED PROCUREMENT | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IV-B | Romblon | 111394 | Bonga ES | SANTA MARIA (IMELDA) | 0 | 1 | 3 | Repair of Classrooms | 1590953 | 1 |  | COMPLETED | 100% |  |  | N/A | INF-SBR-2022-05 | 2022-07-29 | 2022-08-10 | 2022-08-23 | 2022-11-21 | 2022-12-20 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga del Norte | 124539 | Juan C. Dumaog Sr. ES | MUTIA | 1 | 1 | 3 | Repair of Classrooms | 2121271 | 1 | 2116893.07 | COMPLETED | 100% | 2022-09-30 | 2022-09-08 | REPAIR 2022 RIX - ZAMBOANGA DEL NORTE - 001 | Repair 2022 - BEFF - RIX - ZDN | 2022-02-08 | 2022-02-17 | 2022-03-02 | 2022-03-11 | 2022-05-30 | YSL Builders | None | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 3 | Repair of Classrooms | 2052859 | 1 | 2048537.01 | COMPLETED | 100% | 2022-09-30 | 2022-09-08 | REPAIR 2022 RIX - ZAMBOANGA DEL NORTE - 002 | Repair 2022 - BEFF - RIX - ZDN | 2022-02-08 | 2022-02-17 | 2022-03-02 | 2022-03-11 | 2022-05-30 | YSL Builders | None | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga del Sur | 125084 | Mansanas ES | JOSEFINA | 1 | 1 | 5 | Repair of Classrooms | 2685000 | 1 | 2679797.98 | COMPLETED | 100% | 2022-10-22 | 2022-09-08 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-25 | 2022-06-24 | CPIN Builders | None | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga del Sur | 125451 | Caluma ES | TIGBAO | 2 | 1 | 4 | Repair of Classrooms | 2670000 | 1 | 2099420.5519 | COMPLETED | 100% | 2022-10-22 | 2022-10-20 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-24 | 2022-06-24 | JZ MAGO CONSTRUCTION & ENT. | None | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga del Sur | 125454 | Lacarayan Elementary School | TIGBAO | 2 | 1 | 5 | Repair of Classrooms | 4190000 | 1 | 3252206.5106 | COMPLETED | 100% | 2022-10-22 | 2022-10-20 | ZDS-22-RR-01 | ZDS-22-RR-01 | 2022-02-07 | 2022-02-21 | 2022-03-07 | 2022-03-24 | 2022-06-24 | JZ MAGO CONSTRUCTION & ENT. | None | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga Sibugay | 125844 | Bolingan ES | TALUSAN | 1 | 1 | 2 | Repair of Classrooms | 1340717.25 | 1 | 1337716.51 | COMPLETED | 100% | 2022-10-17 | 2022-10-17 | ZSY-2022R-01 | ZSY-2022R-01 | 2022-02-13 | 2022-02-21 | March 07, 2022 | March 31, 2022 | 2022-07-16 | CPAN Engineering & Enterprises | None | [12 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region IX | Zamboanga Sibugay | 125850 | Mahayahay ES | TALUSAN | 1 | 1 | 2 | Repair of Classrooms | 1241738.1 | 1 | 1238891.52 | COMPLETED | 100% | 2022-10-17 | 2022-10-17 | ZSY-2022R-02 | ZSY-2022R-02 | 2022-02-13 | 2022-02-21 | March 07, 2022 | March 31, 2022 | 2022-07-16 | CPAN Engineering & Enterprises | None | [12 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Norte | 112268 | Pulantuna ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Norte | 112277 | V. Ricafrente ES | SAN VICENTE | 2 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS (Junior High) | Cabusao | 1 | 1 | 2 | Repair of Classrooms | 1522541.5 | 2 | 1517154.68 | COMPLETED | 100% | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | [13 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Sur | 112775 | Cagbunga Elementary School | GAINZA | 2 | 1 | 2 | Repair of Classrooms | 1060635.37 | 2 | 1055293.24 | COMPLETED | 100% | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Sur | 302053 | Sulpicio A. Roco Memorial High School | BOMBON | 3 | 1 | 3 | Repair of Classrooms | 1672223.36 | 2 | 2111308.28 | COMPLETED | 100% | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 3 | 1 | 5 | Repair of Classrooms | 2121271 | 2 | 1662197.8 | COMPLETED | 100% | 2023-03-19 | 2023-02-23 |  | 2022-11-112 | SEPT. 16, 2022 | SEPT, 26, 2022 | 2022-10-06 | 2022-10-06 | 2022-12-19 | TGME CONST | project completed | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Catanduanes | 113158 | Sagrada ES | BAGAMANOC | 0 | 1 | 5 | Repair of Classrooms | 3197041.92 | 2 |  | COMPLETED | 100% | [23 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | 6 | Repair of Classrooms | 4546320.5 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Catanduanes | 174016 | Pananaogan Elementary School | BATO | 0 | 1 | 5 | Repair of Classrooms | 3324897.45 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1 | 1 | 5 | Repair of Classrooms | 3181906 | 2 | 2163696.08 | COMPLETED | 100% | 2023-03-12 |  | INFRA 2022-09-009 | 2022-004 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | JOHNCB CONST. & SUPPLY | [13 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Masbate | 113875 | Salvacion ES | SAN FERNANDO | 1 | 1 | 2 | Repair of Classrooms | 1522541 | 2 | 1500159.65 | COMPLETED | 100% | 2023-03-12 |  | INFRA 2022-09-009 | 2022-005 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | RPN CONST. & SERVICES | [13 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Masbate | 113633 | Sorosimbahan ES | Esperanza | 3 | 1 | 2 | Repair of Classrooms | 1522541.5 | 2 | 1502162.59 | COMPLETED | 100% | 2023-03-12 |  | INFRA 2022-09-009 | 2022-006 | 2022-09-13 | 2022-09-20 | 2022-10-03 | 2022-12-02 | 2022-12-12 | RPN CONST. & SERVICES | [13 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Sorsogon | 113987 | Macabari Elementary School | BARCELONA | 2 | 1 | 3 | Repair of Classrooms | 1453495 | 2 | 756026.41 | COMPLETED | 100% | 2021-12-03 | 2021-12-03 | 22-07-003 | 22-07-003-01 | 2022-07-19 | 2023-07-27 | 2022-08-08 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply | [13 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Sorsogon | 114215 | Rizal ES | GUBAT | 2 | 1 | 10 | Repair of Classrooms | 6013327.41 | 2 | 3590336.04 | COMPLETED | 100% | 2023-02-01 | 2022-12-22 | 22-07-003 | 22-07-003-02 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply | [13 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Sorsogon | 114399 | San Fernando ES | PRIETO DIAZ | 2 | 1 | 4 | Repair of Classrooms | 2100000 | 2 | 1206255.75 | COMPLETED | 100% | 2023-01-12 | 2022-12-22 | 22-07-003 | 22-07-003-03 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply | [13 empty] | 100% |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Sorsogon | 114414 | San Sebastian ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of Classrooms | 980000 | 2 | 575436.51 | COMPLETED | 100% | 2023-01-12 | 2022-12-06 | 22-07-003 | 22-07-003-04 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply | [13 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region V | Sorsogon | 114417 | Uson ES | SANTA MAGDALENA | 2 | 1 | 2 | Repair of Classrooms | 1300000 | 2 | 763788.28 | COMPLETED | 100% | 2023-01-12 | 2022-12-06 | 22-07-003 | 22-07-003-04 | 2022-07-19 | 2023-07-27 | 2022-08-09 | 2022-08-22 | 2022-09-15 | La Abel Construction and Supply | [13 empty] | 100% |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VI | Aklan | 114702 | Bel-is ES | BURUANGA | 2 | 1 | 2 | Repair of Classrooms | 829930.76 | 1 | 822267.96 | COMPLETED | 100% | 2022-09-26 | 2022-09-13 | CY 2022 BEFF REAPIR - 001 | CY 2022 BEFF REAPIR - 001 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | EARLY RISER CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Aklan | 114712 | Tigum ES | BURUANGA | 2 | 1 | 3 | Repair of Classrooms | 1291274.33 | 1 | 1275118.05 | COMPLETED | 100% | 2022-09-26 | 2022-10-21 | CY 2022 BEFF REAPIR - 001 | CY 2022 BEFF REAPIR - 001 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | EARLY RISER CONSTRUCTION | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Aklan | 114764 | Bugasongan ES | LEZO | 2 | 1 | 2 | Repair of Classrooms | 1059858.6 | 1 | 1053269.37 | COMPLETED | 100% | 2022-10-14 | 2022-09-26 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Aklan | 114928 | Dapdap Elementary School | TANGALAN | 2 | 1 | 2 | Repair of Classrooms | 742820.94 | 1 | 735800.85 | COMPLETED | 100% | 2022-10-25 | 2022-11-11 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2 | 1 | 1 | Repair of Classroom | 779456.07 | 1 | 771071.55 | COMPLETED | 100% | 2022-10-14 | 2022-11-18 | CY 2022 BEFF REAPIR - 002 | CY 2022 BEFF REAPIR - 002 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHNDISING | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Antique | 114978 | Mojon ES | BELISON | 0 | 1 | 3 | Repair of Classrooms | 2121271 | 1 |  | COMPLETED | 100% | August 23, 2022 | [9 empty] | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Antique | 115131 | Lindero Elementary School | LIBERTAD | 0 | 1 | 7 | Repair of Classrooms | 3181906 | 1 |  | COMPLETED | 100% | September 3, 2022 | [9 empty] | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 0 | 1 | 8 | Repair of Classrooms | 3637208.88 | 1 |  | COMPLETED | 100% | 2023-02-28 |  | 03-2022-lot 2 | No. 03-B-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-09-26 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116107 | Cairohan PS | BINGAWAN | 3 | 1 | 1 | Repair of Classroom | 531001.48 | 1 | 523711.43 | COMPLETED | 100% | ################ | 2022-08-19 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116111 | Maganhop PS | BINGAWAN | 3 | 1 | 2 | Repair of Classrooms | 651145.99 | 1 | 642452.25 | COMPLETED | 100% | ################ | 2022-08-19 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | BINGAWAN | 3 | 1 | 3 | Repair of Classrooms | 1342396.18 | 1 | 1326345.85 | COMPLETED | 100% | ################ | Augsut 29, 2022 | R-06-BEFF-2022-B1-L2 | R-06-BEFF-2022-B1-L2 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Wilkinson Construction | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116604 | Tipolo Elementary School | MINA | 3 | 1 | 11 | Repair of Classrooms | 1914166.05 | 1 | 1469603.52 | COMPLETED | 100% | ################ | 2022-12-16 | R-06-BEFF-2022-B1-L1 | R-06-BEFF-2022-B1-L1 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-18 | Em Sinai Constrction Services | completed | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116092 | Batad CES | BATAD | 5 | 1 | 3 | Repair of Classrooms | 852867.33 | 1 | 851905.57 | COMPLETED | 100% | 2022-11-05 | 2022-08-05 | R-06-BEFF-2022-B1-L4 | R-06-BEFF-2022-B1-L4 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-08 | Early Riser Construction | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116096 | Calangag PS | BATAD | 5 | 1 | 2 | Repair of Classrooms | 683361.1 | 1 | 659836.94 | COMPLETED | 100% | 2022-11-08 | 2022-08-23 | R-06-BEFF-2022-B1-L3 | R-06-BEFF-2022-B1-L3 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-11 | Anjush Builders | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116101 | Tanao ES | BATAD | 5 | 1 | 2 | Repair of Classrooms | 747593.46 | 1 | 722281.84 | COMPLETED | 100% | 2022-11-08 | 2022-08-23 | R-06-BEFF-2022-B1-L3 | R-06-BEFF-2022-B1-L3 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-11 | Anjush Builders | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VI | Iloilo | 116764 | Poscolon ES | SAN RAFAEL | 5 | 1 | 1 | Repair of Classroom | 488869.98 | 1 | 485512.27 | COMPLETED | 100% | 2022-11-05 | 2022-08-05 | R-06-BEFF-2022-B1-L4 | R-06-BEFF-2022-B1-L4 | 2022-02-24 |  | 2022-03-15 | 2022-03-24 | 2022-07-08 | Early Riser Construction | completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 117930 | Bahi Primary School | ALBURQUERQUE | 1 | 1 | 3 | Repair of Classrooms | 1692566.73 | 1 | 1337047.43 | COMPLETED | 100% | Jan 29.2023 |  |  | 12022-03-01-1 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118205 | Tanday ES | CORELLA | 1 | 1 | 4 | Repair of Classrooms | 1685475.3 | 1 | 1331041.93 | COMPLETED | 100% | 2023-02-13 |  |  | 12022-03-01-2 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118207 | Dela Paz ES | CORTES | 1 | 1 | 6 | Repair of Classrooms | 2084958.22 | 1 | 1647277.79 | COMPLETED | 100% | Jan 29.2023 |  |  | 12022-03-01-1 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118699 | Cambuac Sur ES | SIKATUNA | 1 | 1 | 11 | Repair of Classrooms | 2480931.92 | 1 | 1959942.27 | COMPLETED | 100% | 2023-02-13 |  |  | 12022-03-01-2 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118197 | Nahawan ES | CLARIN | 2 | 1 | 9 | Repair of Classrooms | 2651332.26 | 1 | 2634918.21 | COMPLETED | 100% | 2023-02-28 |  |  | 12022-03-01-3 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | INABANGA DRILLING | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118228 | Malitbog Elementary School | DAGOHOY | 2 | 1 | 9 | Repair of Classrooms | 2121016.52 | 1 | 1844676.76 | COMPLETED | 100% | Mach 5, 2023 |  |  | 12022-03-01-4 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 10.6.2022 | ELMUEL JAY TRADING & CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118641 | San Isidro Central ES | SAN ISIDRO | 2 | 1 | 7 | Repair of Classrooms | 1590612.12 | 1 | 1383177.89 | COMPLETED | 100% | 2023-03-05 |  |  | 12022-03-01-4 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 10.6.2022 | ELMUEL JAY TRADING & CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 117955 | Badiang ES | ANDA | 3 | 1 | 9 | Repair of Classrooms | 3181801.14 | 1 | 2532521.16 | COMPLETED | 100% | 2023-02-28 |  |  | 12022-03-01-5 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ALAGAMON CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118024 | Rizal ES | BATUAN | 3 | 1 | 7 | Repair of Classrooms | 2372684.01 | 1 | 1866762.38 | COMPLETED | 100% | 2023-02-28 |  |  | 12022-03-01-6 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Bohol | 118669 | Licolico ES | SEVILLA | 3 | 1 | 7 | Repair of Classrooms | 2011819.45 | 1 | 1577505.46 | COMPLETED | 100% | 2023-02-28 |  |  | 12022-03-01-6 | 3.30.2022 | 4.7.2022 | 4.19.2022 | 6.15.2022 | 9.30.2022 | ROMERO CONST | ATP Jan 17, 2022 | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Cebu | 119134 | Pondohan ES | BOLJOON | 2 | 1 | 6 | Repair of Classrooms | 3067481.98 | 2 | 3051317.85 | COMPLETED | 100% |  |  | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-01 | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-01 | August 3, 2022 | August 10, 2022 | August 22, 2022 | August 30, 2022 | November 21, 2022 | La Prueba Construction | [13 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Cebu | 119447 | Montañeza ES | MALABUYOC | 2 | 1 | 13 | Repair of Classrooms | 8124237.16 | 1 | 8074200.13 | COMPLETED | 100% | 2022-11-01 |  | CY 2022 BEFF REPAIR-DEPED-R7-CEBU | CY 2022 BEFF REPAIR-DEPED-R7-CEBU-01 | 2022-03-15 | 2022-03-22 | 2022-04-04 | 2022-04-18 | 2022-06-27 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  | 44986 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Cebu | 119607 | Dalahikan ES | SAMBOAN | 2 | 1 | 4 | Repair of Classrooms | 2390068.3 | 2 | 2355012.05 | COMPLETED | 100% |  |  | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-02 | CY 2022 REPAIR BATCH 2-DEPED-R7-CEBU-02 | August 3, 2022 | August 10, 2022 | August 22, 2022 | August 30, 2022 | November 21, 2022 | GCATZ Construction | [13 empty] | 100% |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Cebu | 303073 | Pilar NHS | PILAR | 5 | 1 | 12 | Repair of Classrooms | 6283149.47 | 1 | 6264532.5 | COMPLETED | 100% | 2022-10-02 |  | CY 2022 BEFF REPAIR-DEPED-R7-CEBU | CY 2022 BEFF REPAIR-DEPED-R7-CEBU-02 | 2023-03-15 | 2023-03-22 | 2023-04-04 | 2023-04-18 | 2022-06-27 | BARR STEEL CONSTRUCTION | [13 empty] | 100% |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Negros Oriental | 120311 | Aniniaw ES | LA LIBERTAD | 1 | 1 | 5 | Repair of Classrooms & Toilet | 2511000 | 2 | 2490201.33 | COMPLETED | 100% | 2023-04-10 | 2023-03-28 | ITB no. 2022-06-061 | BEFF 202209008 | 2022-07-04 | 2022-07-12 | 2022-07-25 | 2022-07-28 | 2022-09-20 | Tribata Construction and Development | with approved time extension. | [12 empty] | 100% |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VII | Negros Oriental | 120433 | Janayjanay Elementary School | SAN JOSE | 2 | 1 | 5 | Repair of Classrooms | 2801981.26 | 1 | 2207000 | COMPLETED | 100% | 2022-10-14 | 2022-12-06 | ITB no. 2022-02-007 | ITB no. 2022-02-007 | 2022-02-14 | 2023-02-23 | 2022-03-07 | 2022-03-24 | 2022-06-03 | RISM Builders & Construction Services, Inc. | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Siquijor | 120660 | Libo Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | 3 | Repair of Classrooms | 1766789.71 | 1 | 1429945.54 | COMPLETED | 100% | 2022-09-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 1 | Repair of Classroom | 636955.25 | 1 | 535080.38 | COMPLETED | 100% | 2022-08-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 3 | Repair of Classrooms | 1614561.19 | 1 | 1307112.06 | COMPLETED | 100% | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VII | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | 4 | Repair of Classrooms | 3064866.16 | 1 | 2513189.24 | COMPLETED | 100% | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA | 0 | 1 | 2 | Repair of Classrooms | 1061497.39 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120760 | Caucab ES | ALMERIA | 0 | 1 | 7 | Repair of Classrooms | 2857078.39 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120765 | Palayan ES | ALMERIA | 0 | 1 | 3 | Repair of Classrooms | 1593529.73 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | 0 | 1 | 9 | Repair of Classrooms | 1235101.57 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 2 | Repair of Classrooms | 1198599.08 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | 0 | 1 | 6 | Repair of Classrooms | 2590372.35 | 1 | 361130.34 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120799 | Bariis ES | CAIBIRAN | 0 | 1 | 6 | Repair of Classrooms | 2431071.6 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120812 | Tomalistis ES | CAIBIRAN | 0 | 1 | 3 | Repair of Classrooms | 1240222.99 | 1 | 361500 | COMPLETED | 100% | [9 empty] | A AND B ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120838 | Masagaosao ES | KAWAYAN | 0 | 1 | 6 | Repair of Classrooms | 2469990.15 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Biliran | 120841 | Tubig Guinoo ES | KAWAYAN | 0 | 1 | 3 | Repair of Classrooms | 1336564.41 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | 0 | 1 | 8 | Repair of Classrooms | 3332391.33 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122575 | Jipapad Central School | JIPAPAD | 0 | 1 | 5 | Repair of Classrooms | 2153635.59 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122463 | Maslog Central Elementary School | MASLOG | 0 | 1 | 4 | Repair of Classrooms | 1650444.69 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122706 | Bagtong Central Elementary School | SALCEDO | 0 | 1 | 6 | Repair of Classrooms | 2533266.41 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122722 | Campidhan Elementary School | SAN JULIAN | 0 | 1 | 7 | Repair of Classrooms | 2896634.68 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122731 | San Julian Central Elementary School | SAN JULIAN | 0 | 1 | 5 | Repair of Classrooms | 2138180.87 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122736 | Baras Elementary School | SAN POLICARPO | 0 | 1 | 5 | Repair of Classrooms | 2429490.29 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122737 | Binogawan Elementary School | SAN POLICARPO | 0 | 1 | 5 | Repair of Classrooms | 2641047.63 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Eastern Samar | 122742 | San Policarpo Central Elementary School | SAN POLICARPO | 0 | 1 | 16 | Repair of Classrooms | 7703588.17 | 1 |  | COMPLETED | 100% | [10 empty] | 44896 | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121880 | Sta. Fe Central School | SANTA FE | 1 | 1 | 6 | Repair of Classrooms | 1094883.7 | 1 | 892437.57 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | ASTILLA CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121953 | Opong Elementary School | TOLOSA | 1 | 1 | 6 | Repair of Classrooms | 3181905.91 | 1 | 1879039.89 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | JVM BOLLARD CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121570 | Gimiranat West Elementary School | LA PAZ | 2 | 1 | 1 | Repair of Classroom | 604446.32 | 1 | 356497.1 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | BELGES CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121577 | Moroboro Elementary School | LA PAZ | 2 | 1 | 2 | Repair of Classrooms | 1147167.04 | 1 | 664266.77 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | BELGES CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 | 1 | 4 | Repair of Classrooms | 2111833.56 | 1 | 1521938 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-07-01 | SAMARINAN CONSTRUCTION AND DEVELOPMENT CORP. | [13 empty] | 100% |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MACARTHUR | 2 | 1 | 2 | Repair of Classrooms | 840419.15 | 1 |  | COMPLETED | 100% | [10 empty] | Failure of bidding; rebid | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2 | 1 | 8 | Repair of Classrooms | 2863914.54 | 1 | 2051726.88 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-23 | 2022-07-04 | VHITS D. G BUILDERS & ENTERPRISES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 191539 | Quezon Elementary School | MACARTHUR | 2 | 1 | 2 | Repair of Classrooms | 663505.08 | 1 |  | COMPLETED | 100% | [10 empty] | Failure of bidding; rebid | [12 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 191576 | San Isidro Elementary School | MACARTHUR | 2 | 1 | 1 | Repair of Classroom | 462087.9 | 1 | 447080.52 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-27 | APU CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121628 | Tinawan Elementary School | MACARTHUR | 2 | 1 | 3 | Repair of Classrooms | 1075515.26 | 1 | 1060503.91 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-27 | APU CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | 9 | Repair of Classrooms | 2950154.04 | 1 | 2079045 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-23 | 2022-07-01 | J. CUSTORIO CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121719 | Canbantug Elementary School | MERIDA | 4 | 1 | 3 | Repair of Classrooms | 916746.05 | 1 | 584208.4 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121726 | Macario Elementary School | MERIDA | 4 | 1 | 1 | Repair of Classroom | 195488.43 | 1 | 123502.73 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121728 | Mahayag Primary School | MERIDA | 4 | 1 | 2 | Repair of Classrooms | 1002528.02 | 1 | 638934.08 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5 | 1 | 2 | Repair of Classrooms | 756445.15 | 1 | 745916.55 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Leyte | 121412 | Mahilum Elementary School | HINDANG | 5 | 1 | 3 | Repair of Classrooms | 904103.3 | 1 | 887769.2 | COMPLETED | 100% |  |  |  |  | 2022-02-24 | 2022-03-14 | 2022-03-28 | 2022-06-22 | 2022-06-24 | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES | [13 empty] | 100% |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | ALLEN | 1 | 1 | 2 | Repair of Classrooms | 1249477.92 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | MARCARP ENG'G DEV. SUPPLIES | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 122791 | Basud ES | BIRI | 1 | 1 | 3 | Repair of Classrooms | 1105801.04 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | ARKOUZ BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 122824 | Jubang ES | CAPUL | 1 | 1 | 6 | Repair of Classrooms | 3170388.97 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | LA CIVIL ENG'G | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123188 | Aguada PS | ROSARIO | 1 | 1 | 2 | Repair of Classrooms | 1239468.89 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | SIERRA CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123198 | Dalupirit ES | SAN ANTONIO | 1 | 1 | 1 | Repair of Classroom | 727393.74 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123201 | Pilar Elementary School | SAN ANTONIO | 1 | 1 | 2 | Repair of Classrooms | 1130220.13 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123228 | P. Tingzon ES | SAN JOSE | 1 | 1 | 2 | Repair of Classrooms | 1098757.86 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | R.N. CHIA CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123231 | Tubigdanao ES | SAN JOSE | 1 | 1 | 2 | Repair of Classrooms | 1229210.68 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | AL CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123250 | Tarnate ES | SAN VICENTE | 1 | 1 | 2 | Repair of Classrooms | 972957.05 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | GRINDER CIVIL ENG'G | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123276 | Libertad ES | VICTORIA | 1 | 1 | 4 | Repair of Classrooms | 2198908.06 | 1 |  | COMPLETED | 100% | [5 empty] | 2022-02-09 | 2022-03-07 |  |  | MUDOLUS CONST. | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 122993 | Can Maria Elementary School | LAPINIG | 2 | 1 | 2 | Repair of Classrooms | 1126886.22 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123001 | Pio Del Pilar ES | LAPINIG | 2 | 1 | 2 | Repair of Classrooms | 1211740.89 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 123104 | Burgos ES | MAPANAS | 2 | 1 | 2 | Repair of Classrooms | 1289758.13 | 1 |  | COMPLETED | 100% | [10 empty] | SUbject for LD | [12 empty] | 100% |  | 44986 | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Northern Samar | 193008 | Manaybanay Elementary School | MAPANAS | 2 | 1 | 3 | Repair of Classrooms | 1363396.25 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123810 | Pinanangnan Elementary School | SANTO NIÑO | 1 | 1 | 1 | Repair of Classroom | 612514.22 | 1 | 586278.34 | COMPLETED | 100% | 2022-09-11 | 2022-07-05 | CY2022 BEFF R-L1 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | NV&C CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 501924 | Sevilla Integrated School | SANTO NIÑO | 1 | 1 | 3 | Repair of Classrooms | 1736601.91 | 1 | 1654608.92 | COMPLETED | 100% | 2022-09-11 |  | CY2022 BEFF R-L2 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | AGB CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123814 | Villahermosa ES | SANTO NIÑO | 1 | 1 | 3 | Repair of Classrooms | 1736601.91 | 1 | 1673785.08 | COMPLETED | 100% | 2022-09-11 | 2022-08-22 | CY2022 BEFF R-L3 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | GUY CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123823 | Nipa ES | TAGAPUL-AN | 1 | 1 | 4 | Repair of Classrooms | 2361413.15 | 1 | 2346281.62 | COMPLETED | 100% | 2022-09-11 | 2022-08-05 | CY2022 BEFF R-L4 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | LRD CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123584 | Camarubo-an ES | JIABONG | 2 | 1 | 3 | Repair of Classrooms | 1815576.15 | 1 | 1718826.35 | COMPLETED | 100% | 2022-09-11 | 2022-07-22 | CY2022 BEFF R-L5 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | SAMARINAN CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123601 | Parina Elementary School | JIABONG | 2 | 1 | 4 | Repair of Classrooms | 2408532.6 | 1 | 2212003.6 | COMPLETED | 100% | 2022-09-11 |  | CY2022 BEFF R-L6 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | QCC CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 303614 | Osmeña National High School | MARABUT | 2 | 1 | 8 | Repair of Classrooms | 1856094.29 | 1 | 1840732.92 | COMPLETED | 100% | 2022-09-11 | 2022-08-05 | CY2022 BEFF R-L7 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | VHITS DG BUILDERS | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123717 | Canduyocan Elementary School | SAN SEBASTIAN | 2 | 1 | 3 | Repair of Classrooms | 1752094.85 | 1 | 1679386.99 | COMPLETED | 100% | 2022-09-11 |  | CY2022 BEFF R-L8 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | NV&C CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2 | 1 | 5 | Repair of Classrooms | 2193467.91 | 1 | 1964709.71 | COMPLETED | 100% | 2022-09-11 | 2022-08-22 | CY2022 BEFF R-L9 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | HEROES CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Samar (Western Samar) | 123977 | Pangdan ES | ZUMARRAGA | 2 | 1 | 1 | Repair of Classroom | 870845.29 | 1 | 853463.9 | COMPLETED | 100% | 2022-09-11 |  | CY2022 BEFF R-L10 |  | 2022-02-10 | 2022-02-17 | 2022-03-01 | 2022-05-27 | 2022-06-06 | MAGA CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 9 | Repair of Classrooms | 4734639.95 | 2 |  | COMPLETED | 100% |  |  | CY2022-Repair-B2-L2 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Southern Leyte | 122083 | Nahulid Elementary School | LIBAGON | 2 | 1 | 14 | Repair of Classrooms | 7536536.08 | 2 |  | COMPLETED | 100% |  |  | CY2022-Repair-B2-L1 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Southern Leyte | 192019 | Catbawan Elementary School | PINTUYAN | 2 | 1 | 5 | Repair of Classrooms | 2648711.16 | 2 |  | COMPLETED | 100% |  |  | CY2022-Repair-B2-L3 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Southern Leyte | 192020 | Dan-an Elementary School | PINTUYAN | 2 | 1 | 4 | Repair of Classrooms | 2270650.72 | 2 |  | COMPLETED | 100% |  |  | CY2022-Repair-B2-L3 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region VIII | Southern Leyte | 122117 | Tuno Elementary School | SAN FRANCISCO | 2 | 1 | 6 | Repair of Classrooms | 3404208.88 | 2 |  | COMPLETED | 100% |  |  | CY2022-Repair-B2-L4 |  | 2022-07-08 | 2022-07-15 | 2022-07-27 |  |  |  | Post Qualification Stage | [12 empty] | 100% |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Camiguin | 126893 | Tangaro ES | CATARMAN | 0 | 1 | 6 | Repair of Classrooms | 3077889.81 | 1 | 2807412.83 | COMPLETED | 100% | 2022-12-03 |  | INFRA-01-02-2022 | INFRA-01-02-2022 | 2022-02-15 | 2022-02-23 | 2022-03-07 | 2022-04-11 | 2022-06-06 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Camiguin | 500962 | Bacnit Integrated School | SAGAY | 0 | 1 | 5 | Repair of Classrooms | 2836875.5 | 1 | 3046248.33 | COMPLETED | 100% | 2022-12-03 |  | INFRA-01-01-2022 | INFRA-01-01-2022 | 2022-02-15 | 2022-02-23 | 2022-03-07 | 2022-04-11 | 2022-06-06 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2 | 1 | 2 | Repair of Classrooms | 1100000 | 1 | 1098020.25 | COMPLETED | 100% | 2022-09-09 | 2022-09-22 | 2022-02-0014 | 2022-07-0151 | 2022-02-22 | 2022-03-09 | 2022-03-21 | 2022-06-14 | 2022-07-13 | 3L and JES Construction | Completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | El Salvador | 315318 | Hinigdaan NHS | CITY OF EL SALVADOR | 2 | 1 | 4 | Repair of Classrooms | 572224 | 1 | 371364.47 | COMPLETED | 100% | 2022-09-09 | 2022-09-22 | 2022-02-0015 | 2022-07-0152 | 2022-02-22 | 2022-03-09 | 2022-03-21 | 2022-06-14 | 2022-07-13 | 3L and JES Construction | Completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 127043 | Kauswagan CES | KAUSWAGAN | 1 | 1 | 12 | Repair of Classrooms | 5629079.84 | 1 | 4499745.95 | COMPLETED | 100% | 2022-11-10 |  |  | Lot-4 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-05-16 | 2022-07-07 | MOH'D Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 127097 | Purakan Elementary School | LINAMON | 1 | 1 | 7 | Repair of Classrooms | 2802226.63 | 1 | 2296283.81 | COMPLETED | 100% | 2022-10-11 | 2022-10-25 |  | Lot-2 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | ABRAHAM-BM Construction | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1 | 1 | 15 | Repair of Classrooms | 6201512.58 | 1 | 4767687.39 | COMPLETED | 100% | 2022-11-09 |  |  | Lot-5 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | RAMZIE Builders & Enterprises | Punchlist | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 1 | 1 | 3 | Repair of Classrooms | 1524953.52 | 1 | 1325129.24 | COMPLETED | 100% | 2022-10-11 | 2022-11-29 |  | Lot-1 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | SBM Builder | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 1 | 1 | 2 | Repair of Classrooms | 743312.94 | 1 | 646706.7 | COMPLETED | 100% | 2022-10-11 | 2022-11-29 |  |  | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | SBM Builder | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 3 | Repair of Classrooms | 1467550.2 | 1 | 1452276.7 | COMPLETED | 100% | 2022-10-11 |  |  | Lot-3 | 2022-02-15 | 2022-02-23 | 2022-03-08 | 2022-04-18 | 2022-06-20 | MOH'D Construction | Substantially Completed | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 1 | 1 | 3 | Repair of Classrooms | 2009565.97 | 1 |  | COMPLETED | 100% | 2022-10-17 | 2022-11-11 | 010-2022 | 010-2022 | 2022-02-23 | 2022-03-02 | 2022-03-14 | 2022-05-10 | 2022-07-26 | KAYRO Construction and Supply | subject for final inspection | [12 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Misamis Occidental | 304055 | Sinonoc NHS | SINACABAN | 2 | 1 | 17 | Repair of Classrooms | 10675365.03 | 1 |  | COMPLETED | 100% | 2022-12-01 |  | 009-2022 | 009-2022 | 2022-02-23 | 2022-03-02 | 2022-03-14 | 2022-05-10 | 2022-07-26 | JJFY Construction and Services | on-going | [12 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 201505 | Bauk-Bauk ES | BALINGOAN | 1 | 1 | 1 | Repair of Classroom with Embankment & Riprap | 747250 | 1 | 582206.44 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | for punchlisting | [12 empty] | 100% |  | 44986 | 2.24 |  |  |  |  | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127878 | Kabangasan ES | BALINGOAN | 1 | 1 | 1 | Repair of Classroom | 473640.36 | 1 | 432034.86 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | [13 empty] | 100% |  | 44986 | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127887 | Mapua ES | BALINGOAN | 1 | 1 | 2 | Repair of Classrooms | 1104388.18 | 1 | 937124.44 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | [13 empty] | 100% |  | 44986 | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127740 | Valdeconcha ES | BINUANGAN | 1 | 1 | 4 | Repair of Classrooms | 1659691.73 | 1 | 1445658.19 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | GREEN BUILDER AND ENTERPRISE | Substancially Completed | [12 empty] | 100% |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1 | 1 | 2 | Repair of Classrooms | 1110727.03 | 1 | 919693.99 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC. | [13 empty] | 100% |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127747 | Lagonglong CS | LAGONGLONG | 1 | 1 | 4 | Repair of Classrooms | 1976088.08 | 1 | 1571802.16 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC. | on-going | [12 empty] | 100% |  | 44986 | 10.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1 | 1 | 2 | Repair of Classrooms | 1138119.97 | 1 | 930454.79 | COMPLETED | 100% | 2022-12-09 |  |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-24 | ALEBON GENUINE MERCHANDIZING INC. | [13 empty] | 100% |  | 44986 | 5.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127753 | C.P. Garcia ES | GITAGUM | 2 | 1 | 4 | Repair of Classrooms | 1770692.18 | 1 | 1389931.3 | COMPLETED | 100% | 2022-12-09 | 2022-11-25 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | JDE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region X | Misamis Oriental | 127759 | Natalio L. Bongcas Sr. Memorial ES | GITAGUM | 2 | 1 | 2 | Repair of Classrooms | 1107389.8 | 1 | 872625.55 | COMPLETED | 100% | 2022-12-09 | 2022-11-04 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-08-02 | 2022-10-17 | JDE CONSTRUCTION | [13 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1 | 1 | 13 | Repair of Classrooms & H.E. | 10020720 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region XI | Mati City | 129405 | Taguibo ES | CITY OF MATI (Capital) | 2 | 1 | 9 | Repair of Classrooms | 4550909.2 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region XI | Mati City | 129406 | Tamia ES | CITY OF MATI (Capital) | 2 | 1 | 4 | Repair of Classrooms | 2005144.53 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2023 | CAR | Abra | 134967 | Bacsil Elementary School | BANGUED (Capital) | Lone | 1 | 7 | Repair of Classrooms | 6997850.5 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 305092 | Pangtod NHS | BUCAY | Lone | 1 | 14 | Repair of Classrooms | 11962677.41 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135043 | Toon ES | LA PAZ | Lone | 1 | 9 | Repair of Classrooms | 7334722.18 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135082 | Tagodtod ES | LAGANGILANG | Lone | 1 | 17 | Repair of Classrooms | 4701133.31 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135138 | Malapaao ES | LANGIDEN | Lone | 1 | 8 | Repair of Classrooms | 6974744.82 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135105 | Luzong ES | LUBA | Lone | 1 | 11 | Repair of Classrooms | 5227579.94 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 501729 | TABANGAO IS | LUBA | Lone | 1 | 7 | Repair of Classrooms | 1801681.92 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 218519 | Tattawa Primary School | PEÑARRUBIA | Lone | 1 | 2 | Repair of Classrooms | 1370900.69 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135168 | Abas ES | SALLAPADAN | Lone | 1 | 10 | Repair of Classrooms | 14649444.46 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | 4 | Repair of Classrooms | 2466413.86 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | Lone | 1 | 2 | Repair of Classrooms | 2581277.79 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 501104 | Tuquib Integrated School | VILLAVICIOSA | Lone | 1 | 4 | Repair of Classrooms | 1426876.7 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135261 | Daga ES | CONNER | Lone | 1 | 2 | Repair of Classrooms | 839062.9 | DEPED (Batch 2) | 797308.5 | COMPLETED | 100% |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135273 | Paddaoan ES | CONNER | Lone | 1 | 4 | Repair of Classrooms | 2378537.75 | DPWH (Batch 2) | 2324722.22 | COMPLETED | 100% | 2024-05-16 |  |  | 23PC0087 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135288 | Balluyan ES | FLORA | Lone | 1 | 2 | Repair of Classrooms | 484181.88 | DEPED (Batch 2) | 460031.76 | COMPLETED | 100% |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135292 | Sta. Maria ES | FLORA | Lone | 1 | 3 | Repair of Classrooms | 1566065.42 | DPWH (Batch 2) | 1274457.81 | COMPLETED | 100% | 2024-04-27 |  |  | 23PC0088 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | Lone | 1 | 9 | Repair of Classrooms | 2952826.49 | DPWH (Batch 2) | 1467604.95 | COMPLETED | 100% | 2024-04-27 |  |  | 23PC0089 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135335 | Dagupan ES | LUNA | Lone | 1 | 2 | Repair of Classrooms | 1266006.56 | DPWH (Batch 2) | 2763466.23 | COMPLETED | 100% | 2024-05-12 |  |  | 23PC0091 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 219004 | Luyon ES | LUNA | Lone | 1 | 1 | Repair of Classroom | 816380.11 | DEPED (Batch 2) | 775363.96 | COMPLETED | 100% |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 219003 | San Juan ES | SANTA MARCELA | Lone | 1 | 2 | Repair of Classrooms | 1362472.41 | DPWH (Batch 2) | 1185260.55 | COMPLETED | 100% | 2024-04-15 |  |  | 23PC0090 |  | 2023-11-17 | 2023-11-28 |  |  | ECV CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | Lone | 1 | 4 | Repair of Classrooms | 2484261.86 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | GKA ENGINEERING AND CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135380 | Calasipan ES | ATOK | Lone | 1 | 3 | Repair of Classrooms | 2925000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135410 | Cabutotan ES | BAKUN | Lone | 1 | 3 | Repair of Classrooms | 2925000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135443 | Kawal ES | BOKOD | Lone | 1 | 3 | Repair of Classrooms | 5953500 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 501301 | Cayapas Integrated School | BUGUIAS | Lone | 1 | 4 | Repair of Classrooms | 1800000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 219524 | Lebeng PS | KABAYAN | Lone | 1 | 1 | Repair of Classrooms | 1323000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 318903 | Tawangan-Lusod NHS | KABAYAN | Lone | 1 | 2 | Repair of Classrooms | 1575000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135572 | Kaliwaga Barrio School | KAPANGAN | Lone | 1 | 4 | Repair of Classrooms | 1800000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135583 | Pudong ES | KAPANGAN | Lone | 1 | 7 | Repair of Classrooms | 5500000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 501810 | Tacadang Integrated School | KIBUNGAN | Lone | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | completed
REPAIR 2023 | CAR | Benguet | 135646 | Cabacab Elementary School | MANKAYAN | Lone | 1 | 5 | Repair of Classrooms | 4875000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 305155 | Mankayan National High School | MANKAYAN | Lone | 1 | 10 | Repair of Classrooms | 9400000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135673 | Bayabas ES | SABLAN | Lone | 1 | 2 | Repair of Classrooms | 105000 | DEPED (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135707 | Besong-Saddle PS | TUBA | Lone | 1 | 1 | Repair of Classrooms | 703500 | DEPED (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135718 | Albis ES | TUBLAY | Lone | 1 | 11 | Repair and Improvement of School Facilities | 8140000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135720 | Baayan ES | TUBLAY | Lone | 1 | 9 | Repair and Improvement of School Facilities | 6660000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135742 | Awayan ES - Annex | AGUINALDO | Lone | 1 | 5 | Repair of Classrooms | 3011337.85 | DPWH (Batch 2) |  | COMPLETED | 100% | 2024-07-01 | [22 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135776 | Namillangan ES | ALFONSO LISTA (POTIA) | Lone | 1 | 3 | Repair of Classrooms | 2576681.62 | DPWH (Batch 2) |  | COMPLETED | 100% | 2024-06-01 | [22 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135783 | San Marcos ES | ALFONSO LISTA (POTIA) | Lone | 1 | 4 | Repair of Classrooms | 3456627.55 | DPWH (Batch 2) |  | COMPLETED | 100% | 2024-07-01 | [22 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Ifugao | 135830 | Uhaj Elementary School | BANAUE | Lone | 1 | 5 | Repair of Classrooms | 2937266.66 | DPWH (Batch 2) |  | COMPLETED | 100% | 2024-07-01 | [22 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | Lone | 1 | 4 | Repair of Classrooms | 2973883.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 135981 | Salegseg Primary School | BALBALAN | Lone | 1 | 2 | Repair of Classrooms | 774848.08 | DEPED (Batch 2) | 0 | COMPLETED | 100% | [10 empty] | for Award | [12 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | Lone | 1 | 6 | Repair of Classrooms | 3402560.17 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136030 | Pasil CS-Pugong Annex | PASIL | Lone | 1 | 2 | Repair of Classrooms | 830356.32 | DEPED (Batch 2) | 0 | COMPLETED | 100% | [10 empty] | Failure of Bidding (2nd time) For Re-posting | [12 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136059 | Kullayanan Elementary School | PINUKPUK | Lone | 1 | 3 | Repair of Classrooms | 1017441.71 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136066 | Anonang Elementary School | RIZAL (LIWAN) | Lone | 1 | 2 | Repair of Classrooms | 1415699.66 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136120 | Allubaggan Elementary School | TANUDAN | Lone | 1 | 3 | Repair of Classrooms | 1706146.77 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136122 | Pagugo Elementary School | TANUDAN | Lone | 1 | 6 | Repair of Classrooms | 2776711.21 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 305260 | Panabungen School of Arts, Trades, and Home Industries | BESAO | Lone | 1 | 10 | Repair of Classrooms | 16174098.5 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | Lone | 1 | 7 | Repair of Classrooms | 13090971.43 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319206 | Data National High School | SABANGAN | Lone | 1 | 8 | Repair of Classrooms | 6419083.45 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 136365 | Ilang Primary School | TADIAN | Lone | 1 | 1 | Repair of Classrooms | 1881319.77 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319223 | Mabalite National High School | TADIAN | Lone | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136085 | Agbannawag Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 22 | Repair of Classrooms | 22523445.42 | DPWH (Batch 2) | 21730038.06 | COMPLETED | 100% | September 25, 2023 | August 22, 2024 | 23PL0136 | 23PL0136 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | QUINONES CONSTRUCTION | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Tabuk City | 136092 | Bulo west Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 4912187.16 | DPWH (Batch 2) | 4734504.78 | COMPLETED | 100% | May 13, 2024 |  | 23PL0137 | 23PL0137 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | DELTA JO CONSTRUCTION (DELCONS) | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 220522 | Dananao Primary School | CITY OF TABUK (Capital) | Lone | 1 | 1 | Repair of Classroom | 1890529.88 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136168 | Gobgob Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 3 | Repair of Classrooms | 7274113.19 | DPWH (Batch 2) | 6576210.86 | COMPLETED | 100% | May 8, 2024 |  | 23PL0131 | 23PL0131 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 10, 2024 | BAGWIS CONSTRUCTION | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136101 | Madopdop Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 9 | Repair of Classrooms | 9317195.2 | DPWH (Batch 2) | 8316388.82 | COMPLETED | 100% | July 12, 2024 |  | 23PL035 | 23PL035 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | COLUMBIAN CONSTRUCTION SERCIVES | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Tabuk City | 136102 | Magabbangon Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 1 | Repair of Classroom | 1269060.16 | DPWH (Batch 2) | 1220837.95 | COMPLETED | 100% | April 7, 2024 |  | 23PL0132 | 23PL0132 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 9, 2024 | JBC BUILDERS | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 305207 | Nambucayan National High School | CITY OF TABUK (Capital) | Lone | 1 | 3 | Repair of Classrooms | 6321278.02 | DPWH (Batch 2) | 5942542.5 | COMPLETED | 100% | May 14, 2024 |  | 23PL0133 | 23PL0133 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 16, 2024 | BIGA CONSTRUCTION | [13 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CARAGA | Agusan del Norte | 131454 | San Roque Elementary School | KITCHARAO | 2nd | 1 | 5 | Repair of Classrooms | 5135688.01 | DPWH (Batch 1) |  | Completed | 100% | [23 empty] | 97% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Agusan del Norte | 131532 | Luis B. Azura Sr. Memorial ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 3 | Repair of Classrooms | 3613007.04 | DPWH (Batch 1) |  | Completed | 100% | [23 empty] | 97% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Agusan del Norte | 211510 | Poblacion Doz ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 1 | Repair of Classroom | 1680407.71 | DPWH (Batch 1) |  | Completed | 100% | [23 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 3 | Repair of Classroom | 3822833.56 | DPWH (Batch 1) |  | Completed | 100% | [23 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Cabadbaran City | 131515 | Bayabas ES | CITY OF CABADBARAN | 2nd | 1 | 4 | Repair of Classrooms | 3426370.76 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Cabadbaran City | 131516 | Caasinan ES | CITY OF CABADBARAN | 2nd | 1 | 7 | Repair of Classrooms | 5738052.81 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Suspended | [12 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Cabadbaran City | 317312 | La Union National High School | CITY OF CABADBARAN | 2nd | 1 | 2 | Repair of Classrooms | 1744136.59 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Cabadbaran City | 501722 | Mahaba Integrated School | CITY OF CABADBARAN | 2nd | 1 | 2 | Repair of Classrooms | 1864350.77 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Dinagat Island | 132488 | De La Concepcion Elementary School | BASILISA (RIZAL) | Lone | 1 | 4 | Repair of Classrooms | 3915940.43 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-15 | [22 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Dinagat Island | 132499 | Navarro Elementary School | BASILISA (RIZAL) | Lone | 1 | 5 | Repair of Classrooms | 4956773.29 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-04-10 | [22 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Dinagat Island | 132502 | Paniog Elementary School | BASILISA (RIZAL) | Lone | 1 | 6 | Repair of Classrooms | 5267468.18 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-15 | [22 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | Lone | 1 | 6 | Repair of Classrooms | 6398647.58 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-29 | [22 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | Lone | 1 | 8 | Repair of Classrooms | 7044886.13 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-04-20 | [22 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Dinagat Island | 132516 | Don Ruben Elementary School | SAN JOSE (Capital) | Lone | 1 | 6 | Repair of Classrooms | 5634902.24 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-15 | [22 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132126 | Consolacion Elementary School | DAPA | 1st | 1 | 6 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 304774 | Dapa National High School | DAPA | 1st | 1 | 15 | Repair of Classrooms | 8000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1st | 1 | 25 | Repair of Classrooms | 8020106.85 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132167 | Dumoyog Primary School | DEL CARMEN | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 1st | 1 | 7 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 1st | 1 | 4 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1st | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | 31 | Repair of Classrooms | 21000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1st | 1 | 9 | Repair of Classrooms | 9000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132181 | Caridad Elementary School | PILAR | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132183 | Datu Elementary School | PILAR | 1st | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132193 | Buhing Calipay Elementary School | SAN ISIDRO | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132194 | Del Pilar Elementary School | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132203 | Tambacan Elementary School | SAN ISIDRO | 1st | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132204 | Tigasao Elementary School | SAN ISIDRO | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132205 | Abad Santos Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132211 | Magsaysay Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 4 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1st | 1 | 28 | Repair of Classrooms | 12042759.68 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Siargao | 132233 | Lawigan Primary School | SOCORRO | 1st | 1 | 1 | Repair of Classroom | 1000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132238 | San Roque Elementary School | SOCORRO | 1st | 1 | 6 | Repair of Classrooms | 5600000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1st | 1 | 24 | Repair of Classrooms | 14000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132240 | Sta. Cruz Community Elementary School | SOCORRO | 1st | 1 | 3 | Repair of Classrooms | 2941515.74 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Siargao | 132241 | Sudlon Elementary School | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2nd | 1 | 8 | Repair of Classrooms | 4519728.71 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 132336 | Lope R. Ruiz Memo. ES (Japson ES) | SURIGAO CITY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 3478396.02 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 132297 | Mabua ES | SURIGAO CITY (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 6494027.1 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 317706 | Manjagao National High School | SURIGAO CITY (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3897705.12 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 132254 | Mariano Espina Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 28 | Repair of Classrooms | 9832305.46 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 132266 | Martinez ES | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1152448.4 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 132268 | Navarro MCES | SURIGAO CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 8535127.86 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 132269 | Quezon ES | SURIGAO CITY (Capital) | 2nd | 1 | 10 | Repair of Classrooms | 4795113.82 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 304796 | Rizal National High School | SURIGAO CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 5104510.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 132272 | Surigao City Pilot School | SURIGAO CITY (Capital) | 2nd | 1 | 65 | Repair of Classrooms | 15292195.34 | DPWH (Batch 2) |  | Ongoing | 90% | [23 empty] | 30% | [7 empty] | Ongoing
REPAIR 2023 | CARAGA | Surigao City | 132261 | Talisay Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 1114894.39 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao City | 132243 | Vicente C. Cabilao Memorial Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 2616059.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132323 | Budlingin ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 3089549.89 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132326 | L. J. Mordeno ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 2994417.09 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2nd | 1 | 4 | Repair of Classrooms | 2973931.11 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132345 | Cambuayon ES | BACUAG | 2nd | 1 | 5 | Repair of Classrooms | 3561393.63 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | ALGAMON CONSTRUCTION | [13 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2nd | 1 | 5 | Repair of Classrooms | 2969741.05 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132454 | Cansayong ES | MALIMONO | 2nd | 1 | 7 | Repair of Classrooms | 4796584.88 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | P & G CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO | 2nd | 1 | 5 | Repair of Classrooms | 3595637.83 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | P & G CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2nd | 1 | 3 | Repair of Classrooms | 1517569.64 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | P & G CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132461 | Masgad ES | MALIMONO | 2nd | 1 | 4 | Repair of Classrooms | 2994977.65 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 304831 | Masgad National High School | MALIMONO | 2nd | 1 | 2 | Repair of Classrooms | 1583416.01 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132332 | Balite ES | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 4 | Repair of Classrooms | 2973931.11 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 304843 | San Francisco National High School | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 22 | Repair of Classrooms | 13362803.04 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | ROMZ BUILDERS | [13 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao del Norte | 132529 | Hinapayaw ES | SISON | 2nd | 1 | 3 | Repair of Classrooms | 2123142.38 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | C.V. CONSTRUCTION AND DEVELOPMENT | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132531 | Mabuhay ES | SISON | 2nd | 1 | 6 | Repair of Classrooms | 4183100.34 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. Memorial National High School | SISON | 2nd | 1 | 24 | Repair of Classrooms | 6190616.74 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | MIGO CONSTRUCTION | [13 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte National High School | SURIGAO CITY (Capital) | 2nd | 1 | 44 | Repair of Classrooms | 27946795.68 | DPWH (Batch 2) |  | Ongoing | 95% | [9 empty] | 471 LP CONSTRUCTION | [13 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | CARAGA | Surigao del Norte | 132541 | Himama-ug ES | TAGANA-AN | 2nd | 1 | 5 | Repair of Classrooms | 3697672.92 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 60% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2nd | 1 | 2 | Repair of Classrooms | 1578935.52 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CARAGA | Surigao del Norte | 132564 | Mahucdam ES | TUBOD | 2nd | 1 | 2 | Repair of Classrooms | 1515050.58 | DPWH (Batch 2) |  | COMPLETED | 100% | [9 empty] | AMALGO CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1st | 1 | 44 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17111059.79 | COMPLETED | 100% | 2024-07-11 | 2024-06-03 | P00775535NP | 23OD0252 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | WAWAO BUILDERS | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Caloocan City | 305388 | Caloocan HS | KALOOKAN CITY | 2nd | 1 | 102 | Repair of Classrooms | 16991645.34 | DPWH (Batch 2) | 16164581.01 | COMPLETED | 100% | 2024-10-10 | N/A | P00775536NP | 23OD0254 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | AYLAN CONSTRUCTION & TRADING | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Caloocan City | 136649 | Tala ES | KALOOKAN CITY | 3rd | 1 | 64 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17120138.36 | completed | 100% | 2024-10-10 | N/A | P00775537NP | 23OD0253 | 27/09/2023 | 2023-04-10 | 28/11/2023 | 27/12/2023 | 15/01/2024 | FRAMECON BUILDERS | [13 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | NCR | Las Piñas City | 136789 | Pilar Village Elementary School | CITY OF LAS PIÑAS | Lone | 1 | 15 | Repair of Classrooms | 8000000 | DPWH (Batch 2) | 7488565.82 | COMPLETED | 100% | 2024-06-14 | 2024-06-14 | P00775578NP | 23OI0115 | 2024-01-05 | 2024-01-12 | 2024-01-25 | 2024-02-07 | 2024-02-23 | Framecon Builders | waiting the installation of the Solar Control Pannel c/o meralco application | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | NCR | Mandaluyong City | 500334 | Jose Fabella Memorial School | CITY OF MANDALUYONG | Lone | 1 | 32 | Repair of Classrooms | 9746347.14 | DPWH (Batch 2) | 9265002.62 | COMPLETED | 100% | 2024-05-17 | 2024-05-16 | P00775539NP | 23OB0466 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-18 | FRANZCOR TRADING AND CONSTRUCTION | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Manila | 500566 | T. Paez Integrated School | TONDO | 1st | 1 | 40 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% |  | 2024-05-24 | [21 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136444 | Gen. Maximino Hizon Elementary School | TONDO | 2nd | 1 | 24 | Repair of Classrooms | 23500000 | DPWH (Batch 2) |  | COMPLETED | 100% |  | 2024-08-24 | [8 empty] | Completed 12 classrooms only | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4th | 1 | 12 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% |  | 2024-03-24 | [21 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | NCR | Manila | 136474 | Dr. Celedonio A. Salvador Elementary School | PACO | 5th | 1 | 43 | Repair of Classrooms | 22262842.81 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2023 | NCR | Paranaque City | 136763 | F. Serrano Sr. Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 60 | Repair of Classrooms | 18000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 137127 | Marcelo Green Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 40 | Repair of Classrooms | 2000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 305975 | Marcelo Green High School Parañaque | CITY OF PARAÑAQUE | 2nd | 1 | 16 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Paranaque City | 320204 | Sun Valley National High School | CITY OF PARAÑAQUE | 2nd | 1 | 40 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 136724 | Bambang Elementary School | CITY OF PASIG | Lone | 1 | 20 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9648509.54 | COMPLETED | 100% | 2024-05-17 | 2024-05-17 | P00775548NP | 23OB0462 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Prudent Diamond Square Construction Co. | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 305418 | Manggahan High School | CITY OF PASIG | Lone | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4342216.28 | COMPLETED | 100% | 2024-03-18 | 2024-02-19 | P00775551NP | 23OB0465 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Prudent Diamond Square Construction Co. | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 136742 | Maybunga Elementary School | CITY OF PASIG | Lone | 1 | 12 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3859664.34 | COMPLETED | 100% | 2024-03-18 | 2024-02-19 | P00775549NP | 23OB0463 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | 816 Ember Construction Corp. | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | Lone | 1 | 16 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9601704.9 | COMPLETED | 100% | 2024-05-17 | 2024-06-30 | P00775550NP | 23OB0464 | 2023-09-20 | 2023-09-28 | 2023-10-25 | 2024-01-09 | 2024-01-19 | Dahl Construction Corp. | Revised target date of completion: July 1, 2024 | [12 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Quezon City | 136499 | Bayanihan Elementary School | QUEZON CITY | 1st | 1 | 12 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1909971.31 | COMPLETED | 100% | 2024-05-03 | 2024-03-18 |  | 23OF0171 | 2023-09-22 | 2023-09-29 | 2023-10-11 | 2023-12-29 | 2024-01-05 | FRAMECON BUILDERS | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Quezon City | 136502 | Paltok ES | QUEZON CITY | 1st | 1 | 10 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3343725 | COMPLETED | 100% | 2024-05-03 | 2024-03-18 |  | 23OF0171 | 2023-09-22 | 2023-09-29 | 2023-10-11 | 2023-12-29 | 2024-01-05 | FRAMECON BUILDERS | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | completed
REPAIR 2023 | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2nd | 1 | 32 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17039839.13 | COMPLETED | 100% | 2024-08-09 | N/A | P00775555NP | 23OD0249 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | NCR | Valenzuela City | 320403 | Mapulang Lupa National High School | CITY OF VALENZUELA | 2nd | 1 | 21 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17038731.62 | COMPLETED | 100% | 2024-08-09 | N/A | P00775556NP | 23OD05251 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2023 | NCR | Valenzuela City | 305446 | Sitero Francisco Memorial National High School | CITY OF VALENZUELA | 2nd | 1 | 21 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 17034781.35 | COMPLETED | 100% | 2024-08-09 | N/A | P00775554NP | 23OD0520 | 2024-12-30 | 2024-01-05 | 2023-10-17 | 2024-01-30 | 2024-02-12 | Giltop Civil Engineering Construction | for final inspection of DepEd | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2023 | Region I | Batac City | 100077 | Cumcumraas-Manggaddi-Pitpitac ES | CITY OF BATAC | 2nd | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 2883055.04 | COMPLETED | 100% |  |  |  | 23AB0192 | [5 empty] | KRB Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2023 | Region I | Batac City | 100081 | Naguirangan-Capacuan ES | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1917176.65 | COMPLETED | 100% |  |  |  | 23AB0193 | [5 empty] | KRB Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2023 | Region I | Candon City | 100425 | Allangigan Elementary School | CITY OF CANDON | 2nd | 1 | 6 | Repair of Classrooms | 2656157 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | ongoing ( For joint punchlisting) | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 100431 | Balingaoan Elementary School | CITY OF CANDON | 2nd | 1 | 9 | Repair of Classrooms | 3620000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | ongoing ( For joint punchlisting) | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 100433 | Calaoa-an Elementary School | CITY OF CANDON | 2nd | 1 | 8 | Repair of Classrooms | 5360000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 100438 | Filomeno G. Gagarin Elementary School | CITY OF CANDON | 2nd | 1 | 2 | Repair of Classrooms | 451620 | DEPED (Batch 1) | 339198.12 | COMPLETED | 100% | 2023-11-02 | 2023-10-27 |  |  |  |  | 2023-09-14 | 2023-09-15 | 2023-09-19 | M.A TEJADA CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 100443 | Parioc East Elementary School | CITY OF CANDON | 2nd | 1 | 4 | Repair of Classrooms | 1771000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | ongoing ( For joint punchlisting) | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 100448 | Sto. Tomas Elementary School | CITY OF CANDON | 2nd | 1 | 2 | Repair of Classrooms | 268000 | DEPED (Batch 1) | 223763.21 | COMPLETED | 100% | 2023-11-02 | 2023-10-27 |  |  |  |  | 2023-09-14 | 2023-09-15 | 2023-09-19 | M.A TEJADA CONSTRUCTION | [13 empty] | 100% |  |  | 1.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 1206884.64 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | ongoing ( For joint punchlisting) | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4th | 1 | 20 | Repair of Classrooms | 13000000 | DPWH (Batch 2) | 12168650 | COMPLETED | 100% | 2024-06-24 | 2024-06-04 | P00775560NP | 23AH0185 | 2023-09-28 | 2023-10-05 | 2023-09-28 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | 24 | Repair of Classrooms | 20000000 | DPWH (Batch 2) | 16076900 | COMPLETED | 100% | 2024-08-08 | 2024-07-26 | P00775561NP | 23AH0186 | 2023-09-28 | 2023-10-05 | 2023-09-28 | 2023-12-27 | 2024-01-12 | Aquino-dela Cruz Engineering & Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region I | Dagupan City | 500054 | Federico N. Ceralde Integrated School | DAGUPAN CITY | 4th | 1 | 18 | Repair of Classrooms | 15000000 | DPWH (Batch 2) | 14040750 | COMPLETED | 100% | 2024-06-19 | 2024-06-19 | P00775563NP | 23AH0188 | 2023-10-04 | 2023-10-11 | 2023-10-04 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region I | Dagupan City | 102168 | Gen. Gregorio del Pilar ES | DAGUPAN CITY | 4th | 1 | 9 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4680250 | COMPLETED | 100% | 2024-08-23 | 2024-07-26 | P00775559NP | 23AH0184 | 2023-10-03 | 2023-10-10 | 2023-10-03 | 2023-12-27 | 2024-01-12 | Alphatec Chemical Corporation | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY | 4th | 1 | 6 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11232690 | COMPLETED | 100% | 2024-08-08 |  | P00775562NP | 23AH0187 | 2023-10-04 | 2023-10-11 | 2023-10-04 | 2024-03-26 | 2024-04-11 | JG Garcia Construction & Supply. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2023 | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | Burgos | 1st | 1 | 6 | Repair of Classrooms | 1134028.03 | DPWH (Batch 1) |  | completed | 100% | [23 empty] | 7% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 100108 | Saoit-Pagali Elementary School | Burgos | 1st | 1 | 3 | Repair of Classrooms | 861853.58 | DEPED (Batch 1) | 772141.52 | COMPLETED | 100% | 2024-02-01 | 2024-01-25 |  |  | 2023-09-29 |  | 2023-10-04 |  | 2023-11-28 | Plutus Construction | with variation order | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Norte | 100233 | Virbira-Angset ES | Carasi | 1st | 1 | 2 | Repair of Classrooms | 1521626.4 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | Dumalneg | 1st | 1 | 4 | Repair of Classrooms | 2978059.35 | DPWH (Batch 1) |  | completed | 100% | [23 empty] | 7% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 320808 | Bamasesamar National High School | DINGRAS | 2nd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 320811 | Marcos NHS (Agunit) | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 150018 | Barikir ES | NUEVA ERA | 2nd | 1 | 4 | Repair of Classrooms | 2972000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 150019 | Bugayong Elementary Sch. | NUEVA ERA | 2nd | 1 | 4 | Repair of Classrooms | 2972000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 100142 | Cabittauran ES | NUEVA ERA | 2nd | 1 | 9 | Repair of Classrooms | 7320000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 7 | Repair of Classrooms | 5834000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Norte | 300022 | NUEVA ERA NATIONAL HIGH SCHOOL | NUEVA ERA | 2nd | 1 | 2 | Repair of Classrooms | 1486000 | DPWH (Batch 2) |  | completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Ilocos Sur | 100370 | Bantay East Central School | BANTAY | 1st | 1 | 1 | Repair of Classrooms | 171274.37 | DEPED (Batch 2) | 164776.32 | COMPLETED | 100% | 2024-09-04 | 2024-07-31 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100455 | Cal-laguip Elementary School | CAOAYAN | 1st | 1 | 1 | Repair of Classrooms | 650953.97 | DEPED (Batch 2) | 627991.64 | COMPLETED | 100% | 2024-09-04 | 2024-08-19 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100457 | Fuerte Elementary School | CAOAYAN | 1st | 1 | 1 | Repair of Classrooms | 67833.32 | DEPED (Batch 2) | 65000.25 | COMPLETED | 100% | 2024-09-04 | 2024-08-07 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300040 | Belen NHS | SAN ILDEFONSO | 1st | 1 | 4 | Repair of Classrooms | 1566106.43 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | 2024-05-30 | [18 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100605 | Sabangan Elementary School | SAN JUAN (LAPOG) | 1st | 1 | 1 | Repair of Classrooms | 746663.48 | DEPED (Batch 2) | 720286.69 | COMPLETED | 100% | 2024-09-04 | 2024-08-19 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100662 | Paratong ES | SANTA CATALINA | 1st | 1 | 1 | Repair of Classrooms | 341100.3 | DEPED (Batch 2) | 328902.72 | COMPLETED | 100% | 2024-09-04 | 2024-08-19 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100341 | Nagawa Elem. School | SUGPON | 1st | 1 | 3 | Repair of Classrooms | 2009000 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | [19 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300041 | Burgos National High School | BURGOS | 2nd | 1 | 8 | Repair of Classrooms | 4420000 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | [19 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100395 | Padayao ES | BURGOS | 2nd | 1 | 4 | Repair of Classrooms | 2102500 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | [19 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100555 | Alfonso Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 5 | Repair of Classrooms | 3397118.23 | DPWH (Batch 1) |  | Ongoing | 90% |  |  |  | n/a | [19 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region I | Ilocos Sur | 100348 | Banucal Elementary School | LIDLIDDA | 2nd | 1 | 4 | Repair of Classrooms | 1771000 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | [19 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100516 | Banglayan Elementary School | NARVACAN | 2nd | 1 | 4 | Repair of Classrooms | 1671500 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | n/a | [19 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100544 | Narvacan South Central School SPED Center | NARVACAN | 2nd | 1 | 1 | Repair of Classrooms | 355902.25 | DEPED (Batch 2) | 343295.67 | COMPLETED | 100% | 2024-09-04 | 2024-08-19 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300070 | Quirino NHS | QUIRINO (ANGKAKI) | 2nd | 1 | 4 | Repair of Classrooms | 2501576.27 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [18 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 500598 | KALUMSING INTEGRATED SCHOOL | SAN EMILIO | 2nd | 1 | 6 | Repair of Classrooms | 2265500 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [18 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2nd | 1 | 10 | Repair of Classrooms | 6101308 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [18 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 500346 | Mabilbila IS | SANTA | 2nd | 1 | 8 | Repair of Classrooms | 3700000 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [18 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300034 | Amarao NHS | SANTA CRUZ | 2nd | 1 | 4 | Repair of Classrooms | 1640000 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [18 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100702 | Babal-lasioan ES | SANTA MARIA | 2nd | 1 | 6 | Repair of Classrooms | 364000 | DEPED (Batch 1) | 349195.1 | COMPLETED | 100% | 2023-12-30 | 2023-12-18 | n/a | 10284126 | 2023-11-07 | n/a | 2023-11-09 | 2023-11-10 | 2023-11-16 | M.A TEJADA CONSTRUCTION | . | [12 empty] | 100% |  |  | 1.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 150504 | Matallucod PS | SIGAY | 2nd | 1 | 1 | Repair of Classroom | 1220000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 300036 | Sugpon NHS | SUGPON | 2nd | 1 | 8 | Repair of Classrooms | 5383154.75 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Ilocos Sur | 100744 | Bangcag ES | SUYO | 2nd | 1 | 1 | Repair of Classrooms | 319898.6 | DEPED (Batch 2) | 308326.76 | COMPLETED | 100% | 2024-09-04 | 2024-08-05 | PB-01-2024 | n/a | 2024-05-30 | 2024-06-06 | 2024-06-20 | 2024-07-05 | 2024-07-22 | Cleofel Construction | rebidded | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100842 | Baroro Elementary School | BACNOTAN | 1st | 1 | 4 | Repair of Classrooms | 5635648.16 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100883 | Nagsabaran Sur ES | BALAOAN | 1st | 1 | 9 | Repair of Classrooms | 7178402.12 | DPWH (Batch 2) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100885 | Pantar ES | BALAOAN | 1st | 1 | 3 | Repair of Classrooms | 3054148.66 | DPWH (Batch 2) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100888 | Patpata ES | BALAOAN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100899 | Ma. Cristina ES | BANGAR | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% |  |  |  |  | 2024-05-30 | [5 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100905 | Sinapangan ES | BANGAR | 1st | 1 | 8 | Repair of Classrooms | 6416677.87 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 321018 | Luna National Vocational High School | LUNA | 1st | 1 | 5 | Repair of Classrooms | 1741895.36 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100962 | Nagrebcan ES | LUNA | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100953 | Nalvo Norte ES | LUNA | 1st | 1 | 4 | Repair of Classrooms | 4069020.57 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100954 | Rimos del Norte ES | LUNA | 1st | 1 | 8 | Repair of Classrooms | 7020859.31 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100955 | Rimos ES | LUNA | 1st | 1 | 3 | Repair of Classrooms | 3634688.88 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101047 | Amontoc ES | SAN GABRIEL | 1st | 1 | 2 | Repair of Classrooms | 2122094.77 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 300097 | Balbalayang National High School | SAN GABRIEL | 1st | 1 | 2 | Repair of Classrooms | 2932062.07 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101050 | Bumbuneg ES | SAN GABRIEL | 1st | 1 | 5 | Repair of Classrooms | 4918234.85 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 500356 | Lipay Integrated School | SAN GABRIEL | 1st | 1 | 8 | Repair of Classrooms | 6416677.87 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101060 | Bacsayan Elementary School | SAN JUAN | 1st | 1 | 1 | Repair of Classrooms | 1186264.29 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101066 | Legleg Elementary School | SAN JUAN | 1st | 1 | 1 | Repair of Classrooms | 1161310.95 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101072 | Sta. Rosa Elementary School | SAN JUAN | 1st | 1 | 7 | Repair of Classrooms | 5896259.41 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101074 | Taboc ES | SAN JUAN | 1st | 1 | 4 | Repair of Classrooms | 4054407.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101075 | Urbiztondo ES | SAN JUAN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 500471 | BAY-O ELEMENTARY SCHOOL | SANTOL | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101078 | Corrooy ES | SANTOL | 1st | 1 | 4 | Repair of Classrooms | 4095996.47 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 300107 | Corrooy National High School | SANTOL | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101107 | Duplas ES | SUDIPEN | 1st | 1 | 6 | Repair of Classrooms | 5111840.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 300117 | Duplas National High School | SUDIPEN | 1st | 1 | 4 | Repair of Classrooms | 3998921.04 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2nd | 1 | 4 | Repair of Classrooms | 14993885.31 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 500352 | Dagup Integrated School | BAGULIN | 2nd | 1 | 7 | Repair of Classrooms | 4175991.07 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 300149 | Suyo National High School | BAGULIN | 2nd | 1 | 2 | Repair of Classrooms | 3999536.28 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100907 | Acao Elementary School | BAUANG | 2nd | 1 | 1 | Repair of Classrooms | 1692994.44 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100908 | Baccuit Elementary School | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100913 | Bigbiga ES | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 3999549.4 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100919 | Bucayab Elementary School | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 2999805.61 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 501196 | Parian Este Integrated School | BAUANG | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100914 | Paringao ES | BAUANG | 2nd | 1 | 4 | Repair of Classrooms | 14015971.39 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 300128 | Paringao National High School | BAUANG | 2nd | 1 | 5 | Repair of Classrooms | 3999536.28 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100926 | Payocpoc Este ES | BAUANG | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100915 | PUGO ELEMENTARY SCHOOL | BAUANG | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 500600 | Libtong Integrated School | BURGOS | 2nd | 1 | 10 | Repair of Classrooms | 8465065.66 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100991 | Naguilian CS | NAGUILIAN | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 100993 | San Isidro ES | NAGUILIAN | 2nd | 1 | 6 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101093 | Casilagan ES | SANTO TOMAS | 2nd | 1 | 3 | Repair of Classrooms | 3000000.6 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101100 | Patac Elementary School | SANTO TOMAS | 2nd | 1 | 2 | Repair of Classrooms | 1999675.04 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | La Union | 101127 | Pideg Elementary school | TUBAO | 2nd | 1 | 3 | Repair of Classrooms | 5999842.13 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | COMPLETED | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101237 | Dacap Sur ES | BANI | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101446 | Eguia ES | DASOL | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101448 | Macalang ES | DASOL | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101461 | Bayambang ES | INFANTA | 1st | 1 | 3 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN (Capital) | 2nd | 1 | 9 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN (Capital) | 2nd |  | 12 | Repair of Classrooms | 15000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan I, Lingayen | 101439 | Songkoy ES | CALASIAO | 3rd | 1 | 2 | Repair of Classrooms | 1345728.66 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5th | 1 | 2 | Repair of Classrooms | 1300000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6th | 1 | 16 | Repair of Classrooms | 9315000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300339 | Rajal Angayan NHS | BALUNGAO | 6th | 1 | 1 | Repair of Classrooms | 366000 | DEPED (Batch 2) | 352644.42 | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6th | 1 | 24 | Repair of Classrooms | 2700000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6th | 1 | 26 | Repair of Classrooms | 18800000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 102070 | Evangelista ES | TAYUG | 6th | 1 | 6 | Repair of Classrooms | 1957849.1 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 70% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6th | 1 | 32 | Repair of Classrooms | 20420000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300327 | Maseil-seil Alo-o NHS | UMINGAN | 6th | 1 | 4 | Repair of Classrooms | 2840770.36 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6th | 1 | 24 | Repair of Classrooms | 1767551.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region I | Vigan City | 100785 | Burgos Memorial School East | CITY OF VIGAN (Capital) | 1st | 1 | 9 | Repair of Classrooms | 3304786.06 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Vigan City | 100788 | Camangaan Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 4 | Repair of Classrooms | 1368182.96 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region I | Vigan City | 100792 | Mindoro Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 8 | Repair of Classrooms | 3109031.85 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Vigan City | 100794 | Pantay Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 1 | Repair of Classrooms | 928788.93 | DEPED (Batch 2) | 795358.48 | COMPLETED | 100% | 2024-02-29 | 2024-02-29 | [8 empty] | with variation order with punchlist/corrective materials | [12 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Vigan City | 100795 | Raois Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 12 | Repair of Classrooms | 6626284.41 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region I | Vigan City | 100799 | Tamag Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1422689.82 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | 21 | Repair of Classrooms | 5441432.43 | DPWH (Batch 1) | 4724632.2 | COMPLETED | 100% | January 21, 2024 | January 21, 2024 |  | 23BA0059 | [5 empty] | J.F GABOTERA INC. | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 300414 | Itbayat National Agricultural High School | ITBAYAT | Lone | 1 | 6 | Repair of Classrooms | 2784191.27 | DPWH (Batch 1) | 2685153.17 | COMPLETED | 100% | December 8, 2023 | November 16, 2023 |  | 23BA0062 | [5 empty] | MOJR CONST., TRADING AND GE. SERVICES LTD. CO. | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 102322 | Ivana Elementary School | IVANA | Lone | 1 | 3 | Repair of Classrooms | 2086393.1 | DPWH (Batch 1) | 2013368.34 | COMPLETED | 100% | December 12, 2023 | January 15, 2024 |  | 23BA0064 | [5 empty] | PC VALENCIA CONSTRUCTION | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | Lone | 1 | 8 | Repair of Classrooms | 8623639.08 | DPWH (Batch 1) | 6728184.78 | Ongoing | 85% | February 14, 2024 | N/A |  | 23BA0066 | [5 empty] | JERIS CONSTRUCTION AND SUPPLY | Ongoing contract subejct to liquidated damages | [12 empty] | 85% | [7 empty] | ongoing
REPAIR 2023 | Region II | Batanes | 300413 | Batanes Gen. Comp. HS | UYUGAN | Lone | 1 | 6 | Repair of Classrooms | 2021931.7 | DPWH (Batch 1) | 1946156.1 | COMPLETED | 100% | December 8, 2023 | January 24, 2024 |  | 23BA0061 | [5 empty] | SWIFT DEV'T AND SUPPLIES CORP. | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Batanes | 102324 | Uyugan Elementary School | UYUGAN | Lone | 1 | 8 | Repair of Classrooms | 4162420.7 | DPWH (Batch 1) | 3711074.29 | COMPLETED | 100% | December 9, 2023 | February 28, 2024 |  | 23BA0060 | [5 empty] | J.F GABOTERA INC. | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102331 | Abulug Central Elementary School | ABULUG | 2nd | 1 | 5 | Repair of Classrooms | 2678156.25 | DPWH (Batch 2) | 2557794.55 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0266 |  |  |  | 12/27/23 | 12/27/23 | JG YAKAS CONST | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300418 | Abulug National Rural and Vocational High School | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1827157.13 | DPWH (Batch 2) | 1745479.65 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0240 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONSTRUCTION | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2nd | 1 | 9 | Repair of Classrooms | 5260296.29 | DPWH (Batch 2) | 5024938.59 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING WITH 9 CL | 23BC0245 | October 26, 2023 | November 6, 2023 | November 20, 2023 | 12/21/2024 | 12/21/2024 | JG YAKAS CONSTRUCTION | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102333 | Bagu ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1712200.98 | DPWH (Batch 2) | 1635484.62 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0259 |  |  |  | 12/27/23 | 12/27/23 | JG YAKAS CONST | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102334 | Banguian ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1172334.44 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0212 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102335 | Calog Norte ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 1732500 | DPWH (Batch 2) | 1654668.7 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-1-CL | 23BC0213 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102336 | CALOG SUR ELEMENTARY SCHOOL | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1386000 | DPWH (Batch 2) | 1386000 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102337 | Canayun ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 1198312.5 | DPWH (Batch 2) | 1134423.11 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING 1CL | 23BC0249 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102338 | Dana-ili ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227718.5 | DPWH (Batch 2) | 1160880.2 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0248 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102340 | Guiddam ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1227187.5 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102341 | Libertad Elementary School | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1176656.25 | DPWH (Batch 2) | 1124101 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0236 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102342 | Lucban ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1422093.75 | DPWH (Batch 2) | 1422093.75 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102343 | Macugay ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1155000 | DPWH (Batch 2) | 1103303.18 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0242 |  |  |  | 12/27/2023 | 12/27/23 | JG YAKAS CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102344 | Muru ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1849443.75 | DPWH (Batch 2) | 1741849.36 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0247 | October 26, 2023 | November 6, 2023 | November 20, 2023 | 12/27/23 | 12/27/23 | OLIVA CONST | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102345 | Pinili ES | ABULUG | 2nd | 1 | 3 | Repair of Classrooms | 1227187.5 | DPWH (Batch 2) | 1172387.2 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-3CL | 23BC0207 |  |  |  | 12/27/2023 |  | JG YAKAS CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102346 | San Agustin ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1010625 | DPWH (Batch 2) | 965491.39 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0241 |  |  |  | 12/27/2023 | 12/27/2023 | JG YAKAS CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102347 | San Julian ES | ABULUG | 2nd | 1 | 1 | Repair of Classrooms | 2165625 | DPWH (Batch 2) | 2074828.12 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING -4CL | 23BC0205 |  |  |  | December 21, 2023 | December 21, 2023 | ILIVA CONSTRUCTION | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102349 | Simayung ES | ABULUG | 2nd | 1 | 2 | Repair of Classrooms | 1082812.5 | DPWH (Batch 2) | 1023601.61 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2 CL | 23BC0243 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102351 | Sta. Filomena ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1118906.25 | DPWH (Batch 2) | 1068759.65 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0250 |  |  |  | 12/27/2023 | 12/27/23 | JG YAKAS CONST | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102354 | Tayak ES | ABULUG | 2nd | 1 | 4 | Repair of Classrooms | 1479843.75 | DPWH (Batch 2) | 1479843.75 | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102603 | Alimoan ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1406765.15 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0224 |  |  |  | 12/27/202 | 12/27/2023 | BA Lagazo | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102605 | Bilibigao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1429129.76 | DPWH (Batch 2) | 1368760.88 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0232 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102606 | Buenavista-San Isidro ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1343792.21 | DPWH (Batch 2) | 1270855.92 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4cl | 23bc0225 |  |  |  | 12/27/2023 | 12/27/2023 | BJMBJ CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102608 | Claveria CS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1429129.76 | DPWH (Batch 2) | 1365308.64 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0257 |  |  |  | 12/27/23 | 12/27/23 | VG ALCANTARA INTERPRICES | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102609 | Claveria East CS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 135463.32 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0231 |  |  |  | 12/27/2023 | 12/27/2023 | VG ALCANTARA INTERPRICES | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1820329.91 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0221 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300451 | Claveria SAT | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1648763.23 | DPWH (Batch 2) | 1575145.95 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0216 |  |  |  | 12/27/2023 | 12/27/2023 | RJJ ARISTOTEL BUILDERS | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102610 | Culao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1339799.71 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0223 |  |  |  | 12/27/2023 | 12/27/2023 | 5RD KECK CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102611 | Dibalio ES | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1648763.23 | DPWH (Batch 2) | 1556671.53 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0244 |  |  |  | 12/27/23 | 12/27/23 | MARTHA CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102919 | Lablabig ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1445475.27 | DPWH (Batch 2) | 1374738.96 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING 4 CL | 23BC0208 |  |  |  | 12/27/2023 |  | A. NIDUAZA BUILDERS | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102612 | Luzon ES | CLAVERIA | 2nd | 1 | 2 | Repair of Classrooms | 1115354.62 | DPWH (Batch 2) | 1115354.62 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102920 | Mabnang ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1445475.27 | DPWH (Batch 2) | 1363897.54 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING - 4CL | 23BC0207 |  |  |  | 12/27/2023 |  | 5RDKECK CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102615 | Malilitao ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1328640.59 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0229 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102616 | Mapulapula Elementary School | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1406302.94 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0217 |  |  |  | 12/27/2023 | 12/27/2023 | BA LAGAZO | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102617 | Nagsabaran ES | CLAVERIA | 2nd | 1 | 2 | Repair of Classrooms | 1115354.62 | DPWH (Batch 2) | 1054791.25 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-2CL | 23BC0238 |  |  |  | 12/27/2023 | 12/27/2023 | BJMBJ CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102619 | Pinas ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1328865.35 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0218 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102620 | San Vicente Primary School | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1481826.35 | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102621 | Santiago ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1450732.52 | DPWH (Batch 2) | 1371992.86 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0226 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102622 | Sta. Maria PS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1404969.94 | DPWH (Batch 2) | 1329120.32 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0260 | November 8, 2023 | November 16, 2023 | November 28, 2023 | 12/27/23 | 12/27/23 | DANDEX CONST | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102623 | Sto. Tomas PS | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1404433.81 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC027 |  |  |  | 12/27/2023 | 12/27/2023 | BJMJB CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 155032 | Taggat Norte Elementary School | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1409925.69 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING 4 CL | 23BC0209 |  |  |  | 12/27/2023 | 12/27/2023 | 5RDKECK CONSTRUCTION | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102922 | Taggat Sur ES | CLAVERIA | 2nd | 1 | 4 | Repair of Classrooms | 1481826.35 | DPWH (Batch 2) | 1415662.81 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0222 |  |  |  | 12/27/2023 | 12/27/2023 | RJJ ARISTOTEL CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102923 | UNION ELEMENTARY SCHOOL | CLAVERIA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1825279.4 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING- 5CL | 23BC02010 |  |  |  | 12/27/2023 | 12/27/2023 | A. NIDUAZA | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102784 | Bidduang ES | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3743792.65 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING5CL | 23BC0244 |  |  |  | 12/27/23 | 12/27/23 | OLIVA DESIGN CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300436 | Bidduang National High School | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 1915078.41 | DPWH (Batch 2) | 1801665.02 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0229 |  |  |  | 12/27/2023 | 12/27/2023 | OLIVA DESIGN CONST | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102788 | Curva Elementary School | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1914999.29 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0230 |  |  |  | 12/27/2023 | 02/27/2023 | OLIVA DESIGN CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102792 | Pimpila ES | PAMPLONA | 2nd | 1 | 5 | Repair of Classrooms | 4463486.51 | DPWH (Batch 2) | 4178015.24 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0261 |  |  |  | 12/27/23 | 12/27/23 | OLIVA CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102839 | Lattut ES | RIZAL | 2nd | 1 | 2 | Repair of Classrooms | 1321776.89 | DPWH (Batch 1) | 1321776.89 | Ongoing | 72.22% |  |  | REPAIR OF CLASSROOM | 23BC125 | September 1, 2023 | September 8, 2023 | September 25, 2023 | 2023-03-10 | 2023-03-10 | KSC CONST | [13 empty] | 65.1% | [7 empty] | ongoing
REPAIR 2023 | Region II | Cagayan | 102844 | Rizal CS | RIZAL | 2nd | 1 | 4 | Repair of Classrooms | 1436921.32 | DPWH (Batch 2) | 1368896.49 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0219 | October 6, 2023 | October 16, 2023 | October 27, 2023 | 12/27/2023 | 12/27/2023 | KSC CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | completed
REPAIR 2023 | Region II | Cagayan | 102846 | Sinicking ES | RIZAL | 2nd | 1 | 3 | Repair of Classrooms | 1936863.12 | DPWH (Batch 1) | 1850382.18 | Completed | 100% |  |  | REPAIR OF CLASSROOM | 23BC0124 | September 1, 2023 | September 8, 2023 | September 25, 2023 | 2023-03-10 | 2023-03-10 | KSC CONST | ABANDONED | [12 empty] | 31.77% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2023 | Region II | Cagayan | 102848 | Bangan ES | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 3200000 | DPWH (Batch 2) | 3052938.24 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0214 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 155046 | Pureg Elementary School | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 3000000 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300486 | Sanchez Mira SAT | SANCHEZ-MIRA | 2nd | 1 | 5 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4299168.59 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0258 |  |  |  | 12/27/23 | 12/27/23 | JPO BUILDERS | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102915 | Cadcadir ES | SANTA PRAXEDES | 2nd | 1 | 4 | Repair of Classrooms | 1446232.87 | DPWH (Batch 2) | 1367702.43 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-4CL | 23BC0211 |  |  |  | 12/27/2023 | 12/27/2023 | BMJB CONST | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102917 | Capacuan ES | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 2) | 1910682.1 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0215 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3343725.46 | COMPLETED | 100% |  |  | REPAIR OF SCHOOL BUILDING-5CL | 23BC0220 |  |  |  | 12/27/2023 | 12/27/2023 | JPO BUILDERS | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2nd | 1 | 15 | Repair of Classrooms | 3202208.92 | DPWH (Batch 1) | 3042863.65 | COMPLETED | 100% |  |  | REPAIR OF SCHHOL BUILDING | 23B123 |  |  |  | 2023-03-10 | 2023-03-10 | A. NIDUAZA BUILDER | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2nd | 1 | 5 | Repair of Classrooms | 3200000 | DPWH (Batch 2) | 3042863.65 | COMPLETED | 100% |  |  | REPAIR OF SCHHOL BUILDING | 23BC123 |  |  |  | 2023-03-10 | 2023-03-10 | A. NIDUAZA BUILDER | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | City of Ilagan | 103359 | Batong Labang ES | CITY OF ILAGAN | 1st | 1 | 7 | Repair of Classrooms | 6192545.4 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  |  | 23BE0152 | July 21, 2023 to July 27, 2023 | 2023-07-28 | August 10, 2023 | 2023-08-30 | September 8, 2023 | SMT Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region II | Isabela | 103277 | San Macario Elementary School | DELFIN ALBANO (MAGSAYSAY) | 1st | 1 | 4 | Repair of Classrooms | 3172583.45 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region II | Isabela | 103733 | Caunayan Elementary School | SAN MARIANO | 2nd | 1 | 2 | Repair of Classrooms | 2080135.57 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5th | 1 | 3 | Repair of Classrooms | 1945125 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0104 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103489 | Harana Elementary School | LUNA | 5th | 1 | 1 | Repair of Classroom | 1296750 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0108 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103486 | Lalog Elementary School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1945125 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0105 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103487 | Luna Central School | LUNA | 5th | 1 | 1 | Repair of Classroom | 4538625 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0102 | [20 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 306150 | Luna General Comprehensive High School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1304021.86 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0106 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | 4 | Repair of Classrooms | 2593500 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0103 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103488 | Mambabanga Elementary School | LUNA | 5th | 1 | 2 | Repair of Classrooms | 1296750 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BF0107 | [20 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103565 | Callangigan Elementary School | Quezon | 5th | 1 | 3 | Repair of Classrooms | 950000 | DEPED (Batch 1) | 1449861.74 | COMPLETED | 100% | 90 days after the receipt of the Notice to Proceed |  |  | Contract No. 2023-10-03 |  | 2023-09-26 | 2023-10-09 | 2023-10-17 | 2023-11-03 | Fragerr Construction | Same Contractor for CY 2023 BASIC EDUCATION FACILITIES FUND (BEFF) REPAIR OF CLASSROOMS | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region II | Isabela | 500067 | Dolores Integrated School | Quirino | 5th | 1 | 2 | Repair of Classrooms | 950000 | DEPED (Batch 1) | 1449861.74 | COMPLETED | 100% | 90 days after the receipt of the Notice to Proceed |  |  | Contract No. 2023-10-03 |  | 2023-09-26 | 2023-10-09 | 2023-10-17 | 2023-11-03 | Fragerr Construction | Same Contractor for CY 2023 BASIC EDUCATION FACILITIES FUND (BEFF) REPAIR OF CLASSROOMS | [12 empty] | 100% |  | 1.24 | 12.23 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6th | 1 | 6 | Repair of Classrooms | 1477032.01 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BH0245 | [20 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 103704 | Quezon Elementary School | SAN ISIDRO | 6th | 1 | 11 | Repair of Classrooms | 4907044.15 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BH0247 | [20 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6th | 1 | 9 | Repair of Classrooms | 1595303.57 | DPWH (Batch 1) |  | COMPLETED | 100% |  |  | 23BH0246 | [20 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | Lone | 1 | 3 | Repair of Classrooms | 2274570 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104213 | Bintawan North Elementary School | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 2145220 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104214 | Bintawan South Elementary School | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 1974080 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104216 | Nagbitin ES | VILLAVERDE | Lone | 1 | 3 | Repair of Classrooms | 2186015 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Nueva Vizcaya | 104217 | Ocapon Elementary School | VILLAVERDE | Lone | 1 | 1 | Repair of Classroom | 768050 | DEPED (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 104376 | Magsaysay ES | SAGUDAY | Lone | 1 | 2 | Repair of Classrooms | 1287500 | DPWH (Batch 1) | 1242437.41 | COMPLETED | 100% | 2024-01-23 | 2024-01-07 | P00775089NP | 23BK0128 | 2023-08-25 | 2023-09-07 | 2023-09-19 | 2023-09-29 | 2023-10-10 | JMD-68 BUILDERS | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | Lone | 1 | 3 | Repair of Classrooms | 1937500 | DPWH (Batch 1) | 1869396.75 | COMPLETED | 100% | 2024-02-18 | 2024-01-19 | P00775090NP | 23BK0129 | 2023-09-08 | 2023-09-21 | 2023-10-03 | 2023-10-12 | 2023-10-25 | JMD-68 BUILDERS | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | Lone | 1 | 5 | Repair of Classrooms | 3237500 | DPWH (Batch 1) | 3030207.84 | COMPLETED | 100% | 2024-05-24 | 2024-04-12 | P00775091NP | 23BK0127 | 2023-08-25 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2024-01-04 | JMD-68 BUILDERS | for Final Inspection | [12 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Angeles City | 345279 | Angeles City Senior High School | ANGELES CITY | 1st | 1 | 24 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 9368895.1 | COMPLETED | 100% | 2024-07-04 | 2024-01-08 | P00775681NP | 23CI0169 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1st | 1 | 12 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 4684787.65 | COMPLETED | 100% | 2024-07-04 | 2024-01-08 | P00775678NP | 23CI0171 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 301042 | Bonifacio V. Romero HS | ANGELES CITY | 1st | 1 | 28 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 11247421.8 | COMPLETED | 100% | 2024-07-04 | 2024-01-08 | P00775679NP | 23CI0168 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 301043 | Sapang Bato National High School | ANGELES CITY | 1st | 1 | 12 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 4694244.19 | COMPLETED | 100% | 2024-05-04 | 2024-01-08 | P00775680NP | 23CI0170 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Aurora | 104408 | Anacleto V. Mijares ES | BALER (Capital) | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4156888.88 | COMPLETED | 100% | 2025-02-04 | 2024-12-12 | n/a | n/a | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-10 | 2024-10-07 | Traccor Builders | [13 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | Completed
REPAIR 2023 | Region III | Aurora | 104412 | Diego T. Ortiz ES | BALER (Capital) | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4881046.51 | COMPLETED | 100% | 2023-11-02 |  | 23cno192 | 23cno192 |  |  | 2023-08-15 |  | 2023-10-02 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104426 | Dumaguipo ES | CASIGURAN | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3 ,036,412.71 | COMPLETED | 100% | 2023-11-03 |  | 23Cno197 | 23Cno197 |  |  | 2023-08-30 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3 ,687,909.07 | COMPLETED | 100% | 2023-11-03 |  | 23Cno194 | 23Cno194 |  |  | 2023-08-30 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 500738 | Tinib-Calangcuasan IS | CASIGURAN | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3050049.55 | COMPLETED | 100% | 2023-11-14 |  | 23Cno186 | 23Cno186 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 306504 | Diagyan NHS | DILASAG | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5 ,467,954.45 | COMPLETED | 100% | 2023-11-11 |  | 23Cno179 | 23Cno179 |  |  | 2023-07-19 |  | 2023-09-05 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104445 | Dinalungan CS | DINALUNGAN | Lone | 1 | 12 | Repair of Classrooms | 7800000 | DPWH (Batch 1) | 7404483.76 | COMPLETED | 100% | 2024-01-10 |  | 23Cno198 | 23Cno198 |  |  | 2023-07-27 |  | 2023-09-12 | Conrado B. Bautista Construction and Supply Corporation | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 500751 | Cabog IS | DINGALAN | Lone | 1 | 4 | Repair of Classrooms | 2600000 | DPWH (Batch 1) | 2444152.74 | COMPLETED | 100% | 2023-12-01 |  | 23Cno185 | 23Cno185 |  |  | 2023-08-10 |  | 2023-09-25 | Vanmarvil Construction | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104455 | Dingalan CS | DINGALAN | Lone | 1 | 10 | Repair of Classrooms | 6500000 | DPWH (Batch 1) | 6 ,100,903.47 | COMPLETED | 100% | 2023-11-18 |  | 23Cno195 | 23Cno195 |  |  | 2023-07-27 |  | 2023-09-12 | Vanmarvil Construction | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 157503 | Tanawan ES | DINGALAN | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4306701.22 | COMPLETED | 100% | 2023-11-17 |  | 23Cno178 | 23Cno178 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104470 | Dipaculao CS | DIPACULAO | Lone | 1 | 12 | Repair of Classrooms | 7800000 | DPWH (Batch 1) | 7395881.08 | COMPLETED | 100% | 2024-01-07 |  | 23Cno184 | 23Cno184 |  |  | 2023-08-10 |  | 2023-10-02 | Capital Construction | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 300674 | Bayanihan NHS | MARIA AURORA | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5497707 | COMPLETED | 100% | 2023-12-01 |  | 23Cno183 | 23Cno183 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104489 | Calao ES | MARIA AURORA | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3079890.03 | COMPLETED | 100% | 2023-11-23 |  | 23Cno196 | 23Cno196 |  |  | 2023-08-15 |  | 2023-10-02 | Uliran Construction Services | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104498 | Diome ES | MARIA AURORA | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3688972.37 | COMPLETED | 100% | 2023-11-17 |  | 23Cno183 | 23Cno183 |  |  | 2023-08-10 |  | 2023-09-25 | So Construction | COMPLETED | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104505 | Punglo ES | MARIA AURORA | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3666704.41 | COMPLETED | 100% | 2023-11-17 |  | 23Cno181 | 23Cno181 |  |  | 2023-08-10 |  | 2023-09-25 | RNGM Construction | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 306503 | Ramada NHS | MARIA AURORA | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4308415.87 | COMPLETED | 100% | 2023-11-17 |  | 23Cn189 | 23Cn189 |  |  | 2023-08-15 |  | 2023-09-25 | Conrado B. Bautista Construction and Supply Corporation | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104509 | San Leonardo ES | MARIA AURORA | Lone | 1 | 2 | Repair of Classrooms | 1300000 | DPWH (Batch 1) | 1 ,216,578.15 | COMPLETED | 100% | 2023-10-17 |  | 23Cno180 | 23Cno180 |  |  | 2023-07-10 |  | 2023-09-12 | Vanmarvil Construction | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 157505 | Sto. Tomas ES | MARIA AURORA | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3041261.01 | COMPLETED | 100% | 2023-11-24 |  | 23Cno190 | 23Cno190 |  |  | 2023-09-07 |  | 2023-10-02 | RNGM Construction | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 300681 | Dikapinisan NHS | SAN LUIS | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4 ,920,254.30 | COMPLETED | 100% | 2023-11-18 |  | 23Cno194 | 23Cno194 |  |  | 2023-07-17 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104520 | Ditumabo ES | SAN LUIS | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5530921.57 | COMPLETED | 100% | 2023-11-01 |  | 23Cno188 | 23Cno188 |  |  | 2023-08-15 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104527 | San Isidro ES | SAN LUIS | Lone | 1 | 13 | Repair of Classrooms | 7700000 | DPWH (Batch 1) | 7321889.74 | COMPLETED | 100% | 2023-12-01 |  | 23Cno191 | 23Cno191 |  |  | 2023-08-15 |  | 2023-09-25 | Vanmarvil Construction | COMPLETED | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 137096 | St. Ma. Virginia P. Leonzon Memorial Elementary School | HERMOSA | 1st | 1 | 9 | Repair of Classrooms | 13500000 | DPWH (Batch 2) | 12994929.93 | COMPLETED | 100% |  |  | 23CA0078 |  | 11/01/2023 - 11/22/2023 | 2023-10-11 | 22/11/2023 | 12/06/2023 - 01/02/2024 | 14/02/2024 | San Sebastion Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104703 | Gugo ES | SAMAL | 1st | 1 | 8 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11320026.34 | COMPLETED | 100% |  |  | 23CA0079 |  | 11/01/2023 - 11/22/2023 | 2023-10-11 | 22/11/2023 | 12/06/2023 - 12/28/2023 | 15/01/2024 | Ave-Mira Constrruction and Trading | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104689 | Bagumbayan ES | PILAR | 2nd | 1 | 12 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 16961844.05 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104589 | Pinulot ES | DINALUPIHAN | 3rd | 1 | 7 | Repair of Classrooms | 10500000 | DPWH (Batch 2) | 9964092.99 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104642 | Cabcaben ES | MARIVELES | 3rd | 1 | 10 | Repair of Classrooms | 15000000 | DPWH (Batch 2) | 14146340.47 | Ongoing | 60% | [23 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Bulacan | 104816 | Pungo ES | CALUMPIT | 1st | 1 | 8 | Repair of Classrooms | 9750000 | DPWH (Batch 2) | 9220540.14 | COMPLETED | 100% | 2024-05-30 | 2024-05-30 | P00775687NP | 23CC0464 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104853 | San Jose ES | HAGONOY | 1st | 1 | 5 | Repair of Classrooms | 6500000 | DPWH (Batch 2) | 5687701.81 | COMPLETED | 100% | 2024-04-30 | 2024-04-30 | P00775688NP | 23CC0469 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 300737 | Sta. Peregrina HS | PULILAN | 1st | 1 | 9 | Repair of Classrooms | 10400000 | DPWH (Batch 2) | 9835197.15 | COMPLETED | 100% | 2024-05-30 | 2024-05-30 | P00775689NP | 23CC0463 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104750 | Baliwag South Central School | BALIUAG | 2nd | 1 | 25 | Repair of Classrooms | 16250000 | DPWH (Batch 2) | 15289007.79 | COMPLETED | 100% | 2024-06-29 | 2024-06-29 | P00775691NP | 23CC0468 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104746 | Sabang ES | BALIUAG | 2nd | 1 | 8 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9456764.45 | COMPLETED | 100% | 2024-06-29 | 2024-06-29 | P00775690NP | 23CC0466 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Samarah Construction and Supply | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104795 | Tibagan Elementary School | BUSTOS | 2nd | 1 | 23 | Repair of Classrooms | 14950000 | DPWH (Batch 2) | 14065403.32 | COMPLETED | 100% | 2024-04-30 | 2024-04-30 | P00775692NP | 23CC0470 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | Streamline Builders Corporation | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105002 | Culianin ES | PLARIDEL | 2nd | 1 | 8 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9456619.92 | COMPLETED | 100% | 2024-04-30 | 2024-04-30 | P00775693NP | 23CC0462 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | SYMS Construction Trading | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105008 | Parulan ES | PLARIDEL | 2nd | 1 | 11 | Repair of Classrooms | 7150000 | DPWH (Batch 2) | 6761280.76 | COMPLETED | 100% | 2024-05-30 | 2024-05-30 | P00775694NP | 23CC0467 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Streamline Builders Corporation | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 158507 | Duplas ES | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 3 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3801001.89 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00362 | 23C00362 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 306720 | Esteban Paulino HS | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 5 | Repair of Classrooms | 5500000 | DPWH (Batch 2) | 5227977.4 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00364 | 23C00364 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 158509 | Kambubuyugan Elementary School | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4750779.28 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00363 | 23C00363 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105029 | Bubulong Malaki ES | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3326935.94 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00365 | 23C00365 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105030 | Bubulong Munti Elementary School | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3325785.98 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00366 | 23C00366 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105052 | Casalat Elementary School | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3327086.5 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00367 | 23C00367 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105097 | Biclat ES | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4277266.73 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00369 | 23C00369 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105099 | Dr. Juan F. Pascual MS | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4751755.5 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00370 | 23C00370 |  |  |  |  | 2024-07-16 | GMO Construction | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 105105 | Pacalag ES | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4276616.06 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00371 | 23C00371 |  |  |  |  | 2024-07-23 | ADSL Construction & Trading | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105073 | SAN MIGUEL NORTH CENTRAL SCHOOL | SAN MIGUEL | 3rd | 1 | 5 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 5703417.9 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00368 | 23C00368 |  |  |  |  | 2024-07-16 | Pluma Builders Co. | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105115 | Caingin ES | SAN RAFAEL | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4751781.33 | COMPLETED | 100% | 2024-11-18 | 2024-11-18 | 23C00372 | 23C00372 |  |  |  |  | 2024-07-16 | Eirish Builders & Supply Inc. | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 5th | 1 | 30 | Repair of Classrooms | 19500000 | DPWH (Batch 2) | 18346658.83 | COMPLETED | 100% | 2024-05-30 | 2024-05-30 | P00775706NP | 23CC0465 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | SYMS Construction Trading | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104829 | Sta. Rita ES | GUIGUINTO | 5th | 1 | 24 | Repair of Classrooms | 15600000 | DPWH (Batch 2) | 14677399.7 | COMPLETED | 100% | 2024-06-09 | 2024-06-09 | P00775707NP | 23CC0471 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 104832 | Tiaong Elementary School | GUIGUINTO | 5th | 1 | 17 | Repair of Classrooms | 11050000 | DPWH (Batch 2) | 10337752.72 | COMPLETED | 100% | 2024-05-28 | 2024-05-28 | P00775708NP | 23CC0461 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Ma. Liza C. Austria Construction & Supply Corporation | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 300728 | Bunsuran NHS | PANDI | 5th | 1 | 24 | Repair of Classrooms | 15600000 | DPWH (Batch 2) | 14677543.18 | COMPLETED | 100% | 2024-08-28 | 2024-08-28 | P00775709NP | 23CC0472 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 104727 | A. S. De Guzman ES (Taboc ES) | ANGAT | 6th | 1 | 4 | Repair of Classrooms | 4532002.88 | DPWH (Batch 2) | 4486682.85 | COMPLETED | 100% | 2024-04-08 | 2024-04-07 | P00775713NP | 23CD0198 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | SYMS Construction Trading | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 6th | 1 | 2 | Repair of Classrooms | 2859435.52 | DPWH (Batch 2) | 2830552.33 | COMPLETED | 100% | 2024-04-08 | 2024-04-07 | P00775710NP | 23CD0195 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | R.B. CAIN CONSTRUCTION | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104711 | Pablo C. Capistrano ES | ANGAT | 6th | 1 | 1 | Repair of Classroom | 1459126.79 | DPWH (Batch 2) | 1444388.14 | COMPLETED | 100% | 2024-04-08 | 2024-04-07 | P00775711NP | 23CD0196 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104717 | TEODOSO R. MANUEL ELEMENTARY SCHOOL | ANGAT | 6th | 1 | 2 | Repair of Classrooms | 1956312.85 | DPWH (Batch 2) | 1935816.16 | COMPLETED | 100% | 2024-03-09 | 2024-03-08 | P00775712NP | 23CD0197 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104951 | NORTH HILLS VILLAGE ELEMENTARY SACHOOL | NORZAGARAY | 6th | 1 | 6 | Repair of Classrooms | 7752824.32 | DPWH (Batch 2) | 7674512.96 | COMPLETED | 100% | 2024-04-08 | 2024-04-07 | P00775714NP | 23CD0199 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 6th | 1 | 2 | Repair of Classrooms | 2588448 | DPWH (Batch 2) | 2562302.06 | COMPLETED | 100% | 2024-04-08 | 2024-04-07 | P00775715NP | 23CD0200 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105151 | Guyong ES | SANTA MARIA | 6th | 1 | 10 | Repair of Classrooms | 11949271 | DPWH (Batch 2) | 11828571.29 | COMPLETED | 100% | 2024-05-08 | 2024-02-14 | P00775716NP | 23CD0202 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | 1199S CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105167 | Sta. Cruz ES | SANTA MARIA | 6th | 1 | 3 | Repair of Classrooms | 3136258 | DPWH (Batch 2) | 3104578.63 | COMPLETED | 100% | 2024-04-08 | 2024-02-14 | P00775717NP | 23CD0201 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | 1199S CONSTRUCTION | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105282 | Nagmisahan ES | CUYAPO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-15-2024 | INFRA-NE-SVP-01-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105294 | Sta. Clara ES | CUYAPO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-16-2024 | INFRA-NE-SVP-02-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105386 | Faigal ES | GUIMBA | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-17-2024 | INFRA-NE-SVP-03-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105625 | Ricardo L. Joson Elementary School | QUEZON | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-18-2024 | INFRA-NE-SVP-04-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105783 | San Francisco ES | SANTO DOMINGO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-19-2024 | INFRA-NE-SVP-05-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105311 | Pantoc ES | GABALDON (BITULOK & SABANI) | 3rd | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-20-2024 | INFRA-NE-SVP-06-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105218 | Entablado ES | CABIAO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.02 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-21-2024 | INFRA-NE-SVP-07-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105440 | Langla ES | JAEN | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-22-2024 | INFRA-NE-SVP-08-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.03 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-23-2024 | INFRA-NE-SVP-09-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105667 | Maugat ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-24-2024 | INFRA-NE-SVP-10-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105668 | Panabingan ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-25-2024 | INFRA-NE-SVP-11-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105671 | San Francisco ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-26-2024 | INFRA-NE-SVP-12-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105736 | C. I. Villaroman ES | SAN LEONARDO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.03 | COMPLETED | 100% | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-27-2024 | INFRA-NE-SVP-13-2024 | 2024-01-18 | N/A | 2024-01-23 | N/A | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Pampanga | 106152 | Masantol ES | MASANTOL | 4th | 1 | 6 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9650000 | COMPLETED | 100% | 2024-10-01 | 2024-10-01 | P00775718NP | 24CG0170 | 2024-04-11 | 2024-04-19 | 2024-05-02 | 2024-05-13 | 2024-05-22 | Three in One Construction and Trading | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4th | 1 | 2 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4824727.68 | COMPLETED | 100% | 2024-07-14 | 2024-07-14 | P00775719NP | 24CG0112 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-18 | V. Trillana builders & Trading | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 106255 | Dela Paz ES | SAN SIMON | 4th | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4823684.13 | COMPLETED | 100% | 2024-04-12 | 2024-04-12 | P00775720NP | 24CG0113 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-18 | V. Trillana builders & Trading | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 306917 | Sta. Monica High School | SAN SIMON | 4th | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4825000 | COMPLETED | 100% | 2024-08-01 | 2024-08-01 | P00775721NP | 24CG0114 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-19 | Cholo Construction and Trading | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Tarlac | 300946 | Anao NHS | ANAO | 1st | 1 | 3 | Repair of Classrooms | 4517000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106306 | Bantog ES | ANAO | 1st | 1 | 6 | Repair of Classrooms | 3215200 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106307 | Casili ES | ANAO | 1st | 1 | 2 | Repair of Classrooms | 1576790.34 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106305 | Dolores Ongsiako CES | ANAO | 1st | 1 | 13 | Repair of Classrooms | 6971421.61 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 300972 | Marawi National High School | CAMILING | 1st | 1 | 7 | Repair of Classrooms | 5574483.96 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106333 | Pindangan First ES | CAMILING | 1st | 1 | 5 | Repair of Classrooms | 4184183.53 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106353 | Sta. Maria ES | CAMILING | 1st | 1 | 2 | Repair of Classrooms | 1597474.29 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106336 | Tambugan ES | CAMILING | 1st | 1 | 5 | Repair of Classrooms | 5017455.14 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106508 | Bigbiga ES | MAYANTOC | 1st | 1 | 5 | Repair of Classrooms | 3439313.71 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106551 | San Julian ES | MONCADA | 1st | 1 | 4 | Repair of Classrooms | 3760996.48 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106535 | San Pedro ES | MONCADA | 1st | 1 | 1 | Repair of Classroom | 1102695.08 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106594 | Don Quirino Sulit ES | PURA | 1st | 1 | 1 | Repair of Classroom | 1112406.23 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 300974 | Maungib NHS | PURA | 1st | 1 | 2 | Repair of Classrooms | 2037749.45 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106608 | Guiteb ES | RAMOS | 1st | 1 | 7 | Repair of Classrooms | 5330000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106609 | Pance ES | RAMOS | 1st | 1 | 5 | Repair of Classrooms | 4330000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106610 | Ramos CS | RAMOS | 1st | 1 | 6 | Repair of Classrooms | 5212934.88 | DPWH (Batch 2) |  | Ongoing | 15% | [23 empty] | 15% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | 4 | Repair of Classrooms | 3269457.19 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 502346 | Toledo Integrated School | RAMOS | 1st | 1 | 4 | Repair of Classrooms | 2748022.93 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106623 | Casipo PS | SAN CLEMENTE | 1st | 1 | 2 | Repair of Classrooms | 1245051.31 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106624 | Pit-Ao ES | SAN CLEMENTE | 1st | 1 | 3 | Repair of Classrooms | 2408000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 1st | 1 | 5 | Repair of Classrooms | 4070000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106680 | Sta. Ignacia North CS | SANTA IGNACIA | 1st | 1 | 7 | Repair of Classrooms | 5614749.95 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106681 | Sta. Ignacia South CES | SANTA IGNACIA | 1st | 1 | 5 | Repair of Classrooms | 4059091.65 | DPWH (Batch 2) |  | Ongoing | 60% | [23 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region IV-A | Antipolo City | 301421 | Kaysakat NHS | CITY OF ANTIPOLO | 2nd | 1 | 8 | Repair of Classrooms | 3806072.156 | DPWH (Batch 2) | 3561987.53 | COMPLETED | 100% | 2024-03-26 | 2024-03-26 | P00775739NP | 23DN0147 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-11-07 | 2023-11-21 | BELVIAN BUILDERS | N/A | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Batangas | 301134 | Papaya National High School | TINGLOY | 2nd | 1 | 6 | Repair of Classrooms | 4591234.1 | DPWH (Batch 1) | 4430540.91 | Ongoing | 95% | 2024-02-22 |  | P00775119NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region IV-A | Batangas | 107813 | Pisa Elementary School | TINGLOY | 2nd | 1 | 8 | Repair of Classrooms | 3711204 | DPWH (Batch 1) | 3581311.86 | Ongoing | 95% | 2024-02-22 |  | P00775120NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region IV-A | Batangas | 107814 | San Jose Elementary School | TINGLOY | 2nd | 1 | 6 | Repair of Classrooms | 1649424 | DPWH (Batch 1) | 1591694.16 | Ongoing | 75% | 2024-02-22 |  | P00775121NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING | [13 empty] | 75% | [7 empty] | Ongoing
REPAIR 2023 | Region IV-A | Batangas | 107818 | Talahib Elementary School | TINGLOY | 2nd | 1 | 4 | Repair of Classrooms | 1649424 | DPWH (Batch 1) | 1591694.16 | Ongoing | 95% | 2024-02-22 |  | P00775122NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region IV-A | Batangas | 301114 | Maabud National High School | SAN NICOLAS | 3rd | 1 | 6 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | Completed | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region IV-A | Binan City | 108221 | Langkiwa ES | CITY OF BIÑAN | 1st | 1 | 4 | Repair of Classrooms | 911599.61 | DEPED (Batch 2) | 873239.8 | COMPLETED | 100% | 2024-06-09 | 2024-06-11 | 10553108 | 10553108 |  |  |  | 2024-02-19 | 2024-02-21 | GS Motar Builders Construction & Trading | With time extension | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Binan City | 307932 | Mamplasan NHS (Jacobo Annex) | CITY OF BIÑAN | 1st | 1 | 6 | Repair of Classrooms | 999163.1 | DEPED (Batch 2) | 958837.78 | COMPLETED | 100% | 2024-04-22 | 2024-04-23 | 10556258 | 10556258 |  |  |  | 2024-02-19 | 2024-02-21 | GS Motar Builders Construction & Trading | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Cavite | 107926 | Bailen Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 3 | Repair of Classrooms | 2600000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | Completed
REPAIR 2023 | Region IV-A | Laguna | 108286 | Matalatala ES | MABITAC | 4th | 1 | 9 | Repair of Classrooms | 6099507 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Laguna | 301243 | Kabulusan Integrated National High School | PAKIL | 4th | 1 | 5 | Repair of Classrooms | 3388617 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Laguna | 108400 | Maulawin ES | PAKIL | 4th | 1 | 2 | Repair of Classrooms | 1355447 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109728 | Barra Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 950950.44 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109739 | Ilayang Talim Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 935780.08 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109740 | Isabang Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 956890.8 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 167502 | Isabang Elementary School - Bocohan Annex | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 950890.78 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109731 | Lucena South I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 975860.86 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109742 | Lucena West I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 933457.9 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109744 | Lucena West III Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 925795.78 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109745 | Lucena West IV Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 940980.36 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109735 | Mayao Parada Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 966367.8 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Lucena City | 109736 | Talao-Talao Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 945890.9 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 1st | 1 | 12 | Repair of Classrooms | 9655035 | DPWH (Batch 1) | 9654451 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 1st | 1 | 12 | Repair of Classrooms | 9655035 | DPWH (Batch 2) | 9653886.66 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 108991 | Sinintan ES | PATNANUNGAN | 1st | 1 | 2 | Repair of Classrooms | 1655668.9 | DPWH (Batch 2) | 1636376.22 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 108518 | Maligaya ES | ATIMONAN | 4th | 1 | 3 | Repair of Classrooms | 3900000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 108520 | Malinao Ilaya ES | ATIMONAN | 4th | 1 | 10 | Repair of Classrooms | 3640000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 301400 | San Rafael NHS | ATIMONAN | 4th | 1 | 2 | Repair of Classrooms | 1950000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th | 1 | 5 | Repair of Classrooms | 6435000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 6 | Repair of Classrooms | 5395000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 12 | Repair of Classrooms | 7150000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 5 | Repair of Classrooms | 7865000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 3 | Repair of Classrooms | 6890000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-A | Quezon | 109056 | Pedro Cabangon ES | QUEZON | 4th | 1 | 1 | Repair of Classroom | 808244.65 | DEPED (Batch 1) | 778000 | COMPLETED | 100% |  | 2023-09-27 | [8 empty] | Sub-ARO amount is 779,956.09 | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | Completed
REPAIR 2023 | Region IV-A | Quezon | 109056 | Pedro Cabangon ES | QUEZON | 4th | 1 | 1 | Repair of Classroom | 808244.65 | DEPED (Batch 2) | 778000 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4th | 1 | 5 | Repair of Classrooms | 4100365.65 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4th | 1 | 5 | Repair of Classrooms | 4100365.65 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | San Pedro City | 301261 | Sampaguita Vill. NHS | SAN PEDRO | 1st | 1 | 10 | Repair of Classrooms | 4043773.47 | DPWH (Batch 2) |  | COMPLETED | 100% | 2024-08-31 | 2024-08-16 | 23DI0197 | 23DI0197 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | San Pedro City | 307939 | Southville 3A (Sampaguita Ext.) | SAN PEDRO | 1st | 1 | 20 | Repair of Classrooms | 3965689.88 | DPWH (Batch 2) |  | Completed | 100% | [10 empty] | with NOA, Suspended due to structural concern | [12 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region IV-A | San Pedro City | 164528 | Southville 3A ES | SAN PEDRO | 1st | 1 | 30 | Repair of Classrooms | 5754265.09 | DPWH (Batch 2) | 5406845 | COMPLETED | 100% | 2024-08-31 | 2024-08-08 | 23DI0198 | 23DI0198 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | GMO CONSTRUCTION | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF TANAUAN | 3rd | 1 | 6 | Repair of Classrooms | 8500000 | DPWH (Batch 2) |  | Completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region IV-A | Tayabas City | 109236 | LAKAWAN ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 109237 | LAWIGUE ES | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 2400000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 109257 | Malao-A / Calantas ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 109238 | Masin Elementary School | CITY OF TAYABAS | 1st | 1 | 1 | Repair of Classroom | 600000 | DEPED (Batch 2) | 577854.4 | COMPLETED | 100% | 2024-06-20 | 2024-07-02 | ITB-INFRA-2024-003 | ITB-INFRA-2024-003 | 2024-03-06 | 2024-03-14 | 2024-03-26 | 2024-05-03 | 2024-05-14 | LA PROFUGO CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 109258 | POTOL ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 109260 | Tayabas West CS II | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-A | Tayabas City | 301416 | West Palale National High School | CITY OF TAYABAS | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Occidental Mindoro | 110098 | Bulacan ES | LOOC | Lone | 1 | 2 | Repair of Classrooms | 1950000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Occidental Mindoro | 110095 | Tabao ES (Ambil ES-Tabao Site) | LOOC | Lone | 1 | 2 | Repair of Classrooms | 2250000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110351 | Bansud CS | BANSUD | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4771925.35 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775756NP | 23EI0099 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Lumel Glenn Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110370 | Bagong Bayan CS | BONGABONG | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4767177.72 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775760NP | 23EI0102 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Archidus Development Corporation | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110457 | Melecio D. Cantos ES | GLORIA | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4757447.18 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775761NP | 23EI0105 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | LED Reyes Constructio (LCR) OPC | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 300412 | Don Pedro High School | MANSALAY | 2nd | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4771925.35 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775762NP | 23EI0103 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | Lumel Glenn Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110557 | Doña Asuncion Reyes MES | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4757620.02 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775757NP | 23EI0101 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | LED Reyes Constructio (LCR) OPC | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110558 | Juan Morente, Sr. Mem. Pilot Sch. | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4778986.54 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775758NP | 23EI0098 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | RM Sescar Enterprises | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110574 | M. Ansaldo Sr. MES | PINAMALAYAN | 2nd | 1 | 8 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4787243.96 | COMPLETED | 100% | 2024-07-05 | 2024-07-05 | P00775759NP | 23EI0104 | 2023-10-04 | 2023-10-11 | 2023-10-24 | 2023-10-27 | 2024-01-08 | D.M. Almero Enterprises | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Oriental Mindoro | 110644 | San Mariano ES | ROXAS | 2nd | 1 | 18 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4822773.34 | COMPLETED | 100% | 2025-02-17 | 2025-02-17 | P007757563NP | 24EI0123 | 2024-03-20 | 2024-03-27 | 2024-04-11 | 2024-04-23 | 2024-08-19 | Lewis Gjann Construction | with modification - from 18 CL to 8 CL physical target | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2023 | Region IV-B | Palawan | 309138 | Araceli Plainview National High School | ARACELI | 1st | 1 | 1 | Repair of Classrooms | 833858.17 | DEPED (Batch 1) |  | COMPLETED | 100% |  |  | 2023-11-002_INFRA | 2023-11-002_INFRA | 2023-11-17 | - | 2023-11-28 | 2024-01-17 | 2024-05-09 | Futuristic Trading and Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 110751 | Bacao Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classroom | 556936.16 | DEPED (Batch 2) | 531665.75 | COMPLETED | 100% | 2024-12-24 | 2024-09-19 | 2024-04-002_INFRA | 45440 | 2024-06-04 | 2024-06-18 | 2024-07-19 | 2024-08-14 | 2024-08-19 | RBM2 Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 110751 | Bacao ES | Dumaran | 1st | 1 | 4 | Repair of Classrooms | 2922012 | DPWH (Batch 1) | 2805465.86 | COMPLETED | 100% | 2024-02-20 | 2024-02-16 | P00775137NP | 23EE0126 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | Bats Construction Services | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 309109 | Bacao National High School (Dumaran NHS - Bacao NHS) | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3786972.66 | DPWH (Batch 2) | 3615565.98 | COMPLETED | 100% | 2024-04-12 | 2024-04-05 | P00775138NP | 23EE0124 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-11-07 | 2024-01-08 | Maryknoll Builders and Supply | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 309109 | Bacao NHS | Dumaran | 1st | 1 | 18 | Repair of Classrooms | 6557856.34 | DPWH (Batch 1) | 6296307.04 | COMPLETED | 100% | 2024-04-12 | 2024-04-05 | P00775138NP | 23EE0124 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | BJ-RAM Const. Services | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 111136 | Andres Soriano Memorial Elementary School | ROXAS | 1st | 1 | 33 | Repair of Classrooms | 9793897.14 | DPWH (Batch 2) | 9434852.5 | COMPLETED | 100% | 2024-05-12 | 2024-09-20 | P00775765NP | 23EE0134 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-11-07 | 2024-01-08 | E.V.Villaos Trdg. & Const. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 111136 | Andres Soriano Memorial ES | Roxas | 1st | 1 | 27 | Repair of Classrooms | 13879004.19 | DPWH (Batch 1) | 13353149.63 | COMPLETED | 100% | 2024-06-28 | 2024-07-22 | P00775139NP | 23EE0125 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | E.M.Abin Trading & Const. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial Elementary School | ROXAS | 1st | 1 | 4 | Repair of Classrooms | 3663871.54 | DPWH (Batch 2) | 3266926.49 | COMPLETED | 100% | 2024-04-04 | 2024-04-04 | P00775766NP | 23EE0132 | 2023-09-29 | 2023-10-09 | 2023-10-20 | 2023-12-13 | 2024-01-30 | AFG Construction Corporation | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial ES | Roxas | 1st | 1 | 4 | Repair of Classrooms | 1690974.06 | DPWH (Batch 1) | 1626506.9 | COMPLETED | 100% | 2023-12-02 | 2023-12-02 | P00775140NP | 23EE0127 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | New Space Trdg & Const. Corp. | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1st | 1 | 7 | Repair of Classroom | 491022.98 | DEPED (Batch 2) | 471660.02 | COMPLETED | 100% | 2024-12-24 | 2024-09-23 | 2024-04-002_INFRA | 45440 | 2024-06-04 | 2024-06-18 | 2024-07-19 | 2024-08-14 | 2024-08-19 | RBM2 Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1st | 1 | 7 | Repair of Classrooms | 6071208.02 | DPWH (Batch 1) | 5777399.72 | COMPLETED | 100% | 2024-01-11 | 2024-08-30 | P00775141NP | 23EE0128 | 2023-08-29 | 2023-09-08 | 2023-09-19 | 2023-09-25 | 2023-04-28 | E.V.Villaos Trdg. & Const. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Puerto Princesa City | 301787 | Babuyan NHS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 17 | Repair of Classrooms | 13700000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Puerto Princesa City | 111509 | Binduyan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 6 | Repair of Classrooms | 4300000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Puerto Princesa City | 305540 | Buenavista HS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 4000000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IV-B | Puerto Princesa City | 111533 | Tagnipa ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 2 | Repair of Classrooms | 1900000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga City | 303923 | Don Pablo A. Lorenzo MHS | ZAMBOANGA CITY | 1st | 1 | 10 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124397 | El Paraiso ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124399 | La Union ES | LA LIBERTAD | 1st | 1 | 4 | Repair of Classrooms | 3300000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1st | 1 | 1 | Repair of Classroom | 1500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124599 | Birayan ES | RIZAL | 1st | 1 | 3 | Repair of Classrooms | 2500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124601 | La Esperanza ES | RIZAL | 1st | 1 | 2 | Repair of Classrooms | 1710000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124605 | Nangca ES | RIZAL | 1st | 1 | 2 | Repair of Classrooms | 1550000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124659 | Lebote ES | SERGIO OSMEÑA SR. | 1st | 1 | 6 | Repair of Classrooms | 4450000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124648 | San Jose ES | SERGIO OSMEÑA SR. | 1st | 1 | 4 | Repair of Classrooms | 3225000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124741 | Calube ES | SIBUTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124745 | Magsaysay ES | SIBUTAD | 1st | 1 | 4 | Repair of Classrooms | 3350000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1st | 1 | 2 | Repair of Classrooms | 1700000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1st | 1 | 4 | Repair of Classrooms | 3300000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124387 | Sanao ES | KATIPUNAN | 2nd | 1 | 4 | Repair of Classrooms | 2860435.26 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124691 | Mangilay II ES | SIAYAN | 2nd | 1 | 11 | Repair of Classrooms | 7890886.64 | DPWH (Batch 1) |  | Ongoing | 85% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region IX | Zamboanga del Norte | 124307 | Bayanihan ES | GUTALAC | 3rd | 1 | 2 | Repair of Classrooms | 1449529.21 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Norte | 124466 | Candelaria ES | LILOY | 3rd | 1 | 2 | Repair of Classrooms | 1555119.34 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2023 | Region IX | Zamboanga del Sur | 125085 | Moradje Elementary School | JOSEFINA | 1st | 1 | 6 | Repair of Classrooms | 5019137.25 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Sur | 125394 | Eastern Sominot ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 5 | Repair of Classrooms | 4213574.79 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Sur | 125383 | Lantawan ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 2 | Repair of Classrooms | 1711551.39 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Sur | 125464 | Tigbao CES | TIGBAO | 2nd | 1 | 10 | Repair of Classrooms | 6789564.69 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region IX | Zamboanga del Sur | 314208 | Sagucan NHS | VINCENZO A. SAGUN | 2nd | 1 | 4 | Repair of Classrooms | 3881865.41 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Albay | 301821 | Cawayan National High School | BACACAY | 1st | 1 | 6 | Repair of Classrooms | 13008225.92 | DPWH (Batch 2) |  | Ongoing | 90% | [23 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111608 | Gubat Elementary School | BACACAY | 1st | 1 | 4 | Repair of Classrooms | 9262235.97 | DPWH (Batch 2) |  | Ongoing | 75% | [23 empty] | 75% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111613 | Misibis Elementary School | BACACAY | 1st | 1 | 3 | Repair of Classrooms | 6946676.98 | DPWH (Batch 2) |  | Ongoing | 85% | [23 empty] | 85% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111596 | San Pablo Elementary School | BACACAY | 1st | 1 | 9 | Repair of Classrooms | 13980359.31 | DPWH (Batch 2) |  | Ongoing | 97% | [23 empty] | 97% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111597 | Sogod Elementary School | BACACAY | 1st | 1 | 3 | Repair of Classrooms | 7909582.7 | DPWH (Batch 2) |  | Ongoing | 65% | [23 empty] | 65% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111876 | Labnig Elementary School | MALINAO | 1st | 1 | 5 | Repair of Classrooms | 5112559.4 | DPWH (Batch 2) |  | Ongoing | 70% | [23 empty] | 70% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 301810 | Malinao National High School | MALINAO | 1st | 1 | 10 | Repair of Classrooms | 17792715.5 | DPWH (Batch 2) |  | Ongoing | 90% | [23 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 112060 | San Isidro Elementary School | SANTO DOMINGO (LIBOG) | 1st | 1 | 3 | Repair of Classrooms | 2773790.78 | DPWH (Batch 2) |  | Ongoing | 85% | [23 empty] | 85% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 301879 | Sto. Domingo National High School | SANTO DOMINGO (LIBOG) | 1st | 1 | 2 | Repair of Classrooms | 4676970.64 | DPWH (Batch 2) |  | Ongoing | 90% | [23 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111664 | Budiao Elementary School | DARAGA (LOCSIN) | 2nd | 1 | 6 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 112024 | Calanaga Elementary School | RAPU-RAPU | 2nd | 1 | 2 | Repair of Classrooms | 8000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 112000 | Agos Elementary School | POLANGUI | 3rd | 1 | 7 | Repair of Classrooms | 5050000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 172507 | Alomon Elementary School | POLANGUI | 3rd | 1 | 4 | Repair of Classrooms | 3600000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 111980 | Balinad Elementary School | POLANGUI | 3rd | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 112007 | Lanigay Elementary School | POLANGUI | 3rd | 1 | 3 | Repair of Classrooms | 1950000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 112009 | Magurang Elementary School | POLANGUI | 3rd | 1 | 8 | Repair of Classrooms | 6200000 | DPWH (Batch 2) |  | Ongoing | 40% | [23 empty] | 40% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111990 | Maysua Elementary School | POLANGUI | 3rd | 1 | 2 | Repair of Classrooms | 1800000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | Completed
REPAIR 2023 | Region V | Albay | 301829 | Maysua High School | POLANGUI | 3rd | 1 | 2 | Repair of Classrooms | 1800000 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 301865 | Polangui General Comprehensive High School | POLANGUI | 3rd | 1 | 30 | Repair of Classrooms | 25500000 | DPWH (Batch 2) |  | Ongoing | 40% | [23 empty] | 40% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Albay | 111996 | Ponso North Elementary School | POLANGUI | 3rd | 1 | 11 | Repair of Classrooms | 6979654 | DPWH (Batch 2) |  | Ongoing | 85% | [23 empty] | 85% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112110 | Capalonga CS | CAPALONGA | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112111 | Casiano Florendo Elementary School | CAPALONGA | 1st | 1 | 3 | Repair of Classrooms | 1682430.47 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 112117 | Lukbanan ES | CAPALONGA | 1st | 1 | 2 | Repair of Classrooms | 1304151.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 112127 | Talento-Roll Elementary School | CAPALONGA | 1st | 1 | 4 | Repair of Classrooms | 2548913.05 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 10 | Repair of Classrooms | 8550880.56 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1st | 1 | 9 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 301901 | Larap NHS | JOSE PANGANIBAN | 1st | 1 | 9 | Repair of Classrooms | 5431736.33 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112165 | Pag-asa ES | JOSE PANGANIBAN | 1st | 1 | 4 | Repair of Classrooms | 2277976.29 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 112171 | Sta. Elena ES | JOSE PANGANIBAN | 1st | 1 | 3 | Repair of Classrooms | 1872261.15 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1st | 1 | 6 | Repair of Classrooms | 4033853.04 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112179 | Bulhao Elementary School | LABO | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1st | 1 | 3 | Repair of Classrooms | 1954692.04 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112209 | Florence Elementary School | LABO | 1st | 1 | 6 | Repair of Classrooms | 3519407.01 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 112182 | Fundado ES | LABO | 1st | 1 | 8 | Repair of Classrooms | 4947116.61 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | completed
REPAIR 2023 | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1st | 1 | 4 | Repair of Classrooms | 868022.46 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1st | 1 | 2 | Repair of Classrooms | 974361.61 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Norte | 112213 | Macogon Elementary School | LABO | 1st | 1 | 4 | Repair of Classrooms | 2424142.79 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 301908 | Pag-Asa High School | LABO | 1st | 1 | 3 | Repair of Classrooms | 1877567.28 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Norte | 112195 | Severino Francisco Elementary Sch. | LABO | 1st | 1 | 5 | Repair of Classrooms | 3142718.83 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1st | 1 | 10 | Repair of Classrooms | 6244345.53 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 112255 | Pedro V. Moreno Elementary School | PARACALE | 1st | 1 | 3 | Repair of Classrooms | 1924142.79 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Norte | 500634 | Sta. Elena Integrated School | SANTA ELENA | 1st | 1 | 10 | Repair of Classrooms | 4033012.12 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Camarines Sur | 112458 | Cabusao Central School | CABUSAO | 1st | 1 | 4 | Repair of Classrooms | 2859969.17 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Sur | 112460 | Castillo ES | CABUSAO | 1st | 1 | 3 | Repair of Classrooms | 2859969.17 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Sur | 112780 | Loob ES - Gainza | GAINZA | 2nd | 1 | 3 | Repair of Classrooms | 2544562.23 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Sur | 112766 | San Antonio ES | BOMBON | 3rd | 1 | 8 | Repair of Classrooms | 4752458.29 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Camarines Sur | 112768 | San Roque ES | BOMBON | 3rd | 1 | 7 | Repair of Classrooms | 5165841.35 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113154 | Bugao CES | BAGAMANOC | Lone | 1 | 6 | Repair of Classrooms | 5250453.9 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-06-02 | 2024-06-02 | [7 empty] | Altev Construction Services | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113155 | Cahan Bo. Sch. | BAGAMANOC | Lone | 1 | 2 | Repair of Classrooms | 1890151.3 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-11 | 2024-02-11 | [7 empty] | Tri-John Trading & Constrution | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113162 | Pangcayanan ES | BAGAMANOC | Lone | 1 | 4 | Repair of Classrooms | 3382318.24 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-11 | 2024-02-11 | [7 empty] | Dawn Engineering Const. & Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 302100 | San Vicente National High School | BAGAMANOC | Lone | 1 | 4 | Repair of Classrooms | 3781963 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-11 | 2024-02-11 | [7 empty] | Dawn Engineering Const. & Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 174003 | Bagumbayan ES | BATO | Lone | 1 | 3 | Repair of Classrooms | 2537038.77 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-11 | 2024-02-11 | [7 empty] | NVR Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113181 | Batalay ES | BATO | Lone | 1 | 3 | Repair of Classrooms | 2536352.7 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-27 | 2024-01-08 | [7 empty] | JYM Construction Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113187 | Libjo ES | BATO | Lone | 1 | 6 | Repair of Classrooms | 5072704.58 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-12 | 2024-03-12 | [7 empty] | Al-Jon Construction Dev. Inc. | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113188 | Mintay Elementary School | BATO | Lone | 1 | 3 | Repair of Classrooms | 2536352.34 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-04-24 | 2024-05-10 | [7 empty] | TNB Builders | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113246 | Bayhan PS | PANGANIBAN (PAYO) | Lone | 1 | 3 | Repair of Classrooms | 2536172.7 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-11 | 2024-02-11 | [7 empty] | NVR Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113251 | Maculiw Comm. Sch. | PANGANIBAN (PAYO) | Lone | 1 | 5 | Repair of Classrooms | 4676954.5 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-12 | 2024-03-12 | [7 empty] | NVR Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL | Lone | 1 | 23 | Repair of Classrooms | 21283990.7 | DPWH (Batch 1) |  | Ongoing | 80% | [9 empty] | Tri-John Trading & Constrution | [13 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Catanduanes | 113297 | Tobrehon ES | SAN MIGUEL | Lone | 1 | 2 | Repair of Classrooms | 2350781.8 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-04-11 | 2024-04-11 | [7 empty] | Dawn Engineering Const. & Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Legaspi City | 114458 | Bogna Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 5613434.75 | Ongoing | 0% | 2024-05-01 |  |  | 23FB0230 |  |  | 2024-01-09 |  | 2024-02-01 | NEXT GENERATION CONSTRUCTION AND SUPPLY | [13 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Legaspi City | 114483 | Puro Elementary School | LEGAZPI CITY (Capital) | 2nd | 1 | 14 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9347918.16 | Ongoing | 0% | 2024-05-01 |  |  | 23FB0232 |  |  | 2024-01-09 |  | 2024-02-01 | 9 LEAVES BUILDERS AND SUPPLY CORP. | [13 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 2805713.75 | Ongoing | 0% | 2024-04-01 |  |  | 23FB0233 |  |  | 2024-01-09 |  | 2024-02-01 | NEXT GENERATION CONSTRUCTION AND SUPPLY | [13 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Legaspi City | 114474 | Taysan ES | LEGAZPI CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9337918.16 | Ongoing | 0% | 2024-06-30 |  |  | 23FB0231 |  |  | 2024-01-09 |  | 2024-02-01 | 9 LEAVES BUILDERS AND SUPPLY CORP. | [13 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113571 | Boca Engano Elementary School | CLAVERIA | 1st | 1 | 4 | Repair of Classrooms | 3582353.22 | DPWH (Batch 2) | 3411034.83 | Ongoing | 65.5% | [23 empty] | 65.5% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113577 | Claveria North CS | CLAVERIA | 1st | 1 | 13 | Repair of Classrooms | 11230264.95 | DPWH (Batch 2) | 10723313.99 | Ongoing | 31.05% | [23 empty] | 31.05% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113581 | Mabiton Elementary School | CLAVERIA | 1st | 1 | 6 | Repair of Classrooms | 5355266.35 | DPWH (Batch 2) | 5141976.99 | Ongoing | 35.1% | [23 empty] | 35.1% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 302163 | Quezon National High School | CLAVERIA | 1st | 1 | 6 | Repair of Classrooms | 5315078.35 | DPWH (Batch 2) | 5074974.33 | Ongoing | 30.05% | [23 empty] | 30.05% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 | 10 | Repair of Classrooms | 8695825.3 | DPWH (Batch 2) | 8306135.92 | Ongoing | 90.56% | [23 empty] | 90.56% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 302152 | Monreal National High School | MONREAL | 1st | 1 | 12 | Repair of Classrooms | 10385160.58 | DPWH (Batch 2) | 9919485 | Ongoing | 90.15% | [23 empty] | 90.15% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 501273 | Buenavista Integrated School | SAN FERNANDO | 1st | 1 | 3 | Repair of Classrooms | 2599312.2 | DPWH (Batch 2) | 2483236.9 | COMPLETED | 99.8% | [23 empty] | 99.8% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO | 1st | 1 | 2 | Repair of Classrooms | 1728321.7 | DPWH (Batch 2) | 1650678.98 | COMPLETED | 99.75% | [23 empty] | 99.75% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Masbate | 113872 | P. Basas ES | SAN FERNANDO | 1st | 1 | 5 | Repair of Classrooms | 4412819.8 | DPWH (Batch 2) | 4214030.77 | Ongoing | 90.3% | [23 empty] | 90.3% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113888 | Calipat-an ES | SAN JACINTO | 1st | 1 | 5 | Repair of Classrooms | 4420258.25 | DPWH (Batch 2) | 4125743.79 | Ongoing | 80.15% | [23 empty] | 80.15% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1st | 1 | 5 | Repair of Classrooms | 4502160.5 | DPWH (Batch 2) | 4298868.07 | Ongoing | 87.24% | [23 empty] | 87.24% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | 15 | Repair of Classrooms | 13480215.03 | DPWH (Batch 2) | 12871609.07 | Ongoing | 86.75% | [23 empty] | 86.75% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 302108 | Adelina P. Laurio National High School | SAN PASCUAL | 1st | 1 | 6 | Repair of Classrooms | 5288153.45 | DPWH (Batch 2) | 5049661.09 | Ongoing | 95.4% | [23 empty] | 95.4% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 302137 | Halabangbaybay National High School | SAN PASCUAL | 1st | 1 | 2 | Repair of Classrooms | 1753510.58 | DPWH (Batch 2) | 1674253.64 | Ongoing | 85.8% | [23 empty] | 85.8% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 500161 | Iniwaran Integrated School | SAN PASCUAL | 1st | 1 | 11 | Repair of Classrooms | 9548028.05 | DPWH (Batch 2) | 9118339.59 | Ongoing | 32.4% | [23 empty] | 32.4% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113919 | Juanito G. Alburo Elementary School | SAN PASCUAL | 1st | 1 | 2 | Repair of Classrooms | 1802123.93 | DPWH (Batch 2) | 1720586.86 | Ongoing | 83.61% | [23 empty] | 83.61% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 501256 | Palani Integrated School | BALUD | 2nd | 1 | 8 | Repair of Classrooms | 14603252.3 | DPWH (Batch 2) | 14232366.2 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3rd | 1 | 6 | Repair of Classrooms | 8022938.63 | DPWH (Batch 2) |  | Ongoing | 4.36% | 2024-04-29 | [9 empty] | suspended | [12 empty] | 4.36% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113810 | Guindawahan ES | PIO V. CORPUZ (LIMBUHAN) | 3rd | 1 | 9 | Repair of Classrooms | 11365012.29 | DPWH (Batch 2) |  | Ongoing | 75.8% | 2024-05-29 | [22 empty] | 75.8% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate | 113827 | Locso-an ES | PLACER | 3rd | 1 | 3 | Repair of Classrooms | 4105284.92 | DPWH (Batch 2) |  | Ongoing | 9.28% | 2024-03-30 | [9 empty] | suspended | [12 empty] | 9.28% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Masbate City | 321805 | Bantigue High School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3161938.74 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Masbate City | 321804 | Bayombon High School | CITY OF MASBATE (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3037442.85 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Masbate City | 302148 | Masbate National Comprehensive High School | CITY OF MASBATE (Capital) | 2nd | 1 | 15 | Repair of Classrooms | 9508908.36 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon | 302192 | Bulusan High School | BULUSAN | 2nd | 1 | 6 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon | 302225 | Matnog National High School | MATNOG | 2nd | 1 | 6 | Repair of Classrooms | 6700000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114552 | Abuyog Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114524 | Bon-ot Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 302274 | Osiao Paglingap National High School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114575 | Pangpang Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) | 4974858.82 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114560 | Rosa T. Arellano Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114542 | San Isidro Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114545 | San Ramon Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Sorsogon City | 114581 | Sorsogon Pilot Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Tabaco City | 136936 | Guinobat Elementary School | CITY OF TABACO | 1st | 1 | 1 | Repair of Classroom | 1691410.42 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region V | Tabaco City | 114594 | Oson ES | CITY OF TABACO | 1st | 1 | 3 | Repair of Classrooms | 3215013.32 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Tabaco City | 114595 | Pawa ES | CITY OF TABACO | 1st | 1 | 5 | Repair of Classrooms | 4915922.5 | DPWH (Batch 2) |  | Ongoing | 80% | [23 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region V | Tabaco City | 114603 | Tabaco North CS | CITY OF TABACO | 1st | 1 | 2 | Repair of Classrooms | 1966369 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 1st | 1 | 4 | Repair of Classrooms | 2517098.85 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 1st | 1 | 7 | Repair of Classrooms | 4617114.33 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 178002 | Balusbos PS | BURUANGA | 2nd | 1 | 2 | Repair of Classrooms | 1594051.72 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | 2nd | 1 | 3 | Repair of Classrooms | 1198143.75 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2nd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 114852 | Naasog Elementary School | MALAY | 2nd | 1 | 1 | Repair of Classrooms | 708172.08 | DEPED (Batch 1) | 681489.93 | COMPLETED | 100% | 2024-01-15 | 2023-12-22 |  |  | 2023-11-06 | 2023-11-13 | 2023-11-27 | 2023-11-29 | 2023-12-01 | Solid Merchandising | [13 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | Aklan | 114853 | Nabaoy Elementary School | MALAY | 2nd | 1 | 3 | Repair of Classrooms | 1827985.82 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Aklan | 500035 | Numancia Integrated School | NUMANCIA | 2nd | 1 | 12 | Repair of Classrooms | 8133082.16 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 114942 | Iba ES | ANINI-Y | Lone | 1 | 6 | Repair of Classrooms | 3233299.32 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 114953 | San Ramon ES | ANINI-Y | Lone | 1 | 5 | Repair of Classrooms | 3399770.56 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Already conducted final inspection. Contractor complying to punchlist | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 114959 | Binangbang Elementary School | BARBAZA | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 114976 | Concepcion ES | BELISON | Lone | 1 | 8 | Repair of Classrooms | 5240747.43 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115000 | Tono-an ES | BUGASONG | Lone | 1 | 11 | Repair of Classrooms | 4904925.59 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | For final inspection | [12 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115052 | San Antonio ES | CULASI | Lone | 1 | 10 | Repair of Classrooms | 6500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115074 | La Paz ES | HAMTIC | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115135 | San Juan PS | LIBERTAD | Lone | 1 | 2 | Repair of Classrooms | 1212359.82 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115354 | Tuno Elementary School | TIBIAO | Lone | 1 | 11 | Repair of Classrooms | 7150000 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115367 | Igbalogo Elementary School | TOBIAS FORNIER (DAO) | Lone | 1 | 4 | Repair of Classrooms | 2600000 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Antique | 115381 | Nasuli ES | TOBIAS FORNIER (DAO) | Lone | 1 | 5 | Repair of Classrooms | 3000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | Delayed due to delay on the approval of variation orders | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | Lone | 1 | 63 | Repair of Classrooms | 16000000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Bago City | 117494 | Abuanan ES | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 2988398.2 | DPWH (Batch 1) | 2840490.97 | COMPLETED | 100% |  |  |  | 23GN0088 | [5 empty] | 3rd Dragon Builders Innovation | for punchlisting | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4th | 1 | 2 | Repair of Classrooms | 967373.67 | DEPED (Batch 1) |  | Reverted | 0% | [10 empty] | Reverted; Revised Program of Works due to increased in the amount of allocation. New allocation amount is 933,515.59 as reflected in the Sub-ARO | [12 empty] | 0% | [7 empty] | Reverted
REPAIR 2023 | Region VI | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 3685984.43 | DPWH (Batch 1) | 3556969.35 | COMPLETED | 100% |  |  |  | 23GN0089 | [5 empty] | SBK Construction Supplies &Services, Inc. | Punchlisted; For rectification works | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Cadiz City | 117531 | Cadiz East Elem. School II | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4033015.36 | DPWH (Batch 1) |  | Ongoing | 53% | [23 empty] | 53% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Cadiz City | 117546 | Cadiz East I ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 2641333.48 | DPWH (Batch 1) |  | Ongoing | 53% | [23 empty] | 53% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Cadiz City | 117577 | M.V. Gamboa ES | CADIZ CITY | 2nd | 1 | 9 | Repair of Classrooms | 4138015.36 | DPWH (Batch 1) |  | Ongoing | 53% | [23 empty] | 53% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Guimaras | 115863 | Hoskyn Elementary School | JORDAN (Capital) | Lone | 1 | 13 | Repair of Classrooms | 8131708.84 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-02-05 | 2024-10-18 | [21 empty] | 100% |  |  | 10.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | Guimaras | 115906 | Guiwanon Elementary School | NUEVA VALENCIA | Lone | 1 | 3 | Repair of Classrooms | 2292876.22 | DPWH (Batch 1) |  | COMPLETED | 100% | 2023-11-22 | [22 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Guimaras | 115884 | Casilan Elementary School | SIBUNAG | Lone | 1 | 3 | Repair of Classrooms | 2404681.08 | DPWH (Batch 1) |  | COMPLETED | 100% | 2023-11-07 | [22 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Himamaylan City | 117076 | Himamaylan CS | CITY OF HIMAMAYLAN | 5th | 1 | 32 | Repair of Classrooms | 20710702.02 | DPWH (Batch 1) |  | COMPLETED | 100% | 2024-03-12 | [8 empty] | RISM | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Himamaylan City | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5th | 1 | 40 | Repair of Classrooms | 18127395.24 | DPWH (Batch 1) | 16617280.35 | COMPLETED | 100% | 2024-03-12 |  |  | 23GL0110 | [5 empty] | YRJ ENGINEERING SERVICES | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116564 | Aguiauan Elementary School | MIAGAO | 1st | 1 | 4 | Repair of Classrooms | 2016272.62 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116716 | Amboyu-an Elementary School | SAN JOAQUIN | 1st | 1 | 7 | Repair of Classrooms | 1982221.74 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116741 | San Luis ES | SAN JOAQUIN | 1st | 1 | 7 | Repair of Classrooms | 2488661.91 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116749 | Valverde ES | SAN JOAQUIN | 1st | 1 | 6 | Repair of Classrooms | 3305929.51 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 180013 | Sambag PS | ZARRAGA | 2nd | 1 | 2 | Repair of Classrooms | 907827.62 | DEPED (Batch 2) | 692960.41 | COMPLETED | 100% | 2025-02-15 | 2024-09-28 | BEFF2023 B2-RVI-022-ILOILO-L1 | BEFF2023 B2-RVI-022-ILOILO-L1 | 2024-04-15 | 2024-04-15 | 2024-04-29 | 2024-08-12 | 2024-09-16 | ANJUSH BUILDERS | SDo does not received any ATPor memo/ sub-aro to facilitate this project. Previously it was realigned to zaraga CES by DPWH | [12 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | Iloilo | 116863 | Zarraga CES | ZARRAGA | 2nd | 1 | 2 | Repair of Classrooms | 3540000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116104 | Alabidhan ES | BINGAWAN | 3rd | 1 | 11 | Repair of Classrooms | 5948743.45 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116114 | Quinangyana ES | BINGAWAN | 3rd | 1 | 10 | Repair of Classrooms | 5021523.53 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 3rd | 1 | 11 | Repair of Classrooms | 4918391.96 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116173 | Agcalaga ES | CALINOG | 3rd | 1 | 2 | Repair of Classrooms | 2500000 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116448 | Cabatangan PS | LAMBUNAO | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 3rd | 1 | 5 | Repair of Classrooms | 2915360.46 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116097 | Caw-i Primary School | BATAD | 5th | 1 | 2 | Repair of Classrooms | 2700000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo | 116761 | Cabas-an ES | SAN RAFAEL | 5th | 1 | 8 | Repair of Classrooms | 6000000 | DPWH (Batch 1) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | Iloilo City | 117581 | Calaparan ES | ILOILO CITY (Capital) | Lone | 1 | 15 | Repair of Classrooms | 3253237.06 | DPWH (Batch 1) | 3107980.01 | COMPLETED | 100% | 20/2/2024 |  | 170 | 23GJ0124 | 2023-08-09 | 15/9/2023 | 27/9/2023 | 13/11/2023 | 17/11/2023 | BEATUS BUILDERS | Completed | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo City | 117629 | Jalandoni MS | ILOILO CITY (Capital) | Lone | 1 | 2 | Repair of Classrooms | 814156.9 | DEPED (Batch 1) | 667973.35 | COMPLETED | 100% | 2024-07-02 | 2024-05-04 | NONE | 2023-12-002 | 2023-10-20 | 2023-10-27 | 2023-12-12 | 2023-12-19 | 2023-12-29 | STEVEN CONSTRUCTION & SUPPLY | Completed | [12 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | Iloilo City | 302747 | La Paz NHS - San Isidro Campus | ILOILO CITY (Capital) | Lone | 1 | 18 | Repair of Classrooms | 4354560 | DPWH (Batch 2) | 4194560.04 | COMPLETED | 100% | 2024-05-18 | 2024-06-09 | NONE | 23GJ0136 | [5 empty] | BENSON Const. | Completed | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo City | 117583 | Severo Abeto ES | ILOILO CITY (Capital) | Lone | 1 | 3 | Repair of Classrooms | 1167217.69 | DPWH (Batch 1) | 1075666.4 | COMPLETED | 100% | 21/1/2024 |  | 170 | 23GJ0125 | 2023-08-09 | 15/9/2023 | 27/9/2023 | 13/11/2023 | 17/11/2023 | NOE'S BUILDERS | Completed | [12 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Iloilo City | 117584 | Sto. Domingo ES | ILOILO CITY (Capital) | Lone | 1 | 2 | Repair of Classrooms | 806455.7 | DEPED (Batch 1) | 581887.65 | COMPLETED | 100% | 2024-07-02 | 2024-05-04 | NONE | 2023-12-002 | 2023-10-20 | 2023-10-27 | 2023-12-12 | 2023-12-19 | 2023-12-29 | STEVEN CONSTRUCTION & SUPPLY | Completed | [12 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | Iloilo City | 117610 | Ticud ES | ILOILO CITY (Capital) | Lone | 1 | 4 | Repair of Classrooms | 725760 | DEPED (Batch 2) | 619354.91 | COMPLETED | 100% | 2024-09-05 | 2024-08-30 | NONE | 2024-02-001 | 2024-01-05 | 2024-01-12 | 2024-01-26 | 2024-03-28 | 2024-04-01 | NORTH STAR CONST. & TRADING | Completed | [12 empty] | 100% |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6th | 1 | 16 | Repair of Classrooms | 8750000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | Kabankalan City | 302790 | TAGUKON NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6th | 1 | 9 | Repair of Classrooms | 7400000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | La Carlota City | 117646 | Haguimit ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 2929318.76 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4th | 1 | 5 | Repair of Classrooms | 2147772.31 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.25 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | La Carlota City | 117645 | Miguel S. Mondia ES | LA CARLOTA CITY | 4th | 1 | 1 | Repair of Classrooms | 627522.77 | DEPED (Batch 1) | 575,831.40/29,723.19 | COMPLETED | 100% | 2024-04-30 | 2024-03-06 | PI2023-42 | 2024-01-004 | 2023-12-14 | 2024-01-06 | 2024-01-10 | 2024-01-19 | 2024-01-30 | Woodtrade Construction and Supply | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region VI | La Carlota City | 117642 | Nagasi ES | LA CARLOTA CITY | 4th | 1 | 4 | Repair of Classrooms | 2428520.48 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | La Carlota City | 117649 | San Miguel ES I | LA CARLOTA CITY | 4th | 1 | 2 | Repair of Classrooms | 1210779.49 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6th | 1 | 3 | Repair of Classrooms | 2245000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Negros Occidental | 117144 | C.L. Hodges ES | HINOBA-AN (ASIA) | 6th | 1 | 3 | Repair of Classrooms | 2310000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6th | 1 | 4 | Repair of Classrooms | 2850000 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VI | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY | 1st | 1 | 23 | Repair of Classrooms | 52600000 | DPWH (Batch 1) | 49509727.06 | Ongoing | 95% | 2024-10-01 |  | 23GQ0071 |  | 2023-09-05 | 2023-09-12 | SEPT. 28, 2023 | 2023-10-27 |  | Kenneth Construction & General Merchandise | On-going | [12 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VI | San Carlos City | 117749 | Marago-os ES | SAN CARLOS CITY | 1st | 1 | 3 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7250984.52 | COMPLETED | 100% | 2024-04-06 |  | 23GQ0072 |  | 2023-09-05 | 2023-09-12 | 2023-09-28 | 2023-10-27 |  | Kenneth Construction & General Merchandise | Finished | [12 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Silay City | 185001 | Dominador 'Oking' Jison Memorial Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 3811382.65 | DPWH (Batch 2) |  | COMPLETED | 100% | [10 empty] | For punclisting | [12 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Silay City | 302779 | Don Felix T. Lacson Memorial National High School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 2073578.52 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | For punclisting | [12 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3rd | 1 | 8 | Repair of Classrooms | 3131408.66 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | For punclisting | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VI | Silay City | 500201 | Violeta Integrated School | SILAY CITY | 3rd | 1 | 4 | Repair of Classrooms | 1120212.37 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | For punclisting | [12 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bais City | 120071 | Amalao Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 4280000 | DPWH (Batch 1) | 4086043.23 | COMPLETED | 100% | 2023-12-21 | 2024-03-03 | N/A | 23HK0157 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-09-20 | 2023-10-04 | NALE Construction | to schedule punchlist | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bais City | 120073 | Cambanjao ES | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 4110000 | DPWH (Batch 1) | 3960050 | COMPLETED | 100% | 2023-12-16 |  | N/A | 23HK0138 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. & Supplies | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bais City | 120076 | Dansulan ES | BAIS CITY | 2nd | 1 | 5 | Repair of Classrooms | 3710000 | DPWH (Batch 1) | 3566960.5 | COMPLETED | 100% | 2023-12-11 |  | N/A | 23HK0137 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Dumduma Construction and Trading | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bais City | 120104 | San Vicente Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 3340000 | DPWH (Batch 1) | - | COMPLETED | 100% |  | 2024-03-12 | [21 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bayawan City | 120146 | Canabuan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 4 | Repair of Classrooms | 665000 | DEPED (Batch 1) | 641500 | COMPLETED | 100% | [6 empty] | 9/14/2023 | 2023-10-05 | 2023-10-06 | HIT Contractors | [13 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 2035000 | DPWH (Batch 1) | 1959000 | COMPLETED | 100% | 2023-12-31 | 2024-03-15 | 23HL0107 | 23HL0107 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | Tribata Construction and Development | [13 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bayawan City | 120165 | Tayawan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 1745000 | DPWH (Batch 1) | 1681912.41 | COMPLETED | 100% | 2023-12-31 | 2024-03-15 | 23HL0108 | 23HL0108 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | RR Gadingan Construction | [13 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bayawan City | 120141 | Villareal Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 5 | Repair of Classrooms | 3945000 | DPWH (Batch 1) | 3796987.33 | COMPLETED | 100% | 2023-12-31 | 2024-03-15 | 23HL0106 | 23HL0106 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | NRS Builders and Supplies | [13 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Bohol | 186502 | Can-omay PS | ANTEQUERA | 1st | 1 | 1 | Repair of Classrooms | 258248.58 | DEPED (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302811 | Baclayon NHS | BACLAYON | 1st | 1 | 8 | Repair of Classrooms | 2716310.54 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118096 | Kinabag-an ES | CALAPE | 1st | 1 | 5 | Repair of Classrooms | 5345683.59 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118097 | Labu-on ES | CALAPE | 1st | 1 | 9 | Repair of Classrooms | 3672844.13 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118100 | Mantatao ES | CALAPE | 1st | 1 | 6 | Repair of Classrooms | 2074196.6 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312319 | Hagbuaya High School | CATIGBIAN | 1st | 1 | 6 | Repair of Classrooms | 1207513.07 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1st | 1 | 4 | Repair of Classrooms | 1672678.94 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118209 | Loreto ES | CORTES | 1st | 1 | 7 | Repair of Classrooms | 2987668.17 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118216 | San Roque Elementary School | CORTES | 1st | 1 | 8 | Repair of Classrooms | 2906428.22 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118534 | Bayacabac ES | MARIBOJOC | 1st | 1 | 2 | Repair of Classrooms | 692229.67 | DEPED (Batch 1) | 619354.91 | COMPLETED | 100% | 2024-09-05 |  | NONE | 2024-02-001 | 2024-01-05 | 2024-01-12 | 2024-01-26 | 2024-03-28 | 2024-04-01 | NORTH STAR CONST. & TRADING | for award | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118555 | Bolod Elementary School | PANGLAO | 1st | 1 | 8 | Repair of Classrooms | 3217773.27 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118700 | Sikatuna Central ES | SIKATUNA | 1st | 1 | 10 | Repair of Classrooms | 4489855.12 | DPWH (Batch 2) | 0 | Ongoing | 45% | [23 empty] | 45% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 312332 | Bagongbanwa High School | TUBIGON | 1st | 1 | 4 | Repair of Classrooms | 851985.27 | DEPED (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118785 | Jose Boja ES | TUBIGON | 1st | 1 | 7 | Repair of Classrooms | 2171819.18 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118791 | Pangapasan ES | TUBIGON | 1st | 1 | 3 | Repair of Classrooms | 2183161.95 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1st | 1 | 12 | Repair of Classrooms | 3750140.08 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118030 | Hingotanan ES | BIEN UNIDO | 2nd | 1 | 23 | Repair of Classrooms | 35000000 | DPWH (Batch 2) | 0 | Ongoing | 15% | [10 empty] | Bid-out february 20, 2024 | [12 empty] | 15% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 302857 | Hingotanan NHS | BIEN UNIDO | 2nd | 1 | 21 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 0 | Ongoing | 25% | [10 empty] | Bid-out february 20, 2024 | [12 empty] | 25% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118078 | Lubang Elementary School | BUENAVISTA | 2nd | 1 | 10 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 0 | Ongoing | 75% | [23 empty] | 75% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2nd | 1 | 18 | Repair of Classrooms | 9000000 | DPWH (Batch 2) | 0 | Ongoing | 15% | [10 empty] | Bid-out february 20, 2024 | [12 empty] | 15% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118186 | Bonbon Elementary School | CLARIN | 2nd | 1 | 3 | Repair of Classrooms | 1519267.88 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.23 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118218 | Babag ES | DAGOHOY | 2nd | 1 | 5 | Repair of Classrooms | 1610604.28 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | BIDDING 10/25/23 | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118222 | Can-oling ES | DAGOHOY | 2nd | 1 | 9 | Repair of Classrooms | 4792341.93 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118230 | San Vicente ES | DAGOHOY | 2nd | 1 | 14 | Repair of Classrooms | 7269351.88 | DPWH (Batch 2) | 0 | Ongoing | 70% | [10 empty] | bidding march 18, 2024 | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2nd | 1 | 24 | Repair of Classrooms | 9600000 | DPWH (Batch 2) | 0 | Ongoing | 93% | [10 empty] | bidding April 18, 2024 | [12 empty] | 93% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2nd | 1 | 39 | Repair of Classrooms | 16000000 | DPWH (Batch 2) | 0 | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118337 | Nasingin ES | GETAFE | 2nd | 1 | 11 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 0 | Ongoing | 50% | [10 empty] | bidding January 16, 2024 | [12 empty] | 50% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118380 | Liloan Norte ES | INABANGA | 2nd | 1 | 10 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312303 | Mayor Inocencio B. Mendez HS | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 24 | Repair of Classrooms | 9600000 | DPWH (Batch 2) | 0 | Ongoing | 37% | [10 empty] | bid out february 20, 2024 | [12 empty] | 37% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118599 | Popoo ES | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 9 | Repair of Classrooms | 3600000 | DPWH (Batch 2) | 0 | Ongoing | 18% | [10 empty] | bidding march 18, 2024 | [12 empty] | 18% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 501128 | Sto. Rosario Integrated School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 4 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 0 | Ongoing | 20% | [10 empty] | bid out february 6, 2024 | [12 empty] | 20% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118631 | Baryong Daan PS | SAN ISIDRO | 2nd | 1 | 2 | Repair of Classrooms | 1383898.75 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118635 | Cambansag Elementary | SAN ISIDRO | 2nd | 1 | 3 | Repair of Classrooms | 2294836.8 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118636 | Candungao ES | SAN ISIDRO | 2nd | 1 | 5 | Repair of Classrooms | 3012786.89 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2nd | 1 | 2 | Repair of Classrooms | 1301487.58 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118734 | Busalian ES | TALIBON | 2nd | 1 | 16 | Repair of Classrooms | 7200000 | DPWH (Batch 2) | 0 | Ongoing | 60% | [10 empty] | bid out January 16, 2024 | [12 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118735 | Calituban ES | TALIBON | 2nd | 1 | 13 | Repair of Classrooms | 6500000 | DPWH (Batch 2) | 0 | Ongoing | 50% | [10 empty] | bid out february 20, 2024 | [12 empty] | 50% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2nd | 1 | 22 | Repair of Classrooms | 7700000 | DPWH (Batch 2) | 0 | Ongoing | 30% | [10 empty] | bid out february 13, 2024 | [12 empty] | 30% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118732 | P/Lt. Eugenio B. Artiaga ES | TALIBON | 2nd | 1 | 15 | Repair of Classrooms | 6750000 | DPWH (Batch 2) | 0 | Ongoing | 30% | [10 empty] | bid out february 20, 2024 | [12 empty] | 30% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2nd | 1 | 3 | Repair of Classrooms | 1559243.56 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | BID OUT 10/19/23 | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2nd | 1 | 20 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 0 | Ongoing | 15% | [10 empty] | bidding march 19, 2024 | [12 empty] | 15% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 118802 | Bay-ang ES | UBAY | 2nd | 1 | 8 | Repair of Classrooms | 3235520.01 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | bid OUT - 10/16/23 | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312334 | Bulilis High School | UBAY | 2nd | 1 | 19 | Repair of Classrooms | 6969386.4 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118812 | Camambugan ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 6956511.08 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | bid OUT - 10/16/23 | [12 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2nd | 1 | 26 | Repair of Classrooms | 8437707.14 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | bid OUT - 11/08/23 | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118813 | Casate ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 13700000 | DPWH (Batch 2) | 0 | Ongoing | 30% | [10 empty] | bidding march 18, 2024 | [12 empty] | 30% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 303130 | Erico B. Aumentado High School | UBAY | 2nd | 1 | 9 | Repair of Classrooms | 3449802.31 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118825 | Lomangog ES | UBAY | 2nd | 1 | 16 | Repair of Classrooms | 7600000 | DPWH (Batch 2) | 0 | Ongoing | 25% | [10 empty] | bidding April 18, 2024 | [12 empty] | 25% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Bohol | 117943 | Katipunan Elementary School Annex | ALICIA | 3rd | 1 | 6 | Repair of Classrooms | 4366263 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302863 | La Hacienda NHS | ALICIA | 3rd | 1 | 17 | Repair of Classrooms | 5946502 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 117950 | Untaga ES | ALICIA | 3rd | 1 | 13 | Repair of Classrooms | 5732633 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302829 | CANDABONG NATIONAL HIGH SCHOOL | ANDA | 3rd | 1 | 11 | REPAIR OF CLASSROOMS | 9367164 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 117961 | LONDAG ES | ANDA | 3rd | 1 | 8 | REPAIR OF CLASSROOMS | 7801309 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118018 | Cantigdas Elementary School | BATUAN | 3rd | 1 | 5 | Repair of Classrooms | 3883411 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118026 | STA. CRUZ ES | BATUAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 3930471 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118111 | Cadapdapan ES | CANDIJAY | 3rd | 1 | 13 | Repair of Classrooms | 7096749 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118121 | Pagahat ES | CANDIJAY | 3rd | 1 | 2 | Repair of Classrooms | 1700751 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118126 | Tambongan ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 5079535 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3rd | 1 | 9 | Repair of Classrooms | 5408646 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118301 | San Pedro ES | DUERO | 3rd | 1 | 5 | Repair of Classrooms | 2402553 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312336 | Lungsodaan High School | MABINI | 3rd | 1 | 6 | Repair of Classrooms | 1982188 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118665 | CAMBAGUI ES | SEVILLA | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 3911090 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 302903 | SEVILLA NATIONAL HIGH SCHOOL | SEVILLA | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 4573882 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Bohol | 312362 | Nan-od High School | SIERRA BULLONES | 3rd | 1 | 4 | Repair of Classrooms | 1536710 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Bohol | 118858 | Omjon ES | VALENCIA | 3rd | 1 | 13 | Repair of Classrooms | 8230580 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Carcar City | 119159 | Liburon Elementary School | CITY OF CARCAR | 1st | 1 | 15 | Repair of Classrooms | 12335684.24 | DPWH (Batch 1) | 11902888 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Carcar City | 119181 | OCANA CENTRAL ES | CITY OF CARCAR | 1st | 1 | 12 | Repair of Classrooms | 8639234.46 | DPWH (Batch 2) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Carcar City | 119161 | PERRELOS ELEMENTARY SCHOOL | CITY OF CARCAR | 1st | 1 | 13 | Repair of Classrooms | 10161300.46 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119705 | Bahay-Bagacay ES | SIBONGA | 1st | 1 | 5 | Repair of Classrooms | 2809227.56 | DPWH (Batch 1) | 2700404.6 | COMPLETED | 100% | 2024-06-08 | 2024-01-24 | 23HE0182 | [5 empty] | 2023-10-25 | Ten twenty Allied Developers | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | completed
REPAIR 2023 | Region VII | Cebu | 118873 | Bulalacao ES | ALCOY | 2nd | 1 | 6 | Repair of Classrooms | 3038795.55 | DPWH (Batch 1) | - | Ongoing | 70% | 2024-04-08 |  | P00775256NP | 23HG0082 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | 647 Construction and development Corp. | (CLUSTER 3 ) 4,857,971.36 (to verify amount per site) | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 118877 | Nug-as ES | ALCOY | 2nd | 1 | 6 | Repair of Classrooms | 2047185.13 | DPWH (Batch 1) | - | Ongoing | 70% | 2024-04-08 |  | P00775257NP | 23HG0082 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | 647 Construction and development Corp. | (CLUSTER 3 ) 4,857,971.36 (to verify amount per site) | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119604 | Basak Elementary School | SAMBOAN | 2nd | 1 | 5 | Repair of Classrooms | 2710845.95 | DPWH (Batch 1) |  | Ongoing | 75% | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 2HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2 ) 5,434,867.65 (to verify amount per site) | [12 empty] | 75% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 500662 | Bulangsuran Integrated School | SAMBOAN | 2nd | 1 | 5 | Repair of Classrooms | 2535928.75 | DPWH (Batch 1) |  | Ongoing | 70% | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 23HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 187027 | Cambigong ES | SAMBOAN | 2nd | 1 | 4 | Repair of Classrooms | 2049809.28 | DPWH (Batch 1) |  | Ongoing | 60% | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 23HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | [12 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119606 | Cañorong ES | SAMBOAN | 2nd | 1 | 4 | Repair of Classrooms | 2501006.95 | DPWH (Batch 1) |  | Ongoing | 80% | 2024-11-05 |  | P00775264NP P00775262NP P00775259NP | 2HG0076 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 1 ) 6,633,547.64 (to verify amount per site) | [12 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119612 | Monteverde ES | SAMBOAN | 2nd | 1 | 3 | Repair of Classrooms | 1549154.16 | DPWH (Batch 1) |  | Ongoing | 60% | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 23HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2 ) 5,434,867.65 (to verify amount per site) | [12 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2nd | 1 | 3 | Repair of Classrooms | 1546172.27 | DPWH (Batch 1) |  | Ongoing | 60% | 2024-07-06 |  | P00775260NP P00775258NP P00775261NP | 23HG0081 | 2023-04-10 | 2023-11-10 | 24/10/2023 | 20/11/2023 | 2023-11-12 | APRIL ROSE ENT. & BUILDERS | (CLUSTER 2) 5,434,867.65 (to verify amount per site) poor workmanship | [12 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 303089 | San Sebastian NHS | SAMBOAN | 2nd | 1 | 17 | Repair of Classrooms | 8280717.16 | DPWH (Batch 1) | 7751165.3 | Ongoing | 90% | 2024-12-03 |  | P00775263NP | 23HG0075 | 28/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 2023-08-11 | APRIL ROSE ENT. & BUILDERS | [13 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119075 | Budbud ES | BARILI | 3rd | 1 | 7 | Repair of Classrooms | 3782401.92 | DPWH (Batch 1) | 3620017.25 | COMPLETED | 100% | 2024-08-01 | 24/04/2024 | P00775265NP-CW1 | 23HF00100 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | JAY-BR ENTERPRISES | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119078 | Gunting Elementary School | BARILI | 3rd | 1 | 8 | Repair of Classrooms | 4614236.54 | DPWH (Batch 1) | 4422738.26 | COMPLETED | 100% | 23/03/2024 | 24/04/2024 | P00775266NP-CW1 | 23HF00105 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | JAY-BR ENTERPRISES | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119553 | Anapog ES | PINAMUNGAHAN | 3rd | 1 | 19 | Repair of Classrooms | 8176833.34 | DPWH (Batch 1) | 7800598.53 | COMPLETED | 100% | 24/01/2024 | 2024-07-03 | P00775267NP-CW1 | 23HF0093 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 303076 | Anopog NHS | PINAMUNGAHAN | 3rd | 1 | 15 | Repair of Classrooms | 5125707.77 | DPWH (Batch 1) | 4920913.07 | COMPLETED | 100% | 2024-05-02 | 24/04/2024 | P00775267NP-CW1 | 23HF0092 | 2023-06-10 | 2023-12-10 | 24/10/2023 | 2023-03-11 | 2023-08-11 | BL PANGAN CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119557 | Camugao ES | PINAMUNGAHAN | 3rd | 1 | 10 | Repair of Classrooms | 5090040.12 | DPWH (Batch 1) | 4890757.81 | COMPLETED | 100% | 2024-05-02 | 24/04/2024 | P00775268NP-CW1 | 23HF0090 | 2023-06-10 | 2023-12-10 | 24/10/2023 | 2023-03-11 | 2023-08-11 | BL PANGAN CONSTRUCTION | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119562 | Lut-od ES | PINAMUNGAHAN | 3rd | 1 | 14 | Repair of Classrooms | 7243921.95 | DPWH (Batch 1) | 6950000 | COMPLETED | 100% | 23/01/2024 | 2024-06-03 | P00775269NP-CW1 | 23HF0091 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119567 | Punod ES | PINAMUNGAHAN | 3rd | 1 | 7 | Repair of Classrooms | 2977030.39 | DPWH (Batch 1) | 2868797.74 | COMPLETED | 100% | 2024-09-01 | 2024-06-03 | P00775270NP-CW1 | 23HF0103 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119571 | Sibago ES | PINAMUNGAHAN | 3rd | 1 | 7 | Repair of Classrooms | 3933029.84 | DPWH (Batch 1) | 3790517.21 | COMPLETED | 100% | 2024-09-01 | 2024-06-03 | P00775271NP-CW1 | 23HF0104 | 29/09/2023 | 2023-05-10 | 17/10/2023 | 23/10/2023 | 26/10/2023 | DMDG BUILDERS | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 501916 | Catarman Integrated School | LILOAN | 5th | 1 | 6 | Repair of Classrooms | 2189318.39 | DPWH (Batch 1) |  | Ongoing | 95% | [10 empty] | FOR PUNCHLISTING | [12 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119546 | Moabog ES | PILAR | 5th | 1 | 3 | Repair of Classrooms | 1934898.8 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119854 | Buenavista ES | TUDELA | 5th | 1 | 6 | Repair of Classrooms | 2842630.53 | DPWH (Batch 2) |  | Ongoing | 90% | [23 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119856 | Daan Secante ES | TUDELA | 5th | 1 | 3 | Repair of Classrooms | 1553637.41 | DPWH (Batch 2) | 1496542.62 | Ongoing | 30% | 27/07/2024 | [8 empty] | CYJE FIRST BUILDERS CONSTRUCTION CORP. | [13 empty] | 30% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6th | 1 | 36 | Repair of Classrooms | 396436.04 | DEPED (Batch 1) | 5233500 | Ongoing | 95% |  |  | CY 2023 BEFF Repair | CY 2023 BEFF Repair-DepED-R7-Cebu | 2024-04-06 | N/A | 2024-11-06 | 18/06/2024 | 2024-09-07 | BARR STEEL CONSTRUCTION | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119252 | Bangbang ES | CORDOVA | 6th | 1 | 12 | Repair of Classrooms | 4178938.39 | DPWH (Batch 1) | 3914891.02 | Ongoing | 95% | 15/02/2024 |  | P00775274NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA | 6th | 1 | 2 | Repair of Classrooms | 1028357.29 | DPWH (Batch 1) | 992364.78 | Ongoing | 95% | 15/02/2024 |  | P00775276NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119259 | Ibabao ES | CORDOVA | 6th | 1 | 11 | Repair of Classrooms | 3906152.75 | DPWH (Batch 1) | 3623398.99 | Ongoing | 95% | 15/02/2024 |  | P00775275NP | 223HN0156 | 2023-09-22 | 2023-09-29 | 2024-10-12 | 2023-10-18 | 2023-10-27 | Green world construction | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 118887 | Compostela ES | ALEGRIA | 7th | 1 | 10 | Repair of Classrooms | 5464765.99 | DPWH (Batch 1) | 5233500 | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119398 | Anao ES | GINATILAN | 7th | 1 | 3 | Repair of Classrooms | 1770932.8 | DPWH (Batch 1) | 1620000 | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119405 | Kagsing ES | GINATILAN | 7th | 1 | 5 | Repair of Classrooms | 2794373.38 | DPWH (Batch 1) | 2600000 | Ongoing | 95% | [9 empty] | FIRST GRANDEUR BUILDERS | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119442 | Lombo ES | MALABUYOC | 7th | 1 | 4 | Repair of Classrooms | 3075098.68 | DPWH (Batch 1) | 2887973.7 | COMPLETED | 100% |  | 2024-08-07 |  | 23HO0333 | [5 empty] | BT CONSTRUCTION & GENERAL SERVICES | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 502119 | Looc IS | MALABUYOC | 7th | 1 | 10 | Repair of Classrooms | 5768971.99 | DPWH (Batch 1) | 5483508.03 | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 312462 | Mahanlud NHS | MALABUYOC | 7th | 1 | 5 | Repair of Classrooms | 1959991.53 | DPWH (Batch 1) | 1800000 | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Cebu | 119594 | Butong ES | RONDA | 7th | 1 | 4 | Repair of Classrooms | 1611587.61 | DPWH (Batch 1) | 1532133.41 | COMPLETED | 100% | 2024-10-02 | 24/04/2024 | P00775283NP | 23HO0334 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | LA PRUEBA CONSTRUCTION | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 7th | 1 | 16 | Repair of Classrooms | 8186738.78 | DPWH (Batch 1) | 7850202.92 | COMPLETED | 100% | 24/05/2024 | 24/05/2024 | P00775284NP | 23HO0330 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | Ten twenty Allied Developers | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 7th | 1 | 14 | Repair of Classrooms | 5431268.01 | DPWH (Batch 1) | 5184452.32 | COMPLETED | 100% | 2024-10-03 | 21/10/2024 | P00775285NP | 23HO0332 | 2023-01-12 | 2023-11-12 | 21/12/2023 | 29/12/2023 | 2024-11-01 | BANTAY CONSTRUCTION | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1st | 1 | 46 | Repair of Classrooms | 5564000 | DPWH (Batch 1) | 5359000 | COMPLETED | 100% |  |  |  | 23HH0135 |  |  | Sept. 20, 2023 |  | Oct. 16, 2023 | Planac Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2nd | 1 | 104 | Repair of Classrooms | 9000000 | DPWH (Batch 1) | 8663198.33 | COMPLETED | 100% |  |  |  | 23HH0137 |  |  | Sept. 20, 2023 |  | Oct. 19, 2023 | EV Caballero | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2nd | 1 | 38 | Repair of Classrooms | 6350000 | DPWH (Batch 1) | 6062760 | COMPLETED | 100% |  |  |  | 23HH0136 |  |  | Sept. 20, 2023 |  | Oct. 17, 2023 | Matroson Builders & Eng'g Services | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu City | 119907 | Inayawan ES | CEBU CITY (Capital) | 2nd | 1 | 46 | Repair of Classrooms | 9351000 | DPWH (Batch 1) | 9101676.4 | COMPLETED | 100% |  |  |  | 23HH0138 |  |  | Sept. 20, 2023 |  | Oct. 19, 2023 | Corro Const. Devt & Trade Corp. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Cebu City | 187501 | Quiot ES | CEBU CITY (Capital) | 2nd | 1 | 32 | Repair of Classrooms | 5300000 | DPWH (Batch 1) | 5108546.19 | COMPLETED | 100% |  |  |  | 23HH0134 |  |  | Sept. 20, 2023 |  | Oct. 17, 2023 | JAJ & L Construction | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 119514 | Bairan Elementary School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 2102141.53 | DPWH (Batch 1) | 2017154.63 | COMPLETED | 100% | March 22, 2024 |  | P00775292NP | 23HE0167 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | BT CONSTRUCTION & GENERAL SERVICES | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 302929 | Balirong National High School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 1939995.27 | DPWH (Batch 1) | 1860000 | COMPLETED | 100% | March 22, 2024 |  | P00775294NP | 23HE0169 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | LRTY CONSTRUCTION & ENTERPRISES | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial National High School | CITY OF NAGA | 1st | 1 | 5 | Repair of Classrooms | 2784658.45 | DPWH (Batch 1) | 2680000 | COMPLETED | 100% | February 21, 2024 |  | P00775295NP | 23HE0181 | SEPTEMBER 15, 2023 | SEPTEMBER 22, 2023 | OCTOBER 04, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | PLANAC CONSTRUCTION | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 312433 | Lanas National High School | CITY OF NAGA | 1st | 1 | 3 | Repair of Classrooms | 1656748.55 | DPWH (Batch 1) | 1586757.8 | COMPLETED | 100% | February 21, 2024 |  | P00775297NP | 23HE0180 | SEPTEMBER 15, 2023 | SEPTEMBER 22, 2023 | OCTOBER 04, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | A.T. DUMLAO CONSTRUCTION, INC. | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 119518 | Langtad Elementary School | CITY OF NAGA | 1st | 1 | 2 | Repair of Classrooms | 999836.36 | DEPED (Batch 1) | 950096.3 | COMPLETED | 100% | March 05, 2024 | December 16, 2023 | cityofnaga 2023-02 | cityofnaga 2023-02 | November 01, 2023 |  | November 08, 2023 | November 17, 2023 | November 21, 2023 | TRI BAIRN CONSTRUCTION | [13 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 119519 | Lutac Elementary School | CITY OF NAGA | 1st | 1 | 5 | Repair of Classrooms | 2525761.63 | DPWH (Batch 1) | 2427359.77 | COMPLETED | 100% | March 22, 2024 |  | P00775293NP | 23HE0173 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | EMINENT BUILDERS INC. | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 119508 | Naalad Elementary School | CITY OF NAGA | 1st | 1 | 7 | Repair of Classrooms | 3498240.91 | DPWH (Batch 1) | 3365302.48 | COMPLETED | 100% | March 22, 2024 | February 2, 2024 | P00775291NP | 23HE0172 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | TEN TWENTY ALLIED DEVELOPERS | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 502093 | Npc-Colon Integrated School | CITY OF NAGA | 1st | 1 | 4 | Repair of Classrooms | 1999816.33 | DPWH (Batch 1) | 1922000 | COMPLETED | 100% | March 24, 2024 |  | P00775298NP | 23HE0168 | SEPTEMBER 12, 2023 | SEPTEMBER 22, 2023 | OCTOBER 02, 2023 | OCTOBER 18, 2023 | OCTOBER 24, 2023 | PLANAC CONSTRUCTION | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | City of Naga, Cebu | 303035 | Placido L. Señor National High School | CITY OF NAGA | 1st | 1 | 9 | Repair of Classrooms | 4499136.71 | DPWH (Batch 1) | 4331666.53 | COMPLETED | 100% | February 21, 2024 |  | P00775296NP | 23HE0170 | SEPTEMBER 12, 2023 | SEPTEMBER 19, 2023 | OCTOBER 02, 2023 | OCTOBER 17, 2023 | OCTOBER 24, 2023 | EMINENT BUILDERS INC. | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Danao City | 500447 | BINALIW INTEGRATED SCHOOL | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) | 1493454.93 | COMPLETED | 100% | 2023-12-02 |  | P00775300NP | 23HI0130 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction | Completed | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Danao City | 500745 | Cogon Cruz Integrated School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1200000 | DPWH (Batch 1) | 1192198.92 | COMPLETED | 100% | 2023-11-25 | 2023-11-25 | P00775301NP | 23HI0131 | 2023-09-06 | 2023-09-27 |  | 2023-09-29 | 2023-10-06 | WQC Design and Construction | Completed | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Danao City | 302959 | Elpidio H. Perez Memorial Technical-Vocational High School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) | 1441633.79 | COMPLETED | 100% | 2023-12-02 |  | P00775299NP | 23HI0132 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Danao City | 500783 | Guinacot Integrated School | DANAO CITY | 5th | 1 | 3 | Repair of Classrooms | 1200000 | DPWH (Batch 1) | 1192949.76 | COMPLETED | 100% | 2023-12-02 | 2023-12-02 | P00775302NP | 23HI0133 | 2023-09-06 | 2023-09-27 |  | 2023-10-03 | 2023-10-13 | WQC Design and Construction | Completed | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN | 1st | 1 | 1 | Repair of Classrooms | 2800000 | DPWH (Batch 1) | 2800000 | COMPLETED | 100% | 2023-12-29 | 2023-12-29 | P00775305NP | 23HJ0136 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY | N/A | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 120235 | Binobohan ES | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | Ongoing | 60% | 2024-01-06 | n/a | P00775303NP | 23HJ0117 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | KAWAII BUILDERS & SUPPLIES | N/A | [12 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Guihulngan City | 120244 | Don Pelagio Villegas Memorial E/S | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4600000 | COMPLETED | 100% | 2023-12-22 | 2023-12-22 | P00775304NP | 23HJ0107 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2023-09-13 | 2023-09-25 | K.M. GOLONG CONSTRUCTION | N/A | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 120267 | Guihulngan South CS | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | COMPLETED | 100% | 2024-01-06 | 2024-01-06 | P00775306NP | 23HJ0120 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | K.M. GOLONG CONSTRUCTION | N/A | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 120272 | Linantuyan ES | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3900000 | COMPLETED | 100% | 2023-12-29 | 2023-12-29 | P00775307NP | 23HJ0135 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY | N/A | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 324802 | P. Zamora National High School | CITY OF GUIHULNGAN | 1st | 1 | 4 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5400000 | COMPLETED | 100% | 2024-01-18 | 2024-01-18 | P00775308NP | 23HJ0125 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION | N/A | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Guihulngan City | 120638 | Tabon Elementary School | VALLEHERMOSO | 1st | 1 | 3 | Repair of Classrooms | 4400000 | DPWH (Batch 1) | 4400000 | COMPLETED | 100% | 2024-04-15 | 2024-01-08 | P00775309NP | 23HJ0127 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION | N/A | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 119977 | Gun-ob Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 10 | Repair of Classrooms | 3500000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 312704 | Marigondon NHS-Sudtonggan Night High School | LAPU-LAPU CITY (OPON) | 6th | 1 | 4 | Repair of Classrooms | 2000000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 119955 | Pangan-an Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 7 | Repair of Classrooms | 2800000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 119956 | Poo Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | 10 | Repair of Classrooms | 5000000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 303188 | Pusok NHS - Pusok Night HS | LAPU-LAPU CITY (OPON) | 6th | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Lapu-Lapu City | 303191 | Sta. Rosa NHS - Pangan-an High School | LAPU-LAPU CITY (OPON) | 6th | 1 | 5 | Repair of Classrooms | 2500000 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6th | 1 | 9 | Repair of Classrooms | 1379578 | DPWH (Batch 1) | 1330123.48 | COMPLETED | 100% | 2024-01-01 | 2023-12-28 | P00775316NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6th | 1 | 9 | Repair of Classrooms | 2805450 | DPWH (Batch 1) | 2682155.83 | COMPLETED | 100% | 2024-01-01 | 2024-04-15 | P00775319NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 120018 | Don Calixto C. Yongco, Sr. ES (Tawason ES) | MANDAUE CITY | 6th | 1 | 3 | Repair of Classrooms | 1023122 | DPWH (Batch 1) | 985489.62 | COMPLETED | 100% | 2024-01-01 | 2023-12-28 | P00775318NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 303197 | Don Gerardo LLOMNHS | MANDAUE CITY | 6th | 1 | 6 | Repair of Classrooms | 1650000 | DPWH (Batch 1) | 1589835.3 | COMPLETED | 100% | 2024-01-01 | 2024-04-15 | P00775320NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 119996 | Ibabao-Estancia ES | MANDAUE CITY | 6th | 1 | 4 | Repair of Classrooms | 857402 | DEPED (Batch 1) | 761022.91 | COMPLETED | 100% | 2024-04-20 | March 18, 2024 | REP2023-01 | 23-11-036 | September 1, 2023 | September 8, 2023 | September 20, 2023 | September 26, 2023 | 2023-11-20 | HERO Construction & Development Corporation | Clustered Project | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 119999 | Labogon ES | MANDAUE CITY | 6th | 1 | 2 | Repair of Classrooms | 942214 | DEPED (Batch 1) | 836354.84 | COMPLETED | 100% | 2024-04-20 | March 18, 2024 | [21 empty] | 100% |  |  | 2.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 120000 | Leonard Wood ES | MANDAUE CITY | 6th | 1 | 2 | Repair of Classrooms | 825130 | DEPED (Batch 1) | 732309.85 | COMPLETED | 100% | 2024-04-20 | March 18, 2024 | [21 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 303201 | Mandaue City Science HS | MANDAUE CITY | 6th | 1 | 11 | Repair of Classrooms | 1691500 | DPWH (Batch 1) | 1629685.67 | COMPLETED | 100% | 2024-01-01 |  | P00775321NP | 23HN0158 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | GTM Builders and Supply | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Mandaue City | 120017 | Tabok ES II | MANDAUE CITY | 6th | 1 | 14 | Repair of Classrooms | 2500000 | DPWH (Batch 1) | 2410423.83 | COMPLETED | 100% | 2024-01-01 |  | P00775317NP | 23HN0159 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-18 | 2023-10-27 | Bantay Construction | CLUSTERED PROJECT | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120039 | Carol-an Elementary School | AYUNGON | 1st | 1 | 7 | Repair of Classrooms | 6900000 | DPWH (Batch 1) | 6608793.79 | COMPLETED | 100% | 02/20/2024 |  | P00775322NP | 23HJ0119 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120040 | Duli-Duli Elementary School | AYUNGON | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4385649.39 | COMPLETED | 100% | 12/22/23 |  | P00775323NP | 23HJ0108 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 6100000 | DPWH (Batch 1) | 5835766.89 | COMPLETED | 100% | 2024-10-02 |  | P00775326NP | 23HJ0122 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120057 | Tampocon I Elementary School | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4968985.83 | COMPLETED | 100% | 2024-06-01 |  | P00775324NP | 23HJ0134 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120058 | Tibyawan Elementary School | AYUNGON | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5166301.97 | COMPLETED | 100% | 2024-08-01 |  | P00775325NP | 23HJ0129 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120170 | Batangan Elementary School | BINDOY (PAYABON) | 1st | 1 | 8 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7285000 | COMPLETED | 100% | 3/17/24 |  | P00775327NP | 23HJ0131 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1st | 1 | 12 | Repair of Classrooms | 8400000 | DPWH (Batch 1) | 8040003.5 | COMPLETED | 100% | 3/16/24 |  | P00775329NP | 23HJ0106 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/15/23 | 9/25/23 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 189519 | Naula-an Elementary School | BINDOY (PAYABON) | 1st | 1 | 2 | Repair of Classrooms | 5500000 | DPWH (Batch 1) | 5248804.6 | COMPLETED | 100% | 12/22/23 |  | P00775328NP | 23HJ0110 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120291 | Bangcal Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164904.61 | COMPLETED | 100% | 2024-06-01 |  | P00775330NP | 23HJ0115 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 2 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5191029.12 | COMPLETED | 100% | 2024-01-02 |  | P00775331NP | 23HJ0105 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Higel Construction | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120297 | Irene Elementary School | JIMALALUD | 1st | 1 | 1 | Repair of Classrooms | 2270000 | DPWH (Batch 1) | 2180230.39 | Ongoing | 99% | 2024-01-02 |  | P00775329NP | 23HJ0109 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Kawaii Builders and Supplies | [13 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120304 | Owacan ES | JIMALALUD | 1st | 1 | 6 | Repair of Classrooms | 4900000 | DPWH (Batch 1) | 4708620.97 | COMPLETED | 100% | 2024-10-02 |  | P00775333NP | 23HJ0124 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Higel Construction | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120308 | Tamao Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5205977.97 | COMPLETED | 100% | 2024-08-01 |  | P00775334NP | 23HJ0128 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Fakujo Builders | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120314 | Biga-a ES | LA LIBERTAD | 1st | 1 | 3 | Repair of Classrooms | 2900000 | DPWH (Batch 1) | 2779994.93 | COMPLETED | 100% | 2024-06-01 |  | P00775335NP | 23HJ0116 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120315 | Busilac ES | LA LIBERTAD | 1st | 1 | 6 | Repair of Classrooms | 6500000 | DPWH (Batch 1) | 6202500 | COMPLETED | 100% | 3/17/24 |  | P00775336NP | 23HJ0118 | 9/14/23 | 9/21/23 | 2023-03-10 | 10/18/2023 | 2023-03-11 | H.I.T. Contractors | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120326 | Mapalasan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 3370000 | DPWH (Batch 1) | 3219891.04 | COMPLETED | 100% | 12/22/23 |  | P00775337NP | 23HJ0111 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120328 | Nasunggan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4399882.18 | Ongoing | 98% | 12/22/23 |  | P00775338NP | 23HJ0112 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply | [13 empty] | 98% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120330 | Pangca ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 7000000 | DPWH (Batch 1) | 6724010.14 | COMPLETED | 100% | 12/29/23 |  | P00775339NP | 23HJ0126 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Higel Construction | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120380 | Bagtic ES | MANJUYOD | 1st | 1 | 6 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7305783.65 | COMPLETED | 100% | 2024-10-02 |  | P00775340NP | 23HJ0113 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120391 | LOCAY E/S | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 4700000 | DPWH (Batch 1) | 4510326.42 | COMPLETED | 100% | 2024-06-01 |  | P00775341NP | 23HJ0121 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120397 | Palay ES | MANJUYOD | 1st | 1 | 2 | Repair of Classrooms | 5560000 | DPWH (Batch 1) | 5306555.02 | COMPLETED | 100% | 12/27/23 |  | P00775342NP | 23HJ0104 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/19/23 | 9/28/23 | E.F.V. Construction Services | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120399 | Sagrada ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5168401.97 | COMPLETED | 100% | 2024-08-01 |  | P00775343NP | 23HJ0132 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120402 | San Isidro ES | MANJUYOD | 1st | 1 | 5 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6416000 | COMPLETED | 100% | 2024-02-01 |  | P00775344NP | 23HJ0133 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | MAI Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120405 | Tubod ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164201.97 | COMPLETED | 100% | 2024-08-01 |  | P00775345NP | 23HJ0130 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120579 | Banga Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7670000 | COMPLETED | 100% | 02/20/2024 |  | P00775346NP | 23HJ0114 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6414976.03 | COMPLETED | 100% | 02/20/2024 |  | P00775347NP | 23HJ0123 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120027 | Panusuan Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 2 | Repair of Classrooms | 2550000 | DPWH (Batch 2) | 0 | COMPLETED | 100% | 2024-05-10 |  | N/A |  | September 26, 2023 | October 04, 2023 | October 18, 2023 | [16 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 303209 | Silab Community High School Annex | AMLAN (AYUQUITAN) | 2nd | 1 | 8 | Repair of Classrooms | 3660000 | DPWH (Batch 1) | 3513835 | COMPLETED | 100% | 2023-12-10 |  | N/A | 23KH0133 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 | [14 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120029 | Tandayag Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 7 | Repair of Classrooms | 8500000 | DPWH (Batch 2) | 0 | COMPLETED | 100% | 2024-06-08 |  | N/A |  | September 26, 2023 | October 04, 2023 | October 18, 2023 | [16 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 189530 | Alagasihan Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2140000 | DPWH (Batch 1) | 2059300 | COMPLETED | 100% | 2023-11-15 |  | N/A | 23KH0153 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 | [14 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120338 | Arebasore Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3360000 | DPWH (Batch 1) | 3236735.97 | COMPLETED | 100% | 2023-12-11 |  | N/A | 23KH0154 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 15, 2023 | October 04, 2023 | [14 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120340 | Baliw Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3730000 | DPWH (Batch 1) | 3595000 | COMPLETED | 100% | 2023-12-14 |  | N/A | 23KH0144 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 | [14 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120344 | Basakan Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2320000 | DPWH (Batch 1) | 2216406.05 | Ongoing | 99% | 2023-11-17 |  | N/A | 23KH0149 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 312924 | Campanun-an Senior High School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2340000 | DPWH (Batch 1) | 2235488.03 | Ongoing | 98% | 2023-11-17 |  | N/A | 23KH0150 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 98% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120350 | Campo-aling Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2670000 | DPWH (Batch 1) | 2570218 | COMPLETED | 100% | 2023-12-03 |  | N/A | 23KH0151 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 05, 2023 | [14 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120352 | Cansal-ing Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2220000 | DPWH (Batch 1) | 2123745.83 | Ongoing | 99% | 2023-11-16 |  | N/A | 23KH0152 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120358 | Don Cristito C. Tirambulo MES | MABINAY | 2nd | 1 | 6 | Repair of Classrooms | 4830000 | DPWH (Batch 1) | 4650095 | COMPLETED | 100% | 2023-12-28 |  | N/A | 23KH0141 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 | [14 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120360 | Himocdungon Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 3940000 | DPWH (Batch 1) | 3793255 | Ongoing | 99% | 2023-12-17 |  | N/A | 23KH0156 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 189510 | Lower Capanun-an Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 4530000 | DPWH (Batch 1) | 4361349 | COMPLETED | 100% | 2023-12-24 | 2025-02-10 | N/A | 23KH0143 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 19, 2023 | October 03, 2023 | [14 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2710000 | DPWH (Batch 1) | 2587158.27 | Ongoing | 99% | 2023-12-02 |  | N/A | 23KH0147 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120376 | Tadlong Elementary School | MABINAY | 2nd | 1 | 5 | Repair of Classrooms | 3050000 | DPWH (Batch 1) | 2928830 | COMPLETED | 100% | 2023-12-06 |  | N/A | 23KH0155 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 | [14 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120378 | Tara Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3620000 | DPWH (Batch 1) | 3453184 | COMPLETED | 100% | 2023-12-13 | 2024-06-24 | N/A | 23KH0148 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 14, 2023 | October 03, 2023 | [14 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3410000 | DPWH (Batch 1) | 3285000 | COMPLETED | 100% | 2023-12-11 |  | N/A | 23KH0146 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 | [14 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120379 | Tingtingon ES | MABINAY | 2nd | 1 | 1 | Repair of Classrooms | 1830000 | DPWH (Batch 1) | 1747241.23 | Ongoing | 99% | 2023-11-11 |  | N/A | 23KH0142 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | [12 empty] | 99% | [7 empty] | Ongoing
REPAIR 2023 | Region VII | Negros Oriental | 120439 | Sra. Ascion Elementary School | SAN JOSE | 2nd | 1 | 9 | Repair of Classrooms | 8120000 | DPWH (Batch 1) | 7831080 | COMPLETED | 100% | 2024-02-21 |  | N/A | 23KH0132 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 | Ashleyka Construction & Supplies | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120504 | Buenavista Elementary School | SANTA CATALINA | 3rd | 1 | 7 | Repair of Classrooms | 5920000 | DPWH (Batch 1) | 5706383.04 | COMPLETED | 100% | 2023-10-04 |  | N/A | 23HL0089 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120508 | Danao Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1550000 | DPWH (Batch 1) | 1493258.11 | COMPLETED | 100% | 2023-10-05 |  | N/A | 23HL0090 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120516 | Omol Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1780000 | DPWH (Batch 1) | 1715774.88 | COMPLETED | 100% | 2023-10-05 |  | N/A | 23HL0091 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120471 | Nawacat Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2310000 | DPWH (Batch 1) | 2223687.34 | COMPLETED | 100% | 2023-10-04 |  | N/A | 23HL0092 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 189507 | Ulayan Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2145000 | DPWH (Batch 1) | 2067761.72 | COMPLETED | 100% | 2023-10-15 |  | N/A | 23HL0103 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | NRS BUILDERS & SUPPLIES | [13 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Negros Oriental | 120612 | Dobdob ES | VALENCIA (LUZURRIAGA) | 3rd | 1 | 2 | Repair of Classrooms | 1480000 | DPWH (Batch 1) | 1425205.4 | COMPLETED | 100% | 2023-10-17 |  | N/A | 23HL0104 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | 5.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Siquijor | 500232 | Cabulihan IS | LARENA | Lone | 1 | 6 | Repair of Classrooms | 3725844.65 | DPWH (Batch 1) | 3582195.42 | COMPLETED | 100% | January 13, 2024 |  |  | 23HM0126 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | VNCO Construction | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | 6 | Repair of Classrooms | 3929375.04 | DPWH (Batch 1) | 3776406.34 | COMPLETED | 100% | January 13, 2024 |  |  | 23HM0128 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Tesar Builders | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Siquijor | 120697 | Cansayang ES | SAN JUAN | Lone | 1 | 6 | Repair of Classrooms | 3877378.6 | DPWH (Batch 1) | 3726306.32 | COMPLETED | 100% | January 13, 2024 |  |  | 23HM0127 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Quicksilver Construction Services | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 118704 | Cabawan Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 5 | Repair of Classrooms | 1435691.97 | DPWH (Batch 1) | 1380442.75 | COMPLETED | 100% | 2024-01-08 |  | N/A | 23HA0125 - Repair of 5 Classrooms, Cabawan Elementary School, Tagbilaran City, Bohol | 29/09/2023 | 2023-06-10 | 18/10/2023 | 24/10/2023 | 2023-10-11 | One orchard Construction and Corporation | None | [12 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 118705 | City East Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1781974.38 | DPWH (Batch 1) | 0 | COMPLETED | 100% |  |  | N/A | 23HA0139 - Repair of 6 Classrooms, City East Elementary School, Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation | None | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st | 1 | 30 | Repair of Classrooms | 9873441.61 | DPWH (Batch 1) | 0 | COMPLETED | 100% |  |  | N/A | 23HA0135 - Repair of 30 Classrooms, Dr. Cecilio Putong NHS (Bohol NHS), Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 26/10/2023 | 13/11/2023 | 2023-04-12 | HANZGRACE Construction and Trading Corp. | None | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 118711 | Mansasa Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 5 | Repair of Classrooms | 2220493.85 | DPWH (Batch 1) | 0 | COMPLETED | 100% |  |  | N/A | 23HA0134 - Repair of 5 Classrooms, Mansasa Elementary School, Tagbilaran City, Bohol | 2023-05-10 | 2023-12-10 | 24/10/2023 | 27/10/2023 | 13/11/2023 | C Jansen Construction and General Merchandise | None | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 118712 | San Isidro Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 1650000 | DPWH (Batch 1) | 0 | COMPLETED | 100% |  |  | N/A | 23HA0132 - Repair of 3 Classrooms, San Isidro Elementary School, Tagbilaran City, Bohol | 2023-05-10 | 2023-12-10 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation | None | [12 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tagbilaran City | 118714 | Taloto Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 1950296.72 | DPWH (Batch 1) | 0 | COMPLETED | 100% | 2024-02-16 |  | N/A | 23HA0137 - Repair of 3 classrooms, Taloto Elementary School, Tagbilaran City, Bohol | 2023-06-10 | 13/10/2023 | 2023-08-11 | 20/11/2023 | 2023-04-12 | One orchard Construction and Corporation | None | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 119797 | Candulawan Elementary School | CITY OF TALISAY | 1st | 1 | 9 | Repair of Classrooms | 1412421.99 | DPWH (Batch 1) | 0 | COMPLETED | 100% | 2025-09-03 |  | NA | 2024-02-Infra | 23/06/2024 | 24/06/2024 | 2024-05-07 | 2024-10-07 | 2024-03-10 | CJANSEN Construction and General Merchandise | None | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 233504 | Hawanay Elementary School | CITY OF TALISAY | 1st | 1 | 1 | Repair of Classrooms | 544552.33 | DEPED (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 233502 | Lawaan III Elementary School | CITY OF TALISAY | 1st | 1 | 6 | Repair of Classrooms | 1786120.53 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 322201 | Maghaway National High School | CITY OF TALISAY | 1st | 1 | 21 | Repair of Classrooms | 4326779.93 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 119796 | Manipis Elementary School | CITY OF TALISAY | 1st | 1 | 5 | Repair of Classrooms | 2371613.04 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 303056 | Mohon (Divino Amore) National High School | CITY OF TALISAY | 1st | 1 | 12 | Repair of Classrooms | 1023961.81 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 119790 | San Roque ES | CITY OF TALISAY | 1st | 1 | 27 | Repair of Classrooms | 3331406.01 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1st | 1 | 24 | Repair of Classrooms | 5805518.35 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 119792 | Tanke Elementary School | CITY OF TALISAY | 1st | 1 | 10 | Repair of Classrooms | 3163304.37 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 322208 | Tapul National High School | CITY OF TALISAY | 1st | 1 | 13 | Repair of Classrooms | 1843175.49 | DPWH (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | COMPLETD | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Talisay City | 119793 | Vicenta A. Manreal ES | CITY OF TALISAY | 1st | 1 | 12 | Repair of Classrooms | 725295.09 | DEPED (Batch 1) | 0 | COMPLETED | 100% | [10 empty] | for award | [12 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Tanjay City | 120549 | Don Placido Mapa Memorial School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 3270000 | DPWH (Batch 1) | 3117045.62 | COMPLETED | 100% | 2023-12-08 |  | P00775389NP-CWS | 23HK0139 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tanjay City | 120553 | Fabiana G. Banogon MES (Camansi ES) | CITY OF TANJAY | 2nd | 1 | 5 | Repair of Classrooms | 3880000 | DPWH (Batch 1) | 3707378.74 | COMPLETED | 100% | 2023-12-15 |  | P00775390NP-CWS | 23HK0140 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tanjay City | 120408 | Balayong Elem School | PAMPLONA | 2nd | 1 | 6 | Repair of Classrooms | 6480000 | DPWH (Batch 1) | 6248144.77 | COMPLETED | 100% | 2024-01-25 | 2024-01-25 |  | 23HK0134 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. and Supply | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tanjay City | 120425 | San Isidro Elementary School | PAMPLONA | 2nd | 1 | 2 | Repair of Classrooms | 3170000 | DPWH (Batch 1) | 3055741.71 | COMPLETED | 100% | 2023-12-08 | 2024-01-03 |  | 23HK0136 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-05 | Bigfoot Construction and Supply | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Tanjay City | 120427 | Sta. Agueda ES | PAMPLONA | 2nd | 1 | 9 | Repair of Classrooms | 8870000 | DPWH (Batch 1) | 8549504 | COMPLETED | 100% | 2024-03-03 | 2024-03-03 |  | 23HK0135 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | PER Construction | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120711 | Apid ES | TOLEDO CITY | 3rd | 1 | 5 | Repair of Classrooms | 2684230.31 | DPWH (Batch 1) | 2538029.64 | COMPLETED | 100% | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120713 | Biga ES | TOLEDO CITY | 3rd | 1 | 4 | Repair of Classrooms | 2185173.46 | DPWH (Batch 1) | 2103000 | COMPLETED | 100% | [9 empty] | TEN TWENTY ALLIED DEVELOPERS | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120714 | BUNGA ELEMENTARY SCHOOL | TOLEDO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3077072.35 | DPWH (Batch 1) | 2965000 | COMPLETED | 100% | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120728 | Carmen ES | TOLEDO CITY | 3rd | 1 | 2 | Repair of Classrooms | 1073677.95 | DPWH (Batch 1) | 1031089 | COMPLETED | 100% | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3rd | 1 | 10 | Repair of Classrooms | 3058483.89 | DPWH (Batch 1) | 2900809.83 | COMPLETED | 100% | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120717 | Gen. P. Del Rosario ES | TOLEDO CITY | 3rd | 1 | 6 | Repair of Classrooms | 3142137.85 | DPWH (Batch 1) | 3001256.23 | COMPLETED | 100% | [9 empty] | BL PANGAN CONSTRUCTION | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120750 | Jacinta Larosa ES (Ilihan ES) | TOLEDO CITY | 3rd | 1 | 4 | Repair of Classrooms | 2147753.82 | DPWH (Batch 1) | 2070582 | COMPLETED | 100% | [9 empty] | JAY-BR ENTERPRISES | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 120718 | Loay Elementary School | TOLEDO CITY | 3rd | 1 | 5 | Repair of Classrooms | 2756620.27 | DPWH (Batch 1) | 2658150.69 | COMPLETED | 100% | [9 empty] | YBK CONSTRUCTION | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3222929.08 | DPWH (Batch 1) | 3105000 | COMPLETED | 100% | [9 empty] | ANZEN CONSTRUCTION & SUPPLY | DPWH IMPLEMENTED | [12 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region VIII | Baybay City | 121116 | Balao Elementary School | CITY OF BAYBAY | 5th | 1 | 4 | Repair of Classrooms | 2998588.67 | DPWH (Batch 2) | 2577723.06 | COMPLETED | 100% | 2024-07-08 |  | 23IG0160 |  |  | 2024-02-23 | 2024-03-06 |  | 2024-04-03 | Just In Enterprises | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Baybay City | 121104 | Lintaon Elementary School | CITY OF BAYBAY | 5th | 1 | 1 | Repair of Classrooms | 766045.83 | DEPED (Batch 2) | 677505.8 | COMPLETED | 100% |  | 2024-04-04 | [5 empty] | 2024-02-27 | 2024-02-29 | Vhits D.G. Builders and Enterprises | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120759 | Barubuhan ES | ALMERIA | Lone | 1 | 1 | Repair of Classroom | 900000 | DEPED (Batch 2) |  | COMPLETED | 100% | 2024-06-28 | [8 empty] | J. Custorio Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | Lone | 1 | 9 | Repair of Classrooms | 8500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 313201 | Western Biliran High School for the Arts and Culture | ALMERIA | Lone | 1 | 16 | Repair of Classrooms | 15500000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120775 | Burabod ES | BILIRAN | Lone | 1 | 1 | Repair of Classroom | 890000 | DEPED (Batch 2) |  | COMPLETED | 100% | [9 empty] | MB Ang Construction & Supply | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120786 | Bunga ES | CABUCGAYAN | Lone | 1 | 12 | Repair of Classrooms | 12000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120789 | Capayas Elementary School | CABUCGAYAN | Lone | 1 | 1 | Repair of Classroom | 850000 | DEPED (Batch 2) |  | COMPLETED | 100% | [9 empty] | K & A Construction | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120794 | Pawikan ES | CABUCGAYAN | Lone | 1 | 1 | Repair of Classroom | 800000 | DEPED (Batch 2) |  | COMPLETED | 100% | 2024-07-30 | [8 empty] | Rovinval Construction | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120797 | Alegria ES | CAIBIRAN | Lone | 1 | 7 | Repair of Classrooms | 6000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN | Lone | 1 | 5 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120809 | Manlabang ES | CAIBIRAN | Lone | 1 | 3 | Repair of Classrooms | 9000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120810 | Maurang ES | CAIBIRAN | Lone | 1 | 1 | Repair of Classroom | 886000 | DEPED (Batch 2) |  | COMPLETED | 100% | [9 empty] | K & A Construction | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | Lone | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120820 | Culaba CS | CULABA | Lone | 1 | 1 | Repair of Classroom | 900000 | DEPED (Batch 2) |  | COMPLETED | 100% | [9 empty] | MB Ang Construction & Supply | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 120829 | Bilwang ES | KAWAYAN | Lone | 1 | 1 | Repair of Classroom | 1800000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | Lone | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Biliran | 303329 | MARIPIPI NATIONAL VOCATIONAL SCHOOL | MARIPIPI | Lone | 1 | 20 | Repair of Classrooms | 20000000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Eastern Samar | 303507 | Hinolaso National High School | DOLORES | Lone | 1 | 5 | Repair of Classrooms | 4908768.76 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122580 | Recare Elementary School | JIPAPAD | Lone | 1 | 3 | Repair of Classrooms | 1787581.08 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122581 | Roxas Elementary School | JIPAPAD | Lone | 1 | 3 | Repair of Classrooms | 1790684.62 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | Lone | 1 | 4 | Repair of Classrooms | 2547330.44 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | Lone | 1 | 3 | Repair of Classrooms | 2068582.23 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122535 | Banuyo Elementary School | MERCEDES | Lone | 1 | 2 | Repair of Classrooms | 1293675.1 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | Lone | 1 | 3 | Repair of Classrooms | 1304374.99 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122548 | San Jose Primary School | MERCEDES | Lone | 1 | 2 | Repair of Classrooms | 1319938.46 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122551 | Sung-an Elementary School | MERCEDES | Lone | 1 | 5 | Repair of Classrooms | 3285964.01 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122704 | Alog Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 2062660.23 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | Lone | 1 | 6 | Repair of Classrooms | 3285964.01 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122710 | Burak Elementary School | SALCEDO | Lone | 1 | 8 | Repair of Classrooms | 4971012.36 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122712 | Cagaut Elementary School | SALCEDO | Lone | 1 | 5 | Repair of Classrooms | 4927139.53 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122694 | Iberan Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 2825904.02 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122696 | Lusod Elementary School | SALCEDO | Lone | 1 | 5 | Repair of Classrooms | 3620429.05 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122719 | Sta. Cruz Elementary School | SALCEDO | Lone | 1 | 3 | Repair of Classrooms | 1308351.56 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | Lone | 1 | 7 | Repair of Classrooms | 4623552.37 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Eastern Samar | 122734 | Bahay Elementary School | SAN POLICARPO | Lone | 1 | 5 | Repair of Classrooms | 2870950.04 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122740 | Natividad Elementary School | SAN POLICARPO | Lone | 1 | 3 | Repair of Classrooms | 1781806.08 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122741 | Pangpang Elementary School | SAN POLICARPO | Lone | 1 | 8 | Repair of Classrooms | 4294322.54 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | SAN POLICARPO | Lone | 1 | 2 | Repair of Classrooms | 1789417.61 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Eastern Samar | 122752 | San Isidro Elementary School | SULAT | Lone | 1 | 3 | Repair of Classrooms | 2890150.12 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121229 | Nipa Elementary School | CALUBIAN | 3rd | 1 | 6 | Repair of Classrooms | 7200000 | DPWH (Batch 2) |  | Ongoing | 40% | [23 empty] | 40% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121220 | Villahermosa Elementary School | CALUBIAN | 3rd | 1 | 2 | Repair of Classrooms | 2400000 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121901 | Inangatan Elementary School | TABANGO | 3rd | 1 | 10 | Repair of Classrooms | 12000000 | DPWH (Batch 2) |  | Ongoing | 60% | [23 empty] | 60% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121902 | Leoncio Erejer Memorial Elementary School | TABANGO | 3rd | 1 | 6 | Repair of Classrooms | 7200000 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121904 | Tabayla Elementary School | TABANGO | 3rd | 1 | 12 | Repair of Classrooms | 14400000 | DPWH (Batch 2) |  | Ongoing | 40% | [23 empty] | 40% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121977 | Balite Elementary School | VILLABA | 3rd | 1 | 5 | Repair of Classrooms | 6300000 | DPWH (Batch 2) |  | Ongoing | 0% | [23 empty] | 0% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Leyte | 121397 | Anahaw Elementary School | HINDANG | 5th | 1 | 3 | Repair of Classrooms | 2136729.83 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121402 | Canha-ayon Elementary School | HINDANG | 5th | 1 | 1 | Repair of Classroom | 733962.67 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121405 | Doos Elementary School | HINDANG | 5th | 1 | 3 | Repair of Classrooms | 2034662.48 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121404 | Doos Sur Elementary School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1276362.61 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121406 | Himacugo Elementary School | HINDANG | 5th | 1 | 1 | Repair of Classroom | 394888.3 | DEPED (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 303375 | Hindang National High School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1092990.23 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5th | 1 | 4 | Repair of Classrooms | 1665651.98 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121413 | Tabok Elementary School | HINDANG | 5th | 1 | 6 | Repair of Classrooms | 1656698.97 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Leyte | 121414 | Tagbibi Elementary School | HINDANG | 5th | 1 | 2 | Repair of Classrooms | 1262787.41 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Maasin City | 122128 | Gawisan MGS | CITY OF MAASIN (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2656875.24 | DPWH (Batch 2) | 2557803.09 | COMPLETED | 100% | 2024-06-12 |  | P00775963NP | 23IL0085 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | PABLO S. LABASBAS CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Maasin City | 303457 | Guadalupe National High School | CITY OF MAASIN (Capital) | Lone | 1 | 9 | Repair of Classrooms | 8685498.16 | DPWH (Batch 2) | 8368866.47 | COMPLETED | 100% | 2024-08-16 |  | P00775967NP | 23IL0087 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Maasin City | 122136 | Mahayahay ES | CITY OF MAASIN (Capital) | Lone | 1 | 3 | Repair of Classrooms | 3986617.72 | DPWH (Batch 2) | 3839844.25 | COMPLETED | 100% | Jully 22, 2024 |  | P00775964N | 23IL0086 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | JQD CONST. & GEN. SERVICES | [13 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Maasin City | 303474 | Nonok Norte National High School | CITY OF MAASIN (Capital) | Lone | 1 | 9 | Repair of Classrooms | 8185498.52 | DPWH (Batch 2) | 7888024.72 | Ongoing | 95% | 2024-10-10 |  | P00775968N | 23IL0088 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Maasin City | 122143 | Rizal MGS | CITY OF MAASIN (Capital) | Lone | 1 | 1 | Repair of Classrooms | 1054153.28 | DPWH (Batch 2) | 1013775.63 | COMPLETED | 100% | 2024-04-13 |  | P00775965N | 23IL0084 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | JQD CONST. & GEN. SERVICES | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Maasin City | 122176 | Tigbawan IS | CITY OF MAASIN (Capital) | Lone | 1 | 12 | Repair of Classrooms | 10647251.1 | DPWH (Batch 2) | 10258866.07 | Ongoing | 80% | 2024-11-19 |  | P00775966NP | 23IL0089 | 2023-12-06 | 2023-12-13 | 2023-12-27 | 2023-12-29 | 2024-01-10 | M.G. VILLAMIN CONSTRUCTION | [13 empty] | 80% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Ormoc City | 313901 | Lilo-an National High School | ORMOC CITY | 4th | 1 | 6 | Repair of Classrooms | 1919998.18 | DPWH (Batch 2) | 1843533.86 | Ongoing | 50% | February 1, 2024 (suspended due to variation order) |  | P00775970NP | 23IF0121 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | RED AXE BUILDERS AND SUPPLY | suspended due to variation | [12 empty] | 50% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Ormoc City | 501363 | Mas-in Integrated School | ORMOC CITY | 4th | 1 | 3 | Repair of Classrooms | 2191829.57 | DPWH (Batch 2) | 2104538.68 | Ongoing | 90% | 2024-02-21 |  | P00775971NP | 23IF0122 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | CIRCLE Z VENTURES AND DEV. CORP. | The DPWH did not adhere to the approved Program of Works and they failed to submit any variation orders or change orders. | [12 empty] | 90% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Ormoc City | 194502 | VL Villacencio Elementary School | ORMOC CITY | 4th | 1 | 4 | Repair of Classrooms | 2023244.22 | DPWH (Batch 2) | 1942668.52 | COMPLETED | 100% | 2024-02-22 |  | P00775969NP | 23IF0123 | 2023-11-08 | 2023-11-15 | 2023-11-28 | 2023-12-29 | 2024-01-29 | MELGAZO CONSTRUCTION AND SUPPLY | 100% Completed | [12 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123596 | Macabetas Elementary School | JIABONG | 2nd | 1 | 2 | Repair of Classrooms | 1244245.58 | DPWH (Batch 2) | 1200696.98 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123597 | Malino Elementary School | JIABONG | 2nd | 1 | 1 | Repair of Classroom | 759392.25 | DEPED (Batch 2) | 727784.79 | COMPLETED | 100% | 2024-04-21 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | G.I AND 4K CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123606 | Tagbayaon Elementary School | JIABONG | 2nd | 1 | 1 | Repair of Classroom | 759392.25 | DEPED (Batch 2) | 722704.05 | COMPLETED | 100% | 2024-04-19 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | GPUY CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123609 | Canyoyo Elementary School | MARABUT | 2nd | 1 | 3 | Repair of Classrooms | 2007177.84 | DPWH (Batch 2) | 1936926.62 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2nd | 1 | 3 | Repair of Classrooms | 2037970.66 | DPWH (Batch 2) | 1966641.69 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123897 | Mallorga Elementary School | TALALORA | 2nd | 1 | 4 | Repair of Classrooms | 2293471.61 | DPWH (Batch 2) | 2213200.1 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123965 | Bioso Elementary School | ZUMARRAGA | 2nd | 1 | 6 | Repair of Classrooms | 3774847.84 | DPWH (Batch 2) | 3642728.17 | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Samar (Western Samar) | 123969 | Ibarra Elementary School | ZUMARRAGA | 2nd | 1 | 1 | Repair of Classroom | 759392 | DEPED (Batch 2) | 727676.25 | COMPLETED | 100% | 2024-04-21 |  |  |  | 2024-01-10 | 2024-01-18 | 2024-01-30 |  |  | G.I AND 4K CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Southern Leyte | 122180 | Asuncion Multigrade Elementary School | MACROHON | 1st | 1 | 3 | Repair of Classrooms | 1857144.76 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region VIII | Southern Leyte | 122195 | San Roque Elementary School | MACROHON | 1st | 1 | 19 | Repair of Classrooms | 11693996.12 | DPWH (Batch 2) | 11258065.84 | Ongoing | 95% | 2024-08-24 | [8 empty] | M.G VILLAMIN CONSTRUCTION | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Southern Leyte | 303485 | San Roque National High School | MACROHON | 1st | 1 | 21 | Repair of Classrooms | 12861943.5 | DPWH (Batch 2) | 12383426.33 | Ongoing | 95% | 2024-09-10 | [8 empty] | M.G VILLAMIN CONSTRUCTION | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1st | 1 | 9 | Repair of Classrooms | 5711613.49 | DPWH (Batch 2) |  | Ongoing | 95% | [23 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 1st | 1 | 10 | Repair of Classrooms | 6087058.2 | DPWH (Batch 2) | 5865961.61 | Ongoing | 95% | 2024-06-15 | [8 empty] | PABLO S. LABASBAS CONSTRUCTION CORP. | [13 empty] | 95% | [7 empty] | Ongoing
REPAIR 2023 | Region X | Camiguin | 126909 | Benhaan ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 528720.48 | DEPED (Batch 1) | 496580.82 | COMPLETED | 100% | 2024-02-02 | 2024-02-29 | REPAIR 2023 - R X - CAMIGUIN - 001 | OSEC-10-23-4914 | 2023-10-13 | n/a | 2023-12-01 | 2023-12-06 | 2024-01-03 | MINKONSTRAK ENG'G. & GEN. SRVCS. | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Camiguin | 126919 | Sorosoro ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2624639.98 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Camiguin | 126920 | Tagdo ES | MAMBAJAO (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2415853.39 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Camiguin | 126923 | Yumbing ES | MAMBAJAO (Capital) | Lone | 1 | 6 | Repair of Classrooms | 1924624.92 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2705200 | DPWH (Batch 1) | 2532178.52 | COMPLETED | 100% | 2023-10-21 | 2023-10-21 | P00775406NP | 23KL0096 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | KS AGAD Construction | Based on report submitted by DPWH | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | El Salvador | 127676 | Molugan Central School | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2755500 | DPWH (Batch 1) | 2634468.65 | COMPLETED | 100% | 2023-10-21 | 2023-10-21 | P00775407NP | 23KL0097 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | XYTEX Construction | Based on report submitted by DPWH | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | El Salvador | 127680 | Taytay ES | CITY OF EL SALVADOR | 2nd | 1 | 4 | Repair of Classrooms | 2650800 | DPWH (Batch 1) | 2531810.63 | COMPLETED | 100% | 2023-10-21 | 2023-10-21 | P00775408NP | 23KL0095 | 2023-05-17 | 2023-05-24 | 2023-06-15 | 2023-08-17 | 2023-08-22 | M & L Construction and Enterprises | Based on report submitted by DPWH | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 500453 | Kawit Oriental Integrated School | KAUSWAGAN | 1st | 1 | 5 | Repair of Classrooms | 2651306.27 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 5 | Repair of Classrooms | 2671255.51 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | 5 | Repair of Classrooms | 3232784.29 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 501557 | Matampay Integrated School | MATUNGAO | 1st | 1 | 7 | Repair of Classrooms | 4427006.66 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1st | 1 | 9 | Repair of Classrooms | 4924284.54 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 1st | 1 | 4 | Repair of Classrooms | 2267977.31 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 127210 | SAPAD ELEMENTARY SCHOOL | SAPAD | 2nd | 1 | 4 | Repair of Classrooms | 2695218.99 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Lanao del Norte | 501667 | Sapad Integrated School | SAPAD | 2nd | 1 | 3 | Repair of Classrooms | 1916237.29 | DPWH (Batch 1) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Occidental | 127542 | COLUPAN BAJO ES | SINACABAN | 2nd | 1 | 5 | Repair of Classrooms | 4200000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | With rectification works | [12 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Occidental | 127544 | ESTRELLA ES | SINACABAN | 2nd | 1 | 5 | Repair of Classrooms | 4419000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | With rectification works | [12 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Occidental | 304038 | KATIPUNAN NHS | SINACABAN | 2nd | 1 | 16 | Repair of Classrooms | 10930000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | With rectification works | [12 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 9 | Repair of Classrooms | 6485000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Completed | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2023 | Region X | Misamis Oriental | 127893 | San Alonzo ES | BALINGOAN | 1st | 1 | 3 | Repair of Classrooms | 1875000 | DPWH (Batch 1) | 1875000 | COMPLETED | 100% | 19/11/2023 | 2023-12-11 | P00775421NP | 23KK0187 | [19 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 304067 | Dampias A.O. Rañises NHS | BINUANGAN | 1st | 1 | 2 | Repair of Classrooms | 1336750.68 | DPWH (Batch 1) | 1336750.68 | COMPLETED | 100% | 2023-04-12 | 21/11/2023 | P00775422NP | 23KK0188 | [19 empty] | 100% |  |  | 12.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127718 | Bolisong ES | KINOGUITAN | 1st | 1 | 2 | Repair of Classrooms | 1349621.8 | DPWH (Batch 1) | 1349621.8 | COMPLETED | 100% | 2023-01-12 | 27/11/2023 | P00775423NP | 23KK0184 | [19 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127748 | Lumbo ES | LAGONGLONG | 1st | 1 | 4 | Repair of Classrooms | 2395243.76 | DPWH (Batch 1) | 2395243.76 | COMPLETED | 100% | 19/11/2023 | 15/11/2023 | P00775424NP | 23KK0185 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental | [12 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127749 | Manaol ES | LAGONGLONG | 1st | 1 | 2 | Repair of Classrooms | 1345592.02 | DPWH (Batch 1) | 1345592.02 | COMPLETED | 100% | 2023-04-12 | 20/11/2023 | P00775425NP | 23KK0195 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental | [12 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1st | 1 | 3 | Repair of Classrooms | 2115052.94 | DPWH (Batch 1) | 2115052.94 | COMPLETED | 100% | 2023-04-12 | 2023-08-11 | P00775426NP | 23KK0189 | [6 empty] | Ongoing Site inspection by the Engineers from Division of Misamis Oriental | [12 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127736 | Silad ES | SUGBONGCOGON | 1st | 1 | 1 | Repair of Classroom | 625000 | DEPED (Batch 1) |  | COMPLETED | 100% | 2024-03-16 | 2024-03-18 | G2PB Repair 2023-01 |  | n/a | n/a | 2024-02-12 | n/a | 2024-02-16 | RI Construction Services | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | 4 | Repair of Classrooms | 2545875.39 | DPWH (Batch 1) | 2544704.45 | COMPLETED | 100% | 2023-04-12 | 29/11/2023 | P00775427NP | 23KK0196 | [19 empty] | 100% |  |  | 2.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127758 | Gitagum CS | GITAGUM | 2nd | 1 | 3 | Repair of Classrooms | 1875000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Based on report submitted by DPWH and was checked on January 31, 2024. | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2nd | 1 | 4 | Repair of Classrooms | 2500000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Based on report submitted by DPWH and was checked on January 31, 2024. | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 4 | Repair of Classrooms | 2500000 | DPWH (Batch 1) |  | COMPLETED | 100% | [10 empty] | Previous accomplishment was based on the report submitted by DPWH. It was corrected during the joint inspection conducted on January 31, 2024. | [12 empty] | 100% |  |  | 11.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region XI | Davao City | 304391 | Leon Garcia, Sr. NHS | DAVAO CITY | 2nd | 1 | 29 | Repair of Classrooms | 40800000 | DPWH (Batch 2) | 38977181.46 | COMPLETED | 100% | July 24, 2024 |  | 23LB0154 |  |  |  | NOV. 26, 2023 |  | Dec. 28, 2023 | MarkAnthony Construction and Supply JV Andrich Construction | [13 empty] | 100% |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Norte | 128592 | San Miguel ES | SAN ISIDRO | 1st | 1 | 7 | Repair of Classrooms | 6010957.9 | DPWH (Batch 2) | 5713620 | COMPLETED | 100% | May 16, 2024 |  | 23LC0084 | [20 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 128855 | Hagonoy Central Elementary School | HAGONOY | 1st | 1 | 16 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 16883555.21 | COMPLETED | 100% |  |  | 23LD0116 |  | October 20, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 316020 | San Isidro National High School | MAGSAYSAY | 1st | 1 | 11 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9360500 | COMPLETED | 100% |  |  | 23LD0118 |  | October 27, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | K & C BUILDERS | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1st | 1 | 15 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9360500 | COMPLETED | 100% |  |  | 23LD0124 |  | November 06, 2023 | November 14, 2023 | December 20, 2023 | December 29, 2023 | January 05, 2024 | K & C BUILDERS | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 129030 | Bangkal Elementary School | MATANAO | 1st | 1 | 12 | Repair of Classrooms | 13000000 | DPWH (Batch 2) | 12168337.1 | COMPLETED | 100% |  |  | 23LD0119 |  | October 27, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | UPSCALE BUILDERS AND SUPPLY CORP. | [13 empty] | 100% |  |  | 6.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304289 | Bangkal National High School | MATANAO | 1st | 1 | 21 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 43386512.93 | COMPLETED | 100% |  |  | 23LD0125 |  | November 06, 2023 | November 14, 2023 | December 20, 2023 | December 29, 2023 | January 05, 2024 | MARK ANTHONY CONSTRUCTION & SUPPLY | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1st | 1 | 55 | Repair of Classrooms | 45000000 | DPWH (Batch 2) | 11.206,363.31 | COMPLETED | 100% |  |  | 23LD0115 |  | October 06, 2023 | October 17, 2023 | November 07, 2023 | December 27, 2023 | January 05, 2024 | ZJN DEVELOPMENT CONSTRUCTION AND SUPPLY CORPORATION | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Davao del Sur | 304290 | Sinawilan National High School | MATANAO | 1st | 1 | 18 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11232448.14 | COMPLETED | 100% |  |  | 23LD0117 |  | October 20, 2023 | November 07, 2023 | November 21, 2023 | December 27, 2023 | January 05, 2024 | MJTP CONSTRUCTION | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 129750 | Digos City CES | CITY OF DIGOS (Capital) | 1st | 1 | 12 | Repair of Classrooms | 3131629.88 | DPWH (Batch 1) | 2931437.84 | COMPLETED | 100% | 2024-01-17 |  | P00775431MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 129760 | Jolencio R. Alberca ES (San Nicolas PS Annex) | CITY OF DIGOS (Capital) | 1st | 1 | 2 | Repair of Classrooms | 1018010.82 | DPWH (Batch 1) | 952939.83 | COMPLETED | 100% | 2024-01-17 |  | P00775432MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1st | 1 | 8 | Repair of Classrooms | 1661267.66 | DPWH (Batch 1) | 1,586.551.66 | COMPLETED | 100% | 2024-01-17 |  | P00775434MN-CW1 | 23LD0113 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | TWO DEGREES CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 304402 | Ruparan NHS | CITY OF DIGOS (Capital) | 1st | 1 | 17 | Repair of Classrooms | 5759036.56 | DPWH (Batch 1) | 5501087.21 | COMPLETED | 100% | 2024-01-17 |  | P00775435MN-CW1 | 23LD0112 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | PRISM BUILDERS | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Digos City | 341513 | SHS in Digos City | CITY OF DIGOS (Capital) | 1st | 1 | 6 | Repair of Classrooms | 3344592.37 | DPWH (Batch 1) | 3130633.73 | COMPLETED | 100% | 2024-01-17 |  | P00775433MN-CW1 | 23LD0113 | 2023-09-04 | 2023-09-12 | 2023-09-26 | 2023-10-10 | 2023-10-20 | TWO DEGREES CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129410 | Brigido Rodriguez Sr. ES | CITY OF MATI (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 3723083.07 | DPWH (Batch 1) | 3549395.75 | COMPLETED | 100% | 2024-03-24 |  | P00775437NP | 23LG0128 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. | [13 empty] | 100% |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2nd | 1 | 11 | Repair of Classrooms | 6778613.71 | DPWH (Batch 1) | 6462670.2 | COMPLETED | 100% | 2024-06-03 |  | P00775440NP | 23LG0131 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 4936139.54 | DPWH (Batch 1) | 4706074.65 | COMPLETED | 100% | 2024-05-03 |  | P00775438NP | 23LG0129 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129419 | Gelacio G. Ytac ES | CITY OF MATI (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3337821.18 | DPWH (Batch 1) | 3181902.18 | COMPLETED | 100% | 2024-03-05 |  | P00775439NP | 23LG0130 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. | [13 empty] | 100% |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2nd | 1 | 15 | Repair of Classrooms | 9427396.36 | DPWH (Batch 1) | 8966747.84 | COMPLETED | 100% | 2024-07-11 |  | P00775436NP | 23LG0127 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-27 | R. Baudon Construction & Supply Co. | [13 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region XII | North Cotabato | 304480 | Mlang National High School | M'LANG | 3rd | 1 | 10 | Repair of Classrooms | 5000000.25 | DPWH (Batch 2) |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Abra | 134966 | Agtangao ES | BANGUED (Capital) | Lone | 1 | 14 | Repair of Classrooms | 8484848.48 | 1 |  | Ongoing | 50% | [23 empty] | 30% | [7 empty] | Ongoing
REPAIR 2024 | CAR | Abra | 134985 | Abang ES | BUCAY | Lone | 1 | 6 | Repair of Classrooms | 3636363.64 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Apayao | 318812 | Ili National High School | CONNER | Lone | 1 | 4 | Repair of Classrooms | 3478569.81 | 1 | 3373464.301 | Ongoing | 76% | [6 empty] | December 23,2024 |  |  | Enrique T. Chua Development Corporation | Mobilization; Re-aligned from Paddaoan to Ili for Rebidding | [12 empty] | 10% |  |  |  | 1 | 4 | 3478569.81 |  | Ongoing
REPAIR 2024 | CAR | Apayao | 135307 | Kabugao Central School | KABUGAO (Capital) | Lone | 1 | 11 | Repair of Classrooms | 9796188.49 | 1 | 9630076.59 | Ongoing | 68% | [6 empty] | October 7,2024 |  |  | Aquila Construction Co. | [13 empty] | 45% | [7 empty] | Ongoing
REPAIR 2024 | CAR | Baguio City | 136400 | Dona Aurora Elementary School | BAGUIO CITY | Lone | 1 | 4 | Repair of Classrooms | 1010101.01 | 1 |  | COMPLETED | 100% | [6 empty] | october 21, 2024 | [16 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | Lone | 1 | 2 | Repair of Classrooms | 1010101.01 | 1 |  | COMPLETED | 100% | [6 empty] | october 21, 2024 | [16 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Baguio City | 305277 | Roxas National High School | BAGUIO CITY | Lone | 1 | 3 | Repair of Classrooms | 1111111.11 | 1 |  | COMPLETED | 100% | [6 empty] | october 21, 2024 | [16 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Benguet | 135528 | Solomon Solano Elementary School | ITOGON | Lone | 1 | 2 | Repair of Classrooms | 2555912.26 | 1 |  | COMPLETED | 100% | [23 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CAR | Benguet | 135619 | Bekkel ES | LA TRINIDAD (Capital) | Lone | 1 | 6 | Repair of Classrooms | 11209535.3 | 1 |  | Ongoing | 90% | [23 empty] | 60% | [7 empty] | Ongoing
REPAIR 2024 | CAR | Ifugao | 135767 | Calimag ES | ALFONSO LISTA (POTIA) | Lone | 1 | 10 | Repair of Classrooms | 9478787.88 | 1 |  | Ongoing | 45% | [23 empty] | 20% | [7 empty] | Ongoing
REPAIR 2024 | CAR | Kalinga | 136038 | Wagud Elementary School | PINUKPUK | Lone | 1 | 5 | Repair of Classrooms | 2744356.71 | 1 |  | under procurement | 0% | [10 empty] | For Posting (failed bidding) | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | CAR | Kalinga | 136074 | Macutay Elementary School | RIZAL (LIWAN) | Lone | 1 | 5 | Repair of Classrooms | 3306825.17 | 1 |  | under procurement | 0% | [10 empty] | For Posting (failed bidding) | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | CAR | Kalinga | 136121 | Darulog Elementary School | TANUDAN | Lone | 1 | 4 | Repair of Classrooms | 1044997.17 | 1 |  | under procurement | 0% | [10 empty] | For Posting (failed bidding) | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | CAR | Mt. Province | 136206 | Caotit Primary School | BAUKO | Lone | 1 | 6 | Repair of Classrooms | 13030303.03 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Tabuk City | 220522 | DANANAO ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | 2 | Repair of Classrooms | 2598451.4454 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Tabuk City | 136165 | Tuliao Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 4 | Repair of Classrooms | 7535203.26 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CARAGA | Agusan del Norte | 131460 | Dalagangan ES | LAS NIEVES | 1st | 1 | 1 | Repair of Classrooms | 1328281.62 | 1 | 1303320.13 | Completed | 100% | 2025-03-23 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 001 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 001 | 2024-10-17 | 2024-10-25 | 2024-11-08 | 2024-12-12 | 2024-12-16 | Karaga Fast-Track Builders, Inc. | with Time Extension | [12 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CARAGA | Agusan del Norte | 131468 | Las Nieves CES | LAS NIEVES | 1st | 1 | 2 | Repair of Classrooms | 2249285.53 | 1 | 1655302.02 | Completed | 100% | 2025-04-08 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 003 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 003 |  |  | 2024-11-08 | 2024-12-11 | 2024-12-19 | ZEART Construction Supply Co. | with Time Extension | [12 empty] | 50% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CARAGA | Agusan del Norte | 131416 | Cahayagan ES | CARMEN | 2nd | 1 | 2 | Repair of Classrooms | 874101.31 | 1 | 873248.67 | Ongoing | 80% | 2025-06-01 |  | REPAIR 2023 - R XIII - AGUSAN DEL NORTE - 005 | REPAIR 2023 - R XIII - AGUSAN DEL NORTE - 005 |  |  |  | 2025-03-20 | 2025-03-27 | Karaga Fast-Track Builders, Inc. | with approved realignment from Kitcharao NHS to 2 sites (Cahayan ES and Mateo Abao CES) | [12 empty] | 5% |  |  |  | 1 | 7 | 3113238.99 |  | Ongoing
REPAIR 2024 | CARAGA | Agusan del Norte | 131498 | Mateo B. Abao CES | NASIPIT | 2nd | 1 | 2 | Repair of Classrooms | 2239137.68 |  |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | CARAGA | Agusan del Norte | 131536 | TAGBONGABONG ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 2 | Repair of Classrooms | 2297957.57 | 1 | 2259393.29 | Completed | 100% | 2025-03-25 |  | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 002 | REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 002 |  | 2024-10-25 | 2024-11-08 | 2024-12-12 | 2024-12-16 | Karaga Fast-Track Builders, Inc. | with Time Extension | [12 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CARAGA | Agusan del Sur | 304736 | San Luis NHS | SAN LUIS | 1st | 1 | 5 | Repair of Classrooms | 3439916.35 | 1 | 3372981.56 | Ongoing | 95% |  |  | 2024-11-029 (LOT-1) | 2024-11-029 (LOT-1) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | JICLAM BUILDERS & ENTERPRISES | [13 empty] | 45% | [7 empty] | Ongoing
REPAIR 2024 | CARAGA | Agusan del Sur | 131845 | Sta. Ana Elementary School | SAN FRANCISCO | 2nd | 1 | 2 | Repair of Classrooms | 1065150.73 | 1 | 1021188.29 | Ongoing | 95% |  |  | 2024-11-029 (LOT-2) | 2024-11-029 (LOT-2) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | JICLAM BUILDERS & ENTERPRISES | [13 empty] | 45% | [7 empty] | Ongoing
REPAIR 2024 | CARAGA | Agusan del Sur | 131900 | Caigangan Elementary School | VERUELA | 2nd | 1 | 4 | Repair of Classrooms | 2751933.08 | 1 | 2710909.74 | Ongoing | 95% |  |  | 2024-11-029 (LOT-3) | 2024-11-029 (LOT-3) | 2024-11-18 | 2024-11-26 | 2024-12-09 | 2024-12-23 | 2025-01-09 | DDS BUILDERS | [13 empty] | 45% | [7 empty] | Ongoing
REPAIR 2024 | CARAGA | Bayugan City | 131645 | Verdu ES | CITY OF BAYUGAN | 1st | 1 | 4 | Repair of Classrooms | 5323074.95 | 1 |  | Ongoing | 90% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | CARAGA | Butuan City | 132057 | Jose T. Domingo, Sr. CES | BUTUAN CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 2828282.83 | 1 | 1943169.2 | COMPLETED | 100% | 2025-04-12 | February 28, 2025 | 2024-CARAGA-BUTUAN CITY-007 | 2024-CARAGA-BUTUAN CITY-008 | [19 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | CARAGA | Butuan City | 132118 | Libertad CES | BUTUAN CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 2828282.83 | 1 | 2016301.24 | COMPLETED | 100% | 2025-04-15 | March 15, 2025 | 2024-CARAGA-BUTUAN CITY-006 | 2024-CARAGA-BUTUAN CITY-007 | [19 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | CARAGA | Cabadbaran City | 304676 | Calamba National High School | CITY OF CABADBARAN | 2nd | 1 | 10 | Repair of Classrooms | 8402658.12 | 1 | 6020066.94 | Ongoing | 90% | 2025-06-27 |  | PB 2024 -001 | [5 empty] | 2024-12-19 | JR-3 Construction and Supply | [13 empty] | 60% | [7 empty] | Ongoing
REPAIR 2024 | CARAGA | Dinagat Island | 132399 | Magsaysay Elementary School | DINAGAT | Lone | 1 | 5 | Repair of Classrooms | 5369045.39 | 1 | 3652648 | COMPLETED | 100% | 2025-08-15 | 2025-04-25 | INFRA2024-005 | INFRA2024-005 | 2024-10-21 | 2024-10-30 | 2024-11-11 | 2024-11-28 | 2024-12-18 | windfall | realigned from Arellano ES to magsaysay ES | [12 empty] | 100% |  |  | 4.25 | 1 | 5 | 5369045.39 |  | Completed
REPAIR 2024 | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | Lone | 1 | 4 | Repair of Classrooms | 2693298.1 | 1 | 1866329.36 | COMPLETED | 100% | 2025-02-24 | 2025-02-11 | INFRA2024-003 | INFRA2024-003 | 2024-08-08 | 2024-08-20 | 2024-09-04 | 9/223/2024 | 2024-10-28 | windfall | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 2020202.02 | 1 | 1986110.18 | Ongoing | 98% | 2025-01-24 |  |  |  | 2024-10-17 | 2024-10-24 | 2024-11-11 | 2024-11-18 | 2024-11-25 | RBEP Construction | rectification of punch listed items of works | [12 empty] | 98% |  |  |  | 1 | 2 | 2020202.02 |  | Ongoing
REPAIR 2024 | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 7070707.07 | 1 | 6988461.07 | Ongoing | 98% | 2025-02-23 |  |  |  | 2024-10-17 | 2024-10-24 | 2024-11-11 | 2024-11-18 | 2024-11-25 | RBEP Construction | rectification of punch listed items of works | [12 empty] | 98% |  |  |  | 1 | 8 | 7070707.07 |  | Ongoing
REPAIR 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 1161561.33 | 1 | 740000 | Completed | 100% | 2025-04-09 |  |  | FY-2024-INF-027 | 2024-10-31 | 2024-10-31 | 2024-11-13 | 2024-12-17 | 2025-02-03 | LVRO CONSTRUCTION AND SUPPLY | [13 empty] | 98% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CARAGA | Surigao City | 304803 | Day-asan National High School | SURIGAO CITY (Capital) | 2nd | 1 | 16 | Repair of Classrooms | 6643980.54 | 1 | 4347233.71 | Ongoing | 95% | 2025-05-01 |  |  | FY-2024-INF-026 | 2024-10-31 | 2024-10-31 | 2024-11-13 | 2024-12-17 | 2024-12-27 | ARDRAW CONSTRUCTION | [13 empty] | 60% | [7 empty] | Ongoing
REPAIR 2024 | CARAGA | Surigao del Norte | 132326 | L. J. Mordeno ES | ALEGRIA | 2nd | 1 | 6 | Repair of Classrooms | 3771846.61 | 1 | 2315201.09 | COMPLETED | 100% | 2025-01-14 | 2024-10-25 | BEFF 2024-002 | INFRA010-2024 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 2024-07-24 | 2024-09-16 | WINDFALL CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2nd | 1 | 4 | Repair of Classrooms | 2367509.57 | 1 | 1580923.67 | COMPLETED | 100% | 2025-01-14 | 2024-12-09 | BEFF 2024-001 | INFRA009-2024 | 2024-06-27 | 2024-07-04 | 2024-07-16 | 2024-07-24 | 2024-09-16 | WINDFALL CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CARAGA | Surigao del Sur | 132676 | N.A. Uriarte Memorial Elementary School | CANTILAN | 1st | 1 | 5 | Repair of Classrooms | 4636571.93 | 1 | 938,856.40 2,005,958.69 | COMPLETED | 100% | April 02, 2025 April 17, 2025 | April 01, 2025 | REPAIR 2024 - R XIII - SURIGAO DEL SUR - 001 and 002 | 001 - 2024 002 - 2024 | November 25, 2024 | December 02, 2024 | December 13, 2024 | December 19, 2024 | January 03, 2025 | RENOL Egineering Services & Construction Supply | Cluster 2: Approved Extra Work Order | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CARAGA | Surigao del Sur | 132751 | Tagasaka Elementary School | HINATUAN | 2nd | 1 | 4 | Repair of Classrooms | 3896180.64 | 1 | 1,232,167.19 1,404,153.07 | COMPLETED | 100% | May 02, 2025 |  | REPAIR 2024 - R XIII - SURIGAO DEL SUR - 003 and 004 | 003 - 2024 004 - 2024 | November 25, 2024 | December 02, 2024 | December 13, 2024 | December 19, 2024 | January 03, 2025 | Trident Engineering Services | With Contract Time Extension | [12 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CARAGA | Tandag City | 132965 | Hitaob Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | Repair of Classrooms | 3157118.19 | 1 |  | Ongoing | 85% | 2025-03-30 | [7 empty] | 2025-03-25 | CRJ CONSTRUCTION AND SUPPLY | [13 empty] | 50% | [7 empty] | ONGOING
REPAIR 2024 | CARAGA | Tandag City | 304893 | Vicente L. Pimentel Sr. National High School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | Repair of Classrooms | 4188934.24 | 1 |  | Ongoing | 90% | 2025-03-30 | [7 empty] | 2025-03-25 | MELROSHEAN CONSTRUCTION CORPORATION | [13 empty] | 50% | [7 empty] | ONGOING
REPAIR 2024 | NCR | Caloocan City | 136625 | Baesa ES | KALOOKAN CITY | 1st | 1 | 16 | Repair of Classrooms | 7575757.58 | 1 | 7449908.85 | Ongoing | 45% | 2025-06-01 |  | PB No. 2024-Infra-002 | 2024-Cal-PB-009 | 2024-08-20 | 2024-08-27 | 2024-09-11 | 2024-10-01 | 2024-12-03 | CARRY-ON CONSTRUCTION | Limited implementation of works due to unavailability of temporary classrooms | [12 empty] | 30% | [7 empty] | Ongoing
REPAIR 2024 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 | 6 | Repair of Classrooms | 2727272.73 | 1 | 2695000 | COMPLETED | 100% | 2025-04-10 | 2025-03-07 | REPAIR2024-NCR-SAN JUAN-001 | INFRA2024-002 | 2024-06-19 | 2024-06-27 | 2024-07-09 | 2024-11-11 | 2024-12-03 | Hawkstow Construction and Development | Completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Las Piñas City | 136788 | Pamplona Elementary School Unit I | CITY OF LAS PIÑAS | Lone | 1 | 8 | Repair of Classrooms | 6060606.06 | 1 | 5991800.23 | COMPLETED | 100% | 2025-02-16 | 2024-12-06 | 2024-06-I-02 | 2024-06-I-02 | 27/06/2024 | 2024-07-05 | 2024-07-18 | 2024-08-01 | 2024-09-19 | Image Builders and General Services | Completed and Turned over | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Malabon City | 136834 | Imelda ES | CITY OF MALABON | Lone | 1 | 6 | Repair of Classrooms | 959595.96 | 1 | 945760.95 | COMPLETED | 100% | 2025-01-20 | 2024-12-12 |  | 2024-INFRA-09-0004 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | SHERF BUILDERS CORP | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | Lone | 1 | 9 | Repair of Classrooms | 2525252.53 | 1 | 2466707.98 | completed | 100% | 2025-02-19 |  |  | 2024-INFRA-09-0002 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | MARTIAN BUILDERS and SUPPLIES | [13 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | NCR | Malabon City | 136844 | Muzon ES | CITY OF MALABON | Lone | 1 | 6 | Repair of Classrooms | 959595.96 | 1 | 946300.74 | COMPLETED | 100% | 2025-01-20 | 2024-12-12 |  | 2024-INFRA-09-0003 |  | 2024-08-08 | 2024-08-20 | 2024-08-30 | 2024-09-30 | TAPNIO and TAN CONSTRUCTION and DEVT CORP | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Mandaluyong City | 136661 | Plainview Elementary School | CITY OF MANDALUYONG | Lone | 1 | 12 | Repair of Classrooms | 6243580.18 | 1 | 4018358.82 | Ongoing | 95% | 2025-03-20 | 2025-04-20 | REPAIR2024-NCR-MANDALUYONG-001 | OSEC-NCR-24-5376 | 2024-10-23 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2024-11-20 | GUILLAND CONSTRUCTION AND TRADING | For procurement | [12 empty] | 95% | [7 empty] | Ongoing
REPAIR 2024 | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | QUIAPO | 4th | 1 | 7 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 65% | [9 empty] | JKK CONSTRUCTION SERVICES | Contractor received the Notice to Proceed last March 25, 2025 only | [12 empty] | 15% | [7 empty] | Ongoing
REPAIR 2024 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 36 | Repair of Classrooms | 8537771.05 | 1 | 8452393.34 | Completed | 100% | 2025-05-25 |  | BEFF-REPAIR -2024-NCR-MARIKINA CITY-001 | BEFF-REPAIR -2024-NCR-MARIKINA CITY-001 | 2024-11-05 | 2024-11-12 | 2024-11-28 | 2024-12-12 | 2024-12-26 | Marakesh Enterprises | With Approved Extra Work Order of P20,393.34 | [12 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | NCR | Muntinlupa City | 136910 | Bayanan ES - Unit I | CITY OF MUNTINLUPA | Lone | 1 | 38 | Repair of Classrooms | 535173.3 | 1 | 454897.23 | COMPLETED | 100% | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Muntinlupa City | 136913 | Cupang ES - Annex | CITY OF MUNTINLUPA | Lone | 1 | 12 | Repair of Classrooms | 1450569.22 | 1 | 1232983.84 | COMPLETED | 100% | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. | realigned from Cupang ES- Annex to 3 school sites (Cupang ES- Annex, Sucat ES Sitio Pagkakaisa- Annex and Bayanan ES Unit 1) | [12 empty] | 100% |  |  | 4.25 | 1 | 9 | 6060606.06 |  | Completed
REPAIR 2024 | NCR | Muntinlupa City | 136915 | Sucat ES Sitio Pagkakaisa - Annex | CITY OF MUNTINLUPA | Lone | 1 | 6 | Repair of Classrooms | 4014257.48 | 1 | 3412118.83 | COMPLETED | 100% | 2025-03-31 | 2025-03-28 |  | 2024-007 | Sept 20-27, 2024 | Sept. 30, 2024 | 2024-10-14 | 2024-11-13 | 2024-12-02 | Dreamworx Builder and Trading, Inc. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | Navotas City | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | 15 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 85% | [10 empty] | for procurement | [12 empty] | 0% | [7 empty] | Ongoing
REPAIR 2024 | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 20 | Repair of Classrooms | 5850738.62 | 1 |  | COMPLETED | 100% | 2025-03-15 |  | Par -11030754 | PB-2024-032-B | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-05 | 2024-10-16 | RGDG Construction | PROCURED | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | NCR | Pasay City | 136595 | Rivera Village Elementary School | PASAY CITY | Lone | 1 | 11 | Repair of Classrooms | 7575757.58 | 1 | 5779796.68 | Ongoing | 85% | 2025-09-06 |  | SDOPC- 2025-01-001-PB | SDOPC- 2025-01-001-PB | 2025-01-09 | 2025-02-03 | 2025-02-04 | 2025-02-19 | 2025-02-20 | RHR Construction | On-going | [12 empty] | 25% | [7 empty] | Ongoing
REPAIR 2024 | NCR | Quezon City | 136534 | Lagro ES | QUEZON CITY | 5th | 1 | 12 | Repair of Classrooms | 7070707.07 | 1 |  | UNDER PROCUREMENT | 0% | [10 empty] | BID-OUT (APRIL 21, 2025) | [12 empty] | 0% | [7 empty] | Ongoing
REPAIR 2024 | NCR | Taguig City and Pateros | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY | 2nd | 1 | 9 | Repair of Classrooms | 5144117.09 | 1 | 5048001.8 | COMPLETED | 100% |  |  | DTP-CY2024-INFRA-001 |  | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-15 | Ramalla Construction and Trading | Completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | NCR | VALENZUELA CITY | 136798 | MAYSAN ELEMENTARY SCHOOL | CITY OF VALENZUELA | 2nd | 1 | 12 | Repair of Classrooms | 5454545.45 | 1 | 4742254.36 | Completed | 100% |  |  | SDO-VAL-PB-BEFF-REPAIR-2024-11-0004 | SDO-VAL-PB-BEFF-REPAIR-2024-11-0004 |  | 2024-10-29 | 2024-11-11 |  | Decemeber 2, 2024 | Hawkstow Construction and Development | on going, with time extension | [12 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region I | Alaminos City | 500564 | Pangapisan Integrated School | CITY OF ALAMINOS | 1st | 1 | 10 | Repair of Classrooms | 6315970.16 | 1 | 6252810.46 | COMPLETED | 100% | 2025-03-15 | 2025-02-10 | PB-Infra-2024-08-02 |  | 2024-08-28 | 2024-09-05 | 2024-09-17 | 2024-09-23 | 2024-10-17 | MANIMELDS CONSTRUCTION AND IRON WORKS | For Final Punchlisting | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region I | Batac City | 100088 | Benigno Macadaeg Mem. ES | CITY OF BATAC | 2nd | 1 | 6 | Repair of Classrooms | 4141414.14 | 1 | 3341308.11 | COMPLETED | 100% | Feb. 12, 2025 | 2024-12-19 | 2024-001 | 24006 | 2024-07-08 | 2024-07-17 | 2024-07-29 | Aug. 12, 2024 | 2024-10-15 | DPV BUILDERS AND CONSTRUCTION SUPPLY | Part of the savings (P 315,386.58) was used for the Variation Order for the Additional Works of the Project, while the remaining savings (P 443,305.30) was used to fund the project: Repair and Rehabilitation of DepEd Building (Office 12M x 7.5M) of the same school which is now also completed. | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Candon City | 100436 | Candon South Central School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 2480710.23 | 1 | 1761336.18 | COMPLETED | 100% | 2025-01-23 | 2024-12-23 | PB-INFRA-01-2024 |  | 2024-08-14 | 2024-09-03 | 2024-09-06 | 2024-09-23 | 2024-09-25 | M.A. TEJADA CONSTRUCTION | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region I | Candon City | 100445 | Patpata Elementary School | CITY OF CANDON | 2nd | 1 | 3 | Repair of Classrooms | 1813239.72 | 1 | 1601006.84 | COMPLETED | 100% | 2025-01-23 | 2024-12-18 | PB-INFRA-02-2024 |  | 2024-08-14 | 2024-09-03 | 2024-09-06 | 2024-09-23 | 2024-09-25 | AMBROCIO CONSTRUCTION | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 2 | Repair of Classrooms | 1838383.84 | 1 | 1793495.08 | COMPLETED | 100% | 2025-03-10 | 2025-03-10 |  |  | October 14 - November 4, 2024 | 2024-10-22 | 2025-11-04 | 2024-11-08 | 2024-11-11 | LAV CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Dagupan City | 102155 | Caranglaan ES | DAGUPAN CITY | 4th | 1 | 11 | Repair of Classrooms | 2242424.24 | 1 | 2185766.11 | COMPLETED | 100% | 2025-03-10 | 2025-03-10 |  |  | October 14 - November 4, 2024 | 2024-10-22 | 2025-11-04 | 2024-11-08 | 2024-11-11 | LAV CONSTRUCTION AND SUPPLY | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 4146464.65 | 1 | 4105000 | COMPLETED | 100% | 2025-03-06 | 2024-12-10 | PB-03-2024 | PB-03-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-04 | 2024-10-07 | DPV Builders and Construction Supply | Savings was used for Contiguous Contract for the minor repair of 3 classroom BLSB school building amounting to P576,352.31 which is also completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Ilocos Sur | 100471 | Comillas South ES | CERVANTES | 2nd | 1 | 10 | Repair of Classrooms | 6673787.01 | 1 | 6154175.11 | COMPLETED | 100% | 2025-02-20 | 2025-02-19 | PB-06-2024 | n/a | n/a | 2024-07-31 | 2024-08-13 | 2024-08-22 | 2024-09-23 | J.D. JR. GALUTAN BUILDERS | Savings (PhP 452,874.03) was utlized through variation oder (additional works) Revised contract amount: PhP 6,607,049.14 | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region I | La Union | 101126 | Lloren ES | TUBAO | 2nd | 1 | 10 | Repair of Classrooms | 6363636.36 | 1 | 4, 270, 256. 04 | COMPLETED | 100% | 2024-12-22 | 2024-12-10 | 2024REPAIR-RO1-LU-01 | SDOLU - REPAIR 2024 | 2024-07-01 | 2024-07-10 | 2024-07-24 | 2024-08-02 | 2024-10-25 | DPV BUILDERS AND CONSTRUCTION SUPPLY | completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Laoag City | 102182 | Amarosa Elementary School | LAOAG CITY (Capital) | 1st | 1 | 8 | Repair of Classrooms | 6394702.3 | 1 | 4040610.2 | Ongoing | 70% | 2025-05-31 |  | 2024-PB1-001 |  | oct.04,2024 | Oct.11,2024 | Oct.28.2024 | Dec.04,2024 | Dec.19.2024 | Elocin Construction | On Going | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 300245 | Ranao National High School | BANI | 1st | 1 | 3 | Repair of Classrooms | 2302492.17 | 1 | 2302492.17 | COMPLETED | 100% | 2025-01-28 |  | 2024-09-004-INFRA | n/a | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-30 | 2024-10-31 | JFM Altitude Construction Corporation | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 300256 | Tagudin NHS | MABINI | 1st | 1 | 2 | Repair of Classrooms | 1534994.78 | 1 | 1534994.78 | COMPLETED | 100% | 2025-02-03 |  | 2024-09-004-INFRA | n/a | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-28 | 2024-11-06 | JFM Altitude Construction Corporation | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101306 | Telbang ES | BAYAMBANG | 3rd | 1 | 2 | Repair of Classrooms | 1524893.77 | 1 | 1524893.77 | COMPLETED | 100% | 2025-01-28 |  | 2024-09-004-INFRA | n/a | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-28 | 2024-10-31 | Elmuel Jay Trading and Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101623 | Nilombot ES | MAPANDAN | 3rd | 1 | 2 | Repair of Classrooms | 1292570.54 | 1 | 1292570.54 | COMPLETED | 100% | 2025-02-01 |  | 2024-09-004-INFRA | n/a | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-29 | 2024-11-04 | SZCON Builders Incorporated | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | Region I | Pangasinan I, Lingayen | 101628 | Alibago ES | SANTA BARBARA | 3rd | 1 | 1 | Repair of Classrooms | 762446.89 | 1 | 762446.89 | COMPLETED | 100% | 2025-02-01 |  | 2024-09-004-INFRA | n/a | 2024-09-26 | 2024-10-04 | 2024-10-16 | 2024-10-29 | 2024-11-04 | Kalbs Builders and Construction Supply - OPC | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | completed
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 101914 | San Fabian West CES | SAN FABIAN | 4th | 1 | 10 | Repair of Classrooms | 4444444.44 | 1 |  | Completed | 100% | [9 empty] | Elmuel Jay Trading and Construction | [13 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 300295 | Cabilaoan Agro-Industrial HS | LAOAC | 5th | 1 | 4 | Repair of Classrooms | 4242424.24 | 1 |  | Ongoing | 90% | [9 empty] | W.M. Salayog Construction | [13 empty] | 70% | [7 empty] | Ongoing
REPAIR 2024 | Region I | Pangasinan II, Binalonan | 101883 | Rosales South CS | ROSALES | 6th | 1 | 5 | Repair of Classrooms | 5303030.3 | 1 |  | Ongoing | 95% | [9 empty] | Rivbros Construction Factors and Development | [13 empty] | 85% | [7 empty] | Ongoing
REPAIR 2024 | Region I | San Carlos City | 102246 | Mabalbalino Elementary School | SAN CARLOS CITY | 3rd | 1 | 10 | Repair of Classrooms | 6262626.26 | 1 | 5531200.08 | COMPLETED | 100% | APRIL 10,2025 | 2025-04-10 | - | 2024 - 014 | OCTOBER 17 - 24, 2024 | OCTOBER 29,2024 | 2024-11-11 | 2024-11-26 | 2024-12-11 | RGP SUCCESS VENTURES INC | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region I | San Fernando City | 101026 | Ilocanos Elementary School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 5 | Repair of Classrooms | 2245981.73 | 1 | 1888416.18 | COMPLETED | 100% | 2024-11-29 | 2024-11-29 | CSFLU-INFRA-02-2024 | CSFLU-INFRA-002-2024 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-04 | 2024-09-23 | DPV Builders & Construction Supply | Awarded | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | San Fernando City | 500530 | Nagyubuyuban Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 2 | Repair of Classrooms | 1191453.91 | 1 | 1084431.83 | COMPLETED | 100% | 2024-11-29 | 2024-11-22 | CSFLU-INFRA-02-2024 | CSFLU-INFRA-002-2024 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-04 | 2024-09-23 | DPV Builders & Construction Supply | Awarded | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region I | Urdaneta City | 102303 | Nancalobasaan Elementary School | CITY OF URDANETA | 5th | 1 | 6 | Repair of Classrooms | 4232323.23 | 1 | 2595166.7 | Ongoing | 70% | March 28,2025 | n/a | 11006619 | ITB-011-2024 | 2024-07-01 | 2024-07-09 | 2024-07-22 | 2024-11-19 | 2024-11-28 | MACCO Construction | With time extension | [12 empty] | 50% | [7 empty] | Ongoing
REPAIR 2024 | Region I | Vigan City | 100792 | Mindoro Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 6 | Repair of Classrooms | 2020202.02 | 1 | 1587378.57 | COMPLETED | 100% | 2025-01-14 | 2025-01-14 | INFRA-2024-011 | 11202360 | 2024-08-30 | 2024-09-09 | 2024-09-23 | 2024-10-01 | 2024-10-14 | HEAF Engineering and Consultancy | Completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | Lone | 1 | 2 | Repair of Classrooms | 1326118.32 | 1 | 1304928.76 | Ongoing | 90% | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | [12 empty] | 75% | [7 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 300415 | Ivana NHS | IVANA | Lone | 1 | 4 | Repair of Classrooms | 2686868.69 | 1 | 2652129.98 | Ongoing | 0% | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | [12 empty] | 0% | [7 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 102330 | Sumnanga Elementary School | SABTANG | Lone | 1 | 2 | Repair of Classrooms | 1356421.35 | 1 | 1340480.07 | Ongoing | 0% | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | [12 empty] | 0% | [7 empty] | Ongoing
REPAIR 2024 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | Lone | 1 | 2 | Repair of Classrooms | 1343434.34 | 1 | 1328045.66 | Ongoing | 20% | June 23, 2025 | N/a | 2024-08-04 | 2024-08-04 | 09-16-24 | August 22, 2024 | September 16, 2024 |  | October 16, 2024 | Knb Construction | Resumption Date : January 15, 2025 | [12 empty] | 0% | [7 empty] | Ongoing
REPAIR 2024 | Region II | Cagayan | 102370 | Malalatan ES | ALCALA | 1st | 1 | 8 | Repair of Classrooms | 3507780.79 | 1 |  | COMPLETED | 100% |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 1 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 300456 | Don Severino Pagalilauan National High School | PEÑABLANCA | 3rd | 1 | 4 | Repair of Classrooms | 2114928.35 | 1 |  | COMPLETED | 100% |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 2 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 102806 | Penablanca East CS | PEÑABLANCA | 3rd | 1 | 6 | Repair of Classrooms | 2605614.16 | 1 |  | COMPLETED | 100% |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 3 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cagayan | 102819 | Sisim ES | PEÑABLANCA | 3rd | 1 | 3 | Repair of Classrooms | 1569656.49 | 1 |  | COMPLETED | 100% |  |  | Repair rehabilitation of Classroom under cy 2024 beff batch 1 | Infra2024-076 LOT 4 | July 16, 2024 | AUGUST 6, 2024 | AUGUST 6, 2024 |  |  |  | UNDER PROCUREMENT: ONGOING OF ARITHMETIC AND DOCUMENTS EVALUATION | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 103214 | Duminit ES | CITY OF CAUAYAN | 3rd | 1 | 3 | Repair of Classrooms | 1818181.82 | 1 | 1102412.45 | COMPLETED | 100% | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Duminit Elementary School (Lot 1) | CW-001 S. 2024 (LOT 1) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 103217 | Guayabal ES | CITY OF CAUAYAN | 3rd | 1 | 8 | Repair of Classrooms | 4363636.36 | 1 | 2811753.92 | COMPLETED | 100% | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Guayabal Elementary School (Lot 2) | CW-001 S. 2024 (LOT 2) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | Cauayan City | 300613 | Villa Concepcion National High School | CITY OF CAUAYAN | 3rd | 1 | 9 | Repair of Classrooms | 3616161.62 | 1 | 2253082.76 | COMPLETED | 100% | 2025-01-11 |  | Repair/Rehabilitation of Classroom of Villa Concepcion National High School (Lot 3) | CW-001 S. 2024 (LOT 3) | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-06 | 2024-10-14 | GCPK Construction and Supply | For Final Inspection | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region II | City of Ilagan | 103418 | Cabannungan 1st Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | 3 | Repair of Classrooms | 2595959.6 | 1 | 2595959.6 | COMPLETED | 100% | 2024-12-27 | 2024-09-22 |  | INF-2024-R02 | 2024-08-03 | 2024-08-12 | 2024-08-28 | 2024-09-09 | 2024-09-26 | Oroset Construction | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region II | City of Ilagan | 103419 | Cabannungan 2nd ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 3 | Repair of Classrooms | 2393939.39 | 1 | 2357905.57 | completed | 100% | 2024-02-14 |  |  |  | September 20, 2024 | September 30, 2024 | October 14, 2024 | October 30, 2024 | Novemner 12, 2024 | RSKC Construction | [13 empty] | 90% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region II | City of Ilagan | 103427 | Mangcuram ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 4 | Repair of Classrooms | 3191919.19 | 1 | 3109253.81 | completed | 100% | 2024-02-14 |  |  |  | September 20, 2024 | September 30, 2024 | October 14, 2024 | October 30, 2024 | Novemner 12, 2024 | RSKC Construction | [13 empty] | 60% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region II | City of Ilagan | 103369 | Minabang Elementary School | ILAGAN CITY (CAPITAL) | 1st | 1 | 5 | Repair of Classrooms | 1616161.62 | 1 | 1589149.96 | COMPLETED | 100% | 2024-12-27 |  |  | INF-2024-R02 | 2024-08-03 | 2024-08-12 | 2024-08-28 | 2024-09-09 | October 4, 2024 | Atlantic Construction | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | completed
REPAIR 2024 | Region II | Isabela | 501317 | Bayabo East Integrated School | TUMAUINI | 1st | 1 | 7 | Repair of Classrooms | 2869807.43 | 1 | 2803801.8625 | COMPLETED | 100% |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 | [16 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region II | Isabela | 500732 | New Magsaysay Integrated School | BENITO SOLIVEN | 2nd | 1 | 6 | Repair of Classrooms | 3632179.02 | 1 |  | COMPLETED | 100% |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 | [16 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Isabela | 103168 | Canan Elementary School | CABATUAN | 3rd | 1 | 3 | Repair of Classrooms | 1799433.72 | 1 |  | COMPLETED | 100% |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 | [16 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Isabela | 306160 | Nueva Era National High School | SAN MANUEL | 5th | 1 | 2 | Repair of Classrooms | 1565873.82 | 1 |  | COMPLETED | 100% |  |  |  |  | August 02,2024 | August 13, 2024 | August 27,2024 | [16 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Nueva Vizcaya | 103908 | Banganan ES | ARITAO | Lone | 1 | 4 | Repair of Classrooms | 3434343.43 | 1 | 2263457.35 | Ongoing | 75% |  |  | PB 12-001 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 16, 2024 | IA CASTAÑEDA CONSTRUCTION & SUPPLY | [13 empty] | 45.3% | [7 empty] | ONGOING
REPAIR 2024 | Region II | Nueva Vizcaya | 103913 | Canabuan Elementary School | ARITAO | Lone | 1 | 3 | Repair of Classrooms | 2929292.93 | 1 | 2033876.43 | Ongoing | 78% |  |  | PB 12-002 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 16, 2024 | IA CASTAÑEDA CONSTRUCTION & SUPPLY | [13 empty] | 42.23% | [7 empty] | ONGOING
REPAIR 2024 | Region II | Nueva Vizcaya | 103974 | Mabuslo ES | BAMBANG | Lone | 1 | 4 | Repair of Classrooms | 3434343.43 | 1 | 2187406.39 | Ongoing | 80% |  |  | PB 12-003 s. 2024 |  | September 9, 2024 | October 2, 2024 | October 14, 2024 | December 4, 2024 | December 27, 2024 | KNB CONSTRUCTION | [13 empty] | 34.4% | [7 empty] | ONGOING
REPAIR 2024 | Region II | Quirino | 104233 | Osmena ES | AGLIPAY | Lone | 1 | 6 | Repair of Classrooms | 2740027.61 | 1 | 1957660.11 | COMPLETED | 100% | 2025-01-08 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 001 | 26-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-10 | WINLEI CONSTRUCTION & SUPPLY | Ongoing / with Contract Time Extension due to continuous rains in the area | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104246 | San Ramon ES | AGLIPAY | Lone | 1 | 6 | Repair of Classrooms | 1829716.35 | 1 | 1397714.37 | COMPLETED | 100% | 2025-01-29 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 002 | 27-07-19-2024 | 2024-09-17 | 2024-09-23 | 2024-10-07 | 2024-10-10 | 2024-10-31 | WINLEI CONSTRUCTION & SUPPLY | Ongoing / with Contract Time Extension due to continuous rains in the area | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104276 | Andres Bonifacio ES | DIFFUN | Lone | 1 | 9 | Repair of Classrooms | 3914837.05 | 1 | 2935532.63 | COMPLETED | 100% | 2025-01-02 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 003 | 24-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-04 | ACES 3 CONSTRUCTION | Ongoing / with Contract Time Extension due to continuous rains in the area | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Quirino | 104305 | Liwanag Elementary School | DIFFUN | Lone | 1 | 3 | Repair of Classrooms | 1388952.1 | 1 | 1150230.96 | COMPLETED | 100% | 2024-12-08 |  | CY2024 REPAIR/REHAB - II - QUIRINO - 004 | 25-07-19-2024 | 2024-07-20 | 2024-07-26 | 2024-08-07 | 2024-09-18 | 2024-10-09 | HJM Construction Services | Ongoing / with Contract Time Extension due to continuous rains in the area | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | ONGOING
REPAIR 2024 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4th | 1 | 3 | Repair of Classrooms | 1911414.63 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Santiago City | 103837 | Calaocan ES | CITY OF SANTIAGO | 4th | 1 | 6 | Repair of Classrooms | 3499091.07 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Santiago City | 103828 | Patul Elementary School | CITY OF SANTIAGO | 4th | 1 | 4 | Repair of Classrooms | 2582747.67 | 1 |  | completed | 100% | [23 empty] | 70% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Santiago City | 501147 | San Jose Integrated School | CITY OF SANTIAGO | 4th | 1 | 3 | Repair of Classrooms | 1800130.7 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region II | Tuguegarao City | 300668 | Cagayan National High School - Junior HS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 12 | Repair of Classrooms | 4242424.24 | 1 |  | COMPLETED | 100% | [23 empty] | 56% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Tuguegarao City | 104400 | Tuguegarao North CS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 4 | Repair of Classrooms | 1414141.41 | 1 |  | Completed | 100% | [23 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3rd | 1 | 6 | Repair of Classrooms | 2121212.12 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1st | 1 | 6 | Repair of Classrooms | 4209848.77 | 1 | 4156888.88 | COMPLETED | 100% | 2025-02-04 | 2024-12-12 | n/a | n/a | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-10 | 2024-10-07 | Traccor Builders | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Aurora | 104474 | Laboy ES | DIPACULAO | Lone | 1 | 2 | Repair of Classrooms | 1161616.16 | 1 | 733705.21 | COMPLETED | 100% | 2024-11-14 | 2024-11-14 |  |  | 2024-07-10 | July 20, 2024 | August 1, 2024 | Sept 16, 2024 | 2024-09-24 | MACCO CONSTRUCTION | COMPLETED | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Aurora | 104529 | Zarah ES | SAN LUIS | Lone | 1 | 5 | Repair of Classrooms | 3282828.28 | 1 | 2125914.56 | COMPLETED | 100% | 2024-12-05 | 2024-12-05 |  |  | 2025-07-10 | July 20, 2025 | August 1, 2024 | Sept 16, 2024 | 2024-10-04 | DB BARAQUIEL CONSTRUCTION | COMPLETED | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Balanga City | 104563 | M. P. Cuaderno Sr. Memorial Elementary School | CITY OF BALANGA (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 2567473.92 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Balanga City | 502343 | Tanato Integrated School | CITY OF BALANGA (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1282109.62 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bataan | 104615 | Pandatung ES | HERMOSA | 1st | 1 | 3 | Repair of Classrooms | 1713732.22 | 1 | 1322789.87 | COMPLETED | 100% | 2024-11-26 | 2024-11-26 | Repair 2024-Region III-Bataan-014 | 2024 - 07 - 01 | July 9, 2024 to July 28, 2024 | 2024-07-16 | 2024-07-29 | 2024-08-01 | 2024-09-23 | Five A Construction | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bataan | 104601 | Sto. Nino ES | DINALUPIHAN | 3rd | 1 | 3 | Repair of Classrooms | 2084641.52 | 1 | 1570758.1 | COMPLETED | 100% | 2024-11-26 | 2024-11-26 | Repair 2024-Region III-Bataan-010 | 2024 - 07 - 02 | July 9, 2024 to July 28, 2024 | 2024-07-16 | 2024-07-29 | 2024-08-01 | 2024-09-23 | Rodmac Construction & Trading | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 5th | 1 | 10 | Repair of Classrooms | 4444444.44 | 1 | 4400000 | COMPLETED | 100% | 2025-02-18 | 2024-12-20 | PB-24-010 | PB-24-10-015 | 2024-06-26 | 2024-07-06 | 2024-07-22 | 2024-08-06 | 2024-10-14 | T.G. Ocampo Construction and Surveying Services | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Cabanatuan City | 107117 | Sumacab Este ES | CABANATUAN CITY | 3rd | 1 | 5 | Repair of Classrooms | 4443665.28 | 1 | 4339973.18 | COMPLETED | 100% | 2025-01-23 | 2024-12-16 | n/a | 08-2024 | 2024-08-01 | 2024-08-14 | 2024-08-27 | 2024-09-16 | 2024-09-17 | Marvelous Quejada Construction Inc. | completed | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 107161 | San Jose Del Monte Central School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1484848.48 | 1 | PhP1,460,218.65 | COMPLETED | 100% | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | .I. VIACRUSIS CONSTRUCTION | Complete | [12 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 162504 | San Manuel Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1479797.98 | 1 | PhP1,459,880.51 | COMPLETED | 100% | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | JM ALTITUDE CONSTRUCTION COR | Complete | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 107162 | San Martin (BBC) Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1479797.98 | 1 | PhP1,459,869.73 | COMPLETED | 100% | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | RKEA BUILDERS & SUPPLY | Complete | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Gapan City | 105335 | Malimba ES | CITY OF GAPAN | 4th | 1 | 10 | Repair of Classrooms | 4436402.36 | 1 | 4,386,357.66 | COMPLETED | 100% | 2025-01-25 | 2024-12-27 | IB2024-002 | IB2024-002 | 2024-06-26 | 2024-07-09 | 2024-07-23 | 2024-07-26 | 2024-09-27 | Joynieltin Construction and Trading | completed | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Mabalacat City | 306916 | Mabalacat Community High School | MABALACAT CITY | 1st | 1 | 16 | Repair of Classrooms | 4497983.05 | 1 | 3335299.41 | COMPLETED | 100% | 2025-02-16 | 2025-01-30 |  |  |  |  | 2024-10-21 | 2024-11-07 | 2024-11-18 | E.M MALLARI CONSTRUCTION | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Malolos City | 323603 | Malolos City High School - Bungahan | CITY OF MALOLOS (Capital) | 1st | 1 | 6 | Repair of Classrooms | 2319988.19 | 1 | 2285519.82 | COMPLETED | 100% | 2025-01-06 | 2024-11-21 | Infra-2024-02 Lot 2 | Infra-2024-02 Lot 2 | 7/02-7/09/2024 | 2024-07-10 | 2024-07-23 | 2024-07-24 | Oct. 1, 2024 | Samenara Construction & Trading | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Malolos City | 104879 | Stma. Trinidad ES | CITY OF MALOLOS (Capital) | 1st | 1 | 3 | Repair of Classrooms | 2139319.71 | 1 | 2100000 | COMPLETED | 100% | 2025-01-06 | November 26,2024 | Infra-2024-02 Lot 1 | Infra-2024-02 Lot 1 | 7/02-7/09/2024 | 2024-07-10 | 2024-07-23 | 2024-07-24 | Oct. 1, 2024 | V. Trillana Builders & Trading | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Meycauayan City | 104915 | Bagbaguin ES | CITY OF MEYCAUAYAN | 4th | 1 | 2 | Repair of Classrooms | 1915552.25 | 1 | 1891245.73 | Ongoing | 80% | 2025-02-26 | ongoing | 2024-001-INFRA | 2024-001-INFRA | 2024-10-29 | 2024-11-06 | 2024-11-19 | 2024-11-20 | 2024-11-26 | Che-riss Construction and Trading | on-going | [12 empty] | 80% | [7 empty] | Ongoing
REPAIR 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th | 1 | 1 | Repair of Classrooms | 773760.66 | 1 | 760671.89 | COMPLETED | 100% | 2025-01-15 | 2024-12-26 | 2024-001-INFRA | 2024-001-INFRA | 2024-10-29 | 2024-11-06 | 2024-11-19 | 2024-11-20 | 2024-11-26 |  | completed | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105823 | La Torre ES | TALAVERA | 1st | 1 | 2 | Repair of Classrooms | 1005971.55 | 1 | 993344.81 | COMPLETED | 100% | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-132-2024 | INFRA-NE-SVP-21-2024 | 2024-08-03 | N/A | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 306813 | Vega National High School | BONGABON | 3rd | 1 | 2 | Repair of Classrooms | 1005971.55 | 1 | 993344.81 | COMPLETED | 100% | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-133-2024 | INFRA-NE-SVP-22-2024 | 2024-08-03 | N/A | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105228 | San Vicente Elementary School | CABIAO | 4th | 1 | 2 | Repair of Classrooms | 974161.53 | 1 | 961852.88 | COMPLETED | 100% | 2024-11-04 | 2024-10-29 | DEPED-NE-INFRA-134-2024 | INFRA-NE-SVP-20-2024 | 2024-08-03 | N/A | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105448 | Pinanggaan ES | JAEN | 4th | 1 | 2 | Repair of Classrooms | 974161.53 | 1 | 961852.88 | COMPLETED | 100% | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-135-2024 | INFRA-NE-SVP-19-2024 | 2024-08-03 | N/A | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Olongapo City | 107122 | New Cabalan ES | OLONGAPO CITY | 1st | 1 | 5 | Repair of Classrooms | 4444444.44 | 1 | 4380306.97 | COMPLETED | 100% | 2025-04-08 | 2025-02-21 | 2024-11-01 | 2024-11-01 | 2024-10-03 | 2024-10-11 | 2024-10-23 | 2024-12-03 | 2024-12-09 | Mitzie Construction | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Pampanga | 105897 | Anderson ES | ARAYAT | 3rd | 1 | 2 | Repair of Classrooms | 2704938.92 | 1 | 1708518.45 | COMPLETED | 100% | 2024-12-09 | 2024-11-28 | BEFF - 002 | BEFF - 002 | 2024-07-09 | 2024-07-19 | 2024-07-31 | 2024-09-18 | 2024-09-25 | IB MUSNGI CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Pampanga | 105957 | Mandasig ES | CANDABA | 4th | 1 | 2 | Repair of Classrooms | 2073852.75 | 1 | 1526044.51 | COMPLETED | 100% | 2024-12-09 | 2024-11-21 | BEFF - 001 | BEFF - 001 | 2024-07-09 | 2024-07-19 | 2024-07-31 | 2024-09-18 | 2024-09-25 | IB MUSNGI CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | San Fernando City | 500145 | Maimpis Integrated School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 2432861.9 | 1 | 2398888.88 | COMPLETED | 100% | 2025-01-05 | 2024-12-07 | N/A | Infrastructure 2024-002 | 2024-07-15 | 2024-07-22 | 2024-08-05 | 2024-08-30 | 2024-09-30 | Traccor Builders | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | San Fernando City | 107200 | Sto. Nino Elementary School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 2432861.9 | 1 | 2039923.23 | COMPLETED | 100% | 2025-01-05 | 2024-12-07 | N/A | Infrastructure 2024-003 | 2024-07-15 | 2024-07-22 | 2024-08-05 | 2024-08-30 | 2024-10-11 | I.B. Musngi Construction and Trading | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | San Jose City | 105715 | A. Pascual Elementary School | SAN JOSE CITY | 2nd | 1 | 3 | Repair of Classrooms | 2282346.24 | 1 | 2229524.29 | COMPLETED | 100% | 2025-01-08 | 2024-12-08 | REPAIR 2024 - RIII - SAN JOSE CITY - 001 | n/a | 2024-05-24 | 2024-06-07 | 2024-06-24 | 2024-06-27 | 2024-09-20 | DB Baraquiel Construction | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | San Jose City | 105733 | Tondod Elementary School | SAN JOSE CITY | 2nd | 1 | 3 | Repair of Classrooms | 2131889.34 | 1 | 2105413.85 | COMPLETED | 100% | 2025-01-08 | 2024-12-08 | REPAIR 2024 - RIII - SAN JOSE CITY - 002 | n/a | 2024-05-24 | 2024-06-07 | 2024-06-24 | 2024-06-27 | 2024-09-20 | Mitzie Construction | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Science City of Muñoz | 105548 | Maligaya ES | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 2 | Repair of Classrooms | 1434779.8 | 1 | 1417679.74 | COMPLETED | 100% | 2024-12-09 | 2024-12-05 | DepEd-SCM-2024-032 | DepEd-SCM-2024-032 | 2024-06-07 | 2024-06-14 | 2024-07-01 | 2024-07-03 | 2024-10-14 | RB VALERA BUILDERS AND GENERAL MERCHANDISE | completed | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Science City of Muñoz | 105553 | Munoz North CS | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 7 | Repair of Classrooms | 3001488.89 | 1 | 2961273.99 | COMPLETED | 100% | 2025-02-07 | 2024-12-23 | DepEd-SCM-2024-032 | DepEd-SCM-2024-032 | 2024-06-07 | 2024-06-14 | 2024-07-01 | 2024-07-03 | 2024-10-11 | GR ERCILLA CONSTRUCTION | completed | [12 empty] | 100% |  |  | 12.24 | 1 | 3 | 2961273.99 |  | COMPLETED
REPAIR 2024 | Region III | Tarlac | 106316 | Delos Remedios ES | BAMBAN | 3rd | 1 | 2 | Repair of Classrooms | 1573950.29 | 1 | 993615.55 | COMPLETED | 100% | 2025-03-23 | 2025-03-19 |  |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | 2024-11-08 | HOR-VERT ENTERPRISES | DONE | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Tarlac | 106378 | Talaga ES | CAPAS | 3rd | 1 | 3 | Repair of Classrooms | 2678202.61 | 1 | 1749036.31 | COMPLETED | 100% | 2025-05-07 | 2025-04-22 |  |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | 2024-11-08 | HOR-VERT ENTERPRISES | DONE | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Tarlac City | 300970 | Maliwalo NHS | CITY OF TARLAC (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 2222222.22 | 1 | 1399796.19 | COMPLETED | 100% | 2024-12-22 | 2024-12-03 | TCSD-IP-04-2024-LOT 2 | TCSD-IP-04-2024-L2 | 2024-06-29 | 2024-07-11 | 2024-07-22 | 2024-08-01 | 2024-09-23 | HIGH VISION BUILDERS CORPORATION | SAVINGS WERE DOWNLOADED | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Tarlac City | 106763 | San Isidro ES | CITY OF TARLAC (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 2222222.22 | 1 | 1521263.96 | COMPLETED | 100% | 2024-12-22 | 2024-12-16 | TCSD-IP-04-2024-LOT 1 | TCSD-IP-04-2024-L1 | 2024-06-29 | 2024-07-11 | 2024-07-22 | 2024-08-01 | 2024-09-23 | HIGH VISION BUILDERS CORPORATION | SAVINGS WERE DOWNLOADED | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Zambales | 106907 | Dampay Elementary School | PALAUIG | 2nd | 1 | 6 | Repair of Classrooms | 4443087.47 | 1 | 4393434.45 | COMPLETED | 100% | 2025-01-08 | 2025-01-07 | Infra-2024-006 | Infra-2024-009 | 2024-07-10 | 2024-07-17 | 2024-07-29 | 2024-07-31 | Oct. 1, 2024 | KAEE Construction Services | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | Antipolo City | 500391 | Apia IS | CITY OF ANTIPOLO | 2nd | 1 | 10 | Repair of Classrooms | 5930924.83 | 1 | 5860000 | COMPLETED | 100% | 2025-01-14 | 2025-01-07 | N/A | BEFF-ANT-2024-04 | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-09-23 | 2024-10-15 | HAWKSTOW CONST AND DEVELOPMENT | N/A | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | Bacoor City | 107889 | San Nicolas Elementary School | BACOOR | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 |  | under procurement | 0% | [10 empty] | N/A | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region IV-A | Batangas | 307706 | Lian National High School | LIAN | 1st | 1 | 4 | Repair of Classrooms | 3469896.97 | 1 |  | under procurement | 0% | [10 empty] | N/A | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region IV-A | Batangas | 107607 | Calabasahan Elementary School | SAN JUAN | 4th | 1 | 6 | Repair of Classrooms | 3939393.94 | 1 |  | under procurement | 0% | [10 empty] | N/A | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region IV-A | Batangas City | 109572 | Parang Cueva ES | BATANGAS CITY (Capital) | 5th | 1 | 4 | Repair of Classrooms | 3282828.28 | 1 | 3150000 | Completed | 100% | 2025-05-24 |  | 001-01-2025 | 001-01-2025 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-20 | 2025-01-24 | Botey Construction | For Installation of Roofings | [12 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-A | Batangas City | 109621 | Pinamukan ES | BATANGAS CITY (Capital) | 5th | 1 | 1 | Repair of Classrooms | 384808.08 | 1 | 350000 | COMPLETED | 100% | 2025-05-24 | 2025-02-17 | 001-01-2025 | 001-01-2025 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-20 | 2025-01-24 | Botey Constructioin | Completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Cabuyao City | 108236 | Banlic Elementary School | CABUYAO | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 | 2284632.74 | Completed | 100% | 2025-05-04 |  | 2024-07-0051 | 2024-07-0051 | 2024-09-30 | 2024-10-02 | 2024-10-14 | 2024-10-26 | 2024-12-09 | GS Motar Builders Construction & Trading | [13 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-A | Cavite | 108083 | San Antonio Elementary School | NOVELETA | 1st | 1 | 2 | Repair of Classrooms | 2234126.31 | 1 | 2193417.05 | COMPLETED | 100% |  |  |  | RIVACaviteBACInfra 003-2024 |  | 2024-08-08 | 2024-08-27 | Nov. 25, 2024 | 2025-12-18 | Langit Construction | Slow Pace of Work | [12 empty] | 35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-A | Cavite | 301193 | Gen. Vito Belarmino Integrated National High School | SILANG | 5th | 1 | 4 | Repair of Classrooms | 3709069.7 | 1 | 3650284.6 | Ongoing | 40% |  |  |  | RIVACaviteBACInfra 003-2024 |  | 2024-08-08 | 2024-08-27 | Nov. 25, 2024 | 2025-12-18 | Langit Construction | Slow Pace of Work | [12 empty] | 8% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-A | Cavite City | 109632 | Ladislao Diwa ES | CAVITE CITY | 1st | 1 | 4 | Repair of Classrooms | 2534098.23 | 1 | 1881331.85 | COMPLETED | 100% | 2025-01-24 | 2024-12-13 | 2024-07-00007 | 2024-07-00007 | 2024-06-28 | 2024-07-09 | July 22, 2024 - July 29, 2024 (actual) | 2024-08-02 | 2024-09-26 | L2A Builders and Trading | * | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | City of Biñan | 108214 | Our Lady of Lourdes ES (Brgy. Malamig PS) | CITY OF BIÑAN | Lone | 1 | 8 | Repair of Classrooms | 4340603.52 | 1 | 3695579.1 | COMPLETED | 100% | 2025-02-07 | 2025-01-07 | R4A-BNN-2024-06 | R4A-BNN-2024-06 | July 24 - August 13, 2024 | 2024-08-01 | 2024-08-13 | 2024-08-27 | 2024-10-10 | GS Motar Builders Construction & Trading | Awaiting SARO Release | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Dasmarinas City | 107915 | Bautista Elementary School | CITY OF DASMARIÑAS | 4th | 1 | 8 | Repair of Classrooms | 4042483.14 | 1 | 3933887.8 | COMPLETED | 100% | 2025-04-12 | 2025-03-19 | CY2024 BEFF Batch 1 RRC | CY2024 BEFF Batch 1 RRC | August 26-September 13, 2024 | 2024-09-13 | 2024-09-25 | 2024-10-11 | 2024-11-13 | Open Builders Incorporated | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3rd | 1 | 8 | Repair of Classrooms | 4083303.35 | 1 | 4011225.37 | Completed | 100% | May 8, 2025 |  | 2024-10-003 | 2024-10-003 | Nov. 12, 2024 | Nov. 19, 2024 | Dec. 2, 2024 | Dec. 20, 2024 | Dec 27, 2024 | JKK Construction Services | ongoing installation of electrical wirings, fixtures, and painting works | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region IV-A | Laguna | 108500 | San Francisco ES | VICTORIA | 3rd | 1 | 6 | Repair of Classrooms | 3477422.29 | 1 | 2841560.04 | Ongoing | 75% | 2025-09-11 |  | R4A-2024-17 | R4A-2024-17 | 27/09/2024 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2024 | 2025-07-02 | 2025-04-03 | Open Builders Incorporated | [13 empty] | 29% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6th | 1 | 4 | Repair of Classrooms | 2185807.35 | 1 | 2153928.39 | COMPLETED | 100% | 2025-02-21 |  | REPAIR 2024-RIV A-LIPA CITY 001 | REPAIR 2024-RIV A-LIPA CITY 001 | 2024-07-05 | 2024-07-16 | July 29,2024 | 2024-08-08 | 2024-10-17 | TRACCOR BUILDERS | [13 empty] | 100% |  |  | 10.24 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Lipa City | 301499 | San Celestino Integrated National High School | LIPA CITY | 6th | 1 | 2 | Repair of Classrooms | 1728183.83 | 1 | 1700800.48 | COMPLETED | 100% | 2025-01-22 | 2024-12-05 | REPAIR 2024-RIV A-LIPA CITY 002 | REPAIR 2024-RIV A-LIPA CITY 002 | 2024-07-05 | 2024-07-16 | July 29,2024 | 2024-08-08 | 2024-10-17 | TRACCOR BUILDERS | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | Lucena City | 167501 | Hermana Fausta Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3362920.1 | 1 | 3327225.43 | Completed | 100% | [23 empty] | 0% |  |  | 5.25 |  |  |  |  | under procurement
REPAIR 2024 | Region IV-A | Quezon | 109001 | Cabulihan ES | PITOGO | 3rd | 1 | 1 | Repair of Classrooms | 1352208.72 | 1 | 1330000 | COMPLETED | 100% |  | 2024-11-15 | [21 empty] | 100% |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | Quezon | 108845 | Ilayang Ilog B ES | LOPEZ | 4TH | 1 | 3 | Repair of Classrooms | 3824717.87 | 1 | 3778556.12 | COMPLETED | 100% | [23 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-A | Rizal | 301452 | Morong National High School | MORONG | 2nd | 1 | 8 | Repair of Classrooms | 4504148.49 | 1 | 3735628.16 | COMPLETED | 100% | 2025-04-26 |  | INFRA-2024-002 | INFRA-2024-002 | 2024-09-24 | 2024-10-01 | 2024-10-15 | 2024-10-22 | 2024-11-28 | J.G. Gutierrez Construction and Trading | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3181818.18 | 1 | 3109999.88 | COMPLETED | 100% | 2025-04-19 | 2025-04-05 | BEFF-RC-001-2024 | BEFF-RC-001-2024 | 2024-10-22 | 2024-11-06 | 2024-11-19 | 2024-11-22 | 2024-12-20 | N.T. Sotelo Construction and Supply Corporation | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | San Pedro City | 108434 | San Vicente Elementary School | SAN PEDRO | 1st | 1 | 20 | Repair of Classrooms | 3037968.19 | 1 | 2139121.38 | COMPLETED | 100% | 2025-03-20 | 2025-02-01 | 2024-PB-024 | 2024-PB-024 | 2024-06-25 | 2024-07-03 | 2024-07-15 | 2024-10-07 | 2024-10-21 | Open Builders Incorporated | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Sto. Tomas City | 107697 | San Antonio Elementary School | SANTO TOMAS | 3rd | 1 | 10 | Repair of Classrooms | 5777777.78 | 1 | 5238161.19 | COMPLETED | 100% | 2025-04-07 | 2025-04-07 | CW-2024-11-0001 | CW-2024-11-0001 | 2024-11-25 | 2024-12-05 | 2024-12-17 | 2024-12-20 | 2024-12-23 | Open Builders Incorporated | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-A | Tanauan City | 107763 | Luyos ES | CITY OF TANAUAN | 3rd | 1 | 4 | Repair of Classrooms | 4067564.39 | 1 | 3987906.55 | COMPLETED | 100% | 2024-12-21 | 2024-12-21 | BEFF 2024- IV A TANAUAN-001 | BEFF 2024- IV A TANAUAN-001 | 8/16/204 | 2024-08-27 | 2024-09-09 | 2024-10-02 | 2024-10-21 | MARAKESH ENTERPRISES | [13 empty] | 70% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-A | Tayabas City | 109249 | Eugenio Francia Elementary School | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 3122920.91 | 1 | 2935000 | COMPLETED | 100% | 2025-04-09 | 2025-04-03 | ITB-INFRA-2024-007 | ITB-INFRA-2024-007 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2024-12-20 | 2024-12-27 | LLEB CONSTRUCTION AND TRADING | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Calapan City | 111536 | Calapan Central School | CITY OF CALAPAN (Capital) | 1st | 1 | 10 | Repair of Classrooms | 8461616.16 | 1 | 7376203.963 | Ongoing | 70% | 2025-08-20 |  | PBD-2025-01-BEFF-01 | 2025-027 | 2025-01-22 | 2025-01-20 | 2025-02-12 | 2025-02-26 | 2025-03-27 | MARJO CONSTRUCTION AND BUILDERS CORPORATION | with approved realignment scope of works from 7 classrooms to 10classrooms | [12 empty] | 60% |  |  |  | 1 | 7 | 8461616.16 |  | Ongoing
REPAIR 2024 | Region IV-B | Occidental Mindoro | 308904 | Manoot National High School | RIZAL | Lone | 1 | 8 | Repair of Classrooms | 4828311.9 | 1 |  | COMPLETED | 100% |  | 2025-01-21 | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | completed
REPAIR 2024 | Region IV-B | Occidental Mindoro | 110256 | Batasan ES | SAN JOSE | Lone | 1 | 8 | Repair of Classrooms | 5050505.05 | 1 |  | COMPLETED | 100% |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Occidental Mindoro | 110251 | Bubog 2 ES | SAN JOSE | Lone | 1 | 6 | Repair of Classrooms | 3647426.72 | 1 |  | COMPLETED | 100% |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Occidental Mindoro | 110307 | Mapaya III ES - Ong-Ong | SAN JOSE | Lone | 1 | 4 | Repair of Classrooms | 2433914.26 | 1 |  | COMPLETED | 100% |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Occidental Mindoro | 110274 | Tugtugin ES | SAN JOSE | Lone | 1 | 2 | Repair of Classrooms | 1211559.24 | 1 |  | COMPLETED | 100% |  |  | DepEd-OccMdo-2024-07 |  | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-02 | 2024-10-21 | Hawkstow Construction and Development | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110341 | Mangangan II ES | BACO | 1st | 1 | 3 | Repair of Classrooms | 2132504.79 | 1 | 2037924.36 | COMPLETED | 100% | 2024-12-14 | 2024-12-02 | CY 2024 BEFF Repair-001 | 31-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | Kasanga Construction and Supplies | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110588 | Biga Elementary School | POLA | 1st | 1 | 5 | Repair of Classrooms | 3142359.65 | 1 | 3086221.65 | COMPLETED | 100% | 2025-01-12 | 2024-12-11 | CY 2024 BEFF Repair-002 | 32-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | FS Sugay Construction & Supplies | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110677 | Mabuhay II Elementary School | SOCORRO | 1st | 1 | 8 | Repair of Classrooms | 6571347.07 | 1 | 6500903 | COMPLETED | 100% | 2025-03-13 | 2025-01-02 | CY 2024 BEFF Repair-003 | 33-2024 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-14 | 2024-10-02 | ETVR Trading and Construction | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110443 | Kawit ES | GLORIA | 2nd | 1 | 3 | Repair of Classrooms | 1228614.24 | 1 | 1215000 | COMPLETED | 100% | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110569 | Anoling ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1500799.47 | 1 | 1485000 | COMPLETED | 100% | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110555 | Banilad ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1244999.31 | 1 | 1232000 | COMPLETED | 100% | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Oriental Mindoro | 110559 | Lumambayan ES | PINAMALAYAN | 2nd | 1 | 2 | Repair of Classrooms | 1170750.59 | 1 | 1158000 | COMPLETED | 100% | 2025-03-14 | 2025-01-15 | CY 2024 BEFF Repair-004 | 35-2024 | Sept. 14, 2024 | Sept. 23, 2024 | Oct. 7, 2024 | 2024-10-22 | 2024-11-07 | ADL Constrak OPC | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region IV-B | Palawan | 309135 | Ilian National High School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3204863.59 | 1 | 3162752.06 | COMPLETED | 100% | 2024-03-29 | 2025-02-28 | 2024-07-007-INFRA | 2024-11-006_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-11-04 | 2024-11-20 | RBM2 Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Palawan | 170515 | Magsasaka Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3797857.66 | 1 | 3756431.84 | Ongoing | 45% | 2025-07-30 |  | 2024-07-006-INFRA | 2025-03-002_INFRA | 2024-12-31 | 2025-01-07 | 2025-01-20 | 2025-02-24 | 2025-03-24 | Em Abin Trading and Construction | [13 empty] | 10% | [7 empty] | ONGOING
REPAIR 2024 | Region IV-B | Palawan | 110777 | Nala Elementary School | DUMARAN | 1st | 1 | 4 | Repair of Classrooms | 3785615.85 | 1 | 3736878.46 | COMPLETED | 100% | 2024-03-11 | 2025-02-10 | 2024-07-005-INFRA | 2024-09-004_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-09-23 | 2024-10-30 | RBM2 Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Palawan | 110724 | Iraan Elementary School | ABORLAN | 3rd | 1 | 8 | Repair of Classrooms | 5809406.02 | 1 | 5740368.11 | COMPLETED | 100% | 2024-03-29 | 2025-03-24 | 2024-07-008-INFRA | 2024-11-007_INFRA | 2024-08-03 | 2024-08-09 | 2024-08-22 | 2024-11-04 | 2024-11-20 | RBM2 Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IV-B | Puerto Princesa City | 301782 | Inagawan NHS | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 8 | Repair of Classrooms | 6146907.21 | 1 | 6034137.17 | COMPLETED | 100% | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION | REALIGNED FROM STA MONICA HS TO INAGAWAN NHS | [12 empty] | 95% |  |  | 5.25 | 1 | 19 | 6146907.21 |  | Ongoing
REPAIR 2024 | Region IV-B | Puerto Princesa City | 111490 | Napsan ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 1 | Repair of Classrooms | 747782.83 | 1 | 735350.16 | COMPLETED | 100% | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION | For Final Inspection | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-B | Puerto Princesa City | 111497 | Tagburos ES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 11 | Repair of Classrooms | 7363916.44 | 1 | 7226527.24 | COMPLETED | 100% | Jul. 2, 2025 |  |  | INFRA 2024-09-02 | Sept. 26, 2024 | Oct. 2, 2024 | Oct. 14, 2024 | Oct. 21, 2024 | Oct. 28, 2024 | MARYJONICA CONSTRUCTION | [13 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region IV-B | Romblon | 111292 | Magdiwang ES | MAGDIWANG | Lone | 1 | 2 | Repair of Classrooms | 3030303.03 | 1 | 2999981.91 | Ongoing | 49.85% | March 1,2025 |  | BEFF-REF-2024-02 | BEFF-REF-2024-02 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 14, 2024 | 2024-12-04 | RMR Construction & Trading | [13 empty] | 45% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-B | Romblon | 111347 | Amatong (Orlina) Elementary School | ODIONGAN | Lone | 1 | 6 | Repair of Classrooms | 3535353.54 | 1 | 3389028.61 | Ongoing | 22% | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading | [13 empty] | 20% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-B | Romblon | 111334 | Boliganay ES | ODIONGAN | Lone | 1 | 4 | Repair of Classrooms | 3535353.54 | 1 | 3303927.38 | Ongoing | 43% | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading | [13 empty] | 20% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-B | Romblon | 111359 | PROGRESO OESTE ELEMENTARY SCHOOL | ODIONGAN | Lone | 1 | 7 | Repair of Classrooms | 3030303.03 | 1 | 2804196.62 | Ongoing | 34.39% | May 13,2025 |  | BEFF-REF-2024-03 | BEFF-REF-2024-03 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 22, 2024 | 2024-12-09 | RMR Construction & Trading | [13 empty] | 20% | [7 empty] | Ongoing
REPAIR 2024 | Region IV-B | Romblon | 111368 | Agpanabat ES | ROMBLON (Capital) | Lone | 1 | 7 | Repair of Classrooms | 3030303.03 | 1 | 2997442.23 | Ongoing | 50% | March 1,2025 |  | BEFF-REF-2024-01 | BEFF-REF-2024-01 | Sept. 03, 2024 | Sept. 11, 2024 | Sept. 23, 2024 | Nov. 14, 2024 | 2024-12-04 | RMR Construction & Trading | [13 empty] | 50% | [7 empty] | Ongoing
REPAIR 2024 | Region IX | Dapitan City | 125949 | Potungan Central School | DAPITAN CITY | 1st | 1 | 4 | Repair of Classrooms | 3636363.64 | 1 | - | COMPLETED | 100% | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Dipolog City | 125995 | San Alfonso Elementary School | DIPOLOG CITY (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 6549218.22 | 1 | 6481501.28 | COMPLETED | 100% | 2025-03-25 | - | Repair/Rehabilitation of Classrooms of San Alfonso ES | DepED-Repair-24-IX-Dip-001 | September 9, 2024 | July 17, 2024 | July 30, 2024 | September 16, 2024 | September 25, 2024 | CPAN Engineering and Enterprises | None | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Isabela City | 126000 | Isabela Bliss Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | 7 | Repair of Classrooms | 5656565.66 | 1 | - | Ongoing | 90% | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | [12 empty] | 85% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Isabela City | 198008 | M.S. Bernardo Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | 2 | Repair of Classrooms | 1616161.62 | 1 | - | Ongoing | 98% | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | [12 empty] | 95% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Isabela City | 126017 | Tabiawan ES | CITY OF ISABELA (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2424242.42 | 1 | - | Ongoing | 99% | - | - | - | - | - | - | - | - | - | - | Awaiting SARO Release | [12 empty] | 97% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Pagadian City | 314701 | Francisco P. Consolacion National High School | PAGADIAN CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 5552640.82 | 1 | 5487077.06 | COMPLETED | 100% | - | - | REPAIR 2024 - RIX - PAGADIAN CITY - 001 | REPAIR 2024 - RIX - PAGADIAN CITY - 001 | 2024-08-15 | 2024-08-23 | 2024-09-04 | 2024-09-23 | 2024-10-16 | ARADEL CONSTRUCTION AND SUPPLIES | Revised from 9CL to 6CL | [12 empty] | 100% |  |  | 3.25 | 1 | 9 | 5552640.82 |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga City | 126150 | Talisayan ES | ZAMBOANGA CITY | 1st | 1 | 6 | Repair of Classrooms | 3636363.64 | 1 | - | COMPLETED | 100% | Mar. 08,2025 | Mar. 05,2025 | 2024-08-0408-LOT-1 | ZC-24-REPAIR-1 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region IX | Zamboanga City | 126165 | Manicahan Pob. ES | ZAMBOANGA CITY | 2nd | 1 | 12 | Repair of Classrooms | 7272727.27 | 1 | - | Ongoing | 98% | Mar. 08,2025 | - | 2024-08-0408-LOT-2 | ZC-24-REPAIR-2 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | [12 empty] | 95% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Zamboanga City | 126205 | Salaan ES | ZAMBOANGA CITY | 2nd | 1 | 9 | Repair of Classrooms | 5454545.45 | 1 | - | COMPLETED | 100% | Mar. 08,2025 | - | 2024-08-0408-LOT-3 | ZC-24-REPAIR-3 | August 16,2024 | August 22, 2024 | Sept. 3,2024 | Oct. 18,2024 | Nov. 08,2024 | ZAMBOANGA 3VC CONSTRUCTION INC , | - | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region IX | Zamboanga del Norte | 124611 | Rizalina ES | RIZAL | 1st | 1 | 5 | Repair of Classrooms | 4691993.38 | 1 | 4631730.76 | COMPLETED | 100% | - | - | 2024-039-CBZN | 2024-039-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | June 26, 2024 | - | YSL Builders | - | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga del Norte | 303731 | Diongan National High School | SIAYAN | 2nd | 1 | 7 | Repair of Classrooms | 6713038.58 | 1 | 6630234.4 | Ongoing | 40% | - | - | 2024-040-CBZN | 2024-040-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | June 26, 2024 | - | MDS Construcion & Enterprises | - | [12 empty] | 35% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Zamboanga del Norte | 124429 | Bogabongan ES | BACUNGAN (LEON T. POSTIGO) | 3rd | 1 | 7 | Repair of Classrooms | 7070137.42 | 1 | 6981911.91 | COMPLETED | 100% | - | - | 2024-041-CBZN | 2024-041-CBZN | May 28, 2024 | June 05, 2024 | June 18, 2024 | July 03, 2024 | - | YSL Builders | - | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga del Sur | 196011 | Montela ES | AURORA | 1st | 1 | 5 | Repair of Classrooms | 3787878.79 | 1 | 3718090.72 | COMPLETED | 100% | 2025-01-18 | December 15, 2024 | ZDS-24-RR-02 | ZDS-24-RR-02 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | GENEMAR CONSTRUCTION | - | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga del Sur | 125430 | Kapalaran ES | TAMBULIG | 1st | 1 | 3 | Repair of Classrooms | 2272727.27 | 1 | 2248454.12 | COMPLETED | 100% | 2024-12-19 | December 15, 2024 | ZDS-24-RR-01 | ZDS-24-RR-01 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | AYUS BUILDERS AND ENTERPRISES | - | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga del Sur | 125061 | Baguitan ES | GUIPOS | 2nd | 1 | 5 | Repair of Classrooms | 3787878.79 | 1 | 3745121.3 | COMPLETED | 100% | 2025-01-18 | January 05, 2024 | ZDS-24-RR-03 | ZDS-24-RR-03 | 2024-06-19 | 2024-06-28 | 2024-07-10 | 2024-07-16 | 2024-09-13 | JZ MAGO CONSTRUCTION & ENTERPRISES | - | [12 empty] | 100% |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125520 | Kawayan Elementary School | ALICIA | 1st | 1 | 6 | Repair of Classrooms | 4443686.87 | 1 | 3939809.13 | Ongoing | 90% | Mar. 28, 2025 | - | ZSY-2024-REPAIR-01 | ZSY-2024-REPAIR-01 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | - | November 28, 2024 | AFFIAH CONSTRUCTION | - | [12 empty] | 65% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125730 | Upper Sulitan Elementary School | NAGA | 2nd | 1 | 6 | Repair of Classrooms | 4410101.01 | 1 | 4205888.01 | Ongoing | 60% | June 16, 2025 | - | ZSY-2024-REPAIR-02 | ZSY-2024-REPAIR-02 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | February 06, 2025 | February 17, 2025 | MKJ Construction | Nego-Procurement due to failure of bidding | [12 empty] | 15% | [7 empty] | ongoing
REPAIR 2024 | Region IX | Zamboanga Sibugay | 125815 | Batu Elementary School | SIAY | 2nd | 1 | 5 | Repair of Classrooms | 3677060.61 | 1 | 3522291.2 | Ongoing | 50% | June 16, 2025 | - | ZSY-2024-REPAIR-03 | ZSY-2024-REPAIR-03 | Sept. 06, 2024 | Sept. 13, 2024 | Sept. 27, 2024 | February 06, 2025 | February 17, 2025 | MKJ Construction | Nego-Procurement due to failure of bidding | [12 empty] | 15% | [7 empty] | ongoing
REPAIR 2024 | Region V | Albay | 111880 | Ogob Elementary School | MALINAO | 1st | 1 | 5 | Repair of Classrooms | 6455251.77 | 1 | 4530032.65 | COMPLETED | 100% |  |  | PV-ALBAYINFRA-24-02 | PV-ALBAYINFRA-24-02 | 2024-09-06 |  | 2024-09-27 | 2024-11-08 |  | 3G Builder and Supplies | [13 empty] | 65% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Camarines Norte | 112231 | Mambungalon Elementary School | MERCEDES | 2nd | 1 | 7 | Repair of Classrooms | 4595959.6 | 1 |  | COMPLETED | 100% | [10 empty] | MOBILIZATION | [12 empty] | 35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2nd | 1 | 10 | Repair of Classrooms | 6565656.57 | 1 |  | COMPLETED | 100% | [10 empty] | MOBILIZATION | [12 empty] | 35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Camarines Norte | 112239 | Tagongtong Elementary School | MERCEDES | 2nd | 1 | 6 | Repair of Classrooms | 3175781.28 | 1 |  | COMPLETED | 100% | [10 empty] | MOBILIZATION | [12 empty] | 35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Camarines Sur | 112566 | Salvacion Elementary School | CARAMOAN | 4th | 1 | 8 | Repair of Classrooms | 7507902.26 | 1 |  | Not yet started | 0% | [10 empty] | waiting for NTP | [12 empty] | 0% | [7 empty] | Not yet started
REPAIR 2024 | Region V | Camarines Sur | 112993 | Turague ES | SAGÑAY | 4th | 1 | 4 | Repair of Classrooms | 3765384.78 | 1 |  | Not yet started | 0% | [10 empty] | waiting for NTP | [12 empty] | 0% | [7 empty] | Not yet started
REPAIR 2024 | Region V | Catanduanes | 113310 | Buenavista ES | VIGA | Lone | 1 | 4 | Repair of Classrooms | 5050505.05 | 1 | 4163634.52 | COMPLETED | 100% | [10 empty] | for issuance of contract award | [12 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Iriga City | 114426 | San Miguel Elementary School | IRIGA CITY | 5th | 1 | 1 | Repair of Classrooms | 2280005.28 | 1 |  | under procurement | 0% |  |  | 2024-06-24-PR-122 |  | 2024-06-28 | 2024-07-12 | 2024-07-25 | - |  |  | For Award | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region V | Iriga City | 114442 | Sta. Teresita Elementary School | IRIGA CITY | 5th | 1 | 5 | Repair of Classrooms | 4747474.75 | 1 |  | under procurement | 0% |  |  | 2024-06-24-PR-122 |  | 2024-06-28 | 2024-07-12 | 2024-07-25 | - |  |  | For Award | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region V | Ligao City | 321701 | Ligao City National Technical Vocational High School | CITY OF LIGAO | 3rd | 1 | 3 | Repair of Classrooms | 4417204.97 | 1 |  | Under Procurement | 0% | [10 empty] | for award | [12 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Masbate | 113481 | Danao Elementary School | BATUAN | 1st | 1 | 7 | Repair of Classrooms | 6724383.84 | 1 |  | Under Procurement | 0% | [23 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Masbate | 113586 | Nonoc Elemantary School | CLAVERIA | 1st | 1 | 5 | Repair of Classrooms | 4803030.3 | 1 |  | Under Procurement | 0% | [23 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Masbate | 113588 | Pasig ES | CLAVERIA | 1st | 1 | 2 | Repair of Classrooms | 1921212.12 | 1 |  | Under Procurement | 0% | [23 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Masbate | 113916 | Gemino Elementary School | SAN PASCUAL | 1st | 1 | 6 | Repair of Classrooms | 4068769.7 | 1 |  | Under Procurement | 0% | [23 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Masbate City | 113680 | Julian V. Antonio Elementary School | CITY OF MASBATE (Capital) | 2nd | 1 | 9 | Repair of Classrooms | 6739010.88 | 1 | 6622475.05 | COMPLETED | 100% | [10 empty] | revised program of works | [12 empty] | 1% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Naga City | 302265 | Cararayan National High School | NAGA CITY | 3rd | 1 | 10 | Repair of Classrooms | 9212714.83 | 1 |  | Under Procurement | 0% | [23 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR | 1st | 1 | 7 | Repair of Classrooms | 6910782.67 | 1 | 6132057.75 | COMPLETED | 100% | 2025-04-24 |  | 24-11-002 | 24-11-002 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-23 | 2024-12-26 | 144 Cubits Builders and Supply | [13 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Sorsogon City | 114541 | Rawis Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 8 | Repair of Classrooms | 2086653.56 | 1 | 2060786.04 | COMPLETED | 100% | 2025-06-01 |  |  |  | September 30, 2024-October 21, 2024 | 2024-10-08 | 2024-10-21 | 2024-10-24 | 2024-10-27 |  | SARO Released | [12 empty] | 50% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region V | Sorsogon City | 114533 | Sugod Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 14 | Repair of Classrooms | 4954004.55 | 1 | 4899463.03 | COMPLETED | 100% | 2025-06-01 |  |  |  | September 30, 2024-October 21, 2025 | 2024-10-09 | 2024-10-21 | 2024-10-25 | 2024-10-28 |  | REALIGNED FROM ROSA ARELLANO ES TO SUGOD ES | [12 empty] | 15% |  |  | 5.25 | 1 | 14 | 4954004.55 |  | Ongoing
REPAIR 2024 | Region VI | Aklan | 114908 | Ochando ES | NEW WASHINGTON | 1st | 1 | 6 | Repair of Classrooms | 3496545.95 | 1 |  | Under Procurement | 0% |  |  |  |  | 2024-06-07 | 2024-06-14 | 2024-06-26 |  |  | Nems Construction and Supply | Waiting for BAC Decision | [12 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region VI | Aklan | 114914 | Aliputos Elementary School | NUMANCIA | 2nd | 1 | 2 | Repair of Classrooms | 1181532.45 | 1 |  | Under Procurement | 0% |  |  |  |  | 2024-06-07 | 2024-06-14 | 2024-06-26 |  |  | Nems Construction and Supply | Waiting for BAC Decision | [12 empty] | 0% | [7 empty] | Under Procurement
REPAIR 2024 | Region VI | Antique | 115285 | Sebaste CS | SEBASTE | Lone | 1 | 5 | Repair of Classrooms | 4423057.18 | 1 | 3997606.9 | COMPLETED | 100% | 2025-04-09 |  | R6-D2-GAA2024-30-SR | R6-D2-GAA2024-30-SR | 2024-09-10 | 2024-09-17 | 2024-10-01 | 2024-11-04 | 2024-11-18 | One Piece Builders | On-going, with proposed variation order | [12 empty] | 60% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VI | Bacolod City | 117458 | Fernando F. Gonzaga Elementary School | BACOLOD CITY (Capital) | Lone | 1 | 6 | Repair of Classrooms | 3031152.68 | 1 | 2950000 | COMPLETED | 100% | 23/04/2025 |  | REPAIR 2024 -R06- BACOLOD CITY - 001 | R6BCD10112024-P159 | 2024-10-15 | 2024-10-22 | 2024-11-04 | 17/1/2025 | 17/1/2025 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Ongoing implementation | [12 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VI | Cadiz City | 117538 | San Andres ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4292668.79 | 1 | 4149742.1 | COMPLETED | 100% |  |  |  |  | 2024-08-01 | 2024-08-12 | 2024-08-27 | 2024-08-28 |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VI | Capiz | 115433 | Dao Central School | DAO | 2nd | 1 | 5 | Repair of Classrooms | 4054969.82 | 1 | 2694426.46 | COMPLETED | 100% | 2025-03-08 | 2024-12-12 | R6-DEPED-CAPIZ-CY2024-BEFF-BATCH1-LOT1 |  | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-03 | MARIZALOI Construction | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1st | 1 | 4 | Repair of Classrooms | 2873738.94 | 1 | 2100000 | COMPLETED | 100% | 2024-02-02 |  | Project 03-2024 | Project 03, 2024 | 2024-07-23 | Augusut 1, 2024 | 2024-08-13 | 2024-09-11 | 2024-10-02 | Valkyrie Construction | Completed with approved VO in the amount of Php 200,160.90 and revised project completion is March 21, 2025 | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Guimaras | 115835 | Agsanayan Elementary School | BUENAVISTA | Lone | 1 | 3 | Repair of Classrooms | 2153338.98 | 1 | 1874685.87 | COMPLETED | 100% | 2025-01-31 | 2025-01-20 | Project 09-2024 | Project 09-2024 | 2024-05-29 | 2024-06-07 | 2024-06-20 | 2024-06-12 | 2024-09-27 | ALJ Construction & Supply | Completed with approved VO in the amount of 184, 878.02 | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Guimaras | 115892 | Calaya Elementary School | NUEVA VALENCIA | Lone | 1 | 3 | Repair of Classrooms | 2227973.84 | 1 | 1874685.87 | COMPLETED | 100% | 2025-01-31 | 2025-01-20 | Project 09-2024 | Project 09-2024 | 2024-05-29 | 2024-06-07 | 2024-06-20 | 2024-06-12 | 2024-09-27 | ALJ Construction & Supply | Completed with approved VO in the amount of 184, 878.02 | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Himamaylan City | 117092 | Cabanbanan ES | CITY OF HIMAMAYLAN | 5th | 1 | 5 | Repair of Classrooms | 4118434.58 | 1 | 2949000 | COMPLETED | 100% | 2025-03-09 | 2025-01-16 | IB-sdhc-062024-002 | IB-sdhc-062024-002 | 2024-06-26 | 2024-07-05 | 2024-07-17 | Sept. 3, 2024 | 2024-09-27 | RISM BUILDERS AND CONSTRUCTION SERVICES | COMPLETED | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Iloilo | 116733 | Lawigan ES | SAN JOAQUIN | 1st | 1 | 5 | Repair of Classrooms | 2685430.12 | 1 | 2287984.48 | COMPLETED | 100% | 2025-04-04 |  | BEFF2024-RVI-022-ILOILO-REPAIR-L1 | BEFF2024-RVI-022-ILOILO-REPAIR-L1 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-10-11 | 2024-11-29 | PAG-UN BUILDERS & SUPPLY | For issuance of contract | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VI | Iloilo City | 302744 | Jaro National High School | ILOILO CITY (Capital) | Lone | 1 | 52 | Repair of Classrooms | 4219499.09 | 1 | 3165997.45 | COMPLETED | 100% | 2025-04-15 |  |  | 2024-08-002 | 23/07/2024 | 30/07/2024 | 13/08/2023 | 19/09/2024 | 2024-10-11 | MJBL CONST. SERVICES | On-going | [12 empty] | 60% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VI | Kabankalan City | 117829 | Badiangay Elementary School | CITY OF KABANKALAN | 6th | 1 | 6 | Repair of Classrooms | 4273340.4 | 1 | 4207191 | not yet started | 0% |  |  | 2024-SB-03-PB003 |  | 2024-09-20 | 2024-09-26 | 2024-10-09 | 2024-10-15 |  | RISM BUILDERS AND CONSTRUCTION SERVICES INC. | For contract perfection | [12 empty] | 0% | [7 empty] | not yet started
REPAIR 2024 | Region VI | La Carlota City | 117648 | La Granja ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 4846699.89 | 1 | 3205383.35 | COMPLETED | 100% | 2025-12-30 | 2024-01-30 | 2024-15 |  | 2024-07-07 | 2024-07-14 | 2024-07-23 | 2024-08-16 | 2024-08-23 | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES | 100% Completed | [12 empty] | 93% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VI | Negros Occidental | 117283 | Murcia East ES | MURCIA | 3rd | 1 | 2 | Repair of Classrooms | 1406364.12 | 1 | 708927.75 | Not Yet Started | 0% |  |  | 09-42-24 |  | 2024-09-06 | 2024-09-16 | 2024-09-30 |  |  | KEANNE CONSTRUCTION SERVICES | For Award | [12 empty] | 0% | [7 empty] | Not Yet Started
REPAIR 2024 | Region VI | Negros Occidental | 117429 | Valladolid ES | VALLADOLID | 4th | 1 | 6 | Repair of Classrooms | 3562789.12 | 1 |  | Not Yet Started | 0% | [6 empty] | 2024-12-02 |  |  |  | For Procurement | [12 empty] | 0% | [7 empty] | Not Yet Started
REPAIR 2024 | Region VI | Passi City | 117898 | Bagacay Elementary School | CITY OF PASSI | 4th | 1 | 6 | Repair of Classrooms | 3641829.26 | 1 | 2522888.34 | COMPLETED | 100% | 2025-05-05 | 2025-02-21 | BEFF-REPAIR | RO6-D14-FY2024-BEFF-REPAIR-BAGACAY ES | 2024-07-20 | 2024-07-26 | 2024-08-06 | 2024-08-19 | 2024-11-29 | Early Riser Construction | COMPLETED | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Passi City | 117917 | BATU ELEMENTARY SCHOOL | CITY OF PASSI | 4th | 1 | 7 | Repair of Classrooms | 5192559.24 | 1 | 3544345.94 | COMPLETED | 100% | 2025-05-05 | 2025-04-10 | BEFF-REPAIR | RO6-D14-FY2024-BEFF-REPAIR-BATU ES | 2024-07-20 | 2024-07-26 | 2024-08-06 | 2024-08-19 | 2024-11-29 | Early Riser Construction | COMPLETED | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Roxas City | 501336 | Cogon Integrated School | ROXAS CITY (Capital) | 1st | 1 | 3 | Repair of Classrooms | 5209139.51 | 1 | 3610777.43 | COMPLETED | 100% | 2025-05-18 | 2025-01-28 | 2024-059 | CON-2024-059 | sept. 16, 2024 | sept. 24, 2024 | 2024-10-08 | 2024-12-03 | 2024-12-09 | Reubin L. Yap, Contractor | completed | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1968909.78 | 1 | 1580000 | COMPLETED | 100% | 2025-01-31 | 2025-01-20 | CPB-INFRA-01-2024 | CPB-INFRA-01-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | KEANNE CONSTRUCTION SERVICES | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1687636.95 | 1 | 1355000 | COMPLETED | 100% | 2025-01-31 | 2025-01-20 | CPB-INFRA-02-2024 | CPB-INFRA-02-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | VALKYRIE CONSTRUCTION | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | San Carlos City | 117745 | Don Juan Ledesma ES | SAN CARLOS CITY | 1st | 1 | 2 | Repair of Classrooms | 919209.43 | 1 | 912811.81 | COMPLETED | 100% | 2024-12-30 | 2024-10-24 |  | PR# 2024-06-0044 |  |  | 2024-06-28 |  | 2024-09-28 | TMTC Construction & Supply | for approval of resolution to award | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region VI | Silay City | 117812 | Camantero Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 4245236.51 | 1 | 4196891.26 | Not Yet Started | 0% |  |  |  |  | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-21 |  | PAR Builders Electrical and Construction Supply Corp. | Perfection of Contract | [12 empty] | 0% | [7 empty] | Not Yet Started
REPAIR 2024 | Region VI | Sipalay City | 117372 | Canturay ES | CITY OF SIPALAY | 6th | 1 | 12 | Repair of Classrooms | 4380647.68 | 1 |  | Not Yet Started | 0% | [23 empty] | 0% | [7 empty] | Not Yet Started
REPAIR 2024 | Region VI | Victorias City | 117444 | Salvacion ES | CITY OF VICTORIAS | 3rd | 1 | 5 | Repair of Classrooms | 4195227.21 | 1 | 2686903.84 | COMPLETED | 100% | 2025-03-15 |  | SDOVC-INFRA2024-002 | SDOVC-INFRA2024-002 | [19 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bais City | 303212 | Bais City National High School | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 1919274.94 | 1 | 1880000 | COMPLETED | 100% | 2025-02-15 | 2025-01-07 | BCD-2024-075 | [6 empty] | RISM | complete | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2nd | 1 | 2 | Repair of Classrooms | 1442191.82 | 1 | 1118578.74 | COMPLETED | 100% | 2025-02-15 | 2025-01-09 | BCD-2024-075 | BCD-2024-075 | [5 empty] | Triple Jo const. | complete | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bayawan City | 120138 | Senator Lorenzo G. Teves Memorial Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 8 | Repair of Classrooms | 4498259.02 | 1 | 4438000 | COMPLETED | 100% | 2025-01-05 |  | 2024-BEFF-002 | 2024-BEFF-002 | 2024-07-27 | 2024-07-03 | 2024-07-15 | 2024-07-30 | 2024-09-30 | RISM Buidlers and Construction Services inc. | On-going | [12 empty] | 30% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bogo City | 312405 | Bartolome C.Pianar MNHS | CITY OF BOGO | 4th | 1 | 6 | Repair of Classrooms | 3555056.74 | 1 | 3505721.29 | COMPLETED | 100% | 2025-03-02 |  | ITB202406-001 | ITB202406-001 | 2024-07-03 | 2024-07-08 | 2024-07-22 | 2024-07-24 | 2024-10-18 | 3R Builders and Supply OPC | On-going | [12 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 305742 | Candijay Municipal High School | CANDIJAY | 1st | 1 | 4 | Repair of Classrooms | 2808549.27 | 1 | 2754515.71 | COMPLETED | 100% | 2025-03-20 | 2025-04-15 | PBI 2024-08 | PBI 2024-08 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118060 | Bago ES | BUENAVISTA | 2nd | 1 | 9 | Repair of Classrooms | 3521608.78 | 1 | 2638990.9 | COMPLETED | 100% | 2025-03-21 | 2025-03-17 | PBI 2024-01 | PBI 2024-01 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Inabanga Drilling Conts Steel Fab and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118108 | Abihilan ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3863767.14 | 1 | 3806607.53 | COMPLETED | 100% | 2025-03-21 | 2025-03-20 | PBI 2024-10 | PBI 2024-10 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | LJPM Builders and Sconst Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118109 | Anoling ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3502198.08 | 1 | 3458345.23 | COMPLETED | 100% | 2025-05-15 | ongoing | PBI 2024-26 | PBI 2024-26 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | [12 empty] | 58.71% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 302912 | Anoling National High School | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 4509706.7 | 1 | 3441535.89 | COMPLETED | 100% | 2025-03-21 | ongoing | PBI 2024-25 | PBI 2024-25 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Zion Const | mobilization | [12 empty] | 70.15% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118110 | Boyoan ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 5455888.68 | 1 | 4798710.18 | COMPLETED | 100% | 2025-03-21 | ongoing | PBI 2024-12 | PBI 2024-12 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | Zion Const | mobilization | [12 empty] | 55% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118112 | Cambane ES | CANDIJAY | 3rd | 1 | 3 | Repair of Classrooms | 2027073.09 | 1 | 1966202.52 | COMPLETED | 100% | 2025-02-18 | 2025-01-24 | PBI 2024-13 | PBI 2024-13 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Husain Const and Supply Corp. | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118113 | Canawa ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3971975.96 | 1 |  | COMPLETED | 100% |  |  |  |  | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | [12 empty] | 0% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118114 | Candijay Central ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3612679.56 | 1 | 3556539.8 | COMPLETED | 100% | 2025-03-21 | 2025-03-06 | PBI 2024-15 | PBI 2024-15 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3rd | 1 | 21 | Repair of Classrooms | 6629141.18 | 1 | 6540192.12 | COMPLETED | 100% | 2025-04-20 | 2025-03-20 | PBI 2024-29 | PBI 2024-29 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118115 | Can-olin ES | CANDIJAY | 3rd | 1 | 9 | Repair of Classrooms | 4108888.58 | 1 | 4047761.84 | COMPLETED | 100% | 2025-03-21 | completed | PBI 2024-21 | PBI 2024-21 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118116 | Cogtong ES | CANDIJAY | 3rd | 1 | 15 | Repair of Classrooms | 5808126.73 | 1 | 4008758.5 | COMPLETED | 100% | 2025-05-15 | ongoing | PBI 2024-27 | PBI 2024-27 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 302866 | Cogtong NHS | CANDIJAY | 3rd | 1 | 17 | Repair of Classrooms | 6257354.97 | 1 | 6174050.8 | COMPLETED | 100% | 2025-04-20 | completed | PBI 2024-24 | PBI 2024-24 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118117 | La Union Elementary School | CANDIJAY | 3rd | 1 | 15 | Repair of Classrooms | 5922916.73 | 1 | 4221855.58 | COMPLETED | 100% | 2025-03-27 | ongoing | PBI 2024-18 | PBI 2024-18 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | Quicksilver Const Services | mobilization | [12 empty] | 84.35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3rd | 1 | 16 | Repair of Classrooms | 5567480.19 | 1 | 3858829.45 | COMPLETED | 100% | 2025-03-27 | ongoing | PBI 2024-17 | PBI 2024-17 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | Quicksilver Const Services | mobilization | [12 empty] | 85.13% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118119 | Lungsodaan ES | CANDIJAY | 3rd | 1 | 11 | Repair of Classrooms | 3858133.83 | 1 | 3804993.77 | COMPLETED | 100% | 2025-05-15 | ongoing | PBI 2024-16 | PBI 2024-16 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  |  | mobilization | [12 empty] | 60% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118120 | Mahangin Elementary School | CANDIJAY | 3rd | 1 | 6 | Repair of Classrooms | 3166032.56 | 1 | 2494615.88 | COMPLETED | 100% | 2025-03-23 | completed | PBI 2024-20 | PBI 2024-20 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | VVER Const Devt Corp | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118122 | Panadtaran ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 5332022.34 | 1 | 5257776.35 | COMPLETED | 100% | 2025-03-21 | 2025-03-18 | PBI 2024-14 | PBI 2024-14 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118123 | Panas ES | CANDIJAY | 3rd | 1 | 7 | Repair of Classrooms | 2801779.92 | 1 | 2759784.51 | COMPLETED | 100% | 2025-02-18 | completed | PBI 2024-22 | PBI 2024-22 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | DMAM Const Services | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118124 | Pangpang ES | CANDIJAY | 3rd | 1 | 6 | Repair of Classrooms | 1159714.77 | 1 | 910070.31 | COMPLETED | 100% | 2025-01-23 | completed | PBI 2024-19 | PBI 2024-19 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 |  | VVER Const Devt Corp | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118125 | San Isidro ES | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 2919392.92 | 1 | 2077213.76 | COMPLETED | 100% | 2025-02-18 | 2025-01-14 | PBI 2024-28 | PBI 2024-28 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Job D Merchant and Builders | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 302911 | Tambongan NHS | CANDIJAY | 3rd | 1 | 24 | Repair of Classrooms | 6403436.16 | 1 | 6282572.77 | COMPLETED | 100% | 2025-04-19 | 2025-02-14 | PBI 2024-07 | PBI 2024-07 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118127 | Tawid Elementary School | CANDIJAY | 3rd | 1 | 8 | Repair of Classrooms | 3607549.19 | 1 | 3557198.78 | COMPLETED | 100% | 2025-03-21 | 2025-03-28 | PBI 2024-09 | PBI 2024-09 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | LJPM Builders and Sconst Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118128 | Tubod ES | CANDIJAY | 3rd | 1 | 7 | Repair of Classrooms | 3775256.29 | 1 | 2832666.64 | COMPLETED | 100% | 2025-03-21 | 2025-03-18 | PBI 2024-30 | PBI 2024-30 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-22 | C Jansen Const and Gen Mdse | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118129 | Tugas ES | CANDIJAY | 3rd | 1 | 10 | Repair of Classrooms | 3922375.89 | 1 | 3826582.94 | COMPLETED | 100% | 2025-03-20 | 2025-02-21 | PBI 2024-11 | PBI 2024-11 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Anielthon Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118433 | Bonkokan ES | LILA | 3rd | 1 | 12 | Repair of Classrooms | 5583978.5958 | 1 | 4148488.97 | COMPLETED | 100% | 2025-03-20 | ongoing | PBI 2024-02 | PBI 2024-02 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | [12 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Bohol | 118439 | Malinao ES | LILA | 3rd | 1 | 2 | Repair of Classrooms | 1858585.86 | 1 | 2864595.32 | COMPLETED | 100% | 2025-03-19 | completed | PBI 2024-03 | PBI 2024-03 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118441 | Taug PS | LILA | 3rd | 1 | 2 | Repair of Classrooms | 404040.4 | 1 | 1914787.95 | COMPLETED | 100% | 2024-12-05 | completed | PBI 2024-06 | PBI 2024-06 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118442 | Tiguis ES | LILA | 3rd | 1 | 5 | Repair of Classrooms | 2020202.02 | 1 | cluster with taug | COMPLETED | 100% | 2025-02-03 | completed | PBI 2024-03 | PBI 2024-03 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Bohol | 118453 | Tocdog ES | LOAY | 3rd | 1 | 4 | Repair of Classrooms | 2012059.07 | 1 | cluster with malinao | COMPLETED | 100% | 2025-02-18 | completed | PBI 2024-04 | PBI 2024-04 | July 12, 2024 | 2024-07-23 | AUG 5-6, 2024 | Sept 25, 2024 | 2024-10-21 | Sombrio Const and Supply | mobilization | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Canlaon City | 120215 | Pula ES | CANLAON CITY | 1st | 1 | 5 | Repair of Classrooms | 4140248.27 | 1 | 4098845.79 | COMPLETED | 100% | 2025-02-15 |  | ITB2024-003 | 2024-003 | 2024-06-26 | 2024-07-03 | 2024-07-16 | 2024-07-25 | 2024-09-11 | R.R. Gadingan Construction | SARO received | [12 empty] | 82% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu | 501574 | Bugho Integrated School | SAN FERNANDO | 1st | 1 | 11 | Repair of Classrooms | 3434696.73 | 1 | 3376320.13 | COMPLETED | 100% | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | MP Sorela Construction and supply | [13 empty] | 35% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu | 118902 | Bogo ES | ALOGUINSAN | 3rd | 1 | 2 | Repair of Classrooms | 1230936.32 | 1 | 1198335.13 | COMPLETED | 100% | 19/03/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Gela Construction | [13 empty] | 75% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4th | 1 | 36 | Repair of Classrooms | 1609753.76 | 1 | 1586701.96 | COMPLETED | 100% | 19/03/2025 | 2025-09-03 | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | RT Construction and enterprises | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5th | 1 | 25 | Repair of Classrooms | 3257234.88 | 1 | 3214877.65 | COMPLETED | 100% | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Rovilla construction | [13 empty] | 55% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu | 303114 | Tayud National High School | CONSOLACION | 6th | 1 | 20 | Repair of Classrooms | 1531044.87 | 1 | 1512140.42 | COMPLETED | 100% | 18/04/2025 |  | CY2024 BEFF REPAIR-DEPED-R7-CEBU |  | 16/10/2024 | 23/10/2024 | 2024-04-11 | 2024-11-11 | 29/11/2024 | Rovilla construction | [13 empty] | 8% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu City | 119892 | Camp Lapu-Lapu ES | CEBU CITY (Capital) | 1st | 1 | 18 | Repair of Classrooms | 5034542.43 | 1 | 3323822.83 | COMPLETED | 100% | April 14, 2025 |  | 2024-22(Lot 2) | DepEd CCD 2024-30 | September 13, 2024 | September 23, 2024 | October 7, 2024 | November 8, 2024 | December 9, 2024 | Steadfast Builders Construction Corporation | On - Going | [12 empty] | 92% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Cebu City | 119914 | Pasil Elementary School | CEBU CITY (Capital) | 2nd | 1 | 32 | Repair of Classrooms | 8113131.31 | 1 | 6008338.86 | COMPLETED | 100% | April 23, 2025 |  | 2024-22(Lot 1) | DepEd CCD 2024-29 | September 13, 2024 | September 23, 2024 | October 7, 2024 | November 8, 2024 | December 18, 2024 | Hero Construction and Development Corporation | On - Going | [12 empty] | 93% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Dumaguete City | 119932 | Amador Dagudag MES | DUMAGUETE CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 953206.76 | 1 | 676154.66 | COMPLETED | 100% | 2025-04-05 | 2025-03-31 | 2024-005 | 2024-005 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | Millenial Mammoth Development Corporation | COMPLETED | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Dumaguete City | 119944 | Calindagan ES | DUMAGUETE CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 381282.71 | 1 | 273578.95 | COMPLETED | 100% | 2025-05-20 | N/A | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | [12 empty] | 80% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Dumaguete City | 119946 | City Central Elementary School | DUMAGUETE CITY (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3240902.98 | 1 | 2325421.05 | COMPLETED | 100% | 2025-05-20 | N/A | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | [12 empty] | 47% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1st | 1 | 6 | Repair of Classrooms | 5126087.05 | 1 | 4389914.25 | COMPLETED | 100% | 2025-04-21 | N/A | ITB 2024-013 | ITB 2024-013 | 2024-10-16 | 2024-10-24 | November 7, 22024 | 2024-11-25 | 2024-11-28 | G.PO CONSTRUCTION | N/A | [12 empty] | 97% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Lapu-Lapu City | 119973 | Agus Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 12 | Repair of Classrooms | 3039405.44 | 1 | 3000000 | COMPLETED | 100% | 2025-02-14 | 2025-02-14 | 2024-Infra-001 | 2024-Infra-001 | 2024-07-18 | 2024-07-25 | 2024-08-09 | 2024-08-20 | 2024-10-17 | TriBairn Construction | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Lapu-Lapu City | 119963 | Bankal Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 20 | Repair of Classrooms | 3166835.8 | 1 | 3120118.63 | COMPLETED | 100% | 2025-01-15 | 2025-01-11 | 2024-Infra-002 | 2024-Infra-002 | 2024-07-18 | 2024-07-25 | 2024-08-09 | 2024-08-20 | 2024-10-17 | Golden Hammer Construction and Supply | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1st | 1 | 6 | Repair of Classrooms | 6454488.69 | 1 | 6329000 | COMPLETED | 100% | 2025-04-04 | 2025-03-26 | ITB 2024-07-116 | BEFF202409031 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Negros Oriental | 120432 | Cancawas Primary School | SAN JOSE | 2nd | 1 | 3 | Repair of Classrooms | 2304321.13 | 1 | 1932000 | COMPLETED | 100% | 2025-01-27 | 2025-01-16 | ITB 2024-07-117 | BEFF202409032 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Siquijor | 303305 | Catulayan National High School | SAN JUAN | Lone | 1 | 9 | Repair of Classrooms | 5830766.12 | 1 | 5756858.55 | COMPLETED | 100% | 2025-06-30 |  | 10889961 | 2024-032 | 2024-05-25 | 2024-05-30 | 2024-06-13 | 2024-06-19 | 2024-10-07 | Nale Construction | [13 empty] | 78% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VII | Tagbilaran City | 118710 | Manga Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 9 | Repair of Classrooms | 6344702.34 | 1 | 6281255.32 | COMPLETED | 100% | 2025-03-09 | 2025-03-01 | 2024-02-Infra | 2024-02-Infra | 2024-06-23 | 2024-06-24 | 2024-07-05 | 2024-07-10 | 2024-10-03 | CJANSEN Construction and General Merchandise | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Talisay City | 322204 | Bulacao National High School | CITY OF TALISAY | 1st | 1 | 16 | Repair of Classrooms | 3980639.21 | 1 | 3938087.39 | COMPLETED | 100% | 2025-03-04 | 2025-03-04 | talisaycity 2024-015 | talisaycityrepair 2024-2015 | 2024-10-09 | 2024-10-10 | 2024-10-22 | 2024-10-25 | 2025-11-04 | Tri Bairn Construction | Completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Tanjay City | 303285 | Bahi-an High School | CITY OF TANJAY | 2nd | 1 | 1 | Repair of Classrooms | 773357.01 | 1 | 3204000 | COMPLETED | 100% | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Tanjay City | 120558 | Mato-Bato Elementary School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 2468342.68 | 1 | 3204000 | COMPLETED | 100% | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3rd | 1 | 6 | Repair of Classrooms | 3314226.29 | 1 | 2581368.6 | COMPLETED | 100% | 2025-03-13 | 2025-03-14 |  | Repair 2024-14 | 2024-08-28 | 2024-09-04 | 2024-09-18 | 2024-09-18 | 2024-11-13 | GOLDEN COMPASS BUILDERS INC | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VIII | Baybay City | 121130 | Ambacan Elementary School | CITY OF BAYBAY | 5th | 1 | 3 | Repair of Classrooms | 2323232.32 | 1 | 2274593.57 | COMPLETED | 100% | 2024-12-30 | 2024-12-26 | 2024-07-I001 | 2024-07-I001 |  | 2024-08-01 | 2024-08-13 | 2024-09-22 | 2024-09-25 | Melgazo Construction and Supply | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region VIII | Baybay City | 121113 | Villa Elementary School | CITY OF BAYBAY | 5th | 1 | 5 | Repair of Classrooms | 3957141.41 | 1 | 3887121.08 | COMPLETED | 100% | 2025-03-05 | 2025-02-26 | 2024-07-I002 | 2024-07-I002 |  | 2024-08-01 | 2024-08-13 | 2024-09-22 | 2024-09-30 | QCC Construction and Supply | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | Lone | 1 | 9 | Repair of Classrooms | 5941898.1 | 1 | 5876966.13 | COMPLETED | 100% | [9 empty] | WB ALAGAO CONSTRUCTION | REALIGNED FROM TALAHID ES TO ALMERIA CS | [12 empty] | 90% |  |  | 5.25 | 1 | 9 | 5941898.1 |  | Ongoing
REPAIR 2024 | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN | Lone | 1 | 2 | Repair of Classrooms | 1010101.01 | 1 | 997500 | COMPLETED | 100% | [9 empty] | INFRASERVE BUILDERS & SUPPLIES | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region VIII | Borongan City | 122359 | Eugenio A. Abunda Sr. Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 6 | Repair of Classrooms | 3936616.74 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Borongan City | 122361 | Eugenio S. Daza Pilot Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | Repair of Classrooms | 4199778.72 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Borongan City | 303511 | Lalawigan National High School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | Repair of Classrooms | 7206134.8 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Calbayog City | 501970 | Caglanipao Sur Integrated School | CALBAYOG CITY | 1st | 1 | 8 | Repair of Classrooms | 5454545.45 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Eastern Samar | 122485 | Hernani Central Elementary School | HERNANI | Lone | 1 | 3 | Repair of Classrooms | 1909553.3 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | Lone | 1 | 8 | Repair of Classrooms | 5228390.51 | 1 |  | COMPLETED | 100% | [23 empty] | 100% |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VIII | Leyte | 120974 | Mudboron Elementary School | ALANGALANG | 1st | 1 | 8 | Repair of Classrooms | 5107070.71 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1st | 1 | 3 | Repair of Classrooms | 1939393.94 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Maasin City | 122168 | Nonok Norte ES | CITY OF MAASIN (Capital) | 1st | 1 | 10 | Repair of Classrooms | 6938581.82 | 1 | 5013138.41 | COMPLETED | 100% | 2025-04-10 |  | INFRA-2024-005 | INFRA-2024-005 | 2024-07-08 | 2024-07-16 | 2024-07-30 | 2024-09-27 | 2024-10-28 | VHITS D.G BUILDERS & ENTERPRISES | [13 empty] | 85% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region VIII | Northern Samar | 122792 | Biri CES | BIRI | 1st | 1 | 5 | Repair of Classrooms | 2295521.25 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Northern Samar | 122795 | MACARET ELEMENTARY SCHOOL | BIRI | 1st | 1 | 3 | Repair of Classrooms | 1963471.22 | 1 |  | under procurement | 0% | [23 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region VIII | Ormoc City | 124178 | Guintiguian Elementary School | ORMOC CITY | 4th | 1 | 6 | Repair of Classrooms | 5045315.15 | 1 | 3962380.2 | COMPLETED | 100% | 2024-12-31 | 2024-12-02 | REPAIR 2024 - RVIII - ORMOC CITY - 001 | BEFF – CY 2024- REPAIR- BATCH 1 | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-08-19 | 2024-10-18 | EH Antig Construction and Supply | Completed | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region VIII | Samar (Western Samar) | 123531 | Tambongan Elementary School | GANDARA | 1st | 1 | 5 | Repair of Classrooms | 3144887.51 | 1 | 3062665.16 | COMPLETED | 100% | 2025-01-19 | 2024-12-18 | [7 empty] | CABANDON CONSTRUCTION | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1st | 1 | 6 | Repair of Classrooms | 3637235.79 | 1 | 3585629.3 | COMPLETED | 100% | [9 empty] | GPUY CONSTRUCTION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VIII | Southern Leyte | 122084 | Otikon Elementary School | LIBAGON | 2nd | 1 | 11 | Repair of Classrooms | 6850569.67 | 1 | 6658906.37 | COMPLETED | 100% | 2025-02-27 | 2025-11-14 | CY2024- BEFF Repair-Batch 1-L1 | CY2024- BEFF Repair-Batch 1-L1 | 2024-06-04 | 2024-06-11 | 2024-06-24 |  | 2024-09-23 | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Completed | [12 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VIII | Tacloban City | 124247 | Marasbaras Central School | TACLOBAN CITY (Capital) | 1st | 1 | 16 | Repair of Classrooms | 4792879.08 | 1 |  | COMPLETED | 100% |  | 2024-12-01 |  | CY 2024 BEFF_REPAIR (BATCH 1) | 2024-06-25 | 2024-07-02 | 2024-07-15 | 2024-07-18 | 2025-07-19 | VITTS DG. BUILDERS | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region VIII | Tacloban City | 330503 | V&G National High School | TACLOBAN CITY (Capital) | 1st | 1 | 38 | Repair of Classrooms | 1012069.7 | 1 |  | COMPLETED | 100% |  | 2024-12-01 |  | CY 2024 BEFF_REPAIR (BATCH 1) | 2024-06-25 | 2024-07-02 | 2024-07-15 | 2024-07-18 | 2025-07-19 | JDR CONSTRUCTION | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Bukidnon | 126264 | Buenavista ES | BAUNGON | 1st | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1129319.63 | COMPLETED | 100% | 2025-01-09 | 2025-02-08 | PB-02-06-2024-0010 | 046-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-09-04 | 2024-10-18 | TRI FB Construction & General Merchandise | Updated 2-2025. CTE-1 APPROVED. Revised Expiry on February 8, 2025. Awaiting doc reqs for official completion & turnover. | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Bukidnon | 126267 | Kalanganan Elementary School | BAUNGON | 1st | 1 | 2 | Repair of Classrooms | 1378787.88 | 1 | 1264091.35 | COMPLETED | 100% | 2025-01-09 | 2025-02-28 | PB-02-06-2024-0010 | 047-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-09-04 | 2024-10-18 | TRI FB Construction & General Merchandise | Updated 2-2025. CTE-2 APPROVED. Revised Expiry on February 28, 2025. Awaiting doc. reqs for official completion & turnonver. | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Bukidnon | 126751 | Colon ES | SAN FERNANDO | 2nd | 1 | 5 | Repair of Classrooms | 3282828.28 | 1 | 3250000 | COMPLETED | 100% | 2025-04-08 | 2025-04-02 | PB-02-06-2024-0010 | 048-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-07-29 | 2024-11-11 | Vibranium Builders Corporation | Completed | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Bukidnon | 126359 | Old Nongnongan ES | DON CARLOS | 3rd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 | 2555805.04 | COMPLETED | 100% | 2025-03-21 | 2024-12-20 | PB-02-06-2024-0010 | 049-2024 | 2024-06-29 | 2024-07-05 | 2024-07-18 | 2024-07-29 | 2024-10-17 | Vibranium Builders Corporation | Completed | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Cagayan de Oro City | 502015 | Cadayonan Integrated School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 3728406.67 | 1 | 2962474.57 | COMPLETED | 100% | 2025-03-04 | Ongoing | REPAIR 2024-X-CAGAYAN DE ORO-002 | 2024-018 | 2024-06-28 | 2024-07-15 | 2024-07-29 | 2024-08-16 | 2024-11-04 | Parbros Construction & Supply | On-going | [12 empty] | 87% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Cagayan de Oro City | 304107 | Bugo National High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 4986459.21 | 1 | 3813512.21 | COMPLETED | 100% | 2025-03-04 | 2025-03-04 | REPAIR 2024-X-CAGAYAN DE ORO-001 | 2024-019 | 2024-06-28 | 2024-07-15 | 2024-07-29 | 2024-08-16 | 2024-11-04 | HERA1 Strength Construction | Substantially completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region X | Camiguin | 315001 | Maac National High School | GUINSILIBAN | Lone | 1 | 12 | Repair of Classrooms | 2424242.42 | 1 |  | COMPLETED | 100% |  |  | Infra-01-05-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | MINKONSTRAK ENGINEERING & GENERAL SERVICES | On-going | [12 empty] | 15% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Camiguin | 126902 | San Isidro ES | MAHINOG | Lone | 1 | 4 | Repair of Classrooms | 2591596.08 | 1 |  | COMPLETED | 100% |  |  | Infra-01-06-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | VINLABZ CONSTRUCTION | On-going | [12 empty] | 50% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Camiguin | 126903 | Tacangon ES | MAHINOG | Lone | 1 | 2 | Repair of Classrooms | 1616161.62 | 1 |  | COMPLETED | 100% |  |  | Infra-01-07-2024 |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  |  | MINKONSTRAK ENGINEERING & GENERAL SERVICES | On-going | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2nd | 1 | 8 | Repair of Classrooms | 3880688.05 | 1 | 2940701.84 | COMPLETED | 100% | 2024-02-07 | 2024-12-27 | 2024-08-0026 | 2024-09-0011 | 2024-08-08 | 2024-08-27 | 2024-09-09 | 2024-09-16 | 2024-10-07 | JDE Construction | Subject for Final Inspection | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region X | Gingoog City | 501400 | Talon Integrated School | GINGOOG CITY | 1st | 1 | 3 | Repair of Classrooms | 2949448.84 | 1 |  | COMPLETED | 100% | [10 empty] | On-going | [12 empty] | 65% |  |  | 5.25 | 1 | 3 | 2949448.84 |  | Ongoing
REPAIR 2024 | Region X | Gingoog City | 128022 | Tinabalan Elementary School | GINGOOG CITY | 1st | 1 | 2 | Repair of Classrooms | 1915480.8 | 1 |  | COMPLETED | 100% | [10 empty] | Subject for Final Inspection | [12 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Iligan City | 128129 | Mainit ES | ILIGAN CITY | Lone | 1 | 7 | Repair of Classrooms | 6363636.36 | 1 | 5179347.77 | COMPLETED | 100% | 2025-04-10 | 2025-04-07 | INFRA24-08-02 | INFRA24-08-02 | 2024-08-13 | 2024-08-27 | 2024-09-09 | Octobe 15, 2024 | 2024-11-04 | Abraham BM Construction | Ongoing | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Lanao del Norte | 126976 | Baroy CS | BAROY | 1st |  |  | Repair of Classrooms | 2451970.88 | 1 |  | Realigned (see other remarks) | 100% | [10 empty] | allocation was Re-align to Geronima | [16 empty] | 1 | 36 | 2451970.88 |  | Realigned (see other remarks)
REPAIR 2024 | Region X | Lanao del Norte | 304020 | Geronima Cabrera NHS (Riverside NHS) | KOLAMBUGAN | 1st | 1 | 11 | Repair of Classrooms | 5657828.4838 | 1 | 4743199.28 | COMPLETED | 100% | 2025-04-11 |  | 2024-18(Infra) | 2024-18(Infra) | 2024-08-15 | 2024-08-30 | 2024-09-12 | 2024-11-11 | 2024-12-12 | Haffy Construction Services | Completed | [12 empty] | 100% |  |  | 4.25 | 1 | 20 | 1791824.87 |  | COMPLETED
REPAIR 2024 | Region X | Lanao del Norte | 127141 | Pasayanon Elementary School | MATUNGAO | 1st |  |  | Repair of Classrooms | 943065.72 | 1 |  | Realigned (see other remarks) | 100% | [10 empty] | allocation was Re-align to Geronima | [16 empty] | 1 | 10 | 943065.72 |  | Realigned (see other remarks)
REPAIR 2024 | Region X | Lanao del Norte | 127222 | Juan Ardon-Camp 5 ES | TUBOD (Capital) | 1st |  |  | Repair of Classrooms | 471532.86 | 1 |  | Realigned (see other remarks) | 100% | [10 empty] | allocation was Re-align to Geronima | [16 empty] | 1 | 2 | 471532.86 |  | Realigned (see other remarks)
REPAIR 2024 | Region X | Lanao del Norte | 127077 | Panadtaran ES | LALA | 2nd | 1 | 5 | Repair of Classrooms | 2357428.5467 | 1 |  | COMPLETED | 100% | 2025-03-26 | 2025-07-24 | 2025-01(Infra)Negotiated Procurement | 2025-01(Infra)) | 2025-01-16 | 2025-01-22 | 2025-02-05 | 2025-03-14 | 2025-03-20 | S & J BUILDERS | Ongoing | [12 empty] | 20% |  |  | 5.25 | 1 | 2 | 377226.29 |  | Ongoing
REPAIR 2024 | Region X | Lanao del Norte | 501397 | Poonapiagapo Central Integrated School | POONA PIAGAPO | 2nd |  |  | Repair of Classrooms | 565839.43 | 1 |  | Realigned (see other remarks) | 100% | [10 empty] | allocation was Re-align to Geronima | [16 empty] | 1 | 20 | 565839.43 |  | Realigned (see other remarks)
REPAIR 2024 | Region X | Lanao del Norte | 127187 | Salvador CES | SALVADOR | 2nd |  |  | Repair of Classrooms | 1414598.59 | 1 |  | Realigned (see other remarks) | 100% | [10 empty] | allocation was Re-align to Panadtaran | [16 empty] | 1 | 10 | 1414598.59 |  | Realigned (see other remarks)
REPAIR 2024 | Region X | Malaybalay City | 500245 | Can-ayan IS | CITY MALAYBALAY (Capital) | 2nd | 1 | 3 | Repair of Classrooms | 1886131.44 | 1 | 1565974.23 | COMPLETED | 100% | 2025-01-27 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-11-13 | JDE CONSTRUCTION | Completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Malaybalay City | 126564 | Laguitas Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1037372.29 | 1 | 858895.96 | COMPLETED | 100% | 2025-01-03 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-10-29 | WEGE Konstruck Civil Engineering Estimates.Construction | Completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Malaybalay City | 314904 | Malaybalay City National Science HS | CITY MALAYBALAY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1131678.87 | 1 | 998067.06 | COMPLETED | 100% | 2025-01-11 |  | 002-INFRA-2024 | 002-INFRA-2024 | 2024-08-12 | 2024-08-20 | 2024-09-03 |  | 2024-10-29 | WEGE Konstruck Civil Engineering Estimates.Construction | Completed | [12 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Misamis Occidental | 127278 | Timoteo SU ES (Lupagan ES) | BALIANGAO | 1st | 1 | 1 | Repair of Classrooms | 1297167.68 | 1 | 1282667.76 | COMPLETED | 100% | 2025-01-11 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 001 | 022-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | For rectification of issued Punchlist of Corrective Works | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Occidental | 127415 | Don Andres Soriano PS | LOPEZ JAENA | 1st | 1 | 1 | Repair of Classrooms | 1297167.68 | 1 | 1279611.3 | COMPLETED | 100% | 2025-03-12 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 002 | 023-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | For rectification of issued Punchlist of Corrective Works | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Occidental | 127499 | Mamanga ES | PLARIDEL | 1st | 1 | 3 | Repair of Classrooms | 3891502.02 | 1 | 3834248.18 | COMPLETED | 100% | 2025-02-10 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 003 | 024-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going | [12 empty] | 68% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Occidental | 127339 | Dela Paz Elementary School | CLARIN | 2nd | 1 | 2 | Repair of Classrooms | 1717171.72 | 1 | 1691541.52 | COMPLETED | 100% | 2025-02-10 |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 004 | 025-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going | [12 empty] | 58% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Occidental | 127340 | Dolores ES | CLARIN | 2nd | 1 | 2 | Repair of Classrooms | 1717171.72 | 1 | 1690830.59 | COMPLETED | 100% |  |  | BEFF 2024 REPAIR/REHABILITATION OF CLASSROOMS BATCH 1 - REGION X - MISAMIS OCCIDENTAL - 005 | 026-2024 | 2024-07-29 | 2024-08-06 | 2024-08-19 | 2024-09-16 | 2024-10-30 | ESL MILESTONE BUILDERS AND SUPPLY, INC. | On-going | [12 empty] | 55% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1st | 1 | 6 | Repair of Classrooms | 3787878.79 | 1 | 3260255.31 | COMPLETED | 100% | 2025-05-04 |  | PB-BAC1-Repair-2024-002 | 5230097 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-09-10 | 2024-11-27 | I M & M CONSTRUCTION | On-going | [12 empty] | 40% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Oriental | 127785 | Magsaysay CS | MAGSAYSAY (LINUGOS) | 1st | 1 | 4 | Repair of Classrooms | 2525252.53 | 1 | 2137413.94 | COMPLETED | 100% | 2025-04-04 |  | PB-BAC1-Repair-2024-002 | 5230172 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-09-10 | 2024-11-27 | MINKONSTRAK ENGINEERING & GEN. SERVICES | On-going | [12 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1062509.1 | COMPLETED | 100% | 2025-02-27 |  | PB-BAC1-Repair-2024-003 | 5235571 | 2024-09-30 | 2024-10-08 | 2024-10-21 | 2024-11-07 | 2024-12-20 | TRI FB | On-going | [12 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Misamis Oriental | 127599 | Tula ES | ALUBIJID | 2nd | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 991302.16 | COMPLETED | 100% |  | 2025-02-07 | PB-BAC1-Repair-2024-003 | 5267990 | 2024-09-30 | 2024-10-08 | 2024-10-21 | 2024-11-07 | 2024-12-20 | JDE CONSTRUCTION | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Misamis Oriental | 501253 | Natubo IS | JASAAN | 2nd | 1 | 2 | Repair of Classrooms | 1262626.26 | 1 | 1160573.89 | COMPLETED | 100% |  | 2025-02-01 | PB-BAC1-Repair-2024-002 | 5235571 | 2024-07-29 | 2024-08-07 | 2024-08-20 | 2024-10-07 | 2024-11-26 | CY SQUARED | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region X | Oroquieta City | 501972 | Apil Integrated School | OROQUIETA CITY (Capital) | 1st | 1 | 4 | Repair of Classrooms | 4040404.04 | 1 | 3235513.33 | COMPLETED | 100% | 2‎ ‎April‎ ‎2025 |  | INFRA-2024-DEPEDOROQ-03 |  | 2024-06-27 | 2024-07-05 | 2024-07-17 | 2024-09-20 | 2024-10-04 | ESL builders | Ongoing | [12 empty] | 90% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Ozamis City | 128196 | Gregorio A. Saquin Elementary School | OZAMIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 4545454.55 | 1 | 4456644.33 | COMPLETED | 100% | 2025-03-29 |  | 092-CIVIL-2024-001 | 092-CIVIL-2024-001 | 2024-08-08 | 2024-08-15 | 2024-08-27 | 2024-09-30 | 2024-10-30 | MITZ AND NICK BUILDERS | on-going implementation | [12 empty] | 95% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Tangub City | 128213 | San Antonio ES | TANGUB CITY | 2nd | 1 | 4 | Repair of Classrooms | 3547407.4 | 1 | 2835886.17 | COMPLETED | 100% |  |  |  |  | 2024-07-08 | 2024-07-16 | 2024-07-29 | 2024-08-05 |  | ESL Milestone Builders Inc | On-going | [12 empty] | 70% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region X | Valencia City | 126837 | Catumbalon ES | CITY OF VALENCIA | 4th | 1 | 7 | Repair of Classrooms | 5656565.66 | 1 |  | Under procurement | 0% | [10 empty] | rebid; Failure of 1st bidding | [12 empty] | 0% | [7 empty] | Under procurement
REPAIR 2024 | Region XI | Davao City | 129616 | Malakeba Elementary School | DAVAO CITY | 3rd | 1 | 6 | Repair of Classrooms | 10030702.93 | 1 |  | COMPLETED | 100% |  |  | BEFF L003-2024 |  | June 28-July 18, 2024 | July 5, 2024 | July 18, 2024 | [16 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao De Oro | 128266 | Mambusao ES | COMPOSTELA | 1st | 1 | 3 | Repair of Classrooms | 2308508.08 | 1 | 1781821.5339 | Completed | 100% | 2025-05-31 |  |  |  |  | 2024-10-01 | 2024-10-15 | [16 empty] | 79% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region XI | Davao De Oro | 128443 | Muñoz ES | MONKAYO | 1st | 1 | 10 | Repair of Classrooms | 7123091.35 | 1 | 4937022.2021 | Completed | 100% | 2025-05-31 |  | SDD0-019-2024 |  | 9/23/2024 | 2024-10-01 | 2024-10-15 |  |  |  | REALIGNED FROM MANGAYOSN ES AND MONTEVISTA NHS TO MUNOZ ES | [12 empty] | 89% |  |  | 5.25 | 2 | 10 | 7051860.44 |  | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304224 | Datu Balong NHS | KAPALONG | 1st | 1 | 4 | Repair of Classrooms | 2077091.63 | 1 |  | Ongoing | 50% |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services | [13 empty] | 35% | [7 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1st | 1 | 4 | Repair of Classrooms | 2077091.63 | 1 |  | Ongoing | 40% |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services | [13 empty] | 35% | [7 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Norte | 304229 | Dujali National High School | BRAULIO E. DUJALI | 2nd | 1 | 6 | Repair of Classrooms | 3461819.38 | 1 |  | Ongoing | 60% |  |  | # 2025-03-03 | # 2025-03-03 | 2024-11-11 | 2024-11-18 | 2024-12-02 | 2025-03-04 | 2025-03-28 | Matt Glass Aluminum/Const. Supply and Allied Services | [13 empty] | 35% | [7 empty] | Ongoing
REPAIR 2024 | Region XI | Davao del Sur | 128810 | Balagonon Elementary School | BANSALAN | 1st | 1 | 6 | Repair of Classrooms | 5005781.97 | 1 | 3764722.33 | COMPLETED | 100% | April 17, 2025 |  | DS-RRBATCH 1-2024-H-LOT 1 | DS-RRBATCH 1-2024-H-LOT 1 |  | August 12, 2024 | August 27, 2024 |  | November 18, 2024 | R.FABALE CONSTRUCTION CORPORATION | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao del Sur | 128818 | New Clarin Elementary School | BANSALAN | 1st | 1 | 4 | Repair of Classrooms | 3337187.98 | 1 | 2429719.45 | COMPLETED | 100% | April 11, 2025 | April 8, 2025 | DS-RR BATCH 1-2024-H-LOT 2 | DS-RR BATCH 1-2024-H-LOT 2 |  | August 12, 2024 | August 27, 2024 |  | November 12, 2024 | BEBCON BUILDERS & SUPPLY | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao del Sur | 128862 | Leoncio S. Peliño Elementary School | HAGONOY | 1st | 1 | 2 | Repair of Classrooms | 1668593.99 | 1 | 1200102.67 | COMPLETED | 100% | March 12, 2025 | Marcch 7, 2025 | DS-RR BATCH 1-2024-H-LOT 3 | DS-RR BATCH 1-2024-H-LOT 3 |  | August 12, 2024 | August 27, 2024 |  | November 12, 2024 | BEBCON BUILDERS & SUPPLY | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Occidental | 128839 | Dalupan Elementary School | DON MARCELINO | Lone | 1 | 3 | Repair of Classrooms | 2844029.61 | 1 | 2814474.66 | Ongoing | 90% | 150 CD from receipt of NTP |  | ITB W-07-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.19,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | [12 empty] | 54% | [7 empty] | Ongoing
REPAIR 2024 | Region XI | Davao Occidental | 128850 | Jose Villanueva ES | DON MARCELINO | Lone | 1 | 4 | Repair of Classrooms | 3498371.17 | 1 | 3498371.17 | Ongoing | 90% | 150 CD from receipt of NTP |  | ITB W-08-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.20,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | [12 empty] | 70% | [7 empty] | Ongoing
REPAIR 2024 | Region XI | Davao Occidental | 501416 | Aldo Pagagao Integrated School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 8 | Repair of Classrooms | 1899160.34 | 1 | 1899160.34 | COMPLETED | 100% | 90 CD from receipt of NTP |  | ITB W-09-2024 | no contract yet | July 11, 2024 to July 30, 2024 | July 17, 2024 | July 30, 2024 | Resolution no.21,s. 2024 dated August 09, 2024 |  |  | short of award; for NTP | [12 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Oriental | 129206 | Alvar Elementary School | CARAGA | 1st | 1 | 6 | Repair of Classrooms | 4940110.88 | 1 | 3092025.3035 | COMPLETED | 100% | February 14, 2025 | February 13, 2024 | GS 2024 099 |  | July 9, 2024 | July 18, 2024 | July 30, 2024 | August 5, 2024 |  | PHSMB | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Davao Oriental | 129284 | Osmeña Elementary School | GOVERNOR GENEROSO | 2nd | 1 | 6 | Repair of Classrooms | 4345374.08 | 1 | 3225747.9097 | COMPLETED | 100% | February 7, 2025 | February 6, 2025 | GS 2024 100 |  | July 9, 2024 | July 18, 2024 | July 30, 2024 | August 5, 2024 |  | FAJR | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Digos City | 316302 | Matti NHS | CITY OF DIGOS (Capital) | 1st | 1 | 8 | Repair of Classrooms | 8080808.08 | 1 |  | COMPLETED | 100% | 2025-08-15 | [22 empty] | 27% |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | Region XI | Island Garden City of Samal | 301799 | Gamban Dadatan National High School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 2 | Repair of Classrooms | 1685858.59 | 1 | 1386639.61 | COMPLETED | 100% | 2024-12-15 | 2024-06-11 | INFRA002-062024 |  | June 28, 2024 | July 5, 2024 | July 23, 2024 | SEPTEMBER 5, 2024 | 2024-09-16 | KCK Builders | [13 empty] | 100% |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Island Garden City of Samal | 304250 | Samal National High School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 5 | Repair of Classrooms | 2020202.02 | 1 | 1540056.56 | COMPLETED | 100% | 2025-05-04 | 2025-04-24 |  |  | 2024-10-15 | 2024-10-21 | 2024-11-04 | 2025-01-15 |  | R.Fabale Construction | [13 empty] | 100% |  |  | 4.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Mati City | 129377 | Bagong Lipunan Improvement Site and Services Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 11 | Repair of Classrooms | 8663125.15 | 1 | 8404964.1269 | COMPLETED | 100% | 2025-07-02 | 2025-03-03 |  |  | 2024-05-27 | 2024-06-04 | 2024-06-17 |  | 2024-09-25 | FAJR CONSTRUCTION PARTS AND SUPPLY | [13 empty] | 100% |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Panabo City | 129781 | Cabili ES | CITY OF PANABO | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 |  | COMPLETED | 100% | 01/31/2025 |  |  | 2024-08-358 | AUG. 13, 2024 | AUG. 19, 2024 | SEPT.2, 2024 | AUG. 28, 2024 | 11/18/2024 | Najah Construction Supply | [13 empty] | 100% |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region XI | Tagum City | 128787 | BINCUNGAN ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 | 6 | Repair of Classrooms | 5757575.76 | 1 |  | under procurement | 0% | [10 empty] | FOR ADVERTISEMENT | [12 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region XII | General Santos City | 131310 | GSC Elementary School for the Arts | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 10 | Repair of Classrooms | 8235902.4 | 1 |  | COMPLETED | 100% |  | 002-2025- Lot 2 | 45665 | 45665 | 2025-01-21 | 2025-02-04 | 2025-02-17 | Manuela Construction | [15 empty] | 30% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | General Santos City | 304653 | Lagao National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 26 | Repair of Classrooms | 9990784.53 | 1 |  | COMPLETED | 100% |  | 002-2025- Lot 1 | 45665 | 45665 | 2025-01-21 | 2025-02-04 | 2025-02-17 | Manuela Construction | [15 empty] | 30% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Kidapawan City | 131365 | Gayola ES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 7070707.07 | 1 | Php 4,827,722.52 | COMPLETED | 100% | 2024-10- 292 | PB-2024-13 | 45596 | 45604 | 2024-11-25 | 2024-12-18 | 12/27/2024 Note: NTP receipt date by contractor is Jan.3, 2025 | Cyrus James Builders and Supply |  |  | Under Suspension | [12 empty] | 50% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Kidapawan City | 304657 | Gayola National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 6060606.06 | 1 | Php 4,129,315.34 | COMPLETED | 100% | 2024-10- 293 | PB-2024-12 | 45596 | 45604 | 2024-11-25 | 2024-12-18 | 12/27/2024 Note: NTP receipt date by contractor is Jan.3, 2025 | Cyrus James Builders and Supply | [15 empty] | 75% |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Koronadal City | 306088 | GOVERNOR SERGIO B. MORALES NATIONAL HIGH SCHOOL | CITY OF KORONADAL (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 2678370.67 | 1 | 1988744.22 | COMPLETED | 100% | 2024-08-008 | 2024-10-013 | 45527 | 45537 | 2024-09-18 | 2024-10-01 | 2024-10-10 | VYS Construction | [15 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region XII | South Cotabato | 130865 | Tampakan Central Elementary School | TAMPAKAN | 1st | 1 | 11 | Repair of Classrooms | 8255807.78 | 1 |  | under procurement | 0% | [8 empty] | Awaiting SARO Release | [14 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region XII | South Cotabato | 130873 | Luayan Elementary School | TANTANGAN | 2nd | 1 | 8 | Repair of Classrooms | 6004223.84 | 1 |  | under procurement | [9 empty] | Awaiting SARO Release | [14 empty] | 0% | [7 empty] | under procurement
REPAIR 2024 | Region XII | Sultan Kudarat | 130972 | Libertad Elementary School | COLUMBIO | 1st | 1 | 8 | Repair of Classrooms | 6038289.23 | 1 | 4233166.12 | Ongoing | 81% | 24-11-027-lot 1 | 24-11-027-01 | Nov. 12, 2024 | Nov. 20, 2024 | Dec. 02, 2024 | Dec. 10, 2024 | Jan. 06, 2024 | Johnray Developer and Supplies | [15 empty] | 81% | [7 empty] | ongoing
REPAIR 2024 | Region XII | Sultan Kudarat | 131190 | Milbuk Central Elementary School | PALIMBANG | 2nd | 1 | 10 | Repair of Classrooms | 8898594.63 | 1 | 6333338.12 | Ongoing | 68% | 24-11-027-lot 2 | 24-11-027-02 | Nov. 12, 2024 | Nov. 20, 2024 | Dec. 02, 2024 | Dec. 10, 2024 | Jan. 06, 2024 | Johnray Developer and Supplies | [15 empty] | 68% | [7 empty] | ongoing
REPAIR 2024 | Region XII | Tacurong City | 131231 | J. Hector Lacson Elementary School | CITY OF TACURONG | 1st | 1 | 2 | Repair of Classrooms | 1717500.94 | 1 | 1203652.48 | COMPLETED | 100% | IP - 001 - 2024 |  | 45477 | 45485 | 2024-07-24 | 2024-07-26 | 2024-10-30 | Gabriellas Enterprises |  | Gabriellas Enterprises | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region XII | Tacurong City | 131228 | San Rafael ES | CITY OF TACURONG | 1st | 1 | 11 | Repair of Classrooms | 6931017.79 | 1 | 4813184.74 | COMPLETED | 100% | IP - 001 - 2024 |  | 45477 | 45485 | 2024-07-24 | 2024-07-26 | 2024-10-30 | Gabriellas Enterprises |  | Gabriellas Enterprises | [13 empty] | 100% |  |  | 2.25 |  |  |  |  | Completed

## Sheet1 (hidden)
Sum of No. of CL Completed | Column Labels
Row Labels | 1.25 | 2.25 | 3.25 | Grand Total
REPAIR 2023 | 269 | 94 | 143 | 506
CAR |  |  | 4 | 4
NCR | 191 | 43 |  | 234
Region I | 6 |  |  | 6
Region II | 3 | 11 |  | 14
Region III | 56 |  | 14 | 70
Region IV-B |  | 4 |  | 4
Region IX |  | 10 |  | 10
Region VI | 13 | 17 |  | 30
Region VII |  |  | 125 | 125
Region X |  | 9 |  | 9
REPAIR 2024 | 159 | 137 | 213 | 509
NCR | 20 |  | 6 | 26
Region I | 33 |  |  | 33
Region II | 7 | 46 | 22 | 75
Region III | 37 |  | 18 | 55
Region IV-A | 8 |  | 30 | 38
Region IV-B | 25 | 28 |  | 53
Region IX | 25 |  | 12 | 37
Region VI |  | 38 |  | 38
Region VII |  |  | 80 | 80
Region X |  | 8 | 26 | 34
Region XI | 4 |  | 19 | 23
Region XII |  | 17 |  | 17
Grand Total | 428 | 231 | 356 | 1015