## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2017 | CAR | Abra | 135027 | Benben PS | LA PAZ | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 456305.94 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135076 | Pacoc ES | LACUB | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 892219 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135214 | Lukgay PS | LAGAYAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 198244.95 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135117 | Tukipa PS | LUBA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 405290.61 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 134996 | Liagan PS | MANABO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 219559.98 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 218519 | Tattawa PS | PEÑARRUBIA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 254540.88 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135186 | Lam-aoan PS | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1028689.05 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135191 | Nangas-Asan PS | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 465967.53 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135195 | Ud-udiao ES | SALLAPADAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 599527.41 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 329073.96 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Abra | 135196 | Alawa ES | TINEG | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 364334.71 |  | COMPLETED | 1 | [9 empty] | www Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Benguet | 219529 | Cadsi-Amoy ES - Poway Annex | BAKUN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 174192.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135750 | Haitan PS | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 286085.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135759 | Nepojnoc PS | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 234895.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135761 | Talite Primary School | AGUINALDO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 434246.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135766 | Busilac ES | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 802683.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135773 | Laya ES | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835389.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 220011 | Maligaya PS | ALFONSO LISTA (POTIA) | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 401332.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 319006 | Banaue NHS Extension | BANAUE | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 537965.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135838 | Kayang PS | HINGYON | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 311555.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 925056.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 940908.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Ifugao | 135937 | Nattum PS (Proper) | MAYOYAO | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 245847.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135965 | Bassao PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231941.93 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135966 | Bayowong PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 680800.49 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135968 | Bonong Community School | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 351309.51 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135969 | Buaya ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 483534.77 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135970 | Bullalayao PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92771.34 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135975 | Kabugao ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 480823.46 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135977 | Mabaca ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 445017.81 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135985 | Tawang ES | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 600152.85 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135986 | Ubual PS | BALBALAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477185.26 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135988 | Colong PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 92038.13 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135990 | Dugnac PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 145589.59 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 135991 | Latawan PS | LUBUAGAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 60030.07 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136020 | Cagaluan ES Annex (Da-o PS) | PASIL | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 90008.33 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136021 | Cagaluan ES Annex (Putao PS) | PASIL | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 75019.41 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220527 | Aguimitan PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 112190.04 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220511 | Baclas PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 145546.34 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136036 | Ballayangon ES | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 115317.67 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136037 | Bonnong PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 680998.83 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220516 | Coddog PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110076.5 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136051 | Liplipoken PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 140168.49 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136060 | Sagsag PS | PINUKPUK | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 393590.64 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136116 | Baclayam ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 165143.57 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136121 | Darulog ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 146393.25 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136125 | Liyang ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 90084.87 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 220509 | Magtoma PS | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 110504.51 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Kalinga | 136128 | Pangol ES | TANUDAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 144802.45 |  | COMPLETED | 1 | [9 empty] | WWW CONSCTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136272 | Nabhar PS | NATONIN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 518252.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136274 | Pangtor PS | NATONIN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 420817.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136281 | Addang ES | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 431600.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 319226 | Bacarri National Trade Agricultural High School-Bunot Extension | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 403508.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136286 | Bagabag Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 389551.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136291 | Camparadi Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 471192.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136294 | Catao Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 320237.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 221002 | Catubangan PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 267892.43 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 221009 | Damsite PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 153581.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136299 | Gassilang PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1574032.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136301 | Kalao PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 572634.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136305 | Makilo Elementary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 494337.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136306 | Marallag Primary School | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 267148.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136308 | Natta'Longan PS | PARACELIS | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 409013.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 409013.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 319223 | Lubon NHS - Mabalite Extension | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 280934 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | CAR | Mt. Province | 136378 | Vicente Pe ES | TADIAN | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 260832.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | 0 | 1 | UPGRADING | 1 | 825727.12 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | 0 | 1 | UPGRADING | 1 | 807054.31 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305105 | Western Abra NHS | DANGLAS | 0 | 1 | UPGRADING | 1 | 1001258.48 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | 0 | 1 | UPGRADING | 1 | 1221450.81 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | UPGRADING | 1 | 1177438.05 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305102 | Tagodtod NHS | LAGANGILANG | 0 | 1 | UPGRADING | 1 | 1168924.11 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305094 | Pulot NHS | LAGAYAN | 0 | 1 | UPGRADING | 1 | 1162253.81 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | UPGRADING | 1 | 1794998.25 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 | 1 | UPGRADING | 1 | 1072964.35 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | 0 | 1 | UPGRADING | 1 | 729023.16 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | UPGRADING | 1 | 713435.55 |  | COMPLETED | 1 | [9 empty] | www. Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318811 | PIO DALIM Memorial SAT-Sta.Filomena | CALANASAN (BAYAG) | 0 | 1 | UPGRADING | 1 | 886166.84 | 908090.3 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318803 | Conner Central NHS Cupis Annex | CONNER | 0 | 1 | UPGRADING | 1 | 826570.72 | 796851.23 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318812 | Conner Central NHS Ili Annex | CONNER | 0 | 1 | UPGRADING | 3 | 1253305.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318802 | Conner Central NHS Talifugo Annex | CONNER | 0 | 1 | UPGRADING | 3 | 1282984.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135259 | Conner Central School | CONNER | 0 | 1 | UPGRADING | 3 | 976624.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305112 | Conner Natl. HS | CONNER | 0 | 1 | UPGRADING | 3 | 1317860.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305114 | Gov. Benjamin Leguiab, Sr. Mem. NHS Main | CONNER | 0 | 1 | UPGRADING | 3 | 1162205.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 219020 | Mabiga Elementary School | CONNER | 0 | 1 | UPGRADING | 3 | 398700.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | UPGRADING | 1 | 823927.98 | 895499.5 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135287 | Balasi Elementary School | FLORA | 0 | 1 | UPGRADING | 3 | 739360.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135289 | Flora CS | FLORA | 0 | 1 | UPGRADING | 3 | 1214859.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 | 1 | UPGRADING | 1 | 1199958.86 | 1156657.37 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135294 | Mallig ES | FLORA | 0 | 1 | UPGRADING | 3 | 723531.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 | 1 | UPGRADING | 1 | 767937.37 | 988685.78 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS Main | KABUGAO (Capital) | 0 | 1 | UPGRADING | 1 | 1026403.1 | 1074016.92 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305107 | Apayao Science HS | LUNA | 0 | 1 | UPGRADING | 1 | 929638.03 | 1239931.36 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | 0 | 1 | UPGRADING | 2 | 952154.67 | 922980.49 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135336 | Luna CS | LUNA | 0 | 1 | UPGRADING | 3 | 1314374.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305116 | Luna National High School Main | LUNA | 0 | 1 | UPGRADING | 1 | 933340.55 | 725415.93 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | UPGRADING | 2 | 998955.38 | 961612.22 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | UPGRADING | 2 | 879844.34 | 851601.82 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135356 | Mataguisi ES | PUDTOL | 0 | 1 | UPGRADING | 3 | 513708.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 135357 | Pudtol CS | PUDTOL | 0 | 1 | UPGRADING | 3 | 1415078.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | UPGRADING | 1 | 1284282.48 | 849654 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318810 | Swan National Agricultural and Trade High School | PUDTOL | 0 | 1 | UPGRADING | 3 | 1224974.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | 0 | 1 | UPGRADING | 3 | 1280614.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305120 | Mayor Guillermo Barsalan SAT | SANTA MARCELA | 0 | 1 | UPGRADING | 1 | 1119970.26 | 799643.44 | COMPLETED | 1 | November 8, 2018 |  |  |  | April 18 2018 | April 30, 2018 | May 15, 2018 | June 22, 2018 | July 9, 2018 | JUA ELECTRICAL SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | 0 | 1 | UPGRADING | 3 | 1368646.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 5037080.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305269 | Baguio City National High School - Main | BAGUIO CITY | 0 | 1 | UPGRADING | 1 | 5343246.78 | 5314182.16 | COMPLETED | 1 | Sept. 8, 2018 |  |  |  | 2018-04-26 | 2018-05-04 | 2018-05-18 | 2018-05-22 | 2018-06-08 | www.construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136388 | Elpidio R. Quirino Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4795287.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4182575.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 4892682 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3894208.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 136417 | SPED Center (FL) | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3136655.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | UPGRADING | 2 | 3283387.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305129 | Atok NHS | ATOK | 0 | 1 | UPGRADING | 1 | 1128082.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318913 | Ampusongan NHS - Kayapa Ext. | BAKUN | 0 | 1 | UPGRADING | 1 | 1036761.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318901 | Bokod NHS - Daclan Extension | BOKOD | 0 | 1 | UPGRADING | 1 | 1123051.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305134 | Binga NHS | ITOGON | 0 | 1 | UPGRADING | 1 | 1120443.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305159 | Fianza Mem'l NHS - Tinongdan | ITOGON | 0 | 1 | UPGRADING | 1 | 1163516.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305142 | Laurencio Fianza National High School | ITOGON | 0 | 1 | UPGRADING | 1 | 1184835.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305146 | Adaoay National High School | KABAYAN | 0 | 1 | UPGRADING | 1 | 1183986.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 318908 | Gov. Bado Dangwa Agro-Industrial School Extension - Taba-ao Annex | KAPANGAN | 0 | 1 | UPGRADING | 1 | 1139374.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305147 | Kapangan Central NHS (RA8841) | KAPANGAN | 0 | 1 | UPGRADING | 1 | 1022559.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305154 | MADAYMEN NATIONAL HIGH SCHOOL | KIBUNGAN | 0 | 1 | UPGRADING | 1 | 1147876.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305140 | Cordillera Regional Science HS | LA TRINIDAD (Capital) | 0 | 1 | UPGRADING | 1 | 1004906.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305156 | Bulalacao NHS | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1134226.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305139 | Cabiten NHS (RA9087) | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1130157.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305144 | Guinaoang NHS | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1147228.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305155 | Mankayan National High School | MANKAYAN | 0 | 1 | UPGRADING | 1 | 1167917.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305157 | Sablan NHS | SABLAN | 0 | 1 | UPGRADING | 1 | 1162986.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Benguet | 305160 | Tuba NHS (Nangalisan) | TUBA | 0 | 1 | UPGRADING | 1 | 1147313.78 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305171 | Eastern Potia National High School | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 1679924.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305187 | Namillangan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 2203262.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 1552581.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305190 | Sta. Maria NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | 1 | 2725220.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305173 | Haliap NHS | ASIPULO | 0 | 1 | UPGRADING | 2 | 2115765.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 319001 | Bangbang National High School | HUNGDUAN | 0 | 1 | UPGRADING | 2 | 1968987.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 | 1 | UPGRADING | 2 | 1619239.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | 0 | 1 | UPGRADING | 2 | 1450065.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305177 | Hapid NHS - Bimpal Annex | LAMUT | 0 | 1 | UPGRADING | 1 | 1410957.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | UPGRADING | 2 | 1676892.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305183 | Lawig NHS | LAMUT | 0 | 1 | UPGRADING | 1 | 1692354.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Ifugao | 305192 | Tinoc NHS | TINOC | 0 | 1 | UPGRADING | 2 | 1443313.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | UPGRADING | 1 | 2442507.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305223 | Lubuagan National High School | LUBUAGAN | 0 | 1 | UPGRADING | 1 | 784163.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 340131 | SHS - Lubuagan | LUBUAGAN | 0 | 1 | UPGRADING | 1 | 979846.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 | 1 | UPGRADING | 1 | 1792826.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305201 | Cal-owan Agricultural Vocational National High School | PINUKPUK | 0 | 1 | UPGRADING | 1 | 1088979.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305216 | Pinukpuk Vocational School | PINUKPUK | 0 | 1 | UPGRADING | 1 | 1895776.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305218 | Macutay-Palao National High School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | 1 | 1090872.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305217 | Rizal National School of Arts & Trades | RIZAL (LIWAN) | 0 | 1 | UPGRADING | 1 | 2016943.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305211 | Magtoma Pangol NHS-Main | TANUDAN | 0 | 1 | UPGRADING | 1 | 967916.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305220 | Bangad National High School | TINGLAYAN | 0 | 1 | UPGRADING | 1 | 1506409.43 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Kalinga | 305208 | Southern Tinglayan National High School | TINGLAYAN | 0 | 1 | UPGRADING | 1 | 984873.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 | 1 | UPGRADING | 1 | 1559940.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305244 | Guinzadan National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1722122.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305252 | Mt. Data National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1255178.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305259 | Otucan-Bila National High School | BAUKO | 0 | 1 | UPGRADING | 1 | 1195926.78 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305237 | Besao National High School | BESAO | 0 | 1 | UPGRADING | 1 | 703212.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305260 | Panabungen School of Arts, trades, and Home Industries | BESAO | 0 | 1 | UPGRADING | 1 | 1490662.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 | 1 | UPGRADING | 1 | 1648360.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 340155 | Natonin SHS_Stand Alone | NATONIN | 0 | 1 | UPGRADING | 1 | 943990.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 | 1 | ELECTRIFICATION OF SCHOOLS ON-GRID | 1 | 1351919.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305230 | Bacarri National Trade & Agricultural School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1297230.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305239 | Butigue National High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1396732.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305261 | Paracelis National High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1637975.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | 0 | 1 | UPGRADING | 1 | 1913096.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | 0 | 1 | UPGRADING | 1 | 1121246.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305263 | Sabangan National High School | SABANGAN | 0 | 1 | UPGRADING | 1 | 1691013.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305264 | Sadanga National High School | SADANGA | 0 | 1 | UPGRADING | 1 | 1041709.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305266 | Ankileng NHS (Suyo NHS) | SAGADA | 0 | 1 | UPGRADING | 1 | 1041024.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | 0 | 1 | UPGRADING | 1 | 923929.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305240 | Cagubatan National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1035377.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305247 | Lubon National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1055606.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305251 | Masla National High School | TADIAN | 0 | 1 | UPGRADING | 1 | 1022374.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Mt. Province | 305267 | Tadian School of Arts & Trades | TADIAN | 0 | 1 | UPGRADING | 1 | 2542733.34 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 1437535.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1737997.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1566626.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 2823729.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305212 | Nambaran Agro-Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 1471209.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305222 | New Tanglag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 2 | 1321850.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | 1 | 3248280.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 | UPGRADING |  | 992187.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305078 | Boliney NHS | BOLINEY | 0 | 1 | UPGRADING |  | 1108709.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | UPGRADING |  | 1318849.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305089 | Luzong NHS | LUBA | 0 | 1 | UPGRADING |  | 1381279.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | 0 | 1 | UPGRADING |  | 1672920.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 305083 | Dalit National High School | PILAR | 0 | 1 | UPGRADING |  | 1330923.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135128 | San Isidro CS | SAN ISIDRO | 0 | 1 | UPGRADING |  | 1336675.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135115 | Tubo CS | TUBO | 0 | 1 | UPGRADING |  | 1282350.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Abra | 135167 | Villaviciosa CS | VILLAVICIOSA | 0 | 1 | UPGRADING |  | 1448062.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 4251489.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135230 | Butao ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 1441786.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135231 | Cadaclan ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 1431233.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305110 | Calanasan NHS | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135235 | Langnao Elementary School | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 388147.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135239 | Milagrosa ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2128382.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135242 | Namaltugan ES | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2144211.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 318804 | Tanglagan national high school | CALANASAN (BAYAG) | 0 | 1 | SOLAR PANEL | Batch 3 | 2846637.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135252 | Allangigan ES | CONNER | 0 | 1 | SOLAR PANEL | Batch 3 | 1441786.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 0 | 1 | UPGRADING | Batch 2 | 1152968.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135296 | Upper Atok ES | FLORA | 0 | 1 | SOLAR PANEL | Batch 3 | 367042.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 135316 | Kalliat Elementary School | KABUGAO (Capital) | 0 | 1 | SOLAR PANEL | Batch 3 | 739360.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305119 | Mayor Bartolome Serut NATHS-Main | KABUGAO (Capital) | 0 | 1 | SOLAR PANEL | Batch 3 | 1447062.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 219009 | Lydia ES | PUDTOL | 0 | 1 | SOLAR PANEL | Batch 3 | 739360.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Apayao | 305109 | Sta. Marcela NHS | SANTA MARCELA | 0 | 1 | UPGRADING | Batch 2 | 1250284.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136403 | Apolinario Mabini ES | BAGUIO CITY | 0 | 1 | UPGRADING |  | 4509480.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305269 | Baguio City High School - Main | BAGUIO CITY | 0 | 1 | UPGRADING |  | 5022787.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305282 | Guisad Valley National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 5141432.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 2799253.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136413 | Loakan Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3789756.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136394 | Lucban Elementary school | BAGUIO CITY | 0 | 1 | UPGRADING |  | 4741551.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 305281 | Pines City National High School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3198941.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | 0 | 1 | UPGRADING |  | 3791913.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135372 | Adoyunan ES | ATOK | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135374 | Bilis Elementary School | ATOK | 0 | 1 | UPGRADING | Batch 3 | 443616.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135375 | Boneng ES | ATOK | 0 | 1 | UPGRADING | Batch 1 | 446782.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135400 | Ampusongan Elementary School | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135401 | Bagtangan ES | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135399 | Labinio-Mariano ES | BAKUN | 0 | 1 | UPGRADING | Batch 1 | 444671.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135434 | Bisal ES | BOKOD | 0 | 1 | UPGRADING | Batch 3 | 445727.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135442 | Karao ES | BOKOD | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135447 | Naswak ES | BOKOD | 0 | 1 | UPGRADING | Batch 1 | 477385.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135457 | Abatan ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135459 | Alapang ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135460 | Amgaleyguey PS | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135461 | Amlimay ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135463 | Bacasen-Wakit ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451002.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135464 | Bad-ayan ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 448892.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135466 | Bangao Moreno ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 448892.93 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135468 | Bano-oy ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 3 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135469 | Bayoyo-Lukingan-Awal ES | BUGUIAS | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135501 | Baguio Gold Elementary School | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135502 | Binga ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135504 | Botic ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135505 | Gumatdang ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 999019.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135508 | Loacan ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135500 | Maximino Fianza Lopez ES | ITOGON | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135539 | Adaoay ES | KABAYAN | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135562 | Balakbak ES | KAPANGAN | 0 | 1 | UPGRADING | Batch 1 | 445727.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135563 | Beleng-Belis Barrio School | KAPANGAN | 0 | 1 | UPGRADING | Batch 3 | 445727.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135565 | Boklaoan ES | KAPANGAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135633 | Talinguroy ES | LA TRINIDAD (Capital) | 0 | 1 | UPGRADING | Batch 3 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135636 | Am-am ES | MANKAYAN | 0 | 1 | UPGRADING | Batch 1 | 453114.04 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135641 | Baguyos PS | MANKAYAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135673 | Bayabas MG School | SABLAN | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135672 | Omas Ampaguey ES | SABLAN | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135686 | Asin ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 444671.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135687 | Batuan ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135688 | Camp 3 ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135689 | Camp 4 ES | TUBA | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135718 | Albis ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135719 | Ambongdolan ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 451003.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135720 | Baayan ES | TUBLAY | 0 | 1 | UPGRADING | Batch 1 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | 0 | 1 | UPGRADING | Batch 3 | 442561.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135740 | Aguinaldo Central School | AGUINALDO | 0 | 1 | UPGRADING | Batch 3 | 1095258.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305166 | Aguinaldo NHS | AGUINALDO | 0 | 1 | UPGRADING | Batch 3 | 1000900 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319002 | Rufino I. Chungalao Science HS | AGUINALDO | 0 | 1 | UPGRADING | Batch 1 | 928926.95 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305194 | Ubao National High School | AGUINALDO | 0 | 1 | UPGRADING | Batch 1 | 1501140.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135763 | Alfonso Lista CS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | Batch 3 | 1403195.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305189 | Caragasan NHS | ALFONSO LISTA (POTIA) | 0 | 1 | UPGRADING | Batch 1 | 1088862.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | 0 | 1 | UPGRADING | Batch 1 | 1756050.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135788 | Asipulo CS | ASIPULO | 0 | 1 | UPGRADING | Batch 3 | 707990.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305175 | Camandag NHS | ASIPULO | 0 | 1 | UPGRADING | Batch 3 | 1003631.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135813 | Banaue CS | BANAUE | 0 | 1 | UPGRADING |  | 1166975.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305170 | Banaue National High School | BANAUE | 0 | 1 | UPGRADING | Batch 1 | 1219978.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305172 | Gohang NHS | BANAUE | 0 | 1 | UPGRADING |  | 1217067.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135836 | Hingyon CS | HINGYON | 0 | 1 | UPGRADING | Batch 3 | 730337.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305178 | Hingyon NHS | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 1414870.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 340118 | SHS within Namulditan ES | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 859787.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305179 | Southern Hingyon NHS | HINGYON | 0 | 1 | UPGRADING | Batch 1 | 810052.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135855 | Hungduan CS | HUNGDUAN | 0 | 1 | UPGRADING | Batch 3 | 726572.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135871 | Kiangan Central School | KIANGAN | 0 | 1 | UPGRADING | Batch 1 | 1258608.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | 0 | 1 | UPGRADING | Batch 1 | 1414680.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305169 | Caba National High School | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 796168.41 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135887 | Lagawe Central School | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1359033.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319004 | Lagawe NHS | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 3 | 846712.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135891 | Ponghal ES | LAGAWE (Capital) | 0 | 1 | UPGRADING | Batch 1 | 1143534.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 500882 | ALUPAPAN INTEGRATED SCHOOL | LAMUT | 0 | 1 | UPGRADING | Batch 1 | 675569.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135902 | Lamut CS | LAMUT | 0 | 1 | UPGRADING | Batch 3 | 1368574.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 319007 | Lawig National High School Extension | LAMUT | 0 | 1 | UPGRADING | Batch 3 | 581723.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305184 | Mongilit Ligmayo NHS | LAMUT | 0 | 1 | UPGRADING | Batch 1 | 803186.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135934 | Mayoyao Central School | MAYOYAO | 0 | 1 | UPGRADING | Batch 3 | 1135181.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305185 | Mayoyao NHS | MAYOYAO | 0 | 1 | UPGRADING | Batch 1 | 1424577.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305186 | Tulaed NHS | MAYOYAO | 0 | 1 | UPGRADING | Batch 1 | 675856.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 305193 | Kalanguya NHS | TINOC | 0 | 1 | UPGRADING | Batch 1 | 1000900 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | 0 | 1 | UPGRADING | Batch 3 | 1013774.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 135962 | Balbalan Central School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 1263762.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 135985 | Tawang Elementary School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 704039.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | 0 | 1 | UPGRADING | Batch 1 | 1044786.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136019 | Cagaluan Elementary School | PASIL | 0 | 1 | UPGRADING | Batch 1 | 776895.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136032 | Allaguia Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 712552.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305197 | Allaguia National High School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 1575692.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136048 | Magaogao Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 712552.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136056 | Pinococ Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 831588.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136061 | Socbot Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 834443.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 319109 | Socbot National High School | PINUKPUK | 0 | 1 | UPGRADING | Batch 3 | 1541808.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136038 | Wagud Elementary School | PINUKPUK | 0 | 1 | UPGRADING | Batch 1 | 756556 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136065 | Andarayan Elementary School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 3 | 726041.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305209 | Kinama National High School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 1 | 1707703.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136074 | Macutay Elementary School | RIZAL (LIWAN) | 0 | 1 | UPGRADING | Batch 3 | 861477.7 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 220509 | Magtoma Elementary School | TANUDAN | 0 | 1 | UPGRADING | Batch 3 | 585916.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136134 | Bangad Elementary School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 721009.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 136145 | Luplupa Elementary School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 787014.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Kalinga | 305219 | Sumadel National High School | TINGLAYAN | 0 | 1 | UPGRADING | Batch 1 | 1154886.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136185 | Barlig Central School | BARLIG | 0 | 1 | UPGRADING | Batch 3 | 817110.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136187 | KALEO ELEMENTARY SCHOOL | BARLIG | 0 | 1 | UPGRADING | Batch 3 | 895939.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136199 | Bagnen Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 840525.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305232 | Bagnen National High School | BAUKO | 0 | 1 | UPGRADING |  | 968605.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136198 | Bagnen Oriente Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 858186.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | 0 | 1 | UPGRADING |  | 923473.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305249 | Bansa National High School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 818364.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136202 | Bauko Central School | BAUKO | 0 | 1 | UPGRADING |  | 817110.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136204 | Bila Elementary School | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 818364.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136205 | Binaka ES | BAUKO | 0 | 1 | UPGRADING | Batch 3 | 817110.13 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305248 | Mabaay National High School | BAUKO | 0 | 1 | UPGRADING |  | 906852.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136231 | Tapapan Elementary School | BAUKO | 0 | 1 | UPGRADING |  | 818364.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305254 | Tipunan National High School | BAUKO | 0 | 1 | UPGRADING |  | 802231.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136234 | Banguitan Elementary School | BESAO | 0 | 1 | UPGRADING |  | 840525.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136244 | Panabungen Elementary School | BESAO | 0 | 1 | UPGRADING |  | 971201.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319208 | Tamboan National High School | BESAO | 0 | 1 | UPGRADING |  | 852145.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305228 | Albago National High School | BONTOC (Capital) | 0 | 1 | UPGRADING | Batch 3 | 694164.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136270 | Layog-Ogtong Elementary School | NATONIN | 0 | 1 | UPGRADING | Batch 3 | 967491.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | 0 | 1 | UPGRADING | Batch 3 | 1022357.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136277 | Saliok Elementary School | NATONIN | 0 | 1 | UPGRADING |  | 874004.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319209 | Buringal National High School | PARACELIS | 0 | 1 | UPGRADING |  | 939565.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319202 | San Rafael National High School | PARACELIS | 0 | 1 | UPGRADING |  | 884625.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136321 | Lagan Elementary School | SABANGAN | 0 | 1 | UPGRADING |  | 852948.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136324 | Namatec Elementary School | SABANGAN | 0 | 1 | UPGRADING |  | 879716.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136328 | Sabangan Central School | SABANGAN | 0 | 1 | UPGRADING | Batch 3 | 759448.12 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | 0 | 1 | UPGRADING |  | 960056.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 305229 | Antadao National High School | SAGADA | 0 | 1 | UPGRADING | Batch 3 | 819945.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136357 | Banaao Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 850750.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136362 | Cagubatan Elementary School | TADIAN | 0 | 1 | UPGRADING | Batch 3 | 821542.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136369 | Lubon Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 818364.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | 0 | 1 | UPGRADING |  | 1031773.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136085 | Agbannawag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1397703.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136000 | Appas Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1431378.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 1434875.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 3208494.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136004 | Casigayan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1459106.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136009 | Magsaysay Elementary School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1456894.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136089 | Southern Tabuk CS | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1459259.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 3208494.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | UPGRADING |  | 1617645.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 134975 | Sinalang Pilot ES | BANGUED (Capital) | 0 | 1 |  |  | 2325119.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 134989 | Bucay CS | BUCAY | 0 | 1 |  |  | 2530994.45 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | 0 | 1 |  |  | 3124480.97 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305085 | Dugong National High School | BUCAY | 0 | 1 |  |  | 2205406.49 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | 0 | 1 |  |  | 2754618.97 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | 0 | 1 |  |  | 1941154.08 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 135163 | Pilar CS | PILAR | 0 | 1 |  |  | 2843351.03 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 | 1 |  |  | 3450379.29 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-027 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 500518 | Ananaao Integrated School | TAYUM | 0 | 1 |  |  | 2416943.12 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305086 | Gaddani NHS | TAYUM | 0 | 1 |  |  | 2095457.75 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 |  |  | 2294929.15 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Abra | 305103 | Tiempo NHS | TUBO | 0 | 1 |  |  | 2052137.17 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-ABRA-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 318807 | GUINA-ANG NATIONAL HIGHSCHOOL | CONNER | 0 | 1 |  |  | 1946390.46 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-APAYAO-07 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 135270 | Manag ES | CONNER | 0 | 1 |  |  | 1932634.32 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-APAYAO-06 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 135335 | Dagupan ES | LUNA | 0 | 1 |  |  | 1898669.32 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-APAYAO-02 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Apayao | 219023 | AURORA ELEMENTARY SCHOOL | PUDTOL | 0 | 1 |  |  | 1507195.69 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-APAYAO-04 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305271 | Bakakeng National High School | BAGUIO CITY | 0 | 1 |  |  | 3536740.13 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136400 | Dona Aurora Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4194111.6 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305283 | Magsaysay National High School | BAGUIO CITY | 0 | 1 |  |  | 3600644.7 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4010117.36 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305286 | PINGET NATIONAL HIGH SCHOOL | BAGUIO CITY | 0 | 1 |  |  | 3478361.02 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 136387 | Quezon Hill Elementary School | BAGUIO CITY | 0 | 1 |  |  | 4287937.2 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | 0 | 1 |  |  | 3835888.09 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-BAGUIO CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 305128 | AMPUSONGAN NATIONAL HIGH SCHOOL | BAKUN | 0 | 1 |  |  | 1148722.67 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135400 | AMPUSONGAN ELEMENTARY SCHOOL | BAKUN | 0 | 1 |  |  | 1376458.67 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135474 | BUYACAOAN ELEMENTARY SCHOOL | BUGUIAS | 0 | 1 |  |  | 921858.9 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 318903 | TAWANGAN-LUSOD NATIONAL HIGH SCHOOL | KABAYAN | 0 | 1 |  |  | 814995.99 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135569 | DATAKAN ELEMENTARY SCHOOL | KAPANGAN | 0 | 1 |  |  | 1008841.81 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135577 | Lomon ES | KAPANGAN | 0 | 1 |  |  | 1228139.29 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135578 | LONGBOY ELEMENTARY SCHOOL | KAPANGAN | 0 | 1 |  |  | 1437244 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 318916 | BENGUET NATIONAL HIGHSCHOOL ANNEX - PUGUIS | LA TRINIDAD | 0 | 1 |  |  | 1832563.75 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135623 | BUYAGAN ELEMENTARY SCHOOL | LA TRINIDAD | 0 | 1 |  |  | 2144617.49 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135624 | LA TRINIDAD CENTRAL SCHOOL | LA TRINIDAD | 0 | 1 |  |  | 2562477.97 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 135737 | TUBLAY CENTRAL ELEMENTARY SCHOOL | TUBLAY | 0 | 1 |  |  | 1385694.8 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Benguet | 305164 | TUBLAY SCHOOL OF HOME INDUSTRIES EXTENSION - CENTRAL | TUBLAY | 0 | 1 |  |  | 2134596.13 |  | COMPLETED | 1 |  |  | ELEC 2020 - CAR - BENGUET - 030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135776 | Namillangan ES | ALFONSO LISTA (POTIA) | 0 | 1 |  |  | 889922.77 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135854 | Hapao ES | HUNGDUAN | 0 | 1 |  |  | 855129.65 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 305180 | Hungduan National High School | HUNGDUAN | 0 | 1 |  |  | 779595 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135880 | Boliwong ES | LAGAWE (Capital) | 0 | 1 |  |  | 888564.87 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135899 | Hapid ES | LAMUT | 0 | 1 |  |  | 905829.18 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Ifugao | 135920 | Balangbang ES | MAYOYAO | 0 | 1 |  |  | 993175.79 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-IFUGAO-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 135964 | BALBALASANG ELEMENTARY SCHOOL | BALBALAN | 0 | 1 | UPGRADING |  | 2121606.84 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 135978 | PANTIKIAN ELEMENTARY SCHOOL | BALBALAN | 0 | 1 | UPGRADING |  | 1903853.35 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | 0 | 1 | UPGRADING |  | 1185308.31 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136040 | Camalog Elementary School | PINUKPUK | 0 | 1 | UPGRADING |  | 1571899.4 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 305202 | Cawagayan National High School | PINUKPUK | 0 | 1 | UPGRADING |  | 1901551.09 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 136050 | Malagnat Elementary School | PINUKPUK | 0 | 1 | UPGRADING |  | 1165665.29 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 319103 | Tappo Vocational High School | PINUKPUK | 0 | 1 | UPGRADING |  | 1208434.9 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Kalinga | 305224 | Tanudan National High School | TANUDAN | 0 | 1 | UPGRADING |  | 1092110.71 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-KALINGA-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305235 | BARLIG NATIONAL HIGH SCHOOL | BARLIG | 0 | 1 |  |  | 2505211.2 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136203 | BEBE ELEMENTARY SCHOOL | BAUKO | 0 | 1 |  |  | 1340937.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136210 | Guinzandan Norte Elementary School | BAUKO | 0 | 1 |  |  | 1496193.22 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305250 | LESEB NATIONAL HIGH SCHOOL | BAUKO | 0 | 1 |  |  | 1217330.66 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-033 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136214 | LETANG ELEMENTARY SCHOOL | BAUKO | 0 | 1 |  |  | 1447809.04 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305245 | TAPAPAN NATIONAL HIGH SCHOOL | BAUKO | 0 | 1 |  |  | 2200700.78 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319225 | AGAWA NATIONAL HIGH SCHOOL | BESAO | 0 | 1 |  |  | 1544204.81 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136239 | DANDANAC ELEMENTARY SCHOOL | BESAO | 0 | 1 |  |  | 1175205.75 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-056 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136248 | TAMBUAN ELEMENTARY SCHOOL | BESAO | 0 | 1 |  |  | 1164664.7 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-068 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305243 | GUINAANG NATIONAL HIGH SCHOOL | BONTOC | 0 | 1 |  |  | 2251884.32 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319203 | SALIOK NATIONAL HIGH SCHOOL | NATONIN | 0 | 1 |  |  | 1304043.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136283 | ANONAT ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1109293.72 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-049 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136284 | APALIS ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1627051.48 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-067 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136289 | BUTIGUE ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1378027.96 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136293 | CASSAG ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1382281.03 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | 0 | 1 |  |  | 1356533.94 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-058 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136312 | SAN EMILIO ELEMENTARY SCHOOL | PARACELIS | 0 | 1 |  |  | 1180937.47 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-059 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136332 | ANABEL ELEMENTARY SCHOOL | SADANGA | 0 | 1 |  |  | 1439225.63 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319222 | BALUGAN NATIONAL HIGH SCHOOL | SAGADA | 0 | 1 |  |  | 1645221.87 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-062 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | 0 | 1 |  |  | 1032716.69 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-032 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 305241 | Am-am National High School | TADIAN | 0 | 1 |  |  | 2300796.48 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136358 | BANTEY ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1670514.35 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-071 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319224 | BUNGA NATIONAL HIGH SCHOOL | TADIAN | 0 | 1 |  |  | 2735248.21 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-074 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136361 | CADAD-ANAN ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1078239.63 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 319217 | DACUDAC NATIONAL HIGH SCHOOL | TADIAN | 0 | 1 |  |  | 2541346.68 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136373 | PANDAYAN ELEMENTARY SCHOOL | TADIAN | 0 | 1 |  |  | 1107598.7 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-052 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 |  |  | 1518648.2 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-063 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Mt. Province | 136376 | TADIAN CENTRAL SCHOOL | TADIAN | 0 | 1 |  |  | 1908705.51 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-MT. PROVINCE-075 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305195 | Agbannawag National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2619754.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 136091 | Bulo East Elementary School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2414958.05 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2563438.63 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305196 | Eastern Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1547084.64 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305205 | Kalinga National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2737711.74 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-027 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305212 | Nambaran Agro. Industrial National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 2677613.63 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305207 | Nambucayan National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1548818.55 |  | COMPLETED | 1 |  |  | ELEC 2020-CAR-TABUK CITY-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 220501 | Pa-o ES | CITY OF TABUK (Capital) | 0 | 1 |  |  | 1620958.12 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 |  |  | 3296269.15 |  | COMPLETED | 1 |  |  | ELEC-2020-CAR-TABUK CITY-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305078 | Boliney NHS | BOLINEY | Lone | 1 | Upgrading of Electrical System | 1 | 2573112.03 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135003 | Patoc ES | BUCAY | Lone | 1 | Upgrading of Electrical System | 1 | 2700303.62 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | Lone | 1 | Upgrading of Electrical System | 1 | 2893061.4 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135036 | Manganip ES | DANGLAS | Lone | 1 | Upgrading of Electrical System | 1 | 2515595.69 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135038 | Nagaparan ES | DANGLAS | Lone | 1 | Upgrading of Electrical System | 1 | 2698048.96 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135064 | Lacub CS | LACUB | Lone | 1 | Upgrading of Electrical System | 1 | 2556039.77 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | Lone | 1 | Upgrading of Electrical System | 1 | 3035960.33 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135212 | Lagayan CS | LAGAYAN | Lone | 1 | Upgrading of Electrical System | 1 | 2755098.52 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | Lone | 1 | Upgrading of Electrical System | 1 | 2516605.59 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135046 | Licuan-Baay Central School | LICUAN-BAAY (LICUAN) | Lone | 1 | Upgrading of Electrical System | 1 | 2630426.29 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135105 | Luzong ES | LUBA | Lone | 1 | Upgrading of Electrical System | 1 | 2872212.71 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | Upgrading of Electrical System | 1 | 3403470.89 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | Lone | 1 | Upgrading of Electrical System | 1 | 3111511.93 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2644958.28 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2692850.72 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 2886079.19 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | Upgrading of Electrical System | 1 | 2519635.29 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135144 | San Quintin CS | SAN QUINTIN | Lone | 1 | Upgrading of Electrical System | 1 | 2527039.76 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 2 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135110 | Supo ES | TUBO | Lone | 1 | Upgrading of Electrical System | 1 | 2614068.81 |  | COMPLETED | 1 | 2024-03-13 |  | Lot 1 | INF-2023elec-003 |  | 2023-07-19 | 2023-07-31 | 2023-08-31 | ################ | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2749682.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 501104 | Tuquib Integrated School | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2683393.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Abra | 135167 | Villaviciosa CS | VILLAVICIOSA | Lone | 1 | Upgrading of Electrical System | 1 | 2833196.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135677 | Michael G. Angel Elementary School | SABLAN | Lone | 1 | Upgrading of Electrical System | 1 | 1592741.16 |  | COMPLETED | 1 | [10 empty] | Under 3rd re-procurement-Failed-For Rebidding | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135681 | Sablan CS | SABLAN | Lone | 1 | Upgrading of Electrical System | 1 | 1639418.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135726 | Becday Chasoras Lamsis ES (Baayan ES-Annex) | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1943884.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135725 | Dorencio ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1622500.76 |  | COMPLETED | 1 | [10 empty] | Under Procurement-(For Post Qualification Inspection) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135733 | Paoad ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 3327449.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 135734 | Pontino ES | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 1879395.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Benguet | 305162 | Tublay School of Home Industries | TUBLAY | Lone | 1 | Upgrading of Electrical System | 1 | 6325754.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Ifugao | 135843 | Piwong ES | HINGYON | Lone | 1 | Upgrading of Electrical System | 1 | 2575936.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Kalinga | 136027 | Pasil Central School | PASIL | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2403614.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3026925.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136189 | Lias Elementary School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1544622.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1552384.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136192 | Lunas Primary School | BARLIG | Lone | 1 | Upgrading of Electrical System | 1 | 1213229.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136200 | Banao Elementary School | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 2566648.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136201 | Bansa Elementary School | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 1923975.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136235 | Besao Central School | BESAO | Lone | 1 | Upgrading of Electrical System | 1 | 2943575.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | Lone | 1 | Upgrading of Electrical System | 1 | 3014573.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136314 | Bun-ayan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1111821.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136316 | Capinitan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1358370.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136319 | Gayang Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 961217.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136320 | Labbay Primary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1036764.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136322 | Legleg Primary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 961217.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1839246.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136331 | Tambingan Elementary School | SABANGAN | Lone | 1 | Upgrading of Electrical System | 1 | 1117193.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | Upgrading of Electrical System | 1 | 1105334.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136344 | Antadao Elementary School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 951746.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136346 | Bangaan Elementary School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 1262778.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 305234 | Bangaan National High School | SAGADA | Lone | 1 | Upgrading of Electrical System | 1 | 3308154.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Mt. Province | 136368 | Lenga Elementary School | TADIAN | Lone | 1 | Upgrading of Electrical System | 1 | 1662571.78 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136155 | Bado Dangwa Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3494237.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 319108 | Balong National High School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2929014.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2977893.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4594038.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 501971 | Lacnog Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2881584.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136007 | Laya East Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4036192.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3525638.47 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136108 | Namnama Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 3466143.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 502124 | San Pablo Integrated School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2868127.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | CAR | Tabuk City | 136112 | Tannubong Elementary School | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 2733038.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2024 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | Upgrading of Electrical System | 1 | 4977704.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Apayao | 305122 | Pio Dalim Memorial SAT Main | Calanasan | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4525076.03 |  | COMPLETED | 1 |  |  | 2023-ITB-011 |  | August 12,2024 |  | August 19,2024 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.3 | 0.7 |  | 5.25 | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | CAR | Baguio City | 340055 | BAGUIO CITY NATIONAL SCIENCE HIGHSCHOOL | BAGUIO CITY | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 17088567.41 |  | COMPLETED | 1 | [10 empty] | Suspemded due to Transformer Issue (BENECO cannot still provide) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Benguet | 305143 | Gov. Bado Dangwa Agro-Industrial School | KAPANGAN | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 6325754.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Ifugao | 135799 | Namal ES | ASIPULO | Lone | 1 | Upgrading of Electrical System | 1 | 6148782.53 | 6144549.31 | COMPLETED | 1 | 2024-10-12 |  |  | 2024-05 | 2023-11-28 | 2023-12-05 | 2023-12-18 | 2024-01-02 | 2024-06-08 | MSMV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Kalinga | 136169 | BAGTAYAN ELEMENTARY SCHOOL | PASIL | 1st | 1 | Energization of Electrical System (Overhead System) | 1 | 2562806.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Mt. Province | 136202 | BAUKO CENTRAL SCHOOL | BAUKO | Lone | 1 | Upgrading of Electrical System | 1 | 2924532.38 | 2820821 | COMPLETED | 1 | 2024-08-02 | August 2, 2024 | INFRA-2023-006 | INFRA-2023-006 | 11/25/23 | 2023-04-12 | 12/18/2023 | 2024-08-01 | 2024-07-03 | DMYA Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | CAR | Tabuk City | 136101 | MADOPDOP ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | Energization of Electrical System (Overhead System) | 1 | 4524148.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%