## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | CAR | Abra | 134985 | Abang ES | BUCAY | Lone | 1 |  | Construction of 1 storey 7m x 9m Medical and Denatl Facilities | 2800000 |  | 2777723.92 | Completed | 1 | September 11, 2024 | September 18, 2024 | CAR-ABRA-2024-04-008 | CAR-ABRA-2024-04-008 | April 17, 2024 | April 24, 2024 | May 07, 2024 | May 16, 2024 | July 09, 2024 | SEMBRI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | CAR | Apayao | 501344 | Butao Integrated School | CALANASAN (BAYAG) | Lone | 1 |  | Construction of Handwashing Facility,Comfort Room, and clinic | 5079441.86 |  | 5023658.56 | ongoing | 0 |  |  |  |  | September 17,2024 | Septemebr 25,2024 | October 7,2024 | October 28,2024 |  | HighLand Construction Services
SCHOOL HEALTH FACILITIES 2024 | CAR | Benguet | 305138 | Loo National High School | BUGUIAS | Lone | 1 |  | Construction of Clinic, Comfort Room, Group Handwashing Facility | 4805722.03 |  | 4403550.47 | ongoing | 0.85 | June 11, 2025 |  | SHFP-2024-01 | SHFP-2024-02 | August 06,2024 | August 14,2024 | August 27,2024 | December 18, 2024 | January 16, 2025 | CE-CE CONSTRUCTION SERVICES
SCHOOL HEALTH FACILITIES 2024 | CAR | Ifugao | 305190 | Sta. Maria National High School | ALFONSO LISTA (POTIA) | Lone | 1 |  | Construction of School Clinic, Toilet, Water System & Group Handwashing Facility | 6956039.99 |  | 6250490.52 | completed | 1 | December 25, 2024 | January 22,2025 |  | 2024-01 | December 18, 2023 | January 3, 2024 | January 16, 2024 | January 24, 2024 | May 23, 2024 | Habiling Construction
SCHOOL HEALTH FACILITIES 2024 | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | Lone | 1 |  | Construction of School Clinic | 4458237.06 |  | 4285187.15 | ongoing | 0.85 | November 12, 2024 |  | SCHOOL CLINIC 2024-CAR-KALINGA-001 | SCHOOL CLINIC 2024-CAR-KALINGA-001 | November 24, 2023 | December 4, 2023 | December 18, 2023 | February 6, 2024 | August 14, 2024 | EDEJUN CONSTRUCTION SERVICES
SCHOOL HEALTH FACILITIES 2024 | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 |  | Construction of School Clinic, Water and Sanitation Facilities - 3-Seater with Overhead Water Tank, Group Handwashing Facility and Water System (Water Source at Higher Elevation than School Building) | 21529337.31 |  | 21313820.23 | ongoing | 0.93 | March 2, 2025 |  | INFRA 2023-007 | INFRA 2023-007 | November 25, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | July 5, 2024 | CNL Construction | With time extension
SCHOOL HEALTH FACILITIES 2024 | CAR | Tabuk City | 305926 | BANTAY NATIONAL HIGH SCHOOL | Tabuk City | 1st | 1 |  | Construction of School Clinic | 4565251.4 |  | 4299998.99 | completed | 1 | September 9, 2024 | August 27, 2024 | I-2023-6 | I-2023-6 | December 2 - December 21, 2023 | December 8, 2023 @ 8:00am | December 21, 2023 @ 1pm | January 22, 2024 | May 15, 2024 | Northpine Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 587909.9 | BATCH 1 | 598446.55 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588264.49 | BATCH 1 | 587969.51 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588264.49 | BATCH 1 | 589439.51 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134989 | Bucay Central School | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 219019.24 | BATCH 1 | 589741.66 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 598902.18 | BATCH 1 | 587339.51 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 600675.13 | BATCH 1 | 220931.8 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135208 | Collago ES | LAGAYAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 622624.23 | BATCH 1 | 582396.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135178 | Daguioman CS | DAGUIOMAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221819.91 | BATCH 1 | 561396.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135030 | Danglas CS | DANGLAS | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 594221.59 | BATCH 1 | 218475.37 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135017 | Dolores CS | DOLORES | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 569116.64 | BATCH 1 | 579771.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134994 | Dugong ES | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 580463.51 | BATCH 1 | 573996.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135135 | Garreta ES | PIDIGAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563088.61 | BATCH 1 | 587229.53 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 561670.25 | BATCH 1 | 587229.53 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135064 | Lacub CS | LACUB | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 613085.77 | BATCH 1 | 599829.53 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 565216.15 | BATCH 1 | 630225.46 | Completed | 1 | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 565216.15 | BATCH 1 | 622120.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501115 | LICUAN INTEGRATED SCHOOL | LICUAN-BAAY (LICUAN) | 0 | 1 | 1 | CR/Watsan | 587909.9 | BATCH 1 | 559821.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588635.03 | BATCH 1 | 560871.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 564152.38 | BATCH 1 | 593421.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135105 | Luzong ES | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588633.26 | BATCH 1 | 564546.18 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305089 | Luzong NHS | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588633.26 | BATCH 1 | 568591.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134999 | Madalipay ES | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 574790.07 | BATCH 1 | 222675.37 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 591101.2 | BATCH 1 | 566491.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135071 | Malibcong CS | MALIBCONG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 630815.26 | BATCH 1 | 564339.33 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 582945.64 | BATCH 1 | 612145.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 561670.25 | BATCH 1 | 562270.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 586491.54 | BATCH 1 | 562008.33 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 |  | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223920.42 | BATCH 1 | 562795.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 590037.43 | BATCH 1 | 558963.33 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135041 | San Gregorio ES | LA PAZ | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 560606.48 | BATCH 1 | 587995.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305097 | San Isidro NHS | SAN ISIDRO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563443.2 | BATCH 1 | 587995.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223220.25 | BATCH 1 | 587995.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | 0 |  | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 566989.1 | BATCH 1 | 608554.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135144 | San Quintin CS | SAN QUINTIN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563443.2 | BATCH 1 | 608680.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135110 | Supo ES | TUBO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 609539.87 | BATCH 1 | 585895.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 609539.87 | BATCH 1 | 563635.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 562734.02 | BATCH 1 | 223147.87 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135024 | Tayum Central School | TAYUM | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 559897.3 | BATCH 1 | 562795.83 | Completed | 1 | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135718 | Albis ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135719 | Ambongdolan ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135720 | Baayan ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135723 | Basil ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135673 | Bayabas MG School | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135677 | Michael G. Angel Elementary School | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135672 | Omas Ampaguey ES | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135731 | Palew ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135734 | Pontino ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 129846.85 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135681 | Sablan CS | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 134297.31 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 318915 | Sablan NHS Extension-Balluay | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 |  | Completed | 1 | 2022-12-29 | [7 empty] | 2022-08-01 | PBAJ CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135832 | Anao ES | Hingyon | Lone District | 1 | 1 | PROPOSED NEW CONSTRUCTION OF WATER SYSTEM (Water Source at Higher Elevation than School Building) | 591692.97 | BATCH 1 | 589320.92 | Completed | 1 | 2022-10-22
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135787 | Antipolo ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF WATER SYSTEM | 438803.69 | BATCH 1 | 438803.69 | Completed | 1 | 2022-12-05
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135833 | Bangtinon ES | Hingyon | Lone District | 1 | 1 | PROPOSED REPAIR/REHAB OF GROUP HANDWASHING FACILITY | 160638.45 | BATCH 1 | 160638.45 | Completed | 1 | 2022-11-20
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135797 | Maloy PS | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF GROUP HANDWASHING FACILITY, WATER AND SANITATION FACILITIES AND WATER SYSTEM | 489944.01 | BATCH 1 | 489994.01 | Completed | 1 | 2023-02-03
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135804 | Panubtuban ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR/ REHABILITATION OF GROUP HANDWASHING FACILITY,WATER SYSTEM & TOILET | 336138.97 | BATCH 1 | 335148.19 | Completed | 1 | 2022-12-10
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135805 | Pula ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF GROUP HANDWASHING FACILITY, WATER AND SANITATION FACILITIES AND WATER SYSTEM | 505264.65 | BATCH 1 | 504339.7 | Completed | 1 | 2022-12-25
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 333789.4 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 286547.89 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 294431.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136019 | Cagaluan Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 285351.53 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 297741.25 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136026 | Magsilay Elementary School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 183287.7 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 277236.14 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136344 | Antadao Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260764.31 | BATCH 1 | 255470.23 | Completed | 1 | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136234 | Banguitan Elementary School | Besao | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 217108.12 | BATCH 1 | 213877.03 | Completed | 1 | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136234 | Banguitan Elementary School | Besao | Lone District |  | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 256130.74 | BATCH 1 | 250701.89 | Completed | 1 | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305238 | Betwagan National High School | Sadanga | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 269803.57 | BATCH 1 | 265983.63 | Completed | 1 | 2022-09-04 | 2022-08-19 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136237 | Bunga Elementary School | Besao | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260688.35 | BATCH 1 | 255170.43 | Completed | 1 | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | Barlig | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 799989.82 | BATCH 1 | 791989.92 | Completed | 1 | 2022-09-17 |  | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136348 | Kilong Primary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 266005.56 | BATCH 1 | 263345.5 | Completed | 1 | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305236 | Lias National High School | Barlig | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260688.35 | BATCH 1 | 258081.47 | Completed | 1 | 2022-09-17 |  | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136244 | Panabungen Elementary School | Besao | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - THREE (3) SEATER | 692298.32 | BATCH 1 | 684065.57 | Completed | 1 | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136244 | Panabungen Elementary School | Besao | Lone District |  | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 266765.17 | BATCH 1 | 261711.93 | Completed | 1 | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305262 | Pingad National High School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - TWO (2) SEATER | 253868.26 | BATCH 1 | 252531.2 | Completed | 1 | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - SIX (6) SEATER | 602317.33 | BATCH 1 | 600486.55 | Completed | 1 | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 319219 | Saclit National High School | Sadanga | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 250813.52 | BATCH 1 | 248133.63 | Completed | 1 | 2022-09-04 | 2022-08-08 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305264 | Sadanga National Technical Vocational and Skills Training High School | Sadanga | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FIVE (5) SEATER | 562724.98 | BATCH 1 | 557251.21 | Completed | 1 | 2022-09-04 | 2022-09-02 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136330 | Supang Elementary School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 746156.8 | BATCH 1 | 743340.06 | Completed | 1 | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136247 | Suquib Primary School | Besao | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 247431.03 | BATCH 1 | 243945.99 | Completed | 1 | 2022-09-19 | 2022-09-15 | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136352 | Taccong Primary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 261599.87 | BATCH 1 | 258983.87 | Completed | 1 | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136353 | Tanulong Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260992.19 | BATCH 1 | 258382.27 | Completed | 1 | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136354 | Tetepan Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 250814.49 | BATCH 1 | 248306.74 | Completed | 1 | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136000 | Appas Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 259832.23 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250747.63 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM | 273631.8 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305085 | Dugong National High School | BUCAY | 2 | 1 | 1 | Watsan | 580463.51 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SANITATION FACILITY | 393756.88 | BATCH 2 | 785937.1 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 896699.53 | BATCH 2 | 259798.01 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135249 | Sta. Filomena ES | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 260159.49 | BATCH 2 | 259798.01 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135250 | Tanglagan ES | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 260159.49 | BATCH 2 | 895527.99 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135250 | Tanglagan ES | CALANASAN (BAYAG) | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 896227.03 | BATCH 2 | 587639.92 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135259 | Conner Central School | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 588941.25 | BATCH 2 | 609128.16 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135277 | Ripang ES | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 894385.83 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135277 | Ripang ES | CONNER | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787785.76 | BATCH 2 | 587694.14 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 588941.25 | BATCH 2 | 584495.26 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305112 | Conner National HS | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 586333.57 | BATCH 2 | 609297.46 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135284 | San Jose ES | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 785975.91 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135284 | San Jose ES | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787169.62 | BATCH 2 | 608679.7 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135289 | Flora CS | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610375.18 | BATCH 2 | 785716.79 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135289 | Flora CS | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787393.27 | BATCH 2 | 381960.9 | Completed | 1 |  |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135290 | Flora East CS | FLORA | 2 | 1 | 1 | PROPOSED REPAIR OF WATER SYSTEM | 382406.38 | BATCH 2 | 784641.85 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135290 | Flora East CS | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 786394.72 | BATCH 2 | 608928.86 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610375.18 | BATCH 2 | 784477.37 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 786394.72 | BATCH 2 | 615039.98 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 616779.37 | BATCH 2 | 609481.28 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135336 | Luna CS | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 785646.41 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135336 | Luna CS | LUNA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787393.27 | BATCH 2 | 603804.41 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135346 | Shalom PS | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 605228.76 | BATCH 2 | 603625.28 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135347 | Sta. Lina ES | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 605228.76 | BATCH 2 | 261439.08 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135353 | Dona Loreta ES | PUDTOL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 262784.49 | BATCH 2 | 582748.73 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135355 | Malibang ES | PUDTOL | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 584213.62 | BATCH 2 | 578773.34 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135369 | San Mariano ES | SANTA MARCELA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 580457.02 | BATCH 2 | 392557.16 | Completed | 1 |  |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135371 | Sta. Marcela CS | SANTA MARCELA | 2 | 1 | 1 | PROPOSED REPAIR OF WATER SYSTEM | 393756.88 | BATCH 2 | 783880.82 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135371 | Sta. Marcela CS | SANTA MARCELA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 785778.58 | BATCH 2 | 783880.82 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 262784.49 | BATCH 2 | 261439.08 | Completed | 1 |  |  |  |  | 2022-06-07 | 2022-06-13 | 2022-06-27 |  | 2022-08-24 | ECV Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136006 | Ipil Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136009 | Magsaysay Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136099 | Camp Conrado M. Balweg Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 290189 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136111 | Sotto Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 279689 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136154 | Amlao Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 284939 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 220515 | Basao Isla Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 290189 | BATCH 2 |  | Completed | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%