## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46 | Status as of July 4, 2025
REPAIR 2020 | CAR | Abra | 218506 | Lubong PS | Bangued | 0 | 1 | 3 | Repair of Classrooms | 2127169 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135180 | Danac ES | BOLINEY | 0 | 1 | 2 | Repair of Classrooms | 2010666 | 1 |  | COMPLETED | 1 | [10 empty] | Suspended | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135004 | Quimloong ES | Bucay | 0 | 1 | 5 | Repair of Classrooms | 3067940 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135026 | Abaquid ES | DANGLAS | 0 | 1 | 7 | Repair of Classrooms | 4351892 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135092 | Barit ES | DOLORES | 0 | 1 | 4 | Repair of Classrooms | 3228573 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135017 | Dolores CS | Dolores | 0 | 1 | 15 | Repair of Classrooms | 8219742 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | 0 | 1 | 10 | Repair of Classrooms | 6867519 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135094 | Botot ES | LUBA | 0 | 1 | 5 | Repair of Classrooms | 4900628 | 1 |  | COMPLETED | 1 | [10 empty] | Suspended | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 305088 | Lul-luno NHS | LUBA | 0 | 1 | 8 | Repair of Classrooms | 5926820 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | 0 | 1 | 9 | Repair of Classrooms | 5181879 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135194 | Sal-lapadan CS | Sallapadan | 0 | 1 | 12 | Repair of Classrooms | 5332406 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 218513 | Presentar PS | SAN QUINTIN | 0 | 1 | 2 | Repair of Classrooms | 1057033 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135147 | Tangadan ES | SAN QUINTIN | 0 | 1 | 15 | Repair of Classrooms | 9613341 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 135025 | Velasco ES | Tayum | 0 | 1 | 8 | Repair of Classrooms | 5121658 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 | 8 | Repair of Classrooms | 5894653 | 1 |  | COMPLETED | 1 | [10 empty] | Suspended | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | 0 | 1 | 11 | Repair of Classrooms | 4779563 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135229 | Ayayao PS | CALANASAN (BAYAG) | 0 | 1 | 1 | Repair of Classroom | 539850 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135257 | Caglayan ES | CONNER | 0 | 1 | 10 | Repair of Classroom | 4048005 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135295 | MALUBIBIT NORTE ES | FLORA | 0 | 1 | 5 | Repair of Classrooms | 2309657 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135313 | Lenneng Elementary School | KABUGAO (Capital) | 0 | 1 | 5 | Repair of Classrooms | 2139722 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135300 | Mallag PS | KABUGAO (Capital) | 0 | 1 | 1 | Repair of Classroom | 495224 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Apayao | 135364 | IMELDA ES | STA. MARCELA | 0 | 1 | 4 | Repair of Classrooms | 1693306 | 1 |  | COMPLETED | 1 | [10 empty] | Mobilization | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136403 | Apolinario Mabini ES | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 4613665 | 1 | 10427010.49 | COMPLETED | 1 | 2020-10-14 |  | 007,s.2020 | 007,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | RHOB Construction and Eng'g Services | suspended | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7764059 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305269 | Baguio City High School - Main | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 2136319 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136393 | Bonifacio Elementary school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7827739 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136407 | Crystal Cave Elementary School | BAGUIO CITY | 0 | 1 | 8 | Repair of Classrooms | 3658159 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136410 | Happy Hollow Elementary School | BAGUIO CITY | 0 | 1 | 9 | Repair of Classrooms | 3366825 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | 0 | 1 | 8 | Repair of Classrooms | 3263073 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136413 | Loakan Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 1814359 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136394 | Lucban Elementary school | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 7118721 | 1 | 7786214.99 | COMPLETED | 1 | 2020-07-16 |  | 005,s.2020 | 005,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | RC Pulmano Construction and Supply | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305283 | Magsaysay National High School | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1627041 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136414 | Manuel L. Quezon Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 10353735 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 6073211 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305276 | Rizal National High School | BAGUIO CITY | 0 | 1 | 1 | Repair & Const. of Toilet/Const. of Cooking Area | 1504706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 136417 | SPED Center (FL) | BAGUIO CITY | 0 | 1 | 24 | Repair of Classrooms | 7112285 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1858089 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135372 | Adoyunan ES | ATOK | 0 | 1 | 8 | Repair of Classrooms | 3599230 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135373 | Beckes Pol-oc PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1375047 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135374 | Bilis Elementary School | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1241177 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135381 | Caliking ES | ATOK | 0 | 1 | 5 | Repair of Classroom | 2350065 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135383 | Celo Haight Elementary School | ATOK | 0 | 1 | 2 | Repair of Classrooms | 6430478 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135385 | Dalmacio Miguel PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 924293 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135387 | Englandad PS | ATOK | 0 | 1 | 3 | Repair of Classrooms | 2026193 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135391 | Ja'pa PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1256456 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135392 | Mauro P. Laruan ES | ATOK | 0 | 1 | 4 | Repair of Classrooms | 4048738 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135394 | Oyusan PS | ATOK | 0 | 1 | 2 | Repair of Classrooms | 1402704 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135397 | Topdac ES | ATOK | 0 | 1 | 6 | Repair of Classrooms | 3411204 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 219528 | Batanes Primary School | BAKUN | 0 | 1 | 2 | Repair of Classrooms | 802607 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 219519 | Bakian Guiniawan PS | BOKOD | 0 | 1 | 1 | Repair of Classroom | 1489705 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135440 | Ekip ES | BOKOD | 0 | 1 | 3 | Repair of Classrooms | 1869872 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135467 | Bangsalan-Daganos PS | BUGUIAS | 0 | 1 | 2 | Repair of Classrooms | 1437022 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135479 | Cotcot-Talabis ES | BUGUIAS | 0 | 1 | 2 | Repair of Classrooms | 1381392 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135493 | Pugo James Mocate ES | BUGUIAS | 0 | 1 | 1 | Repair of Classroom | 568823 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135548 | Bashoy ES | KABAYAN | 0 | 1 | 6 | Repair of Classrooms | 2785352 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135557 | Tawangan ES | KABAYAN | 0 | 1 | 4 | Repair of Classrooms | 2618230 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135563 | Beleng-Belis Barrio School | KAPANGAN | 0 | 1 | 2 | Repair of Classrooms | 763854 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135570 | Gadang ES | KAPANGAN | 0 | 1 | 4 | Repair of Classrooms | 2216852 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135594 | Camilo Lucaben ES | KIBUNGAN | 0 | 1 | 9 | Repair of Classrooms | 4073883 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135607 | Polis Barrio School | KIBUNGAN | 0 | 1 | 2 | Repair of Classrooms | 1417025 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135608 | Saddle ES | KIBUNGAN | 0 | 1 | 3 | Repair of Classrooms | 1193559 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135618 | Balukas Elementary School | LA TRINIDAD (Capital) | 0 | 1 | 4 | Repair of Classrooms | 2303221 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135641 | Baguyos PS | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1344446 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135668 | Suyoc ES | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1089718 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135670 | Taneg PS | MANKAYAN | 0 | 1 | 3 | Repair of Classrooms | 1161572 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135673 | Bayabas MG School | SABLAN | 0 | 1 | 3 | Repair of Classrooms | 1931257 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135680 | Pappa MG School | SABLAN | 0 | 1 | 4 | Repair of Classrooms | 1705973 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135683 | Taya MG School | SABLAN | 0 | 1 | 2 | Repair of Classrooms | 2031157 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135698 | Lubas ES | TUBA | 0 | 1 | 5 | Repair of Classrooms | 3671290 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | 0 | 1 | 4 | Repair of Classrooms | 2276761 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135757 | Manaot ES | AGUINALDO | 0 | 1 | 2 | Repair of Classrooms | 1312773 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135773 | Laya ES | ALFONSO LISTA (POTIA) | 0 | 1 | 5 | Repair of Classrooms | 1594777 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135779 | Pinto ES | ALFONSO LISTA (POTIA) | 0 | 1 | 12 | Repair of Classrooms | 4739601 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305188 | Pinto NHS | ALFONSO LISTA (POTIA) | 0 | 1 | 10 | Repair of Classrooms | 3459596 | 1 |  | COMPLETED | 1 | [10 empty] | - Contractor's Fault - (The Division Office Isued a demand letter for the Contarctor to finish all the remaining works before the opening of classes) | [12 empty] | 1 |  | 44621 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135793 | Haliap ES | ASIPULO | 0 | 1 | 8 | Repair of Classroom | 4780869 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135832 | Anao ES | HINGYON | 0 | 1 | 2 | Repair of Classrooms | 767767 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135843 | Piwong ES | HINGYON | 0 | 1 | 9 | Repair of Classrooms | 4452945 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135849 | Baang ES | HUNGDUAN | 0 | 1 | 3 | Repair of Classrooms | 1454283 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135858 | Nungulunan ES | HUNGDUAN | 0 | 1 | 5 | Repair of Classrooms | 2225337 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 135869 | Hucab ES | KIANGAN | 0 | 1 | 9 | Repair of Classrooms | 4287534 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305168 | Ayangan National Agricultural & Vocational HS | LAGAWE (Capital) | 0 | 1 | 10 | Repair of Classrooms | 4958595 | 1 |  | COMPLETED | 1 | [10 empty] | Contractor's Fault- Lack of manpower and Difficult accessibility to the project site during raing season | [12 empty] | 1 |  | 44621 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2020 | CAR | Ifugao | 305181 | Ifugao Prov'l. Science HS | LAMUT | 0 | 1 | 11 | Repair of Classrooms | 6018988 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 305199 | Balbalan Agricultural and Industrial School | BALBALAN | 0 | 1 | 6 | Repair of Classrooms | 4546582 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 319116 | Balbalan National High school | Balbalan | 0 | 1 | 4 | Repair of Classrooms | 1460102 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136026 | Magsilay Elementary School | Pasil | 0 | 1 | 3 | Repair of Classrooms | 1508008 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136031 | Aciga Elementary School | Pinukpuk | 0 | 1 | 8 | Repair of Classrooms | 3405448 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136034 | Asibanglan Elementary School | Pinukpuk | 0 | 1 | 2 | Repair of Classrooms | 443303 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 136050 | Malagnat Elementary School | PINUKPUK | 0 | 1 | 10 | Repair of Classrooms | 5088889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Kalinga | 319103 | Tappo Vocational High School | Pinukpuk | 0 | 1 | 6 | Repair of Classrooms | 2662854 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136199 | Bagnen Elementary School | BAUKO | 0 | 1 | 9 | Repair of Classrooms | 5142350 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | 0 | 1 | 11 | Repair of Classrooms | 3919247 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136201 | Bansa Elementary School | BAUKO | 0 | 1 | 7 | Repair of Classrooms | 2716325 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136204 | Bila Elementary School | BAUKO | 0 | 1 | 8 | Repair of Classrooms | 4090415 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305245 | Tapapan National High School | BAUKO | 0 | 1 | 8 | Repair of Classrooms | 3476351 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305243 | Guinaang National High School | BONTOC (Capital) | 0 | 1 | 9 | Repair of Classrooms | 4351525 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305255 | Mt. Prov. Gen. Comprehensive HS | BONTOC (Capital) | 0 | 1 | 18 | Repair of Classrooms | 6638500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136313 | San Rafael Elementary School | PARACELIS | 0 | 1 | 3 | Repair of Classrooms | 1139865 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136357 | Banaao Elementary School | TADIAN | 0 | 1 | 9 | Repair of Classrooms | 4378194 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 305240 | Cagubatan National High School | TADIAN | 0 | 1 | 11 | Repair of Classrooms | 3805972 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | 0 | 1 | 9 | Repair of Classrooms | 4118352 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136155 | Bado Dangwa ES | CITY OF TABUK (Capital) | 0 | 1 | 10 | Repair of Classrooms | 5146257 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 319104 | Bado Dangwa National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3773138 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136158 | Balawag ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 2766453 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305198 | Balawag NHS | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 3940554 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136161 | Binongsay ES | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 3635102 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136162 | Bullagian ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1560899 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136091 | Bulo East ES | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 5260915 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136163 | Cabaritan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3094090 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classrooms | 3077094 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136164 | Calanan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3111037 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136099 | Camp Conrado M. Balweg Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1347970 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136004 | Casigayan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1120533 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220523 | Cataw Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2119557 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220522 | Dananao Primary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 749121 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136167 | Gaogao Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 5 | Repair of Classroom | 2793115 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 220502 | Gawidan Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 712290 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136098 | Hilltop ES | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 9792355 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136100 | Lacnog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1068464 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136175 | Masablang Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 2248302 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136179 | Pinagan ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2240601 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136111 | Sotto ES | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1289762 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136180 | SUYANG ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1332063 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 136181 | Toppan ES | CITY OF TABUK (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3632233 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | CAR | Tabuk City | 305226 | TUGA NATIONAL HIGH SCHOOL | CITY OF TABUK (Capital) | 0 | 1 | 8 | Repair of Classrooms | 4890035 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 134974 | Sappaac ES | BANGUED (Capital) | 0 | 1 | 4 | Repair of Classrooms | 3174289.69 | 1 | 3164484.93 | COMPLETED | 1 | 2022-04-13 | 2021-12-20 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135188 | Lingey Elementary School | BUCLOC | 0 | 1 | 7 | Repair of Classrooms | 4460075.37 | 1 | 4452189.68 | COMPLETED | 1 | 2022-04-13 | 2021-12-20 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | 0 | 1 | 9 | Repair of Classrooms | 6491846.5 | 1 | 6481279.72 | COMPLETED | 1 | 2022-04-13 | 2021-12-20 | CAR-ABRA-2019-010 |  | 2018-05-12 | 2018-12-10 | 2018-12-22 | 2018-12-28 | 2019-08-09 | LONNIE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135027 | Benben PS | LA PAZ | 0 | 1 | 1 | Repair of Classroom | 648764.09 | 1 | 638826.36 | COMPLETED | 1 | 2022-05-23 | 2021-12-20 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135034 | Liguis ES | LA PAZ | 0 | 1 | 9 | Repair of Classrooms | 6821548.24 | 1 | 6806714.7 | COMPLETED | 1 | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135037 | Mudeng ES | LA PAZ | 0 | 1 | 10 | Repair of Classrooms | 7984480.95 | 1 | 7971266.95 | COMPLETED | 1 | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135041 | San Gregorio ES | LA PAZ | 0 | 1 | 11 | Repair of Classrooms | 5732676.73 | 1 | 5721407.05 | COMPLETED | 1 | 2021-04-13 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 218514 | Taping Primary School | LAGANGILANG | 0 | 1 | 2 | Repair of Classrooms | 1178716.27 | 1 | 1173557.22 | COMPLETED | 1 | 2022-04-13 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135060 | Diangay PS | LICUAN-BAAY (LICUAN) | 0 | 1 | 3 | Repair of Classrooms | 2682252.16 | 1 | 2668754.31 | COMPLETED | 1 | 2022-04-13 | 2021-11-12 | [7 empty] | LONNIE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135086 | Agumanay ES | LUBA | 0 | 1 | 3 | Repair of Classrooms | 4635039.19 | 1 | 4626110.79 | COMPLETED | 1 | 2022-06-06 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135108 | Pega PS | LUBA | 0 | 1 | 2 | Repair of Classrooms | 1850476.27 | 1 | 1839361.97 | COMPLETED | 1 | 2022-05-23 | 2022-06-10 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 134996 | Liagan PS | MANABO | 0 | 1 | 2 | Repair of Classrooms | 1570561.53 | 1 | 1555567.3 | COMPLETED | 1 | 2022-04-13 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135146 | Suyo Pilot ES | PIDIGAN | 0 | 1 | 7 | Repair of Classrooms | 4388345.16 | 1 | 4375458.03 | COMPLETED | 1 | 2022-06-06 | 2021-11-12 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305077 | Bolbolo NHS | PILAR | 0 | 1 | 4 | Repair of Classrooms | 1344048.55 | 1 | 1339014.87 | COMPLETED | 1 | 2022-04-13 | 2021-11-12 | CAR-ABRA-2019-019 |  | 2019-07-02 | 2019-07-08 | 2019-07-22 | 2019-07-25 | 2019-09-09 | LONNIE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | 0 | 1 | 9 | Repair of Classrooms | 5567452.93 | 1 | 5558175.15 | COMPLETED | 1 | 2022-06-06 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | 0 | 1 | 5 | Repair of Classrooms | 4718508.77 | 1 | 4710435.02 | COMPLETED | 1 | 2022-06-06 | 2021-12-20 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 109752 | Manicbel PS | Sallapadan | 0 | 1 | 2 | Repair of Classrooms | 2041138.48 | 1 | 2051020.63 | COMPLETED | 1 | 2022-05-23 | 2021-12-20 | [7 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 12 | Repair of Classrooms | 7414928.15 | 1 | 7409546.13 | COMPLETED | 1 | 2022-04-13 | 2021-12-20 | CAR-ABRA-2019-017 |  | 2019-07-02 | 2019-07-08 | 2019-07-22 | 2019-07-25 | 2019-09-09 | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Abra | 135096 | Dacuag PS | TUBO | 0 | 1 | 2 | Repair of Classrooms | 2393325.74 | 1 | 2389794.93 | COMPLETED | 1 | 2021-04-13 | 2022-06-10 | [7 empty] | BAJE CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135279 | Sacpil ES | CONNER | 0 | 1 | 6 | Repair of Classrooms | 3768428.5 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135319 | Madatag ES | KABUGAO (Capital) | 0 | 1 | 6 | Repair of Classrooms | 3795597.14 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 135334 | Catammoyoan ES | LUNA | 0 | 1 | 2 | Repair of Classrooms | 1269199.31 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Apayao | 305118 | Mataguisi Comp. HS Main | PUDTOL | 0 | 1 | 4 | Repair of Classrooms | 2407152.25 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 319304 | BCNHS, Hillside Ext. | BAGUIO CITY | 0 | 1 | 4 | Repair of Classrooms | 1179180.28 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 305273 | Happy Hollow National High School | BAGUIO CITY | 0 | 1 | 6 | Repair of Classrooms | 3847478.78 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 221505 | Irisan Elementary School | BAGUIO CITY | 0 | 1 | 3 | Repair of Classrooms | 2081257.64 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Baguio City | 221501 | Kias Elementary School | BAGUIO CITY | 0 | 1 | 6 | Repair of Classrooms | 3838325.19 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135401 | Bagtangan ES | BAKUN | 0 | 1 | 8 | Repair and Improvement of School Facilities | 4543047.85 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135406 | Ketagan-Cabatan ES | BAKUN | 0 | 1 | 4 | Repair and Improvement of School Facilities | 3029589.92 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135444 | Kiweng PS | BOKOD | 0 | 1 | 2 | Repair of Classrooms | 1713052.17 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135464 | Bad-ayan ES | BUGUIAS | 0 | 1 | 13 | Repair and Improvement of School Facilities | 7991798.63 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135511 | Pacalso ES | ITOGON | 0 | 1 | 7 | Repair of Classrooms | 4000100 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135554 | Kabayan CS | KABAYAN | 0 | 1 | 10 | Repair of Classrooms | 5329056.09 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 501203 | Datakan Integrated School | KAPANGAN | 0 | 1 | 11 | Repair and Improvement of School Facilities | 4437835.42 | 1 |  | COMPLETED | 1 | 2022-10-30 | [9 empty] | The contractor lacks manpower and financial capability, resulting to the delay of the project. | [12 empty] | 1 |  | 44927 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | CAR | Benguet | 135606 | Palina ES | KIBUNGAN | 0 | 1 | 6 | Repair and Improvement of School Facilities | 3281489.2 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135627 | Longlong ES | LA TRINIDAD (Capital) | 0 | 1 | 11 | Repair of Classrooms | 6345300.51 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135681 | Sablan CS | SABLAN | 0 | 1 | 14 | Repair of Classrooms | 8117741.37 | 1 | 7724770.89 | COMPLETED | 1 | 2022-10-30 | [9 empty] | The contractor lacks manpower and financial capability, resulting to the delay of the project. | [12 empty] | 1 |  | 44927 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | CAR | Benguet | 135729 | Mamuyod ES | TUBLAY | 0 | 1 | 3 | Repair of Classrooms | 1849635.81 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Benguet | 135732 | Pangablan PS | TUBLAY | 0 | 1 | 2 | Repair of Classrooms | 1265000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 305190 | Sta. Maria National High School | ALFONSO LISTA (POTIA) | 0 | 1 | 23 | Repair of Classrooms | 12354057.65 | 1 | 11184969.32 | COMPLETED | 1 | 2022-11-30 | [9 empty] | post qualification | [12 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135788 | Asipulo CS | ASIPULO | 0 | 1 | 1 | Repair of Classroom | 577266.8 | 1 | 567981.06 | COMPLETED | 1 | 2021-10-14 | 2021-11-03 | [21 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135791 | Cawayan ES | ASIPULO | 0 | 1 | 8 | Repair of Classrooms | 4504565.68 | 1 | 4500558.68 | COMPLETED | 1 | 2022-11-30 | [9 empty] | hard accessibility,contractors fault/negligence, lack of skilled workers causing repitition of works, hardship in delivery of lumbers. | [12 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135844 | Ubuag PS | HINGYON | 0 | 1 | 4 | Repair of Classrooms | 2129242.21 | 1 | 1844364.55 | COMPLETED | 1 | 2022-02-03 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135881 | Burnay ES | LAGAWE (Capital) | 0 | 1 | 7 | Repair of Classrooms | 2806042.72 | 1 | 2537620.27 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Ifugao | 135915 | Sanafe ES | LAMUT | 0 | 1 | 7 | Repair of Classrooms | 3263849.61 | 1 | 2895974.33 | COMPLETED | 1 | February 9,2022 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 305197 | Allaguia National High School | PINUKPUK | 0 | 1 | 6 | Repair of Classrooms | 3311300.45 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Contractor's Fault | [12 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Kalinga | 136048 | Magaogao Elementary School | PINUKPUK | 0 | 1 | 6 | Repair of Classrooms | 2784538.17 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 319113 | Mananig National High School | PINUKPUK | 0 | 1 | 2 | Repair of Classrooms | 808723.55 | 1 |  | COMPLETED | 1 | [10 empty] | for final inspection | [12 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Kalinga | 136117 | Ammaboy Elementary School | TANUDAN | 0 | 1 | 3 | Repair of Classrooms | 1158191.47 | 1 |  | COMPLETED | 1 | [10 empty] | for final inspection | [12 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | 0 | 1 | 6 | Repair of Classrooms | 4533161.71 | 1 | 4135213.55 | COMPLETED | 1 | 2022-04-28 | 2022-04-22 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-06 | Precious Gold Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136198 | Bagnen Oriente Elementary School | BAUKO | 0 | 1 | 5 | Repair of Classrooms | 5800703.93 | 1 | 5299471.51 | COMPLETED | 1 | 2021-12-11 | 2022-12-22 |  | INF-2021 R-005 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | EMNAR Const'n & Eng'g Services | [13 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136214 | Letang Elementary School | BAUKO | 0 | 1 | 5 | Repair of Classrooms | 4021436.78 | 1 | 3739882 | COMPLETED | 1 | 2022-01-29 | 2022-01-25 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-01 | DMYA Construire Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 305228 | Albago National High School | BONTOC (Capital) | 0 | 1 | 6 | Repair of Classrooms | 5458857.12 | 1 | 4569212.27 | COMPLETED | 1 | 2022-03-08 | 2022-03-23 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-09-29 | JBA Construction & Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136302 | Labay Elementary School | PARACELIS | 0 | 1 | 5 | Repair of Classrooms | 6254664.25 | 1 | 6187398.67 | COMPLETED | 1 | 2022-04-28 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-12-14 | SEMBRI | [13 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136312 | San Emilio Elementary School | PARACELIS | 0 | 1 | 4 | Repair of Classrooms | 5754631.61 | 1 | 2580004.66 | COMPLETED | 1 | 2021-12-11 |  |  | INF-2021 R-009 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | Boyet Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136323 | Madepdeppas Elementary School | SABANGAN | 0 | 1 | 5 | Repair of Classrooms | 3530376.87 | 1 | 3217304.63 | COMPLETED | 1 | 2021-12-28 | 2022-05-24 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-09-29 | Graceron Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136359 | Batayan Elementary School | TADIAN | 0 | 1 | 4 | Repair of Classrooms | 5939992.98 | 1 | 5679281.53 | COMPLETED | 1 | 2022-01-02 | 2022-02-18 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-10-04 | [14 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Mt. Province | 136373 | Pandayan Elementary School | TADIAN | 0 | 1 | 5 | Repair of Classrooms | 5301291.4 | 1 | 5200341.68 | COMPLETED | 1 | 2021-12-11 | 2021-12-23 |  | INF-2021 R-012 | 2021-06-04 | 2021-06-10 | 2021-06-24 | 2021-07-22 | 2021-08-13 | EMNAR Const'n & Eng'g Services | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 305198 | Balawag National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 3999350.83 | 1 | 3113115.58 | COMPLETED | 1 | November 23,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 220515 | Basao Isla Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 2007716.09 | 1 | 1561598.63 | COMPLETED | 1 | November 08,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 3791847.94 | 1 | 2831026.37 | COMPLETED | 1 | November 23,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 1840687.18 | 1 | 1434700.16 | COMPLETED | 1 | November 23,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136166 | Dupag Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | Repair of Classrooms | 4206607.19 | 1 | 3968655.08 | COMPLETED | 1 | December 08,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136007 | Laya Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 1038803.86 | 1 | 809999.18 | COMPLETED | 1 | October 24,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 319117 | Naneng NHS - Mosimos Extension | CITY OF TABUK (Capital) | 0 | 1 | 2 | Repair of Classrooms | 1802145 | 1 | 1802145 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | CAR | Tabuk City | 136181 | Toppan ES | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 3326116.1 | 1 | 2645981.11 | COMPLETED | 1 | November 23,2021 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2022 | CAR | Abra | 134997 | Lublubnac PS | BUCAY | 0 | 1 | 3 | Repair of Classrooms | 2376540.7 | 1 | 1237086.8 | COMPLETED | 1 | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135176 | Cabaruyan ES | DAGUIOMAN | 0 | 1 | 5 | Repair of Classrooms | 3218586.75 | 1 | 2372519.51 | COMPLETED | 1 | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135021 | Mudiit ES | DOLORES | 0 | 1 | 8 | Repair of Classrooms | 4691995.62 | 1 | 3213851.29 | COMPLETED | 1 | 2023-01-07 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135040 | Pidipid ES | LA PAZ | 0 | 1 | 8 | Repair of Classrooms | 6190268.74 | 1 | 2585702.69 | COMPLETED | 1 | 2022-10-29 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | 13 | Repair of Classrooms | 10200503.12 | 1 | 4687393.27 | COMPLETED | 1 | 2022-11-28 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 1 |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135104 | Lul-luno ES | LUBA | 0 | 1 | 4 | Repair of Classrooms | 3883217.7 | 1 | 6182717.4 | COMPLETED | 1 | 2022-12-28 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  | 44986 | 2.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Abra | 135009 | Sto. Tomas Barrio School | MANABO | 0 | 1 | 3 | Repair of Classrooms | 2589323.21 | 1 | 10195730.6 | COMPLETED | 1 | 2023-03-08 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 218517 | Banay PS | PIDIGAN | 0 | 1 | 3 | Repair of Classrooms | 2613153.97 | 1 | 3876538.09 | COMPLETED | 1 | 2022-12-08 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135177 | Callaban PS | SALLAPADAN | 0 | 1 | 1 | Repair of Classroom | 1240563.12 | 1 | 2606198.18 | COMPLETED | 1 | 2022-12-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 218511 | Pantoc ES | SAN QUINTIN | 0 | 1 | 4 | Repair of Classrooms | 3514287.7 | 1 | 3508272.06 | COMPLETED | 1 | 2022-11-08 | [8 empty] | TRAMS CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Abra | 135014 | Bumagcat ES | TAYUM | 0 | 1 | 9 | Repair of Classrooms | 6211798.89 | 1 | 6205959.86 | COMPLETED | 1 | 2023-02-06 | [8 empty] | SEMBRI CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135259 | Conner Central School | CONNER | 0 | 1 | 11 | Repair of Classrooms | 6662077.48 | 2 | 6328972.67 | COMPLETED | 1 | 2023-05-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | Bangyan 3D construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135266 | Karikitan ES | CONNER | 0 | 1 | 9 | Repair of Classrooms | 5846627.59 | 2 | 5554217.88 | COMPLETED | 1 | 2023-05-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | Bangyan 3D construction | [13 empty] | 1 |  | 45017 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 318808 | Allig National Agricultural and Trade HS | FLORA | 0 | 1 | 10 | Repair of Classrooms | 3617786.15 | 2 | 3613888.57 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | For Punchlist | [12 empty] | 1 |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305121 | Mayor Ricardo de San Jose, Sr. Comp. HS | FLORA | 0 | 1 | 9 | Repair of Classrooms | 965067.74 | 2 | 963942.97 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | For Punchlist | [12 empty] | 1 |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305107 | Apayao Science High Shool | LUNA | 0 | 1 | 18 | Repair of Classrooms | 4643093.95 | 2 | 4367761.94 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  | 45017 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135333 | Capagaypayan Primary School | LUNA | 0 | 1 | 2 | Repair of Classrooms | 1643773.83 | 2 | 1641935.01 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | 3 | Repair of Classrooms | 2120307.68 | 2 | 1944680.34 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Apayao | 135351 | Cacalaggan Elementary School | PUDTOL | 0 | 1 | 5 | Repair of Classrooms | 1516808.92 | 2 | 1514879.48 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 319009 | Tawit National High School | PUDTOL | 0 | 1 | 4 | Repair of Classrooms | 753644.59 | 2 | 751772.39 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Apayao | 305120 | MAYOR GUILLERMO BARSATAN MEMORIAL SCHOOL OF ARTS AND TRADE | SANTA MARCELA | 0 | 1 | 9 | Repair of Classrooms | 949317.74 | 2 | 947405.47 | COMPLETED | 1 | 2023-04-05 |  |  |  | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-07-28 | 2022-09-27 | ECV Construction | [13 empty] | 1 |  | 45017 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Benguet | 135679 | Palali ES | SABLAN | 0 | 1 | 5 | Repair of Classrooms | 1672223.81 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Benguet | 135719 | Ambongdolan ES | TUBLAY | 0 | 1 | 6 | Repair of Classrooms | 4024447.62 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Ifugao | 135804 | Panubtuban ES | ASIPULO | 0 | 1 | 5 | Repair of Classrooms | 3263177 | 1 |  | COMPLETED | 1 | 2023-04-09 | [22 empty] | 1 |  | 44986 | 7.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Ifugao | 135834 | Bitu ES | HINGYON | 0 | 1 | 2 | Repair of Classrooms | 1672223.05 | 1 | 1667139.14 | COMPLETED | 1 | 2022-11-21 | Sept.29, 2022 | [21 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Kalinga | 220513 | Balinciagao ES - Limood Annex | PASIL | 0 | 1 | 3 | Repair of Classrooms | 1831297.95 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 6.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Kalinga | 136025 | Galdang Elementary School | PASIL | 0 | 1 | 2 | Repair of Classrooms | 1350608.17 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 4.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | BARLIG | 0 | 1 | 4 | Repair of Classrooms | 2651588.44 | 1 | 2572040.79 | COMPLETED | 1 | 2022-10-02 |  | INF-2022 R-001 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION | completed | [12 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136247 | Suquib Primary School | BESAO | 0 | 1 | 2 | Repair of Classrooms | 1590953 | 1 | 1590953 | COMPLETED | 1 | 2022-09-19 | 2022-09-15 | INF-2022 R-002 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION | completed | [12 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | 0 | 1 | 2 | Repair of Classrooms | 2121270.75 | 1 | 1824355.38 | COMPLETED | 1 | 2022-10-02 |  | INF-2022 R-003 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | ZYMX CONSTRUCTION | completed | [12 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136332 | Anabel Elementary School | SADANGA | 0 | 1 | 1 | Repair of Classroom | 1060635 | 1 | 1049964.94 | COMPLETED | 1 | 2022-09-24 | 2022-09-20 | INF-2022 R-004 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION | completed | [12 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Mt. Province | 136341 | Aguid Elementary School | SAGADA | 0 | 1 | 4 | Repair of Classrooms | 2651588 | 1 | 2598556.24 | COMPLETED | 1 | 2022-10-02 | 2022-09-15 | INF-2022 R-005 |  | 2022-02-24 | 2022-03-03 | 2022-03-16 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION | completed | [12 empty] | 1 |  |  | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | CAR | Tabuk City | 136100 | Lacnog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | Repair of Classroom | 1615715.5 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 1.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | CAR | Abra | 134967 | Bacsil Elementary School | BANGUED (Capital) | Lone | 1 | 7 | Repair of Classrooms | 6997850.5 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 305092 | Pangtod NHS | BUCAY | Lone | 1 | 14 | Repair of Classrooms | 11962677.41 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135043 | Toon ES | LA PAZ | Lone | 1 | 9 | Repair of Classrooms | 7334722.18 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135082 | Tagodtod ES | LAGANGILANG | Lone | 1 | 17 | Repair of Classrooms | 4701133.31 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135138 | Malapaao ES | LANGIDEN | Lone | 1 | 8 | Repair of Classrooms | 6974744.82 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135105 | Luzong ES | LUBA | Lone | 1 | 11 | Repair of Classrooms | 5227579.94 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 501729 | TABANGAO IS | LUBA | Lone | 1 | 7 | Repair of Classrooms | 1801681.92 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 218519 | Tattawa Primary School | PEÑARRUBIA | Lone | 1 | 2 | Repair of Classrooms | 1370900.69 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135168 | Abas ES | SALLAPADAN | Lone | 1 | 10 | Repair of Classrooms | 14649444.46 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | 4 | Repair of Classrooms | 2466413.86 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | Lone | 1 | 2 | Repair of Classrooms | 2581277.79 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Abra | 501104 | Tuquib Integrated School | VILLAVICIOSA | Lone | 1 | 4 | Repair of Classrooms | 1426876.7 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135261 | Daga ES | CONNER | Lone | 1 | 2 | Repair of Classrooms | 839062.9 | DEPED (Batch 2) | 797308.5 | COMPLETED | 1 |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135273 | Paddaoan ES | CONNER | Lone | 1 | 4 | Repair of Classrooms | 2378537.75 | DPWH (Batch 2) | 2324722.22 | COMPLETED | 1 | 2024-05-16 |  |  | 23PC0087 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135288 | Balluyan ES | FLORA | Lone | 1 | 2 | Repair of Classrooms | 484181.88 | DEPED (Batch 2) | 460031.76 | COMPLETED | 1 |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135292 | Sta. Maria ES | FLORA | Lone | 1 | 3 | Repair of Classrooms | 1566065.42 | DPWH (Batch 2) | 1274457.81 | COMPLETED | 1 | 2024-04-27 |  |  | 23PC0088 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 305108 | BAC-DA National High School | LUNA | Lone | 1 | 9 | Repair of Classrooms | 2952826.49 | DPWH (Batch 2) | 1467604.95 | COMPLETED | 1 | 2024-04-27 |  |  | 23PC0089 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 135335 | Dagupan ES | LUNA | Lone | 1 | 2 | Repair of Classrooms | 1266006.56 | DPWH (Batch 2) | 2763466.23 | COMPLETED | 1 | 2024-05-12 |  |  | 23PC0091 |  | 2023-10-10 | 2023-10-23 |  |  | ECV CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 219004 | Luyon ES | LUNA | Lone | 1 | 1 | Repair of Classroom | 816380.11 | DEPED (Batch 2) | 775363.96 | COMPLETED | 1 |  |  |  |  | 2024-12-27 | 2024-01-09 | 2024-01-22 | 2024-02-06 | 2024-02-19 | J.G Yacas Construction, Supply and Equipment Rentals | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 219003 | San Juan ES | SANTA MARCELA | Lone | 1 | 2 | Repair of Classrooms | 1362472.41 | DPWH (Batch 2) | 1185260.55 | COMPLETED | 1 | 2024-04-15 |  |  | 23PC0090 |  | 2023-11-17 | 2023-11-28 |  |  | ECV CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Apayao | 305124 | Sipa-Imelda NHS | SANTA MARCELA | Lone | 1 | 4 | Repair of Classrooms | 2484261.86 | DPWH (Batch 2) |  | COMPLETED | 1 | [9 empty] | GKA ENGINEERING AND CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135380 | Calasipan ES | ATOK | Lone | 1 | 3 | Repair of Classrooms | 2925000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135410 | Cabutotan ES | BAKUN | Lone | 1 | 3 | Repair of Classrooms | 2925000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135443 | Kawal ES | BOKOD | Lone | 1 | 3 | Repair of Classrooms | 5953500 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 501301 | Cayapas Integrated School | BUGUIAS | Lone | 1 | 4 | Repair of Classrooms | 1800000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 219524 | Lebeng PS | KABAYAN | Lone | 1 | 1 | Repair of Classrooms | 1323000 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 318903 | Tawangan-Lusod NHS | KABAYAN | Lone | 1 | 2 | Repair of Classrooms | 1575000 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135572 | Kaliwaga Barrio School | KAPANGAN | Lone | 1 | 4 | Repair of Classrooms | 1800000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135583 | Pudong ES | KAPANGAN | Lone | 1 | 7 | Repair of Classrooms | 5500000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 501810 | Tacadang Integrated School | KIBUNGAN | Lone | 1 | 5 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | completed
REPAIR 2023 | CAR | Benguet | 135646 | Cabacab Elementary School | MANKAYAN | Lone | 1 | 5 | Repair of Classrooms | 4875000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 305155 | Mankayan National High School | MANKAYAN | Lone | 1 | 10 | Repair of Classrooms | 9400000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135673 | Bayabas ES | SABLAN | Lone | 1 | 2 | Repair of Classrooms | 105000 | DEPED (Batch 2) | 0 | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135707 | Besong-Saddle PS | TUBA | Lone | 1 | 1 | Repair of Classrooms | 703500 | DEPED (Batch 2) | 0 | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135718 | Albis ES | TUBLAY | Lone | 1 | 11 | Repair and Improvement of School Facilities | 8140000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Benguet | 135720 | Baayan ES | TUBLAY | Lone | 1 | 9 | Repair and Improvement of School Facilities | 6660000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135742 | Awayan ES - Annex | AGUINALDO | Lone | 1 | 5 | Repair of Classrooms | 3011337.85 | DPWH (Batch 2) |  | COMPLETED | 1 | 2024-07-01 | [22 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135776 | Namillangan ES | ALFONSO LISTA (POTIA) | Lone | 1 | 3 | Repair of Classrooms | 2576681.62 | DPWH (Batch 2) |  | COMPLETED | 1 | 2024-06-01 | [22 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Ifugao | 135783 | San Marcos ES | ALFONSO LISTA (POTIA) | Lone | 1 | 4 | Repair of Classrooms | 3456627.55 | DPWH (Batch 2) |  | COMPLETED | 1 | 2024-07-01 | [22 empty] | 1 |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Ifugao | 135830 | Uhaj Elementary School | BANAUE | Lone | 1 | 5 | Repair of Classrooms | 2937266.66 | DPWH (Batch 2) |  | COMPLETED | 1 | 2024-07-01 | [22 empty] | 1 |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | Lone | 1 | 4 | Repair of Classrooms | 2973883.37 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 135981 | Salegseg Primary School | BALBALAN | Lone | 1 | 2 | Repair of Classrooms | 774848.08 | DEPED (Batch 2) | 0 | COMPLETED | 1 | [10 empty] | for Award | [12 empty] | 1 |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | Lone | 1 | 6 | Repair of Classrooms | 3402560.17 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136030 | Pasil CS-Pugong Annex | PASIL | Lone | 1 | 2 | Repair of Classrooms | 830356.32 | DEPED (Batch 2) | 0 | COMPLETED | 1 | [10 empty] | Failure of Bidding (2nd time) For Re-posting | [12 empty] | 1 |  |  | 8.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136059 | Kullayanan Elementary School | PINUKPUK | Lone | 1 | 3 | Repair of Classrooms | 1017441.71 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136066 | Anonang Elementary School | RIZAL (LIWAN) | Lone | 1 | 2 | Repair of Classrooms | 1415699.66 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136120 | Allubaggan Elementary School | TANUDAN | Lone | 1 | 3 | Repair of Classrooms | 1706146.77 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Kalinga | 136122 | Pagugo Elementary School | TANUDAN | Lone | 1 | 6 | Repair of Classrooms | 2776711.21 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 305260 | Panabungen School of Arts, Trades, and Home Industries | BESAO | Lone | 1 | 10 | Repair of Classrooms | 16174098.5 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | Lone | 1 | 7 | Repair of Classrooms | 13090971.43 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319206 | Data National High School | SABANGAN | Lone | 1 | 8 | Repair of Classrooms | 6419083.45 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 136365 | Ilang Primary School | TADIAN | Lone | 1 | 1 | Repair of Classrooms | 1881319.77 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Mt. Province | 319223 | Mabalite National High School | TADIAN | Lone | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136085 | Agbannawag Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 22 | Repair of Classrooms | 22523445.42 | DPWH (Batch 2) | 21730038.06 | COMPLETED | 1 | September 25, 2023 | August 22, 2024 | 23PL0136 | 23PL0136 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | QUINONES CONSTRUCTION | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Tabuk City | 136092 | Bulo west Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 4912187.16 | DPWH (Batch 2) | 4734504.78 | COMPLETED | 1 | May 13, 2024 |  | 23PL0137 | 23PL0137 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | DELTA JO CONSTRUCTION (DELCONS) | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 220522 | Dananao Primary School | CITY OF TABUK (Capital) | Lone | 1 | 1 | Repair of Classroom | 1890529.88 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136168 | Gobgob Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 3 | Repair of Classrooms | 7274113.19 | DPWH (Batch 2) | 6576210.86 | COMPLETED | 1 | May 8, 2024 |  | 23PL0131 | 23PL0131 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 10, 2024 | BAGWIS CONSTRUCTION | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 136101 | Madopdop Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 9 | Repair of Classrooms | 9317195.2 | DPWH (Batch 2) | 8316388.82 | COMPLETED | 1 | July 12, 2024 |  | 23PL035 | 23PL035 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 15, 2024 | COLUMBIAN CONSTRUCTION SERCIVES | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2023 | CAR | Tabuk City | 136102 | Magabbangon Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 1 | Repair of Classroom | 1269060.16 | DPWH (Batch 2) | 1220837.95 | COMPLETED | 1 | April 7, 2024 |  | 23PL0132 | 23PL0132 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 9, 2024 | JBC BUILDERS | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | CAR | Tabuk City | 305207 | Nambucayan National High School | CITY OF TABUK (Capital) | Lone | 1 | 3 | Repair of Classrooms | 6321278.02 | DPWH (Batch 2) | 5942542.5 | COMPLETED | 1 | May 14, 2024 |  | 23PL0133 | 23PL0133 | October 27, 2023 | November 20, 2023 | November 20, 2023 | December 27, 2023 | January 16, 2024 | BIGA CONSTRUCTION | [13 empty] | 1 |  |  | 11.24 |  |  |  |  | Completed
REPAIR 2024 | CAR | Abra | 134966 | Agtangao ES | BANGUED (Capital) | Lone | 1 | 14 | Repair of Classrooms | 8484848.48 | 1 |  | Ongoing | 0.5 | [23 empty] | 0.3 | [7 empty] | Ongoing
REPAIR 2024 | CAR | Abra | 134985 | Abang ES | BUCAY | Lone | 1 | 6 | Repair of Classrooms | 3636363.64 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Apayao | 318812 | Ili National High School | CONNER | Lone | 1 | 4 | Repair of Classrooms | 3478569.81 | 1 | 3373464.301 | Ongoing | 0.76 | [6 empty] | December 23,2024 |  |  | Enrique T. Chua Development Corporation | Mobilization; Re-aligned from Paddaoan to Ili for Rebidding | [12 empty] | 0.1 |  |  |  | 1 | 4 | 3478569.81 |  | Ongoing
REPAIR 2024 | CAR | Apayao | 135307 | Kabugao Central School | KABUGAO (Capital) | Lone | 1 | 11 | Repair of Classrooms | 9796188.49 | 1 | 9630076.59 | Ongoing | 0.68 | [6 empty] | October 7,2024 |  |  | Aquila Construction Co. | [13 empty] | 0.45 | [7 empty] | Ongoing
REPAIR 2024 | CAR | Baguio City | 136400 | Dona Aurora Elementary School | BAGUIO CITY | Lone | 1 | 4 | Repair of Classrooms | 1010101.01 | 1 |  | COMPLETED | 1 | [6 empty] | october 21, 2024 | [16 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Baguio City | 136404 | Rizal Elementary School | BAGUIO CITY | Lone | 1 | 2 | Repair of Classrooms | 1010101.01 | 1 |  | COMPLETED | 1 | [6 empty] | october 21, 2024 | [16 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Baguio City | 305277 | Roxas National High School | BAGUIO CITY | Lone | 1 | 3 | Repair of Classrooms | 1111111.11 | 1 |  | COMPLETED | 1 | [6 empty] | october 21, 2024 | [16 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Benguet | 135528 | Solomon Solano Elementary School | ITOGON | Lone | 1 | 2 | Repair of Classrooms | 2555912.26 | 1 |  | COMPLETED | 1 | [23 empty] | 0.9 |  |  | 5.25 |  |  |  |  | Ongoing
REPAIR 2024 | CAR | Benguet | 135619 | Bekkel ES | LA TRINIDAD (Capital) | Lone | 1 | 6 | Repair of Classrooms | 11209535.3 | 1 |  | Ongoing | 0.9 | [23 empty] | 0.6 | [7 empty] | Ongoing
REPAIR 2024 | CAR | Ifugao | 135767 | Calimag ES | ALFONSO LISTA (POTIA) | Lone | 1 | 10 | Repair of Classrooms | 9478787.88 | 1 |  | Ongoing | 0.45 | [23 empty] | 0.2 | [7 empty] | Ongoing
REPAIR 2024 | CAR | Kalinga | 136038 | Wagud Elementary School | PINUKPUK | Lone | 1 | 5 | Repair of Classrooms | 2744356.71 | 1 |  | under procurement | 0 | [10 empty] | For Posting (failed bidding) | [12 empty] | 0 | [7 empty] | under procurement
REPAIR 2024 | CAR | Kalinga | 136074 | Macutay Elementary School | RIZAL (LIWAN) | Lone | 1 | 5 | Repair of Classrooms | 3306825.17 | 1 |  | under procurement | 0 | [10 empty] | For Posting (failed bidding) | [12 empty] | 0 | [7 empty] | under procurement
REPAIR 2024 | CAR | Kalinga | 136121 | Darulog Elementary School | TANUDAN | Lone | 1 | 4 | Repair of Classrooms | 1044997.17 | 1 |  | under procurement | 0 | [10 empty] | For Posting (failed bidding) | [12 empty] | 0 | [7 empty] | under procurement
REPAIR 2024 | CAR | Mt. Province | 136206 | Caotit Primary School | BAUKO | Lone | 1 | 6 | Repair of Classrooms | 13030303.03 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Tabuk City | 220522 | DANANAO ELEMENTARY SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | 2 | Repair of Classrooms | 2598451.4454 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | CAR | Tabuk City | 136165 | Tuliao Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 4 | Repair of Classrooms | 7535203.26 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%