## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2018 | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 | UPGRADING | 1 | 1957934.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 672163.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Samaria Tala Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 754858.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Caloocan City |  | Sampaguita Senior High School | KALOOKAN CITY |  | 1 | UPGRADING | 2 | 743289.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING | 2 | 1947303.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | UPGRADING | 2 | 4724091.14 | 3665127.39 | COMPLETED | 1 | 2019-06-20 |  |  |  |  | 2018-11-07 | 2018-11-19 | 2018-12-03 | 2018-12-26 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School (Isaac Lopez ES) | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | 2 | 3345858.02 | 2496908.97 | COMPLETED | 1 |  |  | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | 2 | 4891117.15 | 3650087.43 | COMPLETED | 1 | 2019-01-31 | 2019-01-31 | 2018-Mandauyong -19 | 2018-Mandauyong -19 | July 19, 2018-August 6, 2018 | 2018-07-26 | 2018-08-07 | 2018-08-10 | 2019-08-20 | New Rich General Contractor Services & Trading Co., Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | SAMPALOC | 4 | 1 | UPGRADING | 2 | 3105124.57 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Marikina City | 500052 | Concepcion Integrated School | CITY OF MARIKINA | 2 | 1 | UPGRADING | 2 | 784512.82 |  | COMPLETED | 1 | June 16, 2019 | May 22, 2019 |  |  | March 22, 2019 |  | March 27, 2019 | March 27, 2019 | April 12, 2019 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2 | 1 | UPGRADING | 2 | 591084.11 |  | COMPLETED | 1 | June 16, 2018 | May 22, 2018 |  |  | March 22, 2018 |  | March 27, 2018 | March 27, 2018 | April 12, 2018 | SHERF BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | 2 | 679397.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | 2 | 1192859.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | UPGRADING | 2 | 2194937.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | UPGRADING | 3 | 6470050.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 | 1 | UPGRADING | 2 | 4774665.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305320 | Balingasa HS | Quezon City | 1 | 1 | UPGRADING | 1 | 3168383.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 | 1 | UPGRADING | 1 | 3248178.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | Quezon City | 1 | 1 | UPGRADING | 1 | 1105837.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 | 1 | UPGRADING | 1 | 5943563.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 136540 | Pres. Corazon C. Aquino E/S | QUEZON CITY | 2 | 1 | UPGRADING | 4 | 1744063.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 | 1 | UPGRADING | 1 | 4917426.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305361 | Manuel A. Roxas HS | Quezon City | 4 | 1 | UPGRADING | 1 | 3106367.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 | 1 | UPGRADING | 1 | 3401452.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Taguig | 305466 | Pateros National High School | PATEROS | 1 | 1 | UPGRADING | 2 | 2165075.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | UPGRADING | 3 | 2626512.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | NCR | Valenzuela City | 320404 | Bignay National High School | CITY OF VALENZUELA | 1 | 1 | UPGRADING | 2 | 2484345.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | KALOOKAN CITY | 2 | 1 | UPGRADING | Batch 1 | 3589077.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | City of San Juan | 136749 | Kabayanan ES | CITY OF SAN JUAN | 0 | 1 | UPGRADING | Batch 1 | 2568525.8 | 2545618.14 | COMPLETED | 1 | NOVEMBER 29,2019 |  | PROJECT INFRA 2019-002 | DSJ-CY19-INFRA002 | JULY 31,2019 | AUGUST 7,2019 | AUGUST 19,2019 | AUGUST 28,2019 | OCT. 11, 2019 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | 0 | 1 | UPGRADING | Batch 3 | 1916775.3 | 1899112.96 | COMPLETED | 1 | NOVEMBER 29,2019 |  | PROJECT INFRA 2019-003 | DSJ-CY19-INFRA003 | JULY 19,2019 | AUGUST 7,2019 | AUGUST 19,2019 | AUGUST 28,2019 | OCT. 11, 2019 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 778980.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 1306702.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Malabon City | 136838 | Tañong ES I | CITY OF MALABON | 0 | 1 | UPGRADING | Batch 2 | 5804008.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING | Batch 1 | 5897707.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC | 4 | 1 | UPGRADING | Batch 1 | 1099606.15 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5 | 1 | UPGRADING | Batch 1 | 1178788.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Manila | 136481 | J. Zamora Elementary School | PANDACAN | 6 | 1 | UPGRADING | Batch 1 | 2126244.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 492401.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 511212.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 717615.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 796014.24 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Muntinlupa City | 303450 | Cupang Senior High School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING | Batch 1 | 3705688.32 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | UPGRADING | Batch 3 | 3141017.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | UPGRADING |  | 507323.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Caloocan City | 223503 | Camarin D ES - Unit II | KALOOKAN CITY | 1 | 1 | UPGRADING |  | 6390654.15 |  | COMPLETED | 1 | May 20, 2021 |  | Elec2020-NCR-CaloocanCity-001 | PCA-2020-Infra-002 | November 13, 2020 | November 25, 2020 | December 7, 2020 | December 10, 2020 | December 21, 2020 | MRRM Trading & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Caloocan City | 319701 | Cielito Zamora Junior High School | KALOOKAN CITY | 1 | 1 | UPGRADING |  | 9750743.89 |  | COMPLETED | 1 |  |  | Elec2020-NCR-CaloocanCity-002 | [7 empty] | For Contract (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | 0 | 1 | UPGRADING |  | 15261269.07 |  | COMPLETED | 1 |  |  | Elec2020-NCR-SanJuanCity-001 | [7 empty] | WAITING FOR SIGNED CONTRACT (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | City of San Juan | 305423 | San Juan NHS | CITY OF SAN JUAN | 0 | 1 | UPGRADING |  | 6095379.83 | 4790825.4 | COMPLETED | 1 | May 23, 2021 |  | Elec2020-NCR-SanJuanCity-001 | 2019-PB-002 | January 21, 2020 | February 17, 2020 | March 2, 2020 | March 9, 2020 | December 7, 2020 | MRRM TRADING AND CONSTRUCTION | with suspension order dated May31, 2021 due to on-going retrofitting works of DPWH (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136775 | Gatchalian ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 5467118.17 |  | COMPLETED | 1 |  |  | Elec2020-NCR-LasPiñasCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136777 | Las Pinas ES Central | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 5467118.17 | 4811832.89 | COMPLETED | 1 | 2021-04-19 | 2021-04-14 | Elec2020-NCR-LasPiñasCity-003 | 2020-I15 | 2020-09-29 | 2020-10-07 | 2020-10-15 | 2020-10-29 | 2020-11-20 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Las Piñas City | 136785 | Moonwalk ES | CITY OF LAS PIÑAS | 0 | 1 | UPGRADING |  | 8627777.87 | 8587148.52 | COMPLETED | 1 | 2021-05-06 |  | Elec2020-NCR-LasPiñasCity-001 | 2020-I14 | 2020-11-17 | 2020-11-25 | 2020-12-03 | 2020-12-03 | 2020-12-07 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Malabon City | 500339 | Tañong IS | CITY OF MALABON | 0 | 1 | UPGRADING |  | 6975267.42 | 6949952.93 | COMPLETED | 1 | 2021-03-01 |  | Elec2020-NCR-MalabonCity-001 | 2020-INFRA-09-0004 | 2020-INFRA-09-0004 | 2020-01-17 | 2020-01-22 | 2020-02-10 | 2020-10-01 | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING |  | 10629227.43 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MandaluyongCity-001 | [7 empty] | For NTP (report as of august 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Mandaluyong City | 500332 | Highway Hills Integrated School | CITY OF MANDALUYONG | 0 | 1 | UPGRADING |  | 4972820.43 | 4947956.33 | COMPLETED | 1 | December 4, 2020 | December 4, 2020 | Elec2020-NCR-MandaluyongCity-002 | 2020-Mandaluyong-02 | January 27, 2020 - February 14, 2020 | February 3, 2020 | February 17, 2020 | February 20, 2020 | September 7, 2020 | New Rich General Contractor Services & Trading Company, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 319907 | Jesus Dela Pena National High School | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 616687.82 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 907202.63 | 894685.63 | COMPLETED | 1 | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-001 | [5 empty] | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 370622.76 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 1 | 1 | UPGRADING |  | 3234416.47 | 782092.77 | COMPLETED | 1 | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-009 | [5 empty] | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 500052 | Concepcion Integrated School - Elementary level | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 978444.34 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-009 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 2371106.74 | 3184336.38 | COMPLETED | 1 | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-006 | [5 empty] | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 387534.38 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 401248.84 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 305630 | SSS NHS | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 698494.31 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MarikinaCity-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | UPGRADING |  | 793288.91 | 2321078.17 | COMPLETED | 1 | 2021-02-15 | 2021-02-15 | Elec2020-NCR-MarikinaCity-007 | [5 empty] | 2020-12-15 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 8991962.94 | 8944660.24 | COMPLETED | 1 | May 5, 2021 June 19, 2021 |  | Elec2020-NCR-MuntinlupaCity-002 |  | 11/25/20 |  | 12/16/20 | 12/18/20 | 2020-12-01 | Berto Lucci Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 6167285.42 |  | COMPLETED | 1 |  |  | Elec2020-NCR-MuntinlupaCity-004 | [7 empty] | WAITING FOR MERALCO APPROVAL OF ELECTRICAL PLANS (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 500438 | Lakeview Integrated School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 7803693.73 | 7771377.04 | COMPLETED | 1 | May 5, 2021 June 19, 2021 |  | Elec2020-NCR-MuntinlupaCity-005 |  | 11/25/20 |  | 12/16/20 | 12/18/20 | 2020-12-01 | Berto Lucci Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | UPGRADING |  | 341221.55 |  | COMPLETED | 1 | [10 empty] | WAITING FOR MERALCO APPROVAL OF ELECTRICAL PLANS (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | UPGRADING |  | 5194059.48 |  | COMPLETED | 1 |  |  | Elec2020-NCR-NavotasCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | 0 | 1 | UPGRADING |  | 4963659.48 |  | COMPLETED | 1 |  |  | Elec2020-NCR-NavotasCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | UPGRADING |  | 6204317.63 |  | COMPLETED | 1 |  |  | Elec2020-NCR-ParañaqueCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Paranaque City | 136763 | La Huerta ES | CITY OF PARAÑAQUE | 2 | 1 | UPGRADING |  | 7574686.3 |  | COMPLETED | 1 |  |  | Elec2020-NCR-ParañaqueCity-001 | [7 empty] | with NTP (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | PASIG CITY | 0 | 1 | UPGRADING |  | 4033871.98 |  | COMPLETED | 1 |  |  | Elec2020-NCR-PasigCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | UPGRADING |  | 2193830.67 |  | COMPLETED | 1 |  |  | Elec2020-NCR-QuezonCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 | 1 | UPGRADING |  | 3088839.61 |  | COMPLETED | 1 |  |  | Elec2020-NCR-QuezonCity-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 360868 | SHS within MH del Pilar ES | QUEZON CITY | 1 | 1 | UPGRADING |  | 2113145.1 |  | COMPLETED | 1 |  |  | Elec2020-NCR-QuezonCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 136558 | Eulogio Rodriguez, Sr. ES | QUEZON CITY | 3 | 1 | UPGRADING |  | 6201820.73 |  | COMPLETED | 1 |  |  | Elec2020-NCR-QuezonCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Quezon City | 136554 | Libis ES | QUEZON CITY | 3 | 1 | UPGRADING |  | 5246186.81 |  | COMPLETED | 1 |  |  | Elec2020-NCR-QuezonCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 320607 | Agripino Manalo National HS | PATEROS | 1 | 1 | UPGRADING |  | 1342366.69 | 1342366.69 | COMPLETED | 1 | March 16, 2021 | February 24, 2021 | Elec2020-NCR-TaguigCity&Pateros-001 | DTP-CY-INFRA-007 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | AYZARIZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | UPGRADING |  | 8301022.67 | 5644539.47 | COMPLETED | 1 | March 16, 2021 | March 1, 2021 | Elec2020-NCR-TaguigCity&Pateros-003 | DTP-CY-INFRA-006 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | LORBEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 305467 | Maria Concepcion Cruz HS | PATEROS | 1 | 1 | UPGRADING |  | 3781382.22 | 3781382.22 | COMPLETED | 1 | March 16, 2021 | February 24, 2021 | Elec2020-NCR-TaguigCity&Pateros-002 | DTP-CY-INFRA-007 | 11-26-2019 | 2019-02-12 | 12-20-2020 | 2020-08-01 | 11-16-2020 | AYZARIZ CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Taguig | 136896 | Pateros ES | PATEROS | 1 | 1 | UPGRADING |  | 13616612.01 |  | COMPLETED | 1 |  |  | Elec2020-NCR-TaguigCity&Pateros-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | UPGRADING |  | 15850864.57 |  | COMPLETED | 1 |  |  | Elec2020-NCR-ValenzuelaCity-002 | [7 empty] | awarded (report as of sept 2021) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | UPGRADING |  | 15549594.13 |  | COMPLETED | 1 | 2021-05-29 |  | Elec2020-NCR-ValenzuelaCity-001 | INFRA-EPA-BEFF-2020-09-0002(LII) | 2019-11-27 | 2019-12-05 | 2019-12-17 | 2019-12-27 | 2020-10-01 | Steven Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2024 | NCR | City of San Juan | 136749 | Kabayanan ES | CITY OF SAN JUAN | Lone | 1 | Upgrading of Electrical System | 1 | 3995816.45 | 3882858.23 | COMPLETED | 1 | 2025-05-09 | 2025-04-25 | ELEC2024-NCR-SAN JUAN-001 | INFRA2024-003 | 2024-06-19 | 2024-06-27 | 2024-07-09 | 2024-10-22 | 2024-12-20 | Sherf Builders Corp. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.9 | 0.1 |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Las Piñas City | 320303 | Las Piñas National High School - Gatchalian Annex | CITY OF LAS PIÑAS | Lone | 1 | Upgrading of Electrical System | 1 | 2190261.83 | 2183370.17 | COMPLETED | 1 | 2024-12-25 |  | 2024-06-I-03 | 2024-06-I-03 | 27/06/2024 | 2024-07-05 | 2024-07-18 | 2024-08-01 | 2024-08-27 | Image Builders and General Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1st | 1 | Upgrading of Electrical System | 1 | 6771638.93 | 6042143.96 | ONGOING | 0.5 | 2025-07-27 |  | PB-SDO-MKT-2024-007 | SDO-MKT-25-005 | November 9, 2024 | November 15, 2024 | November 27, 2024 | December 2, 2024 | 2025-02-27 | Zaneya Builders & Supply | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.5 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2nd | 1 | Upgrading of Electrical System | 1 | 7896898.69 | 7105888.76 | ONGOING | 0.5 | 2025-08-26 |  | PB-SDO-MKT-2024-006 | SDO-MKT-25-004 | November 9, 2024 | November 15, 2024 | November 27, 2024 | December 2, 2024 | 2025-02-27 | Zaneya Builders & Supply | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.5 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | Lone | 1 | Electrical Service Entrance Upgrade | 1 | 13000000 | 12940519.92 | ONGOING | 0.7 |  |  |  | 2024-infra-08-0001 | 2024-06-28 | 2024-07-05 | 2024-07-19 | 2024-07-25 | 2024-07-29 | MRRM Trading and Construction | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.7 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Mandaluyong City | 136656 | Dona Basilica Yangco ES | CITY OF MANDALUYONG | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2583423.88 | 2544672.53 | ONGOING | 0.95 | 2025-05-06 | 2025-05-06 | ELEC-2024-MANDALUYONG-001 | OSEC-NCR-24-7842 | 2024-10-24 | 2024-11-05 | 2024-11-12 | 2024-11-14 | 2025-01-06 | E. AGLAHI URBAN BUILDERS | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1st | 1 | Upgrading of Electrical System | 1 | 1577374.98 | 1527148.22 | COMPLETED | 1 | 2024-12-02 | 2024-12-17 |  |  | 2024-05-08 | 2024-05-18 | 2024-05-28 | 2024-06-25 | 2024-09-02 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | Upgrading of Electrical System | 1 | 7230312.11 | 7185247.61 | ONGOING | 0.95 | 2025-03-02 |  |  |  | 2024-05-08 | 2024-05-18 | 2024-05-28 | 2024-06-25 | 2024-09-02 | AYZARIS CORPORATION | Currently applied a load upgrade in Meralco. Subject for final inspection and punchlisting | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4th | 1 | Upgrading of Electrical System | 1 | 7110414.41 | 7096791.7 | ONGOING | 0.65 | June, 2025 | [8 empty] | JKK CONSTRUCTION SERVICES | dates of NOA, Contract and NTP will be revised due to late issunace of SARO and obligation | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.65 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | Lone | 1 | Upgrading of Electrical System | 1 | 22251970.63 | 22199967.28 | COMPLETED | 1 | 2025-02-07 |  |  | # 07-02 | 2024-05-08 | 2024-05-16 | 2024-05-29 | 2024-06-14 | 2024-07-31 | Marakesh Enterprise | Date Started: 8/20/24 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | Lone | 1 | Upgrading of Electrical System | 1 | 5240523.38 | 5214577.9 | ONGOING | 0.98 | 2024-10-31 |  | BAC-PB-2024-2 | BAC-PB-2024-2 | 2024-05-16 | 2024-06-04 | 2024-06-18 | 2024-06-25 | 2024-07-22 | MRRM Trading and Construction | With approved Time Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.98 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Paranaque City | 136762 | Don Galo Elementary School | CITY OF PARAÑAQUE | 1st | 1 | Upgrading of Electrical System | 1 | 3808280.23 | 3758684.08 | COMPLETED | 1 | 2025-05-05 | 2025-05-02 | 038B | 038B | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-05 | 2025-02-10 | Open Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.6 | 0.4 |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | Lone | 1 | Upgrading of Electrical System | 1 | 1850561.24 | 1280750.73 | COMPLETED | 1 | 2024-10-27 |  | SDOPC 2024-5-008-PB | CA-2024-08-012 | 2024-05-02 | 2024-05-10 | 2024-05-28 | 2024-06-13 | 2024-08-07 | Open Builders | on going construction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 10061720.23 | 9995257.7 | COMPLETED | 1 | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 4) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136564 | Pura V. Kalaw ES | QUEZON CITY | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 11242015.08 | 11210528.83 | COMPLETED | 1 | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136583 | Aurora A. Quezon ES | QUEZON CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 8426070.39 | 8412019.86 | COMPLETED | 1 | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136573 | Pinyahan ES | QUEZON CITY | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 9221987.36 | 9175352.54 | COMPLETED | 1 | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 3) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 10806050.43 | 10589934.13 | ONGOING | 0.35 | 2025-01-13 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 5) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-07-17 | E.M. CUERPO, INC. | mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.35 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Quezon City | 136519 | Lucas R. Pascual Memorial Elementary School | QUEZON CITY | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 9211007.25 | 9026791.12 | ONGOING | 0.5 | 2025-01-13 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 5) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-07-17 | E.M. CUERPO, INC. | mobilization | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.5 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Quezon City | 136513 | New Era ES | QUEZON CITY | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 8400050.23 | 8388831.82 | COMPLETED | 1 | 2024-12-06 |  | INFRA 001, s. 2024 | SDO-2024-INFRA-001 (LOT 4) | 2023-11-30 | 2023-12-11 | 2023-12-22 | 2024-01-08 | 2024-06-20 | AYZARIS CORPORATION | 180 CD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Taguig City and Pateros | 136879 | Ususan Elementary School | TAGUIG CITY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2508500.44 | 2486910.13 | COMPLETED | 1 |  |  |  | DTP-CY2024-INFRA-001 | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-31 | Sherf Builders Corp. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0.95 | 0.05 |  | 5.25 | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Taguig City and Pateros | 320612 | Gat. Andres Bonifacio High School | TAGUIG CITY | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 4579971.25 | 4558777.19 | COMPLETED | 1 |  |  |  | DTP-CY2024-INFRA-001 | 2024-07-31 | 2024-08-07 | 2024-08-19 | 2024-08-27 | 2024-10-31 | ST. GABRIEL BUILDERS | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | NCR | Valenzuela City | 136823 | Constantino Elementary School | CITY OF VALENZUELA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5169323.52 | 5139323 | ONGOING | 0.4 |  |  |  | SDO-VAL-PB-BEFF-ELECT-2024-12-0003 | Sept. 20, 2024 | Sept. 30, 2024 | Oct . 14, 2024 | Oct. 17, 2024 | Dec. 27, 2024 | Hawkstow Cosntruction and Development | 120 CD | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.4 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | NCR | Valenzuela City | 136817 | Paso de Blas Elementary School | CITY OF VALENZUELA | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 7579323.14 | 7549323 | ONGOING | 0.4 |  |  |  | SDO-VAL-PB-BEFF-ELECT-2024-12-0003 | Sept. 20, 2024 | Sept. 30, 2024 | Oct . 14, 2024 | Oct. 17, 2024 | Dec. 27, 2024 | Hawkstow Cosntruction and Development | 120 CD | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.4 | 0 |  |  | UPGRADING |  |  | ONGOING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%