## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 943148.5 |  | 933992.7 | completed | 1 | February 28, 2025 | February 7, 2025 | WINS2024-NCR-SANJUAN-002 | INFRA2024-004 | June 28, 2024 | July 8, 2025 | July 18, 2024 | November 11, 2024 | December 20, 2024 | Sherf Builders Corp | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 1098292.86 |  | 884385.37 | completed | 1 | October 14, 2024 | September 26, 2024 | WINS2024-NCR-SANJUAN-001 | INFRA-2024-001 | December 8, 2023 | December 15, 2023 | January 4, 2024 | January 9, 2024 | August 14, 2024 | J.G Mendoza Builders | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 558579.85 |  | 553107.2 | completed | 1 | February 17, 2025 | February 7, 2025 | WINS2024-NCR-SANJUAN-002 | INFRA2024-004 | June 28, 2024 | July 8, 2025 | July 18, 2024 | November 11, 2024 | December 20, 2024 | Sherf Builders Corp | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | Makati City | 136703 | Hen. Pio del Pilar ES Main | CITY OF MAKATI | 1st | 1 |  | Repair of School Clinic | 750000 |  | 748911.83 | ongoing | 0.1 | July 18, 2025 |  | PB-SDO-MKT-2024-008 | SDO-MKT-25-013 | November 29, 2024 | December 6, 2024 | December 18, 2024 | December 23, 2024 | May 19, 2025 | J.R.C.F Construction | On-going
SCHOOL HEALTH FACILITIES 2024 | NCR | Mandaluyong City | 500332 | Highway Hills Integrated School | CITY OF MANDALUYONG | Lone | 1 |  | Repair of classroom to be used/Converted to School Clinic | 750563.88 |  | 723815.73 | ongoing | 0.1 | March 20, 2025 | March 20, 2025 | MANDALUYONG-003 | OSEC-NCR-221-7805 | October 24, 2024 | November 5, 2024 | November 12, 2024 | November 13, 2024 | January 6, 2025 | MAAV CONSTRUCTION SERVICES | for mobilization; with subaro downloaded already; Batch 15
SCHOOL HEALTH FACILITIES 2024 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1st | 1 |  | Construction of School Clinic | 5000000 |  | 4949991.33 | COMPLETED | 1 | November 24, 2024 | May 6, 2025 |  |  | May 8, 2024 | May 18, 2024 | May 28, 2024 | June 25, 2024 | September 2, 2024 | LARZEN-DUTHCER CONSTRACTOR CORPORATION | Delayed due to double handling and typhoons
SCHOOL HEALTH FACILITIES 2024 | NCR | Manila | 136428 | Gregoria de Jesus ES | TONDO | 2nd | 1 |  | Construction of School Clinic | 5000000 |  | 3761368.61 | COMPLETED | 1 | November 24, 2024 | December 2, 2024 |  |  | May 8, 2024 | May 18, 2024 | May 28, 2024 | June 25, 2024 | September 2, 2024 | OPEN BUILDERS INCORPORATED
SCHOOL HEALTH FACILITIES 2024 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | Lone | 1 |  | Repair of School Clinic | 947962.57 |  | 943482.23 | completed | 1 | December 3, 2024 | December 3, 2024 | 2024-006 | 2024-006 | June 21, 2024 | June 24, 2024 | June 26, 2024 | June 28, 2024 | September 4, 2024 | Ayana Construction | Received sub-aro August 12, 2024
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136769 | Baclaran Elementary School Unit II | CITY OF PARAÑAQUE | 1st | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 1 | August 18, 2024 | August 16, 2024 | PB-2024-Infra01a | PB-2024-Infra01a | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 1 | August 18, 2024 | August 16, 2024 | PB-2024-Infra01d | PB-2024-Infra01d | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2nd | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 1 | August 18, 2024 | August 16, 2024 | PB-2024-Infra01b | PB-2024-Infra01b | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 137129 | Don Bosco Elementary School | CITY OF PARAÑAQUE | 2nd | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 1 | August 18, 2024 | August 16, 2024 | PB-2024-Infra01c | PB-2024-Infra01c | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | NCR | Pasig City | 136717 | Ilugin Elementary School | CITY OF PASIG | Lone | 1 |  | Rehabilitation of clinic | 1290256 |  | 997541.22 | completed | 1 | April 10, 2025 | April 8, 2024 | PB-2024-Infra01a | PB-2024-Infra01a | June 27, 2024 | July 4, 2024 | July 29, 2024 | August 12, 2024 | December 11. 2024 | Emica Builders and Supply
SCHOOL HEALTH FACILITIES 2024 | NCR | Pasig City | 136719 | Liberato Damian Elementary School | CITY OF PASIG | Lone | 1 |  | Rehabilitation of clinic | 1290256 |  | 997541.22 | completed | 1 | April 10, 2025 | April 8, 2024 | PB-2024-Infra01b | PB-2024-Infra01b | June 27, 2024 | July 4, 2024 | July 29, 2024 | August 12, 2024 | December 11. 2024 | Emica Builders and Supply
SCHOOL HEALTH FACILITIES 2024 | NCR | Taguig City and Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1st | 1 |  | Repair of School Clinic (9.8 x 11.50m) | 1300000 |  | 1269999.79 | completed | 1 | March 14, 2025 | April 22, 2025 | DTP-CY2024-infra-001 | DTP-CY2024-infra-001 | July 31, 2024 | August 7, 2024 | August 19, 2024 | August 27, 2024 | January 3, 2025 | Jepa Construction and Development Corp. | with subaro downloaded already batch 15
SCHOOL HEALTH FACILITIES 2024 | NCR | Taguig City and Pateros | 136881 | Bagong Tanyag Elementary School - Annex A | TAGUIG CITY | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 350000 |  | 347254.52 | completed | 1 | November 27, 2024 | November 11, 2024 | DTP-CY2024-infra-054 | BAC-SVP-2024-40 | August 1, 2024 | August 5, 2024 | August 5, 2024 | August 8, 2024 | October 14, 2024 | Sherf Builders Corporation | with subaro downloaded already batch 13

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%