## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45 | Status as of July 4, 2025
QRF 2019 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | 60 | REPAIR OF CLASSROOMS | 13562619.87 | 1 | 13517578.74 | Completed | 1 |  |  |  |  | 2019-06-04 | 2019-06-11 | 2019-07-01 | 2019-07-09 |  | MMEEN Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 1 | 0 |  | previous yrs | TORNADO |  |  |  | REPAIR | Completed
QRF 2021 | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | 0 | 1 | 9 | FIRE INCIDENT | 2263841.54 | 1 | 2252902.36 | completed | 1 | [10 empty] | Post Qualification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | previous yrs |  |  |  |  | REPLACEMENT | completed
QRF 2021 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 103 | TY ULYSSES | 26196823.18 | 1 | 26027440.46 | Completed | 1 |  |  | QRF-2021-NCR-MARIKINA CITY-001 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 103 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 48 | TY ULYSSES | 12499062.18 | 1 | 12394039.4 | Completed | 1 |  |  | QRF-2021-NCR-MARIKINA CITY-002 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 48 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 | 1 | 51 | TY ULYSSES | 10415199.95 | 1 | 10311102.1 | Completed | 1 |  |  | QRF-2021-NCR-MARIKINA CITY-003 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | DREAMWORX BUILDER & TRADING INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 51 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | NCR | Manila | 305294 | Jose P. Laurel High School | TONDO | 2 | 1 | 4 | REPAIR/ REHABILITATION | 1400000 | 1 | 1366297.64 | Completed | 1 | [9 empty] | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | previous yrs |  |  |  |  | REPAIR | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%