## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 8995156.39 | 1 | 8526166.78 | Completed | 1 | October 27, 2021 | April 2024 |  | 2021-06-016 | April 8,2021 | April 15, 2021 | April 27,2021 | June 23,2021 | June 28,2021 | KNB Construction | [11 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region II | Cagayan | 102442 | Aparri East CS | APARRI | 1 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 8951555.83 | 1 |  | Reverted | 0 | [21 empty] | 0 | [7 empty] | REVERTED
GABALDON 2020 | Region II | Cagayan | 102403 | Amulung East CS | AMULUNG | 3 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 8667454.4523 | 1 | 5526283.97 | Completed | 1 | October 27, 2021 | April 2024 |  | 2021-06-017 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 23,2021 | June 28,2021 | KNB Construction | [11 empty] | 1 |  |  | 4.24 |  | cy 2024 |  |  | Completed
GABALDON 2020 | Region II | Nueva Vizcaya | 104202 | Imugan ES | Santa Fe | 0 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 7013953.09 | 1 | 7915455.79 | Completed | 1 | August 29, 2021 | November 5, 2021 |  | 2021-02-004 |  |  | December 17, 2020 | February 23,2021 | March 1, 2021 | Pecdasen Builders | [11 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2021 | Region II | Batanes | 102316 | Itbayat Central School | ITBAYAT | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 23912552 | 1 | 23896225.01 | Completed | 1 | December 27, 2021 | April 28, 2023 |  | 2021-06-015 | April 6, 2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 29, 2021 | Pecdasen Builders | Total CA due to variation: 24,376,207.54 | [10 empty] | 1 |  |  | 2.23 | Regional Office | CY 2023 |  |  | Completed
GABALDON 2021 | Region II | Nueva Vizcaya | 104089 | Kongkong Elementary School | KASIBU | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6795389 | 1 | 4371705.54 | COMPLETED | 1 | October 28, 2021 | January 10,2022 |  | 2021-06-013 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 29, 2021 | Zyrrone Construction | Total CA due to variation: 4,798,651.92 | [10 empty] | 1 |  |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 9764168 | 1 | 6878702.89 | COMPLETED | 1 | October 28, 2021 | September 2023 |  | 2021-06-014 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 28, 2021 | Lucky Gems Construction | [11 empty] | 1 |  |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2022 | Region II | Batanes | 102322 | Ivana Elementary School | IVANA | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 17516777.66 | 1 | 12530440.87 | Completed | 1 | February 07, 2024 | March 27, 2025 | 2022-07-0112 | 2022-07-0112 | July 12, 2022 | July 12, 2022 | August 02, 2022 | October 17, 2022 | October 20, 2022 | Wakaii Construction | Completed | [10 empty] | 0.85 |  |  | 5.25 | Division Office |  |  |  | Ongoing
GABALDON 2023 | Region II | Nueva Vizcaya | 104173 | Solano East CS | SOLANO | 0 | 1 | 9 | 1 | Restoration & Conservation of Gabaldon Building | 12975814.87 | 1 | 8950988.1 | COMPLETED | 1 | April 7, 2024 | September 15, 2024 | PB5-001-SDONV-GABALDON-SECS-INFRA | PB5-001-SDONV-GABALDON-SECS-INFRA | May 19, 2023 | May 25, 2023 | June 6, 2023 | July 10, 2023 | August 4, 2023 | Pecdasen Builders | with time extension and additional works Savings Contract: 4,024,727.00 CD: 90 CD | [10 empty] | 1 |  |  | 7.24 | Division Office |  |  |  | COMPLETED
GABALDON 2024 | Region II | Nueva Vizcaya | 104182 | Solano North ES | SOLANO | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 18633863.75 | 1 | 11953716.99 | Ongoing | 0.39 | May 26, 2025 | - | PB 10-001 S.2024 | PB 10-001 S.2024 | August 6, 2024 | August 12, 2024 | August 27, 2024 | October 3, 2024 | December 27, 2024 | KNB CONSTRUCTION | On Going Construction with Variation Order | [10 empty] | 0.1856 |  |  |  | Division Office |  |  | 10 | Ongoing

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%