## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 |  | Construction of School Clinic, Water and Sanitation Facilities - 4-Seater and Group Hadwashing Facility - For Secondary (Option 1B - with Roofing, with Counter, with Tile Finish) | 4975483.73 |  | 3864853.37 | ongoing | 0.96 | SEPTEMBER 14, 2024 |  | Construction of School Clinic, Water and Sanitation Facilities - 4-Seater and Group Hadwashing Facility - For Secondary (Option 1B - with Roofing, with Counter, with Tile Finish) | INFRA 2023-123 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 14, 2024 | MAY 17, 2024 | JIRK CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 3rd | 1 |  | Construction/Repair of Health Facilities | 3516992.21 |  | 1193349.72 | Completed | 1 | March 22, 2025 | March 11, 2025 | Construction/Repair of Health Facilities of Cauayan North Central School | CW-003 S. 2024 | July 2, 2024 | July 10, 2024 | July 23, 2024 | August 6, 2024 | December 23, 2024 | Amianan Construction | with subaro downloaded already; Batch 15
SCHOOL HEALTH FACILITIES 2024 | Region II | City of Ilagan | 500080 | Lupigue Integrated School | ILAGAN CITY (CAPITAL) | 1st | 1 |  | Construction/Repair of Health Facilities | 3004753.81 |  | 2991910.63 | completed | 1 | October 3, 2024 | March 3, 2025 | 10437033 | INF-2024-03 | December 19, 2023 | December 27, 2023 | January 8, 2024 | January 12, 2024 | June 24, 2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES
SCHOOL HEALTH FACILITIES 2024 | Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2nd | 1 |  | Construction/Repair of Health Facilities | 1563881.72 |  | 1512875.56 | Completed | 1 | July 21, 2024 | July 19,2024 | Proj ID No. 2023-11-01 | 2024-0504 | November 11,2023 | November 20,2023 | December 5, 2023 | December 13, 2023 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES
SCHOOL HEALTH FACILITIES 2024 | Region II | Nueva Vizcaya | 300642 | PAIMA NATIONAL HIGH SCHOOL | BAYOMBONG | Lone | 1 |  | Construction/Repair of Health Facilities | 2119125.83 |  | 1486952.49 | COMPLETED | 1 | March 27, 2025 | April 4, 2025 | PB-3-003-SDO-CY2024HWF | PB-3-003-SDO-CY2024HWF | March 19, 2024 | March 17, 2025 | April 5, 2024 | June 24, 2024 | December 27, 2024 | B. Flores Construction and Supply | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region II | Quirino | 104224 | Aglipay West CS | AGLIPAY | Lone | 1 |  | Construction/Repair of Health Facilities | 281498.71 |  | 240747.08 | Completed | 1 | July 22, 2024 | July 17, 2024 | HEALTH FACILITIES 2024 - REGION II - QUIRINO - 001 | 55-12-22-2023 | December 23, 2023 | December 29, 2023 | January 11, 2024 | February 15, 2024 | June 7, 2024 | HABILING CONSTRUCTION | Completed
SCHOOL HEALTH FACILITIES 2024 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4th | 1 |  | Construction/Repair of Health Facilities | 1563881.72 |  | 1407012.83 | not yet started | 0 | August 1, 2025 |  | WINS 2024 - REG II - SANTIAGO - 001 | PI-CB-2024-004 | November 14, 2024 | November 21, 2024 | December 4, 2024 | December 14, 2024 |  | HJM CIBSTRUCTION | To be awarded
SCHOOL HEALTH FACILITIES 2024 | Region II | Tuguegarao City | 300669 | Cataggaman National High School | TUGUEGARAO CITY(Capital) | 3rd | 1 |  | Construction/Repair of Health Facilities | 281498.71 |  |  | under procurement | 0
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 1015926.56 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF FIVE (5) FAUCET HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 148342.88 | BATCH 1 | 145183.24 | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 379853.81 | BATCH 1 | 373662.14 | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102837 | Gaggabutan Elementary School | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102838 | Illuru ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102840 | Liuan ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102844 | Rizal CS | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 |  | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102916 | Cadongdongan ES | SANTA PRAXEDES | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 1 | 2023-01-20 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | 2022-10-23 | GCPK CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 556351.41 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103485 | Dadap Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103489 | Harana Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 155521 | Camarag Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 147432.18 | BATCH 1 |  | COMPLETED | 1 |  |  |  | 2022-06-01 |  |  | 2022-03-22 | 2022-04-04 | 2022-06-02 | EDPIN CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103980 | Ambaguio CS | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242974.69 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103982 | Ammoweg ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155541.67 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103983 | Balong ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 170112.6 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103991 | Labang ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 168465.12 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103992 | Laylaya PS | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 152314.3 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103995 | Napo ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 131576.8 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103996 | Pacdal ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 176412.6 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 137027 | Pihippi ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 137666.8 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 137029 | Hiket ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 147956.8 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104215 | Buenavista ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 172212.6 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104218 | Gov. Juan Manzano ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 121076.8 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104219 | Felix-Juana Brawner Community School | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 167749.48 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104220 | Sawmill ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 186905.91 | BATCH 1 |  | COMPLETED | 1
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104222 | Villa Par-Pale ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 174601.04 | BATCH 1 |  | reverted | 0 | [10 empty] | Failure of Bidding (No taker)
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104374 | Gamis ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 1 |  |  |  |  | 2022-04-28 |  | 2022-05-05 | 2022-05-20 | 2022-08-24 | JIJOMER Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104381 | Lumagui ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 1 |  |  |  |  | 2022-04-28 |  | 2022-05-05 | 2022-05-20 | 2022-08-24 | JIJOMER Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104372 | Cardenas ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 1 |  |  |  |  | 2022-04-28 |  | 2022-05-05 | 2022-05-20 | 2022-08-24 | JIJOMER Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104373 | Dibul ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 1 |  |  |  |  | 2022-04-28 |  | 2022-05-05 | 2022-05-20 | 2022-08-24 | JIJOMER Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104380 | Tres Reyes ES | SAGUDAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 107574.75 | BATCH 2 |  | COMPLETED | 1 | [9 empty] | FNS BUILDERS & ENTERPRISE
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 156518 | La Paz ES Extension Annex | SAGUDAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 2 |  | COMPLETED | 1 | [9 empty] | FNS BUILDERS & ENTERPRISE

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%