## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region III | Mabalacat City | 159536 | Mamatitang PS | MABALACAT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 204313.15 | 201719.65 | COMPLETED | 1 |  | january 10, 2018 | [6 empty] | 2017-12-27 | ANGEL GABRIEL BUILDERS AND REALTY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | UPGRADING | 1 | 173058.28 | 170000 | COMPLETED | 1 | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 | 1 | UPGRADING | 1 | 173058.28 | 170000 | COMPLETED | 1 | 2018-09-22 | 2018-09-22 | [6 empty] | 2018-08-23 | Nulas Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora |  | Baler Stand Alone | BALER | 0 | 1 | UPGRADING | 1 | 1894542.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) | 0 | 1 | UPGRADING | 1 | 1697974.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300673 | Aurora NHS | BALER (Capital) | 0 | 1 | UPGRADING | 1 | 930975.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306504 | Diagyan NHS | DILASAG | 0 | 1 | UPGRADING | 1 | 1902320 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 | 1 | UPGRADING | 2 | 2077387.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 | 1 | UPGRADING | 1 | 1180594.82 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 | 1 | UPGRADING | 1 | 1955011.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 | 1 | UPGRADING | 2 | 2088109.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | 0 | 1 | UPGRADING | 2 | 2064302.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 | 1 | UPGRADING | 1 | 2318025.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 300686 | Ditumabo NHS | SAN LUIS | 0 | 1 | UPGRADING | 1 | 1000358.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 | 1 | UPGRADING | 1 | 2758246.38 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300708 | Luakan National High School | DINALUPIHAN | 1 | 1 | UPGRADING | 1 | 1895363.51 | 1878142.77 | COMPLETED | 1 | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | UPGRADING | 2 | 3272047.49 | 3247080.92 | COMPLETED | 1 | 2018-09-07 |  |  |  | April 24, 2018- May 7, 2018 | 2018-05-03 | 2018-05-21 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300719 | Samal NHS | SAMAL | 1 | 1 | UPGRADING | 1 | 1809224.16 | 1791256.13 | COMPLETED | 1 | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 | 1 | UPGRADING | 1 | 3559235.68 | 3529388.39 | COMPLETED | 1 | 2018-09-07 |  |  |  | May 3-17, 2018 | 2018-05-10 | 2018-05-23 | 2018-06-04 | 2018-07-04 | BQA Construction& Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 306711 | San Francisco Xavier High School | BULACAN | 1 | 1 | UPGRADING | 2 | 5985580.68 | 5060899.37 | COMPLETED | 1 | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300755 | San Pedro National High School | HAGONOY | 1 | 1 | UPGRADING | 2 | 3732220.36 | 3342196.08 | COMPLETED | 1 | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300756 | Sta. Monica National High School | HAGONOY | 1 | 1 | UPGRADING | 2 | 3027526.83 | 2768984.18 | COMPLETED | 1 | 2019-01-27 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-25 | G.M. Caparas Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 2 | 1 | UPGRADING | 2 | 4117936.44 | 3482904.82 | COMPLETED | 1 | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300742 | Guiguinto Nat'l Voc'l. High School | GUIGUINTO | 2 | 1 | UPGRADING | 3 | 6709671.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 | 1 | UPGRADING | 2 | 3003849.46 | 2543748.22 | COMPLETED | 1 | 2019-01-26 |  |  |  | 2018-07-30 | 2018-08-06 | 2018-08-20 | 2018-09-03 | 2018-09-24 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Cabanatuan City | 301045 | Camp Tinio National High School | CABANATUAN CITY | 3 | 1 | UPGRADING | 2 | 2498371.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT | 1 | 1 | UPGRADING | 1 | 341218.2 |  | COMPLETED | 1 | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 306909 | Mabalacat TVS | MABALACAT | 1 | 1 | UPGRADING | 1 | 762937.98 |  | COMPLETED | 1 | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 306942 | Santos Ventura NHS | MABALACAT | 1 | 1 | UPGRADING | 1 | 350614.35 |  | COMPLETED | 1 | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 345342 | SHS w/in Sapang Biabas ES | MABALACAT | 1 | 1 | UPGRADING | 1 | 745566.71 |  | COMPLETED | 1 | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | UPGRADING | 1 | 865728.1 |  | COMPLETED | 1 | 2018-05-24 | [5 empty] | 2018-04-10 | 2018-04-16 | 2018-04-20 | R.S DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | 1 | 2604906.2 | 2573336.85 | COMPLETED | 1 |  |  | MLL2018-06 | MLL2018-06 |  | 2018-05-31 | 2018-06-22 | 2018-07-10 | 2018-07-18 | LOURBEL CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 | 1 | UPGRADING | 2 | 686281.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Munoz Science City | 500630 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 | 1 | UPGRADING | 2 | 752305.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 | 1 | UPGRADING | 2 | 378620.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300801 | Cuyapo National High School | CUYAPO | 1 | 1 | UPGRADING | 2 | 346345.28 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Cuyapo National High School (SHS) | CUYAPO | 1 | 1 | UPGRADING | 2 | 508561.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 | 1 | UPGRADING | 2 | 268199.97 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | UPGRADING | 2 | 415294.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 | 1 | UPGRADING | 2 | 257461.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300869 | Triala NHS | GUIMBA | 1 | 1 | UPGRADING | 2 | 305424.83 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1 | 1 | UPGRADING | 2 | 334163.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Eduardo L. Joson Mem. HS (SHS) | QUEZON | 1 | 1 | UPGRADING | 2 | 380604.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 | 1 | UPGRADING | 2 | 463571.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 | 1 | UPGRADING | 2 | 541860.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300865 | Tabacao National High School | TALAVERA | 1 | 1 | UPGRADING | 2 | 648501.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Carmen NHS (SHS) | ZARAGOZA | 1 | 1 | UPGRADING | 2 | 276511.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 | 1 | UPGRADING | 2 | 402027.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | Carranglan NHS (SHS) | CARRANGLAN | 2 | 1 | UPGRADING | 2 | 352136.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300870 | Llanera National HIgh School | LLANERA | 2 | 1 | UPGRADING | 2 | 245855.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300866 | Talugtug NHS | TALUGTUG | 2 | 1 | UPGRADING | 2 | 323471.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300816 | Macabaclay National High School | BONGABON | 3 | 1 | UPGRADING | 2 | 197600.26 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3 | 1 | UPGRADING | 2 | 267018.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300858 | Sto. Rosario NHS , Sta. Rosa | SANTA ROSA | 3 | 1 | UPGRADING | 2 | 299957.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) | 4 | 1 | UPGRADING | 2 | 374333.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300836 | Lambakin National High School | JAEN | 4 | 1 | UPGRADING | 2 | 538124.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300835 | Putlod-San Jose NHS | JAEN | 4 | 1 | UPGRADING | 2 | 532712.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4 | 1 | UPGRADING | 2 | 312976.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija |  | STA. BARBARA NATIONAL HS (SHS) | SAN ANTONIO | 4 | 1 | UPGRADING | 2 | 450566.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300794 | Calaba National High School | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 325560.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300834 | Pulo NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 452449.94 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 | 1 | UPGRADING | 2 | 384194.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300817 | Magpapalayok NHS | SAN LEONARDO | 4 | 1 | UPGRADING | 2 | 195151.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4 | 1 | UPGRADING | 2 | 347681.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Olongapo City | 162003 | Iram II ES | OLONGAPO CITY | 1 | 1 | SOLAR PANEL | 1 | 2077391.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA | 1 | 1 | UPGRADING | 1 | 2770962.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 | 1 | UPGRADING | 1 | 529630.83 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307106 | JESUS F. MAGSAYSAY TECHNICAL-VOCATIONAL HIGH SCHOOL | CASTILLEJOS | 1 | 1 | UPGRADING | 1 | 359481.51 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160503 | Chiang Chio Te Mem. Aeta School (Ibad PS) | SAN MARCELINO | 1 | 1 | SOLAR PANEL | 1 | 578540.81 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301029 | San Guillermo NHS | SAN MARCELINO | 1 | 1 | UPGRADING | 1 | 555871.38 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307112 | Nagyantok HS | SUBIC | 1 | 1 | UPGRADING | 1 | 238791.09 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 | 1 | UPGRADING | 1 | 433078.49 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307124 | Subic NHS Annex IV - San Isidro HS | SUBIC | 1 | 1 | UPGRADING | 1 | 238791.09 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster I) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301008 | Baquilan Resettlement High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 289720.92 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 2901396.11 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160523 | Burgos ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 787612.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160504 | Cabatuan ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 813993.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307131 | Lakas High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 229562.69 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | MAGUISGUIS IS | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 940096.27 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 281505 | Moraza Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1979019.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301026 | New Taugtog National High School | BOTOLAN | 2 | 1 | UPGRADING | 1 | 302634.44 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 101788 | Owaog-Nebloc Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1963474.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 281503 | Palis Elementary School | BOTOLAN | 2 | 1 | UPGRADING | 3 | 1790672.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160526 | Poon Bato Elementary School | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 782336.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160515 | Villar ES | BOTOLAN | 2 | 1 | SOLAR PANEL | 1 | 782336.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301010 | Cabangan National High School | CABANGAN | 2 | 1 | UPGRADING | 1 | 2678122.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307120 | Pamibian IS | CANDELARIA | 2 | 1 | UPGRADING | 1 | 378399.48 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301004 | Amungan NHS | IBA (Capital) | 2 | 1 | UPGRADING | 1 | 402537.56 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301037 | Zambales NHS | IBA (Capital) | 2 | 1 | UPGRADING | 1 | 2934885.85 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301005 | Bani NHS | MASINLOC | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301007 | Coto High School | MASINLOC | 2 | 1 | UPGRADING | 3 | 524075.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106884 | Felipe E. Estella Elementary School | MASINLOC | 2 | 1 | UPGRADING | 3 | 502782.07 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106891 | Inhobol Elementary School | MASINLOC | 2 | 1 | UPGRADING | 3 | 432186.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307103 | San Salvador HS | MASINLOC | 2 | 1 | UPGRADING | 1 | 320002.7 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | TALTAL NHS | MASINLOC | 2 | 1 | UPGRADING | 1 | 439552.69 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 | 1 | UPGRADING | 1 | 347882.41 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 | 1 | UPGRADING | 1 | 391157.45 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301032 | San Miguel NHS | SAN ANTONIO | 2 | 1 | UPGRADING | 1 | 438055.75 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster II) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | L.A.V. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 160520 | Banawen PS | SAN FELIPE | 2 | 1 | SOLAR PANEL | 1 | 771783.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | SAN FELIPE | 2 | 1 | UPGRADING | 3 | 562157.84 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307104 | San Rafael Technical Vocational High School | SAN FELIPE | 2 | 1 | UPGRADING | 3 | 551263.58 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 106975 | Babuyan ES | SANTA CRUZ | 2 | 1 | SOLAR PANEL | 1 | 976746.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | BOLITOC NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 443158.94 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301014 | Guisguis NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 455413.83 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales |  | LIPAY NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 373296.29 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 301033 | Sta. Cruz NHS | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 294724.19 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region III | Zambales | 307102 | Sta. Cruz NHS - Jesus F. Magsaysay HS Annex | SANTA CRUZ | 2 | 1 | UPGRADING | 1 | 323846.39 |  | COMPLETED | 1 |  |  | INFRA-2018-001 (Cluster III) |  | March 26, 2018 | March 28, 2018 | April 10, 2018 | April 19, 2018 | May 18, 2018 | FBF INDUSTRIAL SALES AND SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 345279 | Angeles City Senior High School | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 307203 | Claro M. Recto ICT High School | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500129 | Gov. Rafael L. Lazatin IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500132 | Malabanias IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Angeles City | 500133 | Sto. Domingo IS | ANGELES CITY | 1 | 1 | UPGRADING | Batch 3 | 173062.6 |  | COMPLETED | 1 |  | December 8, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 4750801.05 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104535 | Mabatang ES | ABUCAY | 1 | 1 | UPGRADING | Batch 3 | 1297834.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104585 | Pagalanggang ES | DINALUPIHAN | 1 | 1 | UPGRADING | Batch 3 | 1007934.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 306602 | Morong NHS-Annex (Mabayo) | MORONG | 1 | 1 | UPGRADING | Batch 1 | 1284158.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 104546 | Parang ES | BAGAC | 2 | 1 | UPGRADING | Batch 3 | 1229688.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 300700 | Saysain NHS | BAGAC | 2 | 1 | UPGRADING | Batch 1 | 1284158.34 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bataan | 306601 | Justice E.A.Gancayco MHS | ORION | 2 | 1 | UPGRADING | Batch 1 | 3303044.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300743 | Iba National High School | HAGONOY | 1 | 1 | UPGRADING | Batch 3 | 1614783.76 | 1444945.67 | COMPLETED | 1 | 2020-11-13 | 2020-10-09 | 19-08-029 | 19-10-037 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | UPGRADING | Batch 3 | 8532066.56 | 8469340.48 | COMPLETED | 1 | 2020-11-13 |  | 19-08-029 | 19-10-038 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | ADIMRE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300749 | Salapungan NHS | SAN RAFAEL | 3 | 1 | UPGRADING | Batch 3 | 2288132.04 | 2226335.96 | COMPLETED | 1 | 2020-11-13 | 2020-03-06 | 19-08-029 | 19-10-039 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | UPGRADING | Batch 3 | 6307674.26 | 6196017.91 | COMPLETED | 1 | 2020-11-13 | 2020-03-06 | 19-08-029 | 19-10-040 | 2019-07-15 | 2019-07-23 | 2019-08-05 | 2019-08-27 | 2019-10-25 | EIRISH BUILDERS & SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Gapan City | 300822 | Maruhat NHS | CITY OF GAPAN | 4 | 1 | UPGRADING |  | 1122771.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Malolos City | 104893 | Mambog ES | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 186661.35 |  | COMPLETED | 1 |  |  |  |  | 11/27-12/4/2020 | 2020-04-12 | 18/12/2020 | 28/12/2020 | 20/01/2021 | SAMENARA CONSTRACTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Malolos City | 104878 | Sta. Isabel ES | CITY OF MALOLOS (Capital) | 1 | 1 | UPGRADING | Batch 3 | 483647.78 |  | COMPLETED | 1 |  |  |  |  | 11/27-12/4/2020 | 2020-04-12 | 18/12/2020 | 28/12/2020 | 20/01/2021 | SAMENARA CONSTRACTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Olongapo City | 301056 | Kalalake NHS | OLONGAPO CITY | 1 | 1 | UPGRADING | Batch 1 | 911338.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | San Jose City | 300800 | San Jose City National High School (formerly Constancio Padilla National High School) | SAN JOSE CITY | 2 | 1 | UPGRADING | Batch 1 | 1445828.67 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300954 | Buenlag NHS | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106467 | Cardona ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300959 | Cardona NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 307007 | Corazon C. Aquino High School | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300965 | Gerona Western National High School | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 106452 | Magaspac ES | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | SOLAR PANEL |  |  |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2019 | Region III | Tarlac | 300995 | Tagumbao NHS | GERONA | 2 | 1 | SOLAR PANEL | Batch 3 | 6138939 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | N | 0 | 0 |  |  | SOLAR |  |  | REVERTED
ELECTRIFICATION 2020 | Region III | Aurora | 104409 | Baler CS | BALER (Capital) | 0 | 1 | UPGRADING |  | 2754098.39 | 2150843.33 | COMPLETED | 1 | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-001 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104410 | Calabuanan ES | BALER (Capital) | 0 | 1 | UPGRADING |  | 2747466.86 | 2703973.25 | COMPLETED | 1 | 2020-11-29 | 2020-10-20 | Elect 2020-RIII-Aurora-014 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | MARVELOUS QUEJADA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 500729 | Carmen T. Valenzuela IS | BALER (Capital) | 0 | 1 | UPGRADING |  | 2814470.95 | 1920347.77 | COMPLETED | 1 | 2020-11-29 | 2020-10-20 | Elect 2020-RIII-Aurora-017 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | FNR BUILDERS & SONS SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104418 | Suklayin ES | BALER (Capital) | 0 | 1 | UPGRADING |  | 2747466.86 | 2718464.72 | COMPLETED | 1 | 2021-01-21 | 2020-12-17 | Elect 2020-RIII-Aurora-015 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-08-24 | ADROIT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104423 | Casiguran CS | CASIGURAN | 0 | 1 | UPGRADING |  | 2810360.13 | 2802325.7 | COMPLETED | 1 | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-002 |  | MAY 18-JUNE 8, 2020 | 2020-06-08 | 2020-06-08 |  | 2020-10-30 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104435 | Dilasag CS | DILASAG | 0 | 1 | UPGRADING |  | 2810360.13 | 2790107.8 | COMPLETED | 1 | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-003 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Aurora | 104528 | San Luis CS | SAN LUIS | 0 | 1 | UPGRADING |  | 4449330.67 | 4443037.53 | COMPLETED | 1 | 2021-01-21 | 2020-12-22 | Elect 2020-RIII-Aurora-008 |  | NOV 6-22, 2019 | 2019-11-23 | 2019-11-23 |  | 2020-10-07 | VB DONATO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Balanga City | 104556 | Cataning Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 3532711.81 |  | COMPLETED | 1 |  |  | Elec2020-RIII-Balanga City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Balanga City | 104567 | Tenejero Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | UPGRADING |  | 3209203.21 |  | COMPLETED | 1 |  |  | Elec2020-RIII-Balanga City-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300697 | BONIFACIO CAMACHO NHS | ABUCAY | 1 | 1 | UPGRADING |  | 2278518.41 | 2248093.68 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-022 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | BQA CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300704 | Jose C. Payumo Jr. MHS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 4192535.54 | 4172300.65 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-010 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 306604 | Magsaysay NHS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 2311861.84 | 2291845.85 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-011 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 306603 | Sta. Lucia HS | DINALUPIHAN | 1 | 1 | UPGRADING |  | 2327471.15 | 2317468.92 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-007 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300701 | Balsik NHS | HERMOSA | 1 | 1 | UPGRADING |  | 3066886.3 | 3056859.34 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-012 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300713 | Morong NHS | MORONG | 1 | 1 | UPGRADING |  | 4671888.25 | 4651212.69 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-014 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300714 | Nagbalayong NHS | MORONG | 1 | 1 | UPGRADING |  | 1456968.28 | 1436554.48 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-003 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | FBF INDUSTRIAL SALES & SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 104549 | Quinawan ES | BAGAC | 2 | 1 | UPGRADING |  | 562626.67 | 0 | COMPLETED | 1 | October, 2020 |  | Elec2020-RIII-Bataan-005 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300711 | MARIVELES NHS -POB. IPAG CAMPUS | MARIVELES | 2 | 1 | UPGRADING |  | 1401805.24 | 1391799.79 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-021 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | MECON SYSTEM SERVICE AND MAINTENANCE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bataan | 300717 | Dr. Victoria B. Roman MHS | PILAR | 2 | 1 | UPGRADING |  | 2183855.55 | 2153139.33 | COMPLETED | 1 | November, 2020 | November, 2020 | Elec2020-RIII-Bataan-002 |  | Nov. 19, 2019-Dec. 3, 2019 | Nov. 28, 2020 | Dec. 11, 2019 | Dec. 16, 2019 | July, 2020 | BQA CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300729 | Masagana HS | PANDI | 2 | 1 | UPGRADING |  | 6750794.78 | 6604438.41 | COMPLETED | 1 | December, 2020 |  | Elec2020-RIII-Bulacan-003 |  | June , 2020 | July , 2020 | August , 2020 | August , 2020 | August , 2020 | EIRISH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300758 | Minuyan National High School | Norzagaray | 3 | 1 | UPGRADING |  | 6186616.21 | 6145855.2798 | COMPLETED | 1 | 2021-07-20 |  | Elec2020-RIII-Bulacan-001 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | UPGRADING |  | 5695225.24 | 5655064.2023 | COMPLETED | 1 | 2021-07-20 |  | Elec2020-RIII-Bulacan-006 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Bulacan | 300767 | Pulong Buhangin NHS | SANTA MARIA | 4 | 1 | UPGRADING |  | 6527480.37 | 6480000 | COMPLETED | 1 | 2021-07-20 |  | Elec2020-RIII-Bulacan-002 |  | 2019-12-04 | 2019-12-11 | 2019-12-23 | 2020-01-21 | 2020-10-09 | Eirish Builders & Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Gapan City | 300815 | Kapalangan National High School | Gapan City | 4 | 1 | UPGRADING |  | 326950.41 | 326138.2 | COMPLETED | 1 | 2020-01-22 | 2020-01-22 | Elec2020-RIII-GapanCity-001 |  | November 13, 2019 | November 22, 2019 | December 9, 2019 | Awating Release of SubAro | Awating Release of SubAro | JOYNIELTIN CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 106077 | Dau Homesite ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 1420751.96 | 1419235.4 | COMPLETED | 1 | 2020-09-16 |  | Elec2020-RIII-Mabalacat City-002 |  | 2019-11-19 | 2019-11-26 | 2019-12-10 | 2019-12-27 | 2020-08-03 | R.S. DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 106065 | Haduan Negrito ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 1024241.55 |  | COMPLETED | 1 |  |  | Elec2020-RIII-Mabalacat City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Mabalacat City | 159529 | Monicayo ES | MABALACAT CITY | 1 | 1 | UPGRADING |  | 394039.1 | 391741.94 | COMPLETED | 1 | 2020-09-16 |  | Elec2020-RIII-Mabalacat City-006 |  | 2019-11-19 | 2019-11-26 | 2019-12-10 | 2019-12-27 | 2020-08-03 | R.S. DELOS REYES ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306803 | BUKLOD PALAD HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 758189.03 | 758190 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-018 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300787 | FORT MAGSAYSAY HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 1206863.67 | 1206864 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-019 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300828 | PALAYAN CITY NAT. HIGH SCHOOL | PALAYAN CITY | 3 | 1 |  |  | 843725.53 | 843726 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-008 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306801 | STA. ROSA NATIONAL HIGH SCHOOL (SHS) | STA. ROSA | 3 | 1 |  |  | 827454.32 | 827455 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-022 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija |  | Mariano Llanera NHS | CABIAO | 4 | 1 |  |  | 1109828.01 | 1109829 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-025 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306823 | STA. ISABEL HIGH SCHOOL | CABIAO | 4 | 1 |  |  | 925384.82 | 925385 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-014 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300808 | GEN. TINIO NAT. HIGH SCHOOL | GEN. TINIO | 4 | 1 |  |  | 983739.35 | 983740 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-002 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306821 | DR. JOSE LAPUZ SALONGA HIGH SCHOOL | SAN ANTONIO | 4 | 1 |  |  | 897358.69 | 897359 | COMPLETED | 1 | October , 2020 |  | Elec2020-RIII-Nueva Ecija-001 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300820 | MALLORCA NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 592471.04 | 592472 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-005 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 300844 | SAN ANTON NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 472896.56 | 472897 | COMPLETED | 1 | October , 2020 |  | Elec2020-RIII-Nueva Ecija-010 |  | June , 2020 | July , 2020 | July , 2020 | August , 2020 | August , 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Nueva Ecija | 306833 | SAN LEONARDO NAT. HIGH SCHOOL | SAN LEONARDO | 4 | 1 |  |  | 841861.57 | 841862 | COMPLETED | 1 |  |  | Elec2020-RIII-Nueva Ecija-012 |  | 2020-08-06 | 6/15/2020 | 6/27/2020 | 2020-10-07 | 7/23/2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 160501 | Judd Hendricks Mem. Aeta School | SAN MARCELINO | 1 | 1 | SOLAR PANEL |  | 2180222.02 | 2173368.62 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-008 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 107020 | Subic Central School | SUBIC | 1 | 1 | UPGRADING |  | 1312135.13 | 1304339.82 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-001 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106869 | Amungan Elementary School | IBA (Capital) | 2 | 1 | UPGRADING |  | 537823.72 | 536327.13 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-006 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106863 | San Agustin Elementary Schools | IBA (Capital) | 2 | 1 | UPGRADING |  | 935743.25 | 931806.6 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-003 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106881 | Sta. Barbara Elementary School | IBA (Capital) | 2 | 1 | UPGRADING |  | 655900.23 | 654063.74 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-004 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106887 | Bani Relocation Elementary School | MASINLOC | 2 | 1 | UPGRADING |  | 429579.36 | 428409.44 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-005 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106893 | Masinloc Central Elementary School | MASINLOC | 2 | 1 | UPGRADING |  | 1020681.07 | 1016189.63 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-013 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106974 | Almasin Elementary School | SANTA CRUZ | 2 | 1 | SOLAR PANEL |  | 2167130.4 |  | COMPLETED | 1 | November 2020 |  | Elec2020-RIII-Zambales-011 |  | June 2020 | July 2020 | July 2020 | August 2020 | September 2020 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2020 | Region III | Zambales | 106986 | Sta. Cruz North Central School | SANTA CRUZ | 2 | 1 | UPGRADING |  | 1014004.43 | 1009608.36 | COMPLETED | 1 | November 2020 | November 2020 | Elec2020-RIII-Zambales-002 |  | December 13, 2019 | December 17, 2019 | January 8, 2020 | March 9, 2020 | July 2020 | ILS POWER ENGINEERING SERVICE & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 704044.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300823 | Mataas Na Kahoy National High School | GENERAL MAMERTO NATIVIDAD | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 731715.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. HS | LAUR | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 592087.44 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 371795.43 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 524063.33 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2024 | Region III | Aurora | 104408 | Anacleto V. Mijares ES | BALER (Capital) | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2929449.51 | 2922317.53 | COMPLETED | 1 | 2024-10-25 | 2024-10-23 | 23-10-472 | SGOD-INFRA-97-1 | May 30,2024 | 2024-06-07 | June 19,2024 | August 9,2024 | 2024-08-14 | A. DELA CRUZ BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Aurora | 104422 | Calantas ES | CASIGURAN | Lone | 1 | Upgrading Electrical System On Grid Schools | 1 | 2010000 | 2005382.11 | COMPLETED | 1 | 2024-10-25 | 2024-10-23 | 23-10472 | SGOD-INFRA-97-2 | May 30,2024 | 2024-06-07 | June 19,2024 | August 9,2024 | 2024-08-14 | A. DELA CRUZ BUILDERS INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Balanga City | 104560 | G.L. David Memorial Elementary School | CITY OF BALANGA (Capital) | 2nd | 1 | Energization of Electrical System (Overhead System) | 1 | 2467323.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 1219998.48 | 993809.21 | COMPLETED | 1 | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 104683 | Pablo R. Roman ES | ORION | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2627403.15 | 2139885.82 | COMPLETED | 1 | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bataan | 104593 | San Benito ES | DINALUPIHAN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2491679.75 | 2030190.71 | COMPLETED | 1 | 2024-09-07 |  |  |  | October 25, 2023-November 21, 2023 | 2023-11-07 | 2023-11-21 | 2023-12-13 | 2024-06-04 | Mecon Systems Service & Maintenance Product |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300768 | Calumpit NHS (San Marcos NHS) | CALUMPIT | 1st | 1 | Upgrading of Electrical System | 1 | 5389963.56 | 3937612.4 | COMPLETED | 1 | 2025-04-27 |  | PB-24-006 | PB-24-07-012 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 306708 | Maronquillo National High School | SAN RAFAEL | 3rd | 1 | Upgrading of Electrical System | 1 | 3885106.25 | 3843446.74 | COMPLETED | 1 | 2025-04-27 |  | PB-24-003 | PB-24-07-014 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300763 | Obando NHS | OBANDO | 4th | 1 | Upgrading of Electrical System | 1 | 3787938.56 | 3735985.38 | COMPLETED | 1 | 2025-03-09 |  | PB-24-005 | PB-24-05-009 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-06-05 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Bulacan | 300728 | Bunsuran NHS | PANDI | 5th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 4759527.1 | 4721263.03 | COMPLETED | 1 | 2025-04-27 |  | PB-24-007 | PB-24-07-013 | 2023-12-05 | 2023-12-14 | 2023-12-27 | 2024-01-08 | 2024-07-24 | EIRISH BUILDERS AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Malolos City | 104877 | Santor ES | CITY OF MALOLOS (Capital) | 1st | 1 | Upgrading of Electrical System | 1 | 709634.11 | 709634.11 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Meycauayan City | 500965 | Saluysoy Integrated School | CITY OF MEYCAUAYAN | 3rd | 1 | Upgrading of Electrical System | 1 | 7000000 | 6816900.88 | ONGOING | 0.8 | 2024-08-30 |  | 2023-002-Infra |  |  |  | 2023-12-15 |  | 2024-06-25 | 3CA BUILDERS CORPORATION | With Time Extension Request | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.8 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 305948 | Simimbaan High School | CUYAPO | 1st | 1 | Installation of Solar Panels | 1 | 997275.75 | 995605.71 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 300870 | Llanera National High School | LLANERA | 2nd | 1 | Installation of Solar Panels | 1 | 1254762.94 | 1250915.91 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 306813 | Bongabon NHS Annex (Vega HS) | BONGABON | 3rd | 1 | Installation of Solar Panels | 1 | 997275.75 | 995605.71 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Nueva Ecija | 305811 | St. Joseph National High School | CABIAO | 4th | 1 | Installation of Solar Panels | 1 | 961963.82 | 960293.78 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Olongapo City | 301051 | Olongapo City National High School | OLONGAPO CITY | 1st | 1 | Upgrading of Electrical System | 1 | 10000000 |  | COMPLETED | 1 |  |  | 2024-06-208 | 2024-06-208 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-01 | 2024-09-18 | EIRISH BUILDERS AND SUPPLY INC. | Awaiting SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 1.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Tarlac | 300996 | Tarlac National High School | CITY OF TARLAC (Capital) | 2nd | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 5072444.44 | 5032432.46 | ONGOING | 0 |  |  |  |  | August 23, 2024 | August 30, 2024 | September 12, 2024 | September 17, 2024 |  | ARESBI CONSTRUCTION | Suspended, with conflict with the protocols of electric cooperatives | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region III | Tarlac City | 300971 | Tibag HS | CITY OF TARLAC (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2667884.73 | 2507500 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Zambales | 106866 | Sta. Maria Elementary School | CASTILLEJOS | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1211806.75 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region III | Zambales | 106896 | San Salvador Elementary School | MASINLOC | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1766126.9 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%