## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region III | Bataan | 104539 | T. Pinpin MES | ABUCAY | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 12124803.73 | 1 |  | Completed | 1 | [10 empty] | Issued Suspension of Procurement | [10 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region III | Bulacan | 104801 | Calumpit CS | Calumpit | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 14289812.4 | 1 |  | Completed | 1 | [10 empty] | CO ISSUED SUSPENSION OF PROCUREMENT | [10 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Nueva Ecija | 105765 | Santa Rosa Central School | SANTA ROSA | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 5621063.31 | 1 |  | Completed | 1 | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE | [10 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Nueva Ecija | 105437 | Jaen Central School | JAEN | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 8791110.01 | 1 |  | Completed | 1 | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE | [10 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Nueva Ecija | 105670 | San Antonio Central School | SAN ANTONIO | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 10441684.8 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6751373.93 | 1 |  | Completed | 1 | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE | [10 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 15369088.53 | 1 |  | Completed | 1 | 2024-02-10 |  | R3INFRA-ITB2023-004 |  | 2023-09-12 | 2023-09-19 | 2023-10-03 |  |  |  | Under Procurement for Take over contract; Re-posted for the partial completion of 7 CL. FFE elevated up to 0.9m due to school prone to flooding | [10 empty] | 1 |  |  | 9.24 |  |  |  |  | Completed
GABALDON 2020 | Region III | Pampanga | 106295 | Sta. Rita CS | STA. RITA | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 13155093.73 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Pampanga | 106284 | Sta. Ana Elementary | SANTA ANA | 3 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7694696.87 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Pampanga | 106152 | Masantol ES | MASANTOL | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5630830.42 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | San Fernando City | 107195 | San Fernando Elementary School | San Fernando City | 3 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 5708292.54 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6223490.48 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Tarlac | 106370 | Capas East Central Elementary School | Capas | 3 | 1 | 10 | 1 | Rehabilitation of Gabaldon Building | 15029045.63 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region III | Zambales | 106932 | Bobulon Elementary School | SAN FELIPE | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4389934.38 | 1 |  | Completed | 1 | [21 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2021 | Region III | Balanga City | 104552 | Balanga Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 7397597 | 1 | 5100000 | COMPLETED | 1 | 2022-03-30 |  |  | ITB2021-10-020 |  |  |  |  | 2021-10-13 | V. TRILLANA BUILDERS AND TRADING | [11 empty] | 1 |  |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region III | Tarlac City | 106691 | Matatalaib Bato ES | CITY OF TARLAC (Capital) | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4496502 | 1 | 3390249.63 | COMPLETED | 1 |  |  |  | ITB2021-10-021 |  |  |  |  | 2021-10-14 | DMGR BUILDERS | [11 empty] | 1 |  |  | previous yrs | Regional Office |  |  |  | COMPLETED
GABALDON 2021 | Region III | Zambales | 501224 | Botolan North Integrated School | BOTOLAN | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 8711059 | 1 | 8668888.88 | Completed | 1 | 2024-02-10 |  | R3INFRA-ITB2023-004 |  | 2023-09-12 | 2023-09-19 | 2023-10-03 |  |  |  | Under Procurement for Take over contract; Re-posted for the partial completion of 7 CL. FFE elevated up to 0.9m due to school prone to flooding | [10 empty] | 1 |  |  | 9.24 | Regional Office |  |  |  | Completed
GABALDON 2023 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 4883900 | x | 4873237.23 | COMPLETED | 1 | 11/27/2023 | 11/24/2023 | PB-2023-07-004 | SBR-2023-08-004 | 2023-05-07 | 2023-12-07 | 7/24/2023 | 8/22/2023 | 8/29/2023 | S.M. SEVERINO CONSTRUCTION AND TRADING | [11 empty] | 1 |  |  | 1.24 | Division Office | cy 2024 |  |  | COMPLETED
GABALDON 2024 | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 6th | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 10662171.54 | 1 | 6695000 | Completed | 1 | 4/19/2025 | 4/18/2025 | PB-24-011 | PB-24-011 | 6/28/2024 | 2024-08-07 | 7/22/2024 | 2024-06-08 | 10/14/2024 | V. Trillana Builders and Trading | [11 empty] | 0.9 |  |  | 5.25 | Division Office |  |  | 9 | Ongoing
GABALDON 2024 | Region III | Pampanga | 105897 | Anderson ES | ARAYAT | 3rd | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 12033643.5 | 1 | 11983176.6 | Completed | 1 | 12/30/2024 | 2024-09-12 | g-2024-013 | g-2024-013 | 4/25/2024 | 2024-06-05 | 5/20/2024 | 7/29/2024 | 2024-02-08 | S.M. SEVERINO CONSTRUCTION AND TRADING | [11 empty] | 1 |  |  | 12.24 | Division Office |  |  | 4 | Completed
GABALDON 2024 | Region III | Tarlac | 501609 | San Clemente Central Integrated School | SAN CLEMENTE | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 6039174.81 | 1 | 3994303.57 | completed | 1 | 3/23/2025 | 1/13/2025 |  |  | 5/24/2024 | 2024-03-06 | 6/17/2024 | 6/28/2024 | 9/24/2024 | T. DEL ROSARIO CONSTRUCTION | [11 empty] | 1 |  |  | 4.25 | Division Office |  |  | 8 | completed
GABALDON 2024 | Region III | Tarlac City | 106698 | Balingcanaway Centro ES | CITY OF TARLAC (Capital) | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 3765154.63 | 1 | 3759728.61 | COMPLETED | 1 | 9/23/2024 | 9/23/2024 | TCSD-IP-03-2024 | TCSD-IP-03-2024 | 2024-05-03 | 3/13/2024 | 3/25/2024 | 2024-01-04 | 6/24/2024 | JFM ALTITUDE CONSTRUCTION CORPORATION | NONE | [10 empty] | 1 |  |  | 9.24 | Division Office |  |  | 1 | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%