## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46 | Status as of July 4, 2025
REPAIR 2020 | Region III | Angeles City | 107022 | Abelardo G. Tinio ES | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 2639883 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 161001 | Air Force City Elementary School | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 773417 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | 16 | Repair of Classrooms | 5524899 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1 | 1 | 11 | Repair of Classrooms | 3594079 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | 12 | Repair of Classrooms | 3976260 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107025 | Cutud ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1451683 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107055 | Don Pepe Henson Memorial School | ANGELES CITY | 1 | 1 | 7 | Repair of Classrooms | 2271624 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 305554 | Dr Clemente N. Dayrit Sr. MHS | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 2932403 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107028 | Enrica Sandico ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1668594 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1977628 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500129 | Gov. Rafael L. Lazatin IS | ANGELES CITY | 1 | 1 | 20 | Repair of Classrooms | 3362242 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107041 | Gueco Balibago ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 1305815 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1 | 1 | 6 | Repair of Classrooms | 2461913 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1 | 1 | 30 | Repair of Classrooms | 8168153 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107059 | Pampang ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 703067 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107032 | Pineda-Gutierrez ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 706015 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107044 | Sapang Bato ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 1827826 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Angeles City | 107048 | Sta. Teresita Elementary School | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1250538 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 500729 | Carmen T. Valenzuela IS | Baler | 0 | 1 | 3 | Repair of Classrooms | 1065612 | 1 | 1065611.28 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-12 | AMC CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104418 | Suklayin ES | Baler | 0 | 1 | 2 | Repair of Classrooms | 737268 | 1 | 737267.01 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104427 | F. BENITEZ ES | Casiguran | 0 | 1 | 4 | Repair of Classrooms | 1480002 | 1 | 1480001.71 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-24 | VB Donato Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104476 | Maligaya ES | Dilasag | 0 | 1 | 2 | Repair of Classrooms | 835626 | 1 | 835625.25 | COMPLETED | 1 |  |  |  |  | Dec 9, 2019-Jan 6, 2020 | 2019-12-17 | 2020-01-07 | 2020-01-07 | 2020-08-24 | MITZIE CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104470 | DIPACULAO CS | Dipaculao | 0 | 1 | 9 | Repair of Classrooms | 2529568 | 1 | 2529567.57 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-08-12 | FNR BUILDERS AND SONS SUPPLY INC | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 300676 | Puangi NHS | Dipaculao | 0 | 1 | 6 | Repair of Classrooms | 1782880 | 1 | 1782879.53 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104497 | DIMOTOL ES | Ma. Aurora | 0 | 1 | 2 | Repair of Classrooms | 622332 | 1 | 622331.56 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | Sept 17, 2020 | MACCO CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Aurora | 104501 | GALINTUJA ES | Ma. Aurora | 0 | 1 | 4 | Repair of Classrooms | 1234817 | 1 | 1234816.66 | COMPLETED | 1 |  |  |  |  | Nov 15-Dec 6, 2019 | 2019-12-06 | 2019-12-06 | 2020-01-07 | 2020-10-07 | ES Pua Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Balanga City | 104567 | Tenejero Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2172873 | 1 | 2169279.43 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Balanga City | 104568 | Tortugas Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 4 | Repair of Classrooms | 719500 | 1 | 723093.14 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104572 | Colo ES | DINALUPIHAN | 1 | 1 | 7 | Repair of Classroom | 4327176 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104575 | Dinalupihan ES | DINALUPIHAN | 1 | 1 | 3 | Repair of Classrooms | 1848889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104580 | Luakan ES | DINALUPIHAN | 1 | 1 | 8 | Repair of Classrooms | 3408889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104583 | New San Jose ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 3610955 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104584 | OLD SAN JOSE ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 10 | Repair of Classrooms | 6024316 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104594 | SAN PABLO ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 9 | Repair of Classrooms | 3147026 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104597 | SAN SIMON ELEMENTARY SCHOOL | DINALUPIHAN | 1 | 1 | 4 | Repair of Classrooms | 2280209 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104609 | Culis ES | HERMOSA | 1 | 1 | 14 | Repair of Classrooms | 4521976 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104665 | PAG ASA ELEMENTARY SCHOOL | ORANI | 1 | 1 | 2 | Repair of Classrooms | 1260486 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104667 | PANTALAN LUMA ELEMENTARY SCHOOL | ORANI | 1 | 1 | 3 | Repair of Classrooms | 1920785 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104668 | Paraiso ES | ORANI | 1 | 1 | 8 | Repair of Classrooms | 2878889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104694 | Nagwaling ES | PILAR | 1 | 1 | 3 | Repair of Classrooms | 968889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104541 | Bagac ES | BAGAC | 2 | 1 | 6 | Repair of Classrooms | 2756222 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104550 | Saysain ES | BAGAC | 2 | 1 | 8 | Repair of Classrooms | 2790375 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104638 | BASECO ELEMENTARY SCHOOL | MARIVELES | 2 | 1 | 6 | Repair of Classrooms | 2104991 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104644 | LUCANIN ELEMENTARY SCHOOL | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 1312724 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104646 | Old Alion ES | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 1538889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104679 | DAAN PARE ELEMENTARY SCHOOL | ORION | 2 | 1 | 6 | Repair of Classrooms | 2308003 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104683 | PABLO ROMAN ELEMENTARY SCHOOL | ORION | 2 | 1 | 6 | Repair of Classrooms | 2305690 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bataan | 104691 | DIWA ELEMENTARY SCHOOL | PILAR | 2 | 1 | 4 | Repair of Classrooms | 2491600 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104802 | Caniogan ES | CALUMPIT | 1 | 1 | 7 | Repair of Classrooms | 2925443 | 1 | 2880704.02 | COMPLETED | 1 |  |  | 20-10-008 | 20-11-029 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-25 | THREE PAUL BUILDERS & SUPPLY | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300769 | Caniogan High school | CALUMPIT | 1 | 1 | 15 | Repair of Classrooms | 3192303 | 1 | 3192302.08 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-012 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | KPS CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104839 | Iba Ibayo ES | HAGONOY | 1 | 1 | 10 | Repair of Classrooms | 5394296 | 1 | 4088696.37 | COMPLETED | 1 |  |  | 20-10-009 | 20-11-030 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | G.M. Caparas Construction & Supply | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104758 | Tarcan Elementary School | BALIUAG | 2 | 1 | 14 | Repair of Classrooms | 6417780 | 1 | 4608181.89 | COMPLETED | 1 |  |  | 20-10-010 | 20-11-031 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104784 | Bonga Mayor ES | BUSTOS | 2 | 1 | 7 | Repair of Classrooms | 2500000 | 1 | 2500000 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-013 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | T.G. OCAMPO CONSTRUCTION & SURVEYING SERVICES | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104794 | San Pedro ES | BUSTOS | 2 | 1 | 7 | Repair of Classrooms | 4003285 | 1 | 4003284.26 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-014 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | SAMENARA CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105000 | Banga ES | PLARIDEL | 2 | 1 | 13 | Repair of Classrooms | 5420938 | 1 | 4413564.28 | COMPLETED | 1 |  |  | 20-10-011 | 20-11-032 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | G.M. Caparas Construction & Supply | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105001 | Bintog ES | PLARIDEL | 2 | 1 | 11 | Repair of Classrooms | 5830315 | 1 | 5420937.28 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-015 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | THREE POLL BUILDERS | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105003 | Dampol ES | PLARIDEL | 2 | 1 | 8 | Repair of Classrooms | 3883370 | 1 | 3883369.25 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-016 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | ELMUEL JAY TRADING & CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300722 | Binagbag NHS | ANGAT | 3 | 1 | 19 | Repair of Classrooms | 5742000 | 1 | 5742000 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-017 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | V. TRILLANA BUILDERS | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104723 | O. M. Esteban ES (Pulong Yantok ES) | ANGAT | 3 | 1 | 14 | Repair of Classrooms | 6280662 | 1 | 6180661.37 | COMPLETED | 1 |  |  | 20-10-012 | 20-11-033 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-02 | Emica Builders & Supply | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105071 | Calumpit Elementary School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 3 | Repair of Classrooms | 1613540 | 1 | 1613539.03 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-018 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EMICA BUILDERS & SUPPLY | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104940 | Banahaw ES | NORZAGARAY | 3 | 1 | 5 | Repair of Classrooms | 2522787 | 1 | 2497433.24 | COMPLETED | 1 |  |  | 20-10-013 | 20-11-034 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-07 | C.B. Tampengco Construction & Supply | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 158532 | Bigte Elementary School | NORZAGARAY | 3 | 1 | 7 | Repair of Classrooms | 3470513 | 1 | 2599888.93 | COMPLETED | 1 |  |  | 20-10-018 | 20-11-039 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104947 | FVR Phase 3 Elementary School | NORZAGARAY | 3 | 1 | 14 | Repair of Classrooms | 3977275 | 1 | 2882869.97 | COMPLETED | 1 |  |  | 20-10-014 | 20-11-035 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104954 | Padling Elementary School | NORZAGARAY | 3 | 1 | 9 | Repair of Classrooms | 4909526 | 1 | 3528761.5 | COMPLETED | 1 |  |  | 20-10-015 | 20-11-036 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104957 | San Mateo Elementary School | NORZAGARAY | 3 | 1 | 8 | Repair of Classrooms | 4115647 | 1 | 2955033.88 | COMPLETED | 1 |  |  | 20-10-016 | 20-11-037 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | Altitude Engineering & Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104958 | Sapang Kawayan Elementary School | NORZAGARAY | 3 | 1 | 14 | Repair of Classrooms | 6968622 | 1 | 5212528.88 | COMPLETED | 1 |  |  | 20-10-017 | 20-11-038 | 2020-09-04 | 2020-09-15 | 2020-09-28 | 2020-10-23 | 2020-12-04 | Altitude Engineering & Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105058 | Palapala Elementary School | SAN ILDEFONSO | 3 | 1 | 13 | Repair of Classrooms | 5348766 | 1 | 5348765.86 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-019 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | ELDICO BUILDERS | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105095 | Batasan ES | SAN MIGUEL | 3 | 1 | 10 | Repair of Classrooms | 5889704 | 1 | 4233011.45 | COMPLETED | 1 |  |  | 20-10-020 | 20-11-041 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105079 | Malibay ES | SAN MIGUEL | 3 | 1 | 11 | Repair of Classrooms | 6179255 | 1 | 4437455.13 | COMPLETED | 1 |  |  | 20-10-019 | 20-11-040 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-02 | Eirish Builders & Supply Inc. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3 | 1 | 64 | Repair of Classrooms | 17217307 | 1 | 17217306.74 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-020 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306708 | Maronquillo National High School | SAN RAFAEL | 3 | 1 | 8 | Repair of Classrooms | 3119632 | 1 | 3119631.36 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-023 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105125 | Pasong Callos ES | SAN RAFAEL | 3 | 1 | 7 | Repair of Classrooms | 2491408 | 1 | 2491407.11 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-021 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | E.B. MATIAS TRADING & CONSTRUCTION | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105135 | Sapang Pahalang Elementary School | SAN RAFAEL | 3 | 1 | 5 | Repair of Classrooms | 1978304 | 1 | 1978303.78 | COMPLETED | 1 |  |  | 19-11-009 | 20-10-022 | 2019-12-03 | 2019-12-10 | 2019-12-23 | 2020-01-21 |  | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 104967 | San Pascual ES | OBANDO | 4 | 1 | 4 | Repair of Classrooms | 2677553 | 1 | 2628643.52 | COMPLETED | 1 |  |  | 20-10-021 | 20-11-042 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-25 | ADIMRE Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 306714 | Catmon HS | SANTA MARIA | 4 | 1 | 18 | Repair of Classrooms | 5530674 | 1 | 4431643.39 | COMPLETED | 1 |  |  | 20-10-027 | 20-11-048 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-26 | OPEN BUILDERS INCORPORATED | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105144 | CORNELIA M. DE JESUS MEMORIAL CENTRAL SCHOOL | SANTA MARIA | 4 | 1 | 19 | Repair of Classrooms | 8359304 | 1 | 5966907.42 | COMPLETED | 1 |  |  | 20-10-022 | 20-11-043 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-27 | T.G. Ocampo Construction & Surveying Services | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 24 | Repair of Classrooms | 10348898 | 1 | 7230931.98 | COMPLETED | 1 |  |  | 20-10-026 | 20-11-047 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-01 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105162 | San Jose Patag Elementary School | SANTA MARIA | 4 | 1 | 10 | Repair of Classrooms | 4610059 | 1 | 3835980.47 | COMPLETED | 1 |  |  | 20-10-023 | 20-11-044 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-11-25 | THREE PAUL BUILDERS & SUPPLY | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105165 | Silangan ES | SANTA MARIA | 4 | 1 | 4 | Repair of Classrooms | 1874751 | 1 | 1452009.69 | COMPLETED | 1 |  |  | 20-10-024 | 20-11-045 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-03 | GELROCK BUILDERS | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Bulacan | 105168 | Sta. Maria Elementary School | SANTA MARIA | 4 | 1 | 12 | Repair of Classrooms | 6233930 | 1 | 4357109.28 | COMPLETED | 1 |  |  | 20-10-025 | 20-11-046 | 2020-09-04 | 2020-09-15 | 2020-09-29 | 2020-10-23 | 2020-12-01 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Cabanatuan City | 307301 | Cesar E. Vergara Memorial High School | CABANATUAN CITY | 3 | 1 | 2 | Repair of Classrooms | 860041 | 1 | 860040.4 | COMPLETED | 1 |  |  |  |  | 2019-12-02 | 2019-12-06 | 2019-12-17 | 2019-12-18 |  | MARVELOUS QUEJADA CONSTRUCTION INC. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Cabanatuan City | 107105 | Macatbong ES | CABANATUAN CITY | 3 | 1 | 10 | Repair of Classrooms | 2808809 | 1 | 2808808.88 | COMPLETED | 1 |  |  |  |  | 2019-12-02 | 2019-12-06 | 2019-12-17 | 2019-12-18 |  | MARVELOUS QUEJADA CONSTRUCTION INC. | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105314 | Bagong Silang ES | CITY OF GAPAN | 4 | 1 | 4 | Repair of Classrooms | 2006325 | 1 | 2006324.27 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 300815 | Kapalangan NHS | CITY OF GAPAN | 4 | 1 | 8 | Repair of Classrooms | 2229905 | 1 | 2229904.97 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105326 | Mangino ES | CITY OF GAPAN | 4 | 1 | 3 | Repair of Classrooms | 1519230 | 1 | 1519229.71 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Gapan City | 105345 | Sto. Nino ES | CITY OF GAPAN | 4 | 1 | 6 | Repair of Classrooms | 2779927 | 1 | 2779926.12 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 306922 | Duquit High School | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 738904 | 1 | 738903.37 | COMPLETED | 1 |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | E.B. MATIAS CONSTRUCTION AND TRADING | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106068 | Madapdap Resettlement ES | MABALACAT CITY | 1 | 1 | 8 | Repair of Classrooms | 2691160 | 1 | 1893668.64 | COMPLETED | 1 | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106084 | Mawake ES | MABALACAT CITY | 1 | 1 | 9 | Repair of Classrooms | 3898654 | 1 | 2675191.75 | COMPLETED | 1 | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 159535 | Northville 16 ES | MABALACAT CITY | 1 | 1 | 16 | Repair of Classrooms | 2865659 | 1 | 700247.19 | COMPLETED | 1 |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | E.B. MATIAS CONSTRUCTION AND TRADING | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106085 | Paralayunan ES | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 473895 | 1 | 331892.45 | COMPLETED | 1 | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106088 | Talimundok Elementary School | MABALACAT CITY | 1 | 1 | 2 | Repair of Classrooms | 700248 | 1 | 2456430.31 | COMPLETED | 1 |  |  |  |  | 2019-11-18 | 2019-11-25 | 2019-12-09 | 2019-12-27 |  | N.M.D CONSTRUCTION AND TRADING | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Mabalacat City | 106089 | Villa Teodora ES | MABALACAT CITY | 1 | 1 | 8 | Repair of Classrooms | 2456431 | 1 | 2005928.25 | COMPLETED | 1 | [8 empty] | 2020-12-11 | KPS Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Malolos City | 300751 | Marcelo H. del Pilar National HS | CITY OF MALOLOS (Capital) | 1 | 1 | 17 | Repair of Classrooms | 4403562 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Malolos City | 104882 | Tikay ES | CITY OF MALOLOS (Capital) | 1 | 1 | 17 | Repair of Classrooms | 3576371 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 104923 | Libtong Elementary School | CITY OF MEYCAUAYAN | 4 | 1 | 11 | Repair of Classrooms | 3782072 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 104934 | Longos ES | CITY OF MEYCAUAYAN | 4 | 1 | 5 | Repair of Classrooms | 2164658 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Meycauayan City | 500965 | Saluysoy Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 3 | Repair of Classrooms | 1804578 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Munoz Science City | 105538 | CABISUCULAN ELEMENTARY SCHOOL | Science City of Muñoz | 2 | 1 | 5 | Repair of Classrooms | 1509126 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-11-19 | 2019-11-26 | 2019-12-11 | 2019-12-27 |  | Front Nine Konstuct (Builders & Reality Dev. Corporation) | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Munoz Science City | 105542 | MAGTANGGOL INTEGRATED SCHOOL (SECONDARY) | Science City of Muñoz | 2 | 1 | 3 | Repair of Classrooms | 701923 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-11-19 | 2019-11-26 | 2019-12-11 | 2019-12-27 |  | Front Nine Konstuct (Builders & Reality Dev. Corporation) | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105171 | Aliaga CS | ALIAGA | 1 | 1 | 8 | Repair of Classrooms | 2836041 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105172 | Betes Es | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2015049 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105183 | San Eustacio ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2104971 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105185 | San Juan ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2150580 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105187 | San Pablo (M) ES | ALIAGA | 1 | 1 | 6 | Repair of Classrooms | 2137812 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105188 | Santiago ES | ALIAGA | 1 | 1 | 3 | Repair of Classrooms | 1143583 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105192 | Sunson Es | ALIAGA | 1 | 1 | 4 | Repair of Classrooms | 1408383 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105255 | Baloy Elementary School | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105256 | Bambanaba ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3222059 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105257 | Bentigan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105259 | Bonifacio ES | CUYAPO | 1 | 1 | 3 | Repair of Classrooms | 1669931 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105261 | Burgos ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3362740 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105263 | Cabileo ES | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1133420 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105269 | Cuyapo CS | CUYAPO | 1 | 1 | 12 | Repair of Classrooms | 6179721 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105270 | Democrito M. Jose ES | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105271 | Dona Consuelo ES | CUYAPO | 1 | 1 | 7 | Repair of Classrooms | 3719598 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105276 | Luna ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105281 | Nagcuralan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105283 | Paitan Norte ES | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2034564 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105285 | Piglisan ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105287 | Rizal Elementary School | CUYAPO | 1 | 1 | 4 | Repair of Classrooms | 2231377 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105289 | Salagusog ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3362740 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105290 | San Antonio ES | CUYAPO | 1 | 1 | 12 | Repair of Classrooms | 5885655 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105295 | Sta. Cruz ES | CUYAPO | 1 | 1 | 6 | Repair of Classrooms | 3215706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105389 | Manacsac ES | GUIMBA | 1 | 1 | 15 | Repair of Classrooms | 4816240 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105420 | Manggang Marikit ES | GUIMBA | 1 | 1 | 14 | Repair of Classrooms | 4144424 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105390 | Maturanoc ES | GUIMBA | 1 | 1 | 16 | Repair of Classrooms | 5256456 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105391 | Naglabrahan ES | GUIMBA | 1 | 1 | 2 | Repair of Classrooms | 710878 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105392 | Nagpandayan Es | GUIMBA | 1 | 1 | 16 | Repair of Classrooms | 4661475 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105427 | Pasong-Inchik ES | GUIMBA | 1 | 1 | 12 | Repair of Classrooms | 3556216 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105393 | San Andres ES | GUIMBA | 1 | 1 | 10 | Repair of Classrooms | 2595629 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105398 | Sta Ana ES | GUIMBA | 1 | 1 | 7 | Repair of Classrooms | 1941275 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306804 | BURGOS NATIONAL HIGH SCHOOL | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 1658020 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105240 | Camanggahan ES | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 977665 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 | 1 | 10 | Repair of Classrooms | 5265044 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN | 2 | 1 | 5 | Repair of Classrooms | 1564738 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300799 | Digdig HS | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 1652547 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105248 | Minuli ES | CARRANGLAN | 2 | 1 | 3 | Repair of Classrooms | 977470 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159013 | Nagcancionan ES | CARRANGLAN | 2 | 1 | 4 | Repair of Classrooms | 2195436 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105250 | Piut ES | CARRANGLAN | 2 | 1 | 4 | Repair of Classrooms | 1300512 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105494 | Caridad Sur ES | LLANERA | 2 | 1 | 9 | Repair of Classrooms | 3035645 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105512 | Agupalo Este ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1189702 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306806 | AGUPALO WESTE HIGH SCHOOL | LUPAO | 2 | 1 | 8 | Repair of Classrooms | 2780247 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105517 | Bagong Flores ES | LUPAO | 2 | 1 | 4 | Repair of Classrooms | 1278237 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105519 | Burgos ES | LUPAO | 2 | 1 | 2 | Repair of Classrooms | 706048 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105522 | Mapangpang ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1154327 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105527 | San Antonio Este ES | LUPAO | 2 | 1 | 10 | Repair of Classrooms | 3222719 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105528 | San Antonio Weste ES | LUPAO | 2 | 1 | 3 | Repair of Classrooms | 1147160 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105529 | San Isidro ES | LUPAO | 2 | 1 | 10 | Repair of Classrooms | 3376702 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105532 | Sto. Domingo ES | LUPAO | 2 | 1 | 5 | Repair of Classrooms | 1291854 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306832 | Conversion IS | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1453871 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105637 | Ballesteros ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 978384 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105645 | Estrella ES | RIZAL | 2 | 1 | 7 | Repair of Classrooms | 2060493 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105651 | Pag-Asa ES | RIZAL | 2 | 1 | 5 | Repair of Classrooms | 1631339 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105657 | Sta. Monica ES | RIZAL | 2 | 1 | 4 | Repair of Classrooms | 1772208 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 6 | Repair of Classrooms | 1999768 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105196 | Bantug Elem. School | BONGABON | 3 | 1 | 4 | Repair of Classrooms | 1410620 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105197 | Bongabon CS | BONGABON | 3 | 1 | 6 | Repair of Classrooms | 2022807 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105200 | Calaanan ES | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1101363 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105201 | Camp Martyr ES | BONGABON | 3 | 1 | 4 | Repair of Classrooms | 1417666 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105202 | Cruz ES | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1121598 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105211 | R. VIJANDRE ELEMENTARY SCHOOL | BONGABON | 3 | 1 | 3 | Repair of Classrooms | 1205140 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105199 | Rosa A. Ilagan ES (Bongabon North ES) | BONGABON | 3 | 1 | 17 | Repair of Classrooms | 5314706 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105298 | Bagong Sikat ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 2119838 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105301 | Bateria ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 7 | Repair of Classrooms | 3857236 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105302 | Bugnan ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | Repair of Classrooms | 1292516 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105306 | F. Buencamino Sr. Integrated School (F. Buencamino Sr. ES) | GABALDON (BITULOK & SABANI) | 3 | 1 | 8 | Repair of Classrooms | 4129219 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105307 | Gabaldon CS | GABALDON (BITULOK & SABANI) | 3 | 1 | 8 | Repair of Classrooms | 2668145 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300805 | Gabaldon Voc'l. Agric. HS | GABALDON (BITULOK & SABANI) | 3 | 1 | 18 | Repair of Classrooms | 9421526 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105309 | Ligaya ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 9 | Repair of Classrooms | 5052082 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306814 | Ligaya National High School | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 3126062 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105311 | Pantoc ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | Repair of Classrooms | 1651240 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105312 | Pinamalisan ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | Repair of Classrooms | 2200467 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105313 | Tagumpay ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | Repair of Classrooms | 1995274 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105346 | Azarcon ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 5 | Repair of Classrooms | 1906771 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105348 | Belen ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2088305 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105349 | Bravo ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2000947 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105350 | Burol ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2196276 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105355 | Manarog ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2062401 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105356 | Mataas Na Kahoy ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 8 | Repair of Classrooms | 2720969 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105363 | Talabutab Norte ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 8 | Repair of Classrooms | 2674755 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105364 | Talabutab Sur Elementary School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Repair of Classrooms | 2042532 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105362 | Virginia D. Dulay Elementary School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 2 | Repair of Classroom | 927002 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105577 | Bagong Buhay ES | PALAYAN CITY (Capital) | 3 | 1 | 10 | Repair of Classrooms | 2917986 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300787 | Fort Magsaysay NHS (formerly Barangay Militar HS) | PALAYAN CITY (Capital) | 3 | 1 | 7 | Repair of Classrooms | 2134529 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105584 | Maligaya ES | PALAYAN CITY (Capital) | 3 | 1 | 10 | Repair of Classrooms | 3101159 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105587 | Marcos Village ES | PALAYAN CITY (Capital) | 3 | 1 | 5 | Repair of Classrooms | 2174495 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105592 | Sandelain ES | PALAYAN CITY (Capital) | 3 | 1 | 6 | Repair of Classrooms | 1924722 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105593 | Sapang Buho ES | PALAYAN CITY (Capital) | 3 | 1 | 8 | Repair of Classrooms | 2581288 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105747 | Berang Elementary School | SANTA ROSA | 3 | 1 | 2 | Repair of Classrooms | 801412 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159026 | Casimiro Pagsanjan Mem. Sch. | SANTA ROSA | 3 | 1 | 5 | Repair of Classrooms | 1500797 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105749 | Dr. A. Oliveros Mem. ES | SANTA ROSA | 3 | 1 | 17 | Repair of Classrooms | 4040713 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105748 | Dr. Sancho T. Manubay ES | SANTA ROSA | 3 | 1 | 8 | Repair of Classrooms | 1942623 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105750 | E. Saulo Mem. ES | SANTA ROSA | 3 | 1 | 15 | Repair of Classrooms | 4468661 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105764 | Esing T. Angeles E/S | SANTA ROSA | 3 | 1 | 3 | Repair of Classrooms | 1142500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105746 | Eulalio N. Adriano Elementary School | SANTA ROSA | 3 | 1 | 10 | Repair of Classrooms | 2839845 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105752 | La Fuente ES | SANTA ROSA | 3 | 1 | 12 | Repair of Classrooms | 3685271 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105755 | Mapalad North ES | SANTA ROSA | 3 | 1 | 9 | Repair of Classrooms | 2869216 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105756 | Mapalad Sur ES | SANTA ROSA | 3 | 1 | 7 | Repair of Classrooms | 2152139 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105758 | Pilang ES | SANTA ROSA | 3 | 1 | 3 | Repair of Classrooms | 1130434 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105760 | San Gregorio ES | SANTA ROSA | 3 | 1 | 23 | Repair of Classrooms | 6690512 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105761 | San Pedro ES | SANTA ROSA | 3 | 1 | 9 | Repair of Classrooms | 2859540 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105765 | SANTA ROSA CENTRAL SCHOOL | SANTA ROSA | 3 | 1 | 25 | Repair of Classrooms | 7017038 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105762 | Sapsap ES | SANTA ROSA | 3 | 1 | 2 | Repair of Classrooms | 801412 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105766 | Sto. Rosario ES | SANTA ROSA | 3 | 1 | 21 | Repair of Classrooms | 4801331 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4 | 1 | 20 | Repair of Classrooms | 10191999 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4 | 1 | 16 | Repair of Classrooms | 5163618 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105217 | Concepcion ES | CABIAO | 4 | 1 | 18 | Repair of Classrooms | 9488597 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105218 | Entablado ES | CABIAO | 4 | 1 | 16 | Repair of Classrooms | 8159361 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105231 | Jose Rico Cruz ES (Sta. Ines ES) | CABIAO | 4 | 1 | 4 | Repair of Classrooms | 2196301 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105219 | Maligaya ES | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3610248 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105220 | Palasinan ES | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3853712 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105221 | POLILIO ELEMENTARY SCHOOL | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3604061 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105222 | San Antonio-Bagong Buhay Elementary School | CABIAO | 4 | 1 | 12 | Repair of Classrooms | 6481726 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105224 | San Fernando Norte ES | CABIAO | 4 | 1 | 7 | Repair of Classrooms | 3221517 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105226 | San Gregorio ES | CABIAO | 4 | 1 | 3 | Repair of Classrooms | 1666450 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105227 | San Roque ES | CABIAO | 4 | 1 | 1 | Repair of Classrooms | 600667 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105228 | San Vicente Elementary School | CABIAO | 4 | 1 | 8 | Repair of Classrooms | 4081283 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105230 | St. Joseph ES | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3343879 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 306823 | Sta. Isabel High School | CABIAO | 4 | 1 | 6 | Repair of Classrooms | 3179853 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105233 | Sta. Rita ES | CABIAO | 4 | 1 | 10 | Repair of Classrooms | 5255570 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105365 | Bago ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 8 | Repair of Classrooms | 2822327 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159014 | Gawad Kalinga Comm. ES (Pahalang ES) | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 714957 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105367 | Gen. Tinio East CS | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 1988904 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105368 | Gen. Tinio West Central School | GENERAL TINIO (PAPAYA) | 4 | 1 | 10 | Repair of Classrooms | 3202694 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 159019 | Minalungao Elementary School | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 708056 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105370 | Padolina ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 1988486 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105588 | Palale ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 5 | Repair of Classrooms | 1689174 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105371 | Patindig-Araw ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 2 | Repair of Classrooms | 704885 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105372 | Pias ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 2039777 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105373 | Rio Chico ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms | 1094044 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300840 | Rio Chico National High School | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | Repair of Classrooms | 2115010 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105439 | Lambakin ES | JAEN | 4 | 1 | 4 | Repair of Classrooms | 1220558 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105442 | Magsalisi East Elementary School | JAEN | 4 | 1 | 7 | Repair of Classrooms | 2659199 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105443 | Malabon Kaingin ES | JAEN | 4 | 1 | 3 | Repair of Classrooms | 963934 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105455 | Sapang ES | JAEN | 4 | 1 | 6 | Repair of Classrooms | 2002776 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105456 | Sta. Rita ES | JAEN | 4 | 1 | 10 | Repair of Classrooms | 2831361 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105458 | Sto. Tomas South ES | JAEN | 4 | 1 | 4 | Repair of Classrooms | 1763007 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105616 | San Josef ES | PEÑARANDA | 4 | 1 | 9 | Repair of Classrooms | 3046722 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105617 | San Mariano ES | PEÑARANDA | 4 | 1 | 3 | Repair of Classrooms | 1475181 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105667 | Maugat ES | SAN ANTONIO | 4 | 1 | 7 | Repair of Classrooms | 2589321 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105670 | San Antonio CS | SAN ANTONIO | 4 | 1 | 15 | Repair of Classrooms | 4721514 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105678 | Tikiw ES | SAN ANTONIO | 4 | 1 | 6 | Repair of Classrooms | 1858770 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105679 | Alua Elementary School | SAN ISIDRO | 4 | 1 | 18 | Repair of Classrooms | 5890306 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105680 | Barangka ES | SAN ISIDRO | 4 | 1 | 6 | Repair of Classrooms | 2453118 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105684 | Malapit West ES | SAN ISIDRO | 4 | 1 | 12 | Repair of Classrooms | 3307954 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO | 4 | 1 | 7 | Repair of Classrooms | 3167589 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105689 | Sto. Cristo ES | SAN ISIDRO | 4 | 1 | 5 | Repair of Classrooms | 1535138 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 | 1 | 14 | Repair of Classrooms | 2234453 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105737 | Mallorca ES | SAN LEONARDO | 4 | 1 | 6 | Repair of Classrooms | 2056871 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105740 | San Anton ES | SAN LEONARDO | 4 | 1 | 11 | Repair of Classrooms | 5145314 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4 | 1 | 6 | Repair of Classrooms | 1926099 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105742 | San Roque ES | SAN LEONARDO | 4 | 1 | 13 | Repair of Classrooms | 3935074 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105743 | Tagumpay Elementary School | SAN LEONARDO | 4 | 1 | 2 | Repair of Classrooms | 706072 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Nueva Ecija | 105744 | Tambo North E/S | SAN LEONARDO | 4 | 1 | 13 | Repair of Classrooms | 2996022 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 162002 | Amelia Heights ES | OLONGAPO CITY | 1 | 1 | 6 | Repair of Classrooms | 2253614 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 107118 | Bangal ES | OLONGAPO CITY | 1 | 1 | 6 | Repair of Classrooms | 2030302 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Olongapo City | 301055 | Iram High School | OLONGAPO CITY | 1 | 1 | 4 | Repair of Classrooms | 1258235 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106117 | Ayala ES | MAGALANG | 1 | 1 | 8 | Repair of Classrooms | 2911636 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106118 | Balitucan ES | MAGALANG | 1 | 1 | 9 | Repair of Classrooms | 4168331 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106123 | Magalang ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1336078 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159515 | Orchard Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1178349 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106126 | Pitabacan ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 2092366 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106127 | San Agustin ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1303006 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159546 | San Isidro Resettlement ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 3376673 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106132 | San Pablo ES | MAGALANG | 1 | 1 | 5 | Repair of Classrooms | 2065701 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106134 | San Roque Es | MAGALANG | 1 | 1 | 12 | Repair of Classrooms | 5585730 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106138 | Sta Maria ES | MAGALANG | 1 | 1 | 10 | Repair of Classrooms | 5296195 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106137 | Sta. Lucia ES | MAGALANG | 1 | 1 | 6 | Repair of Classrooms | 2982501 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106139 | Sto Nino ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1606878 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106140 | Sto Rosario ES | MAGALANG | 1 | 1 | 5 | Repair of Classrooms | 2342476 | 1 | 1065977.99 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106142 | Turu ES | MAGALANG | 1 | 1 | 4 | Repair of Classrooms | 1821595 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105969 | Paguiruan ES | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 1820395 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105992 | Pandaguirig ES | Floridablanca | 2 | 1 | 2 | Repair of Classrooms | 725858 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106006 | Lambac ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2962178 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106008 | Maquiapo Elementary School | GUAGUA | 2 | 1 | 10 | Repair of Classrooms | 3842905 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106009 | Mauli ES | GUAGUA | 2 | 1 | 3 | Repair of Classrooms | 1349993 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2841606 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106012 | Rizal ES | GUAGUA | 2 | 1 | 6 | Repair of Classrooms | 2599844 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106015 | San Juan ES | Guagua | 2 | 1 | 6 | Repair of Classrooms | 3021207 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106017 | San Vicente ES | GUAGUA | 2 | 1 | 9 | Repair of Classrooms | 4793869 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106022 | Graciano Paule ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2667050 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106047 | Lauc Pao ES | LUBAO | 2 | 1 | 4 | Repair of Classrooms | 1951368 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106023 | Lubao ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1105624 | 1 |  | COMPLETED | 1 | [10 empty] | Classroom to be repared use as Quarantine Facilities by DOH and LGU | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106048 | Prado Saba | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1152135 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106030 | San Miguel ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2878277 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106052 | San Pablo 1st ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1573751 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 300925 | San Pablo II NHS | LUBAO | 2 | 1 | 11 | Repair of Classrooms | 4186351 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106054 | San Pedro Palcarangan ES | LUBAO | 2 | 1 | 6 | Repair of Classrooms | 3148829 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106058 | Sta Cruz Es | LUBAO | 2 | 1 | 4 | Repair of Classrooms | 2640845 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106034 | Sta Lucia ES | LUBAO | 2 | 1 | 3 | Repair of Classrooms | 1086265 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106035 | Sta Maria ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2557899 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106036 | Sta. Monica Elementary School | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2509562 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159538 | Mancantian ES (Balik Barangay) | PORAC | 2 | 1 | 3 | Repair of Classrooms | 1018519 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106291 | San Basilio ES | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 2841343 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106292 | San Isidro ES | SANTA RITA | 2 | 1 | 5 | Repair of Classrooms | 2698001 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106295 | Sta. Rita CS | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 3138516 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106272 | Sasmuan ES | SASMUAN (SEXMOAN) | 2 | 1 | 6 | Repair of Classrooms | 3034203 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105884 | Cupang ES | ARAYAT | 3 | 1 | 4 | Repair of Classrooms | 2083940 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105893 | San Nicolas ES | ARAYAT | 3 | 1 | 10 | Repair of Classrooms | 5168395 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105900 | Baliti ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 3985843 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105901 | Bitas ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 3915955 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105902 | Buensuseso ES | Arayat | 3 | 1 | 8 | Repair of Classrooms | 2145280 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105903 | Cacutud ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 1135532 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105904 | Gatiawin ES | Arayat | 3 | 1 | 11 | Repair of Classrooms | 5900428 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105907 | Palinlang ES | Arayat | 3 | 1 | 2 | Repair of Classrooms | 901560 | 1 | 891625.54 | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105908 | Plaza Luma ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 2182601 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105909 | San Antonio ES | Arayat | 3 | 1 | 5 | Repair of Classrooms | 2588432 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105891 | San Juan Baño ES | Arayat | 3 | 1 | 6 | Repair of Classrooms | 2812490 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105910 | Telapayong ES | Arayat | 3 | 1 | 4 | Repair of Classrooms | 1797984 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105913 | Cabalantian ES | BACOLOR | 3 | 1 | 8 | Repair of Classrooms | 3171315 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105920 | Maliwalo ES | Bacolor | 3 | 1 | 8 | Repair of Classrooms | 3171450 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105925 | San Isidro ES | Bacolor | 3 | 1 | 5 | Repair of Classrooms | 2608525 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105927 | Talba ES | Bacolor | 3 | 1 | 8 | Repair of Classrooms | 3181963 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159507 | Tinajero ES (Madapdap Resettlement ) | Bacolor | 3 | 1 | 5 | Repair of Classrooms | 2695016 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106162 | Acli ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1415064 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106165 | Buenavista ES | MEXICO | 3 | 1 | 4 | Repair of Classrooms | 2078208 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106166 | Camuning ES | MEXICO | 3 | 1 | 7 | Repair of Classrooms | 3256300 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106168 | Concepcion ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1471122 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106184 | Lagundi ES | MEXICO | 3 | 1 | 5 | Repair of Classrooms | 2107747 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106171 | Laput ES | MEXICO | 3 | 1 | 2 | Repair of Classrooms | 1045346 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106187 | Mexico CS | MEXICO | 3 | 1 | 9 | Repair of Classrooms | 5382071 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106197 | Nueva Victoria ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1582569 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106174 | Panipuan ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1540775 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106193 | San Lorenzo ES | MEXICO | 3 | 1 | 8 | Repair of Classrooms | 3512794 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106194 | San Miguel ES | MEXICO | 3 | 1 | 2 | Repair of Classrooms | 1015309 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106176 | San Patricio ES | MEXICO | 3 | 1 | 6 | Repair of Classrooms | 3044581 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106179 | Sto Rosario ES | MEXICO | 3 | 1 | 7 | Repair of Classrooms | 3449278 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106181 | Tangle ES | MEXICO | 3 | 1 | 3 | Repair of Classrooms | 1367609 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106278 | Fulgencio Matias ES | SANTA ANA | 3 | 1 | 3 | Repair of Classrooms | 1314340 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106276 | San Agustin ES | SANTA ANA | 3 | 1 | 3 | Repair of Classrooms | 1354876 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106277 | San Isidro ES | SANTA ANA | 3 | 1 | 10 | Repair of Classrooms | 4599156 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106281 | San Pablo ES | SANTA ANA | 3 | 1 | 8 | Repair of Classrooms | 3747918 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106279 | San Pedro - San Juan ES | SANTA ANA | 3 | 1 | 2 | Repair of Classrooms | 879693 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106284 | Sta Ana ES | SANTA ANA | 3 | 1 | 11 | Repair of Classrooms | 5131866 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106285 | Sta Lucia ES | SANTA ANA | 3 | 1 | 11 | Repair of Classrooms | 5932524 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106286 | Sta. Maria ES | STA. ANA | 3 | 1 | 3 | Repair of Classrooms | 1603918 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105867 | Balucuc ES | APALIT | 4 | 1 | 6 | Repair of Classrooms | 2808354 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105873 | Macario Arnedo ES | APALIT | 4 | 1 | 3 | Repair of Classrooms | 1524777 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105872 | Jose Escaler MES | Apalit | 4 | 1 | 5 | Repair of Classrooms | 2685200 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105944 | Pulong Palazan ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1567249 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105945 | Salapungan ES | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 2815282 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105947 | Talang ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2122329 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105950 | Vizal San Pablo I ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1588743 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105952 | Vizal San Sto Niño ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1644889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 105946 | Tagulod ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 1563776 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106104 | Consuelo Elementary | MACABEBE | 4 | 1 | 9 | Repair of Classrooms | 3713215 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159514 | Bebe PS | SAN LUIS | 4 | 1 | 3 | Repair of Classrooms | 1638737 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106240 | San Carlos ES | SAN LUIS | 4 | 1 | 11 | Repair of Classrooms | 5467399 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106244 | San Juan ES | SAN LUIS | 4 | 1 | 9 | Repair of Classrooms | 4459480 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106247 | San Roque Es | San Luis | 4 | 1 | 5 | Repair of Classrooms | 2570934 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106251 | Sta Rita ES | San Luis | 4 | 1 | 6 | Repair of Classrooms | 2794104 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 159503 | San Juan ES | SAN SIMON | 4 | 1 | 2 | Repair of Classrooms | 1077029 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 106260 | San Nicolas ES | SAN SIMON | 4 | 1 | 3 | Repair of Classrooms | 1439986 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Pampanga | 300938 | Sto Tomas NHS | SANTO TOMAS | 4 | 1 | 10 | Repair of Classrooms | 4420170 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 871551 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 |  | 4 | Repair of Classrooms | 1809288 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500981 | Arch. Emilio Cinense Memorial Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 986563 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500140 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2182804 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500146 | Calulut IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1659518 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500138 | City of San Fernando West IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1676821 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500147 | Del Carmen Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1595162 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107181 | Dela Paz Norte ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1551658 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107182 | Dolores ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1649456 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500136 | Lara Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1283183 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500148 | Magliman Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1476251 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500145 | Maimpis Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1457905 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 501141 | Malino Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500137 | Nuestra Senora Del Pilar IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | Repair of Classrooms | 2990792 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 301064 | Pampanga HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2102513 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107186 | Panipuan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2454314 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 307603 | Panipuan High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 873859 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500143 | Saguin Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | Repair of Classrooms | 869145 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 163004 | San Agustin ES (Annex) | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Repair of Classrooms | 2303703 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500149 | San Agustin IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1417557 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1574612 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107197 | San Juan South ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 5 | Repair of Classrooms | 2051615 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500142 | San Nicolas IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1475461 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107198 | San Pedro ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1584297 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 107190 | Sindalan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573960 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Fernando City | 500144 | Telebastagan Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1573500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105724 | Parang Mangga ES | San Jose City | 2 | 1 | 2 | Repair of Classrooms | 812533 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105731 | Sto. Tomas ES | San Jose City | 2 | 1 | 6 | Repair of Classrooms | 2233299 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose City | 105714 | Villa Floresta Es | San Jose City | 2 | 1 | 4 | Repair of Classrooms | 1511037 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107153 | Dulong Bayan ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 2 | Repair of Classroom | 651166 | 1 | 651165.13 | COMPLETED | 1 | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107155 | Gaya-Gaya ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | Repair of Classrooms | 5681659 | 1 | 5681658.84 | COMPLETED | 1 | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 162506 | Goldenville ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 21 | Repair of Classrooms | 5048646 | 1 | 5048645.88 | COMPLETED | 1 | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107160 | S. Palay Proper ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 11 | Repair of Classrooms | 4330492 | 1 | 4330492 | COMPLETED | 1 | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | San Jose del Monte City | 107161 | San Jose Del Monte Central School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 19 | Repair of Classrooms | 5189604 | 1 | 5189603.88 | COMPLETED | 1 | [10 empty] | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 160004 | Dagundon ES | ANAO | 1 | 1 | 4 | Repair of Classrooms | 1962060 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106339 | Bilad ES | CAMILING | 1 | 1 | 7 | Repair of Classrooms | 2988914 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106347 | Marawi ES | Camiling | 1 | 1 | 4 | Repair of Classrooms | 1847777 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106524 | San Jose ES | MAYANTOC | 1 | 1 | 4 | Repair of Classrooms | 2032268 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106535 | San Pedro ES | MONCADA | 1 | 1 | 5 | Repair of Classrooms | 2004224 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106582 | Mabilang ES | PANIQUI | 1 | 1 | 3 | Repair of Classrooms | 1145606 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106585 | Paniqui South Central Elementary School | PANIQUI | 1 | 1 | 1 | Repair of Classroom | 707901 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106672 | Macaguing Primary School | SANTA IGNACIA | 1 | 1 | 2 | Repair of Classrooms | 912404 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300979 | Pilpila NHS | Sta. Ignacia | 1 | 1 | 2 | Repair of Classrooms | 905247 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4393346 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106463 | Ayson ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 970716 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106464 | Bawa ES | GERONA | 2 | 1 | 7 | Repair of Classrooms | 2926749 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106446 | Carbonel ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 1085370 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106447 | Caturay ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 1916555 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106450 | Gabaldon ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4363042 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | 9 | Repair of Classrooms | 3696798 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106452 | Magaspac ES | GERONA | 2 | 1 | 5 | Repair of Classrooms | 2625334 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106472 | Matapitap ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 836651 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106474 | New Salem ES | GERONA | 2 | 1 | 2 | Repair of Classrooms | 954870 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106477 | Pinasling ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 1601166 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106455 | Quezon ES | GERONA | 2 | 1 | 10 | Repair of Classrooms | 4621090 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | 9 | Repair of Classrooms | 4189987 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106480 | San Agustin ES | GERONA | 2 | 1 | 4 | Repair of Classrooms | 2177557 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106482 | San Bartolome ES | GERONA | 2 | 1 | 3 | Repair of Classrooms | 1351848 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300986 | San Jose NHS | GERONA | 2 | 1 | 8 | Repair of Classrooms | 2905787 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106641 | Pao ES | SAN JOSE | 2 | 1 | 8 | Repair of Classrooms | 3882486 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106776 | Bantog ES | VICTORIA | 2 | 1 | 3 | Repair of Classrooms | 1480642 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106367 | Angelina Dizon Jimenez ES (Sto. Domingo ES) | CAPAS | 3 | 1 | 3 | Repair of Classrooms | 1478216 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106393 | Cafe ES | CONCEPCION | 3 | 1 | 6 | Repair of Classrooms | 2621875 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106539 | Demetrio F. Nagtalon ES | Moncada | 1 | 1 | 3 | Repair of Classrooms | 1290975 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106540 | Villa PS | Moncada | 1 | 1 | 2 | Repair of Classrooms | 837845 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106570 | San Isidro ES | Paniqui | 1 | 1 | 10 | Repair of Classrooms | 4147472 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106592 | Buenavista ES | PURA | 1 | 1 | 10 | Repair of Classrooms | 4275159 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106613 | Serrano PS | RAMOS | 1 | 1 | 1 | Repair of Classroom | 494268 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1 | 1 | 8 | Repair of Classrooms | 3526330 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106616 | Bamban ES | San Clemente | 1 | 1 | 1 | Repair of Classroom | 558252 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106619 | Doclong 1st ES | San Clemente | 1 | 1 | 3 | Repair of Classrooms | 1658198 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 300985 | San Felipe HS | San Manuel | 1 | 1 | 9 | Repair of Classrooms | 4185564 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106661 | San Manuel | San Manuel | 1 | 1 | 2 | Repair of Classrooms | 795279 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac | 106686 | Taguiporo-Cabaruan ES | Sta. Ignacia | 1 | 1 | 3 | Repair of Classrooms | 1412459 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac City | 106694 | San Nicolas ES | CITY OF TARLAC (Capital) | 2 | 1 | 24 | Repair of Classrooms | 1687448 | 1 | 1687447.61 | COMPLETED | 1 |  |  |  |  | Nov. 26, 2019 | Dec. 2,2019 | Dec. 10, 2019 | Dec. 17, 2019 |  | Boycing Construction Services | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Tarlac City | 106721 | Sepung Calzada Panampunan ES | CITY OF TARLAC (Capital) | 2 | 1 | 13 | Repair of Classrooms | 2726781 | 1 | 2726780.78 | COMPLETED | 1 |  |  |  |  | Nov. 26, 2019 | Dec. 2,2019 | Dec. 10, 2019 | Dec. 17, 2019 |  | J.P Aquino Construction | WAITING FOR SARO RELEASE | [12 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106864 | San Isidro Elementary School | CASTILLEJOS | 1 | 1 | 9 | Repair of Classrooms | 3518889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106837 | Sta. Rita Elementary School | CABANGAN | 2 | 1 | 6 | Repair of Classrooms | 2748889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106849 | San Roque Elementary School | CANDELARIA | 2 | 1 | 8 | Repair of Classrooms | 2938889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106881 | Sta. Barbara Elementary School | IBA (Capital) | 2 | 1 | 8 | Repair of Classrooms | 3668889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 301005 | Bani National High School | MASINLOC | 2 | 1 | 10 | Repair of Classrooms | 5388889 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region III | Zambales | 106920 | Angel C. Manglicmot Mem. Elementary School | SAN ANTONIO | 2 | 1 | 8 | Repair of Classrooms | 2924426 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 161001 | Air Force City Elementary School | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344973.74 | COMPLETED | 1 | 2021-10-30 | 2021-10-07 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301038 | Angeles City Nat'l. Trade School | ANGELES CITY | 1 | 1 | 16 | Repair of Classrooms | 3116479.76 | 1 | 3111464.79 | COMPLETED | 1 | 2021-11-29 | 2021-10-13 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1 | 1 | 32 | Repair of Classrooms | 7096381.72 | 1 | 7086139.77 | COMPLETED | 1 | 2021-11-29 |  |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | GMO Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1 | 1 | 8 | Repair of Classrooms | 3600000 | 1 | 3593489.6 | COMPLETED | 1 | 2021-11-29 |  |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Eldico Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107052 | Apung Guidang Nepomuceno Elementary School | ANGELES CITY | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 | 494888.88 | COMPLETED | 1 | 2021-10-21 | 2021-10-21 |  |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107024 | Belen Homesite ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344960.94 | COMPLETED | 1 | 2021-10-30 | 2021-10-07 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | RAS2 Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107025 | Cutud ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344133.09 | COMPLETED | 1 | 2021-10-30 | 2021-09-30 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Mam Construction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1800000 | 1 | 1794988.33 | COMPLETED | 1 | 2021-10-30 | 2021-10-20 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Nulas Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 301040 | Francisco G. Nepomuceno Mem. HS | ANGELES CITY | 1 | 1 | 24 | Repair of Classrooms | 2923827.98 | 1 | 2916984.81 | COMPLETED | 1 | 2021-10-30 | 2021-09-20 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | EB Matias COnstruction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107041 | Gueco Balibago ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2244540.91 | COMPLETED | 1 | 2021-10-30 | 2021-10-18 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Marveric Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 1 | 2021-10-21 | 2021-10-21 |  |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107059 | Pampang ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2250000 | 1 | 2245474.37 | COMPLETED | 1 | 2021-10-30 | 2021-10-19 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | GMO Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107033 | Pulung Cacutud ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 1 | 2021-10-21 | 2021-10-21 |  |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107034 | Pulungbulo ES | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 900000 | 1 | 892888.88 | COMPLETED | 1 | 2021-10-21 | 2021-10-21 |  |  | 2021-06-21 | 2021-06-26 | 2021-07-30 | 2021-08-02 | 2021-08-17 | Traccor Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 | 1 | 12 | Repair of Classrooms | 2515459.64 | 1 | 2509960.73 | COMPLETED | 1 | 2021-10-30 | 2021-09-20 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | TG Ocampo Construction and Surveying Services | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107035 | Salapungan ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1345777.5 | COMPLETED | 1 | 2021-10-30 | 2021-09-09 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Altitude Engineering and Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107036 | San Ignacio ES | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 1800000 | 1 | 1794767.82 | COMPLETED | 1 | 2021-10-30 | 2021-09-08 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | V.Trillana Builders and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107037 | Sapalibutad ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1350000 | 1 | 1344568.33 | COMPLETED | 1 | 2021-10-30 | 2021-09-30 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Apu Construction, Inc. | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 107048 | Sta. Teresita Elementary School | ANGELES CITY | 1 | 1 | 11 | Repair of Classrooms | 4950000 | 1 | 4938888.88 | COMPLETED | 1 | 2021-11-29 |  |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | Traccor Builders | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Angeles City | 500133 | Sto. Domingo IS | ANGELES CITY | 1 | 1 | 6 | Repair of Classrooms | 2700000 | 1 | 2689371.37 | COMPLETED | 1 | 2021-10-30 | 2021-10-07 |  |  | 2021-06-15 | 2021-06-22 | 2021-07-06 | 2021-07-08 | 2021-07-27 | PVB Construction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104423 | Casiguran CS | CASIGURAN | 0 | 1 | 15 | Repair of Classrooms | 6219097.83 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | 15 | Repair of Classrooms | 6300933.24 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104424 | Dibacong ES | CASIGURAN | 0 | 1 | 8 | Repair of Classrooms | 3472876.98 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 306502 | Dibacong NHS | CASIGURAN | 0 | 1 | 12 | Repair of Classrooms | 5932859.84 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104432 | Diagyan ES | DILASAG | 0 | 1 | 6 | Repair of Classrooms | 2540300.52 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104433 | Dicabasan ES | DILASAG | 0 | 1 | 4 | Repair of Classrooms | 1751483.75 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104434 | Dilaguidi ES | DILASAG | 0 | 1 | 7 | Repair of Classrooms | 3089493.28 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104437 | Diniog ES | DILASAG | 0 | 1 | 8 | Repair of Classrooms | 2782588.68 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104463 | BAYABAS ES | DIPACULAO | 0 | 1 | 12 | Repair of Classrooms | 7497102.63 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300693 | DIPACULAO NHS | DIPACULAO | 0 | 1 | 19 | Repair of Classrooms | 12775492.22 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104483 | TOYTOYAN ES | DIPACULAO | 0 | 1 | 2 | Repair of Classrooms | 1363370.02 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104488 | Cabituculan East ES | MARIA AURORA | 0 | 1 | 11 | Repair of Classrooms | 4813419.68 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300679 | Canili Area NHS | MARIA AURORA | 0 | 1 | 10 | Repair of Classrooms | 5771155.34 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104502 | Kadayakan ES | MARIA AURORA | 0 | 1 | 7 | Repair of Classrooms | 3089493.28 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104485 | Marcos R. Necesito Sr. Memorial ES | MARIA AURORA | 0 | 1 | 5 | Repair of Classrooms | 2183562.85 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 157506 | Ramada ES | MARIA AURORA | 0 | 1 | 6 | Repair of Classrooms | 1778650.81 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 104518 | Diotorin ES | SAN LUIS | 0 | 1 | 2 | Repair of Classrooms | 909958.59 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Aurora | 300686 | DITUMABO NHS | San Luis | 0 | 1 | 18 | Repair of Classrooms | 9558789.84 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1964739.03 | 1 | 1947613.51 | COMPLETED | 1 | 2021-11-09 | 2021-09-17 | 2021-06-01-3R | 2021-06-01-3R | 2021-06-30 | 2021-07-08 | 2021-07-30 | 2021-08-03 | 2021-08-11 | YELLOW CIRCLES CONS. AND TRADING CORP. | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 104557 | Cupang Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 6 | Repair of Classrooms | 3485178.13 | 1 | 3470385 | COMPLETED | 1 | 2021-11-02 |  | 2021-06-01-01 | 2021-06-01-01 | 2021-06-30 | 2021-07-08 | 2021-07-21 | 2021-07-23 | 2021-08-04 | RAVH construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Balanga City | 104562 | Puerto Rivas Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 2 | Repair of Classrooms | 1415596.91 | 1 | 1400000 | COMPLETED | 1 | 2021-11-02 | 2021-09-17 | 2021-06-01-02 | 2021-06-01-02 | 2021-06-30 | 2021-07-08 | 2021-07-21 | 2021-07-23 | 2021-08-04 | L. A. GONIDO BUILDERS INC. | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 300708 | Luakan NHS | DINALUPIHAN | 1 | 1 | 11 | Repair of Classrooms | 7716237.91 | 1 | 7695356.71 | COMPLETED | 1 | 2021-12-19 |  | BEEF CY2021 -REPAIR-0001 | 2021-CON-00017 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-23 | AMP Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104590 | Pita ES | DINALUPIHAN | 1 | 1 | 12 | Repair of Classrooms | 3122076.98 | 1 | 3091400.95 | COMPLETED | 1 | 2021-10-12 | 2021-09-28 | BEEF CY2021 -REPAIR-0002 | 2021-CON-00018 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | Rodmac Construction & Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104595 | San Ramon ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 3443226.79 | 1 | 3432803.2 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0003 | 2021-CON-00019 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RZ Tigas Construction & Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104597 | San Simon ES | DINALUPIHAN | 1 | 1 | 6 | Repair of Classrooms | 5051050.39 | 1 | 5039000 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0004 | 2021-CON-00020 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | De Jesus Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306603 | Sta. Lucia HS | DINALUPIHAN | 1 | 1 | 5 | Repair of Classrooms | 3224558.77 | 1 | 3214492.95 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0005 | 2021-CON-00021 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | MJ Camacho Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104663 | Orani North ES | ORANI | 1 | 1 | 12 | Repair of Classrooms | 5728355.99 | 1 | 5677892.94 | COMPLETED | 1 | 2021-12-10 |  | BEEF CY2021 -REPAIR-0006 | 2021-CON-00022 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | AJN Construction INC | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104672 | Talimundoc ES | ORANI | 1 | 1 | 5 | Repair of Classrooms | 4452753.42 | 1 | 4421845.34 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0007 | 2021-CON-00023 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RWD Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104702 | F.C. Del Rosario ES | SAMAL | 1 | 1 | 6 | Repair of Classrooms | 3450193.48 | 1 | 3440178.44 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0008 | 2021-CON-00024 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | Bonibal Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104708 | Samal South ES | SAMAL | 1 | 1 | 4 | Repair of Classrooms | 2855061.48 | 1 | 2841340.27 | COMPLETED | 1 | 2021-10-12 | 2021-10-08 | BEEF CY2021 -REPAIR-0009 | 2021-CON-00025 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-05 | 2021-07-08 | 2021-07-15 | RCS Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104709 | Sapa ES | SAMAL | 1 | 1 | 6 | Repair of Classrooms | 4845801.52 | 1 | 4835618.09 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0010 | 2021-CON-00026 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Mecon Systems | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104541 | Bagac ES | BAGAC | 2 | 1 | 14 | Repair of Classrooms | 7196707.49 | 1 | 7160574.49 | COMPLETED | 1 | 2021-12-10 |  | BEEF CY2021 -REPAIR-0011 | 2021-CON-00027 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | BQA Construction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104640 | Bayview ES | MARIVELES | 2 | 1 | 5 | Repair of Classrooms | 2003696.12 | 1 | 1993634.94 | COMPLETED | 1 | 2021-10-10 | 2021-10-08 | BEEF CY2021 -REPAIR-0012 | 2021-CON-00028 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Macco Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306607 | Mariveles NHS Cab. Annex- New Alion | MARIVELES | 2 | 1 | 16 | Repair of Classrooms | 7719964.38 | 1 | 7669082.06 | COMPLETED | 1 | 2021-12-10 |  | BEEF CY2021 -REPAIR-0014 | 2021-CON-00030 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | V Trillana Builders and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 306610 | Mariveles NHS Cab.-Annex-Batangas II | MARIVELES | 2 | 1 | 4 | Repair of Classrooms | 3505504.87 | 1 | 3500165.91 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0015 | 2021-CON-00031 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Five A Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 300710 | Mariveles NHS Cabcaben | MARIVELES | 2 | 1 | 15 | Repair of Classrooms | 6715056.17 | 1 | 6614285.57 | COMPLETED | 1 | 2021-12-10 |  | BEEF CY2021 -REPAIR-0013 | 2021-CON-00029 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Turquoise Construction & Realty Development | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104678 | Capunitan ES | ORION | 2 | 1 | 6 | Repair of Classrooms | 5364413.31 | 1 | 5354192.45 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0016 | 2021-CON-00032 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | RTDJR Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104683 | Pablo R. Roman ES | ORION | 2 | 1 | 6 | Repair of Classrooms | 5753642.58 | 1 | 5732990.17 | COMPLETED | 1 | 2021-12-10 |  | BEEF CY2021 -REPAIR-0017 | 2021-CON-00033 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | Polymer Vic Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bataan | 104695 | Panilao ES | PILAR | 2 | 1 | 8 | Repair of Classrooms | 4518178.57 | 1 | 4505663.68 | COMPLETED | 1 | 2021-11-11 |  | BEEF CY2021 -REPAIR-0018 | 2021-CON-00034 | June 8, 2021 to June 22, 2021 | 2021-06-15 | 2021-07-06 | 2021-07-08 | 2021-07-15 | NBZ Engineering & Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104797 | Buguion ES | CALUMPIT | 1 | 1 | 8 | Repair of Classrooms | 5539435.93 | 1 | 3700000 | COMPLETED | 1 | 2022-02-11 | 2021-12-28 | PB-21-016 | PB-21-027 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104729 | Borol I ES | BALAGTAS | 2 | 1 | 6 | Repair of Classrooms | 3094968.93 | 1 | 2341888.88 | COMPLETED | 1 | 2022-01-12 | 2022-01-10 | PB-21-017 | PB-21-028 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104740 | Dr. N.V. Rustia MS | BALIUAG | 2 | 1 | 5 | Repair of classrooms | 2973898 | 1 | 2221888.88 | COMPLETED | 1 | 2022-01-12 | 2022-01-10 | PB-21-018 | PB-21-029 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 306717 | Teodoro Evangelista Mem. HS | BALIUAG | 2 | 1 | 2 | Repair of Classrooms | 1084238.79 | 1 | 878179.43 | COMPLETED | 1 | 2021-12-13 | 2022-02-10 | PB-21-020 | PB-21-031 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | G.M. CAPARAS CONSTRUCTION AND SUPPLY | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104759 | Tiaong ES | BALIUAG | 2 | 1 | 10 | Repair of Classrooms | 6046645.27 | 1 | 4383888.88 | COMPLETED | 1 | 2022-02-11 | 2021-12-03 | PB-21-019 | PB-21-030 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | ALTITUDE ENGINEERING AND CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300720 | Alexis G. Santos National High School | BUSTOS | 2 | 1 | 12 | Repair of Classrooms | 4467440.6 | 1 | 3000000 | COMPLETED | 1 | 2022-02-11 | 2021-11-18 | PB-21-021 | PB-21-032 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 104721 | Paltok Elementary School | ANGAT | 3 | 1 | 9 | Repair of Classrooms | 5149218.55 | 1 | 4089389.39 | COMPLETED | 1 | 2022-02-11 | 2022-01-21 | PB-21-022 | PB-21-033 | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-25 | 2021-09-07 | D' JARED VIEW CONSTRUCTION CORP. | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105074 | Kalawakan Elementary School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 4 | Repair of Classrooms | 2086281.89 | 1 | 1519879.67 | COMPLETED | 1 | 2022-02-23 | 2022-02-11 | PB-21-023 | PB-21-061 | 2021-09-17 | 2021-09-24 | 2021-10-06 | 2021-10-12 | 2021-10-19 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105076 | Kalayakan E/S | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 3 | Repair of Classrooms | 2242268.01 | 1 | 1634818.96 | COMPLETED | 1 | 2022-02-23 | 2022-01-20 | PB-21-024 | PB-21-062 | 2021-09-17 | 2021-09-24 | 2021-10-06 | 2021-10-12 | 2021-10-19 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300758 | MINUYAN NATIONAL HIGH SCHOOL | NORZAGARAY | 3 | 1 | 16 | Repair of Classrooms | 6246511.56 | 1 | 4398425.46 | COMPLETED | 1 | 2022-02-11 | 2022-02-11 | PB-21-025 | PB-21-034 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | T.G. OCAMPO CONSTRUCTION AND SURVEYING SERVICES | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105050 | Bagong Baryo Elementary School | SAN ILDEFONSO | 3 | 1 | 9 | Repair of Classrooms | 6095001.86 | 1 | 5554601.96 | COMPLETED | 1 | 2022-02-18 | 2021-12-20 | PB-21-027 | PB-21-048 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-09-01 | 2021-09-14 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105034 | Calawitan Elementary School | SAN ILDEFONSO | 3 | 1 | 12 | Repair of Classrooms | 4524468.72 | 1 | 3244044.07 | COMPLETED | 1 | 2022-02-11 | 2022-01-20 | PB-21-026 | PB-21-035 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | GMO CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300730 | Calawitan NHS | SAN ILDEFONSO | 3 | 1 | 17 | Repair of Classrooms | 5945745.09 | 1 | 4263099.23 | COMPLETED | 1 | 2022-02-11 | 2022-02-11 | PB-21-028 | PB-21-036 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | GMO CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300772 | Partida HS (San Miguel NHS - Partida HS) | SAN MIGUEL | 3 | 1 | 13 | Repair of Classrooms | 3728391.26 | 1 | 3105283.35 | COMPLETED | 1 | 2022-01-19 | 2021-11-29 | PB-21-030 | PB-21-049 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-09-01 | 2021-09-14 | R.G. ROQUE CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 158502 | San Vicente ES | SAN MIGUEL | 3 | 1 | 3 | Repair of Classrooms | 1733486.25 | 1 | 1609677.73 | COMPLETED | 1 | 2022-01-12 | 2022-01-17 | PB-21-029 | PB-21-037 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | S.M. SEVERINO CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 105126 | Pasong Inchik ES | SAN RAFAEL | 3 | 1 | 7 | Repair of Classrooms | 3691870.19 | 1 | 2944713.7 | COMPLETED | 1 | 2022-01-12 | 2022-01-10 | PB-21-031 | PB-21-038 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | R.G. ROQUE CONSTRUCTION AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Bulacan | 300740 | ASSEMBLYWOMAN FELICITA G. BERNARDINO MEMORIAL TRADE SCHOOL | MARILAO | 4 | 1 | 12 | Repair of Classrooms | 3261889.39 | 1 | 2480102.24 | COMPLETED | 1 | 2022-01-12 | 2022-01-10 | PB-21-032 | PB-21-039 | 2021-07-13 | 2021-07-22 | 2021-08-05 | 2021-08-25 | 2021-09-07 | RHR CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Cabanatuan City | 107081 | Ibabao Bana ES | CABANATUAN CITY | 3 | 1 | 2 | Repair of Classrooms | 811379.13 | 1 |  | COMPLETED | 1 | 2021-09-03 | 2021-08-31 | [7 empty] | RC Pallarca Contruction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Cabanatuan City | 107114 | Pagas Elementary School | CABANATUAN CITY | 3 | 1 | 4 | Repair of Classrooms | 2167148.36 | 1 |  | COMPLETED | 1 | 2021-11-02 | 2021-09-03 | [7 empty] | Marvelous Quejada Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Gapan City | 105322 | Mabuga ES | CITY OF GAPAN | 4 | 1 | 4 | Repair of Classrooms | 2788898.31 | 1 | 2779344.7 | COMPLETED | 1 | 2021-10-03 | 2021-09-08 | 2021-05-31-001-CL-Repair | 2021-05-31-001-CL-Repair | 2021-06-01 | 2021-06-08 | 2021-06-21 | 2021-06-28 | 2021-07-05 | Joynieltin Construction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106073 | Bical ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1200000 | 1 | 1188888.88 | COMPLETED | 1 | 2021-10-17 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | F.A ASPRER CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106064 | Calumpang ES | MABALACAT CITY | 1 | 1 | 7 | Repair of Classrooms | 4000000 | 1 | 3970038.52 | COMPLETED | 1 | 2021-12-09 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106075 | Dapdap ES | MABALACAT CITY | 1 | 1 | 7 | Repair of Classrooms | 3000000 | 1 | 2989121.21 | COMPLETED | 1 | 2021-10-25 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106078 | Duquit ES | MABALACAT CITY | 1 | 1 | 4 | Repair of Classrooms | 1304023.09 | 1 | 1288888.88 | COMPLETED | 1 | 2021-10-17 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106080 | Lakandula ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 | 1363525.22 | COMPLETED | 1 | 2021-10-17 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1 | 1 | 12 | Repair of Classrooms | 3200000 | 1 | 2896823.85 | COMPLETED | 1 | 2021-11-26 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT CITY | 1 | 1 | 26 | Repair of Classrooms | 10000000 | 1 | 7188888.88 | COMPLETED | 1 | 2021-12-12 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | NULAS BUILDERS | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106069 | Mauaque Resetlement ES | MABALACAT CITY | 1 | 1 | 18 | Repair of Classrooms | 7000000 | 1 | 6989813.25 | COMPLETED | 1 | 2021-12-09 |  |  |  | 2019-07-08 | 2019-07-15 | 2019-07-29 | 2019-08-06 | 2019-09-06 | TRACCOR BUILDERS | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106070 | San Joaquin ES | MABALACAT CITY | 1 | 1 | 18 | Repair of Classrooms | 9000000 | 1 | 6210013.85 | COMPLETED | 1 | 2021-12-16 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 306942 | Santos Ventura National High School | MABALACAT CITY | 1 | 1 | 24 | Repair of Classrooms | 6000000 | 1 | 4664104.47 | COMPLETED | 1 | 2021-12-12 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106071 | Sapang Biabas Resettlement ES | MABALACAT CITY | 1 | 1 | 12 | Repair of Classrooms | 6000000 | 1 | 4799865.66 | COMPLETED | 1 | 2021-12-16 |  |  |  | 2018-11-13 | 2018-11-22 | 2018-12-06 | 2019-01-11 | 2019-08-27 | F.A ASPRER CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 345342 | SHS within Sapang Biabas Resettlement ES | MABALACAT CITY | 1 | 1 | 3 | Repair of Classrooms | 1686102.39 | 1 | 1306846.51 | COMPLETED | 1 | 2021-10-17 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 106072 | Sta. Ines ES | MABALACAT CITY | 1 | 1 | 24 | Repair of Classrooms | 7000000 | 1 | 5247520.08 | COMPLETED | 1 | 2021-12-09 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | 17 | Repair of Classrooms | 7200000 | 1 | 7169996.42 | COMPLETED | 1 | 2021-12-16 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 104887 | Balayong ES | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | Repair of Classrooms | 1514093.45 | 1 | 1029265.01 | COMPLETED | 1 | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-01 | RADIANCE TRADERS & BUILDERS | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 323604 | Cong. Teodulo Natividad High School | CITY OF MALOLOS (Capital) | 1 | 1 | 12 | Repair of Classrooms | 2071171.7 | 1 | 1659737.13 | COMPLETED | 1 | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-01 | R. G. DIAZ BUILDERS AND TRADING | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Malolos City | 104869 | Dakila ES | CITY OF MALOLOS (Capital) | 1 | 1 | 2 | Repair of Classrooms | 1364038.83 | 1 | 1049168.41 | COMPLETED | 1 | 2021-12-29 |  |  |  | 07/02-0709/2021 | 2021-07-09 | 2021-07-22 | 2021-08-11 | 2021-09-02 | ELMUEL JAY TRADING & CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 4 | Repair of Classrooms | 1735446.03 | 1 | 1215979.68 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 500967 | Malhacan Integrated School | CITY OF MEYCAUAYAN | 4 | 1 | 2 | Repair of Classrooms | 1039502.43 | 1 | 828529.23 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Meycauayan City | 104936 | Tugatog ES | CITY OF MEYCAUAYAN | 4 | 1 | 4 | Repair of Classrooms | 1627673.53 | 1 | 1160149.17 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105537 | Licaong ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 1 | Repair of Classroom | 189079 | 1 |  | COMPLETED | 1 | 2021-10-04 | 2021-08-16 |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500396 | Magtanggol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2436219.35 | 1 |  | COMPLETED | 1 | 2021-10-29 |  |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | AMC CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500396 | Magtanggol IS | SCIENCE CITY OF MUÑOZ | 2 |  | 4 | Repair of Classrooms | 1998270.36 | 1 |  | COMPLETED | 1 | 2021-10-29 |  |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | GR ERCILLA CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105549 | Mangandingay Elementary School | SCIENCE CITY OF MUÑOZ | 2 | 1 | 7 | Repair of Classrooms | 3643972.5 | 1 |  | COMPLETED | 1 | 2021-11-28 |  |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | FC MARTINEZ CONSTRUCTION DEVELOPMENT AND SUPPLY CORPORATION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 500398 | Palusapis IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2239646.39 | 1 |  | COMPLETED | 1 | 2021-10-29 |  |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | D.B. BARAQUEL CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105563 | Villa Isla ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2075870.16 | 1 |  | COMPLETED | 1 | 2021-10-29 |  |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | MN COLOMA CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Munoz Science City | 105564 | Villa Nati ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | Repair of Classrooms | 436159.58 | 1 |  | COMPLETED | 1 | 2021-10-04 | 2021-08-16 |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 22 | Repair of Classrooms | 10000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105280 | C.B. Tejero E/S | CUYAPO | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105267 | Columbitin Elementry School | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 306824 | Cuyapo National High School Annex | CUYAPO | 1 | 1 | 7 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105273 | Dr. A. Ongsiako Sr. ES | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105279 | Matindeg ES | CUYAPO | 1 | 1 | 1 | Repair of Classroom | 500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105296 | Tagtagumbao PS | CUYAPO | 1 | 1 | 3 | Repair of Classrooms | 1703864.41 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105405 | Bagong Barrio ES | GUIMBA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105407 | Balingog West ES | GUIMBA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105380 | Cavite ES | GUIMBA | 1 | 1 | 10 | Repair of Classrooms | 4312500 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105382 | Consuelo ES | GUIMBA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105388 | Guiset ES | GUIMBA | 1 | 1 | 8 | Repair of Classrooms | 3812500 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105419 | Macamias ES | GUIMBA | 1 | 1 | 4 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 501658 | Maybubon Integrated School | GUIMBA | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105399 | Sta. Cruz ES | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105430 | STA. VERONICA ELEMENTARY SCHOOL | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105433 | Yuson ES | GUIMBA | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105480 | Licab CS | LICAB | 1 | 1 | 18 | Repair of Classrooms | 8062500 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105481 | Linao ES | LICAB | 1 | 1 | 5 | Repair of Classrooms | 2500000 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105483 | San Casimiro ES | LICAB | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105619 | Bertese ES | QUEZON | 1 | 1 | 5 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105622 | Labong ES | QUEZON | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105623 | Pulong Bahay Elementary School | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105624 | Quezon CS | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3358788.77 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105627 | San Andres I ES | QUEZON | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105629 | San Manuel ES | QUEZON | 1 | 1 | 10 | Repair of Classrooms | 4312500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105631 | Sta. Rita ES | QUEZON | 1 | 1 | 11 | Repair of Classrooms | 4562500 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105769 | Buasao ES | SANTO DOMINGO | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105775 | Dolores ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105785 | Sta. Rita ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105781 | Villa Juan ES | SANTO DOMINGO | 1 | 1 | 6 | Repair of Classrooms | 2812500 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105789 | Bagong Silang ES | TALAVERA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105790 | Bakal I ES | TALAVERA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105791 | Bakal II ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 1976215.59 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105794 | Bulac ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105798 | Casulucan Este ES | TALAVERA | 1 | 1 | 2 | Repair of Classrooms | 1000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105817 | Dimasalang Sur ES | TALAVERA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 | 1 | 10 | Repair of Classrooms | 5000000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105831 | Sibul ES | TALAVERA | 1 | 1 | 4 | Repair of Classrooms | 1976215.59 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105855 | Concepcion East ES | ZARAGOZA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105856 | Concepcion West ES | ZARAGOZA | 1 | 1 | 8 | Repair of Classrooms | 3812500 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159016 | Felicidad V. Buendia ES | ZARAGOZA | 1 | 1 | 4 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159010 | Manaol ES | ZARAGOZA | 1 | 1 | 4 | Repair of Classrooms | 2000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105860 | Mayamot ES | ZARAGOZA | 1 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105861 | San Isidro Elementary School | ZARAGOZA | 1 | 1 | 15 | Repair of Classrooms | 6562500 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105864 | Sta. Lucia (Y) ES | ZARAGOZA | 1 | 1 | 6 | Repair of Classrooms | 3000000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105595 | Cambitala ES | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1710328.89 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105600 | Liberty ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1968182.78 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105601 | Marikit ES | PANTABANGAN | 2 | 1 | 2 | Repair of Classrooms | 1122245.81 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 159007 | Masiway ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1918731.2 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105604 | Pantabangan East CS | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1494082.21 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105606 | Salvacion Elementary School | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms | 1951540.35 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105608 | San Juan ES | PANTABANGAN | 2 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105638 | Bicos ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1147507.92 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105639 | Cabucbucan ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105648 | Macapsing ES | RIZAL | 2 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105299 | Bagting ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1123672.8 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105300 | Bantug ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1135127.05 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105303 | Calabasa ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1123672.8 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105304 | Camatchile Elementay School | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | Repair of Classrooms | 1209314.78 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105310 | Malinao Elementary School | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105347 | Balangkare ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 2 | Repair of Classrooms | 1154027.53 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105462 | Casa Real Elementary School | LAUR | 3 | 1 | 3 | Repair of Classrooms | 1746398.03 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105578 | Langka ES | PALAYAN CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1230314.78 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105590 | Pinaltakan ES(Red Cross Village PS) | PALAYAN CITY (Capital) | 3 | 1 | 2 | Repair of Classrooms | 1230314.78 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300856 | Sta. Rita NHS | CABIAO | 4 | 1 | 3 | Repair of Classrooms | 1746398.03 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105369 | Nazareth Elementary School | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms | 975216.62 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 300848 | San Mariano National High School | SAN ANTONIO | 4 | 1 | 12 | Repair of Classrooms | 5500000 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Nueva Ecija | 105688 | San Roque ES | SAN ISIDRO | 4 | 1 | 3 | Repair of Classrooms | 1927485.54 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 301050 | Baretto National HIgh School | OLONGAPO CITY | 1 | 1 | 8 | Repair of Classrooms | 4400000 | 1 | 4389769.38 | COMPLETED | 1 | 2021-11-23 |  | 2021-07-194 lot 4 | 2021-07-194 lot 4 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | J.I. Viacrusis Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107119 | Boton ES | OLONGAPO CITY | 1 | 1 | 11 | Repair of Classrooms | 6000000 | 1 | 5957131.73 | COMPLETED | 1 | 2021-12-23 |  | 2021-07-194 lot 3 | 2021-07-194 lot 3 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | V. Trillana Builders and Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107126 | Gordon Heights I Elementary School | OLONGAPO CITY | 1 | 1 | 30 | Repair of Classrooms | 12000000 | 1 | 11969997.92 | COMPLETED | 1 | 2022-01-21 |  | 2021-07-194 lot 1 | 2021-07-194 lot 1 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | Mitzie Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 301056 | Kalalake NHS | OLONGAPO CITY | 1 | 1 | 14 | Repair of Classrooms | 7600000 | 1 | 7569619.71 | COMPLETED | 1 | 2021-12-23 |  | 2021-07-194 lot 2 | 2021-07-194 lot 2 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | AMP Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Olongapo City | 107130 | Tabacuhan ES | OLONGAPO CITY | 1 | 1 | 7 | Repair of Classrooms | 3593934.69 | 1 | 3542319.53 | COMPLETED | 1 | 2021-11-23 |  | 2021-07-194 lot 5 | 2021-07-194 lot 5 | 2021-07-08 | 2021-07-16 | 2021-07-28 | 2021-08-13 | 2021-08-25 | Bancal Construction and Supply | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106119 | Bucanan Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1538159.62 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 159527 | Mariano D. Baron ES | MAGALANG | 1 | 1 | 4 | Repair of Classrooms | 1529504.96 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106131 | San Miguel ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1016684.6 | 1 | 1182095.53 | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106141 | Talimundoc Elementary School | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 1376840.38 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105966 | FLORIDABLANCA ELEMENTARY SCHOOL | FLORIDABLANCA | 2 | 1 | 6 | Repair of Classrooms | 3711312.31 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 159528 | Sitio Culubasa ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 2419352.65 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105975 | Sta. Monica ES | FLORIDABLANCA | 2 | 1 | 6 | Repair of Classrooms | 3490321.48 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105976 | Sto. Rosario ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 2437094.17 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 2 | Repair of Classrooms | 1016684.6 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106013 | San Antonio ES | GUAGUA | 2 | 1 | 5 | Repair of Classrooms | 2449530.1 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106057 | Santiago ES | LUBAO | 2 | 1 | 5 | Repair of Classrooms | 2667607.41 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106216 | Camias ES | PORAC | 2 | 1 | 8 | Repair of Classrooms | 3736512.16 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106296 | V. De Castro ES | SANTA RITA | 2 | 1 | 6 | Repair of Classrooms | 3045421.61 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106267 | Batang II ES | SASMUAN (SEXMOAN) | 2 | 1 | 2 | Repair of Classrooms | 1486465.98 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106271 | San Pedro ES | SASMUAN (SEXMOAN) | 2 | 1 | 4 | Repair of Classrooms | 2508155.57 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105898 | Arayat CS | ARAYAT | 3 | 1 | 8 | Repair of Classrooms | 3705737.72 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105881 | Batasan ES | ARAYAT | 3 | 1 | 8 | Repair of Classrooms | 3900024.22 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105883 | Candating ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3739085.41 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105885 | Guemasan ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3981381.25 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105886 | Lacquios ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3503855.85 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105887 | Mapalad ES | ARAYAT | 3 | 1 | 5 | Repair of Classrooms | 2766819.95 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 305740 | San Juan Baño High School | ARAYAT | 3 | 1 | 10 | Repair of Classrooms | 2454028.14 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105893 | San Nicolas ES | ARAYAT | 3 | 1 | 7 | Repair of Classrooms | 3503855.85 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106172 | Malino ES | MEXICO | 3 | 1 | 6 | Repair of Classrooms | 3117879 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106189 | Pandacaqui Resettlement Elementary School | MEXICO | 3 | 1 | 8 | Repair of Classrooms | 3189141.64 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105869 | Cansinala Elementary School | APALIT | 4 | 1 | 6 | Repair of Classrooms | 3703073.13 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105870 | Fausto Gonzales Sioco Memorial School | APALIT | 4 | 1 | 5 | Repair of Classrooms | 2900097.13 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105871 | Galang Memo. ES (Calantipe ES) | APALIT | 4 | 1 | 5 | Repair of Classrooms | 3063958.63 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105875 | Sampaga ES | APALIT | 4 | 1 | 4 | Repair of Classrooms | 2749163.22 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105878 | Sto. Rosario ES | APALIT | 4 | 1 | 8 | Repair of Classrooms | 4849474.59 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105879 | Sucad ES | APALIT | 4 | 1 | 10 | Repair of Classrooms | 5935952.22 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105880 | Sulipan ES | APALIT | 4 | 1 | 6 | Repair of Classrooms | 3115052.34 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105929 | Bahay Pare ES | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105955 | Gulap ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2648153.32 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105956 | Lanang ES | CANDABA | 4 | 1 | 2 | Repair of Classrooms | 1434384.43 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105936 | Magumbali Elementary School | CANDABA | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 105957 | Mandasig ES | CANDABA | 4 | 1 | 4 | Repair of Classrooms | 2733276.36 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106097 | San Vicente Ferrer ES | MACABEBE | 4 | 1 | 3 | Repair of Classrooms | 1651357.85 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106241 | San Isidro ES | SAN LUIS | 4 | 1 | 7 | Repair of Classrooms | 3506001.97 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106242 | San Jose ES | SAN LUIS | 4 | 1 | 6 | Repair of Classrooms | 3117879.32 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106245 | San Luis CS | SAN LUIS | 4 | 1 | 2 | Repair of Classrooms | 1107135.94 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Pampanga | 106253 | Sto. Rosario ES | SAN LUIS | 4 | 1 | 5 | Repair of Classrooms | 3034613.11 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500981 | Arch. E. Cinense Memorial Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107167 | Bulaon ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1906166.55 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500146 | Calulut IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107180 | Del Rosario ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1821749.41 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500136 | Lara IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500145 | Maimpis IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500980 | Malpitic Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 307611 | Northville High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1799902.5 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 12 | Repair of Classrooms | 5220000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500979 | Pandaras Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 5 | Repair of Classrooms | 3500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500978 | Pulung Bulu Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500143 | Saguin IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107195 | San Fernando ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 5916427 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 107175 | San Jose-Juliana ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 3 | Repair of Classrooms | 1500000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Fernando City | 500150 | Sta. Lucia Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 1840000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose City | 105709 | San Jose East Central School | SAN JOSE CITY | 2 | 1 | 13 | Repair of Classrooms | 3497407.03 | 1 | 3497407.03 | COMPLETED | 1 | 2021-12-19 |  | REPAIR 2021 - RIII - SAN JOSE CITY - 001 | [6 empty] | JGR DESIGN AND CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose City | 105727 | Saranay Elementary School | SAN JOSE CITY | 2 | 1 | 3 | Repair of Classrooms | 1213958.94 | 1 |  | COMPLETED | 1 | 2021-09-19 | 2021-09-19 | REPAIR 2021 - RIII - SAN JOSE CITY - 002 | [6 empty] | ADROIT CONSTRUCTION | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107144 | Bagong Buhay E ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | Repair of Classrooms | 3610367.54 | 1 | 3564888.88 | COMPLETED | 1 | 2021-12-07 |  | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 001 | PB-ER-CW-2021-07-01 lot 1 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | Altitude Engineering and Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107149 | Minuyan ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | Repair of Classrooms | 4851098.41 | 1 | 4831093.18 | COMPLETED | 1 | 2021-12-07 | 2021-10-19 | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 002 | PB-ER-CW-2021-07-01 lot 2 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | RKEA Builders and Supply | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | San Jose del Monte City | 107163 | SAN RAFAEL (BBH) ELEMENTARY SCHOOL | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | Repair of Classrooms | 2006901.5 | 1 | 1993656.57 | COMPLETED | 1 | 2021-12-07 | 2021-10-19 | REPAIR 2021 - RIII - SAN JOSE DEL MONTE CITY - 003 | PB-ER-CW-2021-07-01 lot 3 | 2021-07-04 | 2021-07-14 | 2021-07-26 | 2021-08-06 | 2021-08-09 | Che-Riss Construction and Trading | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106309 | San Jose ES | ANAO | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106338 | Bancay I ES | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 846601.64 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106342 | Caniag ES | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 1078788.65 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106361 | Cayasan PS | CAMILING | 1 | 1 | 2 | Repair of Classrooms & Toilets | 846676.14 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106362 | Libueg ES | CAMILING | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106346 | Malacampa ES - Main | CAMILING | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2005912.29 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106332 | Pindangan 2nd ES | CAMILING | 1 | 1 | 5 | Repair of Classrooms & Toilets | 2747329.51 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106335 | Surgui ES | CAMILING | 1 | 1 | 5 | Repair of Classrooms & Toilets | 2516279.6 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106522 | Rotrottooc-Calabtangan ES | MAYANTOC | 1 | 1 | 1 | Repair of Classrooms & Toilets | 491854 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106523 | San Bartolome ES | MAYANTOC | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2317898.59 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106525 | Taldiapan PS | MAYANTOC | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1605328.99 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106541 | Banaoang East Elementary School | MONCADA | 1 | 1 | 1 | Repair of Classrooms & Toilets | 490723.35 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106528 | Calamay ES | MONCADA | 1 | 1 | 2 | Repair of Classrooms & Toilets | 857532.76 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106547 | Camangaan PS | MONCADA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106529 | Lapsing ES | MONCADA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1637633.26 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106532 | Moncada North CS | MONCADA | 1 | 1 | 4 | Repair of Classrooms | 2546329.18 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106577 | Carino ES | PANIQUI | 1 | 1 | 3 | Repair of Classrooms | 1482402.1 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106595 | Doña Felisa Y. Sawit ES | PURA | 1 | 1 | 6 | Repair of Classrooms & Toilets | 3395792.52 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106596 | Estipona ES | PURA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1899462.94 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106599 | Matindeg ES | PURA | 1 | 1 | 3 | Repair of Classrooms & Toilets | 1632680.09 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106603 | Poroc PS | PURA | 1 | 1 | 2 | Repair of Classrooms & Toilets | 1261201.14 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1 | 1 | 4 | Repair of Classrooms | 1928035.01 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106612 | San Raymundo ES | RAMOS | 1 | 1 | 3 | Repair of Classrooms | 1792612.4 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106615 | Balloc ES | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 1702097.21 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106622 | Maasin Elementary School | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 2768946.07 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106653 | Legaspi ES | SAN MANUEL | 1 | 1 | 8 | Repair of Classrooms | 4839624.09 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106657 | Salcedo ES | SAN MANUEL | 1 | 1 | 3 | Repair of Classrooms | 1779579.11 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106673 | Nambalan ES | SANTA IGNACIA | 1 | 1 | 10 | Repair of Classrooms | 4954809.45 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106674 | Pilpila ES | SANTA IGNACIA | 1 | 1 | 3 | Repair of Classrooms | 1752756.61 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106629 | David Elementary School | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 2406468.52 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 307001 | Moriones High School | SAN JOSE | 2 | 1 | 2 | Repair of Classrooms | 1173034.34 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 160015 | Quimmardero Elementary School | SAN JOSE | 2 | 1 | 5 | Repair of Classrooms | 2480562.82 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106646 | Sta. Cruz ES | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 1694032.09 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 307021 | Balayang HS | VICTORIA | 2 | 1 | 9 | Repair of Classrooms | 3292984.28 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106787 | Bulo ES | VICTORIA | 2 | 1 | 7 | Repair of Classrooms | 3922672.67 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106780 | Mangolago Elementary School | VICTORIA | 2 | 1 | 3 | Repair of Classrooms | 1544896.65 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106782 | San Agustin ES | VICTORIA | 2 | 1 | 5 | Repair of Classrooms | 2728771.37 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106314 | Banaba ES | BAMBAN | 3 | 1 | 6 | Repair of Classrooms | 3288427.8 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106311 | Pag-asa Elementary School | BAMBAN | 3 | 1 | 6 | Repair of Classrooms | 2740683 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106373 | Dolores ES | CAPAS | 3 | 1 | 4 | Repair of Classrooms | 2393193.01 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106372 | Juan Navarro ES | CAPAS | 3 | 1 | 2 | Repair of Classrooms | 1276692.87 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106374 | Kawili-Wili ES | CAPAS | 3 | 1 | 3 | Repair of Classrooms | 1753488.11 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 300968 | Lawy NHS | CAPAS | 3 | 1 | 6 | Repair of Classrooms | 3178167.26 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106404 | Concepcion North CES | CONCEPCION | 3 | 1 | 11 | Repair of Classrooms | 4377888.63 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106428 | Concepcion West Central ES | CONCEPCION | 3 | 1 | 9 | Repair of Classrooms | 4045549.89 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106399 | Magunting ES | CONCEPCION | 3 | 1 | 5 | Repair of Classrooms | 2912652.73 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106496 | Bantog ES | LA PAZ | 3 | 1 | 6 | Repair of Classrooms | 3477686.04 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106493 | Matayumtayum ES | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1619336.1 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106494 | Mayang ES | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1772645.66 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac | 106504 | Rizal Multigrade | LA PAZ | 3 | 1 | 3 | Repair of Classrooms | 1628242.98 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac City | 106740 | Lourdes ES | CITY OF TARLAC (Capital) | 2 | 1 | 5 | Repair of Classrooms | 1649234.99 | 1 | 1393961.94 | COMPLETED | 1 | 2021-10-30 | [8 empty] | MRRM Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Tarlac City | 106772 | Tarlac West Central ES | CITY OF TARLAC (Capital) | 2 | 1 | 17 | Repair of Classrooms | 6822915.62 | 1 | 6455834.24 | COMPLETED | 1 | 2021-10-30 | [8 empty] | AR. ESBI Construction | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 160507 | Buenavista Elementary School | CASTILLEJOS | 1 | 1 | 4 | Repair of classrooms | 1811036.46 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106950 | Linusungan Elementary School | SAN MARCELINO | 1 | 1 | 12 | Repair of classrooms | 5299956.09 | 1 |  | COMPLETED | 1 | 2022-10-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 107021 | Tibag Elementary School | SUBIC | 1 | 1 | 4 | Repair of classrooms | 1581329.3 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | 8 | Repair of classrooms | 3268711.74 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106818 | Bucao Elementary School | BOTOLAN | 2 | 1 | 7 | Repair of classrooms | 2589175.25 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106830 | Laoag Elementary School | CABANGAN | 2 | 1 | 7 | Repair of classrooms | 3464002.24 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region III | Zambales | 106838 | Sto. Nino Primary School | CABANGAN | 2 | 1 | 3 | Repair of classrooms | 1273198.44 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106843 | Dampay Elementary School | CANDELARIA | 2 | 1 | 7 | Repair of classrooms | 1943439.6 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region III | Zambales | 106915 | Manggahan Elementary Scchool | PALAUIG | 2 | 1 | 5 | Repair of classrooms | 2188736.27 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44958 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 501022 | Don Ambrocio Mendiola ES | ANGELES CITY | 1 | 1 | 3 | Repair of Classrooms | 1650000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107027 | Dr. Clemente N. Dayrit Sr. Elem. School | ANGELES CITY | 1 | 1 | 2 | Repair of Classrooms | 1500000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1 | 1 | 5 | Repair of Classrooms | 2750000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Angeles City | 107051 | Virgen Delos Remedios Elementary School | ANGELES CITY | 1 | 1 | 4 | Repair of Classrooms | 2100000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104610 | Hermosa ES | HERMOSA | 1 | 1 | 7 | Repair of Classrooms & Toilet | 3587274.66 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104661 | Kaparangan ES | ORANI | 1 | 1 | 3 | Repair of Classrooms & Toilet | 1888335.16 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104700 | Adamson ES | SAMAL | 1 | 1 | 5 | Repair of Classrooms & Toilet | 3597965.23 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Bataan | 104573 | Daang Bago ES | DINALUPIHAN | 3 | 1 | 5 | Repair of Classrooms & Toilet | 3788120.23 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107095 | Bakero Elementary School | CABANATUAN CITY | 3 | 1 | 3 | Repair of Classrooms | 1435845.59 | 2 | 1435845.59 | COMPLETED | 1 | 2022-12-20 | 2022-12-06 |  | 08-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | RC Pallarca Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107109 | Cabanatuan North ES | CABANATUAN CITY | 3 | 1 | 8 | Repair of Classrooms | 3246291.99 | 2 | 3246291.99 | COMPLETED | 1 | 2023-01-19 | 2023-01-04 |  | 09-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | R.B. Valera Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Cabanatuan City | 107116 | Sumacab ES | CABANATUAN CITY | 3 | 1 | 12 | Repair of Classrooms | 8318700.46 | 2 | 8318700.46 | COMPLETED | 1 | 2023-01-19 | 2022-12-19 |  | 10-2022 | 2022-08-11 | 2022-08-19 | 2022-08-31 | 2022-10-10 | 2022-10-14 | Marvelous Quejada Construction | with approved project modification; change of number of classrooms from 14 to 12 | [12 empty] | 1 |  | 45017 | 3.23 | 1 | 14 | 8318700.46 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105337 | Parcutela ES | CITY OF GAPAN | 4 | 1 | 3 | Repair of Classrooms | 1475367.24 | 2 | 2779344.7 | COMPLETED | 1 | 2021-10-03 | 2021-09-13 | 2021-05-31-001-CL-Repair | 2021-05-31-001-CL-Repair | 2021-06-01 | 2021-06-08 | 2021-06-21 | 2021-06-28 | 2021-07-05 | Joynieltin Construction and Trading | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105328 | Puting Tubig ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 2696212.29 | 2 | 1474689.14 | COMPLETED | 1 | 2023-01-08 | 2022-11-24 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 229001 | Sapang Kawayan ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 3085558.94 | 2 | 2691143.44 | COMPLETED | 1 | 2023-01-08 | 2022-12-01 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Gapan City | 105331 | Velcar ES | CITY OF GAPAN | 4 | 1 | 5 | Repair of Classrooms | 2742861.53 | 2 | 3082063.66 | COMPLETED | 1 | 2023-01-08 | 2022-12-01 | 2022-07-25-BEFF | 2022-07-25-BEFF | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | Joynieltin Construction and Trading | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Mabalacat City | 106089 | Villa Teodora ES | MABALACAT CITY | 1 | 1 | 5 | Repair of Classrooms | 2111541.18 | 2 | 2101009.15 | COMPLETED | 1 | 2023-01-08 | 2022-12-07 |  |  | 2022-07-20 | 2022-08-02 | 2022-08-15 | 2022-08-22 | 2022-10-10 | RAS2 Construction | [13 empty] | 1 |  | 45017 | 8.23 | 1 | 18 | 2111541.18 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 105537 | Licaong ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 9 | Repair of Classrooms | 1583079.96 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 500397 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 1998270.3 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 300824 | Munoz National HS-Main | SCIENCE CITY OF MUÑOZ | 2 | 1 | 8 | Repair of Classrooms | 4085861.56 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 9.23 | 2 | 8 | 4085861.56 | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Munoz Science City | 105565 | Villa Santos Elementary School | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | Repair of Classrooms | 2054270.2 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA | 1 | 1 | 28 | Repair of Classrooms & Toilet | 14000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105571 | Monic ES | NAMPICUAN | 1 | 1 | 4 | Repair of Classrooms & Toilets | 2120339.25 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105509 | San Vicente ES | LLANERA | 2 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105521 | Lupao Central School | LUPAO | 2 | 1 | 10 | Repair of Classrooms & Toilet | 5000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105599 | Kalayaan ES | PANTABANGAN | 2 | 1 | 4 | Repair of Classrooms & Toilet | 2000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105207 | E. Gotangco ES (Larcon ES) | BONGABON | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105308 | Gabaldon South ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 7 | Repair of Classrooms & Toilet | 3500000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105357 | Panacsac ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 5 | Repair of Classrooms & Toilet | 2500000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105470 | San Felipe ES | LAUR | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105753 | Malacanang Centro ES | SANTA ROSA | 3 | 1 | 6 | Repair of Classrooms & Toilet | 3000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105223 | San Carlos ES | CABIAO | 4 | 1 | 4 | Repair of Classrooms & Toilet | 2000000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105374 | Sibug ES | GENERAL TINIO (PAPAYA) | 4 | 1 | 3 | Repair of Classrooms & Toilet | 1500000 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105448 | Pinanggaan ES | JAEN | 4 | 1 | 3 | Repair of Classrooms & Toilet | 1500000 | 2 | 5494658.89 | COMPLETED | 1 | 2023-02-28 | 2023-02-28 | 2022-10-275 Lot 3 | 2022-10-275 Lot 3 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | Kevin Paul Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105612 | Kapt. Pedro Villanueva Elementary School | PEÑARANDA | 4 | 1 | 11 | Repair of Classrooms & Toilet | 5500000 | 2 | 1644967.35 | COMPLETED | 1 | 2023-02-28 | 2023-01-12 | 2022-10-275 Lot 1 | 2022-10-275 Lot 1 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | Mitzie Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105686 | Pulo Elementary School | SAN ISIDRO | 4 | 1 | 7 | Repair of Classrooms & Toilet | 3500000 | 2 | 2739018.17 | COMPLETED | 1 | 2023-02-28 | 2023-02-03 | 2022-10-275 Lot 2 | 2022-10-275 Lot 2 | 2022-10-05 | 2022-10-13 | 2022-10-25 | 2022-11-25 | 2022-11-29 | J.I. Viacrusis Construction | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Nueva Ecija | 105738 | Mambangnan ES | SAN LEONARDO | 4 | 1 | 10 | Repair of Classrooms & Toilet | 5000000 | 2 | 1532289.94 | COMPLETED | 1 | 2022-12-22 | 2022-11-11 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | M.P. LINGAT CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 107138 | Ilalim ES | OLONGAPO CITY | 1 | 1 | 10 | Repair of Classrooms | 5500000 | 2 | 2267286.46 | COMPLETED | 1 | 2023-01-06 | 2022-11-21 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | P.V.B. CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 107128 | Mabayuan Elementary School | OLONGAPO CITY | 1 | 1 | 3 | Repair of Classrooms | 1650000 | 2 | 2371346.34 | COMPLETED | 1 | 2023-01-06 | 2022-11-17 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Olongapo City | 500756 | Old Cabalan Integrated School | OLONGAPO CITY | 1 | 1 | 5 | Repair of Classrooms | 2750000 | 2 | 1459363.16 | COMPLETED | 1 | 2022-12-22 | 2022-11-04 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | RAS2 CONSTRUCTION | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106125 | Navaling ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1540552.88 | 2 | 2477090.29 | COMPLETED | 1 | 2023-01-06 | 2022-11-11 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | E.B. MATIAS CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106127 | San Agustin ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2277786.41 | 2 | 1174757.49 | COMPLETED | 1 | 2022-12-22 | 2022-11-11 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | J.V. BUAN CONSTRUCTION *T | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106128 | San Francisco ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2384119.08 | 2 | 2474932.77 | COMPLETED | 1 | 2023-01-06 | 2022-11-28 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | EIRISH BUILDERS & SUPPLY INC. | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106131 | San Miguel ES | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1472467.1 | 2 | 2008727.8 | COMPLETED | 1 | 2023-01-06 | 2022-11-10 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | ELDICO BUILDERS | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106136 | Sta. Cruz ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2485869.52 | 2 | 3511866.37 | COMPLETED | 1 | 2023-01-06 | 2022-11-22 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | BFF CONSTRUCTION | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106141 | Talimundoc Elementary School | MAGALANG | 1 | 1 | 2 | Repair of Classrooms | 1223726.72 | 2 | 3172196.24 | COMPLETED | 1 | 2023-01-06 | 2022-11-24 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | CHARIOTS CONSTRUCTION INC. | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106142 | Turu ES | MAGALANG | 1 | 1 | 3 | Repair of Classrooms | 2487954.94 | 2 | 2949000 | COMPLETED | 1 | 2023-01-06 | 2022-01-06 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | V. TRILLANA BUILDERS & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105981 | Calantas ES | FLORIDABLANCA | 2 | 1 | 3 | Repair of Classrooms | 2025398.15 | 2 | 3106866.26 | COMPLETED | 1 | 2023-01-06 | 2022-01-06 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | R.G. ROQUE CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105982 | Camachile es | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 3659843.37 | 2 | 3158377.72 | COMPLETED | 1 | 2023-01-06 | 2022-11-08 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | I.B. MUSNGI CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 501827 | Nabuclod Integrated School | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 3182047.28 | 2 | 2932731.42 | COMPLETED | 1 | 2023-01-06 | 2022-11-02 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | TRACCOR BUILDERS | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 305365 | Pasay City North High School | FLORIDABLANCA | 2 | 1 | 5 | Repair of Classrooms | 2969082.06 | 2 | 2386859.4 | COMPLETED | 1 | 2023-01-06 | 2022-11-21 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | S.M. SEVERINO CONSTRUCTION & TRADING | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105971 | San Isidro ES | FLORIDABLANCA | 2 | 1 | 4 | Repair of Classrooms | 3116158 | 2 | 1452348.41 | COMPLETED | 1 | 2022-12-22 | 2022-11-04 |  |  | 2022-06-27 | 2022-07-05 | 2022-07-18 | 2022-09-14 | Friday, September 23, 2022 | TRACCOR BUILDERS | [13 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106219 | Katutubo Village ES | PORAC | 2 | 1 | 4 | Repair of Classrooms | 3182047.28 | 2 |  | COMPLETED | 1 | [10 empty] | For procurement, suspension of procurement lifted on August | [12 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 306935 | Bacolor HS | BACOLOR | 3 | 1 | 6 | Repair of Classrooms | 3055397.99 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 105954 | Candaba ES | CANDABA | 4 | 1 | 3 | Repair of Classrooms | 2397165.31 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Pampanga | 106209 | Sta. Maria Elementary School | MINALIN | 4 | 1 | 2 | Repair of Classrooms | 1512902.81 | 2 |  | COMPLETED | 1 | [23 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 1 | 2021-10-04 | 2021-08-16 |  |  | 2021-06-07 | 2021-06-15 | 2021-06-28 | 2021-06-29 | 2021-07-01 | BM CABANES TRADING & CONSTRUCTION | completed | [12 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 500140 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 1 | [10 empty] | completed | [12 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 501137 | San Jose Panlumacan Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 1 | [10 empty] | completed | [12 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | San Fernando City | 500142 | San Nicolas IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Repair of Classrooms | 2070380.91 | 2 |  | COMPLETED | 1 | [10 empty] | completed | [12 empty] | 1 |  | 45017 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106307 | Casili ES | ANAO | 1 | 1 | 3 | Repair of Classrooms | 1225710.58 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106607 | Coral ES | RAMOS | 1 | 1 | 6 | Repair of Classrooms | 3961082.42 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2022 | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 1 | 1 | 3 | Repair of Classrooms | 2095026.05 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 44986 | 3.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Angeles City | 345279 | Angeles City Senior High School | ANGELES CITY | 1st | 1 | 24 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 9368895.1 | COMPLETED | 1 | 2024-07-04 | 2024-01-08 | P00775681NP | 23CI0169 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1st | 1 | 12 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 4684787.65 | COMPLETED | 1 | 2024-07-04 | 2024-01-08 | P00775678NP | 23CI0171 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 301042 | Bonifacio V. Romero HS | ANGELES CITY | 1st | 1 | 28 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 11247421.8 | COMPLETED | 1 | 2024-07-04 | 2024-01-08 | P00775679NP | 23CI0168 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Angeles City | 301043 | Sapang Bato National High School | ANGELES CITY | 1st | 1 | 12 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 4694244.19 | COMPLETED | 1 | 2024-05-04 | 2024-01-08 | P00775680NP | 23CI0170 | 2023-10-25 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-01-08 | GMO Construction | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | Completed
REPAIR 2023 | Region III | Aurora | 104408 | Anacleto V. Mijares ES | BALER (Capital) | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4156888.88 | COMPLETED | 1 | 2025-02-04 | 2024-12-12 |  |  | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-10 | 2024-10-07 | Traccor Builders | [13 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | Completed
REPAIR 2023 | Region III | Aurora | 104412 | Diego T. Ortiz ES | BALER (Capital) | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4881046.51 | COMPLETED | 1 | 2023-11-02 |  | 23cno192 | 23cno192 |  |  | 2023-08-15 |  | 2023-10-02 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104426 | Dumaguipo ES | CASIGURAN | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3 ,036,412.71 | COMPLETED | 1 | 2023-11-03 |  | 23Cno197 | 23Cno197 |  |  | 2023-08-30 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3 ,687,909.07 | COMPLETED | 1 | 2023-11-03 |  | 23Cno194 | 23Cno194 |  |  | 2023-08-30 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 500738 | Tinib-Calangcuasan IS | CASIGURAN | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3050049.55 | COMPLETED | 1 | 2023-11-14 |  | 23Cno186 | 23Cno186 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 306504 | Diagyan NHS | DILASAG | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5 ,467,954.45 | COMPLETED | 1 | 2023-11-11 |  | 23Cno179 | 23Cno179 |  |  | 2023-07-19 |  | 2023-09-05 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104445 | Dinalungan CS | DINALUNGAN | Lone | 1 | 12 | Repair of Classrooms | 7800000 | DPWH (Batch 1) | 7404483.76 | COMPLETED | 1 | 2024-01-10 |  | 23Cno198 | 23Cno198 |  |  | 2023-07-27 |  | 2023-09-12 | Conrado B. Bautista Construction and Supply Corporation | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 500751 | Cabog IS | DINGALAN | Lone | 1 | 4 | Repair of Classrooms | 2600000 | DPWH (Batch 1) | 2444152.74 | COMPLETED | 1 | 2023-12-01 |  | 23Cno185 | 23Cno185 |  |  | 2023-08-10 |  | 2023-09-25 | Vanmarvil Construction | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2023 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104455 | Dingalan CS | DINGALAN | Lone | 1 | 10 | Repair of Classrooms | 6500000 | DPWH (Batch 1) | 6 ,100,903.47 | COMPLETED | 1 | 2023-11-18 |  | 23Cno195 | 23Cno195 |  |  | 2023-07-27 |  | 2023-09-12 | Vanmarvil Construction | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 157503 | Tanawan ES | DINGALAN | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4306701.22 | COMPLETED | 1 | 2023-11-17 |  | 23Cno178 | 23Cno178 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104470 | Dipaculao CS | DIPACULAO | Lone | 1 | 12 | Repair of Classrooms | 7800000 | DPWH (Batch 1) | 7395881.08 | COMPLETED | 1 | 2024-01-07 |  | 23Cno184 | 23Cno184 |  |  | 2023-08-10 |  | 2023-10-02 | Capital Construction | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 300674 | Bayanihan NHS | MARIA AURORA | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5497707 | COMPLETED | 1 | 2023-12-01 |  | 23Cno183 | 23Cno183 |  |  | 2023-08-10 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104489 | Calao ES | MARIA AURORA | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3079890.03 | COMPLETED | 1 | 2023-11-23 |  | 23Cno196 | 23Cno196 |  |  | 2023-08-15 |  | 2023-10-02 | Uliran Construction Services | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104498 | Diome ES | MARIA AURORA | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3688972.37 | COMPLETED | 1 | 2023-11-17 |  | 23Cno183 | 23Cno183 |  |  | 2023-08-10 |  | 2023-09-25 | So Construction | COMPLETED | [12 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104505 | Punglo ES | MARIA AURORA | Lone | 1 | 6 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3666704.41 | COMPLETED | 1 | 2023-11-17 |  | 23Cno181 | 23Cno181 |  |  | 2023-08-10 |  | 2023-09-25 | RNGM Construction | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 306503 | Ramada NHS | MARIA AURORA | Lone | 1 | 7 | Repair of Classrooms | 4550000 | DPWH (Batch 1) | 4308415.87 | COMPLETED | 1 | 2023-11-17 |  | 23Cn189 | 23Cn189 |  |  | 2023-08-15 |  | 2023-09-25 | Conrado B. Bautista Construction and Supply Corporation | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104509 | San Leonardo ES | MARIA AURORA | Lone | 1 | 2 | Repair of Classrooms | 1300000 | DPWH (Batch 1) | 1 ,216,578.15 | COMPLETED | 1 | 2023-10-17 |  | 23Cno180 | 23Cno180 |  |  | 2023-07-10 |  | 2023-09-12 | Vanmarvil Construction | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 157505 | Sto. Tomas ES | MARIA AURORA | Lone | 1 | 5 | Repair of Classrooms | 3250000 | DPWH (Batch 1) | 3041261.01 | COMPLETED | 1 | 2023-11-24 |  | 23Cno190 | 23Cno190 |  |  | 2023-09-07 |  | 2023-10-02 | RNGM Construction | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 300681 | Dikapinisan NHS | SAN LUIS | Lone | 1 | 8 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4 ,920,254.30 | COMPLETED | 1 | 2023-11-18 |  | 23Cno194 | 23Cno194 |  |  | 2023-07-17 |  | 2023-09-12 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Aurora | 104520 | Ditumabo ES | SAN LUIS | Lone | 1 | 9 | Repair of Classrooms | 5850000 | DPWH (Batch 1) | 5530921.57 | COMPLETED | 1 | 2023-11-01 |  | 23Cno188 | 23Cno188 |  |  | 2023-08-15 |  | 2023-09-25 | Radiance Traders & Builders | COMPLETED | [12 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Aurora | 104527 | San Isidro ES | SAN LUIS | Lone | 1 | 13 | Repair of Classrooms | 7700000 | DPWH (Batch 1) | 7321889.74 | COMPLETED | 1 | 2023-12-01 |  | 23Cno191 | 23Cno191 |  |  | 2023-08-15 |  | 2023-09-25 | Vanmarvil Construction | COMPLETED | [12 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 137096 | St. Ma. Virginia P. Leonzon Memorial Elementary School | HERMOSA | 1st | 1 | 9 | Repair of Classrooms | 13500000 | DPWH (Batch 2) | 12994929.93 | COMPLETED | 1 |  |  | 23CA0078 |  | 11/01/2023 - 11/22/2023 | 2023-10-11 | 22/11/2023 | 12/06/2023 - 01/02/2024 | 14/02/2024 | San Sebastion Construction | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104703 | Gugo ES | SAMAL | 1st | 1 | 8 | Repair of Classrooms | 12000000 | DPWH (Batch 2) | 11320026.34 | COMPLETED | 1 |  |  | 23CA0079 |  | 11/01/2023 - 11/22/2023 | 2023-10-11 | 22/11/2023 | 12/06/2023 - 12/28/2023 | 15/01/2024 | Ave-Mira Constrruction and Trading | [13 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104689 | Bagumbayan ES | PILAR | 2nd | 1 | 12 | Repair of Classrooms | 18000000 | DPWH (Batch 2) | 16961844.05 | COMPLETED | 1 | [23 empty] | 1 |  |  | 9.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104589 | Pinulot ES | DINALUPIHAN | 3rd | 1 | 7 | Repair of Classrooms | 10500000 | DPWH (Batch 2) | 9964092.99 | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bataan | 104642 | Cabcaben ES | MARIVELES | 3rd | 1 | 10 | Repair of Classrooms | 15000000 | DPWH (Batch 2) | 14146340.47 | Ongoing | 0.6 | [23 empty] | 0.6 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Bulacan | 104816 | Pungo ES | CALUMPIT | 1st | 1 | 8 | Repair of Classrooms | 9750000 | DPWH (Batch 2) | 9220540.14 | COMPLETED | 1 | 2024-05-30 | 2024-05-30 | P00775687NP | 23CC0464 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104853 | San Jose ES | HAGONOY | 1st | 1 | 5 | Repair of Classrooms | 6500000 | DPWH (Batch 2) | 5687701.81 | COMPLETED | 1 | 2024-04-30 | 2024-04-30 | P00775688NP | 23CC0469 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 300737 | Sta. Peregrina HS | PULILAN | 1st | 1 | 9 | Repair of Classrooms | 10400000 | DPWH (Batch 2) | 9835197.15 | COMPLETED | 1 | 2024-05-30 | 2024-05-30 | P00775689NP | 23CC0463 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | PTM Development Corp. | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104750 | Baliwag South Central School | BALIUAG | 2nd | 1 | 25 | Repair of Classrooms | 16250000 | DPWH (Batch 2) | 15289007.79 | COMPLETED | 1 | 2024-06-29 | 2024-06-29 | P00775691NP | 23CC0468 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104746 | Sabang ES | BALIUAG | 2nd | 1 | 8 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9456764.45 | COMPLETED | 1 | 2024-06-29 | 2024-06-29 | P00775690NP | 23CC0466 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Samarah Construction and Supply | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104795 | Tibagan Elementary School | BUSTOS | 2nd | 1 | 23 | Repair of Classrooms | 14950000 | DPWH (Batch 2) | 14065403.32 | COMPLETED | 1 | 2024-04-30 | 2024-04-30 | P00775692NP | 23CC0470 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | Streamline Builders Corporation | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105002 | Culianin ES | PLARIDEL | 2nd | 1 | 8 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9456619.92 | COMPLETED | 1 | 2024-04-30 | 2024-04-30 | P00775693NP | 23CC0462 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | SYMS Construction Trading | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105008 | Parulan ES | PLARIDEL | 2nd | 1 | 11 | Repair of Classrooms | 7150000 | DPWH (Batch 2) | 6761280.76 | COMPLETED | 1 | 2024-05-30 | 2024-05-30 | P00775694NP | 23CC0467 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Streamline Builders Corporation | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 158507 | Duplas ES | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 3 | Repair of Classrooms | 4000000 | DPWH (Batch 2) | 3801001.89 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00362 | 23C00362 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 306720 | Esteban Paulino HS | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 5 | Repair of Classrooms | 5500000 | DPWH (Batch 2) | 5227977.4 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00364 | 23C00364 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 158509 | Kambubuyugan Elementary School | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4750779.28 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00363 | 23C00363 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105029 | Bubulong Malaki ES | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3326935.94 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00365 | 23C00365 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105030 | Bubulong Munti Elementary School | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3325785.98 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00366 | 23C00366 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105052 | Casalat Elementary School | SAN ILDEFONSO | 3rd | 1 | 3 | Repair of Classrooms | 3500000 | DPWH (Batch 2) | 3327086.5 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00367 | 23C00367 |  |  |  |  | 2024-07-16 | RVR3 Construction Supply and Services | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105097 | Biclat ES | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4277266.73 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00369 | 23C00369 |  |  |  |  | 2024-07-16 | ADSL Construction & Trading | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105099 | Dr. Juan F. Pascual MS | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4751755.5 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00370 | 23C00370 |  |  |  |  | 2024-07-16 | GMO Construction | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 105105 | Pacalag ES | SAN MIGUEL | 3rd | 1 | 4 | Repair of Classrooms | 4500000 | DPWH (Batch 2) | 4276616.06 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00371 | 23C00371 |  |  |  |  | 2024-07-23 | ADSL Construction & Trading | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105073 | SAN MIGUEL NORTH CENTRAL SCHOOL | SAN MIGUEL | 3rd | 1 | 5 | Repair of Classrooms | 6000000 | DPWH (Batch 2) | 5703417.9 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00368 | 23C00368 |  |  |  |  | 2024-07-16 | Pluma Builders Co. | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105115 | Caingin ES | SAN RAFAEL | 3rd | 1 | 4 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4751781.33 | COMPLETED | 1 | 2024-11-18 | 2024-11-18 | 23C00372 | 23C00372 |  |  |  |  | 2024-07-16 | Eirish Builders & Supply Inc. | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 5th | 1 | 30 | Repair of Classrooms | 19500000 | DPWH (Batch 2) | 18346658.83 | COMPLETED | 1 | 2024-05-30 | 2024-05-30 | P00775706NP | 23CC0465 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | SYMS Construction Trading | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104829 | Sta. Rita ES | GUIGUINTO | 5th | 1 | 24 | Repair of Classrooms | 15600000 | DPWH (Batch 2) | 14677399.7 | COMPLETED | 1 | 2024-06-09 | 2024-06-09 | P00775707NP | 23CC0471 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 104832 | Tiaong Elementary School | GUIGUINTO | 5th | 1 | 17 | Repair of Classrooms | 11050000 | DPWH (Batch 2) | 10337752.72 | COMPLETED | 1 | 2024-05-28 | 2024-05-28 | P00775708NP | 23CC0461 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-12-21 | 2024-01-02 | Ma. Liza C. Austria Construction & Supply Corporation | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 300728 | Bunsuran NHS | PANDI | 5th | 1 | 24 | Repair of Classrooms | 15600000 | DPWH (Batch 2) | 14677543.18 | COMPLETED | 1 | 2024-08-28 | 2024-08-28 | P00775709NP | 23CC0472 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-12-21 | 2024-01-02 | TBB Construction Corporation | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2023 | Region III | Bulacan | 104727 | A. S. De Guzman ES (Taboc ES) | ANGAT | 6th | 1 | 4 | Repair of Classrooms | 4532002.88 | DPWH (Batch 2) | 4486682.85 | COMPLETED | 1 | 2024-04-08 | 2024-04-07 | P00775713NP | 23CD0198 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | SYMS Construction Trading | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 6th | 1 | 2 | Repair of Classrooms | 2859435.52 | DPWH (Batch 2) | 2830552.33 | COMPLETED | 1 | 2024-04-08 | 2024-04-07 | P00775710NP | 23CD0195 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | R.B. CAIN CONSTRUCTION | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104711 | Pablo C. Capistrano ES | ANGAT | 6th | 1 | 1 | Repair of Classroom | 1459126.79 | DPWH (Batch 2) | 1444388.14 | COMPLETED | 1 | 2024-04-08 | 2024-04-07 | P00775711NP | 23CD0196 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104717 | TEODOSO R. MANUEL ELEMENTARY SCHOOL | ANGAT | 6th | 1 | 2 | Repair of Classrooms | 1956312.85 | DPWH (Batch 2) | 1935816.16 | COMPLETED | 1 | 2024-03-09 | 2024-03-08 | P00775712NP | 23CD0197 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104951 | NORTH HILLS VILLAGE ELEMENTARY SACHOOL | NORZAGARAY | 6th | 1 | 6 | Repair of Classrooms | 7752824.32 | DPWH (Batch 2) | 7674512.96 | COMPLETED | 1 | 2024-04-08 | 2024-04-07 | P00775714NP | 23CD0199 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 6th | 1 | 2 | Repair of Classrooms | 2588448 | DPWH (Batch 2) | 2562302.06 | COMPLETED | 1 | 2024-04-08 | 2024-04-07 | P00775715NP | 23CD0200 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | RICHBIAN CONSTRUCTION AND SUPPLY | [13 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105151 | Guyong ES | SANTA MARIA | 6th | 1 | 10 | Repair of Classrooms | 11949271 | DPWH (Batch 2) | 11828571.29 | COMPLETED | 1 | 2024-05-08 | 2024-02-14 | P00775716NP | 23CD0202 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | 1199S CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Bulacan | 105167 | Sta. Cruz ES | SANTA MARIA | 6th | 1 | 3 | Repair of Classrooms | 3136258 | DPWH (Batch 2) | 3104578.63 | COMPLETED | 1 | 2024-04-08 | 2024-02-14 | P00775717NP | 23CD0201 | 2023-11-03 | 2023-11-10 | 2023-11-23 | 2023-12-28 | 2024-01-04 | 1199S CONSTRUCTION | [13 empty] | 1 |  |  | 3.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105282 | Nagmisahan ES | CUYAPO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-15-2024 | INFRA-NE-SVP-01-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105294 | Sta. Clara ES | CUYAPO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-16-2024 | INFRA-NE-SVP-02-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105386 | Faigal ES | GUIMBA | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-17-2024 | INFRA-NE-SVP-03-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105625 | Ricardo L. Joson Elementary School | QUEZON | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-18-2024 | INFRA-NE-SVP-04-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105783 | San Francisco ES | SANTO DOMINGO | 1st | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959279.28 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-19-2024 | INFRA-NE-SVP-05-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | IJK MAE CONSTRUCTION INC. | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105311 | Pantoc ES | GABALDON (BITULOK & SABANI) | 3rd | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959016.21 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-20-2024 | INFRA-NE-SVP-06-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | MITZIE CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105218 | Entablado ES | CABIAO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.02 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-21-2024 | INFRA-NE-SVP-07-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105440 | Langla ES | JAEN | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-22-2024 | INFRA-NE-SVP-08-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.03 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-23-2024 | INFRA-NE-SVP-09-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105667 | Maugat ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-24-2024 | INFRA-NE-SVP-10-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105668 | Panabingan ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-25-2024 | INFRA-NE-SVP-11-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105671 | San Francisco ES | SAN ANTONIO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959283.98 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-26-2024 | INFRA-NE-SVP-12-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Nueva Ecija | 105736 | C. I. Villaroman ES | SAN LEONARDO | 4th | 1 | 2 | Repair of Classrooms | 995911.83 | DEPED (Batch 2) | 959483.03 | COMPLETED | 1 | 2024-03-29 | 2024-03-07 | DEPED-NE-INFRA-27-2024 | INFRA-NE-SVP-13-2024 | 2024-01-18 |  | 2024-01-23 |  | 2024-01-29 | JV BUAN CONSTRUCTION*T | [13 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Pampanga | 106152 | Masantol ES | MASANTOL | 4th | 1 | 6 | Repair of Classrooms | 10000000 | DPWH (Batch 2) | 9650000 | COMPLETED | 1 | 2024-10-01 | 2024-10-01 | P00775718NP | 24CG0170 | 2024-04-11 | 2024-04-19 | 2024-05-02 | 2024-05-13 | 2024-05-22 | Three in One Construction and Trading | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4th | 1 | 2 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4824727.68 | COMPLETED | 1 | 2024-07-14 | 2024-07-14 | P00775719NP | 24CG0112 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-18 | V. Trillana builders & Trading | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 106255 | Dela Paz ES | SAN SIMON | 4th | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4823684.13 | COMPLETED | 1 | 2024-04-12 | 2024-04-12 | P00775720NP | 24CG0113 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-18 | V. Trillana builders & Trading | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Pampanga | 306917 | Sta. Monica High School | SAN SIMON | 4th | 1 | 3 | Repair of Classrooms | 5000000 | DPWH (Batch 2) | 4825000 | COMPLETED | 1 | 2024-08-01 | 2024-08-01 | P00775721NP | 24CG0114 | 2024-02-29 | 2024-03-08 | 2024-03-21 | 2024-03-27 | 2024-04-19 | Cholo Construction and Trading | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | completed
REPAIR 2023 | Region III | Tarlac | 300946 | Anao NHS | ANAO | 1st | 1 | 3 | Repair of Classrooms | 4517000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106306 | Bantog ES | ANAO | 1st | 1 | 6 | Repair of Classrooms | 3215200 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106307 | Casili ES | ANAO | 1st | 1 | 2 | Repair of Classrooms | 1576790.34 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106305 | Dolores Ongsiako CES | ANAO | 1st | 1 | 13 | Repair of Classrooms | 6971421.61 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 300972 | Marawi National High School | CAMILING | 1st | 1 | 7 | Repair of Classrooms | 5574483.96 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106333 | Pindangan First ES | CAMILING | 1st | 1 | 5 | Repair of Classrooms | 4184183.53 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106353 | Sta. Maria ES | CAMILING | 1st | 1 | 2 | Repair of Classrooms | 1597474.29 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106336 | Tambugan ES | CAMILING | 1st | 1 | 5 | Repair of Classrooms | 5017455.14 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106508 | Bigbiga ES | MAYANTOC | 1st | 1 | 5 | Repair of Classrooms | 3439313.71 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106551 | San Julian ES | MONCADA | 1st | 1 | 4 | Repair of Classrooms | 3760996.48 | DPWH (Batch 2) |  | Ongoing | 0 | [23 empty] | 0 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106535 | San Pedro ES | MONCADA | 1st | 1 | 1 | Repair of Classroom | 1102695.08 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 11.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106594 | Don Quirino Sulit ES | PURA | 1st | 1 | 1 | Repair of Classroom | 1112406.23 | DPWH (Batch 2) |  | Ongoing | 0 | [23 empty] | 0 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 300974 | Maungib NHS | PURA | 1st | 1 | 2 | Repair of Classrooms | 2037749.45 | DPWH (Batch 2) |  | Ongoing | 0 | [23 empty] | 0 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106608 | Guiteb ES | RAMOS | 1st | 1 | 7 | Repair of Classrooms | 5330000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106609 | Pance ES | RAMOS | 1st | 1 | 5 | Repair of Classrooms | 4330000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106610 | Ramos CS | RAMOS | 1st | 1 | 6 | Repair of Classrooms | 5212934.88 | DPWH (Batch 2) |  | Ongoing | 0.15 | [23 empty] | 0.15 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | 4 | Repair of Classrooms | 3269457.19 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 4.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 502346 | Toledo Integrated School | RAMOS | 1st | 1 | 4 | Repair of Classrooms | 2748022.93 | DPWH (Batch 2) |  | Ongoing | 0 | [23 empty] | 0 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106623 | Casipo PS | SAN CLEMENTE | 1st | 1 | 2 | Repair of Classrooms | 1245051.31 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106624 | Pit-Ao ES | SAN CLEMENTE | 1st | 1 | 3 | Repair of Classrooms | 2408000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 1st | 1 | 5 | Repair of Classrooms | 4070000 | DPWH (Batch 1) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 1.24 |  |  |  | CY 2024 | COMPLETED
REPAIR 2023 | Region III | Tarlac | 106680 | Sta. Ignacia North CS | SANTA IGNACIA | 1st | 1 | 7 | Repair of Classrooms | 5614749.95 | DPWH (Batch 2) |  | Ongoing | 0 | [23 empty] | 0 | [7 empty] | Ongoing
REPAIR 2023 | Region III | Tarlac | 106681 | Sta. Ignacia South CES | SANTA IGNACIA | 1st | 1 | 5 | Repair of Classrooms | 4059091.65 | DPWH (Batch 2) |  | Ongoing | 0.6 | [23 empty] | 0.6 | [7 empty] | Ongoing
REPAIR 2024 | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1st | 1 | 6 | Repair of Classrooms | 4209848.77 | 1 | 4156888.88 | COMPLETED | 1 | 2025-02-04 | 2024-12-12 |  |  | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-10 | 2024-10-07 | Traccor Builders | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Aurora | 104474 | Laboy ES | DIPACULAO | Lone | 1 | 2 | Repair of Classrooms | 1161616.16 | 1 | 733705.21 | COMPLETED | 1 | 2024-11-14 | 2024-11-14 |  |  | 2024-07-10 | July 20, 2024 | August 1, 2024 | Sept 16, 2024 | 2024-09-24 | MACCO CONSTRUCTION | COMPLETED | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Aurora | 104529 | Zarah ES | SAN LUIS | Lone | 1 | 5 | Repair of Classrooms | 3282828.28 | 1 | 2125914.56 | COMPLETED | 1 | 2024-12-05 | 2024-12-05 |  |  | 2025-07-10 | July 20, 2025 | August 1, 2024 | Sept 16, 2024 | 2024-10-04 | DB BARAQUIEL CONSTRUCTION | COMPLETED | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Balanga City | 104563 | M. P. Cuaderno Sr. Memorial Elementary School | CITY OF BALANGA (Capital) | 2nd | 1 | 5 | Repair of Classrooms | 2567473.92 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Balanga City | 502343 | Tanato Integrated School | CITY OF BALANGA (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 1282109.62 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 3.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bataan | 104615 | Pandatung ES | HERMOSA | 1st | 1 | 3 | Repair of Classrooms | 1713732.22 | 1 | 1322789.87 | COMPLETED | 1 | 2024-11-26 | 2024-11-26 | Repair 2024-Region III-Bataan-014 | 2024 - 07 - 01 | July 9, 2024 to July 28, 2024 | 2024-07-16 | 2024-07-29 | 2024-08-01 | 2024-09-23 | Five A Construction | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bataan | 104601 | Sto. Nino ES | DINALUPIHAN | 3rd | 1 | 3 | Repair of Classrooms | 2084641.52 | 1 | 1570758.1 | COMPLETED | 1 | 2024-11-26 | 2024-11-26 | Repair 2024-Region III-Bataan-010 | 2024 - 07 - 02 | July 9, 2024 to July 28, 2024 | 2024-07-16 | 2024-07-29 | 2024-08-01 | 2024-09-23 | Rodmac Construction & Trading | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 5th | 1 | 10 | Repair of Classrooms | 4444444.44 | 1 | 4400000 | COMPLETED | 1 | 2025-02-18 | 2024-12-20 | PB-24-010 | PB-24-10-015 | 2024-06-26 | 2024-07-06 | 2024-07-22 | 2024-08-06 | 2024-10-14 | T.G. Ocampo Construction and Surveying Services | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Cabanatuan City | 107117 | Sumacab Este ES | CABANATUAN CITY | 3rd | 1 | 5 | Repair of Classrooms | 4443665.28 | 1 | 4339973.18 | COMPLETED | 1 | 2025-01-23 | 2024-12-16 |  | 08-2024 | 2024-08-01 | 2024-08-14 | 2024-08-27 | 2024-09-16 | 2024-09-17 | Marvelous Quejada Construction Inc. | completed | [12 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 107161 | San Jose Del Monte Central School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1484848.48 | 1 | PhP1,460,218.65 | COMPLETED | 1 | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | .I. VIACRUSIS CONSTRUCTION | Complete | [12 empty] | 1 |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 162504 | San Manuel Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1479797.98 | 1 | PhP1,459,880.51 | COMPLETED | 1 | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | JM ALTITUDE CONSTRUCTION COR | Complete | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | City of San Jose Del Monte | 107162 | San Martin (BBC) Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 2 | Repair of Classrooms | 1479797.98 | 1 | PhP1,459,869.73 | COMPLETED | 1 | Nov. 30,2024 | completed | BEEF - 001 | PB-EF-CW-2024-08-01 | Aug 8,2024 | Aug 18,2024 | Aug. 28,2024 | Sept. 6, 2024 | Sept. 23, 2024 | RKEA BUILDERS & SUPPLY | Complete | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Gapan City | 105335 | Malimba ES | CITY OF GAPAN | 4th | 1 | 10 | Repair of Classrooms | 4436402.36 | 1 | 4,386,357.66 | COMPLETED | 1 | 2025-01-25 | 2024-12-27 | IB2024-002 | IB2024-002 | 2024-06-26 | 2024-07-09 | 2024-07-23 | 2024-07-26 | 2024-09-27 | Joynieltin Construction and Trading | completed | [12 empty] | 1 |  |  | 1.25 |  |  |  |  | Completed
REPAIR 2024 | Region III | Mabalacat City | 306916 | Mabalacat Community High School | MABALACAT CITY | 1st | 1 | 16 | Repair of Classrooms | 4497983.05 | 1 | 3335299.41 | COMPLETED | 1 | 2025-02-16 | 2025-01-30 |  |  |  |  | 2024-10-21 | 2024-11-07 | 2024-11-18 | E.M MALLARI CONSTRUCTION | [13 empty] | 1 |  |  | 1.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Malolos City | 323603 | Malolos City High School - Bungahan | CITY OF MALOLOS (Capital) | 1st | 1 | 6 | Repair of Classrooms | 2319988.19 | 1 | 2285519.82 | COMPLETED | 1 | 2025-01-06 | 2024-11-21 | Infra-2024-02 Lot 2 | Infra-2024-02 Lot 2 | 7/02-7/09/2024 | 2024-07-10 | 2024-07-23 | 2024-07-24 | Oct. 1, 2024 | Samenara Construction & Trading | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Malolos City | 104879 | Stma. Trinidad ES | CITY OF MALOLOS (Capital) | 1st | 1 | 3 | Repair of Classrooms | 2139319.71 | 1 | 2100000 | COMPLETED | 1 | 2025-01-06 | November 26,2024 | Infra-2024-02 Lot 1 | Infra-2024-02 Lot 1 | 7/02-7/09/2024 | 2024-07-10 | 2024-07-23 | 2024-07-24 | Oct. 1, 2024 | V. Trillana Builders & Trading | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | Meycauayan City | 104915 | Bagbaguin ES | CITY OF MEYCAUAYAN | 4th | 1 | 2 | Repair of Classrooms | 1915552.25 | 1 | 1891245.73 | Ongoing | 0.8 | 2025-02-26 | ongoing | 2024-001-INFRA | 2024-001-INFRA | 2024-10-29 | 2024-11-06 | 2024-11-19 | 2024-11-20 | 2024-11-26 | Che-riss Construction and Trading | on-going | [12 empty] | 0.8 | [7 empty] | Ongoing
REPAIR 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th | 1 | 1 | Repair of Classrooms | 773760.66 | 1 | 760671.89 | COMPLETED | 1 | 2025-01-15 | 2024-12-26 | 2024-001-INFRA | 2024-001-INFRA | 2024-10-29 | 2024-11-06 | 2024-11-19 | 2024-11-20 | 2024-11-26 |  | completed | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105823 | La Torre ES | TALAVERA | 1st | 1 | 2 | Repair of Classrooms | 1005971.55 | 1 | 993344.81 | COMPLETED | 1 | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-132-2024 | INFRA-NE-SVP-21-2024 | 2024-08-03 |  | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 306813 | Vega National High School | BONGABON | 3rd | 1 | 2 | Repair of Classrooms | 1005971.55 | 1 | 993344.81 | COMPLETED | 1 | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-133-2024 | INFRA-NE-SVP-22-2024 | 2024-08-03 |  | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105228 | San Vicente Elementary School | CABIAO | 4th | 1 | 2 | Repair of Classrooms | 974161.53 | 1 | 961852.88 | COMPLETED | 1 | 2024-11-04 | 2024-10-29 | DEPED-NE-INFRA-134-2024 | INFRA-NE-SVP-20-2024 | 2024-08-03 |  | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Nueva Ecija | 105448 | Pinanggaan ES | JAEN | 4th | 1 | 2 | Repair of Classrooms | 974161.53 | 1 | 961852.88 | COMPLETED | 1 | 2024-11-04 | 2024-10-30 | DEPED-NE-INFRA-135-2024 | INFRA-NE-SVP-19-2024 | 2024-08-03 |  | 2024-08-12 | 2024-08-16 | 2024-09-20 | JOYUS CONSTRUCTION | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Olongapo City | 107122 | New Cabalan ES | OLONGAPO CITY | 1st | 1 | 5 | Repair of Classrooms | 4444444.44 | 1 | 4380306.97 | COMPLETED | 1 | 2025-04-08 | 2025-02-21 | 2024-11-01 | 2024-11-01 | 2024-10-03 | 2024-10-11 | 2024-10-23 | 2024-12-03 | 2024-12-09 | Mitzie Construction | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Pampanga | 105897 | Anderson ES | ARAYAT | 3rd | 1 | 2 | Repair of Classrooms | 2704938.92 | 1 | 1708518.45 | COMPLETED | 1 | 2024-12-09 | 2024-11-28 | BEFF - 002 | BEFF - 002 | 2024-07-09 | 2024-07-19 | 2024-07-31 | 2024-09-18 | 2024-09-25 | IB MUSNGI CONSTRUCTION AND TRADING | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Pampanga | 105957 | Mandasig ES | CANDABA | 4th | 1 | 2 | Repair of Classrooms | 2073852.75 | 1 | 1526044.51 | COMPLETED | 1 | 2024-12-09 | 2024-11-21 | BEFF - 001 | BEFF - 001 | 2024-07-09 | 2024-07-19 | 2024-07-31 | 2024-09-18 | 2024-09-25 | IB MUSNGI CONSTRUCTION AND TRADING | [13 empty] | 1 |  |  | 10.24 |  |  |  |  | completed
REPAIR 2024 | Region III | San Fernando City | 500145 | Maimpis Integrated School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 2432861.9 | 1 | 2398888.88 | COMPLETED | 1 | 2025-01-05 | 2024-12-07 |  | Infrastructure 2024-002 | 2024-07-15 | 2024-07-22 | 2024-08-05 | 2024-08-30 | 2024-09-30 | Traccor Builders | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | San Fernando City | 107200 | Sto. Nino Elementary School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 4 | Repair of Classrooms | 2432861.9 | 1 | 2039923.23 | COMPLETED | 1 | 2025-01-05 | 2024-12-07 |  | Infrastructure 2024-003 | 2024-07-15 | 2024-07-22 | 2024-08-05 | 2024-08-30 | 2024-10-11 | I.B. Musngi Construction and Trading | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | Completed
REPAIR 2024 | Region III | San Jose City | 105715 | A. Pascual Elementary School | SAN JOSE CITY | 2nd | 1 | 3 | Repair of Classrooms | 2282346.24 | 1 | 2229524.29 | COMPLETED | 1 | 2025-01-08 | 2024-12-08 | REPAIR 2024 - RIII - SAN JOSE CITY - 001 |  | 2024-05-24 | 2024-06-07 | 2024-06-24 | 2024-06-27 | 2024-09-20 | DB Baraquiel Construction | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | San Jose City | 105733 | Tondod Elementary School | SAN JOSE CITY | 2nd | 1 | 3 | Repair of Classrooms | 2131889.34 | 1 | 2105413.85 | COMPLETED | 1 | 2025-01-08 | 2024-12-08 | REPAIR 2024 - RIII - SAN JOSE CITY - 002 |  | 2024-05-24 | 2024-06-07 | 2024-06-24 | 2024-06-27 | 2024-09-20 | Mitzie Construction | [13 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Science City of Muñoz | 105548 | Maligaya ES | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 2 | Repair of Classrooms | 1434779.8 | 1 | 1417679.74 | COMPLETED | 1 | 2024-12-09 | 2024-12-05 | DepEd-SCM-2024-032 | DepEd-SCM-2024-032 | 2024-06-07 | 2024-06-14 | 2024-07-01 | 2024-07-03 | 2024-10-14 | RB VALERA BUILDERS AND GENERAL MERCHANDISE | completed | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Science City of Muñoz | 105553 | Munoz North CS | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 7 | Repair of Classrooms | 3001488.89 | 1 | 2961273.99 | COMPLETED | 1 | 2025-02-07 | 2024-12-23 | DepEd-SCM-2024-032 | DepEd-SCM-2024-032 | 2024-06-07 | 2024-06-14 | 2024-07-01 | 2024-07-03 | 2024-10-11 | GR ERCILLA CONSTRUCTION | completed | [12 empty] | 1 |  |  | 12.24 | 1 | 3 | 2961273.99 |  | COMPLETED
REPAIR 2024 | Region III | Tarlac | 106316 | Delos Remedios ES | BAMBAN | 3rd | 1 | 2 | Repair of Classrooms | 1573950.29 | 1 | 993615.55 | COMPLETED | 1 | 2025-03-23 | 2025-03-19 |  |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | 2024-11-08 | HOR-VERT ENTERPRISES | DONE | [12 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Tarlac | 106378 | Talaga ES | CAPAS | 3rd | 1 | 3 | Repair of Classrooms | 2678202.61 | 1 | 1749036.31 | COMPLETED | 1 | 2025-05-07 | 2025-04-22 |  |  | 2024-09-23 | 2024-10-01 | 2024-10-14 |  | 2024-11-08 | HOR-VERT ENTERPRISES | DONE | [12 empty] | 1 |  |  | 4.25 |  |  |  |  | COMPLETED
REPAIR 2024 | Region III | Tarlac City | 300970 | Maliwalo NHS | CITY OF TARLAC (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 2222222.22 | 1 | 1399796.19 | COMPLETED | 1 | 2024-12-22 | 2024-12-03 | TCSD-IP-04-2024-LOT 2 | TCSD-IP-04-2024-L2 | 2024-06-29 | 2024-07-11 | 2024-07-22 | 2024-08-01 | 2024-09-23 | HIGH VISION BUILDERS CORPORATION | SAVINGS WERE DOWNLOADED | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Tarlac City | 106763 | San Isidro ES | CITY OF TARLAC (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 2222222.22 | 1 | 1521263.96 | COMPLETED | 1 | 2024-12-22 | 2024-12-16 | TCSD-IP-04-2024-LOT 1 | TCSD-IP-04-2024-L1 | 2024-06-29 | 2024-07-11 | 2024-07-22 | 2024-08-01 | 2024-09-23 | HIGH VISION BUILDERS CORPORATION | SAVINGS WERE DOWNLOADED | [12 empty] | 1 |  |  | 12.24 |  |  |  |  | completed
REPAIR 2024 | Region III | Zambales | 106907 | Dampay Elementary School | PALAUIG | 2nd | 1 | 6 | Repair of Classrooms | 4443087.47 | 1 | 4393434.45 | COMPLETED | 1 | 2025-01-08 | 2025-01-07 | Infra-2024-006 | Infra-2024-009 | 2024-07-10 | 2024-07-17 | 2024-07-29 | 2024-07-31 | Oct. 1, 2024 | KAEE Construction Services | [13 empty] | 1 |  |  | 3.25 |  |  |  |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%