## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region IV-A | Laguna | 164505 | Tubog ES | PAETE | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 80008.2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108549 | San Isidro Ilaya ES | BUENAVISTA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 139411.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109092 | Inanuran ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 515315.68 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109097 | Tala ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 834971.96 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109099 | Tamnao ES | SAN ANDRES | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 556061.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109120 | Cawayan II ES | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228870.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109121 | Cumbahan ES | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 294194.06 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 308044 | Huyon-Uyon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 195687.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109138 | Bangkuro ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 241645.46 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109146 | Nangka ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 152536.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109147 | Pinagsama ES | SAN NARCISO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243594.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108580 | Mambaling ES | CALAUAG | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 331718.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108802 | Cawayanin ES | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213636.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 308042 | Cogorin Ibaba NHS - Jongo Ext. | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160892.19 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 231264.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 301387 | Ilayang Ilog-A NHS (Formerly San Francisco B NHS Ilayang Ilog A Ext.) | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 213066.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108819 | Sta. Catalina ES | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 187812.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 108830 | VIllaminda Elementary School | LOPEZ | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 143866.3 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109218 | Sabang ES | TAGKAWAYAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 252026.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IV-A | Quezon | 109226 | Sto. Niño ES | TAGKAWAYAN | 4 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 155957.27 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 500391 | APIA IS | Antipolo City | 2 | 1 | UPGRADING | 2 | 513838.5906 |  | COMPLETED | 1 |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 109349 | CANUMAY ES | Antipolo City | 2 | 1 | UPGRADING | 2 | 783383.1514 |  | COMPLETED | 1 |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 321502 | Canumay NHS | Antipolo City | 2 | 1 | UPGRADING | 2 | 751744.6159 |  | COMPLETED | 1 |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Antipolo City | 109322 | LIBIS ES | Antipolo City | 2 | 1 | UPGRADING | 2 | 778402.4915 |  | COMPLETED | 1 |  |  |  |  | 2018-11-26 | 2018-12-03 | 2018-12-14 | 2018-12-21 | 2019-01-18 | Hawkstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Bacoor City | 107867 | Proposed Stand-Alone SHS 5- Bacoor ES | Bacoor City | 2 | 1 | UPGRADING | 1 | 1146067.18 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301470 | Balete NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 695612.46 | COMPLETED | 1 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301473 | Conde Labac NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855711.74 | 850003.71 | COMPLETED | 1 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855977.1 | 851559.48 | COMPLETED | 1 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 695939.47 | COMPLETED | 1 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 700915.01 | 697193.22 | ONGOING | 0.9 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION | DONE Erection of Post for Transformer waiting for the schedule of meralco | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2018 | Region IV-A | Batangas City | 301481 | Tabangao NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | 1 | 855711.74 | 849691.66 | COMPLETED | 1 | 2018-09-16 |  | R4A-D1-BEFF 2018-ELEC6 | R4A-D1-BEFF 2018-ELEC6 | 2018-06-07 | 2018-06-18 | 2018-06-29 | 2018-07-03 | 2018-07-16 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Calamba City | 301515 | Calamba Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | 2 | 2227134.6 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Calamba City | 301514 | Calamba Bayside Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | 2 | 1863464.5 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 301166 | Amadeo National High School | AMADEO | 6 | 1 | UPGRADING | 2 | 1591456.9177 | 1554123.06 | COMPLETED | 1 |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 307817 | Tanza Trade NHS | TANZA | 6 | 1 | UPGRADING | 2 | 2324139.6983 | 2259976.58 | COMPLETED | 1 |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Cavite | 301165 | ALFONSO NATIONAL HIGH SCHOOL | ALFONSO | 7 | 1 | UPGRADING | 2 | 2307918.5169 | 2245684.72 | COMPLETED | 1 |  |  |  |  | 6/21/0218 | 2018-06-28 | 2018-08-08 | 2018-08-16 | 2018-08-17 | R.A Del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 301230 | Biñan National High School | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 1581624.3 | 1560549.3 | COMPLETED | 1 | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 307931 | Saint Francis NHS | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 569350.89 | 543300.29 | COMPLETED | 1 | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | UPGRADING | 1 | 607488.83 | 586424.13 | COMPLETED | 1 | 2019-02-25 |  | R4A-BNN-2018-07 | R4A-BNN-2018-07 | July 19 - Aug. 8, 2018 | 2018-07-30 | 2018-08-13 | 2018-08-13 | 2018-08-25 | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Quezon | 301307 | Camohaguin National High School | GUMACA | 4 | 1 | UPGRADING | 2 | 2607323.41 |  | COMPLETED | 1 | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Quezon | 301386 | San Francisco B NHS | LOPEZ | 4 | 1 | UPGRADING | 2 | 2832509.36 |  | COMPLETED | 1 | [9 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301428 | Bagumbong NHS | JALA-JALA | 2 | 1 | UPGRADING | 2 | 1630063.4 | 1618689.15 | COMPLETED | 1 |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301430 | Bayugo NHS | JALA-JALA | 2 | 1 | UPGRADING | 1 | 1995063.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 308121 | Hulo National High School | PILILLA | 2 | 1 | UPGRADING | 2 | 1136666.03 | 1128753.89 | COMPLETED | 1 |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 308133 | Laiban NHS | TANAY | 2 | 1 | SOLAR PANEL | 1 | 1001553.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301461 | Sto. Niño NHS | TANAY | 2 | 1 | SOLAR PANEL | 1 | 1646492.71 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | SOLAR | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | Rizal | 301467 | Teresa National High School | TERESA | 2 | 1 | UPGRADING | 2 | 905229.96 | 899714.96 | COMPLETED | 1 |  |  | INFRA-2018-004 |  | 2018-06-05 | 2018-06-13 | 2018-06-25 | 2018-06-27 | 2018-07-20 | LOURBEL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 1 | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 1 | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | San Pablo City | 301504 | San Pablo City National High School | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 1 | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | SAN PABLO CITY | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 | 1 | UPGRADING | 1 | 497945.3776 | 495945.38 | COMPLETED | 1 | 2018-11-26 |  |  | BRF-009-2018 | BRF-009-2018 | 2018-05-25 | 2018-06-08 | 2018-06-18 | 2018-06-21 | Power K Construction Supply and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TANAUAN CITY | 301133 | Pantay NHS | CITY OF TANAUAN | 3 | 1 | UPGRADING | 1 | 490560.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TANAUAN CITY | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 | 1 | UPGRADING | 1 | 1383834.72 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IV-A | TAYABAS CITY | 342576 | STAND ALONE SHS (POTOL) | TAYABAS | 1 | 1 | UPGRADING | 1 | 1306742.55 |  | COMPLETED | 1 | 2018-10-01 |  |  |  | 2018-06-07 | 2018-06-13 | 2018-06-25 | 2018-07-01 | 2018-07-04 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Antipolo City | 230006 | Paglitaw ES | CITY OF ANTIPOLO | 2 | 1 | UPGRADING | Batch 2 | 608772.6 | 603655 | COMPLETED | 1 |  |  |  |  | 2019-06-27 | 2019-07-04 | 2019-07-15 | 2019-07-22 | 2019-10-27 | Hakstow Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Bacoor City | 107888 | Queen's Row ES | BACOOR | 2 | 1 | UPGRADING | Batch 1 | 9405258.9 |  | COMPLETED | 1 |  |  |  |  | 2019-04-07 | 2019-12-07 | 07/30/2019 | 08/13/19 | 08/28/19 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Bacoor City | 107874 | Real Elementary School | BACOOR | 2 | 1 | UPGRADING | Batch 3 | 3773422.45 |  | COMPLETED | 1 |  |  |  |  | 2019-04-07 | 2019-12-07 | 07/30/2019 | 08/13/19 | 08/28/19 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 342219 | SHS in Sto. Tomas | SANTO TOMAS | 3 | 1 | UPGRADING |  | 2322221.07 |  | COMPLETED | 1 | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 1 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 1 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | UPGRADING |  | 2775039.26 |  | COMPLETED | 1 | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 2 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 2 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301069 | Alupay NHS | ROSARIO | 4 | 1 | UPGRADING | Batch 3 | 1926581.98 |  | COMPLETED | 1 | 2020-02-22 |  | R4A – D2 – Electrification CY 2019 - Lot 3 | 11/21/2018 | R4A – D2 – Electrification CY 2019 - Lot 3 | 11/29/2018 | 2018-11-12 | 01/24/2019 | 2019-10-25 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas | 301139 | Rosario NHS | ROSARIO | 4 | 1 | UPGRADING |  | 1898075.48 |  | COMPLETED | 1 | 2020-02-22 | 2020-02-22 | R4A – D2 – Electrification CY 2019 - Batch 2 | 43684 | R4A – D2 – Electrification CY 2019 - Batch 2 | 07/18/2019 | 2019-05-08 | 08/23/2019 | for issuance of NTP | G.S Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 342235 | Alangilan Senior High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 1583219.45 | 1369441.57 | COMPLETED | 1 | ` |  | R4A-D1-BEFFII2019-2019-08-05I | R4A-D1-BEFFII2019-2019-08-05I | 2019-08-13 | 2019-08-19 | 2019-09-02 | 2019-09-17 | 2019-11-05 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301471 | Banaba West NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 855998.5 |  | COMPLETED | 1 | 12-14-2019 |  |  |  | 11/16/2018 | 11/22/2018 | 2018-06-12 | 2019-01-08 | 2019-09-08 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301472 | Batangas National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 1072624.09 | 788000 | ONGOING | 0.9 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-09I | R4A-D1-BEFF2019-2018-11-09I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | RM Tejada Construction & Supplies Corp. | Ready for Energization waiting for the schedule of Meralco Installed Transformer and waiting for the Meter | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308204 | Libjo National High School | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 739207.4 | 677224.27 | COMPLETED | 1 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301475 | Pedro S. Tolentino MNHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 4000297.51 | 3650000 | COMPLETED | 1 | 2020-02-10 |  | R4A-D1-BEFFII2019-2019-089-03I | R4A-D1-BEFFII2019-2019-08-03I | 2019-08-13 | 08-19-2019 | 2019-09-02 | 2019-09-17 | 2019-11-05 | BOTEY CONSTRUCTION | Energized | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308203 | Sta. Rita NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 700932.53 | 678000 | COMPLETED | 1 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-09I | R4A-D1-BEFF2019-2018-11-09I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | RM Tejada Construction & Supplies Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301480 | STO. NIÑO NATIONAL HIGH SCHOOL | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3466113.53 |  | COMPLETED | 1 |  |  |  |  | 2019-09-08 | 08-19-2019 | 2019-02-09 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301482 | Talahib Pandayan NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 662657.66 | 632291.79 | ONGOING | 0.9 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | as per DE recompute for Bill Deposit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 301483 | Talumpok NHS | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 739207.4 | 687146.77 | ONGOING | 0.9 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading | as per DE recompute for Bill Deposit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Y | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Batangas City | 308202 | Tinga Sorosoro National High School (TISISI) | BATANGAS CITY (Capital) | 2 | 1 | UPGRADING |  | 426203.99 | 401134.35 | COMPLETED | 1 | 12-14-2019 |  | R4A-D1-BEFF2019-2018-11-10I | R4A-D1-BEFF2019-2018-11-10I | 11/16/2018 | 11/22/2018 | 2018-12-06 | 2018-12-11 | 2019-08-16 | GS Motar Builders Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342241 | Biñan City Senior High School - SPORTS (Sto. Tomas Campus) | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 3356919.42 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342240 | Biñan City Senior High School - TIMBAO | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 2252698.37 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Binan City | 342242 | Biñan City Senior High School-San Antonio Campus | CITY OF BIÑAN | 1 | 1 | UPGRADING | Batch 3 | 4298158.74 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301516 | Camp Vicente Lim Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 1 | 5864118.02 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301521 | Kapayapaan Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 3 | 1852366.59 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Calamba City | 301525 | Punta Integrated School | CITY OF CALAMBA | 2 | 1 | UPGRADING | Batch 3 | 1431951.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Laguna | 307927 | Dayap National Integrated High School | CALAUAN | 3 | 1 | UPGRADING | Batch 2 | 3144488.22 |  | ONGOING | 0.91 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | N | 0.91 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301487 | BOLBOK NATIONAL HIGH SCHOOL | LIPA CITY | 4 | 1 | UPGRADING |  | 3031713.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1911261.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy NHS | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 5995513.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 109680 | Mabini ES | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1103476 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1910980 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 2004214.01 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Lipa City | 301499 | San Celestino National High School | LIPA CITY | 4 | 1 | UPGRADING | Batch 2 | 1666029.08 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 308113 | Regional Lead School for the Arts in Angono | ANGONO | 1 | 1 | UPGRADING | Batch 3 | 2358246.45 | 2305993.74 | COMPLETED | 1 |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 301453 | Pililla SHS | PILILLA | 2 | 1 | UPGRADING | Batch 3 | 2079707.23 | 2019022.19 | COMPLETED | 1 |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IV-A | Rizal | 308123 | Pantay NHS (Teresa NHS - Pantay Annex) | TERESA | 2 | 1 | UPGRADING | Batch 3 | 9206388.52 | 7726389.06 | COMPLETED | 1 |  |  | INFRA-2019-002 | INFRA-2019-002 | 8/5/2019 - 8/26/2019 | 2019-08-13 | 2019-08-27 | 2019-11-04 |  | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Antipolo City | 109360 | San Ysiro ES | CITY OF ANTIPOLO | 2 | 1 |  |  | 1081542.16 | 1077802.12 | COMPLETED | 1 | 2021-02-12 | 2021-02-10 | Elec2020-RIV-A-AntipoloCity-001 | SBP-2020-02 | 2020-02-25 | 2020-03-04 | 2020-03-16 | 2020-11-27 | 2020-12-14 | Hawkstow Const. and Dev. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 107877 | Aniban CS | BACOOR | 2 | 1 |  |  | 6216862.98 | 6216862.98 | COMPLETED | 1 | 2021-01-17 |  | Elec2020-RIVA-BacoorCity-005 | [5 empty] | Septermber 17, 2020 | MRRM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 307815 | Bacoor NHS - Villa Maria Annex | BACOOR | 2 | 1 |  |  | 2053906.38 | 2033867.14 | COMPLETED | 1 | 2021-12-08 |  | Elec2020-RIVA-BacoorCity-009 | [5 empty] | 2021-08-03 | 3CA Builders | For installation of Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu ES | BACOOR | 2 | 1 |  |  | 7543254.82 | 7543254.82 | COMPLETED | 1 | 2021-01-21 |  | Elec2020-RIVA-BacoorCity-002 | [5 empty] | Septermber 28, 2020 | R.A. del Rosario Construction | For installation of Transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Bacoor City | 342600 | SHS in San Nicholas III, Bacoor City | BACOOR | 2 | 1 |  |  | 7746040.86 | 7746040.86 | COMPLETED | 1 | 2021-01-17 |  | Elec2020-RIVA-BacoorCity-011 | [5 empty] | Septermber 17, 2020 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 342211 | SHS in Calatagan | CALATAGAN | 1 | 1 |  |  | 2952925.81 | 2952925.81 | COMPLETED | 1 | 2021-05-05 |  | Elec2020-RIVA-BatangasProvince-003 |  | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2021-12-07 | 2021-01-05 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 301079 | Bauan National Agricultural and Vocational High School | BAUAN | 2 | 1 |  |  | 7219880.01 | 7219880.01 | COMPLETED | 1 | 2021-05-05 |  | Elec2020-RIVA-BatangasProvince-002 |  | 2019-11-26 | 2019-12-02 | 2019-12-16 | 2021-12-07 | 2021-01-05 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas | 301105 | Itlugan National High School | ROSARIO | 4 | 1 |  |  | 3310459.67 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-BatangasProvince-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Batangas City | 342234 | Gulod Senior High School | BATANGAS CITY (Capital) | 5 | 1 |  |  | 2112972.37 | 1711499.24 | COMPLETED | 1 | 1-28-2021 |  | Elec2020-RIVA-BatangasCity-001 |  | 11-18-2019 | 11-26-2019 | 2019-09-12 | 2020-08-01 | 9-30-2020 | Marakesh Enterprises | Installed Transformer and waiting for the Meter | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cabuyao City | 108239 | Cabuyao CES | CABUYAO | 2 | 1 |  |  | 2905020.86 | 2892836.33 | COMPLETED | 1 | 2021-10-30 |  | Elec2020-RIV-A-CabuyaoCity-001 | [6 empty] | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Calamba City | 301511 | Bubuyan Integrated School | CITY OF CALAMBA | 2 | 1 |  |  | 1245565.31 | 1238996.78 | COMPLETED | 1 | 2022-01-27 | 2022-06-27 | Elec2020-RIV-A-CalambaCity-001 | Contract No. 1 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-09-14 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 6.22 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Calamba City | 301523 | Makiling Integrated School | CITY OF CALAMBA | 2 | 1 |  |  | 2787756.08 | 2787002.38 | COMPLETED | 1 | 2021-04-16 | 2021-10-19 | Elec2020-RIV-A-CalambaCity-002 | Contract No. 4 s. 2020 | Sept. 18, 2020 | Sept. 24, 2020 | 2020-10-06 | 11/25/2020 | 12/16/2020 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301180 | Bulihan NHS | SILANG | 5 | 1 |  |  | 11812616.22 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301202 | Lumil NHS | SILANG | 5 | 1 |  |  | 8070444.69 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 | 1 |  |  | 16899985.44 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 107842 | Buck Estate ES | ALFONSO | 7 | 1 |  |  | 2240416.22 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-013 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301199 | Lucsuhin National High School | ALFONSO | 7 | 1 |  |  | 7148861.63 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 108051 | Tulay ES | MARAGONDON | 7 | 1 |  |  | 5226723.94 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301168 | Anuling NHS | MENDEZ (MENDEZ-NUÑEZ) | 7 | 1 |  |  | 7190797.63 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 301207 | Naic NHS | NAIC | 7 | 1 |  |  | 13738524.52 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite | 108078 | San Roque ES | NAIC | 7 | 1 |  |  | 7237316.71 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-CaviteProvince-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 109632 | Ladislao Diwa ES | CAVITE CITY | 1 | 1 |  |  | 9367762.14 | 9302305.48 | COMPLETED | 1 | 2021-12-26 | 2022-02-18 | Elec2020-RIVA-CaviteCity-004 |  | 2021-05-27 | 2021-06-03 | 2021-06-15 | 2021-06-22 | 2021-06-29 | RA Yolangco | 1 suspension due to meralco | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.22 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 109631 | Sangley Point ES | CAVITE CITY | 1 | 1 |  |  | 4425012.93 | 4403923.39 | COMPLETED | 1 | 2021-04-20 | 2021-04-20 | Elec2020-RIVA-CaviteCity-002 |  | 2019-11-22 | 2019-11-27 | 2019-12-18 | 2020-01-17 | 2020-12-21 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Cavite City | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 |  |  | 2451288.88 | 2429212.9 | COMPLETED | 1 | 2021-04-20 | 2021-04-20 | Elec2020-RIVA-CaviteCity-003 |  | 2019-11-22 | 2019-11-27 | 2019-12-18 | 2020-01-17 | 2020-12-21 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 325902 | Paliparan II National High School | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 7260407.77 | ₱5,737,906.70 | COMPLETED | 1 | 2022-03-19 |  | Elec2020-RIVA-DasmariñasCity-006 | CY2020 BEFF ELEC Batch 2 | 2021-07-19 | 2021-07-27 | 2021-08-09 | 2021-08-25 | 2021-09-09 | MRRM Trading and Construction | Installation of transformer and energization by MERALCO is completed on October 12, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107908 | Paliparan III ES | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 9172054.59 | ₱7,279,567.94 | COMPLETED | 1 | 2022-03-19 |  | Elec2020-RIVA-DasmariñasCity-002 | CY2020 BEFF ELEC Batch 2 | 2021-07-19 | 2021-07-27 | 2021-08-09 | 2021-08-25 | 2021-09-09 | MRRM Trading and Construction | Installation of transformer and energization by MERALCO is completed on October 12, 2022 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107923 | Pintong Gubat Elementary School | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 4691477.87 | ₱11,153,105.62 | COMPLETED | 1 | 2021-12-16 |  | Elec2020-RIVA-DasmariñasCity-003 | CY2020 BEFF ELEC C1 | 2019-11-26 | 2019-12-06 | 2019-12-16 | 2020-01-13 | 2020-09-01 | R.A Del Rosario Construction | With Issued Suspension of Works due to the delay in the Installation of Transformer and Energization by MERALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Dasmariñas City | 107920 | Sta. Cruz ES (Dasmariñas BBES E) | CITY OF DASMARIÑAS | 4 | 1 | UPGRADING |  | 11159076.6 | ₱4,671,893.24 | COMPLETED | 1 | 2021-12-16 |  | Elec2020-RIVA-DasmariñasCity-005 | CY2020 BEFF ELEC C1 | 2019-11-26 | 2019-12-06 | 2019-12-16 | 2020-01-13 | 2020-09-01 | R.A Del Rosario Construction | With Issued Suspension of Works due to the delay in the Installation of Transformer and Energization by MERALCO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | General Trias City | 107959 | Diego Mojica MS | CITY OF GENERAL TRIAS | 6 | 1 |  |  | 7340176.19 | 7290176.19 | COMPLETED | 1 | 2021-01-22 | 2021-01-22 | Elec2020-RIVA-GeneralTriasCity-001 | [6 empty] | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3 | 1 |  |  | 6162276.31 | 6121913.44 | COMPLETED | 1 | March 30, 2021 | "Dec. 19, 2022 | Elec2020-RIVA-ImusCity-008 | ITB - 2020 - 03 - 003 |  |  |  |  | Nov. 19, 2020 | 3CA Builders | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107972 | Buhay na Tubig Elementary School | IMUS | 3 | 1 |  |  | 5466782.73 | 5423748.42 | COMPLETED | 1 | March 30, 2021 | December 23, 2022 | Elec2020-RIVA-ImusCity-009 | ITB - 2020 - 03 - 002 | [6 empty] | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107984 | E. Villanueva ES | IMUS | 3 | 1 |  |  | 2877415.7 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-ImusCity-002 | [6 empty] | R.A. del Rosario Construction | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino ES | IMUS | 3 | 1 |  |  | 15347805.6 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-ImusCity-003 | [6 empty] | R.A. del Rosario Construction | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Imus City | 107979 | Tanzang Luma ES | IMUS | 3 | 1 |  |  | 5453366.85 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-ImusCity-006 | [7 empty] | Project was suspended due to Meralco processing and installation of transformer | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 |  |  | 1423668.82 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-Laguna-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301237 | Calumpang NHS - Lowland NHS Annex | NAGCARLAN | 3 | 1 |  |  | 2097625.91 |  | ONGOING | 0.9 | For installation of Transformer |  | Elec2020-RIV-A-Laguna-009 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301258 | Plaridel NHS | NAGCARLAN | 3 | 1 |  |  | 6883253.96 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-Laguna-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 | 1 |  |  | 6454363.01 |  | ONGOING | 0.9 | For installation of Transformer |  | Elec2020-RIV-A-Laguna-015 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301228 | Banca-Banca NHS - Integrated Senior High School | VICTORIA | 3 | 1 |  |  | 3703337.62 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-Laguna-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 301250 | Masapang NHS | VICTORIA | 3 | 1 |  |  | 2799361.19 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-Laguna-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 7.23 | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Laguna | 307906 | Gov. Felicisimo T. San Luis Memorial National High School | SANTA CRUZ (Capital) | 4 | 1 |  |  | 6678071.91 |  | ONGOING | 0.9 | For installation of Transformer |  | Elec2020-RIV-A-Laguna-001 | [8 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2020 | Region IV-A | Laguna | 342362 | Santa Cruz SHS | SANTA CRUZ (Capital) | 4 | 1 |  |  | 2239194.37 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-Laguna-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301489 | Bulacnin NHS | LIPA CITY | 4 | 1 |  |  | 6283440.82 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109673 | Calamias ES | LIPA CITY | 4 | 1 |  |  | 2211352.69 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109663 | Lumbang ES | LIPA CITY | 4 | 1 |  |  | 2607629.33 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109693 | Padre Valerio Malabanan MS | LIPA CITY | 4 | 1 |  |  | 5596380.26 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109650 | San Celestino ES | LIPA CITY | 4 | 1 |  |  | 1681710.72 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School ( | LIPA CITY | 4 | 1 |  |  | 6180929.04 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-011 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109704 | Tangway ES | LIPA CITY | 4 | 1 |  |  | 2967880.83 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 |  |  | 2890060.15 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301495 | Lumbang NHS | LIPA CITY | 6 | 1 |  |  | 2249980.53 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 301498 | Rizal NHS | LIPA CITY | 6 | 1 |  |  | 2015728.17 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109652 | San Isidro ES | LIPA CITY | 6 | 1 |  |  | 2005355.46 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109700 | San Salvador Loob ES | LIPA CITY | 6 | 1 |  |  | 2094338.39 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-022 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lipa City | 109654 | Sto. Niño ES | LIPA CITY | 6 | 1 |  |  | 2382897.67 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LipaCity-028 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109718 | Elvira Razon Aranilla ES | LUCENA CITY (Capital) | 2 | 1 |  |  | 5095322.69 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LucenaCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109717 | Gulang-gulang Elementary School | LUCENA CITY (Capital) | 2 | 1 |  |  | 5081068.66 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LucenaCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 167502 | Isabang ES-Bocohan Annex | LUCENA CITY (Capital) | 2 | 1 |  |  | 1315373.14 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LucenaCity-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 |  |  | 15608257.02 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LucenaCity-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 | 1 |  |  | 10036454.29 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-LucenaCity-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 | 1 |  |  | 10684093.83 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-025 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 | 1 |  |  | 6929037.69 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-026 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308004 | Pagbilao NHS | PAGBILAO | 1 | 1 |  |  | 7361096.25 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-030 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 | 1 |  |  | 5811249.04 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-024 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301407 | Talipan NHS | PAGBILAO | 1 | 1 |  |  | 8389147.86 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-029 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308020 | GOV. ANACLETO C. ALCALA NATIONAL HIGH SCHOOL | SARIAYA | 2 | 1 |  |  | 4778606.09 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-021 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 |  |  | 4215205.75 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-039 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301310 | Catanauan NHS | CATANAUAN | 3 | 1 |  |  | 4181508.16 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-042 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308001 | Matandang Sabang NHS | CATANAUAN | 3 | 1 |  |  | 6233239.58 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-043 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301312 | Tagbacan NHS | CATANAUAN | 3 | 1 |  |  | 5028870.71 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-045 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301393 | San Isidro NHS, General Luna | GENERAL LUNA | 3 | 1 |  |  | 6053807.56 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-046 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 |  |  | 15652496.42 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-020 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 |  |  | 5045900.95 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-047 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301330 | Pakiing NHS | MULANAY | 3 | 1 |  |  | 3872684.15 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-048 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301280 | Abuyon NHS | SAN NARCISO | 3 | 1 |  |  | 5482964.64 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-041 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 |  |  | 7593809.65 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301357 | Malusak National High School | ATIMONAN | 4 | 1 |  |  | 4546052.94 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-019 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301402 | San Roque-Ilaya NHS, Calauag | CALAUAG | 4 | 1 |  |  | 4733950.85 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-016 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301404 | Sto. Domingo NHS | CALAUAG | 4 | 1 |  |  | 7074714.93 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301320 | Dungawan NHS | GUINAYANGAN | 4 | 1 |  |  | 5712244.35 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301331 | Gumaca IS | GUMACA | 4 | 1 |  |  | 6200927.2 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-034 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301372 | Panikihan NHS | GUMACA | 4 | 1 |  |  | 6258231.59 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-035 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301346 | Cogorin Ibaba NHS | LOPEZ | 4 | 1 |  |  | 4877395.52 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-038 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301316 | Concepcion NHS | PLARIDEL | 4 | 1 |  |  | 6868584.24 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-031 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301287 | Bagong Silang NHS | TAGKAWAYAN | 4 | 1 |  |  | 5684812.41 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308038 | Cabibihan National High School | TAGKAWAYAN | 4 | 1 |  |  | 4474396.04 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301338 | Kinatakutan NHS | TAGKAWAYAN | 4 | 1 |  |  | 4672613.34 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 308002 | Mapulot National High School | TAGKAWAYAN | 4 | 1 |  |  | 4789843.8 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Quezon | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 |  |  | 5702333.09 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-Quezon-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Rizal | 301463 | Talim Point NHS | BINANGONAN | 1 | 1 |  |  | 3474859.92 | 3457278.19 | COMPLETED | 1 |  |  | Elec2020-RIV-A-Rizal-001 | INFRA-2019-006 | November 20, 2019 to December 9, 2019 | November 28, 2019 | December 10, 2019 | December 12, 2019 | October 21,2020 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109777 | Bagong Bayan Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 2337922.19 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo city-017 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109768 | Del Remedios Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 4512466.26 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo city-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109795 | San Antonio I ES | CITY OF SAN PABLO | 3 | 1 |  |  | 891949.45 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-014 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109797 | San Gregorio Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 885245.08 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-015 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109799 | San Isidro Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 1031759.94 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-023 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109772 | San Mateo Elementary School | CITY OF SAN PABLO | 3 | 1 |  |  | 1253145.32 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-018 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 342575 | San Pablo Stand-Alone Senior High School - San Juan | CITY OF SAN PABLO | 3 | 1 |  |  | 3151848.48 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 308601 | Santissimo Rosario National High School | CITY OF SAN PABLO | 3 | 1 |  |  | 3941531.53 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | San Pablo City | 109775 | Sta.Filomina Integrated National High School | CITY OF SAN PABLO | 3 | 1 |  |  | 2596779.99 |  | COMPLETED | 1 |  |  | Elec2020-RIV-A-San Pablo City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 321602 | BALELE INTEGRATED HIGH SCHOOL | TANAUAN CITY | 3 | 1 |  |  | 1586760.2 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-TanauanCity-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301113 | LUYOS NHS | TANAUAN CITY | 3 | 1 |  |  | 2703042.04 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-TanauanCity-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301133 | PANTAY NATIONAL HIGH SCHOOL | TANAUAN CITY | 3 | 1 |  |  | 2925876.19 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-TanauanCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tanauan City | 301154 | TANAUAN SCHOOL OF FISHERIES | TANAUAN CITY | 3 | 1 |  |  | 5333861.6 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-TanauanCity-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS | 1 | 1 |  |  | 19660229.99 |  | COMPLETED | 1 |  |  | Elec2020-RIVA-TayabasCity-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 342201 | Primitivo Kalaw Senior High School | BALETE | 3rd | 1 | Upgrading of Electrical System | 1 | 2998674.2 | 2994666.11 | COMPLETED | 1 | 2024-01-30 |  | Elec2023-RIVA-BatangasProvince-001 | Elec2023-RIVA-BatangasProvince-001 |  |  | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 307729 | Aplaya National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 594728.0229 | 582050.49 | COMPLETED | 1 | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 6.24 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 301094 | Calubcob I National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 656627.2153 | 645856.69 | COMPLETED | 1 | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 6.24 | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Batangas | 301160 | Tipas Integrated National High School | SAN JUAN | 4th | 1 | Installation of Metering and Transformer | 1 | 747686.9341 | 727426.71 | COMPLETED | 1 | [6 empty] | 2023-08-04 |  | 2023-10-25 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Cavite | 301191 | Gen. Emilio Aguinaldo-Bailen Integrated School | GENERAL EMILIO AGUINALDO | 8th | 1 | Electrification of Unenergized School and Modernized of Electrical System of On-Grid Schools | 1 | 6290439.38 | 4898453.46 | COMPLETED | 1 | 2024-04-09 |  | Elec.2023RIVACavite-001 |  |  | 2023-08-01 | 2023-08-15 | 2023-10-03 | 2023-10-12 | 3CA BUILDERS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | ENERGIZATION | bbm 2023 ONGRID | ongrid | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109671 | Anilao ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3905532.01 |  | COMPLETED | 1 | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -005 | ELEC 20223-RIVA-LIPA CITY -005 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 501184 | Cumba-Quezon Integrated School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3921383.41 |  | COMPLETED | 1 | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -003 | ELEC 20223-RIVA-LIPA CITY -003 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 301494 | LodLod NHS | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 6673701.15 |  | COMPLETED | 1 | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -009 | ELEC 20223-RIVA-LIPA CITY -009 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109684 | Rizal Elementary School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3679809.77 |  | COMPLETED | 1 | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -002 | ELEC 20223-RIVA-LIPA CITY -002 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109648 | San Adriano MES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 4159841.48 |  | COMPLETED | 1 | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -004 | ELEC 20223-RIVA-LIPA CITY -004 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 501185 | San Jose Integrated School | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 4944300.44 |  | COMPLETED | 1 | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -007 | ELEC 20223-RIVA-LIPA CITY -007 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109699 | San Salvador ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3957039.95 |  | COMPLETED | 1 | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -001 | ELEC 20223-RIVA-LIPA CITY -001 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | GS MOTAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 5322651.55 |  | COMPLETED | 1 | 2023-10-17 |  | ELEC 20223-RIVA-LIPA CITY -008 | ELEC 20223-RIVA-LIPA CITY -008 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY | 4th | 1 | Upgrading of Electrical System | 1 | 3912335.9 |  | COMPLETED | 1 | 2023-09-17 |  | ELEC 20223-RIVA-LIPA CITY -006 | ELEC 20223-RIVA-LIPA CITY -006 | 05/02/2023 - 05/22/2023 | 2023-05-10 | 2023-05-22 |  | 2023-06-19 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Quezon | 109085 | Sampaloc Elementary School (Main) | SAMPALOC | 1st | 1 | Modernization of Electrical System On-Grid Schools | 1 | 4627751.06 |  | COMPLETED | 1 | 2023-12-16 |  | ELEC 2023 - RIVA - QUEZON PROVINCE - 001 |  | 2023-05-26 | 2023-06-02 | 2023-06-14 | 2023-06-22 | 2023-07-19 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2023 UPGRADE |  | COMPLETED
ELECTRIFICATION 2023 | Region IV-A | Tayabas City | 109243 | Tayabas East CS I | CITY OF TAYABAS | 1st | 1 | Modernization of Electrical System On-Grid Schools | 1 | 5108295.16 | 3958936.07 | ONGOING | 0.86 | 2024-03-26 |  | INFRA-2023-001 |  | 2023-07-25 | 2023-08-02 | 2023-08-14 | 2023-09-01 | 2023-09-28 | 3CA BUILDERS CORPORATION | Processing of MERALCO application | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.86 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Antipolo City | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2nd | 1 | Upgrading of Electrical System (Underground System) | 1 | 13988227.07 | 13970000 | ONGOING | 0 | 2025-03-14 |  |  | BEFF-ANT-2024-03 | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-08-07 | 2024-10-15 | Hawkstow Const. and Devt. | SUSPENDED, Awaiting Electrification Permit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Bacoor City | 107878 | Bayanan Elementary School | BACOOR | 2nd | 1 | Modernization of Electrical Systems of On-Grid Schools | 1 | 8852615.57 | 8835874.64 | ONGOING | 0.85 | 2024-11-29 |  | ELEC2023-0001 | 2023-0018 | November 30,2023 | 2023-12-07 | 2023-12-20 | 2023-12-27 | 2024-06-03 | MRRM TRADING AND CONSTRUCTION | Suspended due to Meralco | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.7 | 0.15 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 342206 | Lian Senior High School | LIAN | 1st | 1 | Upgrading of Electrical System | 1 | 12024847.46 | 11956875.42 | ONGOING | 0.6 |  |  | ELEC 2024 - RIVA - BATANGAS - 003 | ELEC 2024 - RIVA - BATANGAS - 003 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 | 2025-01-30 | Marakesh Enterprises | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.6 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301115 | Anselmo A. Sandoval Memorial NHS | MABINI | 2nd | 1 | Upgrading of Electrical System | 1 | 11288429.5 | 11200000 | ONGOING | 0.6 |  |  | ELEC 2024 - RIVA - BATANGAS - 002 | ELEC 2024 - RIVA - BATANGAS - 002 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Botey Construction | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.6 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301149 | Sta. Teresita NHS | STA. TERESITA | 3rd | 1 | Upgrading of Electrical System | 1 | 10770775.87 | 10702805.3 | ONGOING | 0.6 |  |  | ELEC 2024 - RIVA - BATANGAS - 001 | ELEC 2024 - RIVA - BATANGAS - 001 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Marakesh Enterprises | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.6 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas | 301098 | Dagatan NHS | TAYSAN | 4th | 1 | Upgrading of Electrical System | 1 | 13317186 | 13250000 | ONGOING | 0.8 |  |  | ELEC 2024 - RIVA - BATANGAS - 004 | ELEC 2024 - RIVA - BATANGAS - 004 | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-17 |  | Botey Construction | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.8 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Batangas City | 109615 | Jose C. Pastor MES | BATANGAS CITY (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical System of On-Grid Schools | 1 | 7208674.94 | 7000000 | ONGOING | 0.8875 | 2024-10-07 |  | 2023-10-003-PB-INFRA | 05-001-2024 INFRA | 2023-10-24 | 2023-11-03 | 2023-11-15 | 2023-12-28 | 2024-05-31 | Botey Construction | with Suspension Order | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.8875 | 0 |  |  | ENERGIZATION |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Binan City | 108213 | Biñan CES (Doña Aurora ES) | CITY OF BIÑAN | 1st | 1 | Upgrading of Electrical System | 1 | 16787346.89 | 16737346.89 | ONGOING | 0.96 | 2025-01-19 |  | R4A-BNN-2023-04 | R4A-BNN-2023-04 | December 27, 2023 - January 16, 2024 | 2024-01-04 | 2024-01-16 | 2024-02-07 | 2024-05-24 | Marakesh Enterprises |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.96 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Calamba City | 109815 | E. Barretto Sr. ES | CITY OF CALAMBA | Lone | 1 | Upgrading of Electrical Facilities | 1 | 4500000 | 4489385.57 | ONGOING | 0.2 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.2 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 108016 | AGUINALDO ELEMENTARY SCHOOL | KAWIT | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6978426.71 | 6955504.45 | ONGOING | 0.55 | [10 empty] | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.55 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107892 | Bancal Elementary School | CARMONA | 5th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 7475122.6 | 7443971.23 | ONGOING | 0.55 |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.55 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107860 | Loma Elementary School | AMADEO | 7th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 6984796.05 | 6963039.13 | ONGOING | 0.55 |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.55 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite | 107926 | BAILEN ES | GEA | 8th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 11155889.25 | 11118914.41 | ONGOING | 0.55 |  |  |  | RIVACaviteBACInfra 004-2024 |  | 2024-08-08 | 2024-08-27 | Jan. 6. 2025 | Jan. 14, 2025 | R.A. Del Rosario Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.55 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Cavite City | 109628 | Garita ES | CAVITE CITY | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 9808334.02 | 9000000 | COMPLETED | 1 | 2025-02-06 |  | 2024-06-0005 | 2024-06-0005 | 2024-06-04 | 2024-06-13 | 2024-06-26 | 2024-07-04 | 2024-09-26 | 3CA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 3.25 | ENERGIZATION | BBM 2025 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Dasmarinas City | 107917 | Dasmariñas II CS (Dasmariñas BBES B) | CITY OF DASMARIÑAS | 4th | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 22396279.87 | 22342252.33 | ONGOING | 0.75 | 2025-07-10 |  | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | August 26-September 13, 2024 | 2024-09-25 | 2024-10-11 | 2025-01-15 | 3CA Builders Corporation | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.75 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Dasmarinas City | 107913 | V. P. Villanueva MS (Palapala) | CITY OF DASMARIÑAS | 4th | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 7530097.97 | 7524654.77 | ONGOING | 0.75 | 2025-07-10 |  | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | CY2024 BEFF ELEC Batch 2 | August 26-September 13, 2024 | 2024-09-25 | 2024-10-11 | 2025-01-15 | 3CA Builders Corporation | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.75 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | General Trias City | 107944 | Angel L. Bawalan ES | CITY OF GENERAL TRIAS | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 5348091.76 | 5300303.11 | ONGOING | 0.8 | 2025-06-27 |  | 2024-12-002 | 2024-12-002 | 2024-07-18 | 2024-07-26 | 2024-08-07 | 2024-08-13 | 2024-12-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.8 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Imus City | 107968 | Anabu I Elementary School | IMUS | 3rd | 1 | Modernization of Electrical Systems of On-Grid Schools | 1 | 6760877.85 | 6739888.88 | ONGOING | 0.75 | Aug. 20, 2025 |  | 2024-10-004 | 2024-10-004 | August 8, 2024 | August 27, 2024 | September 9, 2024 | September 30, 2024 |  | 144 cubits builders and supply | already downloaded subaro | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.75 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Laguna | 108305 | Bernaldo N. Calara ES | Los Baños | 2nd | 1 | Upgrading of Electrical System | 1 | 4907472.04 | 3809235.44 | Under procurement | 0 | [9 empty] | EBLL Electrical Engineering Services | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Laguna | 108256 | Dayap ES | Calauan | 3rd | 1 | Upgrading of Electrical System | 1 | 10272779.81 | 8024471.98 | Under procurement | 0 | [9 empty] | EBLL Electrical Engineering Services | RTA submitted to CO- waiting for approval of downloading of funds | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Laguna | 301232 | Buenavista INHS | Magdalena | 4th | 1 | Upgrading of Electrical System | 1 | 7572083.57 | 6661782.89 | Under Procurement | 0 | [9 empty] | AYZARIZ Corporation | RTA submitted to CO- waiting for SARO | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109658 | Abundio Torre Memorial Elementary School | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 8931838.41 | 8915317.29 | COMPLETED | 1 | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-024 | ELEC 2024-RIVA-LIPA CITY-024 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 5465282.4 | 5455051.2 | COMPLETED | 1 | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-007 | ELEC 2024-RIVA-LIPA CITY-007 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109660 | Bulacnin ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 12025935 | 11975546.02 | COMPLETED | 1 | 2024-12-31 |  | ELEC 2024-RIVA-LIPA CITY-001 | ELEC 2024-RIVA-LIPA CITY-001 | 2024-06-11 | 2024-06-19 | 2024-07-01 | 2024-07-17 | 2024-09-02 | 144 cubits builders and supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 109646 | Malitlit ES | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 8729469.09 | 8719457.3 | COMPLETED | 1 | 2024-10-01 | 2024-08-08 | ELEC 2024-RIVA-LIPA CITY-015 | ELEC 2024-RIVA-LIPA CITY-015 |  |  | 2023-12-18 | 2023-12-29 | 2024-06-03 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 8.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 6th | 1 | Upgrading of Electrical System | 1 | 7993270.23 | 7943210.95 | COMPLETED | 1 | 2024-12-31 |  | ELEC 2024-RIVA-LIPA CITY-006 | ELEC 2024-RIVA-LIPA CITY-006 | 2024-06-11 | 2024-06-19 | 2024-07-01 | 2024-07-17 | 2024-09-02 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Lucena City | 109715 | Lucena East VIII Elementary School | LUCENA CITY (Capital) | 2nd | 1 | Upgrading of Electrical System | 1 | 3983306.63 | 3963665.7 | COMPLETED | 1 |  | 2024-08-30 | ELEC 2023-LUCENA CITY - 001 |  | November 22,2023 - December 12, 2023 | 2023-11-30 | 2023-12-12 |  | 2024-07-03 | 144 cubits builders and supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 109074 | REAL CENTRAL ELEMENTARY SCHOOL | REAL | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 12022005.85 | 11990000 | ONGOING | 0.83 | November 17, 2024 |  |  | 2023-07-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 22, 2024 | Hawstow Construction and Development |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.83 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Quezon | 301380 | RECTO MEMORIAL NATIONAL HIGH SCHOOL | TIAONG | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 34238345.22 | 34163589.19 | COMPLETED | 1 | 2024-12-22 | [7 empty] | 2024-05-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3rd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 12086998.27 | 9609287.1 | COMPLETED | 1 | 2024-11-16 | 2024-10-07 | [6 empty] | 2024-05-21 | EBLL Electrical Engineering Services | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Quezon | 301325 | Gumaca National High School | GUMACA | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 47697923.85 | 47594367.01 | COMPLETED | 1 | 2025-01-21 | [7 empty] | 2024-05-27 | 3CA Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 12.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Rizal | 109535 | Taytay Elementary School | Taytay | 1st | 1 | Upgrading of Electrical System (Undergound System) | 1 | 7488492.59 | 7288533.09 | Under procurement | 0 |  |  |  |  | November 15, 2024 | November 22, 2024 | December 6, 2024 | December 11, 2024 |  | NMDC Construction Corporation | for award | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | not yet started
ELECTRIFICATION 2024 | Region IV-A | Rizal | 301454 | Quisao National High School | Pililla | 2nd | 1 | Upgrading of Electrical System (Undergound System) | 1 | 12472902.42 | 10976154.7 | ONGOING | 0.35 |  |  |  |  | 2024-09-23 | 2024-10-01 | 2024-10-15 | 2024-11-11 | 2025-01-20 | NMDC Construction Corporation |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.3 | 0.05 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | San Pablo City | 109806 | Guerilla Elementary School | SAN PABLO CITY | 3rd | 1 | Upgrading of Electrical System | 1 | 10000000 | 5119388.4 | COMPLETED | 1 | 2024-11-30 |  | BEFF-E-001 | BEFF-E-001 | 2023-12-01 | 2023-12-12 | 2023-12-27 | 2024-01-12 | 2024-07-02 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IV-A | Tanauan City | 107753 | Bernardo Lirio Memorial Central School | CITY OF TANAUAN | 3rd | 1 | Upgrading of Electrical System | 1 | 14314741.51 | 14296923.19 | ONGOING | 0.9 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.9 | 0 |  |  | UPGRADING |  |  | ONGOING
ELECTRIFICATION 2024 | Region IV-A | Tayabas City | 109232 | Busal ES | CITY OF TAYABAS | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 4560947.36 | 4552000 | ONGOING | 0.95 | February 13, 2025 as to approved extension by the SDO |  | ITB-INFRA-2024-004 | ITB-INFRA-2024-004 | 2024-03-28 | 2024-04-05 | 2024-04-17 | 2024-06-11 | 2024-07-24 | Hawstow Construction and Development | Pending on the completion of the punchlist item due to access and weather condition Conducted inspection last April 14, 2025 (with remaining punchlist) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0.95 | 0 |  |  | SOLAR |  |  | ONGOING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%