## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region IX | Zamboanga City | 199005 | Latap ES-Lacumba Annex | ZAMBOANGA CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 740248.18 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga City | 126144 | Mt. View ES | ZAMBOANGA CITY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 515884.75 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124549 | Bagong Silang PS | PIÑAN (NEW PIÑAN) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303720 | Rizal NHS | RIZAL | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124643 | Don Eleno Razo ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124661 | Macalibre ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124663 | Nazareth ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124652 | Situbo ES | SERGIO OSMEÑA SR. | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 228966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303737 | Sibutad NHS | SIBUTAD | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124323 | Bitoon ES | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124331 | Lumaping ES | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 220880.44 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 315641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124365 | Danao PS | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303727 | Seres NHS | KATIPUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 315641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 314141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124517 | Serongan ES | MANUKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 313641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124481 | Mateo Denoyo ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124489 | Sibatog ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124490 | Sibod ES | PRES. MANUEL A. ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124674 | Balok ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124681 | Dumuyog ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124684 | Guibo ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124686 | Gunyan ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 321141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303730 | Siayan NHS | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 321141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124703 | Suminogod ES | SIAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124769 | Dagum ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124793 | Datagan ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 316141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOO | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303739 | Sindangan NHS | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320141.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124807 | Tinaplan ES | SINDANGAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 320641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303675 | Bacungan NHS Annex - Tinuyop | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 322641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124430 | Cilago ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263892.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195525 | San Isidro ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 328641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195510 | Malinao PS | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124270 | Nonoyan ES | BALIGUIAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 223966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303684 | Godod NHS | GODOD | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 325641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 328641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195501 | Matunoy ES | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124320 | Tipan ES | GUTALAC | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 261310.12 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 327641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124354 | Palalihan ES | KALAWIT | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 314120 | Balas NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 325641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303707 | COMPRA NHS | LILOY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303706 | Liloy NHS | LILOY | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 324641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 324641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303721 | Salug National High School | SALUG | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 322641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124714 | Dumintag ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124715 | Guimba Parang ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195532 | Litawan ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303708 | Malayal NHS | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 340641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124732 | Puliran ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303734 | Sibuco NHS | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 340641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303735 | Sibuco NHS Annex - Lunday | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124735 | Sto. Niño ES | SIBUCO | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124816 | Cuyan ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195533 | Jolito Camatura ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124826 | Matiag ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 195517 | Paduan ES | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 330641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124834 | Bitugan ES | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303743 | Dacon NHS (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 335641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 333641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 124845 | Tapanayan ES | SIRAWAI | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 243966.18 |  | COMPLETED | 1 |  |  |  |  | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-20 | 2017-12-23 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 326641.7291 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 124942 | Grap ES | DIMATALING | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 226606.17 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 124982 | Songayan ES | DINAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 200398.72 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga del Sur | 125359 | Mabang Intermediate School | SAN PABLO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160500.21 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125536 | Tantawan PS | ALICIA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 385756.45 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125552 | Ligaya PS | BUUG | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 239668.95 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125597 | Israel PS | IMELDA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160729.35 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125604 | Mali Little Baguio PS | IMELDA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 336448.94 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125682 | Tandu-Comot ES | MABUHAY | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 239258.89 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125699 | Malongon ES | MALANGAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 249361.67 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125708 | Tigabon PS | MALANGAS | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 445775.63 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125770 | Mayabo PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160075.71 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125771 | Minundas PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 455738.57 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125780 | Talaptap PS | PAYAO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 272143.76 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125620 | Labe Primary School | IPIL | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 313968.32 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125643 | Goodyear PS | KABASALAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 272383.69 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125653 | Salupan PS | KABASALAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 162327.35 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 196526 | Gutayan PS | ROSELLER LIM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160290.83 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125799 | San Ernesto ES | ROSELLER LIM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 160531.61 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 125811 | Bagong Silang ES | SIAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 314449.84 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region IX | Zamboanga Sibugay | 196517 | Teras Elementary School | TUNGAWAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 486239.05 |  | COMPLETED | 1 | [7 empty] | 2017-12-29 | 2018-01-03 | Stone Throw Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 871922.87 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 2011470.98 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City |  | Zamboanga Norte NHS - Miputak Campus | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 443826.29 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Dipolog City |  | Zamboanga Norte NHS - Turno Campus | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | 2 | 875609.79 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 4706721.6 |  | COMPLETED | 1 | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 2098158.43 |  | COMPLETED | 1 | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 314601 | Isabela City NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 939814.63 |  | COMPLETED | 1 | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Isabela City | 303895 | Malamawi National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | 2 | 1155357.27 |  | COMPLETED | 1 | [9 empty] | MMP Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126086 | Banale ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 637234.95 | 633785.58 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126037 | Bogo ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 616609.25 | 611977.36 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126060 | Bulatok ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 709967.65 | 702771.47 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 314705 | Co Tek Chun National Trade School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1470348.25 | 1462436.82 | COMPLETED | 1 | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126039 | Danlugan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 690065.67 | 683848.14 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 964515.41 | 956340.56 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303901 | Lala National High School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1297232.37 | 1290162.54 | COMPLETED | 1 | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303904 | Manga NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1284604.6 | 1277620.44 | COMPLETED | 1 | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 724441.83 | 719003.36 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 314702 | Norberta Guillar NHS (Napolan NHS - Norberta Guillar Mem. School Ext.) | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1483030.63 | 1475015.43 | COMPLETED | 1 | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 303908 | Pagadian City NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 1614991.95 | 1595444.32 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 683190.44 | 675872.5 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126052 | San Pedro Central Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 802766.55 | 798127.74 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126079 | Sta. Lucia Central Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 847998.33 | 840631.43 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City |  | Stand Alone - Zamboanga del Sur NHS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2660165.92 | 2645388.69 | COMPLETED | 1 | 2018-12-27 |  | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | DepED-2018-RIX-PAG-ELECTRIFICATION-1 | 2018-07-12 |  | 2018-08-01 | 2018-08-07 | 2018-08-22 | ALINAB CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1542244.33 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Y | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Pagadian City | 126054 | Tawagan Sur Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING | 3 | 762798.38 | 754866.03 | COMPLETED | 1 |  |  | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | DepED-2018-RIX-PAG-ELECTRIFICATION-3 | 2018-11-24 |  | 2018-12-14 | 2018-12-19 | 2018-12-27 | MAQUESERG CONST. & GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303915 | Ayala NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 2010000 | 1788937.91 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 345869 | Baliwasan Senior High School | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 904500 | 738378.12 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 314805 | Recodo NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 838517.37 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303933 | Southcom NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 847456.17 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303935 | Talisayan NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | 1 | 1005000 | 814771.02 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303918 | Bunguiao NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 629391.63 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303928 | Manicahan NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 628909.03 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303929 | Mercedes NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 1005000 | 919671.2 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga City | 303936 | Tictapul NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING | 1 | 703500 | 627582.12 | COMPLETED | 1 | 2018-11-17 | 2019-06-15 |  |  | 2018-03-16 | 2018-03-27 | 2018-04-10 | 2018-07-11 | 2018-07-17 | RCDG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1 | 1 | UPGRADING | 1 | 636254.46 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 | 1 | UPGRADING | 1 | 640017.36 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124561 | Piñan CS | PIÑAN (NEW PIÑAN) | 1 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124579 | Polanco CS | POLANCO | 1 | 1 | UPGRADING | 1 | 637379.23 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124597 | Silawe CS | POLANCO | 1 | 1 | UPGRADING | 1 | 637379.23 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124610 | Rizal CS | RIZAL | 1 | 1 | UPGRADING | 1 | 640017.36 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124671 | San Isidro CS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING | 1 | 643710.73 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124651 | Sergio Osmeña CS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING | 1 | 641600.23 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | UPGRADING | 1 | 641072.61 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124335 | Ponot CS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124369 | Katipunan CS | KATIPUNAN | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124396 | Taga CS | KATIPUNAN | 2 | 1 | UPGRADING | 1 | 634829.87 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124524 | Gupot ES | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124510 | Manukan East CS | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124511 | Manukan West CS | MANUKAN | 2 | 1 | UPGRADING | 1 | 638962.11 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124495 | Dohinob CS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124488 | Roxas CS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING | 1 | 638434.48 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-31 | YSL BUILDER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124701 | Siayan CS | SIAYAN | 2 | 1 | UPGRADING | 1 | 637930.59 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124778 | Juan Bugarin CS | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124802 | Mandih CS | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 | 1 | UPGRADING | 1 | 640544.98 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124278 | Godod CS | GODOD | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124417 | Labason CS | LABASON | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124463 | Baybay CS | LILOY | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124454 | Liloy CS | LILOY | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124625 | Bacong CS | SALUG | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124623 | Salug CS | SALUG | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124830 | Siocon CS | SIOCON | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN | 3 | 1 | UPGRADING | 1 | 646551.25 |  | COMPLETED | 1 | 2018-11-09 |  |  |  | 2018-03-18 | 2018-03-26 | 2018-04-10 | 2018-04-25 | 2018-05-30 | MAQUESERG CONSTRUCTION AND GEN. MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1 | 1 | UPGRADING | 1 | 1060275 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1 | 1 | UPGRADING | 1 | 974850 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 | 1 | UPGRADING | 1 | 1015050 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125030 | Mate ES | DUMINGAG | 1 | 1 | UPGRADING | 1 | 547725 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 | 1 | UPGRADING | 1 | 547725 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 | 1 | UPGRADING | 1 | 1206000 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 345844 | LABANGAN SENIOR HIGH SCHOOL | LABANGAN | 1 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125183 | Lactayan ES | MAHAYAG | 1 | 1 | UPGRADING | 1 | 874350 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125190 | Pilas ES | MAHAYAG | 1 | 1 | UPGRADING | 1 | 407025 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | UPGRADING | 1 | 1125600 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303817 | Sominot NHS | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | UPGRADING | 1 | 849225 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1 | 1 | UPGRADING | 1 | 1100475 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303757 | Bayog NHS | BAYOG | 2 | 1 | UPGRADING | 1 | 1075350 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 124920 | Deporehan IES | BAYOG | 2 | 1 | UPGRADING | 1 | 532650 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 196004 | Lower Conacon ES | BAYOG | 2 | 1 | UPGRADING | 1 | 351750 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303770 | Dimataling NHS | DIMATALING | 2 | 1 | UPGRADING | 1 | 994950 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303771 | Dinas NHS | DINAS | 2 | 1 | UPGRADING | 1 | 1097460 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 124983 | Sumilom PS | DINAS | 2 | 1 | UPGRADING | 1 | 593250 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303778 | Guipos NHS | GUIPOS | 2 | 1 | UPGRADING | 1 | 1085400 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125104 | Mapao CPS | KUMALARANG | 2 | 1 | UPGRADING | 1 | 331650 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314249 | Poblacion Comprehensive NHS | LAKEWOOD | 2 | 1 | UPGRADING | 1 | 1100475 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303823 | Tubod NHS | LAKEWOOD | 2 | 1 | UPGRADING | 1 | 974850 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125152 | Cubo ES | LAPUYAN | 2 | 1 | UPGRADING | 1 | 407025 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | UPGRADING |  |  | REVERTED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314261 | Lapuyan National High School - Maralag Extension | LAPUYAN | 2 | 1 | UPGRADING | 1 | 530250 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 125161 | Mahalingeb PS | LAPUYAN | 2 | 1 | UPGRADING | 1 | 362250 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303783 | Kalian NHS | MARGOSATUBIG | 2 | 1 | UPGRADING | 1 | 859275 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303804 | Paulino Dari NHS | PITOGO | 2 | 1 | UPGRADING | 1 | 829125 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 | 1 | UPGRADING | 1 | 854250 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303813 | San Pablo NHS | SAN PABLO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Ext. | SAN PABLO | 2 | 1 | UPGRADING | 1 | 672000 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303768 | Tabina NHS | TABINA | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303800 | Nilo NHS | TIGBAO | 2 | 1 | UPGRADING | 1 | 844200 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region IX | Zamboanga del Sur | 303782 | Kabatan NHS | VINCENZO A. SAGUN | 2 | 1 | UPGRADING | 1 | 1226100 |  | COMPLETED | 1 | 2018-11-07 |  |  |  | 2018-04-17 | 2018-04-24 | 2018-05-17 | 2018-05-29 | 2018-07-04 | J.S ENGINEERING & MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125945 | Aseniero ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303876 | Aseniero NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303877 | Barcelona National High School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 934650.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125925 | Baylimango CS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303878 | Baylimango NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 899475.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125926 | Canlucani ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125939 | Dapitan City Experimental ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 2341708.56 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125916 | Ilaya ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 500675 | Kauswagan Integrated School | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125940 | Lawaan ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125948 | Opao ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125942 | Polo ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 303883 | Potungan NHS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 904500.03 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125952 | Sigayan ES | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125943 | Sinonoc ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125935 | Taguilon ES | DAPITAN CITY | 1 | 1 | UPGRADING |  | 650000.8 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dapitan City | 125936 | Tag-ulo Elementary School | DAPITAN CITY | 1 | 1 | UPGRADING | Batch 3 | 485000.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'l. Sci. HS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 1012893.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303886 | Cogon NHS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 570502.66 | 566769.16 | COMPLETED | 1 | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 125982 | Dipolog Pilot Demonstration School | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 459044.78 | 449907.21 | COMPLETED | 1 | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 125972 | Galas ES | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 464377.98 | 461753.52 | COMPLETED | 1 | 2019-12-23 | 2020-09-25 | [6 empty] | 2019-11-09 | Maqueserg Construction & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. HS | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 518849.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Dipolog City | 303891 | Punta National High School | DIPOLOG CITY (Capital) | 2 | 1 | UPGRADING |  | 560571.54 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 314603 | Baluno National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1572345.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126005 | Begang Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1423532.52 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126027 | Busay Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1534350.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126007 | Calvario Peak ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1129525.92 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1598589.1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1537113.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126020 | Kaumpurnah Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1166796.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126032 | Lanote ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1102386.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126023 | Malamawi Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1283313.99 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126034 | Maligue Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1102839.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126036 | Sumagdang ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1170819.16 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 126017 | Tabiawan ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING | Batch 3 | 1084294.14 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Isabela City | 133031 | Caro Elementary School | CITY OF ISABELA (Capital) | 1 | 1 | UPGRADING |  | 848184.23 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 126221 | Catalina Vda de Jalon MS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 1 | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303923 | Don Pablo A. Lorenzo MHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING | Batch 3 | 2010050.25 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 126261 | Zamboanga East CS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1144423.15 |  | COMPLETED | 1 | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303914 | Arena Blanco NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 1 | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 303922 | Maria Clara L. Lobregat NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1144423.15 |  | COMPLETED | 1 | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga City | 314801 | Talon-Talon NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1005025.12 |  | COMPLETED | 1 | [9 empty] | JS ENGG. MKTG. SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303720 | Rizal National High School | RIZAL | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124651 | Sergio Osmeña Central School | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 1 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124525 | Linay CS | MANUKAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | UPGRADING |  | 1409686.31 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3 | 1 | UPGRADING |  | 2130358.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303721 | Salug National High School | SALUG | 3 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | UPGRADING |  | 699566.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | UPGRADING |  | 694290.39 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | UPGRADING |  | 1399133.55 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1 | 1 | UPGRADING | Batch 3 | 1850000 |  | COMPLETED | 1 |  |  |  |  | 2019-07-17 | 2019-08-02 | 2019-08-14 | 2019-08-26 |  | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 314203 | BONIAO NATIONAL HIGH SCHOOL | MAHAYAG | 1 | 1 | UPGRADING |  | 1600000 |  | COMPLETED | 1 | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303796 | Midsalip NHS- Main | MIDSALIP | 1 | 1 | UPGRADING |  | 1766000 |  | COMPLETED | 1 | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303814 | SAPA ANDING AGRICULTURAL VOCATIONAL TECHNICAL SCHOOL | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | UPGRADING |  | 1659000 |  | COMPLETED | 1 | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303811 | Tukuran Tech. Voc'l. HS | TUKURAN | 1 | 1 | UPGRADING |  | 1521000 |  | COMPLETED | 1 | 2020-01-26 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303774 | Dumalinao NHS | DUMALINAO | 2 | 1 | UPGRADING |  | 2092000 |  | COMPLETED | 1 | 2019-12-27 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303808 | Rebokon AVHS | DUMALINAO | 2 | 1 | UPGRADING |  | 1501000 |  | COMPLETED | 1 | 2019-12-27 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-19 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303784 | Kumalarang NHS | KUMALARANG | 2 | 1 | UPGRADING |  | 1672000 |  | COMPLETED | 1 | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303788 | Lapuyan NHS | LAPUYAN | 2 | 1 | UPGRADING | Batch 3 | 1580000 |  | COMPLETED | 1 |  |  |  |  | 2019-07-17 | 2019-08-02 | 2019-08-14 | 2019-08-26 |  | MAQUESERG CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303822 | Toribio Minor NHS | MARGOSATUBIG | 2 | 1 | UPGRADING |  | 1654000 |  | COMPLETED | 1 | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga del Sur | 303791 | Betinan NHS | SAN MIGUEL | 2 | 1 | UPGRADING |  | 1524000 |  | COMPLETED | 1 | 2019-12-21 |  |  |  | 2018-10-24 | 2018-11-06 | 2018-11-27 | 2018-12-12 | 2019-08-14 | BDV CONSTRUCTION & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303824 | ALICIA NHS | Alicia | 1 | 1 | UPGRADING |  | 4847218.66 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303825 | DAWA-DAWA NHS | Alicia | 1 | 1 | UPGRADING | Batch 3 | 3684763.21 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303829 | BUUG NHS | BUUG | 1 | 1 | UPGRADING | Batch 3 | 5650378.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303828 | DIPLAHAN NHS | DIPLAHAN | 1 | 1 | UPGRADING | Batch 3 | 3089516.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 314314 | DITAY NHS | DIPLAHAN | 1 | 1 | UPGRADING |  | 445687.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303837 | IMELDA NHS | IMELDA | 1 | 1 | UPGRADING |  | 3077673.45 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial HS | MABUHAY | 1 | 1 | UPGRADING |  | 726852.11 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303852 | MABUHAY NHS | MABUHAY | 1 | 1 | UPGRADING | Batch 3 | 2581516.65 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303845 | MALANGAS NHS | MALANGAS | 1 | 1 | UPGRADING |  | 2901868.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303851 | OLUTANGA NHS | OLUTANGA | 1 | 1 | UPGRADING |  | 2532995.73 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303856 | PAYAO NHS | PAYAO | 1 | 1 | UPGRADING | Batch 3 | 3031211.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303854 | ZAMBOANGA SIBUGAY NHS | IPIL | 2 | 1 | UPGRADING |  | 3089516.4 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303827 | Francisco Ramos NHS | KABASALAN | 2 | 1 | UPGRADING |  | 2072864.62 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303872 | TITAY NHS | TITAY | 2 | 1 | UPGRADING |  | 1140480.91 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2022 |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303859 | PIONEER NHS | TUNGAWAN | 2 | 1 | UPGRADING |  | 411731.69 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region IX | Zamboanga Sibugay | 303874 | TUNGAWAN NHS | TUNGAWAN | 2 | 1 | UPGRADING |  | 1927052.86 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 303879 | Dakak NHS | Dapitan City | 1 | 1 | UPGRADING |  | 2428476.92 | 2421854.57 | COMPLETED | 1 | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-015 | 2020-09-002 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 125938 | Dapitan City Central School | Dapitan City | 1 | 1 | UPGRADING |  | 2401488.84 | 2397806.37 | COMPLETED | 1 | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-013 | 2020-09-001 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 125949 | Potungan CS | DAPITAN CITY | 1 | 1 | UPGRADING |  | 555088.13 | 538357.75 | COMPLETED | 1 | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-001 | 2020-07-017 | 2020-08-04 | 2020-08-11 | 2020-10-08 | 2021-07-06 | 2021-10-06 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dapitan City | 303884 | Sulangon NHS | Dapitan City | 1 | 1 | UPGRADING |  | 1055605.94 | 1047599.32 | COMPLETED | 1 | 26/09/2021 | 26/09/2021 | Elec2020-R IX-DAPITAN CITY-016 | 2020-09-001 | 30/11/2019 | 2019-07-12 | 23/12/2019 | 14/09/2020 | 28/09/2020 | MAQUESERG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dipolog | 125972 | GALAS ES | DIPOLOG CITY (Capital) | 2 | 1 | CONNECTION TO GRID |  | 336785.55 | 334127.34 | COMPLETED | 1 | 2020-11-01 | 2020-11-01 | Elec2020-RIX-Dipolog City-001 | DepEd-20-IX-Dip-Electrification-Galas ES | 2020-02-12 | 2020-02-20 | 2020-03-04 | 2020-09-16 | 2020-10-01 | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Dipolog | 125973 | MAGSAYSAY ES | DIPOLOG CITY (Capital) | 2 | 1 | CONNECTION TO GRID |  | 352333.99 | 351065.88 | COMPLETED | 1 | 2020-11-01 | 2020-11-01 | Elec2020-RIX-Dipolog City-003 | DepEd-20-IX-Dip-Electrification-Magsaysay ES | 2020-02-12 | 2020-02-20 | 2020-03-04 | 2020-09-16 | 2020-10-01 | MAQUESERG CONSTRUCTION & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | ENERGIZATION |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 314602 | Calvario Peak National High School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1771369.36 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126030 | Campo Barn Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1614846.64 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 303899 | Kumalarang NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1695111.32 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126011 | Latuan Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1580611.32 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-007 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 126024 | Marang Marang ES | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1541507.12 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-008 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Isabela City | 303898 | Tandung Ahas NHS | CITY OF ISABELA (Capital) | 0 | 1 | UPGRADING |  | 1188377.64 |  | COMPLETED | 1 |  |  | Elec2020-R IX-Isabela City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126062 | Dominador Yocogo Sr. ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 949924.61 | 947680.75 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-003 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126089 | Kahayagan ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 875691.26 | 874881.35 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-017 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 126064 | Lenienza ES | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1152429.2 | 1149205.1 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-006 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 314704 | Pagadian Science HS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1910916.87 | 1910199.19 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-011 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 314703 | Tulawas IS | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 1795381.01 | 1794735.05 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-015 | DepEd-Elec-2020-IX-PAG-2 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | JJFY CONST. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 303913 | ZSSAT | PAGADIAN CITY (Capital) | 1 | 1 | UPGRADING |  | 2076882.04 | 2070159.48 | COMPLETED | 1 | 2021-02-01 | 2021-02-01 | Elec2020-RIX-Pagadian City-016 | DepEd-Elec-2020-IX-PAG-1 | 2019-11-29 | 2019-12-09 | 2019-12-23 | 2020-03-05 | 2020-09-24 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Pagadian City | 303913 | ZSSAT | PAGADIAN CITY (Capital) | 1 |  |  |  | 1758285.76 | 1757058.54 | COMPLETED | 1 | 2021-08-27 | 2021-08-27 | Elec2020-RIX-Pagadian City-009 | DepEd-Elec-2020-IX-PAG-3 | 2020-10-01 | 2020-10-08 | 2020-10-20 | 2020-11-11 | 2021-06-09 | ALIÑAB CONST. & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1600000 | 1597362.46 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-005 | ZC-ELEC-2020-02 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303924 | Ramon Enriquez HS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1400000 | 1397175.24 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-016 | ZC-ELEC-2020-04 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303943 | Regional Science HS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1200000 | 1197298.55 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-023 | ZC-ELEC-2020-06 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126104 | Sinunuc ES | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 2200000 | 2197363.75 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-002 | ZC-ELEC-2020-01 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126220 | Sta. Maria CS SPED Center | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1600000 | 1597972.47 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-010 | ZC-ELEC-2020-05 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 314807 | Tulungatung NHS | ZAMBOANGA CITY | 1 | 1 | UPGRADING |  | 1200000 | 1197793.24 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-025 | ZC-ELEC-2020-03 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303917 | Bolong NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1796813.9 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-015 | ZC-ELEC-2020-07 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 314802 | Lubigan NHS, Curuan Annex | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1200000 | 1197298.55 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-024 | ZC-ELEC-2020-08 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303930 | Sangali NHS | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1650685.58 | COMPLETED | 1 | 2020-11-24 | 2020-11-30 | Elec2020-R IX-Zamboanga City-017 | ZC-ELEC-2019 SAVING | 2020-07-07 | 2020-07-14 | 2020-07-28 | 2020-08-18 | Sept 10,2020 | JS ENGINEERING AND MARKETING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 126229 | Tetuan Central School | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 1800000 | 1794918.54 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-014 | ZC-ELEC-2020-09 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga City | 303940 | Zamboanga City HS, Main | ZAMBOANGA CITY | 2 | 1 | UPGRADING |  | 3700000 | 3693624.79 | COMPLETED | 1 | 2020-12-14 | 2020-12-28 | Elec2020-R IX-Zamboanga City-021 | ZC-ELEC-2020-10 | 2020-07-27 | 2020-08-11 | 2020-08-25 | SEPT 10,2020 | SEPT 21,2020 | GHR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314105 | Polanco NHS Ext. - ISIS | POLANCO | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-001 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303725 | SAN PEDRO NHS | POLANCO | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-002 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303726 | SEBACA NHS | RIZAL | 1 | 1 | UPGRADING |  | 739403.2 | 738188 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-003 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303723 | San Isidro NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-006 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303724 | San Jose NHS | SERGIO OSMEÑA SR. | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-007 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303694 | KANIM NHS | SIBUTAD | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-004 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303695 | SAWANG NHS | SIBUTAD | 1 | 1 | UPGRADING |  | 744653.2 | 742388 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-005 | CID-2020-003 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303709 | MANAWAN NHS | JOSE DALMAN (PONOT) | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-014 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303698 | DON TEOTIMO Z. OCHOTORENA NHS | KATIPUNAN | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-009 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 124381 | Malugas ES | KATIPUNAN | 2 | 1 | UPGRADING |  | 947000 | 851148 | COMPLETED | 1 | 2021-03-17 | 2021-03-05 | Elec2020-R IX-Zamboanga Del Sur-001 | ELEC-2020-BEFF-RIX ZDN | 2019-11-27 | 2020-02-28 | 2020-03-12 | 2020-03-16 | Sept. 16, 2020 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314104 | Matam NHS | KATIPUNAN | 2 | 1 | UPGRADING |  | 744653.2 | 743273 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-008 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314115 | GODOD NHS- SIANAN | GODOD | 3 | 1 | UPGRADING |  | 755153.2 | 753773 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-025 | CID-2020-004 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 15, 2020 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 314107 | Cawit-Cawit National High School | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-037 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303708 | Malayal NHS | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-038 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303735 | Sibuco NHS Annex - Lunday | SIBUCO | 3 | 1 | UPGRADING |  | 791903.2 | 787798 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-036 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 | 1 | UPGRADING |  | 781403.2 | 777806 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-035 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Norte | 303743 | Dacon National High School (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | UPGRADING |  | 770903.2 | 766149 | COMPLETED | 1 | 2021-03-17 | 2021-02-26 | Elec2020-RIX-Zamboanga Del Norte-033 | CID-2020-005 | 2019-11-22 | Nov.25, 2019 | 2019-12-11 | 2019-12-16 | Sept. 16, 2020 | CCO ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1 | 1 | UPGRADING |  | 3012000 | 2625502.7 | COMPLETED | 1 | 2021-04-27 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-003 | ZDS-20-E-02 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | RAKZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | UPGRADING |  | 2612000 | 2244500.05 | COMPLETED | 1 | 2021-04-27 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-004 | ZDS-20-E-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | JJFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga del Sur | 314217 | Bibilik NHS | DUMALINAO | 2 | 1 | UPGRADING |  | 1750000 | 1502483.79 | COMPLETED | 1 | 2021-03-28 | 2022-08-08 | Elec2020-R IX-Zamboanga Del Sur-005 | ZDS-20-E-01 | 2019-11-28 | 2019-12-09 | 2019-12-23 | 2020-02-20 | 2020-10-29 | JJFY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | 8.22 | UPGRADING | BBM JULY 2022-DEC2022 |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125510 | Alicia CES | ALICIA | 1 | 1 | UPGRADING |  | 410723.03 | 410563.18 | COMPLETED | 1 | Sept. 27, 2021 | - | Elec2020-R IX-Zamboanga Sibugay-001 | ZSY-2020Eadd-01 | 2021-04-20 | 2021-04-28 | 2021-05-10 | 2021-06-23 | 2021-06-29 | CPAN Engineering and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 | 5.24 | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125566 | Diplahan CES | Diplahan | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-004 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125673 | Mabuhay CES | Mabuhay | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-006 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125743 | Olutanga CES | OLUTANGA | 1 | 1 | UPGRADING |  | 435923.03 | 376500.98 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-009 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125774 | Payao CES | PAYAO | 1 | 1 | UPGRADING |  | 409673.03 | 354983.7 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-010 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125617 | Ipil CES | IPIL | 2 | 1 | UPGRADING |  | 443459.47 | 384984.19 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-012 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 196519 | Ipil SPED School | IPIL | 2 | 1 | UPGRADING |  | 409673.03 | 356314.16 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-013 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125804 | Surabay CES | ROSELLER LIM | 2 | 1 | UPGRADING |  | 445787.53 | 387074.19 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-018 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 303864 | Siay NHS | SIAY | 2 | 1 | UPGRADING |  | 1063897.79 | 913527.99 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-024 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region IX | Zamboanga Sibugay | 125882 | Titay CES | TITAY | 2 | 1 | UPGRADING |  | 447887.53 | 387074.15 | COMPLETED | 1 | 2021-04-10 | 2021-04-10 | Elec2020-R IX-Zamboanga Sibugay-021 | n.a | 2020-01-08 | 2020-01-16 | 2020-02-03 | 2020-03-04 | 2020-12-03 | Maqueserg Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Norte | 124614 | Sipaon ES | RIZAL | 1st | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1st | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga del Sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2nd | 1 | Solar PV System (On Grid) | 1 | 2995178.49 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 5.24 | previous years | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2023 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1st | 1 | Solar PV System (Off-grid or On-grid) | 1 | 3000000 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 5.24 | SOLAR | bbm 2023 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Dapitan City | 501790 | Selinog IS | DAPITAN CITY | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3054986.49 | 3012306.2 | COMPLETED | 1 | August 29, 2024 | - | SDODAP-INFRA-2023-006 | SDODAP-INFRA-2023-006 | November 14, 2023 | November 21, 2023 | December 07, 2023 | June 10, 2024 | June 14, 2024 | MORTE CONSTRUCTION | Island school - limited accessibility going to school site | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 2.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Dipolog City | 197502 | Kepiyanan Elementary School | DIPOLOG CITY | 2nd | 1 | For Supply and installation of Solar PV Energy System | 1 | 3490869.25 | 3206594.87 | COMPLETED | 1 | August 29, 2024 | 2024-10-25 | INFRA-January2024-01 | ELEC2024-RIX-DIPOLOGCITY | January 09, 2024 | January 05, 2024 | January 30, 2024 | May 21, 2024 | May 31, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3027278.06 | 2534155.19 | COMPLETED | 1 | 2024-12-10 | - | INFRAEPA2024-02 | - | - | - | 2023-12-04 | 2024-05-13 | September 10,2024 | CLA ONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | SOLAR | BBM 2025 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Pagadian City | 303902 | Lourdes National High School | PAGADIAN CITY (Capital) | 1st | 1 | Solar PV Power Off-Grid or On-Grid | 1 | 3012633.52 | 3000682 | COMPLETED | 1 | August 17, 2024 | - | ELEC-2024-RIX-PAGADIANCITY-01 | ELEC-2024-RIX-PAGADIANCITY-01 | November 13, 2023 | November 21, 2023 | December 04, 2023 | December 11, 2023 | June 03, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | SOLAR | BBM 2024 SOLAR |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 124659 | LEBOTE ES | SERGIO OSMEÑA SR. | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5696151.71 | 5663568.2 | COMPLETED | 1 | August 27, 2024 | - | 2024-007-CBZN | CB-2024-021 | December 14, 2023 | December 21, 2023 | January 03, 2024 | January 10, 2024 | May 27, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 501156 | BULAWAN INTEGRATED SCHOOL | KATIPUNAN | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5630939.28 | 5612008.6 | COMPLETED | 1 | August 27, 2024 | - | 2024-008-CBZN | CB-2024-022 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 27, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Norte | 124447 | CAUSWAGAN ES | LILOY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 5699878.14 | 5682921.41 | COMPLETED | 1 | July 27, 2024 | - | 2024-009-CBZN | CB-2024-023 | November 21, 2023 | November 24, 2023 | December 07, 2023 | December 22, 2023 | May 27, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 9.24 | ENERGIZATION | BBM 2024 ONGRID |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Sur | 303786 | Lantungan National High School | AURORA | 1st | 1 | Electrification and Modernization of Electrical Systems in various Schools (Single Phase) | 1 | 2276315.86 | 2111249.23 | COMPLETED | 1 | August 27, 2024 | 2024-10-21 | ZDS-24-E-01 | ZDS-24-E-01 | November 13, 2023 | November 21, 2023 | December 4, 2023 | January 03, 2024 | May 29, 2024 | CPAN ENGINEERING & ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga del Sur | 303769 | Culabay NHS | TABINA | 2nd | 1 | Electrification and Modernization of Electrical Systems in various Schools (Single Phase) | 1 | 3223678.46 | 3054897.86 | COMPLETED | 1 | August 27, 2024 | 2024-10-23 | ZDS-24-E-02 | ZDS-24-E-02 | November 13, 2023 | November 21, 2023 | December 4, 2023 | January 03, 2024 | May 29, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga Sibugay | 125538 | Agutayan ES | Buug | 1st | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 1951565.58 | 1803105.87 | COMPLETED | 1 | September 30, 2024 | 2024-10-25 | ZSY-2024ELEC-01 | ZSY-2024ELEC-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | July 03, 2024 | ELETTRO ENGINEERING ENTERPRISES | - | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 10.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2024 | Region IX | Zamboanga Sibugay | 196512 | Logdeck PS | Kabasalan | 2nd | 1 | Upgrading and Modernization of Electrical System On-Grid | 1 | 1881036.92 | 1716664.17 | COMPLETED | 1 | September 30, 2024 | - | ZSY-2024ELEC-02 | ZSY-2024ELEC-02 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | July 03, 2024 | ELETTRO ENGINEERING ENTERPRISES | Logistical constraints apply due to the four (4) - hour walking distance and difficult terrain | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 11.24 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%