## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45 | Status as of July 4, 2025
QRF 2020 | Region IX | Zamboanga del Norte | 303711 | Don Jose Aguirre NHS | MANUKAN | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8866108.44 | 1 | 8808680.91 | Completed | 1 | 2020-12-31 | 2020-12-16 | QRF 2020-RIX-ZDN | QRF 2020-RIX-ZDN-001 | 2020-04-15 | April 24, 2020 | May 7, 2020 | May 26, 2020 | June 15, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 18706024.7 | 1 | 18597394.16 | Completed | 1 | 2020-12-31 | 2020-12-16 | QRF 2020-RIX-ZDN | QRF 2020-RIX-ZDN-002 | 2020-04-15 | April 24, 2020 | May 7, 2020 | May 26, 2020 | June 15, 2020 | YSL BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2021 | Region IX | Zamboanga del Norte | 124753 | Sipaloc ES | SIBUTAD | 1 | 1 | 2 | FIRE INCIDENT | 4553463.46 | 1 | 4541309.89 | Completed | 1 | 2021-11-07 | 2021-11-17 | QRF 2022 RIX - ZAMBOANGA DEL NORTE | QRF 2022 RIX-ZDN-01 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-06-28 | July 6, 2021 | July 6, 2021 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124541 | New Siquijor ES | MUTIA | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2256282.5094 | 1 | 2251032.51 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 | 2023-03-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124738 | Bagacay ES | SIBUTAD | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2846844.2811 | 1 | 2841594.28 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124740 | Calilic ES | SIBUTAD | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1661419.86 | 1 | 1659319.86 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124742 | Delapa ES | SIBUTAD | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1677169.86 | 1 | 1675069.86 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124743 | Kanim ES | SIBUTAD | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2774392.3764 | 1 | 2769142.38 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4547777.0333 | 1 | 4547777.03 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124802 | Mandih CS | SINDANGAN | 2 | 1 | 6 | REPAIR/ REHABILITATION | 3444320.6957 | 1 | 3443315.59 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | MJMARI Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124417 | Labason CS | LABASON | 3 | 1 | 8 | REPAIR/ REHABILITATION | 4503127.9593 | 1 | 4502127.32 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | MJMARI Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124625 | Bacong CS | SALUG | 3 | 1 | 6 | REPAIR/ REHABILITATION | 3348970.27 | 1 | 3338470.27 | Completed | 1 | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2023 | Region IX | Dapitan City | 125916 | Ilaya Elementary School | DAPITAN CITY | 1st | 1 | 10 | 2STY10CL | 32421818.5311 | 2- NC | 32327913.17 | Ongoing | 0.79 | 2024-08-01 |  | SDODAP-INFRA-2023-003 | SDODAP-INFRA-2023-003 | 2023-11-14 | 2023-11-21 | 2023-12-07 | 2023-12-22 | 2024-01-03 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0.79 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region IX | Dapitan City | 125919 | Oyan Elementary School | DAPITAN CITY | 1st | 1 | 4 | 1STY4CL | 21233503.4667 | 2- NC | 21363407.93 | completed | 1 | 2024-07-01 |  | SDODAP-INFRA-2023-002 | SDODAP-INFRA-2023-002 |  | 2023-11-21 | 2023-12-07 | 2023-12-22 | 2024-01-03 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4.24 |  |  |  |  | REPLACEMENT | completed
QRF 2023 | Region IX | Dapitan City | 125919 | Oyan Elementary School | DAPITAN CITY | 1st |  | 3 | REPAIR OF CLASSROOMS | 2524721.336 | 2-R | 2488604.93 | Completed | 1 | 2024-03-20 | 2024-03-18 | SDODAP-INFRA-2023-001 | SDODAP-INFRA-2023-001 |  | 2023-11-21 | 2023-12-07 | 2023-12-22 | 2024-01-03 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2024 | Region IX | Zamboanga Del Norte | 124575 | Lingasad ES | POLANCO | 1st | 1 | 6 | 2STY6CL with PWD ramp with handrails, parapet all on concrete gutter and complete with Electrical works, Sanitary/plumbing works, Ventilation, Water pumping and Fire protection systems | 24877957.84 | 1- NC | 24837942.65 | Ongoing | 0.7 | - | - | 2024-049-CBZN | CB-2024-043 | - | Aug. 01, 2024 | Aug. 14, 2024 | Sept. 5, 2024 | Sept. 10, 2024 | YSL BUILDERS |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0.7 | 0 |  |  | Fire |  |  |  | REPLACEMENT | Ongoing

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%