## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 1st | 1 |  | Construction of School Clinic | 3957175.63 |  | 2501064.38 | COMPLETED | 1 | November 8, 2024 | November 7, 2024 | DepED-RO6-D1-2024-BEFF-HEALTHFACILITIES-057-2024 | DepED-RO6-D1-2024-BEFF-HEALTHFACILITIES-057-2024 | November 14, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2023 | 5/17.2024 | NEM CONSTRUCTION SUPPLIES & SERVICES | Completed
SCHOOL HEALTH FACILITIES 2024 | Region VI | Antique | 115268 | Panpanan I ES | SAN REMIGIO | Lone | 1 |  | Construction of School Clinic | 4520316.75 |  | 3355352.91 | ongoing | 0.34 | November 27, 2024 |  | R6-D2-GAA2024-08-SHF | R6-D2-GAA2024-08-SHF | January 26, 2024 | February 2, 2024 | February 16, 2024 | April 5, 2024 | July 19, 2024 | MDG Const. & Supply | Already issued ressumption Order last Febryary 24, 2025
SCHOOL HEALTH FACILITIES 2024 | Region VI | Bacolod City | 302714 | Mansilingan Agro-Industrial High School | BACOLOD CITY (Capital) | Lone | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2200000 | ongoing | 0.45 | June 11, 2025 |  | HEALTH FACILITIES 2024 - REGION VI - BACOLOD -001 | R6BCD08182024-P129 | August 19, 2024 | August 27, 2024 | September 10, 2024 | October 4, 2024 | February 5, 2025 | KEANNE CONSTRUCTION SERVICES | with request for time extension
SCHOOL HEALTH FACILITIES 2024 | Region VI | Bago City | 117523 | Ma-ao Elementary School | BAGO CITY | 4th | 1 |  | Construction/Repair of Health Facilities | 2510592.22 |  |  | Under Procurement | 0 | [10 empty] | For Posting of Advertisement for interested Bidders
SCHOOL HEALTH FACILITIES 2024 | Region VI | Capiz | 115413 | Balingasag Elementary School | CUARTERO | 2nd | 1 |  | Construction/Repair of Health Facilities | 5440093.41 |  | 3474057.78 | COMPLETED | 1 | March 8, 2025 | February 25, 2025 | R6-DEPED-CAPIZ-CY2024-BEFF-BALINGASAGES-LOT3 | CB No. 2024-034 | June 28, 2024 | July 10, 2024 | July 22, 2024 | August 15, 2024 | October 3, 2024 | MARIZALOI CONSTRUCTION | Completed
SCHOOL HEALTH FACILITIES 2024 | Region VI | Escalante City | 117055 | Dian-ay Elementary School | CITY OF ESCALANTE | 1st | 1 |  | Construction/Repair of Health Facilities | 4012106.54 |  | 3950000 | completed | 1 | October 25, 2024 | February 3, 2025 | Health Facilities-Region VI- Escalante City-002 | 2024-004 | December 6, 2023 | December 15, 2023 | December 27, 2024 | December 29, 2023 | June 24, 2024 | Valkyrie Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | Region VI | Iloilo | 311017 | Bancal NHS | ALIMODIAN | 2nd | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2442997.42 | ongoing | 0.76 | July 28, 2025 |  | BEEF2024-RVI-022-ILOILO-CLINIC-L1 | BEEF2024-RVI-022-ILOILO-CLINIC-L1 | August 7, 2024 | August 14, 2024 | August 30, 2024 | October 4, 2024 | December 23, 2024 | Marissa's Construction | With time extension
SCHOOL HEALTH FACILITIES 2024 | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | Lone | 1 |  | Construction/Repair of Health Facilities | 2513797.56 |  | 2250687.5 | ongoing | 0 | October 29, 2025 |  | NONE | 2024-12-001 | October 15, 2024 | October 22, 2024 | November 5, 2024 | December 4, 2024 | March 27, 2025 | URBANCON Builders & Supply | Processing of Permits | URBANCON Builders & Supply
SCHOOL HEALTH FACILITIES 2024 | Region VI | Kabankalan City | 117836 | Carol-an Elementary School | CITY OF KABANKALAN | 6th | 1 |  | Construction/Repair of Health Facilities | 2980787.62 |  | 2978318.85 | Completed | 1 | February 14, 2025 | February 10, 2025 | 2024-SB-01-PB001 | 2024-019 | July 10, 2024 | July 17, 2024 | July 31, 2024 | September 24, 2024 | October 15, 2024 | Rism BUILDERS AND CONSTRUCTION SERVICES, INC. | completed
SCHOOL HEALTH FACILITIES 2024 | Region VI | Negros Occidental | 311104 | Efegenio Lizares National High School | CITY OF TALISAY | 3rd | 1 |  | Construction/Repair of Health Facilities | 3308711.07 |  | 2534432.95 | Completed | 1 | December 13, 2024 | December 19, 2024 | 24-09-001 | 12016 | November 11, 2023 | November 27, 2023 | December 11, 2023 | July 25, 2024 | August 30, 2024 | Sunshine Sapphire Construction And Supply Inc | Completed
SCHOOL HEALTH FACILITIES 2024 | Region VI | Passi City | 302806 | Efraim M. Santibañez National High School | CITY OF PASSI | 4th | 1 |  | Construction/Repair of Health Facilities | 4426340.48 |  | 3385971.76 | Completed | 1 | December 8, 2024 | December 2, 2024 | BEFF-PSHF | RO6-D14-FY2024-BEFF-CHF-EMSNHS | February 12, 2024 | February 21, 2024 | March 3, 2024 | April 5, 2024 | July 4, 2024 | Early Riser Construction | 100% disbursement
SCHOOL HEALTH FACILITIES 2024 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 2389970.5 |  | 2357719.21 | not yet started | 0 |  |  | 2025-005 | CON-2025-005 | March 3, 2025 | March 11, 2025 | March 25, 2025 | March 31, 2025 |  | Reubin L. Yap, Contractor | RTA send to C.O last May 20, 2025 waiting for Sub-ARO
SCHOOL HEALTH FACILITIES 2024 | Region VI | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2nd | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2493000 | ongoing | 0.8 | June 15, 2025 |  | CPB-INFRA-04-2024 | CPB-INFRA-04-2024 | July 23, 2024 | July 30, 2024 | August 12, 2024 | September 28, 2024 | January 6, 2025 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Ongoing
SCHOOL HEALTH FACILITIES 2024 | Region VI | San Carlos City | 117747 | Greenville Elementary School | SAN CARLOS CITY | 1st | 1 |  | Construction/Repair of Health Facilities | 2732388.66 |  | 2700000 | Completed | 1 | November 8, 2024 | October 21, 2024 | 202310-0093 | 10388986-2023-10-0093 | December 14, 2023 | December 18, 2023 | December 27, 2023 | January 18, 2024 | May 24, 2024 | Valkyrie Construction | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VI | Silay City | 117814 | Eustaquio Lopez Elementary School | SILAY CITY | 3rd | 1 |  | Construction/Repair of Health Facilities | 2980787.62 |  | 2930085.02 | ongoing | 0.72 | May 6, 2025 |  | 2024-07-ELES-001 | 2024-C-006 | June 29, 2024 | July 7, 2024 | July 22, 2024 | August 6, 2024 | January 6, 2025 | CGGFR Constrcution and Construction Supply
SCHOOL HEALTH FACILITIES 2024 | Region VI | Victorias City | 117430 | Doña Andrea Palanca ES | CITY OF VICTORIAS | 3rd | 1 |  | Construction/Repair of Health Facilities | 3225253.91 |  | 1687612.07 | COMPLETED | 1 | September 28, 2024 | August 16, 2024 | School Clinic-01Carcar | BEFF 2024-REpair of Classroom to be used / convered to School Clinic (7.00mx9.00m) at Perrelos Elementary School | March 13, 2024 | March 19, 2024 | April 3, 2024 | April 17, 2024 | June 21, 2024 | A.O.S. Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 114701 | Bagongbayan Elementary School | Buruanga | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 627587.16 | BATCH 1 |  | Completed | 1 | 2022-10-14
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 302318 | BURUANGA NATIONAL HIGH SCHOOL | Buruanga | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 630917.76 | BATCH 1 |  | completed | 1 | 2022-08-06 | 2023-03-01 | DepED-RO6-D1-2022WATSAN-013-2022 | DepED-RO6-D1-2022WATSAN-013-2022 | 2022-03-08 | 2022-03-15 | 2022-03-28 | 2022-04-07 | 2022-06-15 | SOLID MERCHANDISING
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 302304 | Catalino M. Prado NHS | Lezo | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 634502.46 | BATCH 1 |  | Completed | 1 | 2022-09-26
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 114934 | Tagas Elem. School | Tangalan | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 605906.24 | BATCH 1 |  | Completed | 1 | 2022-10-14
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 501181 | Vivo Integrated School | Tangalan | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 614740.94 | BATCH 1 |  | Completed | 1 | 2022-10-14
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 114973 | Belison CS | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 114976 | Concepcion ES | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302347 | Belison NS | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115130 | Libertad Central School | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115133 | Paz ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 148181.01 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115136 | San Roque ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115138 | Tinigbas ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200217.28 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115140 | Union ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302363 | Libertad NVS | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302383 | Union NHS | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 |  | Completed | 1 | 2022-08-19 | 2022-08-17 | R6-D2-2022BEFF-04-HWF | R6-D2-2022BEFF-04-HWF | 2022-03-17 | 2022-03-24 | 2022-04-07 | 2022-04-28 | 2022-06-14 | Nesmark Construction and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115851 | Fiscal Jose M. Zambarrano, Sr. Memorial School | San Lorenzo (Buenavista III) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) with Rain Water Collector | 413873.68 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  | 03-2002-lot3 | No.-03-C-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-10-03 | Early Riser Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115857 | Silvestra Galarpe Melgar Memorial School | San Lorenzo (Buenavista III) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) with Rain Water Collector | 413873.68 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  | 03-2002-lot3 | No.-03-C-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-10-03 | Early Riser Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115849 | Constancia Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2324096.02 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115850 | Doña Lucia C. Locsin Memorial School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2361288.64 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115854 | San Enrique Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2342692.33 | BATCH 2 | 2320995.12 | Completed | 1 | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2370586.79 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2351990.84 | BATCH 2 | 2320995.12 | Completed | 1 | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116107 | Cairohan PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225574.55 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-22 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116109 | Guinhulacan ES | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225034.27 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-22 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116111 | Maganhop PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226924.27 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-22 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226414.55 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-22 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116594 | Abat Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221494.83 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-16 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116595 | Agmanaphao Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226278.99 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-16 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116600 | Dala-Singay Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228573.71 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-16 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116604 | Tipolo Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228033.43 | BATCH 1 |  | Completed | 1 | 2023-03-22 | 2023-03-16 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | BEFF2022-RVI-022-ILOILO-WATSAN-B1L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | 2022-08-08 | 2022-11-22 | Wilkinson Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116092 | Batad CES | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226338.15 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116096 | Calangag PS | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221630.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116101 | Tanao ES | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 224839.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 501483 | Bulak Integrated School | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 229098.71 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 501484 | Embarcadero Integrated School | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227328.99 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116759 | Aripdip Elementary School | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223848.71 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116762 | Calaigang ES | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225093.43 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116768 | San Rafael CS | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218869.83 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222603.99 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116090 | Alapasco Primary School | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | completed | 1 | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116091 | Banban PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-06 | 2023-06-30 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227659.27 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 180021 | Sta. Ana PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 1 | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-15 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116113 | Ngingi-an PS | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-16 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116116 | Tapacon Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116603 | Nasirum Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116763 | Ilongbukid E/S | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116767 | San Florentino ES | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115849 | Constancia Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2324096.02 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115850 | Doña Lucia C. Locsin Memorial School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2361288.64 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115854 | San Enrique Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2342692.33 | BATCH 2 | 2320995.12 | Completed | 1 | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2370586.79 | BATCH 2 | 2334753.36 | Completed | 1 | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2351990.84 | BATCH 2 | 2320995.12 | Completed | 1 | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116090 | Alapasco Primary School | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | completed | 1 | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116091 | Banban PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-06 | 2023-06-30 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227659.27 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 180021 | Sta. Ana PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 1 | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-15 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116113 | Ngingi-an PS | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-16 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116116 | Tapacon Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1 | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116603 | Nasirum Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | Completed | 1 | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116763 | Ilongbukid E/S | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116767 | San Florentino ES | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%