## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | Unnamed: 45 | Status as of July 4, 2025
GABALDON 2020 | Region VII | Bohol | 118106 | Tultugan ES | CALAPE | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6655556.76 | 1 |  | COMPLETED | 1 | [6 empty] | January 20, 2021 | [14 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Bohol | 118504 | Sto. Niño Dela Paz ES | LOON | 1 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5424493.98 | 1 | 5404011.5 | Completed | 1 | 2021-12-15 |  | 6944754-Lot 1 | 44320 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 19, 2021 | ELEEO CONSTRUCTION AND SUPPLY | [11 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region VII | Bohol | 118065 | Dagohoy Central Elementary | BUENAVISTA | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 4447691.3 | 1 | 4401399.38 | COMPLETED | 1 | 2021-12-08 |  |  | 44321 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-04 | C. JANSEN CONSTRUCTION AND GENERAL MERCHANDISE | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Bohol | 118358 | Guindulman Central ES | GUINDULMAN | 3 | 1 | 17 | 1 | Rehabilitation of Gabaldon Building | 17354037.14 | 1 | 13669174.29 | COMPLETED | 1 | 2022-09-30 |  | 6944754-Lot 3 | 44324 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 30, 2021 | JY BONTILAO CONSTRUCTION AND ENTERPRISE | [11 empty] | 1 |  |  | previous yrs |  | CY 2022 |  |  | COMPLETED
GABALDON 2020 | Region VII | Carcar City | 119170 | Valladolid Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7095987.75 | 1 |  | COMPLETED | 1 | [6 empty] | January 20, 2021 | [14 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 9684010.33 | 1 | 6905228.73 | Completed | 1 | 2022-10-30 |  | 6944754-Lot 4 | 44325 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-25 | JY BONTILAO CONSTRUCTION AND ENTERPRISE | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VII | Cebu | 119377 | DUMANJUG CENTRAL SCHOOL | DUMANJUG | 2 | 1 | 17 | 1 | Rehabilitation of Gabaldon Building | 14736225.74 | 1 | 10885703.67 | COMPLETED | 1 | 2021-12-28 |  | 6944754-Lot 5 | 44326 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Cebu | 119566 | Pinamungajan Central School | PINAMUNGAHAN | 3 | 1 | 14 | 1 | Rehabilitation of Gabaldon Building | 16571044.5 | 1 | 12738307.98 | Completed | 1 | 2022-09-30 |  | 6944754-Lot 6 | 44322 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 10, 2021 | MP SORELA CONSTRUCTION AND SUPPLY AND MARINE SERVICES | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VII | Cebu City | 119910 | Pardo Ext. Elementary School | CEBU CITY | 2 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 3257286.22 | 1 | 2896989.43 | COMPLETED | 1 | 2021-11-20 |  | 6944754-Lot 7 | 44327 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-16 | GELA CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Danao City | 119357 | Severo Duterte MES | DANAO CITY | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 5532839.71 | 1 | 4514013.67 | COMPLETED | 1 | 2021-11-18 |  | 6944754-Lot 8 | 44331 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 14, 2021 | PB OBIAL CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Mandaue City | 120010 | Canduman Elementary School | MANDAUE CITY | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3305576.84 | 1 | 2412962.02 | COMPLETED | 1 | 2021-10-29 | August 25, 2021 | 6944754-Lot 9 | 44328 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Negros Oriental | 120587 | Lutay ES | TAYASAN | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4097116.4 | 1 | 4077000 | COMPLETED | 1 | 2021-12-14 |  | 6944754-Lot 10 | 44323 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 10, 2021 | RISM BUILDERS AND CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 1857042.7 | 1 | 1836406.24 | COMPLETED | 1 | 2021-10-29 |  | 6944754-Lot 11 | 44329 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2020 | Region VII | Talisay City | 119787 | Lawaan Elementary School | CITY OF TALISAY | 1 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1851252.72 | 1 | 1348308.86 | COMPLETED | 1 | 2021-10-29 | August 25, 2021 | 6944754-Lot 12 | 44330 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
GABALDON 2021 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3538205 | 1 | 3502098.85 | COMPLETED | 1 | 2021-12-08 |  | 7595364-Lot 2 | 44318 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 4, 2021 | C. JANSEN CONSTRUCTION AND GENERAL MERCHANDISE | [11 empty] | 1 |  |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region VII | Cebu | 119864 | VILLAHERMOSA ES | TUDELA | 5 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2804104 | 1 | 2779358.3 | COMPLETED | 1 | 2021-10-16 |  | 7595364-Lot 3 | 44319 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 11, 2021 | BARR STEEL CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2021 | Region VII | Dumaguete City | 119935 | Camanjac Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 4102769 | 1 | 4061000 | COMPLETED | 1 | 2021-12-14 | c/o Maam Daday Guillen/Region-Implemented | 7595364-Lot 1 | 44317 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 10, 2021 | RISM BUILDERS AND CONSTRUCTION | [11 empty] | 1 |  |  | previous yrs | Regional Office | CY 2022 |  |  | COMPLETED
GABALDON 2022 | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 952221.1 | 1 |  | Reverted | 0 |  |  | 6944754-Lot 2 | 44321 | [6 empty] | REVERTED SINCE FUNDED IN THE QRF BATCH 2 | [10 empty] | 0 |  |  |  | Division Office |  |  |  | REVERTED
GABALDON 2023 | Region VII | Bohol | 118672 | SEVILLA CENTRAL ELEMENTARY SCHOOL | SEVILLA | 3 | 1 | 6 | 1 | Restoration & Conservation of Gabaldon Building | 7036885.43 | 1 |  | COMPLETED | 1 | [21 empty] | 1 |  |  | 1.25 | Division Office |  |  |  | COMPLETED
GABALDON 2023 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 15492410.45 | 1 | 15431357.88 | COMPLETED | 1 | 2024-10-02 | 2024-03-08 | cy 2023 gabaldon-deped-region 7-cebu | cy 2023 gabaldon-deped-region 7-cebu-02 | 11/29/2023 | 2023-06-12 | 12/18/2023 | 2024-01-05 | 2024-01-26 | Anielthon construction and supply | [11 empty] | 1 |  |  | 8.24 | Division Office |  |  |  | COMPLETED
GABALDON 2023 | Region VII | Cebu | 119549 | Pilar Central School | PILAR | 5 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 9189509.48 | 1 | 9133229.31 | COMPLETED | 1 | 2024-08-03 | 2024-08-03 | cy 2023 gabaldon-deped-region 7-cebu | cy 2023 gabaldon-deped-region 7-cebu-01 | 11/29/2023 | 2023-06-12 | 12/18/2023 | 2024-01-05 | 2024-01-26 | Barr steel construction | [11 empty] | 1 |  |  | 1.25 | Division Office |  |  |  | COMPLETED
GABALDON 2024 | Region VII | Cebu | 119566 | Pinamungajan Central School | PINAMUNGAHAN | 3rd | 1 |  | 1 | Conservation and Restoration of Gabaldon School Building | 485257.42 | 1 |  | Not Yet Started | 0 | [9 empty] | MP Sorela Construction | RO is waiting for the release of SARO as payment of the V.O. to MP Sorela Construction declined by DO. Variation order implemented by RO. Several Letters sent by RO to CO requesting for the release of the fund. The project was already 100% completed. | [10 empty] | 0 |  |  |  | Division Office |  | 1 | 0 | not yet started
GABALDON 2024 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6th | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3731085.93 | 1 | 3710147.91 | completed | 1 | 2025-02-13 | 2025-02-12 | CY 2024 BEFF Gabaldon-DepED-R7-Cebu | CY 2024 BEFF Gabaldon-DepED-R7-Cebu | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-22 | 2024-09-13 | JAJ&L CONSTRUCTION AND ENGINEERING SERVICES | [11 empty] | 1 |  |  | 3.25 | Division Office |  |  | 7 | completed
GABALDON 2024 | Region VII | Cebu City | 119874 | City Central ES | CEBU CITY (Capital) | 1st | 1 | 20 | 1 | Conservation and Restoration of Gabaldon School Building | 8310520 | 1 | 6093285.05 | Completed | 1 | 1/27/2025 | 3/13/2025 | Gabaldon 2024 - R VII - Cebu City - 002 | DepED CCD - Contract # 2024 - 11 | 2024-06-06 | 6/14/2024 | 6/26/2024 | 7/24/2024 | 9/23/2024 | JAJ & L CONSTRUCTION AND ENGINEERING SERVICES | Completed with (45 days extension) | [10 empty] | 1 |  |  | 3.25 | Division Office |  |  | 8 | Completed
GABALDON 2024 | Region VII | Danao City | 119357 | Severo Duterte Memo. ES | DANAO CITY | 5th | 1 |  | 1 | Conservation and Restoration of Gabaldon School Building | 424730.16 | 1 |  | Not Yet Started | 0 | 11/18/2021 |  | 6944754-Lot 8 | 44331 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 14, 2021 | PB OBIAL CONSTRUCTION | Declined to Procure (with letter submitted thru Regional Director, dated May 31, 2024). RO is also waiting for a response from CO on the downloading of funds for V.O. The project was satisfactorily done by the Contractor. Follow-up letter sent to Usec. Cabral dated Dec. 8, 2024 | [10 empty] | 0 |  |  |  | Division Office |  | FOR REALIGNMENT TO OTHER DIVISION- declined by DO. Variation order implemented by RO. Letter sent to CO. | 0 | not yet started
GABALDON 2024 | Region VII | Dumaguete City | 119938 | North City ES | DUMAGUETE CITY (Capital) | 2nd | 1 | 16 | 1 | Conservation and Restoration of Gabaldon School Building | 10057346.25 | 1 | 6973017 | Ongoing | 0.93 | 2025-02-03 |  | 2024-003 | 2024-003 | 6/20/2024 | 2024-01-07 | 7/16/2024 | 2024-02-08 | 9/27/2024 | Four SG Enterprises | On - Going | [10 empty] | 0.92 |  |  |  | Division Office |  |  | 8 | Ongoing
GABALDON 2024 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6th | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6033004.04 | 1 | 5993579.01 | Completed | 1 | 9/20/2024 | 9/20/2024 | 2024GAB01 | 45323 | 2024-12-04 | 4/20/2024 | 2024-02-05 | 2024-07-05 | 6/24/2024 | Golden Hammer Construction and Supply | [11 empty] | 1 |  |  | 9.24 | Division Office |  |  | 2 | Completed
GABALDON 2024 | Region VII | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building (10 Classrooms + 2 Offices) | 36145286.53 | 1 | 35761963.38 | Ongoing | 0.65 | 12/26/2025 |  | ITB 2024-03-038 | GAB202406026 | 3/27/2024 | 2024-04-04 | 4/16/2024 | 5/15/2024 | 6/24/2024 | TrinityCAD Corporation | with time extension due to erratic weather conditions, processing of cutting permit, and scarcity of wood supply | [10 empty] | 0.45 |  |  |  | Division Office |  |  | 2 | Ongoing
GABALDON 2024 | Region VII | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 5057563.48 | 1 | 4996657.17 | Ongoing | 0.7 | Jan. 26, 2025 |  | 10743443 | 2024-025 | 2024-11-04 | 4/18/2024 | 4/30/2024 | 2024-05-05 | 2024-01-07 | Nale Construction | with Time Extention. Revised Target Completion March 17, 2025 | [10 empty] | 0.55 |  |  |  | Division Office |  |  | 3 | Ongoing
GABALDON 2024 | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building | 24222461.26 | 1 | 24202271.24 | Completed | 1 | 3/25/2025 | 1/30/2025 | 2024-001-Infra | 2024-001-Infra | 2024-11-03 | 3/21/2024 | 2024-05-04 | 2024-10-04 | 6/21/2024 | CJANSEN CONSTRUCTION AND GENERAL MERCHANDISE | [11 empty] | 0.92 |  |  | 5.25 | Division Office |  |  | 1 | Ongoing
GABALDON 2024 | Region VII | Toledo City | 120757 | South City Central School | TOLEDO CITY | 3rd | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 8822869.51 | 1 | 7032361.23 | Completed | 1 | 11/18/2024 | 10/31/2024 | GAB 2022-R VII-TOLEDO-001 | 2024-001 | 2024-05-03 | 3/14/2024 | 3/26/2024 | 2024-03-04 | 2024-08-06 | Anielthone Construction & Supply | [11 empty] | 1 |  |  | 1.25 | Division Office |  |  | 1 | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%