## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Baybay City | 121135 | Caridad Elementary School | CITY OF BAYBAY | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish) | 387051.36 |  | 1063343.04 | Completed | 1 | August 2, 2024 | August 2, 2024 | 2023-12-I001 | 2023-12-I001 | December 4, 2023 | December 11, 2023 | December 27, 2023 | May 23, 2024 | May 27, 2024 | MELGAZO CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Baybay City | 121135 | Caridad Elementary School | CITY OF BAYBAY | 5th |  |  | Construction of 1 unit Water Sanitation Facilities 4 Seater | 717391.46 |  |  | Completed | 1 | August 2, 2024 | August 2, 2024 | 2023-12-I001 | 2023-12-I001 | December 4, 2023 | December 11, 2023 | December 27, 2023 | May 23, 2024 | May 27, 2024 | MELGAZO CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Biliran | 120761 | Iyosan ES | ALMERIA | Lone | 1 |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 674177.51 |  | 670221.45 | Completed | 1 | August 16, 2024 | August 16, 2024 | 2023INFRA-WSF-10 | CONSTRUCTION OF WATER&SANITATION-10 | November 23, 2023 | December 5, 2023 | December 19, 2023 | January 2, 2024 | June 13, 2024 | RK ENGINEERING | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 2945620.86 |  | 2935619.36 | COMPLETED | 1 | October 4, 2024 | September 30, 2024 | CY2024-BEFF-SHF-BOR-01 | CY2024-BEFF-SHF-BOR-01 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | LEXBUILD CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Construction of Group Handwashing Facilities | 336908.87 |  | 336639.44 | COMPLETED | 1 | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Repair of Water and Sanitation Facilities - 4-Seater | 398282.76 |  | 398109.53 | COMPLETED | 1 | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Construction of Group Handwashing Facilities | 389754.19 |  | 389498.44 | COMPLETED | 1 | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303500 | Eastern Samar National Comprehensive High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2980621.64 | COMPLETED | 1 | October 4, 2024 | September 30, 2024 | CY2024-BEFF-SHF-BOR-03 | CY2024-BEFF-SHF-BOR-03 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | TRIPLE Z MC CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303511 | Lalawigan National High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2685885.58 | COMPLETED | 1 | October 4, 2024 | July 14, 2024 | CY2024-BEFF-SHF-BOR-04 | CY2024-BEFF-SHF-BOR-04 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | GALACAN CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303525 | Sta. Fe National High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2985944.27 | COMPLETED | 1 | October 4, 2024 | October 2, 2024 | CY2024-BEFF-SHF-BOR-05 | CY2024-BEFF-SHF-BOR-05 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | YFL BUILDERS | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | Lone | 1 |  | Construction of Group Handwashing Facilities | 236887.87 |  | 231835.72 | Completed | 1 | August 8, 2024 | July 16, 2024 | 122594 | CY2024-BEFF-SHF-L1 | October 13, 2023 | October 24, 2023 | November 8, 2023 | April 30, 2024 | May 3, 2024 | Galacan Construction Services
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | Lone |  |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 588278.06 |  | 586845.33 | Completed | 1 | August 8, 2024 | July 16, 2024 | 122594 | CY2024-BEFF-SHF-L1 | October 13, 2023 | October 24, 2023 | November 8, 2023 | April 30, 2024 | May 3, 2024 | Galacan Construction Services
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st | 1 |  | Construction of Group Handwashing Facility | 335893.89 |  | 324120.6 | COMPLETED | 1 | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st |  |  | Construction of Toilets | 637216.59 |  | 619715.76 | COMPLETED | 1 | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st |  |  | Construction of School Clinic | 2828127.22 |  | 2394306.16 | COMPLETED | 1 | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Maasin City | 122176 | Tigbawan IS | CITY OF MAASIN (Capital) | 1st | 1 |  | Construction of 1 units Water Sanitation Facilities - 4-Seater | 717391.46 |  | 717164.64 | Completed | 1 | June 25, 2024 | August 14, 2024 | WATSAN-23-11-001 | WATSAN-23-11-001 | November 29, 2023 | December 12, 2023 | January 5, 2024 | March 12, 2024 | May 17, 2024 | RJM DESIGN & CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Northern Samar | 123180 | Inanahawan ES | PAMBUJAN | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish | 337875.84 |  | 328652.75 | Completed | 1 |  |  | HEALTH2024-RVIII-Northern Samar-L1 | HEALTH2024-RVIII-Northern Samar-L1 |  |  | November 20, 2023 |  |  | Sierra Construction
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Ormoc City | 124213 | Licuma Elementary School | ORMOC CITY | 4th | 1 |  | Construction of Group Handwashing Facility | 359000 |  | 356514.34 | Completed | 1 | July 6, 2024 | July 5, 2024 | WINS 2024 - RVIII - ORMOC CITY - 001 | RO-8-24-2965 | February 16, 2024 | February 23, 2024 | March 8, 2024 | March 11, 2024 | June 3, 2024 | Melgazo Construction and Supply | inaugurated
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires Integrated School | PAGSANGHAN | 1st | 1 |  | Repair of 2-Seater CR | 281354.26 |  | 279808.19 | Completed | 1 | June 26, 2024 | June 24, 2024 | HF2024 | 2024-003 | October 23, 2023 | NOVEMB ER 8, 2023 | December 1, 2023 | May 6, 2024 | May 13, 2024 | G I AND 4K CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122002 | Divisoria Elementary School | Bontoc | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3054837.71 | Completed | 1 | October 26, 2024 | January 17, 2025 | CY2024-BEFF-Health-L1 | CY2024-BEFF-Health-L1 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122014 | Paku Elementary | Bontoc | 1st | 1 |  | Construction of Group Handwashing Facility | 358954.48 |  | 341503.28 | Completed | 1 | October 18, 2024 | November 15, 2024 | CY2024-BEFF-Health-L4 | CY2024-BEFF-Health-L4 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122014 | Paku Elementary | Bontoc | 1st |  |  | Construction of WATSAN (4-Seater CR) | 693836.25 |  | 665660.59 | Completed | 1 | October 18, 2024 | November 15, 2024 | CY2024-BEFF-Health-L4 | CY2024-BEFF-Health-L4 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122194 | San Joaquin Elementary School | Macrohon | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3037411.47 | Completed | 1 | November 2, 2024 | January 15, 2025 | CY2024-BEFF-Health-L2 | CY2024-BEFF-Health-L2 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | RJM DESIGN & CONSTRUCTION
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122321 | San Isidro Elementary School | Tomas Oppus | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3054837.71 | Completed | 1 | October 26, 2024 | January 17, 2025 | CY2024-BEFF-Health-L3 | CY2024-BEFF-Health-L3 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Tacloban City | 124234 | Camansihay Elementary School | TACLOBAN CITY (Capital) | 1st | 1 |  | Construction of Group Handwashing Facility | 348552.66 |  | 342044.52 | COMPLETED | 1 | August 31, 2024 | October 29, 2024 | CY 2024 BEFF_SCHOOL HEALTH FACILITIES-01 | 01-2024 BEFF SHF-01 | November 7, 2023 | November 14, 2023 | November 27, 2023 | November 30, 2023 | July 25, 2024 | DGJ CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Tacloban City | 124234 | Camansihay Elementary School | TACLOBAN CITY (Capital) | 1st |  |  | Construction of One (1) Unit One (1) Storey School Clinic | 2858302.25 |  | 2833811.74 | COMPLETED | 1 | October 29, 2024 | October 29, 2024 | CY 2024 BEFF_SCHOOL HEALTH FACILITIES-01 | 01-2024 BEFF SHF-01 | November 7, 2023 | November 14, 2023 | November 27, 2023 | November 30, 2023 | July 25, 2024 | DGJ CONSTRUCTION | COMPLETED
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 195826.21 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120760 | Caucab ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120772 | Tamarindo ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120766 | Pili ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | JFR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376016.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120781 | Julita ES | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120774 | Biliran Central School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 196788.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 370766.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120789 | Capayas Elementary School | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120785 | Balaquid ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120791 | J.D. Garcia ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120793 | Looc ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-21 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303328 | MANLABANG NHS | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 370766.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-21 | Infraserve
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120802 | Caibiran Central School SPED Center | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 369993.96 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-21 | Infraserve
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376016.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-21 | Infraserve
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120804 | Katipunan ES | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-21 | Infraserve
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120820 | Culaba CS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-10 | BNL Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303321 | Bool NHS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376015.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-10 | BNL Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 757396.29 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-11-10 | BNL Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 386516.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303326 | Kawayan National High School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 381266.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120834 | Kawayan CS | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 386516.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120829 | Bilwang ES | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 194688.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120839 | Masagongsong ES | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-09-01 | QYT Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120853 | Maripipi Central School | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 282888.78 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-10-11 | VHITS DG
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303329 | Maripipi NVS | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 809896.29 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-10-11 | VHITS DG
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 460016.24 | BATCH 1 |  | Completed | 1 | [8 empty] | 2022-10-11 | VHITS DG
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122619 | Julag Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122621 | Magsaysay Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122486 | Laurel Primary School | GENERAL MACARTHUR | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122513 | Parena Elementary School | GIPORLOS | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122514 | Paya Elementary School | GIPORLOS | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122475 | Batang Elementary School | HERNANI | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122498 | San Isidro Elementary School | HERNANI | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 224619.84 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122581 | Roxas Elementary School | JIPAPAD | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122343 | Beta-og Elementary School | LAWAAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122355 | Taguite Elementary School | LAWAAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122355 | Taguite Elementary School | LAWAAN | 0 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122449 | Carayacay Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122462 | Maputi Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122463 | Maslog Central Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122532 | Anuron Elementary School | MERCEDES | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122535 | Banuyo Elementary School | MERCEDES | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122672 | Anislag Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122681 | Naga Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 192503 | San Isidro Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-04
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122707 | Balud Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122711 | Butig Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122723 | Caruyagon Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122724 | Casoroy Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122725 | Layog Primary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122729 | Putong Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122730 | San Isidro Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | 2022-11-08
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122740 | Natividad Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122741 | Pangpang Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 1 | 2022-11-12 | ################
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121870 | Catoogan Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Group Handwashing Facility | 213784.24 | BATCH 1 | 191042.7 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121871 | Gapas Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 141434.75 | BATCH 1 | 99731.29 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121872 | Katipunan Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 510048.99 | BATCH 1 | 454693.74 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121875 | Pitogo Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Group Handwashing Facility | 213784.24 | BATCH 1 | 187720.2 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121882 | Victoria Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 141434.75 | BATCH 1 | 93314.12 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191513 | Baculanad Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 510048.99 | BATCH 1 | 464147.67 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121948 | Cantariwis Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 142484.75 | BATCH 1 | 121703.5 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Group Handwashing Facility | 219034.24 | BATCH 1 | 167390.35 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 515298.99 | BATCH 1 | 411575.87 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121517 | Anibong Elementary School | JULITA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 167698.02 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 168641.59 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121562 | Cabadiangan Elementary School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121574 | Luneta Elementary School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 80946.47 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121574 | Luneta Elementary School | LA PAZ | 2 |  | 1 | Constructiom of Water System (Rainwater Collector) | 131036.53 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303428 | Sta. Ana National High School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 |  | 1 | Constructiom of Water System (Rainwater Collector) | 131036.53 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121622 | Maya Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121625 | Palale Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121626 | San Antonio Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191556 | Burabod Primary School | MACARTHUR | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 492126.54 | BATCH 1 | 489063.08 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191556 | Burabod Primary School | MACARTHUR | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1674771.64 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121709 | San Roque Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121713 | Wilson Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121815 | Dumarag Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194652.31 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BELGES CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121815 | Dumarag Elementary School | PASTRANA | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1655149.9 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BELGES CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121821 | Macalpiay Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121823 | Manaybanay Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 192519.22 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121823 | Manaybanay Elementary School | PASTRANA | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1675265.5 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121825 | Pastrana Central School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 196399.35 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121912 | Guingauan Elementary School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121916 | San Pablo Elementary School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121917 | Tabontabon Central School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303382 | Justimbaste-Remandaban National High School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 196399.35 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121961 | Tunga Central School | TUNGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 178255.88 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 183049.21 | Completed | 1 |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121715 | Cabaliwan Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 224432.2 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121722 | Lamanoc Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 222332.82 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121726 | Macario Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 226470.51 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121727 | Mahalit Elementary School | MERIDA | 4 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 542359.28 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121731 | Minesite Elementary School | MERIDA | 4 | 1 | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 143759.38 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121733 | San Isidro Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 224815.85 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303408 | Merida Vocational School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 222239.82 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121409 | Katipunan Elementary School | HINDANG | 5 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 495622.41 | BATCH 1 | 492586.34 | Completed | 1 |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5 | 1 | 1 | Construction of Group Handwashing Facility | 212218.74 | BATCH 1 | 201544.5 | Completed | 1 |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121412 | Mahilum Elementary School | HINDANG | 5 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 548624.93 | BATCH 1 | 505476.41 | Completed | 1 |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 313329 | Capudlosan National High School | HINDANG | 5 | 1 | 1 | Construction of Group Handwashing Facility | 209444.01 | BATCH 1 | 203673.63 | Completed | 1 |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 304683.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122780 | Caputian Primary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243303.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122780 | Caputian Primary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 294183.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122781 | Frederick Elementary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122781 | Frederick Elementary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 304683.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122790 | Bagong Silang Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246978.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122790 | Bagong Silang Elementary School | Biri | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 309933.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122794 | Langub-Langub Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246978.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122794 | Langub-Langub Elementary School | Biri | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 310458.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122797 | SALVACION Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 566721.62 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122827 | Sagao-Sawan Elementary School | Capul | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 570921.62 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122830 | Talugaan Primary School | Capul | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 314133.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123190 | Buenavista Elementary School | Rosario | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238053.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123190 | Buenavista Elementary School | Rosario | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 301533.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123193 | Kailingan Elementary School | Rosario | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 559371.62 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123202 | Rizal Elementary School | San Antonio | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242253.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123202 | Rizal Elementary School | San Antonio | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 305733.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123205 | Vinisitahan Elementary School | San Antonio | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123221 | Bagong Sabang ES | SAN JOSE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123221 | Bagong Sabang ES | SAN JOSE | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123225 | Gengarog Elementary School | San Jose | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235428.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123225 | Gengarog Elementary School | San Jose | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 298908.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123227 | Mandugang Elementary School | San Jose | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299958.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123249 | Sila Elementary School | San Vicente | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 576171.62 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123271 | Buenasuerte Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239628.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123271 | Buenasuerte Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 303108.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123272 | Buenos Aires Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 230703.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123272 | Buenos Aires Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 294183.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123278 | Lungib Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123278 | Lungib Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123282 | San Miguel Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236530.89 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122993 | Can Maria Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 555171.62 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122995 | Imelda Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122995 | Imelda Elementary School | Lapinig | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123000 | Palanas Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123000 | Palanas Elementary School | Lapinig | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123109 | Naparasan Elementary School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238578.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123109 | Naparasan Elementary School | Mapanas | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 302058.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 193015 | Mapanas North Primary School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239103.39 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 313622 | Magtaon National High School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237967.14 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 313622 | Magtaon National High School | Mapanas | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123285 | Almagro CS | ALMAGRO | 1 | 1 | 1 | 1 UNIT GHW OPTION 1A | 240214.31 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123286 | Bacjao ES | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1A | 240214.31 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123289 | Guin-Ansan ES | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1A | 238114.31 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303588 | Almagro National High School | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1B | 252716.16 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303600 | Costa Rica National High School | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1B | 247466.16 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501934 | Kerikite Integrated School | ALMAGRO | 1 | 1 | 1 | 1 UNIT GHW OPTION 2A AND 1 RAINWATER COLLECTOR | 308790.09 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123540 | De-It ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 154457.04 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123549 | Matuguinao CES | MATUGUINAO | 1 | 1 | 1 | NEW CON OF 2 UNITS GHW OPTION 1A | 459542.44 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123550 | Nagpapacao ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 152357.04 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123557 | San Isidro ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 153407.04 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193536 | Inubod ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 152388.27 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO | 1 | 1 | 1 | NEW CON OF 2 UNITS GHW OPTION 1B | 468796.14 | BATCH 1 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1 | 1 | 1 | NEW CON OF 4 SEATER CR | 587334.17 | BATCH 1 | 583043.74 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | BMO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313713 | Villahermosa Integrated School | PAGSANGHAN | 1 | 1 | 1 | NEW CON OF 4 SEATER CR | 592584.17 | BATCH 1 | 585990.03 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | BMO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123806 | Corocawayan ES | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.61 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123807 | Ilijan ES | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 163609.63 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123808 | Lobe-Lobe Elementary School | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.63 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123810 | Pinanangnan Elementary School | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 163831.45 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123812 | Sto. Nino CS | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.63 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123813 | Takut ES | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 2 SEATER CR TYPE II | 240295.87 | BATCH 1 | 239262.6 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303638 | Villahermosa National High School | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 3 SEATER CR TYPE II | 303771.81 | BATCH 1 | 303114.51 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313703 | Cabunga-an Integrated School | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 3 SEATER CR TYPE II | 303771.81 | BATCH 1 | 303114.51 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123827 | Tagapul-an CS | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1A | 234176.55 | BATCH 1 | 233202.71 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303590 | Baquiw National High School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1B | 241428.41 | BATCH 1 | 240449.95 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303633 | Tagapul-an National High School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1B | 242216.16 | BATCH 1 | 240449.95 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW 1 UNIT OPTION 1A AND 1B | 451931.83 | BATCH 1 | 450762.66 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123583 | Bugho ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123589 | Cristina Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123590 | Dogongan Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 160631.45 | BATCH 1 | 160530.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123594 | Jidanao Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 161681.45 | BATCH 1 | 161580.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123599 | Mercedes ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 162731.45 | BATCH 1 | 162630.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123600 | Nagbac Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123602 | Salvacion Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164729.15 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123603 | San Andres ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 162731.45 | BATCH 1 | 162630.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123606 | Tagbayaon ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123607 | VICTORY ELEMENTARY SCHOOL | JIABONG | 2 | 1 | 1 | NEWCON 4 SEATER CR | 576834.17 | BATCH 1 | 576698.57 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123611 | Kaluwayan Elementary School | MARABUT | 2 | 1 | 1 | REPAIR OF 2 UNITS 2 SEATER CR | 393819.59 | BATCH 1 | 392286.09 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123612 | Legaspi Elementary School | MARABUT | 2 | 1 | 1 | REPAIR OF CR AND HANDWASHING | 330478.67 | BATCH 1 | 327798.7 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123618 | San Roque ES | MARABUT | 2 | 1 | 1 | REPAIR OF CR AND HANDWASHING | 330478.67 | BATCH 1 | 327798.6 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123620 | Tinabanan ES | MARABUT | 2 | 1 | 1 | REPAIR OF 1 UNIT 2 SEATER CR | 235045.87 | BATCH 1 | 234322.76 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123713 | Bontod Elementary School | SAN SEBASTIAN | 2 | 1 | 1 | REPAIR OF 3 SEATER CR | 300621.81 | BATCH 1 | 299565.13 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123714 | Cabaywa ES | SAN SEBASTIAN | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 159581.45 | BATCH 1 | 157633.05 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123719 | Hitaasan ES | SAN SEBASTIAN | 2 | 1 | 1 | REPAIR OF 4 SEATER CR | 351797.86 | BATCH 1 | 349786.19 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2 | 1 | 1 | NEWCON 4 SEATER CR | 582084.17 | BATCH 1 | 579365.72 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123903 | San Juan ES | TALALORA | 2 | 1 | 1 | REPAIR OF 2 SEATER CR | 240295.87 | BATCH 1 | 239907.32 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123905 | Talalora CS | TALALORA | 2 | 1 | 1 | 1 GHW OPTION 1A AND REPAIR OF 2 SEATER CR | 464696.63 | BATCH 1 | 463062.49 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303608 | Independencia National High School | TALALORA | 2 | 1 | 1 | 2 GHW OPTION 1B AND REPAIR OF 3 SEATER CR | 750405.63 | BATCH 1 | 748718.27 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501372 | Tatabunan Integrated School | TALALORA | 2 | 1 | 1 | NEW CON OF 1 GHW OPTION 1 C | 240830.73 | BATCH 1 | 238542.77 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123763 | Camayse ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 308790.09 | BATCH 1 | 307785.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123964 | Arteche Elementary School | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 309840.09 | BATCH 1 | 308310.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123966 | Boblaran ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 311940.09 | BATCH 1 | 310410.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123973 | MAPUTI ELEMENTARY SCHOOL | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 311940.09 | BATCH 1 | 309360.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123975 | Mombon Elementary School | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 308790.09 | BATCH 1 | 307260.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123983 | Tubigan ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 314040.09 | BATCH 1 | 312510.87 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 259288.78 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 266083.17 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | 2 |  | 3 | Repair of WATSAN | 247145.03 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 260609.97 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303466 | LUNGSODAAN NHS | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303466 | LUNGSODAAN NHS | HINUNDAYAN | 2 | 1 | 1 | Repair of WATSAN | 814934.28 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122079 | Kawayan Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 257126.83 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122080 | Libagon Central School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 255939.4 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122083 | Nahulid Elementary School | LIBAGON | 2 | 1 | 2 | Repair of WATSAN | 215370.53 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122084 | Otikon Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 257522.64 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 265043.05 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 265834.67 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122224 | Padre Burgos Central School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 258821.69 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 260856.16 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303476 | Pintuyan National High School | PINTUYAN | 2 | 1 | 3 | Repair of WATSAN | 241143.04 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 256335.21 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 257126.83 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 2 | 1 | 3 | Repair of WATSAN | 246248.82 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2 |  | 9 | Repair of WATSAN | 714626.33 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 2 | 1 | 3 | Repair of WATSAN | 259764.65 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 262668.19 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 271322.98 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 1 |  | 2 | Repair of WATSAN | 207045.4 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 1 | 1 | 3 | Repair of WATSAN | 229168.94 | BATCH 1 |  | Completed | 1 |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120843 | Ungale I ES | KAWAYAN | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 179667.12 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120852 | Danao ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120855 | Viga ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122499 | San Miguel Elementary School | HERNANI | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 326150.48 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121520 | Calbasag Elementary School | Julita | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121529 | Sta. Cruz Elementary School | Julita | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121529 | Sta. Cruz Elementary School | Julita | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121533 | Villahermosa Elementary School | Julita | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 200144.06 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121533 | Villahermosa Elementary School | Julita | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 522704.42 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 200784.56 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 522704.42 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121621 | MacArthur Central School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121621 | MacArthur Central School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121716 | Calunangan Elementary School | Merida | 2 | 1 | 1 | Construction of Group Handwashing Facility | 213746.38 | BATCH 2 | 212144.19 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-07-05 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121719 | Canbantug Elementary School | Merida | 2 | 1 | 1 | Construction of Group Handwashing Facility | 214481.38 | BATCH 2 | 212354.19 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121810 | Bahay Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121810 | Bahay Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532313.63 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121813 | Canino-an Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121814 | Colawen Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 202339.31 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121814 | Colawen Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 530955.83 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121816 | Halaba Primary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 202339.31 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121816 | Halaba Primary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 530955.83 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121817 | Jones Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121827 | Tingib Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203669.62 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC.
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121827 | Tingib Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532459.26 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC.
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121828 | Yapad Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203669.62 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC.
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121828 | Yapad Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532459.26 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC.
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121868 | Badiangay Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507324.88 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121878 | San Miguelay Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507322.11 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121881 | Tibak Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507324.88 | Completed | 1 |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123587 | CASAPA ELEMENTARY SCHOOL | JIABONG | 2 | 1 | 1 | I UNIT RAIN WATER COLLECTOR | 152934.94 | BATCH 2 | 151934.94 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123598 | Malobago ES | JIABONG | 2 | 1 | 1 | 2 UNITS RAIN WATER COLLECTOR | 300733.71 | BATCH 2 | 299019.01 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 281506 | FLORA MABAET MABANSAG ES | JIABONG | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 593554.77 | BATCH 2 | 590821.75 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 589018 | BATCH 2 | 588508.26 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123609 | Canyoyo Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123613 | Logero Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123616 | Pinalangga ES | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123617 | Pinamitinan Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193516 | Mabuhay ES | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193541 | Salvacion PS | MATUGINAO | 2 | 1 | 1 | I UNIT GHW 2A AND 1 UNIT RAIN WATER COLLECTOR | 316333.28 | BATCH 2 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | HAL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123657 | San Luis ES | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 600635.4 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan National High School | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 600635.4 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires IS | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 607165.07 | BATCH 2 | 605885.4 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123715 | Camanhagay ES | SAN SEBASTIAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 598745.48 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2 | 1 | 1 | I UNIT GHW 2A AND 1 UNIT RAIN WATER COLLECTOR | 309345.32 | BATCH 2 | 306127.05 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2 |  | 1 | REPAIR OF 2 SEATER CR | 237308.79 | BATCH 2 | 234231.17 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303632 | STO NINO NHS | STO NINO | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 611701.83 | BATCH 2 |  | Completed | 1 |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | HAL CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123816 | Baquiw ES | TAGAPUL-AN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 611701.83 | BATCH 2 | 610523.12 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123820 | Luna Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123821 | Manlangit Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123825 | Pulangbato Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123977 | Pangdan ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 314040.09 | BATCH 2 | 309614.25 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | TRIPLE Z CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 607165.07 | BATCH 2 | 602396.72 | Completed | 1 | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | TRIPLE Z CONSTRUCTION
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122070 | Capacuhan Elementary School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 267436.21 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 192001 | Calintaan Elementary School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 268227.83 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122073 | Lungsodaan Elementary School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122073 | Lungsodaan Elementary School | HINUNDAYAN | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122076 | Plaridel Elementary School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 268227.83 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122078 | Gakat Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 264190.56 | BATCH 2 |  | completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122078 | Gakat Elementary School | LIBAGON | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 270802.89 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 |  | 4 | New Construction of WATSAN | 560850.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303465 | Limasawa National High School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 271394.32 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303465 | Limasawa National High School | LIMASAWA | 1 |  | 4 | New Construction of WATSAN | 560850.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1 |  | 4 | New Construction of WATSAN | 540087.5 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 |  | 1 | New Construction of GHW | 263723.31 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 |  | 4 | New Construction of WATSAN | 548392.55 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 192019 | Catbawan Elementary School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 260609.97 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 263873.91 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 2 |  | 4 | New Construction of WATSAN | 544240.05 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122250 | Garsavic Elementary School | SAN JUAN (CABALIAN) | 2 | 1 | 1 | New Construction of GHW | 266644.59 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 267436.21 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2 |  | 4 | New Construction of WATSAN | 554621.3 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122312 | Canlupao Elementary School | TOMAS OPPUS | 1 | 1 | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | Completed | 1
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122319 | Maslog Elementary School | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 263478.1 | BATCH 2 |  | Completed | 1

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%