## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | Status as of July 4, 2025
SCHOOL HEALTH FACILITIES 2024 | Region X | Bukidnon | 126263 | Balintad ES | BAUNGON | 1st | 1 |  | Construction/Repair of Health Facilities | 3250000 |  | 2851203.94 | Completed | 1 | October 22, 2024 | October 22, 2024 | PB-02-11-2023-0025 | 011-2024 | November 26, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | May 20, 2024 | TRI FB Construction & General Merchandise | Completed - UPDATED 2-2025
SCHOOL HEALTH FACILITIES 2024 | Region X | Cagayan de Oro City | 127986 | Tignapoloan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 3792377.06 |  | 3104683.66 | Completed | 1 | September 10, 2024 | September 10, 2024 | Health-RX-Cagayan de Oro City-003 | 2024-007 | January 1, 2024 | January 15, 2024 | January 29, 2024 | February 12, 2024 | May 10, 2024 | HERA1 Strength Construction | Turned over to Medical Section
SCHOOL HEALTH FACILITIES 2024 | Region X | Camiguin | 303994 | Mambajao National High School | SAGAY | Lone | 1 |  | Construction/Repair of Health Facilities | 3995351.01 |  | 3744327.68 | Completed | 1 | August 2, 2024 | September 30, 2024 | Infra-01-02-2024 | Infra-01-02-2024 | November 23, 2023 | December 1, 2023 | December 14, 2023 | January 8, 2024 | May 29, 2024 | Minkonstrak Engineering & General Services | completed
SCHOOL HEALTH FACILITIES 2024 | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2nd | 1 |  | Construction/Repair of Health Facilities | 2994361 |  | 2352919.89 | Completed | 1 | October 7, 2024 | October 4, 2024 | 2024-03-0006 | 2024-04-0004 | March 4, 2024 | March 13, 2024 | March 26, 2024 | May 27, 2024 | June 6, 2024 | DICACE Construction & Supplies Trading | completed
SCHOOL HEALTH FACILITIES 2024 | Region X | Gingoog City | 315507 | Lunao National High School | GINGOOG CITY | 1st | 1 |  | Construction/Repair of Health Facilities | 2937873.19 |  | 2908494.46 | Completed | 1 | October 11, 2024 | - | HEALTH FACILITIES 2023 - REGION 10 - GINGOOG CITY - 016 | BEFF-2024-LNHS | November 3, 2023 | November 10, 2023 | November 21, 2023 | May 21, 2024 | June 7, 2024 | DCD Builders and Enterprises
SCHOOL HEALTH FACILITIES 2024 | Region X | Iligan City | 128079 | Bagong Silang ES | ILIGAN CITY | Lone | 1 |  | Construction of School Clinic | 2933245.82 |  | 2199869.55 | Completed | 1 | October 1, 2024 | September 23, 2024 | INFRA-2023-11-01 | INFRA-2023-11-01 | November 28, 2023 | December 6, 2023 | December 21, 2023 | January 26, 2024 | May 29, 2024 | Abraham BM Construction | Completed
SCHOOL HEALTH FACILITIES 2024 | Region X | Lanao del Norte | 126937 | Alegria ES | BACOLOD | 1st | 1 |  | Construction/Repair of Health Facilities | 250000 |  | 240050.3 | Completed | 1 | March 5, 2025 | March 4, 2025 | 101-24-10-245 | 101-24-10-245 |  |  |  | September 20, 2024 |  | RARMAN CONSTRUCTION AND TRADING | ALTERNATIVE MODE OF PROCUREMENT BY SMALL VALUE PROCUREMENT
SCHOOL HEALTH FACILITIES 2024 | Region X | Malaybalay City | 126534 | Bagong Silang Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 |  | Construction/Repair of Health Facilities | 3642255.6 |  | 3058004.97 | Completed | 1 | January 19, 2025 | - | 004-INFRA-2023 | 004-INFRA-2023 | November 29, 2023 | December 7, 2023 | December 19, 2023 | January 29, 2024 | September 1, 2024 | Vibranium Builder's Corporation | Completed
SCHOOL HEALTH FACILITIES 2024 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1st | 1 |  | Construction of Health Facilities | 2994136.07 |  | 2991345.25 | Completed | 1 | November 12, 2024 | November 12, 2024 | HEALTH FACILITIES 2024 - REGION X - MISAMIS OCCIDENTAL - 001 | 009-2024 | November 29, 2023 | December 7, 2023 | December 19, 2023 | January 16, 2024 | July 15, 2024 | 3R'S BUILDERS & RESOURCES | Completed
SCHOOL HEALTH FACILITIES 2024 | Region X | Misamis Oriental | 127602 | Balingasag CS | BALINGASAG | 1st | 1 |  | Construction/Repair of Health Facilities | 2784018.17 |  | 2250784.19 | Completed | 1 | November 27, 2024 | February 15, 2025 | PB-BAC1- Construction-2024-002 |  | January 17, 2024 | January 24, 2024 | February 5, 2024 | February 21, 2024 | August 29, 2024 | Trench Engineering and Construction Services | Completed
SCHOOL HEALTH FACILITIES 2024 | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 2933245.82 |  | 2924786.36 | Completed | 1 | 1 ‎February‎ ‎2025 | 1 ‎February‎ ‎2025 | INFRA-2023-DEPED OROQ-05 |  | November 23, 2024 | November 30, 2024 | December 14, 2023 | August 14, 2024 |  | RJLG Construction & supply | waiting for the issuance of NTP
SCHOOL HEALTH FACILITIES 2024 | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2nd | 1 |  | Construction of School Clinic and Construction of Toilet (4-Seater) with Handwashing | 3806245.25 |  | 3792882.61 | Completed | 1 | October 25, 2024 | January 30, 2025 | 092-CIVIL 2023-002 (EPA) | 092-CIVIL 2023-002 (EPA) | November 22, 2023 | November 29, 2023 | December 15, 2023 | January 2, 2024 | June 27, 2024 | Mitz and Nick Builders | with approved time extension
SCHOOL HEALTH FACILITIES 2024 | Region X | Tangub City | 501029 | Bintana Integrated School | TANGUB CITY | 2nd | 1 |  | Construction/Repair of Health Facilities | 2969830.3 |  | 2910263.88 | Completed | 1 | November 26, 2024 | November 20, 2025 | Health Facilities 2023-Region X-Tangub 008 |  | November 23, 2024 | November 30, 2024 | December 12, 2023 | December 20, 2023 | July 4, 2024 | RIC Construction | with approved time extension
SCHOOL HEALTH FACILITIES 2024 | Region X | Valencia City | 126863 | Valencia City Central School | CITY OF VALENCIA | 4th | 1 |  | Construction/Repair of Health Facilities | 6820243.92 |  | 5774303.39 | completed | 1 | September 25, 2024 | - | 45292 | 008 s. 2024 | June 3, 2024 | February 2, 2024 | February 16, 2024 | February 26, 2024 | May 27, 2024 | JDE CONSTRUCTION | completed
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303990 | CAMIGUIN NATIONAL HIGH SCHOOL | CATARMAN | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 797662.05 | BATCH 1 | 778341.11 | Completed | 1 | 2022-08-08 |  | WINS 2022 - R X - Camiguin - 001 | [5 empty] | 2022-06-09 | MINKONSTRAK ENGINEERING & GEN. SRVC.
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 315001 | MAAC NATIONAL HIGH SCHOOL | GUINSILIBAN | 2 | 1 | 1 | CONSTRUCTION OF ONE (1) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) INCLUDING MAIN WATER SUPPLY LINE AND DISTRIBUTION LINE IMPROVEMENT | 637839.07 | BATCH 1 | 619065.57 | Completed | 1 | 2022-08-08 |  | WINS 2022 - R X - Camiguin - 002 | [5 empty] | 2022-06-09 | MINKONSTRAK ENGINEERING & GEN. SRVC.
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303993 | SIXTO A. ABAO NHS | MAHINOG | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 810164.53 | BATCH 1 | 792296.97 | Completed | 1 | 2022-08-08 |  | WINS 2022 - R X - Camiguin - 003 | [5 empty] | 2022-06-09 | MINKONSTRAK ENGINEERING & GEN. SRVC.
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303995 | EULALIO U. PABILLORE NHS | SAGAY | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 812976.96 | BATCH 1 | 791979 | Completed | 1 | 2022-08-08 |  | WINS 2022 - R X - Camiguin - 004 | [5 empty] | 2022-06-09 | MINKONSTRAK ENGINEERING & GEN. SRVC.
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127667 | Amoros ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 1500498.2 | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 501927 | Kalabaylabay Integrated School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2D - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127680 | Taytay ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (NEW OPTION 2D - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 |  | Completed | 1 | 2022-12-24 |  | 2022-03-0048 | 2022-08-0187 | 2022-03-28 | 2022-04-06 | 2022-04-18 |  | 2022-08-24 | HID Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127042 | Jose Balazo Memorial Elementary School | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 216107.1 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-03-28 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127043 | Kauswagan CES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127046 | Libertad ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213750.16 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127048 | Tacub ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 315106 | Sultan Dimasangcay Mananggolo IS (Delabayan ES) | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222078.51 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 500453 | Kawit Oriental ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 217573.85 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501807 | Baraason Integrated School | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 240157.07 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 1 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | GREEN Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127098 | Robocon ES | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220507.16 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 216578.43 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127093 | Bosque Elementary School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221571.74 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127127 | Batangan ES | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215007.08 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127139 | Pangi Elementary School | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127144 | Somiorang PS | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 212807.05 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215810.27 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 2 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-10 | GREEN Builder and Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 211707.04 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127163 | Kalanganan Elementary School | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127163 | Kalanganan Elementary School | PANTAR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 188544.87 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 157528.33 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 214353.19 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223510.37 | BATCH 1 |  | completed | 1 | 2023-03-22 | 2023-03-21 |  | Cluster Lot No. 3 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-10-11 | 2022-12-15 | HAFFY Construction Services
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220732.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 160126.03 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 161424.88 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127215 | Lininding Elementary School | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127216 | Payawan ES | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 160126.03 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 219878.48 | BATCH 1 |  | Completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 4 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127100 | Datu Bebit Dalug ES (Baguiguicon ES) | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220207.07 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127103 | Magsaysay CS | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226182.13 | BATCH 1 |  | Completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127104 | Abucay -Cancamo ES (Olango ES) | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227282.14 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226703.48 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127177 | Camp 3 ES | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 257854.69 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127177 | Camp 3 ES | SALVADOR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 174718.76 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127180 | Daligdigan PS | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246620.02 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127187 | Salvador CES | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 259855.64 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 258755.62 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501392 | Madaya Integrated School | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 254502.34 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 6 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 255440.39 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 174718.76 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501667 | Sapad Integrated School | SAPAD | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 257807.45 | BATCH 1 |  | completed | 1 | 2023-01-17 |  |  | Cluster Lot No. 5 | 2022-04-12 | 2022-04-20 | 2022-07-19 | 2022-08-15 | 2022-10-11 | RAMZIE Builders & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225885.3 | BATCH 1 |  | completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 7 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228178.45 | BATCH 1 |  | completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 7 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127051 | Banisilon Central Elementary School | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227930.34 | BATCH 1 |  | completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 7 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127051 | Banisilon Central Elementary School | TANGCAL | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 204294.87 | BATCH 1 |  | completed | 1 | 2022-11-22 |  |  | Cluster Lot No. 7 | 2022-04-12 | 2022-04-20 | 2022-05-11 | 2022-06-09 | 2022-08-08 | MOH'D Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127364 | Malvar ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501858 | New Casul Integrated School | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127372 | Upper Dioyo ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127373 | Upper Salimpono PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127363 | Guiban ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | Substancially Completed
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127369 | Pogan PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 201020 | Virayan PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-04-13 |  |  | 019-2022 | 2022-09-04 | 2022-09-12 | 2022-09-26 | 2022-10-06 | 2022-12-14 | Kayro Construction and Supply | for final inspection after rectification works
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127285 | Sinian ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 148775.24 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127272 | Agapito Yap MES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127275 | Landing ES | BALIANGAO | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127282 | Punta Miray ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127283 | Punta Sulong ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127284 | Quezon ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127276 | Lipacon ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127280 | Magcamiguing ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127279 | Lusot ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150351.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127274 | Del Pilar ES | BALIANGAO | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150351.24 | BATCH 1 | 150349.99 | Completed | 1 | 2023-02-04 |  |  | 014-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-09-30 | RRJ Builders and Gen. Msde.
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127486 | San Juan ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127476 | Baga PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127487 | San Roque ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127480 | F.T. Paylaga MPS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127482 | Mohon ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127477 | Bangko ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127478 | Camanucan PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127484 | Punta PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 015-2022 | 2022-06-28 | 2022-07-06 | 2022-07-18 | 2022-08-15 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 188627.51 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127527 | Masubong PS | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127517 | Dasa ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501884 | Bitibut Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127530 | Proceso Saldivar ES (Sepac ES) | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127532 | Salvador ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127534 | Sinaad ES | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127529 | Napilan ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127537 | Ventura ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127513 | Caluya ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127519 | Disoy ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127522 | Libertad ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-18 |  |  | 016-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-14 | Kayro Construction & Supply
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127550 | San Isidro Bajo PS | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127540 | Caraghanan PS | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127542 | Colupan Bajo ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127543 | Dinas ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127544 | Estrella ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127549 | San Isidro Alto ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127551 | San Lorenzo Ruiz ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 201004 | San Vicente ES Annex | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127556 | Tipan ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127552 | San Vicente ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 |  | Completed | 1 | 2023-02-11 |  |  | 017-2022 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-07-14 | 2022-10-07 | 3R'S BUILDERS & RESOURCES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 203841.38 | BATCH 1 | 189212.41 | Completed | 1 | 2022-12-09 |  |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 205130.15 | BATCH 1 | 189212.41 | Completed | 1 | 2022-12-09 |  |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215171.14 | BATCH 1 | 189212.41 | Completed | 1 | 2022-12-09 |  |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 203841.38 | BATCH 1 | 189212.41 | Completed | 1 | 2022-12-09 |  |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127762 | Matangad ES | GITAGUM | 2 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 2271334.41 | BATCH 1 | 1863173.82 | Completed | 1 | 2022-12-09 |  |  | 3874972 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-28 | KL BUILDER SERVICES AND SUPPLIES
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127763 | Pangayawan ES | GITAGUM | 2 | 1 | 8 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) 8 FAUCETS | 114530.72 | BATCH 1 | 100334.78 | Completed | 1 | 2022-12-09 |  |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 204386.38 | BATCH 1 | 179281.41 | Completed | 1 | 2022-12-09 | April 20.2023 |  | 3871971 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-12 | TRI FB CONST. AND GEN. MRDSE
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 2 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 2265034.41 | BATCH 1 | 1802984.15 | Completed | 1 | 2022-12-09 |  |  | 3871973 | 2022-08-09 | 2022-08-16 | 2022-08-30 | 2022-09-19 | 2022-12-14 | DICACE CONST. AND SUPPLIES TRADING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%