## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Program-Year | Status as of July 4, 2025
SHS | REGION X | Bukidnon | 303944 | Alae Nhs | Manolo Fortich | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303944 | Alae Nhs | Manolo Fortich | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6369337.64 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Bukidnon | 303947 | Baungon National High School | Baungon | 1 | 1 | 20 | 2STY10CL | BATCH 1 CL | 25642620.1861 |  |  | Completed | 1 |  |  | P00070137MN | 16KC0010 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | LLM Concrete Products |  | NC 2016
TECHVOC | REGION X | Bukidnon | 314901 | Dalirig Nhs | Manolo Fortich | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6389337.6381 |  |  | Completed | 1 |  |  | P00070144MN | 16KC0017 |  |  | 2016-06-30 | 2016-07-20 | -618499 | KEZ Enterprises |  | NC 2016
SHS | REGION X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 |  | 18 | 3STY18CL | BATCH 1 CL | 25777559.98 |  |  | Completed | 1 |  |  | P00070143MN | 16KC0015 |  |  | 2016-06-30 | 2016-07-20 | -618499 | LLM Concrete Products |  | NC 2016
SHS | REGION X | Bukidnon | 303958 | Kalilangan Nhs | Kalilangan | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6389337.6381 |  |  | Completed | 1 |  |  | P00070142MN | 16KC0016 |  |  | 2016-06-30 | 2016-07-20 | -618499 | KEZ Enterprises |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303969 | Kinawe National High School | Libona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303966 | Lampanusan Nhs | Kalilangan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303968 | Libona Nhs | Libona | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2552472.0728 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303968 | Libona Nhs | Libona | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18272268.79 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Bukidnon | 303972 | Malitbog Nat. Agr'I. Hs | Malitbog | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2700000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8925121.051 |  |  | Completed | 1 |  |  | P00070141MN | 16KC0014 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Footprints Construction |  | NC 2016
SHS | REGION X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 20 | 4STY20CL | BATCH 1 CL | 31152890.27 |  |  | Completed | 1 |  |  | P00070139MN | 16KC0011 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Legacy Construction |  | NC 2016
SHS | REGION X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8264965.051 |  |  | Completed | 1 |  |  | P00070140MN | 16KC0013 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | RR Seismundo Construction & Supply |  | NC 2016
SHS | REGION X | Bukidnon | 303974 | Manolo Fortich Nhs | Manolo Fortich | 1 |  | 6 | 2STY6CL | BATCH 1 CL | 8264965.051 |  |  | Completed | 1 |  |  | P00070138MN | 16KC0012 |  |  | 2016-06-30 | 2016-07-20 | 2016-08-09 | Footprints Construction |  | NC 2016
SHS | REGION X | Bukidnon | 303978 | Pangantucan Nhs | Pangantucan | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15191327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Bukidnon | 303978 | Pangantucan Nhs | Pangantucan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2570000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303983 | Sankanan Nhs | Manolo Fortich | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303986 | Sumilao Nhs | Sumilao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2560000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 314924 | Sumilao Nhs - Vista Villa Annex | Sumilao | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8294965.051 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303987 | Talakag Nhs | Talakag | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12821310.09 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Bukidnon | 314919 | Tikalaan Nhs | Talakag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2600000 |  |  | Completed | 1 | [6 empty] | 2016-08-04 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303952 | Cabulohan-Paradise Nhs | Cabanglasan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2597333.12 |  |  | Completed | 1 |  |  |  | 16KA0032 |  |  | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 314908 | Cabulohan-Paradise Nhs - Townsite Annex | Cabanglasan | 2 | 1 | 16 | 2STY8CL | BATCH 1 CL | 22194685.1834 |  |  | Completed | 1 |  |  |  | 16KA0004 | [5 empty] | J.T. Gamolo Construction |  | NC 2016
TECHVOC | REGION X | Bukidnon | 314908 | Cabulohan-Paradise Nhs - Townsite Annex | Cabanglasan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2549549.27 |  |  | Completed | 1 |  |  |  | 16KA0005 |  |  | 2016-05-24 |  |  | Angel & Sam Construction |  | NC 2016
TECHVOC | REGION X | Bukidnon | 314907 | Halapitan Nhs - Little Baguio Annex | San Fernando | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2607333.12 |  |  | Completed | 1 |  |  |  | 16KA0033 |  |  | 2016-08-09 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303956 | Impasugong Nhs | Impasug-Ong | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16KA0031 |  |  | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION X | Bukidnon | 303956 | Impasugong Nhs | Impasug-Ong | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8464965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303957 | Kalabugao Nhs | Impasug-Ong | 2 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1173449.69 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303957 | Kalabugao Nhs | Impasug-Ong | 2 |  | 8 | 2STY8CL | BATCH 13 CL | 12175076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 | 1 | 30 | 3STY15CL | BATCH 7 CL | 47450000 |  |  | Completed | 1 |  |  |  | 16KA0013 |  |  | 2016-05-24 |  |  | Legacy Construction |  | NC 2016
K10 | REGION X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6551031.01 |  |  | Completed | 1 |  |  |  | 16KA0012 |  |  | 2016-05-24 |  |  | Mafil Builders Inc. |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303967 | Lantapan National High School | Lantapan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5285000 |  |  | Completed | 1 |  |  |  | 16KA0014 |  |  | 2016-05-24 |  |  | Mafil Builders |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303948 | Bocboc Nhs | Don Carlos | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2806435.56 |  |  | Completed | 1 |  |  |  | 16KB0030 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34086221.03 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 |  | 18 | 3STY9CL | BATCH 9 CL | 30218711.82 |  |  | Completed | 1 |  |  |  | 16KB0026 |  | 2016-07-22 | 2016-08-02 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 |  | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1 |  |  |  | 16KB0018 |  |  | 2016-08-02 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303951 | Bukidnon Nshi | Maramag | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2550000 |  |  | Completed | 1 |  |  |  | 16KB0024 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11284616.02 |  |  | Completed | 1 |  |  | P00070146MN | 16KB0001 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products |  | NC 2016
SHS | REGION X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 |  | 6 | 2STY6CL | BATCH 1 CL | 8645614.7 |  |  | Completed | 1 |  |  | P00070147MN | 16KB0002 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products |  | NC 2016
SHS | REGION X | Bukidnon | 303953 | Dangcagan Nhs | Dangcagan | 3 |  | 6 | 2STY6CL | BATCH 1 CL | 8495614.7 |  |  | Completed | 1 |  |  | P00070148MN | 16KB0003 |  |  | 2016-03-10 |  | 2016-06-24 | Davao Concrete Products |  | NC 2016
K10 | REGION X | Bukidnon | 303960 | Kibawe National High School | Kibawe | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20992991.13 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Bukidnon | 303961 | Kiburiao National High School | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1 |  |  |  | 16KB0027 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 303965 | Kuya Nhs | Maramag | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2739283.03 |  |  | Completed | 1 |  |  |  | 16KB0031 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
TECHVOC | REGION X | Bukidnon | 314929 | Macapari Nhs | Damulog | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2833296.57 |  |  | Completed | 1 |  |  |  | 16KB0029 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6571031.01 |  |  | Completed | 1 |  |  | P00072492MN | 16KB0019 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | Cartesian Builders |  | NC 2016
SHS | REGION X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 |  | 12 | 2STY12CL | BATCH 7 CL | 15163509.35 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303976 | Old Damulog Nhs | Damulog | 3 |  | 6 | 2STY6CL | BATCH 7 CL | 8545614.7 |  |  | Completed | 1 |  |  | P00072499MN | 16KB0021 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | RR Seismundo Construction & Supply |  | NC 2016
TECHVOC | REGION X | Bukidnon | 314912 | Quezon Nhs | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2575000 |  |  | Completed | 1 |  |  |  | 16KB0028 |  | 2016-08-19 | 2016-08-30 |  |  |  |  | NC 2016
SHS | REGION X | Bukidnon | 314912 | Quezon Nhs | Quezon | 3 | 1 | 45 | 3STY15CL | BATCH 13 CL | 70918944.385 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6571031.01 |  |  | Completed | 1 |  |  | P00074125MN | 16KB0020 |  | 2016-06-10 | 2016-06-21 | 2016-07-04 | 2016-08-03 | Mafil Builders, Inc. |  | NC 2016
SHS | REGION X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 |  | 12 | 2STY12CL | BATCH 9 CL | 15163509.35 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Bukidnon | 303979 | Salawagan Nhs | Quezon | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2575000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Bukidnon | 303980 | San Andres Nhs | Kadingilan | 3 | 1 | 12 | 3STY12CL | BATCH 13 CL | 21390000.48 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Cagayan De Oro City | 127959 | Bayabas Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6904740.0014 |  |  | Completed | 1 |  |  | P00074127MN | 16KH0046 | 2016-07-28 | 2016-08-16 | 2016-08-16 |  |  |  |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 304108 | Bulua National High School | Cagayan De Oro City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31914205.49 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Cagayan De Oro City | 304109 | Canitoan National High School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Cagayan De Oro City | 315409 | Iponan Nhs - San Simon Annex | Cagayan De Oro City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8775713.3 |  |  | Completed | 1 |  |  | P00070595MN | 16KH0038 | 2016-07-06 | 2016-07-13 | 2016-07-25 |  |  |  |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 315409 | Iponan Nhs - San Simon Annex | Cagayan De Oro City (Capital) | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6785304.52 |  |  | Completed | 1 |  |  | P00070596MN | 16KH0037 | 2016-07-06 | 2016-07-13 | 2016-07-25 |  |  |  |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 304121 | Mambuaya National High School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10766122.08 |  |  | Completed | 1 |  |  | P00070593MN | 16KH0014 | 2016-04-15 | 2016-04-15 | 2016-04-27 |  | 2016-05-23 | L & L Construction |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 304121 | Mambuaya National High School | Cagayan De Oro City (Capital) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8775713.3 |  |  | Completed | 1 |  |  | P00070594MN | 16KH0015 | 2016-04-15 | 2016-04-15 | 2016-04-27 |  | 2016-05-23 | L & L Construction |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 304122 | Mambuaya Nhs-Bayanga Annex | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 |  |  | P00074128MN | 16KH0044 | 2016-07-13 | 2016-07-20 | 2016-08-01 |  |  |  |  | NC 2016
K10 | REGION X | Cagayan De Oro City | 127999 | Pedro "Oloy" N. Roa, Sr. Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10949545.4331 |  |  | Completed | 1 |  |  | P00074129MN | 16KH0043 | 2016-07-13 | 2016-07-20 | 2016-08-01 |  |  |  |  | NC 2016
K10 | REGION X | Cagayan De Oro City | 127993 | Sacred Heart Vill Es Elementary School | Cagayan De Oro City (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Cagayan De Oro City | 304125 | Taglimao National High School | Cagayan De Oro City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6904740 |  |  | Completed | 1 |  |  | P00070597MN | 16KH0036 | 2016-07-06 | 2016-07-13 | 2016-07-25 |  |  |  |  | NC 2016
TECHVOC | REGION X | Cagayan De Oro City | 315401 | Balubal, National High School | Cagayan De Oro City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2599609.1386 |  |  | Reverted | 0 |  |  |  | 16KD00013 | 2016-02-18 | 2016-03-04 | 2016-03-22 | 2016-06-23 | 2016-06-29 | FFJJ Construction |  | NC 2016
SHS | REGION X | Cagayan De Oro City | 304111 | Cagayan De Oro National High School | Cagayan De Oro City (Capital) | 2 | 1 | 40 | 4STY20CL | BATCH 5 CL | 63508449.18 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Cagayan De Oro City | 315404 | Camaman-An,National High School | Cagayan De Oro City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Reverted | 0 | [11 empty] | NC 2016
K10 | REGION X | Cagayan De Oro City | 127955 | Corrales Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23311859.63 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Cagayan De Oro City | 127965 | Indahag Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Cagayan De Oro City | 127954 | Tablon Elementary School | Cagayan De Oro City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23311859.63 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Camiguin | 126925 | Bacnit Es | Sagay | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532755 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074144 MN | 16KE0036 | 2016-05-27 | 2016-06-07 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303989 | Bonbon Nhs | Catarman | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058584.1914 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074130 MN | 16KE0044 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074131 MN | 16KE0029 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074132 MN | 16KE0028 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15909000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074133 MN | 16KE0033 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-07 |  | JAPUZ-JANSOL ENT. |  | NC 2016
SHS | REGION X | Camiguin | 303990 | Camiguin Nhs | Catarman | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15909000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074134 MN | 16KE0034 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-07 |  | JAPUZ-JANSOL ENT. |  | NC 2016
K10 | REGION X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | Sagay | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6555338 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070590 MN | 16KE0005 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT. |  | NC 2016
K10 | REGION X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | Sagay | 0 |  | 4 | 2STY4CL | BATCH 3 CL | 6555338 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070591 MN | 16KE0006 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT. |  | NC 2016
SHS | REGION X | Camiguin | 303991 | Guinsiliban National High School | Guinsiliban | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6532755 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074137 MN | 16KE0038 | 2016-05-27 | 2016-06-07 | 2016-07-27 |  |  |  |  | NC 2016
K10 | REGION X | Camiguin | 315005 | Kuguita Integrated School | Mambajao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6607000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070592 MN | 16KE0007 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 | 2016-07-23 | JAPUZ-JANSOL ENT. |  | NC 2016
SHS | REGION X | Camiguin | 303992 | Lawigan-Bura National High School | Catarman | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2058584.1914 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074135 MN | 16KE00043 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
K10 | REGION X | Camiguin | 315001 | Maac National High School | Guinsiliban | 0 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8516440 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072471 MN | 16KE0032 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | GCMG CONST. |  | NC 2016
TECHVOC | REGION X | Camiguin | 315001 | Maac National High School | Guinsiliban | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2636400 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072643 MN | 16KE0042 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303993 | Mahinog Nhs | Mahinog | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11564000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074139 MN | 16KE0037 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303993 | Mahinog Nhs | Mahinog | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6510000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074138 MN | 16KE0045 | 2016-05-27 | 2016-06-07 | 2016-06-29 | 2016-07-04 | 2016-07-23 | GCMG CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 1 CL | 15999000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070130 MN | 16KE0008 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT. |  | NC 2016
SHS | REGION X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 |  | 12 | 3STY12CL | BATCH 1 CL | 19245000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070131 MN | 16KE0009 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT. |  | NC 2016
SHS | REGION X | Camiguin | 303994 | Mambajao Nhs | Mambajao (Capital) | 0 |  | 12 | 3STY12CL | BATCH 1 CL | 19245000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00070132 MN | 16KE0010 | 2016-06-10 | 2016-06-17 | 2016-06-29 | 2016-07-04 |  | JAPUZ-JANSOL ENT. |  | NC 2016
K10 | REGION X | Camiguin | 126892 | Sto. Nino Es | Catarman | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8516440 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074136 MN | 16KE0031 | 2016-05-27 | 2016-06-07 | 2016-07-27 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303996 | Tupsan Nhs | Mambajao (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6530000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00072472 MN | 16KE0025 | 2016-05-18 | 2016-05-27 | 2016-06-10 | 2016-07-04 | 2016-07-23 | SHEEN-SHEEN CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11485000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074140 MN | 16KE0046 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8424000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074141 MN | 16KE0030 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | SHEEN-SHEEN CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6465000 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074142 MN | 16KE0035 | 2016-05-27 | 2016-06-07 | 2016-06-28 | 2016-07-03 | 2016-07-23 | SHEEN-SHEEN CONST. |  | NC 2016
SHS | REGION X | Camiguin | 303997 | Yumbing National High School | Mambajao (Capital) | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1 |  |  | SCHOOL BLDG. P00074143 MN | 16KE0041 | 2016-07-15 | 2016-07-25 | 2016-08-09 |  |  |  |  | NC 2016
SHS | REGION X | El Salvador | 304065 | Cogon Nhs | City Of El Salvador | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22350000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | El Salvador | 304065 | Cogon Nhs | City Of El Salvador | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | El Salvador | 315318 | Hinigdaan Nhs | City Of El Salvador | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15350000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | El Salvador | 315305 | Molugan Nhs | City Of El Salvador | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26950000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304129 | Bal-Ason Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304130 | Gingoog City Cnhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2662953.92 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Gingoog City | 304130 | Gingoog City Cnhs | Gingoog City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24401857.982 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 315504 | Gingoog City Cnhs - Pundasan Nhs Annex | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304132 | Kalipay Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304133 | Malibud National High School | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2575000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304135 | Mimbunga Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 304136 | Odiongan Nhs | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Gingoog City | 315502 | Odiongan Nhs - Talisay Nhs Annex | Gingoog City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Iligan City | 304138 | Acelo C. Badelles, Sr. Mnhs (Tipanoy Nhs) | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15518925.24 |  |  | Completed | 1 |  |  | P00074147MN | 16KF0044 | [5 empty] | LANAO BUILDER AND ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 128153 | Bernardo E. Ramos Memorial School | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1990417.57 |  |  | Completed | 1 |  |  | P00074148MN | 16KF0019 | [5 empty] | AMSCON BUILDERS ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 203003 | Binasan Es | Iligan City | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3015174.43 |  |  | Completed | 1 |  |  | P00074149MN | 16KF0023 | [5 empty] | D.O.T CONSTRUCTION |  | NC 2016
SHS | REGION X | Iligan City | 304140 | Bunawan Agri. Hs | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11691139.03 |  |  | Completed | 1 |  |  | P00074150MN | 16KF0026 | [5 empty] | AHMADI BUILDERS |  | NC 2016
K10 | REGION X | Iligan City | 128119 | Caribao Es | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2167459.327 |  |  | Completed | 1 |  |  | P00074151MN | 16KF0030 | [5 empty] | D.O.T CONSTRUCTION |  | NC 2016
K10 | REGION X | Iligan City | 128098 | Dalamas Es | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6521031.01 |  |  | Completed | 1 |  |  | P00074152MN | 16KF0031 | [5 empty] | D.O.T CONSTRUCTION |  | NC 2016
K10 | REGION X | Iligan City | 304143 | Dalipuga National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11371139.03 |  |  | Completed | 1 |  |  | P00074153MN | 16KF0040 | [5 empty] | AHMADI BUILDERS |  | NC 2016
TECHVOC | REGION X | Iligan City | 304143 | Dalipuga National High School | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074598MN | 16KF0033 | [5 empty] | AHM BUILDERS |  | NC 2016
SHS | REGION X | Iligan City | 304144 | Dalipuga Nhs - Hindang Nhs Annex | Iligan City | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 4020835.14 |  |  | Completed | 1 |  |  | P00074154MN | 16KF0028 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Iligan City | 304144 | Dalipuga Nhs - Hindang Nhs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074597MN | 16KF0037 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
SHS | REGION X | Iligan City | 304154 | Esperidion F. Encabo I Mhs (Pugaan Nhs) | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15518925.24 |  |  | Completed | 1 |  |  | P00074155MN | 16KF0046 | [5 empty] | D.C.M CONSTRUCTION |  | NC 2016
SHS | REGION X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8375614.7 |  |  | Completed | 1 |  |  | P00074156MN | 16KF0016 | [5 empty] | DCM ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Iligan City | 315608 | Francisco Laya Memorial Integrated School | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074599MN | 16KF0034 | [5 empty] | SALMAN CONSTRUCTION DEVELOPMENT |  | NC 2016
K10 | REGION X | Iligan City | 304149 | Iligan City East High School - Hinaplanon Annex | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15498925.24 |  |  | Completed | 1 |  |  | P00074157MN | 16KF0045 | [5 empty] | AL-FAHDEL CONST. AND ENGINEERING |  | NC 2016
TECHVOC | REGION X | Iligan City | 304149 | Iligan City East High School - Hinaplanon Annex | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5040000 |  |  | Completed | 1 |  |  | P00074600MN | 16KF0032 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
SHS | REGION X | Iligan City | 304147 | Iligan City East Hs - Kiwalan Annex | Iligan City | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15508925.24 |  |  | Completed | 1 |  |  | P00074158MN | 16KF0043 | [5 empty] | AL-FAHDEL CONST. AND ENGINEERING |  | NC 2016
TECHVOC | REGION X | Iligan City | 304147 | Iligan City East Hs - Kiwalan Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074601MN | 16KF0042 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT |  | NC 2016
TECHVOC | REGION X | Iligan City | 304148 | Iligan City East Hs - Santiago Hs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075262MN | 16KF0059 | [5 empty] | GLOBAL TECH DESIGN BUILDERS INC. |  | NC 2016
SHS | REGION X | Iligan City | 304148 | Iligan City East Hs - Santiago Hs Annex | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6451031.01 |  |  | Reverted | 0 | [11 empty] | NC 2016
K10 | REGION X | Iligan City | 304146 | Iligan City East National Hs (Sta. Filomena) | Iligan City | 0 | 1 | 20 | 4STY20CL | BATCH 1 CL | 34337130.83 |  |  | Completed | 1 |  |  | P00070129MN | 16KF0006 | [5 empty] | D.C.M CONSTRUCTION |  | NC 2016
TECHVOC | REGION X | Iligan City | 304146 | Iligan City East National Hs (Sta. Filomena) | Iligan City | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 10085080.61 |  |  | Completed | 1 |  |  | P00070123MN | 16KF0014 | [5 empty] | AHMADI BUILDERS |  | NC 2016
K10 | REGION X | Iligan City | 304142 | Kabacsanan National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11991139.03 |  |  | Completed | 1 |  |  | P00074159MN | 16KF0035 | [5 empty] | D.C.M CONSTRUCTION |  | NC 2016
K10 | REGION X | Iligan City | 128121 | Kabangahan I Es | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6521031.01 |  |  | Completed | 1 |  |  | P00074160MN | 16KF0027 | [5 empty] | DCD BUILDERS AND ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 315609 | Kalubihon High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11791139.03 |  |  | Completed | 1 |  |  | P00074161MN | 16KF0036 | [5 empty] | AHMADI BUILDERS |  | NC 2016
K10 | REGION X | Iligan City | 128141 | Lumbatin Elementary School | Iligan City | 0 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3990835.14 |  |  | Completed | 1 |  |  | P00074162MN | 16KF0029 | [5 empty] | NDP CONSTRUCTION DEVELOPMENT |  | NC 2016
TECHVOC | REGION X | Iligan City | 304151 | Mainit High School | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2600000 |  |  | Completed | 1 |  |  | P00075263MN | 16KF0058 | [5 empty] | DCD BUILDERS AND ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 304153 | Maria Cristina Hs - Ditucalan Annex | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8395614.7 |  |  | Completed | 1 |  |  | P00074163MN | 16KF0022 | [5 empty] | DCM CONTRUCTION |  | NC 2016
K10 | REGION X | Iligan City | 304153 | Maria Cristina Hs - Ditucalan Annex | Iligan City | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 2915174.43 |  |  | Completed | 1 |  |  | P00074164MN | 16KF0025 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 304152 | Maria Cristina National High School | Iligan City | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11371397.03 |  |  | Completed | 1 |  |  | P00074165MN | 16KF0039 | [5 empty] | AHMADI BUILDERS |  | NC 2016
TECHVOC | REGION X | Iligan City | 304152 | Maria Cristina National High School | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2520000 |  |  | Completed | 1 |  |  | P00074601MN | 16KF0038 | [5 empty] | NDP CONSTRUCTION DEVELOPMET |  | NC 2016
SHS | REGION X | Iligan City | 304155 | Rogongon Agricultural High School | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8795614.7 |  |  | Completed | 1 |  |  | P00074166MN | 16KF0021 | [5 empty] | LANAO BUILDER AND ENTERPRISES |  | NC 2016
K10 | REGION X | Iligan City | 128087 | Servillano G. Reuyan Memorial Elementary School | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1995417.57 |  |  | Completed | 1 |  |  | P0074167MN | 16KF0020 | [5 empty] | AL QAOD CONSTRUCTION AND SUPPLY |  | NC 2016
SHS | REGION X | Iligan City | 304157 | Tomas Cabili Nhs | Iligan City | 0 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6421031.01 |  |  | Completed | 1 |  |  | P00075963MN | 16KF0065 | [7 empty] | NC 2016
SHS | REGION X | Iligan City | 304158 | Tomas Cabili Nhs - Annex | Iligan City | 0 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8625324.52 |  |  | Completed | 1 |  |  | P00070128MN | 16KF0003 | [5 empty] | AL-FAHDEL CONTS. AND ENGINEERING |  | NC 2016
TECHVOC | REGION X | Iligan City | 304158 | Tomas Cabili Nhs - Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 4800013.39 |  |  | Completed | 1 |  |  | P00070212MN | 16KF0007 | [5 empty] | N.D.P. CONSTRUCTION |  | NC 2016
SHS | REGION X | Iligan City | 304159 | Tubaran Nhs | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2020417.57 |  |  | Completed | 1 |  |  | P00074168MN | 16KF0017 | [5 empty] | GREEN BUILDERS AND ENTERPRISES |  | NC 2016
SHS | REGION X | Iligan City | 304159 | Tubaran Nhs | Iligan City | 0 |  | 3 | 1STY3CL | BATCH 9 CL | 2925174.43 |  |  | Completed | 1 |  |  | P00074169MN | 16KF0024 | [5 empty] | SDM VENTURES |  | NC 2016
SHS | REGION X | Iligan City | 304160 | Tubaran Nhs - Digkilaan Hs Annex | Iligan City | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2020417.57 |  |  | Completed | 1 |  |  | P0074170MN | 16KF0018 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Iligan City | 304160 | Tubaran Nhs - Digkilaan Hs Annex | Iligan City | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2550000 |  |  | Completed | 1 |  |  | P00074603MN | 16KF0042 | [5 empty] | GLOBAL TECH DESIGN BUILDERS INC. |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 304002 | Arsenio A. Quibranza Nhs (Lnnaihs) | Tubod (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 |  |  | P00075303MN | 16KF0054 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte |  | Binuni-Demologan Nhs | Bacolod | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2587125.29 |  |  | Completed | 1 |  |  | P00075299MN | 16KF0056 | [5 empty] | TESAR BUILDERS |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 304013 | Diego H. Patigayon Nhs (Mukas Nhs) | Kolambugan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668449.38 |  |  | Reverted | 0 | [11 empty] | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 304005 | Lanao Del Norte Nchs | Baroy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2860276.42 |  |  | Completed | 1 |  |  | P00075296MN | 16KF0055 | [5 empty] | MJALONTO BUILDER AND ENTERPRISES |  | NC 2016
SHS | REGION X | Lanao Del Norte | 304005 | Lanao Del Norte Nchs | Baroy | 1 | 1 | 18 | 3STY9CL | BATCH 13 CL | 32086060.84 |  |  | Completed | 1 |  |  | P00075964MN | 16KF0061 | [7 empty] | NC 2016
SHS | REGION X | Lanao Del Norte | 315102 | Lanao Del Norte Provincial Science And Technology Hs (Former Malingao Nhs (Annex New Pualas Nhs) | Tubod (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 7266271.404 |  |  | Completed | 1 |  |  | P00074924MN | 16KF0051 | [5 empty] | MJALONTO BUILDER AND ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 315102 | Lanao Del Norte Provincial Science And Technology Hs (Former Malingao Nhs (Annex New Pualas Nhs) | Tubod (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 |  |  | P00075304MN | 16KF0053 | [5 empty] | MARKBUILT ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 304008 | Linamon Nhs | Linamon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2589808.27 |  |  | Completed | 1 |  |  | P00075302MN | 16KF0052 | [5 empty] | AMSCON BUILDERS AND ENTERPRISES |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte |  | Marcela T. Mabanta Nhs | Kauswagan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2620710.36 |  |  | Completed | 1 |  |  | P00075300MN | 16KF0057 | [5 empty] | TESAR BUILDERS |  | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 304003 | Kapatagan Nhs | Kapatagan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2750000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Lanao Del Norte | 304003 | Kapatagan Nhs | Kapatagan | 2 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.898 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Lanao Del Norte | 304004 | Lala Nhs | Lala | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 43039971.1394 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Lanao Del Norte | 304004 | Lala Nhs | Lala | 2 |  | 12 | 4STY12CL | BATCH 13 CL | 22919343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Lanao Del Norte | 315101 | Sultan Ali Dimaporo Memorial Is | Sultan Naga Dimaporo (Karomatan) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2765539.15 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Malaybalay City | 303946 | Bangcud Nhs | City Malaybalay (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12020076.849 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Malaybalay City | 303950 | Bukidnon Nhs | City Malaybalay (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 23506314.795 |  |  | Completed | 1 |  |  | Construction of School Building @ BNHS (1unit of 3S 15CL) | 16KA0028 |  | 2016-07-21 | 2016-08-02 |  |  |  |  | NC 2016
K10 | REGION X | Malaybalay City |  | Casisang Cs | City Malaybalay (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21583013.45 |  |  | Completed | 1 |  |  | Construction of School Building @ Casisang CS- SHS (1unit of 3S 15CL) | 16KA0029 |  | 2016-07-21 | [5 empty] | NC 2016
K10 | REGION X | Malaybalay City |  | Casisang Cs | City Malaybalay (Capital) | 2 |  | 12 | 3STY12CL | BATCH 11 CL | 18422268.79 |  |  | Completed | 1 |  |  | Construction of School Building @ Casisang CS- SHS (1unit of 3S 12CL) | 16KA0030 |  | 2016-07-21 | [5 empty] | NC 2016
K10 | REGION X | Malaybalay City | 314904 | Malaybalay City National Science Hs | City Malaybalay (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20089495.669 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304024 | Aloran Trade Hs | Aloran | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1 |  |  | P00275970MN-CW1 | 16KI0042 | [5 empty] | DICON BUILDERS CORP. |  | NC 2016
TECHVOC | REGION X | Misamis Occidental | 304024 | Aloran Trade Hs | Aloran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16KJ10028 |  |  | 2016-07-28 | [5 empty] | NC 2016
TECHVOC | REGION X | Misamis Occidental | 304025 | Baliangao Sof | Baliangao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | 16KJ10029 |  |  | 2016-07-28 | [5 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304040 | Looc Nhs | Plaridel | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 |  |  | P00275975MN-CW1 | 16KI0043 | [5 empty] | RUDHIL CONST. & ENTERPRISES, INC |  | NC 2016
TECHVOC | REGION X | Misamis Occidental | 315207 | Sibugon Is | Lopez Jaena | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | 16KJ10030 |  |  | 2016-07-28 | [5 empty] | NC 2016
TECHVOC | REGION X | Misamis Occidental | 304028 | Bonifacio Nhs | Bonifacio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304031 | Clarin Nhs | Clarin | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24352577.982 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304031 | Clarin Nhs | Clarin | 2 |  | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Misamis Occidental | 304034 | Diwat National High School | Bonifacio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2666968.4882 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304035 | Don Victoriano Nhs | Don Victoriano Chiongbian | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 7071751.654 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Occidental | 304046 | Nueva Vista National High School | Don Victoriano Chiongbian | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9008016.57 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Oriental | 304061 | Baliwagan Nhs | Balingasag | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31964205.49 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304062 | Binuangan Nhs | Binuangan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127718 | Bolisong Es | Kinoguitan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1924740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304066 | Consuelo Nhs | Magsaysay (Linugos) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 304077 | Kinoguitan National Agricultural Hs | Kinoguitan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11027342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304080 | Looc Nhs | Salay | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 315304 | Lumbo Nhs | Lagonglong | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6845304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 315304 | Lumbo Nhs | Lagonglong | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5260000 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127730 | Mabini Es | Binuangan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6795304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127620 | Mambayaan Es | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127886 | Mantangale Es | Balingoan | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8825713.3 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127890 | Pook Es | Talisayan | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 315306 | Rosario Nhs | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304096 | Salay Nhs | Salay | 1 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11107342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-02-12 | 2016-02-17 | 2016-03-10 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304096 | Salay Nhs | Salay | 1 |  | 10 | 2STY10CL | BATCH 1 CL | 12821310.093 |  |  | Completed | 1 |  |  |  |  | 2016-02-12 | 2016-02-17 | 2016-03-10 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304097 | San Isidro Nhs | Balingasag | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6835304.52 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304098 | San Juan Nhs | Balingasag | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1964740.17 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127896 | Sta. Ines Es | Talisayan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15669491.95 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304101 | Sugbongcogon Nhs | Sugbongcogon | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11037342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304093 | Talisayan Nhs | Talisayan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11037342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304093 | Talisayan Nhs | Talisayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2660000 |  |  | Completed | 1 |  |  |  |  | 2016-05-25 | 2016-06-02 | 2016-06-30 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31302890.27 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6359337.6381 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304059 | Alubijid Nchs | Alubijid | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2429549.27 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Misamis Oriental | 127635 | Aposkahoy Ii Es | Claveria | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690829 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 315309 | Aposkahoy Nhs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127865 | Baluarte Es | Tagoloan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127922 | Biga Es | Lugait | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304064 | Cabalantian Nhs | Manticao | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127866 | Casinglot Es | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127901 | Don F. Jacinto Es | Villanueva | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-14 | 2016-04-26 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 304069 | Dr. Gerardo Sabal Mnhs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304071 | Hinaplanan Nhs | Claveria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127703 | Ignacio S. Cruz Es | Jasaan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304072 | Initao Nchs | Initao | 2 | 1 | 16 | 2STY8CL | BATCH 7 CL | 21954685.18 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 315317 | Kalacapan Nhs | Initao | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 315317 | Kalacapan Nhs | Initao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 304074 | Kalingagan National High School | Villanueva | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 19350000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304074 | Kalingagan National High School | Villanueva | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304078 | Laguindingan Nhs | Laguindingan | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31914205.49 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304078 | Laguindingan Nhs | Laguindingan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127589 | Lanao Es | Alubijid | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304079 | Libertad Nhs | Libertad | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304079 | Libertad Nhs | Libertad | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304081 | Lourdes Alubijid Nhs | Alubijid | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13550000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127930 | Lubilan Es | Naawan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127842 | Luyong Bonbon Es | Opol | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304083 | Malagana Nhs | Claveria | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127933 | Maputi Es | Naawan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127868 | Maribojoc Es | Tagoloan | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Oriental | 304086 | Matangad Nhs | Gitagum | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 304088 | Mat-I (Naawan) Nhs | Naawan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127655 | Mat-I Cs | Claveria | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10977342.59 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127709 | Natubo Es | Jasaan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304094 | Opol Nsts | Opol | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Misamis Oriental | 304094 | Opol Nsts | Opol | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Misamis Oriental | 127658 | Panampawan Es | Claveria | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2690829 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127908 | San Martin Es | Villanueva | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 22650000 |  |  | Completed | 1 |  |  |  |  | 2016-04-13 | 2016-04-14 | 2016-04-26 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental |  | Shs In Lugait, Misamis Oriental | Lugait | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 16125000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 304099 | Sta Ana Nhs | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
TECHVOC | REGION X | Misamis Oriental | 304099 | Sta Ana Nhs | Tagoloan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2600000 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127873 | Tagoloan Cs | Tagoloan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-04-13 | 2016-04-25 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127696 | Tagpaco Es | Initao | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
SHS | REGION X | Misamis Oriental | 315315 | Tambobong-Balacanas Nhs | Villanueva | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8775713.3 |  |  | Completed | 1 | [5 empty] | 2016-03-07 | 2016-03-18 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127767 | Tangkub Es | Libertad | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6785304.52 |  |  | Completed | 1 | [5 empty] | 2016-04-13 | 2016-04-25 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127597 | Taparak Es | Alubijid | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
K10 | REGION X | Misamis Oriental | 127666 | Tipolohon Es | Claveria | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1864740.17 |  |  | Completed | 1 | [5 empty] | 2016-04-15 | 2016-04-27 |  |  |  |  | NC 2016
TECHVOC | REGION X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2661358.7 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 | 1 | 32 | 4STY32CL | BATCH 13 CL | 48980442.044 |  |  | Completed | 1 |  |  | P002759789MN-CW1 | 16KI0040 | [5 empty] | GENETIAN BUILDERS |  | NC 2016
SHS | REGION X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 |  | 20 | 4STY20CL | BATCH 13 CL | 34208179.297 |  |  | Completed | 1 |  |  | P00275978MN-CW1 | 16KI0040 | [5 empty] | RUDHIL CONST. & ENTERPRISES, INC |  | NC 2016
SHS | REGION X | Oroquieta City | 304045 | Misamis Occidental Nhs | Oroquieta City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 13 CL | 16377270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Oroquieta City | 304057 | Talairon Nhs | Oroquieta City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2663131.1667 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8416000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6472000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 304164 | Calabayan National High School | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2800000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 203506 | Capucao C Es | Ozamis City | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1160000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8396000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 |  | 3 | 1STY3CL | BATCH 3 CL | 2881000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 315701 | Kinuman Norte National High School | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2650000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 304161 | Labinay National High School | Ozamis City | 2 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5662000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304163 | Labo Nhs | Ozamis City | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18223000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13048000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6462000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 304166 | Montol Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2650000 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 304167 | Ozamiz City National High School | Ozamis City | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Ozamis City | 304167 | Ozamiz City National High School | Ozamis City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 304168 | Ozamiz City School Of Arts And Trades | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304168 | Ozamiz City School Of Arts And Trades | Ozamis City | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304169 | Pulot Nhs | Ozamis City | 2 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12898000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 304169 | Pulot Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2600000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304165 | San Antonio Nhs | Ozamis City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304165 | San Antonio Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10985000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Ozamis City | 304162 | Tabid Nhs | Ozamis City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2600000 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Tangub City | 304054 | Caniangan Nhs | Tangub City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8753897.86 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Tangub City | 304041 | Lorenzo Tan Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Tangub City | 304053 | Silangit Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Tangub City | 323302 | Simasay Nhs | Tangub City | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9031363.81 |  |  | Completed | 1 | [11 empty] | NC 2016
TECHVOC | REGION X | Tangub City | 304056 | Sumirap Nhs | Tangub City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2667882.5863 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Tangub City | 304171 | Tangub City Nhs | Tangub City | 2 | 1 | 18 | 2STY6CL | BATCH 13 CL | 27100098.835 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Tangub City | 304171 | Tangub City Nhs | Tangub City | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6950951.864 |  |  | Completed | 1 | [11 empty] | NC 2016
K10 | REGION X | Valencia City | 126846 | Lumbo Es | City Of Valencia | 4 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15271327.92 |  |  | Completed | 1 | [11 empty] | NC 2016
SHS | REGION X | Valencia City | 303988 | Valencia Nhs | City Of Valencia | 4 | 1 | 20 | 2STY10CL | BATCH 13 CL | 26442620.18 |  |  | Completed | 1 | [11 empty] | NC 2016

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.