## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Site Reverted | No. of Site Not yet started | No. of Site Under Procurement | No. of Site On Going | No. of Site Completed | No. of Site Terminated | WITH TRANSFOPMER (Y/N) | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | CATEGORY 2 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Status as of July 4, 2025
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317201 | Bacongco NHS (Koronadal NCHS - Annex, Bacongco Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 220860.79 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 156384.76 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304670 | Esperanza NHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 222512.36 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 494116.35 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 131381 | Marbel 7 Elementary School | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 217391.63 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317203 | Rotonda National High School | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 178926.34 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | Koronadal City | 317202 | Saravia NHS (Koronadal NCHS - Annex, Saravia Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 217649.87 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129829 | Maracabac ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207548 | Pidatan ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207527 | Tabunan ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207549 | Talha ES | ALAMADA | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129860 | Dungguan ES | ALEOSAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129931 | Balindong PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207516 | Buay-Buay PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207540 | Kalalagan PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129939 | Kudon Elementary School | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207501 | Kulawan ES | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129950 | Sabang PS | BANISILAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129976 | Bai Matabay Piang MPS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129957 | BAROYON ELEMENTARY SCHOOL | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129983 | Kibenes ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207535 | Kilabao PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129985 | Langogan Elementary School | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129964 | Macabenban ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207521 | Malugasa PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129969 | Mesopa PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129970 | New Bentangan PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129971 | Old Bentangan ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129988 | Palanggalan ES | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129990 | Sambag PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129974 | Tawagon PS | CARMEN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207569 | Tulunan ES | KABACAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207525 | Dabpil Sampulna ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130223 | Datu Guilem Piang ES (Upper Olandang ES) | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130221 | Kadingilan ES (Pagao Memorial) | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130213 | Kudarangan ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130216 | Macasendeg ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130218 | Mudseng ES | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 200221.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316532 | Salunayan NHS-Dabpil Sampulna Olandang HS Annex | MIDSAYAP | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130283 | Balacayon Primary School | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130285 | Buricain Elementary School | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207542 | Datu Mantil PS | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130289 | KADINGILAN ELEMENTARY SCHOOL | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130294 | Matilac ES | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 304479 | Matilac HS | PIGKAWAYAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130305 | Balongis ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130335 | Binandal PS | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130319 | Bulod ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130343 | Dulangan M. Abid ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130341 | Langayen ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207563 | Malik Mem. ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207543 | Senior Malao ES | PIKIT | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 200221.98 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129882 | Datu Embangan PS | ANTIPAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129894 | Anuling PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316553 | Datu Ladayon HS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129907 | Kapayahan PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129908 | Katindu ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 271936.64 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129910 | Kiatao PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129913 | Kulaman ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 129916 | Lumbo PS | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207502 | Paco-Paco ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207544 | Sinayawan ES | ARAKAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 316538 | Bagumbayan HS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207555 | Cebomailo Primary School Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130075 | Datu Celo ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130053 | Don Panaca ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130059 | Lubas PS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207537 | Mahongkog PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207518 | Noa PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130063 | Owas ES | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207541 | Temporan PS Annex | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130067 | Timodos PS | MAGPET | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207558 | Agustin Doneza PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130084 | Balawan ES | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207566 | Lower Saguing PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130105 | San Isidro PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207560 | Sitio Mainit PS | MAKILALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130144 | Arakan PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207572 | Diosdado Almarines ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207552 | Eden Elementary School-Maligaya Primary School Annex | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130149 | Ilian ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207529 | Kulog ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207573 | Langka ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130132 | Layangan ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207562 | Migcuan ElementarySchool | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130138 | New Xavier ES | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207561 | Rajah Sumonsang Dilangalen PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207505 | West Patadon PS | MATALAM | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207567 | Banawa ES | M'LANG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130350 | Calixta Daguman ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130353 | Guinto ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130354 | Hope PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130359 | Kabinuangan PS (Lawitan) | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 207272.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130356 | Kimahuring PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130358 | Lamalama ES | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130386 | Sumakwelan PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130364 | Tahongtong PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130365 | Tarinan PS | PRESIDENT ROXAS | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130401 | Batang ES | TULUNAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130012 | Buluan ES | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207551 | Dangleg Primary School | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207545 | Dilanggalen PS | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 130016 | Malabuaya ES | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207547 | Simbuhay ES - Mulita PS Annex | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | North Cotabato | 207546 | Tamped ES - Dilutan PS Annex | KABACAN | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 130441.77 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130648 | Ebenezer ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130629 | Kataan ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 159283.09 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION |  | ongrid | COMPLETED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130650 | Lam-asam ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 201220.9 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130651 | Lamkot Elementary School | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 270638.88 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130634 | Lamtabong ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 255453.43 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130652 | Little Baguio ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 228620.67 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 208522 | Gumama PS | NORALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 171895.18 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 208514 | Lambusong ES | NORALA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 201220.9 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130768 | Defensor ES | SURALLAH | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 159283.09 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | South Cotabato | 130777 | Upper Talahik ES | SURALLAH | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 2 | 298038.66 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130956 | Balisan PS | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 369182.57 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130971 | Lasak ES | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 188877.94 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130973 | Limonzo PS | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130961 | New Ilocos ES | COLUMBIO | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123724.46 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 316801 | Laguilayan NHS - Sultan Ali Akbar Sinenggayan HS Annex | ISULAN (Capital) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 209029 | Baumol ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 130947 | San Vicente ES | BAGUMBAYAN | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 149388.48 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 209036 | Tiger ES | ESPERANZA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131035 | Minorok ES | KALAMANSIG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 123724.46 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131125 | Kimakang ES | LEBAK | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 421377.59 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131170 | Dumolol E/S | PALIMBANG | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 240299.44 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131049 | Balite ES | SEN. NINOY AQUINO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 477676.74 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2017 | Region XII | Sultan Kudarat | 131057 | Malegdeg Primary School | SEN. NINOY AQUINO | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 151330.77 |  | REVERTED | 0 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  |  | ENERGIZATION |  | ongrid | REVERTED
ELECTRIFICATION 2018 | Region XII | Cotabato City | 304634 | Notre Dame Village National High School | COTABATO CITY | 1 | 1 | UPGRADING | 2 | 4427334.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 304646 | Gen. Santos City High School - Lanton High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2029337.58 |  | COMPLETED | 1 | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 500302 | General Santos City SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2502091.86 |  | COMPLETED | 1 | Oct. 21, 2018 | [5 empty] | May 15, 2018 |  | July 16, 2018 | Automatgeneric Trading and Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | General Santos City | 304650 | Labangal National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | 2 | 2441996.22 |  | COMPLETED | 1 | Oct. 21, 2018 | Oct. 30, 2018 |  |  |  |  | May 15, 2018 |  | July 16, 2018 | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | 2 | 4189628.61 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | UPGRADING | 2 | 5136663.58 | 4599881.29 | COMPLETED | 1 | January 24 2018 |  | GEPS 5410273 | I-2018-09-008 | June 8, 2018 | July 16, 2018 | July 30, 2018 | September 12, 2018 | September 24, 2018 | EC SOLICON BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304412 | Alamada NHS | ALAMADA | 1 | 1 | UPGRADING | 1 | 2028571.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304413 | Aleosan NHS | ALEOSAN | 1 | 1 | UPGRADING | 1 | 2024350.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 | 1 | UPGRADING | 1 | 2024562.0482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 | 1 | UPGRADING | 1 | 2024878.6232 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 | 1 | UPGRADING | 1 | 2028360.9482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304494 | Pikit NHS | PIKIT | 1 | 1 | UPGRADING | 1 | 2022240.4982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304415 | Antipas NHS | ANTIPAS | 2 | 1 | UPGRADING | 1 | 2029099.6232 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 | 1 | UPGRADING | 1 | 2035958.7482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304463 | Magpet NHS | MAGPET | 2 | 1 | UPGRADING | 1 | 2022768.1232 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304466 | Makilala NHS | MAKILALA | 2 | 1 | UPGRADING | 1 | 2021185.2482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2 | 1 | UPGRADING | 1 | 2023295.7482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | UPGRADING | 1 | 2041234.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 1992027.4212 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304444 | Kabacan NHS | KABACAN | 3 | 1 | UPGRADING | 1 | 2020129.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 | 1 | UPGRADING | 1 | 2024350.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304478 | Matalam NHS, Brgy Poblacion | MATALAM | 3 | 1 | UPGRADING | 1 | 2020129.9982 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 | 1 | UPGRADING | 1 | 2021712.8732 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | UPGRADING | 1 | 2025406.2482 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | South Cotabato | 304559 | Poblacion Polomolok NHS | POLOMOLOK | 1 | 1 | UPGRADING | 2 | 9864781.29 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | South Cotabato | 304556 | Maltana NHS | TAMPAKAN | 1 | 1 | UPGRADING | 2 | 6800902.85 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | UPGRADING | 2 | 3336871.31 | 2500055.17 | COMPLETED | 1 |  |  |  |  | Dec. 07, 2018 | Dec. 14, 2018 | Dec. 27, 2018 | Dec. 28, 2018 |  | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2018 | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | UPGRADING | 2 | 4563975.22 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304628 | CANIZARES NATIONAL HIGH SCHOOL- School of Arts and Trades | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 4427334.88 | 2835068.08 | COMPLETED | 1 | Dec.6,2019 | Dec.6,2019 | GEPS 6278991 | 2019DIVINFRA-10 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304630 | Cotabato City NHS - Main | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 2851424.58 | 2835068.08 | COMPLETED | 1 | Dec.6,2019 | Dec.6,2019 | GEPS 6278980 | 2019DIVINFRA-08 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304633 | J. Marquez NHS | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 2851424.58 | 4403093.11 | COMPLETED | 1 | Dec.6,2019 | Dec.6,2019 | GEPS 6278974 | 2019DIVINFRA-07 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Cotabato City | 304635 | Pilot Provincial Science and Technology High School | COTABATO CITY | 1 | 1 | UPGRADING | Batch 3 | 4427334.88 | 4403093.11 | COMPLETED | 1 | Dec.6,2019 | Dec.6,2019 | GEPS 6278987 | 2019DIVINFRA-09 | June 27,2019 | July 2, 2019 | July 17, 2019 | Sept.5, 2019 | Sept. 6,2019 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317003 | Baluan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1776026.61 |  | COMPLETED | 1 | December 30, 2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 131275 | Balunto Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1476152.55 |  | COMPLETED | 1 | December 30,2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304649 | Datu B. Balunto National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1222548.19 |  | COMPLETED | 1 | December 30, 2019 | December 16, 2019 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304651 | Ligaya High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1210745.69 |  | COMPLETED | 1 | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 2917622.17 |  | COMPLETED | 1 | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317002 | Pao-Pao High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1560238.02 |  | COMPLETED | 1 | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | General Santos City | 317006 | Samboang-Ngilay High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING | Batch 1 | 1249822.23 |  | COMPLETED | 1 | [9 empty] | Kupler Industries Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304656 | Amas National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3218081.51 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304658 | Ginatilan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3011164.88 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3006881.53 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Kidapawan City | 304663 | Kalaisan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | UPGRADING | Batch 3 | 3007232.17 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | North Cotabato | 304418 | Mariano Untal HS | M'LANG | 3 | 1 | UPGRADING | Batch 1 | 4710444.89 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 | UPGRADING | Batch 2 | 8690370 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304569 | Sto. Niño NSAT | SANTO NIÑO | 2 | 1 | UPGRADING |  | 3094443.62 | 2399143.54 | COMPLETED | 1 | 2019-11-10 |  |  | 2019-08-019 | 2018-11-27 |  | 2018-12-17 | 2019-08-06 | 2019-09-11 | ISULAN ECT CONSTRUCTION & GEN. MDSE INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | UPGRADING |  | 7901621.66 | 6179079.1 | COMPLETED | 1 | 2019-12-10 |  |  | 2019-08-0120 | 2018-11-27 |  | 2018-12-17 | 2019-08-06 | 2019-09-11 | ISULAN ECT CONSTRUCTION & GEN. MDSE INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Sultan Kudarat | 304585 | Bambad National High School | ISULAN (Capital) | 1 | 1 | UPGRADING | Batch 1 | 3308950.98 | 3072155.74 | COMPLETED | 1 | Sept. 28, 2020 |  |  | 003-2020 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Dec. 23, 2019 | Mar. 16, 2020 | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2019 | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | UPGRADING | Batch 1 | 3960641.93 | 3703302.54 | COMPLETED | 1 | Sept. 28, 2020 |  |  | 004-2020 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Dec. 23, 2019 | Mar. 16, 2020 | 3K'S Industrial Maintenance and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Cotabato City | 316907 | CCNHS - Annex (Don E. Sero Site) | COTABATO CITY | 1 | 1 | UPGRADING |  | 2837168.08 | 2837150.43 | COMPLETED | 1 | Dec. 4, 2020 | Dec. 4, 2020 | Elec2019-RXII-Kidapawan City-002 | 2020DIVINFRA-04 | January 4, 2020 | Jannuary 10, 2020 | January 20, 2020 | January 23, 2020 | Sept. 14, 2020 | ARKIPOWERLINES CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 8424149.47 | Kupler Industries Inc. | COMPLETED | 1 |  |  | Elec2020-R12-GENSAN-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 6012095.58 | Kupler Industries Inc. | COMPLETED | 1 |  |  | Elec2020-R12-GENSAN-004 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | General Santos City | 304637 | Tinagacan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | UPGRADING |  | 5964667.21 | Kupler Industries Inc. | COMPLETED | 1 |  |  | Elec2020-R12-GENSAN-006 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Memorial National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 |  |  | 2991847.12 |  | COMPLETED | 1 |  |  | Elec2019-RXII-Kidapawan City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | ENERGIZATION | bbm 2023 ONGRID |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Koronadal City | 131406 | Koronadal Central I ES | CITY OF KORONADAL (Capital) | 2 | 1 |  |  | 4367788.32 |  | COMPLETED | 1 |  |  | Elec 2020-RXII-Koronadal City-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304435 | Dualing High School | Aleosan | 1 | 1 |  |  | 3436815.02 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020-RXII-COTABATO-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 316502 | Katalicanan High School | Aleosan | 1 | 1 |  |  | 3449323.79 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020-RXII-COTABATO-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING | BBM 2025 UPGRADE |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 1 | 1 |  |  | 3072490.97 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020-RXII-COTABATO-012 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304456 | Kisante National High School | Makilala | 2 | 1 |  |  | 3058840.97 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020-RXII-COTABATO-010 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | Makilala | 2 | 1 |  |  | 3056740.97 |  | COMPLETED | 1 |  |  | ELECTRIFICATION 2020-RXII-COTABATO-005 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304557 | Norala NHS | Norala | 2 | 1 |  |  | 6074475.44 |  | COMPLETED | 1 |  |  | Elec2020-R12-South Cotabato-001 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304568 | Sto. Niño NHS | SANTO NIÑO | 2 | 1 |  |  | 3274525.52 |  | COMPLETED | 1 |  |  | Elec2020-R12-South Cotabato-002 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 |  |  | 2881823.41 |  | COMPLETED | 1 |  |  | Elec2020-R12-South Cotabato-003 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2020 | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO | 1 | 1 | UPGRADING |  | 6202395.91 |  | COMPLETED | 1 |  |  | Elec 2020-RXII-Sultan Kudarat-001 |  | July 23, 2021 | July 30, 2021 | August 11, 2021 |  |  | CCO Engineering Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | previous years | UPGRADING |  |  | COMPLETED
ELECTRIFICATION 2024 | Region XII | General Santos City | 304654 | Lagao National High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | Upgrading of Electrical System | 1 | 5581077.08 |  | COMPLETED | 1 | 120CD |  |  | 010-2024 | 2024-09-11 | 2024-09-23 | 2024-10-07 | 2024-10-11 | 2024-01-24 | KUPLER INDUSTRIES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 |  | 4.25 | UPGRADING | BBM 2024 UPGRADE |  | COMPLETED

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%