## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM TERM COMPLETED | Unnamed: 46 | Status as of July 4, 2025
REPAIR 2020 | Region XII | City of Tacurong | 131219 | AMADO FERNANDEZ SR. CES | CITY OF TACURONG | 1 | 1 | 12 | Repair of Classrooms | 5213289 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | City of Tacurong | 131227 | SAN ANTONIO ES | CITY OF TACURONG | 1 | 1 | 6 | Repair of Classrooms | 2402967 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | General Santos City | 317004 | Elias Buscano Sr. High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 5 | Repair of Classrooms | 1574730 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | General Santos City | 131291 | Sarif Mucsin Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 13 | Repair of Classrooms | 4444243 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Kidapawan City | 131349 | Sibawan Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 7 | Repair of Classrooms | 2890817 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Koronadal City | 131404 | Engkong ES | CITY OF KORONADAL (Capital) | 2 | 1 | 8 | Repair of classrooms | 2911633 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 129847 | Polayagan ES | Alamada | 1 | 1 | 8 | Repair of Classrooms | 3033956 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130195 | Central Bulanan ES | Midsayap | 1 | 1 | 5 | Repair of Classrooms | 1762770 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 316515 | Malibatuan HS - Ganatan Annex | Arakan | 2 | 1 | 5 | Repair of Classrooms | 1951383 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 316534 | Meocan High School | Arakan | 2 | 1 | 2 | Repair of Classrooms | 762404 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130151 | Kibia CES | Matalam | 2 | 1 | 16 | Repair of Classrooms | 5640974 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130016 | Malabuaya ES | Kabacan | 3 | 1 | 6 | Repair of Classrooms | 2299825 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  | 44896 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130255 | Bagontapay CES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 954546 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | North Cotabato | 130408 | Lampagang ES | Tulunan | 3 | 1 | 4 | Repair of classrooms | 1412060 | 1 |  | COMPLETED | 1 |  |  |  |  | 2020-01-11 | 2020-01-22 | 2020-02-03 | [16 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130439 | Tokawal ES | Alabel | 0 | 1 | 10 | Repair of classrooms | 3556420 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500297 | Spring IS | ALABEL (Capital) | 0 | 1 | 3 | Repair of classrooms | 2230024 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500795 | Glan Central Integrated SPED Center | Glan | 0 | 1 | 2 | Repair of classrooms | 735805 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500281 | Wali Integrated School | Maitum | 0 | 1 | 10 | Repair of classrooms | 7611720 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 500711 | Francisco A. Cagang Sr. Integrated School | Malapatan | 0 | 1 | 6 | Repair of classrooms | 5236787 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130577 | Malalag Cogon ES | Malungon | 0 | 1 | 10 | Repair of classrooms | 4189694 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sarangani | 130621 | San Roque ES | Malungon | 0 | 1 | 10 | Repair of classrooms | 6883419 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130904 | Ricardo O. Avila Memorial Elementary School | TUPI | 1 | 1 | 8 | Repair of Classrooms | 2512269 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130908 | Simbo ES | TUPI | 1 | 1 | 5 | Repair of Classrooms | 1997101 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130635 | Matlong Elementary School | BANGA | 2 | 1 | 9 | Repair of Classrooms | 3078617 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | South Cotabato | 130642 | Rizal ES | Banga | 2 | 1 | 21 | Repair of Classrooms | 6346541 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131089 | Kapingkong Central Elementary School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 12 | Repair of Classrooms | 4817960 | 1 |  | COMPLETED | 1 | Mar. 15, 2021 |  |  | 2020-008 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Palmares Gen. Merchandise | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131001 | Magsaysay Elementary School | Esperanza | 2 | 1 | 5 | Repair of Classrooms | 1511627 | 1 |  | COMPLETED | 1 | Apr. 14, 2021 | Feb. 15, 2021 |  | 2020-007 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Cofejok Construction & Supply Corporation | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131115 | Celeste Central Elementary School | Lebak | 2 | 1 | 3 | Repair of Classrooms | 1357010 | 1 |  | COMPLETED | 1 | Mar. 15, 2021 | Feb. 15, 2021 |  | 2020010 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | KLD Engineering Construction | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131127 | F. Parohinog Sr. Memorial Elementary School | Lebak | 2 | 1 | 8 | Repair of Classrooms | 2698003 | 1 |  | COMPLETED | 1 | Apr. 14, 2021 | Jun. 10, 2021 |  | 2020-011 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Bamec Developer | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2020 | Region XII | Sultan Kudarat | 131113 | Nuling Elementary School | Lebak | 2 | 1 | 6 | Repair of Classrooms | 2222211 | 1 |  | COMPLETED | 1 | Mar. 15, 2021 | Jun. 10, 2021 |  | 2020-009 | Nov. 27, 2019 | Dec. 04, 2019 | Dec. 19, 2019 | Jan. 08, 2020 | Nov. 09, 2020 | Bamec Developer | [13 empty] | 1 |  |  | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | General Santos City | 131301 | Daan Banwang Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | Repair of classrooms | 2953865.29 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | General Santos City | 210002 | Ignacio D. Solis Sr. Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 7 | Repair of classrooms | 3737537.94 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | Kidapawan City | 131345 | Luvimin Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 5 | Repair of classrooms | 3825479.86 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Koronadal City | 131386 | Supon ES | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | Repair of classrooms | 3000000 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130040 | Cabpangi ES | LIBUNGAN | 1 | 1 | 4 | Repair of classrooms | 1890510.44 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130034 | Sinapangan ES | LIBUNGAN | 1 | 1 | 2 | Repair of classrooms | 1257607.73 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130042 | Wendelin Eduarte ES (Gumaga ES) | LIBUNGAN | 1 | 1 | 2 | Repair of classrooms | 912542.29 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130177 | Patindeguen ES | MIDSAYAP | 1 | 1 | 2 | Repair of classrooms | 912405.23 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130047 | AMABIL ELEMENTARY SCHOOL | MAGPET | 2 | 1 | 2 | Repair of classrooms | 1597235.09 | 1 |  | COMPLETED | 1 | 2022-12-31 | [22 empty] | 1 |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2 | 1 | 4 | Repair of classrooms | 1735541.5 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130124 | Sinkatulan ES | MAKILALA | 2 | 1 | 4 | Repair of classrooms | 1996026.01 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130370 | Dona Concordia B. Jayme CES | PRESIDENT ROXAS | 2 | 1 | 7 | Repair of classrooms | 2714581.63 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130371 | Egmedio Fernando ES (Jose Tuburan Sr.) | PRESIDENT ROXAS | 2 | 1 | 4 | Repair of classrooms | 2308535.18 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 129970 | New Bentangan PS | CARMEN | 3 | 1 | 2 | Repair of classrooms | 1333787.66 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 44896 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130000 | Katidtuan Central Elementary School | KABACAN | 3 | 1 | 2 | Repair of classrooms | 912542.29 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130126 | Bangbang ES | MATALAM | 3 | 1 | 3 | Repair of classrooms | 1905715.99 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130241 | Langkong ES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 1948106.67 | 1 |  | COMPLETED | 1 | 2022-11-30 | [22 empty] | 1 |  | 44986 | 8.23 |  |  |  | CY 2023 | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130225 | Luz Village ES | M'LANG | 3 | 1 | 2 | Repair of classrooms | 1240283.71 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130233 | Pulanglupa ES | M'LANG | 3 | 1 | 3 | Repair of classrooms | 1757826.17 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130404 | Damawato ES | TULUNAN | 3 | 1 | 2 | Repair of classrooms | 1258441.62 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | North Cotabato | 130414 | New Culasi ES | TULUNAN | 3 | 1 | 2 | Repair of classrooms | 1221407.11 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 500283 | Hadji Musa IS | GLAN | 0 | 1 | 8 | Repair of classrooms | 7449381.88 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 304523 | Colon NHS | MAASIM | 0 | 1 | 36 | Repair of classrooms | 5797443.37 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 130586 | Balacayo ES | MALUNGON | 0 | 1 | 7 | Repair of classrooms | 6090886.77 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON | 0 | 1 | 10 | Repair of classrooms | 6806323.35 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 316603 | Malungon Gamay National High School | MALUNGON | 0 | 1 | 14 | Repair of classrooms | 1591195.09 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sarangani | 500825 | Panamin IS | MALUNGON | 0 | 1 | 6 | Repair of classrooms | 5615613.46 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | South Cotabato | 130700 | Esperanza ES | NORALA | 2 | 1 | 10 | Repair of classrooms | 4346436.44 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | South Cotabato | 130782 | Shri- Visaya ES | SURALLAH | 2 | 1 | 7 | Repair of classrooms | 2964223.54 | 1 |  | COMPLETED | 1 | 2022-09-30 | [22 empty] | 1 |  | 0 | previous yrs |  |  |  | CY 2022 | COMPLETED
REPAIR 2021 | Region XII | Sultan Kudarat | 131206 | Bannawag Elementary School | Pres. Quirino | 1 | 1 | 12 | Repair of classrooms | 6930227.21 | 1 | 4771656.5 | COMPLETED | 1 | Mar. 17, 2022 | Mar. 14, 2022 | 2021-05-008-Lot 1 | 2021-05-008 | Jul. 23, 2021 | Jul. 30, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Oct. 05, 2021 | John Ray Developer & Supplies | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Sultan Kudarat | 130913 | Dorin Elementary School | Bagumbayan | 2 | 1 | 5 | Repair of classrooms | 3103050.23 | 1 | 2271179.12 | COMPLETED | 1 | Feb. 22, 2022 | Jan. 20, 2022 | 2021-05-008-Lot 2 | 2021-05-009 | Jul. 23, 2021 | Jul. 30, 2021 | Aug. 11, 2021 | Sept. 03, 2021 | Oct. 05, 2021 | Cofejok Construction & Supply Corporation | [13 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2021 | Region XII | Tacurong City | 131221 | Abang Suizo ES | CITY OF TACURONG | 1 | 1 | 9 | Repair of Classrooms | 4372530.33 | 1 |  | COMPLETED | 1 | [23 empty] | 1 |  | 0 | previous yrs |  |  |  |  | COMPLETED
REPAIR 2023 | Region XII | North Cotabato | 304480 | Mlang National High School | M'LANG | 3rd | 1 | 10 | Repair of Classrooms | 5000000.25 | DPWH (Batch 2) |  | COMPLETED | 1 | [23 empty] | 1 |  |  | 7.24 |  |  |  |  | COMPLETED
REPAIR 2024 | Region XII | General Santos City | 131310 | GSC Elementary School for the Arts | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 10 | Repair of Classrooms | 8235902.4 | 1 |  | COMPLETED | 1 |  | 002-2025- Lot 2 | 45665 | 45665 | 2025-01-21 | 2025-02-04 | 2025-02-17 | Manuela Construction | [15 empty] | 0.3 |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | General Santos City | 304653 | Lagao National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 26 | Repair of Classrooms | 9990784.53 | 1 |  | COMPLETED | 1 |  | 002-2025- Lot 1 | 45665 | 45665 | 2025-01-21 | 2025-02-04 | 2025-02-17 | Manuela Construction | [15 empty] | 0.3 |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Kidapawan City | 131365 | Gayola ES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 7 | Repair of Classrooms | 7070707.07 | 1 | Php 4,827,722.52 | COMPLETED | 1 | 2024-10- 292 | PB-2024-13 | 45596 | 45604 | 2024-11-25 | 2024-12-18 | 12/27/2024 Note: NTP receipt date by contractor is Jan.3, 2025 | Cyrus James Builders and Supply |  |  | Under Suspension | [12 empty] | 0.5 |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Kidapawan City | 304657 | Gayola National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 6060606.06 | 1 | Php 4,129,315.34 | COMPLETED | 1 | 2024-10- 293 | PB-2024-12 | 45596 | 45604 | 2024-11-25 | 2024-12-18 | 12/27/2024 Note: NTP receipt date by contractor is Jan.3, 2025 | Cyrus James Builders and Supply | [15 empty] | 0.75 |  |  | 5.25 |  |  |  |  | ongoing
REPAIR 2024 | Region XII | Koronadal City | 306088 | GOVERNOR SERGIO B. MORALES NATIONAL HIGH SCHOOL | CITY OF KORONADAL (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 2678370.67 | 1 | 1988744.22 | COMPLETED | 1 | 2024-08-008 | 2024-10-013 | 45527 | 45537 | 2024-09-18 | 2024-10-01 | 2024-10-10 | VYS Construction | [15 empty] | 1 |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region XII | South Cotabato | 130865 | Tampakan Central Elementary School | TAMPAKAN | 1st | 1 | 11 | Repair of Classrooms | 8255807.78 | 1 |  | under procurement | 0 | [8 empty] | Awaiting SARO Release | [14 empty] | 0 | [7 empty] | under procurement
REPAIR 2024 | Region XII | South Cotabato | 130873 | Luayan Elementary School | TANTANGAN | 2nd | 1 | 8 | Repair of Classrooms | 6004223.84 | 1 |  | under procurement | [9 empty] | Awaiting SARO Release | [14 empty] | 0 | [7 empty] | under procurement
REPAIR 2024 | Region XII | Sultan Kudarat | 130972 | Libertad Elementary School | COLUMBIO | 1st | 1 | 8 | Repair of Classrooms | 6038289.23 | 1 | 4233166.12 | Ongoing | 0.81 | 24-11-027-lot 1 | 24-11-027-01 | Nov. 12, 2024 | Nov. 20, 2024 | Dec. 02, 2024 | Dec. 10, 2024 | Jan. 06, 2024 | Johnray Developer and Supplies | [15 empty] | 0.81 | [7 empty] | ongoing
REPAIR 2024 | Region XII | Sultan Kudarat | 131190 | Milbuk Central Elementary School | PALIMBANG | 2nd | 1 | 10 | Repair of Classrooms | 8898594.63 | 1 | 6333338.12 | Ongoing | 0.68 | 24-11-027-lot 2 | 24-11-027-02 | Nov. 12, 2024 | Nov. 20, 2024 | Dec. 02, 2024 | Dec. 10, 2024 | Jan. 06, 2024 | Johnray Developer and Supplies | [15 empty] | 0.68 | [7 empty] | ongoing
REPAIR 2024 | Region XII | Tacurong City | 131231 | J. Hector Lacson Elementary School | CITY OF TACURONG | 1st | 1 | 2 | Repair of Classrooms | 1717500.94 | 1 | 1203652.48 | COMPLETED | 1 | IP - 001 - 2024 |  | 45477 | 45485 | 2024-07-24 | 2024-07-26 | 2024-10-30 | Gabriellas Enterprises |  | Gabriellas Enterprises | [13 empty] | 1 |  |  | 2.25 |  |  |  |  | Completed
REPAIR 2024 | Region XII | Tacurong City | 131228 | San Rafael ES | CITY OF TACURONG | 1st | 1 | 11 | Repair of Classrooms | 6931017.79 | 1 | 4813184.74 | COMPLETED | 1 | IP - 001 - 2024 |  | 45477 | 45485 | 2024-07-24 | 2024-07-26 | 2024-10-30 | Gabriellas Enterprises |  | Gabriellas Enterprises | [13 empty] | 1 |  |  | 2.25 |  |  |  |  | Completed

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%